## Sheet1
[44 empty] | PO 035321 | PO 035187 |  |  | PO 036945
[13 empty] | PO 036139 | PO 036870 | [29 empty] | PO 035321 | PO 035189 | PO 036944
[10 empty] | PO 034163 |  | PO 034206 | PO 036227 & 036226 | PO 035978 | PO 034231 | PO 034231 | PO 034231 | 2019-2020 PO's | 2019-2020 PO's | Pending Encumbrance | PO 035356 | PO 036906 | PO 034577 | PO 034575 | PO 034576 | PO 037140 | PO 037139 | Pending E | Pending E | PO 033066 | PO 037036 |  | PO 034230 | PO 034336 | PO 033086 | PO 033085 | PO 034335 | PO 034337 | PO 033087 | PO 037138 | PO 037137 | PO 037109 | JE - Land Purchase | PO035320 | PO 035190 | and PA |  | PO 036942 | PO 035767 &66 | PO 037133 | PO 34764 | PO 34763
Stafford Municipal School District | [12 empty] | PO 037112 | [14 empty] | Encumbrance | Encumbrance |  | PO 033080 | CK 101716 | [11 empty] | PO 037044 | PO 035188 | PO 036944 |  | PO 036943 | PO 036140
Bond Payment Log Project to Date | [8 empty] | PO AMOUNT --> | 38269 | 1500 | 3900 | 9198 | 22174.57 | 709675.22 | 162876.28 | 290850.5 | 300955 | 346640 | 3982900 | 27287533.8 | 6241427 | 1396000 | 125250 | 296500 | 99360 | 162720 |  |  | 8500 | 72840 | 11950 | 19500 | 18565 | 45100 | 36300 | 103350 | 32900 | 38300 | 167833 | 65270 | 20000 | 1258221 | 396282.3 | 435127.37 | 7326.56 |  | 14761.31 | 68200.81 | 15000 | 114600 | 41340
As of August 31, 2019 | [9 empty] | PA Approved | PA Approved | [34 empty] | Centerpoint | Centerpoint | Centerpoint
[15 empty] | LAN | LAN | LAN |  |  | DryMalla | DryMalla | DryMalla | Architects | Architects | Architects | Architects | Architects | Architects | Architects | Paradigm | Weisser | Weisser | Weisser | Kaluza | Kaluza | Kaluza | Kaluza | Kaluza | Kaluza | HVJ | HVJ | Traffic | City of Stafford |  |  | Electrical | Electrical | Electrical | Bedrock | Educators | TechKNowledge | TechKNowledge
[10 empty] | Legal | Tx Education | Housotn | Electrical | Water | Proj Mgr | Proj Mgr | Proj Mgr | Proj Mgr | Proj Mgrs | Construction | Construction | Construction | Auto arch | Auto Arch | Auto Arch | Auto Arch | Auto Arch | Molina Walker | Smith & Co | Consultants | Engineering | Engineering | Engineering | [6 empty] | Associates | Associates | Engineers | Land | Buses & | Library | Work | Work | Work | Rocks | Depot, Inc | Consulting | Consulting
[10 empty] | Fees | Agency | Bs Journal | Work | Connection | Middle | Adnmin | Site Dev | Var Renovations | Var Renovations #2 | Site Improvements | Middle Sch. | Admin Bdlg | Middle | Site Work | Admin Bdlg | High School | Magnet Schl | Elem and Pre K RENO | AG Barn and Com Ctr RENO | Middle | Middle | Site Work | Admin | Middle | Middle | Site Work | Site Work | Admin Bdlg | Admin Bdlg | Middle | Admin | Site Work | Purchase | Vehicles | Books | Middle | Site Work | Admin | Middle
REQ # | DATE PAID | DRAWS | VENDOR | GROSS AMT | RETAINAGE | NET AMT | PURPOSE | PROJECT
CK 098944 | 2018-08-02 |  | Autoarch Architects, LLC | 3131.25 | 0 | 3131.25 | A&E Services Site Work | Middle School | [15 empty] | 3131.25
CK 098944 | 2018-08-02 |  | Autoarch Architects, LLC | 279200 | 0 | 279200 | A&E Services | Middle School | [14 empty] | 279200
CK 098944 | 2018-08-02 |  | Autoarch Architects, LLC | 263.28 | 0 | 263.28 | Misc Site Work Svcs | Middle School | [15 empty] | 263.28
CK 098944 | 2018-08-02 |  | Autoarch Architects, LLC | 14825 | 0 | 14825 | A&E Services | Admin Bldg | [16 empty] | 14825
CK 099020 | 2018-08-08 |  | Paradigm Consultants, Inc | 8500 | 0 | 8500 | Consultant Fees | Middle School | [21 empty] | 8500
CK 099143 | 2018-08-22 |  | Karczewski, Bradford, LLP | 3037.5 | 0 | 3037.5 | Legal Fees |  |  | 3037.5
CK 099215 | 2018-08-24 |  | Weisser Engineering Co. | 51890 | 0 | 51890 | Engineering Fees | Middle School | [22 empty] | 51890
CK 099166 | 2018-08-24 |  | Autoarch Architects, LLC | 279200 | 0 | 279200 | A&E Services | Middle School | [14 empty] | 279200
CK 099261 | 2018-08-30 |  | Kakuza Inc | 2850 | 0 | 2850 |  | Site Work | [27 empty] | 2850
CK 99261 | 2018-08-30 |  | Kaluza, Inc | 26255 | 0 | 26255 |  | Middle School | [25 empty] | 26255
CK 99261 | 2018-08-30 |  | Kaluza, Inc | 4050 | 0 | 4050 |  | Admin Bldg | [30 empty] | 4050
GJ 013090 | 2018-08-30 |  | Kaluza Inc Ck 99966 | 14250 | 0 | 14250 |  | Middle School | [25 empty] | 14250
CK 013090 | 2018-08-31 |  | Karczewski, Bradford, LLP | 3668.75 | 0 | 3668.75 | Legal Fees |  |  | 3668.75
CK 099325 | 2018-08-31 |  | Lockwood, Andrews & Newman | 134238.7 | 0 | 134238.7 | Site Work | Middle School | [6 empty] | 134238.7
CK 099325 | 2018-08-31 |  | Lockwood, Andrews & Newman | 912.35 | 0 | 912.35 | Misc Site Work | [7 empty] | 912.35
GJ 013090 | 2018-08-31 |  | CK#099966 Kaluza, Inc | 6820 | 0 | 6820 |  | Middle School | [26 empty] | 6820
GJ 013090 | 2018-08-31 |  | CK#099966 Kaluza, Inc | 1350 | 0 | 1350 |  | Admin Bldg | [29 empty] | 1350
GJ 031090 | 2018-08-31 |  | Autoarch Architects CK#099943 | 139600 | 0 | 139600 | A&E Services | Middle School | [14 empty] | 139600
GJ 031090 | 2018-08-31 |  | Autoarch Architects CK#099943 | 22237.5 | 0 | 22237.5 | A&E Services | Admin Bldg | [16 empty] | 22237.5
CJ 013122 | 2018-08-31 |  | Audit Adj Entry #1003 | 80621.25 | 0 | 80621.25 |  | Middle School | [6 empty] | 70946.7 | 9674.55
GJ 013122 | 2018-08-31 |  | Audit Adjusting Entry #1003 | 134238.7 | 0 | 134238.7 | Project Manager | Middle School | [6 empty] | 118130.056 | 16108.644
GJ 013122 | 2018-08-31 |  | AJE #1003 | 731075 | 0 | 731075 | A&E Services | Middle School | [14 empty] | 731075
GJ 013122 | 2018-08-31 |  | AJE#1003 | 42462.5 | 0 | 42462.5 | A&E Services | Admin Bldg | [16 empty] | 42462.5
CJ 013122 | 2018-08-31 |  | Audit Adj Entry #1003 | -214859.95 | 0 | -214859.95 |  | Middle School | [14 empty] | -214859.95
GJ 013122 | 2018-08-31 |  | AJE #1003 | -731075 | 0 | -731075 | A&E Services | Middle School | [14 empty] | -731075
GJ 013122 | 2018-08-31 |  | AJE#1003 | -42462.5 | 0 | -42462.5 | A&E Services | Admin Bldg | [16 empty] | -42462.5
GJ013115 | 2018-09-06 |  | Land Purchase | 8220.6 | 0 | 8220.6 | Land Purchase | [35 empty] | 8220.6
GJ013115 | 2018-09-06 |  | Land Purchase | 1250000 | 0 | 1250000 | Land Purchase | [35 empty] | 1250000
CK 100224 | 2018-11-09 |  | Thompson and Horton LLP | 586.25 | 0 | 586.25 | Legal Fees |  |  | 586.25
CK 100181 | 2018-11-09 |  | Karczewski and Bradshaw LLP | 3532.5 | 0 | 3532.5 | Legal Fees |  |  | 3532.5
CK 100290 | 2018-11-16 |  | Lockwood, Andrews and Newman | 67460.9 | 0 | 67460.9 | Project Management | [7 empty] | 59365.592 | 8095.308
CK 100370 | 2018-11-30 |  | Karczewski and Bradshaw LLP | 5692.44 | 0 | 5692.44 | Legal Fees |  |  | 5692.44
CK 100421 | 2018-11-30 |  | Weissner Engingeering Comp. | 19500 | 0 | 19500 | Site Work | Admin Bldg | [24 empty] | 19500
CK 100374 | 2018-11-30 |  | Lockwood, Andrews and Newman | 67119.35 | 0 | 67119.35 | Project Management | [7 empty] | 59065.028 | 8054.322
CK 100434 | 2018-12-07 |  | Autoarch Architects LLC | 10096.67 | 0 | 10096.67 | Site Work | [16 empty] | 10096.67
CK 100434 | 2018-12-07 |  | Autoarch Architects LLC | 11119 | 0 | 11119 | A&E Services | Admin Bldg | [16 empty] | 11119
CK 100434 | 2018-12-07 |  | Autoarch Architects LLC | 139600 | 0 | 139600 | A&E Services | Middle School | [14 empty] | 139600
CK 100744 | 2018-12-19 |  | Karczewski and Bradshaw LLP | 1381.25 | 0 | 1381.25 | Legal Fees |  |  | 1381.25
CK100741 | 2018-12-19 |  | Houston Business Journal | 520 |  | 520 | Advertising |  |  |  |  | 520
CK 100805 | 2019-01-04 |  | Lockwood, Andrews and Newman | 136670.62 | 0 | 136670.62 | Project Management | [7 empty] | 120270.1456 | 16400.4744
CK 100793 | 2019-01-04 |  | Autoarch Architects, LLC | 70419 |  | 70419 | Project Management | Admin Bldg | [16 empty] | 70419
CK 100816 | 2019-01-04 |  | Techknowledge Consulting | 3701.25 | 0 | 3701.25 | Project Management | Middle School | [42 empty] | 3701.25
CK 100886 | 2019-01-11 |  | Kaluza Inc | 14190 | 0 | 14190 | Site Work | [29 empty] | 14190
CK 100886 | 2019-01-11 |  | Kaluza Inc | 5238 | 0 | 5238 | [31 empty] | 5238
CK 100886 | 2019-01-11 |  | Kaluza Inc | 6820 | 0 | 6820 | Site Work | Middle School | [25 empty] | 6820
CK 101207 | 2019-02-01 |  | Karczewski and Bradshaw LLP | 5638.95 | 0 | 5638.95 | Legal Fees |  |  | 5638.95
CK 101289 | 2019-02-08 |  | Classic Chevrolet | 45127.13 | 0 | 45127.13 | Purchase Surburban | Transportation | [35 empty] | 45127.13
CK 101538 | 2019-02-21 |  | Kaluza Inc | 17218.5 | 0 | 17218.5 | Site Work | Admin Bldg | [29 empty] | 17218.5
CK 101538 | 2019-02-21 |  | Kaluza Inc | 2755 | 0 | 2755 | Site Work | Middle School | [25 empty] | 2755
CK 101533 | 2019-02-21 |  | Houston Business Journal | 390 | 0 | 390 | Advertising |  |  |  |  | 390
CK 101716 | 2019-03-01 |  | Weissner Engineering Comp | 11950 | 0 | 11950 | Site Work | [24 empty] | 11950
CK 101651 | 2019-03-01 |  | Lockwood, Andrews and Newman | 67562.38 | 0 | 67562.38 | Project Management | [7 empty] | 59454.8944 | 8107.4856
CK 101792 | 2019-03-08 |  | Karczewski and Bradshaw LLP | 2193.75 | 0 | 2193.75 | Legal Fees |  |  | 2193.75
CK 101779 | 2019-03-08 |  | Houston Business Journal | 960 | 0 | 960 | Advertising |  |  |  |  | 960
CK 101732 | 2019-03-08 |  | Bedrock Rocks LLC | 66325.81 | 0 | 66325.81 |  | Middle School | [40 empty] | 66325.81
CK 101927 | 2019-03-22 |  | Kaluza Inc | 9845 | 0 | 9845 | Site Work | [29 empty] | 9845
CK 101927 | 2019-03-22 |  | Kaluza Inc | 3492 | 0 | 3492 | Site Work | Admin Bldg | [29 empty] | 3492
CK 101984 | 2019-03-22 |  | Unique Digital Inc. | 174295.8 | 0 | 174295.8 | [8 empty] | 153380.304 | 20915.496
CK 102034 | 2019-03-29 |  | Karczewski and Bradshaw LLP | 975 | 0 | 975 | Legal Fees |  |  | 975
E 00001 | 2019-03-29 |  | Drymall Construction | 348899.36 | -17444.97 | 331454.39 | Payment #1 | Middle School | [12 empty] | 331454.39
CK 102075 | 2019-03-29 |  | Fort Bend CO WCID #2 | 19880 | 0 | 19880 | Water Connection Fee? | [6 empty] | 19880
CK 102136 | 2019-04-05 |  | Lockwood, Andrews and Newman | 127675.52 | 0 | 127675.52 | Project Management | [7 empty] | 112354.4576 | 15321.0624
CK 102194 | 2019-04-10 |  | Centerpoint Energy | 5520 | 0 | 5520 | Move Electrical Boxes | [5 empty] | 5520
CK 102209 | 2019-04-12 |  | Bedrock Rocks LLP | 1875 | 0 | 1875 | [42 empty] | 1875
CK 102244 | 2019-04-12 |  | Longhorn Bus Sales | 193588 | 0 | 193588 | Purchased 2 Regular Buses | Transportation | [35 empty] | 193588
CK 102244 | 2019-04-12 |  | Longhorn Bus Sales | 97274 | 0 | 97274 | Purchased 1 Spec Ed Bus | Transportation | [35 empty] | 97274
CK 102360 | 2019-04-18 |  | Centerpoint Energy | 3678 | 0 | 3678 | Electrical Work | [5 empty] | 3678
E 00002 | 2019-04-25 |  | Drymall Construction | 815455.95 | -40772.8 | 774683.15 | Payment #2 | Middle School | [12 empty] | 774683.15
CK 102406 | 2019-04-26 |  | Karczewski and Bradshaw LLP | 812.5 | 0 | 812.5 | Legal Fees |  |  | 812.5
CK 102407 | 2019-04-26 |  | Kaluza Inc | 2798 | 0 | 2798 | Site Work | [29 empty] | 2798
CK 102407 | 2019-04-26 |  | Kaluza Inc | 1785 | 0 | 1785 | Site Work | Middle School | [25 empty] | 1785
CK 102407 | 2019-04-26 |  | Kaluza Inc | 4365 | 0 | 4365 | Site Work | Admin Bldg | [29 empty] | 4365
CK 102412 | 2019-04-26 |  | Lockwood, Andrews and Newman | 76465.39 | 0 | 76465.39 | Project Management | [7 empty] | 67289.5432 | 9175.8468
CK 102493 | 2019-05-03 |  | Lockwood, Andrews and Newman | 77025.25 | 0 | 77025.25 | Project Management | [7 empty] | 67782.22 | 9243.03
CK 102487 | 2019-05-03 |  | Houston Business Journal | 780 | 0 | 780 | Advertising |  |  |  |  | 780
CK 102465 | 2019-05-03 |  | Children's Plus Inc | 218808.54 | 0 | 218808.54 | Library Books | [37 empty] | 218808.54
CK 102704 | 2019-05-17 |  | Houston Business Journal | 520 | 0 | 520 | Advertising |  |  |  |  | 520
CK 102812 | 2019-05-24 |  | Karczewski and Bradshaw LLP | 81.25 | 0 | 81.25 | Legal Fees |  |  | 81.25
CK 102813 | 2019-05-24 |  | Kaluza Inc | 2520 | 0 | 2520 | Site Work | Middle School | [28 empty] | 2520
E 00003 | 2019-05-24 |  | Drymall Construction | 734229.28 | -36711.46 | 697517.82 | Payment #3 | Middle School | [12 empty] | 697517.82
CK 102941 | 2019-06-05 |  | Autoarch Architects LLC | 63274.35 | 0 | 63274.35 | A&E Services Site Work | [16 empty] | 63274.35
CK 102941 | 2019-06-05 |  | Autoarch Architects LLC | 74125 | 0 | 74125 | A&E Services Site Work | Admin Bldg | [16 empty] | 74125
CK 102941 | 2019-06-05 |  | Autoarch Architects LLC | 94928 | 0 | 94928 | A&E Services Site Work | Middle School | [14 empty] | 94928
CK 103030 | 2019-06-13 |  | Lockwood, Andrews and Newman | 76778.85 | 0 | 76778.85 | Project Management | [7 empty] | 67565.388 | 9213.462
CK 103094 | 2019-06-20 |  | Kaluza Inc | 12591 | 0 | 12591 | Site Work | [29 empty] | 12591
CK 103094 | 2019-06-20 |  | Kaluza Inc | 2910 | 0 | 2910 | Site Work | Admin Bldg | [29 empty] | 2910
CK 103094 | 2019-06-20 |  | Kaluza Inc | 2520 | 0 | 2520 | Site Work | Middle School | [25 empty] | 2520
E00004 | 2019-06-25 |  | Drymall Construction | 1307767.96 | -65388.4 | 1242379.56 | Payment #4 | Middle School | [12 empty] | 1242379.56
GJ 013918 | 2019-06-25 |  | Drymall Construction | 449317 | -22465.85 | 426851.15 | Payment #1 | Admin Bldg | [13 empty] | 426851.15
CK 103150 | 2019-06-26 |  | Fort Bend Co WCID #2 | 2294.57 | 0 | 2294.57 | Water Connection Fee? | Admin Bldg | [5 empty] | 2294.57
CK 103202 | 2019-07-12 |  | Karczewski and Bradshaw LLP | 568.75 | 0 | 568.75 | Legal Fees |  |  | 568.75
CK 103205 | 2019-07-12 |  | Lockwood, Andrews and Newman | 76644.43 | 0 | 76644.43 | Project Management | [7 empty] | 67447.0984 | 9197.3316
CK 103192 | 2019-07-12 |  | Children's Plus Inc | 216318.83 | 0 | 216318.83 | Library Books | [37 empty] | 216318.83
CK 103249 | 2019-07-18 |  | Houston Business Journal | 650 | 0 | 650 | [5 empty] | 650
CK 103279 | 2019-07-25 |  | Centerpoint Energy | 2230.56 | 0 | 2230.56 | Electrical Work | Middle School | [37 empty] | 2230.56
CK 103278 | 2019-07-25 |  | Centerpoint Energy | 2612.31 | 0 | 2612.31 | Electrical Work | Admin School | [39 empty] | 2612.31
CK 103280 | 2019-07-25 |  | Centerpoint Energy | 3878 | 0 | 3878 | Electrical Work | Admin School | [39 empty] | 3878
CK 103281 | 2019-07-25 |  | Centerpoint Energy | 8274 | 0 | 8274 | Electrical Work | Admin School | [39 empty] | 8274
CK 103393 | 2019-08-09 |  | Karczewski and Bradshaw LLP | 3511.73 | 0 | 3511.73 | Legal Fees |  |  | 3511.73
GJ 013942 | 2019-08-13 |  | Drymall Construction | 1841798.16 | -92089.91 | 1749708.25 | Payment #5 | Middle School | [12 empty] | 1749708.25
GJ 013968 | 2019-08-14 |  | Drymall Construction | 466423 | -23321.15 | 443101.85 | Payment #2 | Admin Bldg | [13 empty] | 443101.85
CK 103514 | 2019-08-23 |  | Knapp Chevrolet | 60293.17 | 0 | 60293.17 | Purchase Truck | Transportation | [35 empty] | 60293.17
CK 103547 | 2019-08-23 |  | Weissner Engineering | 9000 | 0 | 9000 | Site Work | [23 empty] | 9000
CK103593 | 2019-08-23 |  | Paradigm Consultants | 3800 | 0 | 3800 | Site Work | [23 empty] | 3800
CK 103591 | 2019-08-28 |  | Lockwood Andrews | 76638.49 | 0 | 76638.49 | Project Management | [9 empty] | 76638.49
CK 103579 | 2019-08-28 |  | Centerpoint | 5096 | 0 | 5096 | [39 empty] | 5096
GJ 014095 | 2019-08-29 |  | DryMalla Construction | 2119485.46 | -105974.27 | 2013511.19 | Payment #6 | Middle School | [12 empty] | 2013511.19
CK 103633 | 2019-08-30 |  | Kaluza & Assoc | 12091.5 | 0 | 12091.5 | Site Work | [29 empty] | 12091.5
CK 103661 | 2019-08-30 |  | Traffic Engineers | 18000 | 0 | 18000 | Traffic Study | Site Work | [33 empty] | 18000
CK 103633 | 2019-08-30 |  | Kaluza & Assoc | 875 | 0 | 875 | Site Work | Middle School | [25 empty] | 875
CK 103631 | 2019-08-30 |  | HVJ Associates | 75269.77 | 0 | 75269.77 | MEP Work | Middle School | [31 empty] | 75269.77
CK 103633 | 2019-08-30 |  | Kaluza & Assoc | 9490 | 0 | 9490 | Site Work | Admin Bldg
CK 103631 | 2019-08-30 |  | HVJ Associates | 21308.88 | 0 | 21308.88 | MEP Work | Admin Bldg | [29 empty] | 9490 |  |  | 21308.88
GJ 014149 | 2019-08-31 |  | Drymalla Construction | 871249 | -43562.45 | 827686.55 | Payment #3 | Admin Bldg | [13 empty] | 827686.55
GJ 014150 | 2019-08-31 |  | Drymalla Construction | 388753 | -19437.65 | 369315.35 | Payment #4 | Admin Bldg | [13 empty] | 369315.35
GJ 014152 | 2019-08-31 |  | Drymalla Construction | 2460708.67 | -123035.43 | 2337673.24 | Payment #7 | Middle School | [12 empty] | 2337673.24
GJ 014154 | 2019-08-31 |  | Lockwood, Andrews & Newman | 76397.3 | 0 | 76397.3 | Project Mgmt | Proj Mgmt | [8 empty] | 76397.3
APAUG1 | 2019-08-31 |  | HVJ Associates | 2172.75 | 0 | 2172.75 | MEP Work | Admin Bldg | [32 empty] | 2172.75
APAUG1 | 2019-08-31 |  | Techknowledge Consulting | 977.5 | 0 | 977.5 | MEP Work | Middle School | [31 empty] | 977.5
APAUG1 | 2019-08-31 |  | Autoarch Architects | 12280.13 | 0 | 12280.13 | Architect Work | Middle School | [14 empty] | 12280.13
| 2019-08-31 |  | Autoarch Architects | 48113.4 | 0 | 48113.4 | Architect Work | Admin Bldg | [16 empty] | 48113.4
GJ 014146 | 2019-08-31 |  | Autoarch Architects | 63813 | 0 | 63813 | Architect Work | Site Improvmnt | [15 empty] | 63813
GJ 014156 | 2019-08-31 |  | Traffic Engineers< Inc | 2000 | 0 | 2000 | Traffic Study | Site Work | [33 empty] | 2000
GJ 014159 | 2019-08-31 |  | Karczewski and Bradshaw LLP | 6343.48 | 0 | 6343.48 | Legal Services | Legal Fees |  | 6343.48
GJ 014159 | 2019-08-31 |  | Karczewski and Bradshaw LLP | 243.75 | 0 | 243.75 | Legal Services | Legal Fees |  | 243.75
CK 103825 | 2019-09-18 |  | Knapp Chevrolet Inc | 19893.06 | 0 | 19893.06 | Purchase Chevy Malibu | Transportation | [35 empty] | 19893.06
CK 103823 | 2019-09-18 |  | Helfman Ford | 37235 | 0 | 37235 | Purchase 10 Pass Van | Transportation | [35 empty] | 37235
0
|  |  | Total Disbursements to Date: | 17071857.33 | -590204.34 | 16481652.99 |  | PAYMENTS | 0 | 38267.85 | 0 | 3820 | 9198 | 22174.57 | 1158202.4772 | 139507.0128 | 153035.79 | 0 | 0 | 0 | 9146927.6 | 2066954.9 | 729948.18 | 140578.55 | 240838.9 | 0 | 0 | 0 | 0 | 8500 | 64690 | 11950 | 19500 | 55260 | 6820 | 2850 | 54035.5 | 44063.5 | 4050 | 76247.27 | 23481.63 | 20000 | 1258220.6 | 453410.36 | 435127.37 | 7326.56 | 0 | 14764.31 | 68200.81 | 0 | 3701.25 | 0 | 16481652.99
[9 empty] | 16481652.99 | [7 empty] | project mgr |  |  |  | 11213882.5
RECAP: |  |  | EXPENDITURES BY MONTH | [13 empty] | Allocation |  |  |  | 81.57% | 18.43%
[9 empty] | 0 | Variance Check | [6 empty] | based on
|  |  | New NET Bonds | 52000000 | [12 empty] | construction
|  |  | August 31, 2018 | -996279.33 | [12 empty] | costs
|  |  | July 31, 2019 | -7362316.8
|  |  | August 31, 2019 | -8656133.14
|  |  | September 30, 2019 | -57128.06
|  |  | Additional Interest Earnings | 1741977.37 |  |  |  | PO BALANCES | ---> | 1.15 | 1500 | 80 | 0 | 0 | -448527.2572 | 23369.2672 | 137814.71 | 300955 | 346640 | 3982900 | 18140606.2 | 4174472.1 | 666051.82 | -15328.55 | 55661.1 | 99360 | 162720 | 0 | 0 | 0 | 8150 | 0 | 0 | -36695 | 38280 | 33450 | 49314.5 | -11163.5 | 34250 | 91585.73 | 41788.37 | 0 | 0.4 | -57128.06 | 0 | 0 | 0 | -3 | 0 | 15000 | 110898.75 | 41340
Item is being psid from interest earnings on pay as you go
basis.
[6 empty] | 27987343.73 | Committed through PO and encumbrances
A & E Services = architectural & engineering |  |  | Total: | 36670120.04 |  | 36670120.04 | Available Cash as September 30, 2019
[6 empty] | 8682776.31 | Amount not encumbered OR PO issued
[15 empty] | Allocated Total | Middle PO | Admin PO |  |  |  | Projected Projc
[15 empty] | 44891640.8 | 27287533.8 | 6204107 |  |  |  | 11400000
[15 empty] | Percent of Total | 60.79% | 13.82% |  |  |  | 25.39%
Project Management Costs

## Sheet2
Stafford Municipal School District | [29 empty] | Centerpoint | Centerpoint | Centerpoint
Bond Payment Log Project to Date | [10 empty] | DryMalla | DryMalla |  |  |  |  | Paradigm | Weissner | Weissner | Weissner | Kaluza | Kaluza | Kaluza | LAN | LAN | LAN | City of Stafford |  |  | Electrical | Electrical | Electrical | Bedroom | TechKNowledge
As of July 31, 2019 | [9 empty] | Legal | Construction | Construction | Auto arch | Auto Arch | Auto Arch |  | Consultants | Engineering | Engineering | Engineering |  |  |  | Project Mgr | Project Mgr | Project Mgr | Land | Buses & | Library | Work | Work | Work | Rocks | Consulting
[10 empty] | Fees | Middle Sch. | Admin Bdlg | Middle | Site Work | Admin Bdlg | Engineering | Middle | Middle | Site Work | Admin | Middle | Site Work | Admin Bdlg | Middle | Admin | Site | Purchase | Vehicles | Books | Middle | Site Work | Admin | Middle
REQ # | DATE PAID | DRAWS | VENDOR | GROSS AMT | RETAINAGE | NET AMT | PURPOSE | PROJECT
CJ 013122 | 2018-08-31 |  | Audit Adj Entry #1003 | 80621.25 | 0 | 80621.25 |  | Middle School | 80621.25
GJ 013122 | 2018-08-31 |  | Audit Adjusting Entry #1003 | 134238.7 | 0 | 134238.7 | Project Manager | Middle School | 134238.7
CK 100290 | 2018-11-16 |  | Lockwood, Andrews and Newman | 67460.9 | 0 | 67460.9 | Project Management |  | 67460.9
CK 100374 | 2018-11-30 |  | Lockwood, Andrews and Newman | 67119.35 | 0 | 67119.35 | Project Management |  | 67119.35
CK 100805 | 2019-01-04 |  | Lockwood, Andrews and Newman | 136670.62 | 0 | 136670.62 | Project Management |  | 136670.62
CK 101651 | 2019-03-01 |  | Lockwood, Andrews and Newman | 67562.38 | 0 | 67562.38 | Project Management |  | 67562.38
CK 101984 | 2019-03-22 |  | Unique Digital Inc. | 174295.8 | 0 | 174295.8 |  |  | 174295.8
CK 102075 | 2019-03-29 |  | Fort Bend CO WCID #2 | 19880 | 0 | 19880 | Water Connection Fee? |  | 19880
CK 102136 | 2019-04-05 |  | Lockwood, Andrews and Newman | 127675.52 | 0 | 127675.52 | Project Management |  | 127675.52
CK 102194 | 2019-04-10 |  | Centerpoint Energy | 5520 | 0 | 5520 | Move Electrical Boxes |  | 5520
CK 102360 | 2019-04-18 |  | Centerpoint Energy | 3678 | 0 | 3678 | Electrical Work |  | 3678
CK 102412 | 2019-04-26 |  | Lockwood, Andrews and Newman | 76465.39 | 0 | 76465.39 | Project Management |  | 76465.39
CK 102493 | 2019-05-03 |  | Lockwood, Andrews and Newman | 77025.25 | 0 | 77025.25 | Project Management |  | 77025.25
CK 103030 | 2019-06-13 |  | Lockwood, Andrews and Newman | 76778.85 | 0 | 76778.85 | Project Management |  | 76778.85
CK 103205 | 2019-07-12 |  | Lockwood, Andrews and Newman | 76644.43 | 0 | 76644.43 | Project Management |  | 76644.43
|  |  | Total Disbursements to Date: | 1191636.44 | 0 | 1191636.44 |  |  | 1191636.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1191636.44
RECAP: |  |  | EXPENDITURES BY MONTH |  |  | EXPENDITURES BY TYPE
[9 empty] | 0 | Variance Check
|  |  | New NET Bonds | 52000000
|  |  | August 31, 2018 | -214859.95 |  | Bond Fees
|  |  | July 31, 2019 | -976776.49 |  | Construction
Architect
|  |  | Total: | 50808363.56 |  | Total: | 0
A & E Services = architectural & engineering