## Sheet1
| Mt. Lebanon School District |  | S- Safety/Security |  | MES- Markham Elementary
| 7 Horsman Drive |  | E- Educational |  | HvES- Hoover Elementary
| Pittsburgh, PA 15228-1107 |  | G- General Maintenance |  | HwES- Howe Elementary
|  |  | MFC-Mellon Field Complex |  | LES- Lincoln Elementary
|  |  | JFC- Jefferson Field Complex |  | MMS- Mellon Middle
| CAPITAL PROJECT LIST |  | SFC- Stadium Field Complex |  | JMS- Jefferson Middle
| 2021-2022 |  | JES-Jefferson Elementary |  | HS- High School
WES- Washington Elementary
| 2022-02-17 |  | FES- Foster Elementary |  | Highlighted projects are complete
| Projects for 2021-22 | ASN | Budget Amnt | Actual Cost | Status
1 | DW- Electrical wiring, boxes and light fixture repairs | 19427 | 15000 | 18247 | Project Complete ($1,269 from insurance to reimburse)
2 | DW- Mechanical system repairs | 19428 | 20000 | 42178.2 | T. F. Campbell, CS&E $26,294.34 from Insur. to reimburs.
3 | DW- Plumbing system repairs | 19429 | 10000 | 21450 | Project Complete
4 | DW- Repair and maintain roofs (annual) | 19430 | 15000 | 12566 | Project Complete
5 | DW- Carpentry and locksmith repairs | 21714 | 10000 | 0 | Project Complete
6 | DW- Painting interior and exterior (annual) | 12790 | 15000 | 2730 | Project Complete
7 | DW- Fencing and Repair (annual) | 19466 | 10000 | 8460 | $460.00 Re-imbursed from insurance
7.1 | FES- Re-tie fence, install gate at tennis court and playground |  | 2050 | 2020 | Project Complete
7.2 | LES- Relocate fence and posts along North Meadowcroft |  | 3740 | 3740 | Project Complete
7.3 | LES- Repair gate to field along North Meadowcroft |  | 940 | 940 | Project Complete
8 | DW- Stage rigging repairs | 14584 | 20000 | 21632 | Project Complete
9 | DW- Interior finishes (annual) | 19457 | 15000 | 3659.62 | Project Complete
10 | DW- Playground equipment check and repair | 21726 | 3500 | 5001.43 | Project Complete
11 | DW-Landscaping & tree removal and planting (annual) | 19481 | 20000 | 33634.71 | Project Complete
12 | DW- Replace broken concr. sidewalks (LES, HS, JMS) | 20172 | 59775 | 59775 | Project Complete
13 | DW-Seal coat brick masonry:MES, HwES | 21717 | 32590 | 32589.75 | Project Complete
14 | DW- Window Repair | 20152 | 3500 | 2948 | Project Complete
15 | SFC-Repair sink hole drainage pipe behind visitor bleachers | 25033 | 1700 | 1700 | Project Complete
16 | HvES- Replace belgium block with concrete and curb | 13229 | 15425 | 15425 | Project Complete
17 | HS- Replace utility vehicle | 11456 | 15000 | 14882 | Project Complete
18 | SFC-Repave asphalt parking near stadium gate A | 25034 | 40915 | 40915 | Project Complete
19 | JES- Repave lower parking area along Ruth street | 13461 | 36435 | 36435 | Project Complete
20 | MMS- Repave rear parking area | 13463 | 53335 | 53335 | Project Complete
21 | HwES- Repave driveway and seal coat parking lot | 13453 | 11605 | 11605 | Project Complete
22 | HS- Refinish floors in center court and 3 gymnasiums | 20130 | 17500 | 16915 | Project Complete
23 | JMS- Repaint auditorium | 20930 | 18000 | 16380 | Project Complete
24 | LES- Extend retaining wall around meter pit at ballfield | 24922 | 6500 | 6500 | Project Complete
25 | WES- Replace 3 broken cafeteria tables | 14190 | 5550 | 5532 | Project Complete
26 | LES- Extend concrete sidewalk D16 to C15 | 20172 | 9295 | 9295 | Project Complete
27 | WES- Replace carpet in room 4 with VCT | 14207 | 3400 | 5070 | Project Complete
|  | TOTAL | 490755 | 505560.71 | * $477,537.37 including insurance reimbursement
Completed from operating budget
28 | FES- Replace door thresholds and hindges in the gymnasium |  | 6750
29 | LES- Install heat and dehumidifier in outside shed |  | 2200
30 | WES- Repair torn rubber pad under swing set |  | 4000
31 | LES- Replace concrete steps near outside classroom |  | 18425
32 | HwES/FES - Regrade ballfields |  | 15000
33 | MMS- Repair gym floor where buckling |  | 4500