## Measure BB_Data
Combined Headers | Pha se | Category | Project Site | Project Description | Vendor Name | Description (Services) | Est. start date | Est. end date | School Year | BEST Req. | PO Number | Committed Amount | Total Exp. & Committed | Invoice Number | Warrant Date | Warrant Number | Completed Amount | DSA Number | Project Tracking # | Fund | Res. | Goal | Funct. | Obj. | Loc. | % Completion | Detail Description
Amar-21st Century-Technology | 0 | Technology | Amar | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 19593.92 | 0175554-IN | 2019-10-21 | 000000020028933 | 19593.92 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9011101 | 2.469% | Ergotron Zip40 Charging carts to store laptops at Amar. Total carts: 15
Amar-21st Century-FF & E | 0 | FF & E | Amar | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5002 | PO3W-200000001592 | 0 | 43947.28 | 3205801119 | 2020-02-03 | 000000020065149 | 43947.28 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9011101 | 62.45% | Furniture - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc for Amar
Amar-21st Century-FF & E | 0 | FF & E | Amar | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5002 | PO3W-200000001592 | 0 | 26429.02 | 3205801119 | 2020-02-03 | 000000020065149 | 26429.02 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9011101 | 37.55% | Furniture - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc for Amar
Amar-21st Century-FF & E | 0 | FF & E | Amar | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5018 | PO3W-200000001595 | 0 | 7509.33 | 3207401219 | 2020-02-03 | 000000020065148 | 7509.33 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9011101 | 100% | Furniture - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc for Amar. The original PO was for $245,447.23 - $237,937.90 (moved to fund 12.0, per Annie Bui) = $7,509.33 (remaining balance charged to bond).
Amar-21st Century-FF & E | 0 | FF & E | Amar | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-01-31 | 2019/20 | 2-5020 | PO3W-200000001597 | 0 | 12081.12 | 3469331119 | 2020-01-31 | 000000020064674 | 12081.12 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9011101 | 81.66% | Furniture - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc for Amar
Amar-21st Century-FF & E | 0 | FF & E | Amar | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-01-31 | 2019/20 | 2-5020 | PO3W-200000001597 | 0 | 2713.22 | 3469331119 | 2020-01-31 | 000000020064674 | 2713.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9011101 | 18.34% | Furniture - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc for Amar
Amar-21st Century-Environ Consultant | 0 | Environ Consultant | Amar | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10236 | PO2W-200000005314 | 0 | 2600 | MCSI-4532 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9011101 | 100% | Asbestos & lead-based paint survey of Amar's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Amar-Ceiling replacement-Contractor | 0 | Contractor | Amar | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 17165.07 | Pay app #1 | 2019-12-17 | 000000020049998 | 17165.07 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9011105 | 0.3753% | Ceiling replacement for Amar.
Amar-Ceiling replacement-Contractor | 0 | Contractor | Amar | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-4981 | PO1-200000000729 | 163519.93 | 163519.93 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9011105 | 0% | Ceiling replacement for Amar.
Amar-Drinking fountain replacement-Contractor | 0 | Contractor | Amar | Drinking fountain replacement | Optima | Contractor | 2019-08-20 | 2020-02-20 | 2019/20 | 2-4812 | PO2W-200000002201 | 0 | 8200 | 5000189 | 2020-02-20 | 000000020071939 | 8200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9011104 | 100% | Provide & install 1 new drinking fountain at Amar.
Amar-Drinking fountain replacement-DSA Inspection | 0 | DSA Inspection | Amar | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6599 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9011104 | 0% | General inspection for the project as defined in Title 24 at Amar. Replacement of 2-exterior drinking fountains
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15596.68 | 0173757-IN | 2019-10-08 | 000000020023867 | 15596.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10917.68 | 0175537-IN | 2019-10-08 | 000000020023867 | 10917.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 0.2513% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 200 | 0173757-IN | 2019-10-08 | 000000020023867 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 380 | 0173757-IN | 2019-10-08 | 000000020023867 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173757-IN | 2019-10-08 | 000000020023867 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173757-IN | 2019-10-08 | 000000020023867 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173757-IN | 2019-10-08 | 000000020023867 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173757-IN | 2019-10-08 | 000000020023867 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 140 | 0175537-IN | 2019-10-08 | 000000020023867 | 140 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.003222% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 266 | 0175537-IN | 2019-10-08 | 000000020023867 | 266 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.006122% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 325.92 | 0175537-IN | 2019-10-08 | 000000020023867 | 325.92 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.007502% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 896.84 | 0175537-IN | 2019-10-08 | 000000020023867 | 896.84 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.02064% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 84 | 0175537-IN | 2019-10-08 | 000000020023867 | 84 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.001933% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 42 | 0175537-IN | 2019-10-08 | 000000020023867 | 42 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0009667% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 388.14 | 0173882-IN | 2019-10-10 | 000000020025135 | 388.14 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 0.008934% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 155966.8 | 0174031-IN | 2019-10-10 | 000000020025135 | 155966.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 3.59% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 32.03 | 0173882-IN | 2019-10-10 | 000000020025135 | 32.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0007372% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 11.64 | 0173882-IN | 2019-10-10 | 000000020025135 | 11.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0002679% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9.5 | 0173882-IN | 2019-10-10 | 000000020025135 | 9.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5 | 0173882-IN | 2019-10-10 | 000000020025135 | 5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0001151% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3 | 0173882-IN | 2019-10-10 | 000000020025135 | 3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 6.905e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1.5 | 0173882-IN | 2019-10-10 | 000000020025135 | 1.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 3.452e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 600 | 0174031-IN | 2019-10-10 | 000000020025135 | 600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.01381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1200 | 0174031-IN | 2019-10-10 | 000000020025135 | 1200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.02762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2000 | 0174031-IN | 2019-10-10 | 000000020025135 | 2000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.04603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3800 | 0174031-IN | 2019-10-10 | 000000020025135 | 3800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.08746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4656 | 0174031-IN | 2019-10-10 | 000000020025135 | 4656 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.1072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 12812 | 0174031-IN | 2019-10-10 | 000000020025135 | 12812 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.2949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 2600.65 | 0173900-IN | 2019-09-23 | 000000020017958 | 2600.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 2.854% | Ergotron Zip40 Charging carts to store laptops at Baldwin. Total carts: 14
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 15603.88 | 0174051-IN | 2019-09-23 | 000000020017958 | 15603.88 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 17.12% | Ergotron Zip40 Charging carts to store laptops at Baldwin. Total carts: 14
Baldwin-21st Century-Technology | 3 | Technology | Baldwin | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-11-07 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 16981.39 | 0174405-IN | 2019-11-07 | 000000020035575 | 16981.39 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 2.14% | Ergotron Zip40 Charging carts to store laptops at Baldwin. Total carts: 13
Baldwin-21st Century-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 960 | 100653 | 2021-09-08 | 000000020253624 | 960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 0.05248% | Construction management services for Baldwin - phase 3 & 4. This PO includes allowances of $40,000.00
Baldwin-21st Century-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 1760 | 101514 | 2021-09-29 | 000000020275054 | 1760 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 0.09622% | Construction management services for Baldwin - phase 3 & 4. This PO includes allowances of $40,000.00
Baldwin-21st Century-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2024-07-01 | 2021/22 | 22-1057 | PO1-220000000334 | 292142 | 292142 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 0% | Construction management services for Baldwin - phase 3 & 4. This PO includes allowances of $40,000.00
Baldwin-21st Century-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862 | 0 | 5650 | 102578 | 2021-11-08 | 000000020325325 | 5650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 11.52% | Construction management services for Baldwin - phase 3 & 4. This PO is to pay invoice #102578 (Prof service from 09/01-09/30/21), dated 09/30/21
Baldwin-21st Century-Contractor | 3 | Contractor | Baldwin | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 2020/21 | 21-4688 | PO2W-210000001838 | 0 | 50000 | 2021-022D | 2021-04-23 | 000000020182905 | 50000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021101 | 38.46% | Demo of ceiling tiles in 20 classrooms at Baldwin
Baldwin-21st Century-Contractor | 3 | Contractor | Baldwin | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-06-14 | 2021-09-09 | 2021/22 | 21-6790 | PO2W-210000002615 | 0 | 6500 | 2021-088D | 2021-09-09 | 000000020255195 | 6500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021101 | 38.24% | Demo of ceiling tiles in 2 classrooms at Baldwin for room #TK-KA & TK-KB
Baldwin-21st Century-FF & E | 3 | FF & E | Baldwin | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2019-12-19 | 2019/20 | 2-5017 | PO3W-200000001593 | 0 | 17081.11 | 3205971119 | 2019-12-19 | 000000020051312 | 17081.11 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 73.67% | Furniture - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc. for Baldwin
Baldwin-21st Century-FF & E | 3 | FF & E | Baldwin | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2019-12-19 | 2019/20 | 2-5017 | PO3W-200000001593 | 0 | 6105.79 | 3205971119 | 2019-12-19 | 000000020051312 | 6105.79 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 26.33% | Furniture - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc. for Baldwin
Baldwin-21st Century-FF & E | 3 | FF & E | Baldwin | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 3.16% | Furniture for Baldwin - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Baldwin-21st Century-FF & E | 3 | FF & E | Baldwin | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 1.655% | Furniture for Baldwin - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Baldwin-21st Century-Environ Consultant | 3 | Environ Consultant | Baldwin | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10237 | PO2W-200000005315 | 0 | 2600 | MCSI-4533 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9021101 | 100% | Asbestos & lead-based paint survey of Baldwin's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Baldwin-21st Century-Design | 3 | Design | Baldwin | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002222 | 0 | 29733.8 | T8701 | 2021-09-09 | 000000020255214 | 29733.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 8.82% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Baldwin-21st Century-Design | 3 | Design | Baldwin | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002222 | 0 | 26941.05 | 3294 | 2021-10-19 | 000000020302604 | 26941.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 7.992% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Baldwin-21st Century-Design | 3 | Design | Baldwin | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002222 | 0 | 6874.45 | 3338 | 2021-10-19 | 000000020302604 | 6874.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 2.039% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Baldwin-21st Century-Design | 3 | Design | Baldwin | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6236 | PO2W-210000002222 | 273555.7 | 273555.7 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Baldwin-Ceiling replacement-Contractor | 3 | Contractor | Baldwin | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 29986.18 | Pay app #1 | 2019-12-17 | 000000020049998 | 29986.18 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021105 | 0.6557% | Ceiling replacement for Baldwin.
Baldwin-Ceiling replacement-Contractor | 3 | Contractor | Baldwin | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 89958.54 | Pay app #2 | 2020-10-21 | 000000020136454 | 89958.54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021105 | 1.967% | Ceiling replacement for Baldwin.
Baldwin-Ceiling replacement-Contractor | 3 | Contractor | Baldwin | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 179917.08 | Pay app #5 | 2021-06-17 | 000000020198995 | 179917.08 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021105 | 3.934% | Ceiling replacement for Baldwin.
Baldwin-Ceiling replacement-Contractor | 3 | Contractor | Baldwin | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5057 | PO1-200000000729 | 15782.2 | 15782.2 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021105 | 0% | Ceiling replacement for Baldwin.
Baldwin-Drinking fountain replacement-DSA Fees | 3 | DSA Fees | Baldwin | Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7621 | PO1-200000000954 | 0 | 1050 | Per email | 2020-02-13 | 000000020070039 | 1050 | 03-120655 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9021104 | 100% | DSA plan check review fee for Baldwin drinking fountain.
Baldwin-Fire Alarm-DSA Fees | 3 | DSA Fees | Baldwin | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3175 | PO2W-200000001057 | 0 | 1020 | Per email | 2019-09-13 | 000000020015013 | 1020 | 03-120157 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9021103 | 100% | DSA plan check review fee for Baldwin fire alarm.
Baldwin-Fire alarm-Design | 3 | Design | Baldwin | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 2021/22 | 21-1992 | PO2W-210000000680 | 12125 | 12125 |  |  |  | 0 | 03-120157 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Baldwin. Facilities paid PO2W-20*3585 & 19-109869 in the amount of $36,375.00. The total architect contract for Baldwin FA is $48,500.00
Baldwin-Interim Housing-Design | 3 | Design | Baldwin | Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6242 | PO2W-210000002227 | 79400 | 79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021102 | 0% | Architect - Prepare design documents for Baldwin Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5822.17 | 0173716-IN | 2019-10-10 | 000000020025135 | 5822.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9031101 | 0.134% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7762.89 | 0173799-IN | 2019-10-10 | 000000020025135 | 7762.89 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9031101 | 0.1787% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 50458.8 | 0174050-IN | 2019-10-10 | 000000020025135 | 50458.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9031101 | 1.161% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 174.6 | 0173716-IN | 2019-10-10 | 000000020025135 | 174.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.004019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 142.5 | 0173716-IN | 2019-10-10 | 000000020025135 | 142.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.00328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 480.45 | 0173716-IN | 2019-10-10 | 000000020025135 | 480.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.01106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 75 | 0173716-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 45 | 0173716-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 22.5 | 0173716-IN | 2019-10-10 | 000000020025135 | 22.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.0005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173799-IN | 2019-10-10 | 000000020025135 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173799-IN | 2019-10-10 | 000000020025135 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173799-IN | 2019-10-10 | 000000020025135 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173799-IN | 2019-10-10 | 000000020025135 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173799-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173799-IN | 2019-10-10 | 000000020025135 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 195 | 0174050-IN | 2019-10-10 | 000000020025135 | 195 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.004488% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 390 | 0174050-IN | 2019-10-10 | 000000020025135 | 390 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.008976% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 650 | 0174050-IN | 2019-10-10 | 000000020025135 | 650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.01496% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1235 | 0174050-IN | 2019-10-10 | 000000020025135 | 1235 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.02843% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1513.2 | 0174050-IN | 2019-10-10 | 000000020025135 | 1513.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.03483% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4163.9 | 0174050-IN | 2019-10-10 | 000000020025135 | 4163.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.09584% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0174085-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9031101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Bixby. Total carts: 5
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 5201.29 | 0174091-IN | 2019-09-23 | 000000020017958 | 5201.29 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9031101 | 5.707% | Ergotron Zip40 Charging carts to store laptops at Bixby. Total carts: 5
Bixby-21st Century-Technology | 6 | Technology | Bixby | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 11702.91 | 0175105-IN | 2019-10-08 | 000000020023867 | 11702.91 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9031101 | 1.475% | Ergotron Zip40 Charging carts to store laptops at Bixby. Total carts: 9
Bixby-21st Century-Contractor | 6 | Contractor | Bixby | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-05-11 | 2021-06-28 | 2020/21 | 21-6371 | PO2W-210000002308 | 0 | 52500 | 2021-061A | 2021-06-28 | 000000020201777 | 52500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9031101 | 100% | Demo of ceiling tiles in 21 classrooms at Bixby
Bixby-21st Century-FF & E | 6 | FF & E | Bixby | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9031101 | 3.16% | Furniture for Bixby - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Bixby-21st Century-FF & E | 6 | FF & E | Bixby | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9031101 | 1.655% | Furniture for Bixby - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Bixby-21st Century-Environ Consultant | 6 | Environ Consultant | Bixby | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10238 | PO2W-200000005316 | 0 | 2600 | MCSI-4534 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9031101 | 100% | Asbestos & lead-based paint survey of Bixby's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Bixby-Ceiling replacement-Contractor | 6 | Contractor | Bixby | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 28196.47 | Pay app #1 | 2019-12-17 | 000000020049998 | 28196.47 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9031105 | 0.6165% | Ceiling replacement for Bixby.
Bixby-Ceiling replacement-Contractor | 6 | Contractor | Bixby | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-09-09 | 2021/22 |  | PO1-200000000729 | 0 | 253768.28 | Pay app #6 | 2021-09-09 | 000000020255213 | 253768.28 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9031105 | 5.549% | Ceiling replacement for Bixby.
Bixby-Ceiling replacement-Contractor | 6 | Contractor | Bixby | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5058 | PO1-200000000729 | 14840.25 | 14840.25 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9031105 | 0% | Ceiling replacement for Bixby.
Bixby-Drinking fountain replacement-DSA Fees | 6 | DSA Fees | Bixby | Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2021-04-27 | 2021-05-05 | 2020/21 | 21-6130 | PO2W-210000002164 | 0 | 1050 | Per email | 2021-05-05 | 000000020186220 | 1050 | 03-121642 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9031104 | 50% | DSA plan check review fee for Bixby's drinking fountain
Bixby-Fire Alarm-DSA Fees | 6 | DSA Fees | Bixby | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6932 | PO1-200000000849 | 0 | 870 | Per email | 2020-02-13 | 000000020070034 | 870 | 03-120620 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9031103 | 100% | DSA plan check review fee for Bixby fire alarm.
Bixby-Fire Alarm-Design | 6 | Design | Bixby | Fire Alarm | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 2021/22 | 2-6863 | PO1-200000000846 | 12125 | 12125 |  |  |  | 0 | 03-120620 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9031103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Bixby. Facilities paid PO2W-20*4417 in the amount of $36,375.00. The total architect contract for Bixby FA is $48,500.00
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7018.51 | 0173641-IN | 2019-10-08 | 000000020023867 | 7018.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 0.1615% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 209.52 | 0173641-IN | 2019-10-08 | 000000020023867 | 209.52 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.004822% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 171 | 0173641-IN | 2019-10-08 | 000000020023867 | 171 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.003936% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 576.54 | 0173641-IN | 2019-10-08 | 000000020023867 | 576.54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.01327% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 90 | 0173641-IN | 2019-10-08 | 000000020023867 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 54 | 0173641-IN | 2019-10-08 | 000000020023867 | 54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.001243% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 27 | 0173641-IN | 2019-10-08 | 000000020023867 | 27 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.0006214% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173804-IN | 2019-10-21 | 000000020028933 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 73694.31 | 0175624-IN | 2019-10-21 | 000000020028933 | 73694.31 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 1.696% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173804-IN | 2019-10-21 | 000000020028933 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173804-IN | 2019-10-21 | 000000020028933 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173804-IN | 2019-10-21 | 000000020028933 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173804-IN | 2019-10-21 | 000000020028933 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173804-IN | 2019-10-21 | 000000020028933 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173804-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 283.5 | 0175624-IN | 2019-10-21 | 000000020028933 | 283.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.006525% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 567 | 0175624-IN | 2019-10-21 | 000000020028933 | 567 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.01305% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 945 | 0175624-IN | 2019-10-21 | 000000020028933 | 945 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.02175% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1795.5 | 0175624-IN | 2019-10-21 | 000000020028933 | 1795.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.04133% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2199.96 | 0175624-IN | 2019-10-21 | 000000020028933 | 2199.96 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.05064% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6053.67 | 0175624-IN | 2019-10-21 | 000000020028933 | 6053.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.1393% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 10137.84 | 0175604-IN | 2019-11-13 | 000000020037339 | 10137.84 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 0.3613% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 130 | 0175604-IN | 2019-11-13 | 000000020037339 | 130 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.004634% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 247 | 0175604-IN | 2019-11-13 | 000000020037339 | 247 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.008804% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 302.64 | 0175604-IN | 2019-11-13 | 000000020037339 | 302.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.01079% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 832.78 | 0175604-IN | 2019-11-13 | 000000020037339 | 832.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.02968% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 78 | 0175604-IN | 2019-11-13 | 000000020037339 | 78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.00278% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 39 | 0175604-IN | 2019-11-13 | 000000020037339 | 39 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.00139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175607-IN | 2019-10-21 | 000000020028933 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9041101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at California. Total carts: 16
California-21st Century-Technology | 3 | Technology | California | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 19593.92 | 0175608-IN | 2019-10-21 | 000000020028933 | 19593.92 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9041101 | 2.469% | Ergotron Zip40 Charging carts to store laptops at California. Total carts: 16
California-21st Century-CM/PM Management | 3 | CM/PM Management | California | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 800 | 100653 | 2021-09-08 | 000000020253624 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 0.04374% | Construction management services for California - phase 3 & 4. This PO includes allowances of $40,000.00
California-21st Century-CM/PM Management | 3 | CM/PM Management | California | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 7360 | 101514 | 2021-09-29 | 000000020275054 | 7360 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 0.4024% | Construction management services for California - phase 3 & 4. This PO includes allowances of $40,000.00
California-21st Century-CM/PM Management | 3 | CM/PM Management | California | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2024-07-01 | 2021/22 | 22-1057 | PO1-220000000334 | 170210 | 170210 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 0% | Construction management services for California - phase 3 & 4. This PO includes allowances of $40,000.00
California-21st Century-CM/PM Management | 3 | CM/PM Management | California | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862 | 0 | 9450 | 102578 | 2021-11-08 | 000000020325325 | 9450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 19.27% | Construction management services for Baldwin - phase 3 & 4. This PO is to pay invoice #102578 (Prof service from 09/01-09/30/21), dated 09/30/21
California-21st Century-Contractor | 3 | Contractor | California | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 12744.48 | Pay app #4 | 2020-12-08 | 000000020148205 | 12744.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041101 | 2.831% | Prep & install Mohawk LVT, walk off mat & base at California for room #5 & 12
California-21st Century-Contractor | 3 | Contractor | California | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2022-09-14 | 2020/21 | 21-1882 | PO2W-210000000658 | 0 | 40000 | 2020-089A | 2021-04-23 | 000000020182905 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041101 | 100% | Demo of ceiling tiles in 16 classrooms at California
California-21st Century-FF & E | 3 | FF & E | California | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 3.16% | Furniture for California - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
California-21st Century-FF & E | 3 | FF & E | California | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9041101 | 1.655% | Furniture for California - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
California-21st Century-Environ Consultant | 3 | Environ Consultant | California | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10239 | PO2W-200000005317 | 0 | 2600 | MCSI-4535 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9041101 | 100% | Asbestos & lead-based paint survey of California's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
California-21st Century-Design | 3 | Design | California | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002223 | 0 | 24160.2 | T8702 | 2021-09-09 | 000000020255214 | 24160.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 9.84% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
California-21st Century-Design | 3 | Design | California | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-10-01 | 2021/22 |  | PO2W-210000002223 | 0 | 18877.95 | T8722 | 2021-10-01 | 000000020283685 | 18877.95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 7.689% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
California-21st Century-Design | 3 | Design | California | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002223 | 0 | 19695.11 | 3339 | 2021-10-19 | 000000020302604 | 19695.11 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 8.022% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
California-21st Century-Design | 3 | Design | California | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6238 | PO2W-210000002223 | 182791.74 | 182791.74 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
California-Ceiling replacement-Contractor | 3 | Contractor | California | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 22513.29 | Pay app #1 | 2019-12-17 | 000000020049998 | 22513.29 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041105 | 0.4923% | Ceiling replacement for California.
California-Ceiling replacement-Contractor | 3 | Contractor | California | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 202619.61 | Pay app #3 | 2021-01-08 | 000000020155354 | 202619.61 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041105 | 4.43% | Ceiling replacement for California.
California-Ceiling replacement-Contractor | 3 | Contractor | California | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5059 | PO1-200000000729 | 11849.1 | 11849.1 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041105 | 0% | Ceiling replacement for California.
California-Drinking fountain replacement-DSA Fees | 3 | DSA Fees | California | Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7620 | PO1-200000000953 | 0 | 1050 | Per email | 2020-02-13 | 000000020070038 | 1050 | 03-120656 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9041104 | 100% | DSA plan check review fee for California drinking fountain.
California-Fire alarm-DSA Fees | 3 | DSA Fees | California | Fire alarm | Department of General Services (DGS) | DSA fees | 2021-08-25 | 2021-09-09 | 2021/22 | 22-1428 | PO2W-220000000367 | 0 | 1290 | 12742 | 2021-09-09 | 000000020255188 | 1290 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9041103 | 100% | DGS plan/field review fee for California fire alarm
California-Fire Alarm-DSA Fees | 3 | DSA Fees | California | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3172 | PO2W-200000001054 | 0 | 780 | Per email | 2019-09-13 | 000000020015009 | 780 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9041103 | 100% | DSA plan check review fee for California fire alarm.
California-Fire alarm-Design | 3 | Design | California | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28169 | 2021-02-05 | 000000020162584 | 2425 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The total architect contract for California FA is $48,500.00
California-Fire alarm-Design | 3 | Design | California | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28227 | 2021-02-05 | 000000020162584 | 2425 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The total architect contract for California FA is $48,500.00
California-Fire alarm-Design | 3 | Design | California | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28469 | 2021-03-24 | 000000020174735 | 2425 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The total architect contract for California FA is $48,500.00
California-Fire alarm-Design | 3 | Design | California | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28606 | 2021-05-26 | 000000020192536 | 2425 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The total architect contract for California FA is $48,500.00
California-Fire alarm-Design | 3 | Design | California | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1455 | 28733 | 2021-09-09 | 000000020255226 | 1455 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 0.8491% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The total architect contract for California FA is $48,500.00
California-Fire alarm-Design | 3 | Design | California | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2022-01-19 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 970 | 29053 | 2022-01-19 | 000000020391276 | 970 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 0.5661% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The total architect contract for California FA is $48,500.00
California-Fire Alarm-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm | Team Inspections | General inspection | 2020-10-22 | 2021-02-05 | 2020/21 |  | PO2W-210000000977 | 0 | 3060 | 202011-08:CFA | 2021-02-05 | 000000020162579 | 3060 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 24.98% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system.
California-Fire Alarm-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm | Team Inspections | General inspection | 2020-10-22 | 2021-02-09 | 2020/21 |  | PO2W-210000000977 | 0 | 3060 | 202012-13:CFA | 2021-02-09 | 000000020163358 | 3060 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 24.98% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system.
California-Fire Alarm-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm | Team Inspections | General inspection | 2020-10-22 | 2021-02-09 | 2020/21 |  | PO2W-210000000977 | 0 | 3060 | 202101-14:CFA | 2021-02-09 | 000000020163358 | 3060 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 24.98% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system.
California-Fire Alarm-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm | Team Inspections | General inspection | 2020-10-22 | 2021-09-15 | 2020/21 |  | PO2W-210000000977 | 0 | 2570 | 20210630-12:CFA | 2021-09-15 | 000000020259610 | 2570 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 20.98% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system.
California-Fire Alarm-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm | Team Inspections | General inspection | 2020-10-22 | 2022-10-22 | 2021/22 | 21-2655 | PO2W-210000000977 | 500 | 500 |  |  |  | 0 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 0% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system.
California-Fire Alarm-Contractor | 3 | Contractor | California | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2020-12-18 | 2020/21 |  | PO2W-200000004928 | 0 | 100034.1 | Pay app #1 | 2020-12-18 | 000000020151942 | 100034.1 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 44.15% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 is created using Facilities' account string (PO2W-22*912). The total project cost with change order is $250,564.92
California-Fire Alarm-Contractor | 3 | Contractor | California | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-02-02 | 2020/21 |  | PO2W-200000004928 | 0 | 95444.14 | Pay app #2 | 2021-02-02 | 000000020161539 | 95444.14 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 42.13% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 is created using Facilities' account string (PO2W-22*912). The total project cost with change order is $250,564.92
California-Fire Alarm-Contractor | 3 | Contractor | California | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-06-02 | 2020/21 |  | PO2W-200000004928 | 0 | 10570.21 | Pay app #3 | 2021-06-02 | 000000020194112 | 10570.21 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 4.665% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 is created using Facilities' account string (PO2W-22*912). The total project cost with change order is $250,564.92
California-Fire Alarm-Contractor | 3 | Contractor | California | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-06-02 | 2020/21 |  | PO2W-200000004928 | 0 | 8055.98 | Pay app #4 | 2021-06-02 | 000000020194112 | 8055.98 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 3.556% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 is created using Facilities' account string (PO2W-22*912). The total project cost with change order is $250,564.92
California-Fire Alarm-Contractor | 3 | Contractor | California | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2023-07-11 | 2021/22 | 2-9608 | PO2W-200000004928 | 12468.65 | 12468.65 |  |  |  | 0 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 0% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 is created using Facilities' account string (PO2W-22*912). The total project cost with change order is $250,564.92
California-Interim Housing-Contractor | 3 | Contractor | California | Interim Housing | Suburban Water Systems | Fire flow testing | 2021-09-15 | 2021-09-27 | 2021/22 |  | PO2W-220000000489 | 0 | 212 | Per email | 2021-09-27 | 000000020272930 | 212 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041102 | 100% | Fee for fire flow testing performed or witnessed using Utility personnel for California. This fees applies to tests performed on distrubution systems in the entire territory served by the Utility.
California-Interim Housing-Contractor | 3 | Contractor | California | Interim Housing | Suburban Water Systems | Fire flow testing | 2021-09-15 | 2021-09-27 | 2021/22 | 22-1909 | PO2W-220000000489 | 0 | -212 | Per email | 2021-09-27 | 000000020272930 | -212 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041102 | -100% | This check was stale dated. The project was on hold - email per Jeffrey Bissiri dated 03/30/22 (JVA22*1009). Fee for fire flow testing performed or witnessed using Utility personnel for California. This fees applies to tests performed on distrubution systems in the entire territory served by the Utility.
California-Interim Housing-Design | 3 | Design | California | Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002228 | 0 | 3096 | T8706 | 2021-09-09 | 000000020255214 | 3096 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041102 | 3.179% | Architect - Prepare design documents for California Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00
California-Interim Housing-Design | 3 | Design | California | Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002228 | 0 | 1550.25 | 3340 | 2021-10-19 | 000000020302604 | 1550.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041102 | 1.592% | Architect - Prepare design documents for California Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00
California-Interim Housing-Design | 3 | Design | California | Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6243 | PO2W-210000002228 | 92753.75 | 92753.75 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041102 | 0% | Architect - Prepare design documents for California Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00
Cedarlane-21st Century-Reprographics | 1 | Reprographics | Cedarlane | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 40.85 | 10744155 | 2020-10-13 | 000000020134052 | 40.85 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 1.157% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane.
Cedarlane-21st Century-Reprographics | 1 | Reprographics | Cedarlane | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 20.51 | 10744848 | 2020-10-13 | 000000020134052 | 20.51 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.5809% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane.
Cedarlane-21st Century-Reprographics | 1 | Reprographics | Cedarlane | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 106.6 | 10742434 | 2020-10-13 | 000000020134052 | 106.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 3.019% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane.
Cedarlane-21st Century-Reprographics | 1 | Reprographics | Cedarlane | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 |  | PO1-200000001133 | 0 | 41.17 | 10746782 | 2020-10-20 | 000000020136011 | 41.17 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 1.166% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane.
Cedarlane-21st Century-Reprographics | 1 | Reprographics | Cedarlane | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 | 2-9811 | PO1-200000001133 | 0 | 7.03 | 10746778 | 2020-10-20 | 000000020136011 | 7.03 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.1991% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane. Close-out PO.
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 17466.51 | 0173447-IN | 2019-10-10 | 000000020025135 | 17466.51 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 0.402% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 11644.34 | 0173687-IN | 2019-10-10 | 000000020025135 | 11644.34 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 0.268% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 135 | 0173447-IN | 2019-10-10 | 000000020025135 | 135 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.003107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 225 | 0173447-IN | 2019-10-10 | 000000020025135 | 225 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 427.5 | 0173447-IN | 2019-10-10 | 000000020025135 | 427.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.00984% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 523.8 | 0173447-IN | 2019-10-10 | 000000020025135 | 523.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.01206% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1441.35 | 0173447-IN | 2019-10-10 | 000000020025135 | 1441.35 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.03318% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 67.5 | 0173447-IN | 2019-10-10 | 000000020025135 | 67.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.001554% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 150 | 0173687-IN | 2019-10-10 | 000000020025135 | 150 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 285 | 0173687-IN | 2019-10-10 | 000000020025135 | 285 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.00656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 349.2 | 0173687-IN | 2019-10-10 | 000000020025135 | 349.2 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.008037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 960.9 | 0173687-IN | 2019-10-10 | 000000020025135 | 960.9 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.02212% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 90 | 0173687-IN | 2019-10-10 | 000000020025135 | 90 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 45 | 0173687-IN | 2019-10-10 | 000000020025135 | 45 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7762.89 | 0173800-IN | 2019-10-21 | 000000020028933 | 7762.89 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 0.1787% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173800-IN | 2019-10-21 | 000000020028933 | 190 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173800-IN | 2019-10-21 | 000000020028933 | 100 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173800-IN | 2019-10-21 | 000000020028933 | 232.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173800-IN | 2019-10-21 | 000000020028933 | 640.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173800-IN | 2019-10-21 | 000000020028933 | 60 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173800-IN | 2019-10-21 | 000000020028933 | 30 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 201835.22 | 0175292-IN | 2019-10-22 | 000000020029495 | 201835.22 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 7.194% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 780 | 0175292-IN | 2019-10-22 | 000000020029495 | 780 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.0278% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1560 | 0175292-IN | 2019-10-22 | 000000020029495 | 1560 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.0556% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2600 | 0175292-IN | 2019-10-22 | 000000020029495 | 2600 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.09267% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 4940 | 0175292-IN | 2019-10-22 | 000000020029495 | 4940 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.1761% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 6052.8 | 0175292-IN | 2019-10-22 | 000000020029495 | 6052.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.2157% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 16655.6 | 0175292-IN | 2019-10-22 | 000000020029495 | 16655.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.5937% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173470-IN | 2019-09-23 | 000000020017958 | 1300.32 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Cedarlane. Total cart: 1
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1300.32 | 0175313-IN | 2019-10-15 | 000000020026572 | 1300.32 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 0.1639% | Ergotron Zip40 Charging carts to store laptops at Cedarlane. Total carts: 21
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 26006.47 | 0175340-IN | 2019-10-15 | 000000020026572 | 26006.47 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 3.277% | Ergotron Zip40 Charging carts to store laptops at Cedarlane. Total carts: 21
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-12-02 | 2021-03-04 | 2020/21 |  | PO3W-210000001075 | 0 | 13871.18 | 0195589-IN | 2021-03-04 | 000000020169354 | 13871.18 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 10.08% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Cedarlane. Total monitors: 25
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-12-02 | 2021-04-09 | 2020/21 | 21-3335 | PO3W-210000001075 | 0 | 40746.58 | 0196289-IN | 2021-04-09 | 000000020179111 | 40746.58 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 29.6% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Cedarlane. Total monitors: 25
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | 1988.53 | 0193365-IN | 2021-01-22 | 000000020158901 | 1988.53 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 2.995% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 25
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | 24363.75 | 0193365-IN | 2021-01-22 | 000000020158901 | 24363.75 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 36.69% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 25
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-03-04 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | -2.74 | 193365C-CM | 2021-03-04 | 000000020169354 | -2.74 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | -0.004126% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 25. Credit memo from vendor
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Desktop computer(s) | 2021-08-18 | 2022-02-08 | 2021/22 | 22-1266 | PO3W-220000000256 | 0 | 86.3 | 0207936-IN | 2022-02-08 | 000000020409355 | 86.3 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 1.292% | Desktop computers (ThinkCentre M70q), ThinkCentre Tiny Sandwich Kit II, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 2
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Desktop computer(s) | 2021-08-18 | 2022-02-08 | 2021/22 | 22-1266 | PO3W-220000000256 | 0 | 2061.76 | 0207936-IN | 2022-02-08 | 000000020409355 | 2061.76 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 30.86% | Desktop computers (ThinkCentre M70q), ThinkCentre Tiny Sandwich Kit II, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 2
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2021-08-18 | 2022-02-08 | 2021/22 | 22-1266 | PO3W-220000000256 | 0 | 4357.42 | 0205845-IN | 2022-02-08 | 000000020409355 | 4357.42 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 65.22% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Cedarlane. Total monitors: 2
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Arey Jones Educational Solutions | Web camera(s) | 2021-08-18 | 2022-02-08 | 2021/22 | 22-1266 | PO3W-220000000256 | 0 | 175.21 | 0205845-IN | 2022-02-08 | 000000020409355 | 175.21 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 2.623% | Viewsonic ViewCam VB-CAM-001 for Cedarlane. Total web cam: 2
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Camcor | Document camera(s) | 2020-12-02 | 2021-04-14 | 2020/21 | 21-3339 | PO3W-210000001076 | 0 | 15519.98 | 2508704 | 2021-04-14 | 000000020180213 | 15519.98 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 39.68% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Cedarlane. Total cameras: 25
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 380.19 | 8316064 | 2021-03-05 | 000000020169721 | 380.19 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 9.92% | C2G HDMI and USB pass through wall plates for Cedarlane. Total items: 25
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 67.45 | 5725548 | 2021-03-05 | 000000020169721 | 67.45 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 1.76% | C2G HDMI and USB pass through wall plates for Cedarlane. Total items: 25
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 318.86 | 8312741 | 2021-03-05 | 000000020169721 | 318.86 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 8.32% | C2G HDMI and USB pass through wall plates for Cedarlane. Total items: 25
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 |  | PO2W-210000001657 | 0 | 3799.65 | 31135 | 2021-03-24 | 000000020174718 | 3799.65 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 4.958% | Furniture for Cedarlane students grade 1-3 (Room F-2, F-3, G-3, & H-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 |  | PO2W-210000001657 | 0 | 9983.73 | 31135 | 2021-03-24 | 000000020174718 | 9983.73 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 13.03% | Furniture for Cedarlane students grade 1-3 (Room F-2, F-3, G-3, & H-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-08-16 | 2021/22 | 21-4030 | PO2W-210000001657 | 0 | 52203.03 | 32071 | 2021-08-16 | 000000020230714 | 52203.03 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 68.12% | Furniture for Cedarlane students grade 1-3 (Room F-1, F-2, G-3, & H-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-08-16 | 2021/22 | 21-4030 | PO2W-210000001657 | 0 | 10649.97 | 32071 | 2021-08-16 | 000000020230714 | 10649.97 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 13.9% | Furniture for Cedarlane students grade 1-3 (Room F-1, F-2, G-3, & H-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 | 21-4032 | PO2W-210000001659 | 0 | 27615.9 | 31136 | 2021-03-24 | 000000020174718 | 27615.9 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 72.8% | Furniture for Cedarlane students grade 4-8 (Room F-1 & G-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 |  | PO2W-210000001659 | 0 | 4991.86 | 31136 | 2021-03-24 | 000000020174718 | 4991.86 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 13.16% | Furniture for Cedarlane students grade 4-8 (Room F-1 & G-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-04-19 | 2020/21 | 21-4032 | PO2W-210000001659 | 0 | 5324.99 | 31181 | 2021-04-19 | 000000020181375 | 5324.99 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 14.04% | Furniture for Cedarlane students grade 4-8 (Room F-1 & G-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 | 21-6167 | PO2W-210000002168 | 0 | 160829.48 | 32191 | 2021-08-16 | 000000020230714 | 160829.48 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 72.12% | Furniture for Cedarlane students grade 4-8 (Room A-1 through A-4, B-1, B-3, C-1 through C-4, D-1, & Band). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 | 21-6167 | PO2W-210000002168 | 0 | 62180.33 | 32191 | 2021-08-16 | 000000020230714 | 62180.33 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 27.88% | Furniture for Cedarlane students grade 4-8 (Room A-1 through A-4, B-1, B-3, C-1 through C-4, D-1, & Band). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6362 | PO2W-210000002280 | 0 | 42470.95 | 32074 | 2021-08-16 | 000000020230714 | 42470.95 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 73.21% | Furniture for Cedarlane students grade 4-8 (Room E-1, E-2, & E-4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 |  | PO2W-210000002280 | 0 | 11816.6 | 32074 | 2021-08-16 | 000000020230714 | 11816.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 20.37% | Furniture for Cedarlane students grade 4-8 (Room E-1, E-2, & E-4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-09-30 | 2021/22 | 21-6362 | PO2W-210000002280 | 0 | 3728.48 | 32478 | 2021-09-30 | 000000020276414 | 3728.48 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 6.427% | Furniture for Cedarlane students grade 4-8 (Room E-1, E-2, & E-4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6363 | PO2W-210000002281 | 0 | 28313.96 | 32073 | 2021-08-16 | 000000020230714 | 28313.96 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 73.21% | Furniture for Cedarlane students grade 1-3 (Room E-3 & H-3) . Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6363 | PO2W-210000002281 | 0 | 10363.39 | 32073 | 2021-08-16 | 000000020230714 | 10363.39 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 26.79% | Furniture for Cedarlane students grade 1-3 (Room E-3 & H-3) . Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Culver Newlin | Furniture | 2022-01-14 | 2023-01-14 | 2021/22 | 22-3983 | PO2W-220000001344 | 28827.85 | 28827.85 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 0% | Mid-tower mobile storage with shelves & 2 locking doors for Cedarlane. Total towers: 24
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 9648.75 | 80804 | 2020-01-09 | 000000020055612 | 9648.75 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.671% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3193.75 | 80796 | 2020-01-14 | 000000020057268 | 3193.75 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.2221% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8378.75 | 81699 | 2020-01-14 | 000000020057268 | 8378.75 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.5827% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 7852.5 | 83068 | 2020-04-01 | 000000020085959 | 7852.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.5461% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 10365 | 82273 | 2020-04-01 | 000000020085960 | 10365 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.7208% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 10562.5 | 84567 | 2020-04-15 | 000000020089466 | 10562.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.7346% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 10410 | 85320 | 2020-05-28 | 000000020100719 | 10410 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.724% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 6977.5 | 86240 | 2020-06-17 | 000000020106117 | 6977.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.4853% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 14165 | 86864 | 2020-07-27 | 000000020116270 | 14165 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.9851% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 10209.09 | 88480 | 2020-08-17 | 000000020119773 | 10209.09 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.71% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 9643.06 | 89359 | 2020-10-13 | 000000020134067 | 9643.06 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6706% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 9136.35 | 90460 | 2020-10-20 | 000000020136025 | 9136.35 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6354% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 10180.08 | 91321 | 2020-12-18 | 000000020151933 | 10180.08 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.708% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 8801.11 | 91964 | 2020-12-18 | 000000020151933 | 8801.11 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6121% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 9411.62 | 92821 | 2021-02-08 | 000000020162981 | 9411.62 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6545% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 6923.17 | 94011 | 2021-04-05 | 000000020177572 | 6923.17 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.4815% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 5862.68 | 94918 | 2021-04-16 | 000000020181024 | 5862.68 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.4077% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 6261.09 | 95700 | 2021-05-25 | 000000020192064 | 6261.09 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.4354% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 3630.82 | 96936 | 2021-05-25 | 000000020192064 | 3630.82 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.2525% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-30 | 2021/22 |  | PO1-200000000640 | 0 | 25487.18 | 101444 | 2021-09-30 | 000000020276415 | 25487.18 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 1.773% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4694 | PO1-200000000640 | 22 | 22 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | David M Bertino Mfg | Furniture | 2021-11-09 | 2022-01-11 | 2021/22 | 22-3033 | PO2W-220000000940 | 0 | 3858.78 | J21117-2519 | 2022-01-11 | 000000020381073 | 3858.78 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 100% | Custom made rolling instrument storage cabinets for Cedarlane. Total cabinets: 2
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 9695.45 | 10513843591 | 2021-08-27 | 000000020245275 | 9695.45 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 13.33% | PowerSwitch N2200-ON OS6 for Cedarlane. Total power switch: 2
Cedarlane-21st Century-DSA Fees | 1 | DSA Fees | Cedarlane | 21st Century | Division of the State Architect (DSA) | DSA fees | 2020-04-13 | 2020-04-24 | 2019/20 | 2-9602 | PO2W-200000004897 | 0 | 22159 | Per email | 2020-04-24 | 000000020092204 | 22159 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9051101 | 100% | DSA plan check review fee for Cedarlane 21st Century.
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Graybar | Door hardware | 2021-06-16 | 2021-08-30 | 2021/22 |  | PO3W-210000003051 | 0 | 376.36 | 9322335589 | 2021-08-30 | 000000020246134 | 376.36 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 17.34% | Mounting brackets, faceplates, & mini com stereo for Cedarlane
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Graybar | Door hardware | 2021-06-16 | 2021-09-23 | 2021/22 |  | PO3W-210000003051 | 0 | 358.62 | 9323008978 | 2021-09-23 | 000000020271037 | 358.62 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 16.53% | Mounting brackets, faceplates, & mini com stereo for Cedarlane
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Graybar | Door hardware | 2021-06-16 | 2022-03-15 | 2021/22 | 21-6866 | PO3W-210000003051 | 0 | 101.99 | 9325677028 | 2022-03-15 | 000000020443754 | 101.99 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 4.7% | Mounting brackets, faceplates, & mini com stereo for Cedarlane
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 2169.1 | 35275 | 2021-10-21 | 000000020304825 | 2169.1 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9051101 | 70.32% | Troubleshot intercom system, was unable to hear bell system at Cedarlane. Repair damage caused by bond work.
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 163.5 | 35255 | 2021-10-21 | 000000020304825 | 163.5 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9051101 | 5.3% | Walked and reviewed site for the wireless door contacts installation at Cedarlane. Repair damage caused by bond work.
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5992 | PO3W-210000002406 | 0 | 2660.68 | 34985 | 2021-06-07 | 000000020195370 | 2660.68 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 31.87% | Equipment to repair & replace security system at Cedarlane
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5992 | PO3W-210000002406 | 0 | 558.94 | 34985 | 2021-06-07 | 000000020195370 | 558.94 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 6.694% | Equipment to repair & replace security system at Cedarlane
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-16 | 2020/21 | 21-3578 | PO2W-210000001495 | 0 | 18390.28 | 2322450221 | 2021-04-16 | 000000020181030 | 18390.28 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 46.37% | Furniture for Cedarlane. Tables, chairs, stools, carpets, filing cabinets, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-16 | 2020/21 | 21-3578 | PO2W-210000001495 | 0 | 21273.58 | 2322450221 | 2021-04-16 | 000000020181030 | 21273.58 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 53.63% | Furniture for Cedarlane. Tables, chairs, stools, carpets, filing cabinets, etc
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 3.16% | Furniture for Cedarlane - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 1.655% | Furniture for Cedarlane - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Lightspeed | Voice amplification system | 2020-12-03 | 2021-04-13 | 2020/21 | 21-3356 | PO3W-210000001079 | 0 | 5475 | 133637 | 2021-04-13 | 000000020179759 | 5475 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 11.95% | Voice amplification system - Topcat, mounting kit & sensor clip for Cedarlane. Total system: 25
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | Lightspeed | Voice amplification system | 2020-12-03 | 2021-04-13 | 2020/21 | 21-3356 | PO3W-210000001079 | 0 | 40350.82 | 133637 | 2021-04-13 | 000000020179759 | 40350.82 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 88.05% | Voice amplification system - Topcat, mounting kit & sensor clip for Cedarlane. Total system: 25
Cedarlane-21st Century-Move Management | 1 | Move Management | Cedarlane | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 3328.8 | RI90797 | 2021-02-22 | 000000020166212 | 3328.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9051101 | 16.07% | Rental of 2 - 40' dry containers with lock box for 6 months for Cedarlane. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Cedarlane-21st Century-Move Management | 1 | Move Management | Cedarlane | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 | 21-4281 | PO1-210000000608 | 0 | 394.2 | RI95473 | 2021-09-09 | 000000020255202 | 394.2 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9051101 | 1.903% | Rental of 2 - 40' dry containers with lock box for 6 months for Cedarlane. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO.
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-10-13 | 2020/21 | 2-10466 | PO2W-200000005389 | 0 | 2800 | MCSI-4529 | 2020-10-13 | 000000020134092 | 2800 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 100% | Asbestos & lead-based paint survey of Cedarlane's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-10-27 | 2021-02-04 | 2020/21 |  | PO2W-210000000995 | 0 | 6950 | MCSI-4651 | 2021-02-04 | 000000020162190 | 6950 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 58.9% | Oversight asbestos abatement at Cedarlane for room #F1-F3, G1-G4, & H1
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-10-27 | 2023-01-16 | 2021/22 | 21-2726 | PO2W-210000000995 | 4850 | 4850 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #F1-F3, G1-G4, & H1
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-01-27 | 2021-03-22 | 2020/21 |  | PO2W-210000001656 | 0 | 6950 | MCSI-4686 | 2021-03-22 | 000000020174069 | 6950 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 41.49% | Oversight asbestos abatement at Cedarlane for room #E1, E2, E3 & H3
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-01-27 | 2023-01-27 | 2021/22 | 21-4009 | PO2W-210000001656 | 500 | 500 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #E1, E2, E3 & H3
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-03-19 | 2021-04-16 | 2020/21 |  | PO2W-210000001982 | 0 | 4750 | MCSI-4712 | 2021-04-16 | 000000020181032 | 4750 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 68.35% | Oversight asbestos abatement at Cedarlane for room #C1-C3.
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-03-19 | 2023-03-19 | 2021/22 | 21-5452 | PO2W-210000001982 | 2200 | 2200 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #C1-C3.
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-05-06 | 2021-05-25 | 2020/21 |  | PO2W-210000002278 | 0 | 3050 | MCSI-4735 | 2021-05-25 | 000000020192073 | 3050 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 40.4% | Oversight asbestos abatement at Cedarlane for room #A2, A3, & B1.
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-05-06 | 2021-09-08 | 2021/22 |  | PO2W-210000002278 | 0 | 2200 | MCSI-4872. | 2021-09-08 | 000000020253629 | 2200 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 29.14% | Oversight asbestos abatement at Cedarlane for room #A2, A3, & B1.
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-05-06 | 2023-05-06 | 2021/22 | 21-6338 | PO2W-210000002278 | 2300 | 2300 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #A2, A3, & B1.
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-06-07 | 2023-06-07 | 2020/21 | 21-6713 | PO2W-210000002602 | 0 | 425 | MCSI-4746 | 2021-06-22 | 000000020200055 | 425 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 33.33% | Oversight asbestos abatement at Cedarlane (asbestos cement pipe)
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-08-10 | 2021-09-30 | 2021/22 |  | PO2W-220000000246 | 0 | 2200 | MCSI-4873 | 2021-09-30 | 000000020276431 | 2200 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 84.62% | Oversight asbestos abatement for Cedarlane's flooring at room #B3 & D1 under the cabinets and side rooms off Band room
Cedarlane-21st Century-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-08-10 | 2023-08-10 | 2021/22 | 22-976 | PO2W-220000000246 | 400 | 400 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement for Cedarlane's flooring at room #B3 & D1 under the cabinets and side rooms off Band room
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-01-22 | 2020/21 |  | PO2W-210000000983 | 0 | 588686.5 | Pay app #1 | 2021-01-22 | 000000020158915 | 588686.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 15.43% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-01-22 | 2020/21 |  | PO2W-210000000983 | 0 | 318682.25 | Pay app #2 | 2021-01-22 | 000000020158915 | 318682.25 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 8.353% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-03-17 | 2020/21 |  | PO2W-210000000983 | 0 | 137481.65 | Pay app #3 | 2021-03-17 | 000000020172903 | 137481.65 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 3.604% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-04-07 | 2020/21 |  | PO2W-210000000983 | 0 | 346238.1 | Pay app #4 | 2021-04-07 | 000000020178357 | 346238.1 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 9.076% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-05-21 | 2020/21 |  | PO2W-210000000983 | 0 | 264523.27 | Pay app #5 | 2021-05-21 | 000000020191176 | 264523.27 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 6.934% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-05-21 | 2020/21 |  | PO2W-210000000983 | 0 | 60733.5 | Pay app #6 | 2021-05-21 | 000000020191176 | 60733.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 1.592% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-06-18 | 2020/21 |  | PO2W-210000000983 | 0 | 161808.95 | Pay app #7 | 2021-06-18 | 000000020199433 | 161808.95 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 4.241% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-07-12 | 2020/21 |  | PO2W-210000000983 | 0 | 470243.82 | Pay app #8 | 2021-07-12 | 000000020207269 | 470243.82 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 12.33% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-08-17 | 2021/22 |  | PO2W-210000000983 | 0 | 277494.35 | Pay app #9 | 2021-08-17 | 000000020231509 | 277494.35 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 7.274% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-11-23 | 2021/22 |  | PO2W-210000000983 | 0 | 143188.64 | Pay app #10 | 2021-11-23 | 000000020343098 | 143188.64 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 3.753% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-12-20 | 2021/22 |  | PO2W-210000000983 | 0 | 71418.97 | Pay app #11 | 2021-12-20 | 000000020370752 | 71418.97 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 1.872% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Contractor | 1 | Contractor | Cedarlane | 21st Century | Masters Contracting Corp | Contractor | 2020-10-23 | 2023-10-23 | 2021/22 | 21-2507 | PO2W-210000000983 | 149500 | 149500 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 0% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2018-10-12 | 2017/18 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2672 | 514189 | 2018-10-12 | 24854124 | 2672 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.74% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2019-04-22 | 2018/19 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2672 | 516548 | 2019-04-22 | 25242024 | 2672 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.74% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2019-10-10 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 21376 | 518434 | 2019-10-10 | 000000020025176 | 21376 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 13.92% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2020-04-17 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 7481.6 | 522495 | 2020-04-17 | 000000020090429 | 7481.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 4.871% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2020-06-22 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 45958.4 | 523906 | 2020-06-22 | 000000020107236 | 45958.4 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 29.92% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2020-08-18 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 524035 | 2020-08-18 | 000000020120086 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2020-08-18 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 19100 | 524035 | 2020-08-18 | 000000020120086 | 19100 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 12.43% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Allowances for topographic survey, fire water plan, coutyard grading, & revised site plan.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2020-10-13 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 524655 | 2020-10-13 | 000000020134100 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2020-10-13 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 668 | 525158 | 2020-10-13 | 000000020134100 | 668 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 0.4349% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2020-10-21 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2672 | 525717 | 2020-10-21 | 000000020136453 | 2672 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.74% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2021-02-05 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 526191 | 2021-02-05 | 000000020162570 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2021-02-05 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 526648 | 2021-02-05 | 000000020162570 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 527231 | 2022-01-25 | 000000020397386 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2004 | 528248 | 2022-01-25 | 000000020397386 | 2004 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.305% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2338 | 528686 | 2022-01-25 | 000000020397386 | 2338 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.522% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1336 | 529088 | 2022-01-25 | 000000020397386 | 1336 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 0.8698% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 4008 | 530146 | 2022-01-25 | 000000020397386 | 4008 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 2.609% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 3340 | 527739 | 2022-01-26 | 000000020398558 | 3340 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 2.174% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2338 | 529656 | 2022-01-26 | 000000020398558 | 2338 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.522% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Design | 1 | Design | Cedarlane | 21st Century | PBK Architects | Architect | 2018-06-26 | 2023-01-16 | 2021/22 | 2-525 | PO2W-200000000856, 19-100508, 18-109907 | 27286 | 27286 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 0% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00.
Cedarlane-21st Century-Technology | 1 | Technology | Cedarlane | 21st Century | PI Manufacturing Corp. | Computer cables | 2020-12-03 | 2021-02-10 | 2020/21 | 21-3361 | PO3W-210000001096 | 0 | 1351.5 | 956470 | 2021-02-10 | 000000020163835 | 1351.5 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Computer cables for Cedarlane
Cedarlane-21st Century-Advertisement | 1 | Advertisement | Cedarlane | 21st Century | San Gabriel Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 2020/21 | 21-2253 | PO2W-210000000882 | 0 | 301.67 | 11412572 | 2020-10-19 | 000000020135642 | 301.67 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9051101 | 33.33% | Advertising for Bid 2020-21.01 HLPUSD Bid Bundle #2: 21st Century Classroom Improvements for Cedarlane, Mesa Robles, & Cedarlane Interim Housing. Publication dates: 09/22/20 & 09/28/20
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202102-04:CMSM | 2021-03-24 | 000000020174730 | 2880 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 1.427% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 5760 | 202103-06:CMSM | 2021-03-24 | 000000020174730 | 5760 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.853% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 5184 | 202012-10:CMSM | 2021-04-19 | 000000020181403 | 5184 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.568% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 3168 | 202101-07:CMSM | 2021-04-19 | 000000020181403 | 3168 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 1.569% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-04-20 | 2020/21 |  | PO2W-210000001035 | 0 | 6624 | 202104-05:CMSM | 2021-04-20 | 000000020181749 | 6624 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 3.281% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-06-09 | 2020/21 |  | PO2W-210000001035 | 0 | 6336 | 202105-04:CMSM | 2021-06-09 | 000000020196442 | 6336 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 3.138% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-06-23 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202106-04:CMSM | 2021-06-23 | 000000020200462 | 2880 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 1.427% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-09-09 | 2020/21 |  | PO2W-210000001035 | 0 | 3168 | 202107-04:CMSM | 2021-09-09 | 000000020255215 | 3168 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 1.569% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-09-22 | 2021/22 |  | PO2W-210000001035 | 0 | 11520 | 202108-03:CMSM | 2021-09-22 | 000000020269793 | 11520 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 5.706% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-10-22 | 2021/22 |  | PO2W-210000001035 | 0 | 6480 | 202110-03:CMSM | 2021-10-22 | 000000020305831 | 6480 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 3.21% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-12-01 | 2021/22 |  | PO2W-210000001035 | 0 | 5760 | 202111-03:CMSM | 2021-12-01 | 000000020346455 | 5760 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.853% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-12-20 | 2021/22 |  | PO2W-210000001035 | 0 | 6048 | 202112-03:CMSM | 2021-12-20 | 000000020370771 | 6048 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.996% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2022-01-12 | 2021/22 |  | PO2W-210000001035 | 0 | 3024 | 202108-09:CMSM | 2022-01-12 | 000000020382224 | 3024 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 1.498% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2025-07-11 | 2021/22 | 21-2812 | PO2W-210000001035 | 24768 | 24768 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 0% | General inspection for the project as defined in Title 24 for Cedarlane modernization.
Cedarlane-21st Century-Move classroom | 1 | Move classroom | Cedarlane | 21st Century | Warehouse | Boxes | 2020-10-20 | 2020-10-28 | 2020/21 |  | XSRQ-210000001812 | 0 | 318.12 |  |  |  | 318.12 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(240) for teachers' to pack their classrooms at Cedarlane.
Cedarlane-21st Century-Move classroom | 1 | Move classroom | Cedarlane | 21st Century | Warehouse | Boxes & tapes | 2020-12-03 | 2020-12-08 | 2020/21 |  | XSRQ-210000002207 | 0 | 484.13 |  |  |  | 484.13 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(250) & packing tapes (50) for teachers' to pack their classrooms at Cedarlane.
Cedarlane-21st Century-Move classroom | 1 | Move classroom | Cedarlane | 21st Century | Warehouse | Boxes & tapes | 2020-12-08 | 2020-12-10 | 2020/21 |  | XSRQ-210000002247 | 0 | 484.13 |  |  |  | 484.13 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(250) & packing tapes (50) for teachers' to pack their classrooms at Cedarlane.
Cedarlane-21st Century-Move classroom | 1 | Move classroom | Cedarlane | 21st Century | Warehouse | Boxes & tapes | 2021-01-08 | 2021-01-12 | 2020/21 |  | XSRQ-210000002484 | 0 | 795.26 |  |  |  | 795.26 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(260) & packing tapes (150) for teachers' to pack their classrooms at Cedarlane.
Cedarlane-21st Century-Move classroom | 1 | Move classroom | Cedarlane | 21st Century | Warehouse | Boxes | 2021-01-14 | 2021-06-04 | 2020/21 |  | XSRQ-210000002565 | 0 | 466.62 |  |  |  | 466.62 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(360) for teachers' to pack their classrooms at Cedarlane.
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Warehouse | Soap dispensers | 2021-07-09 | 2021-07-12 | 2021/22 |  | XSRQ-220000000064 | 0 | 0 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Classroom soap dispensers (24) for Cedarlane. These items are free to sites.
Cedarlane-21st Century-FF & E | 1 | FF & E | Cedarlane | 21st Century | Warehouse | Paper towel dispenser | 2021-07-13 | 2021-07-22 | 2021/22 |  | XSRQ-220000000112 | 0 | 918.52 |  |  |  | 918.52 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Classroom paper towel dispensers (24) for Cedarlane
Cedarlane-Drinking fountain replacement-DSA Inspection | 1 | DSA Inspection | Cedarlane | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6600 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051104 | 0% | General inspection for the project as defined in Title 24 at Cedarlane. Replacement of 3-exterior drinking fountains
Cedarlane-Fire alarm-DSA Fees | 1 | DSA Fees | Cedarlane | Fire alarm | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-01-20 | 2020/21 | 21-3658 | PO2W-210000001557 | 0 | 1290 | 12367 | 2021-01-20 | 000000020157905 | 1290 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9051103 | 60% | DGS plan/field review fee for Cedarlane fire alarm
Cedarlane-Fire Alarm-Environ Consultant | 1 | Environ Consultant | Cedarlane | Fire Alarm | Masek Consulting | Asbestos survey | 2020-04-13 | 2020-04-29 | 2019/20 | 2-9606 | PO2W-200000004872 | 0 | 800 | MCSI-4872 | 2020-04-29 | 000000020093275 | 800 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051103 | 100% | Limited asbestos survey of Cedarlane's permanent buildings. Testing for fire alarm project.
Cedarlane-Fire alarm-Design | 1 | Design | Cedarlane | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28044 | 2020-10-14 | 000000020134523 | 2375 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Cedarlane. Facilities paid PO2W-20*5349 & 19-104043 in the amount of $42,750.00. The total architect contract for Cedarlane FA is $47,500.00
Cedarlane-Fire alarm-Design | 1 | Design | Cedarlane | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28165 | 2021-02-05 | 000000020162584 | 1425 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051103 | 0.8316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Cedarlane. Facilities paid PO2W-20*5349 & 19-104043 in the amount of $42,750.00. The total architect contract for Cedarlane FA is $47,500.00
Cedarlane-Fire alarm-Design | 1 | Design | Cedarlane | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 | 21-1992 | PO2W-210000000680 | 0 | 950 | 28461 | 2021-03-24 | 000000020174735 | 950 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051103 | 0.5544% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Cedarlane. Facilities paid PO2W-20*5349 & 19-104043 in the amount of $42,750.00. The total architect contract for Cedarlane FA is $47,500.00
Cedarlane-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Cedarlane | Fire Alarm | Team Inspections | General inspection | 2020-02-07 | 2020-05-26 | 2019/20 |  | PO2W-200000004017 | 0 | 6185 | 202005-01:CFA | 2020-05-26 | 000000020099846 | 6185 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051103 | 74.97% | General inspection for the project as defined in Title 24 at Cedarlane. Alterations to 11 buildings' fire alarm: CR bldg A, B, C, D (Library), E, F, G, H, K (Locker bldg), M (Admin), P (MPR).
Cedarlane-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Cedarlane | Fire Alarm | Team Inspections | General inspection | 2020-02-07 | 2020-10-14 | 2020/21 | 2-7749 | PO2W-200000004017 | 0 | 2065 | 202009-08:CFA | 2020-10-14 | 000000020134520 | 2065 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051103 | 25.03% | General inspection for the project as defined in Title 24 at Cedarlane. Alterations to 11 buildings' fire alarm: CR bldg A, B, C, D (Library), E, F, G, H, K (Locker bldg), M (Admin), P (MPR).
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VoIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1202.7 | Pay app #1 | 2020-03-10 | 000000020079637 | 1202.7 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 0.09398% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915)
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VoIP, Inc | Contractor | 2019-09-26 | 2020-04-08 | 2019/20 |  | PO1-200000000662 | 0 | 22141.65 | Pay app #2 | 2020-04-08 | 000000020087746 | 22141.65 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 1.73% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915)
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VoIP, Inc | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 38354.72 | Pay app #4 | 2020-05-29 | 000000020101116 | 38354.72 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 2.997% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915)
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 24329.03 | Pay app #5 | 2020-07-30 | 000000020117024 | 24329.03 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 1.901% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915)
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 14196.89 | Pay app #6 | 2020-07-30 | 000000020117024 | 14196.89 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 1.109% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915)
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VoIP, Inc | Contractor | 2019-09-26 | 2020-12-18 | 2020/21 |  | PO1-200000000662 | 0 | 855 | Pay app #10 | 2020-12-18 | 000000020151942 | 855 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 0.06681% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915)
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VoIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4499 | PO1-200000000662 | 5320 | 5320 |  |  |  | 0 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 0% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915)
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VoIP, Inc | Contractor | 2019-09-26 | 2020-06-30 | 2019/20 |  | PO1-200000000662 | 0 | 0.01 |  |  |  | 0.01 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 7.814e-07% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915)
Cedarlane-Fire Alarm-Contractor | 1 | Contractor | Cedarlane | Fire Alarm | Telenet VoIP, Inc | Contractor | 2019-09-26 | 2020-06-30 | 2020/21 |  | PO1-200000000662 | 0 | -0.01 |  |  |  | -0.01 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | -7.814e-07% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 is created using Facilities' account string (PO2W-22*915). Reverse accrual from prior year
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-02-05 | 2020/21 |  | PO2W-210000001098 | 0 | 5342.5 | 20-31311-30-01 | 2021-02-05 | 000000020162565 | 5342.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 31.58% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane.
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-02-05 | 2020/21 |  | PO2W-210000001098 | 0 | 1360 | 20-31311-30-02 | 2021-02-05 | 000000020162565 | 1360 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 8.038% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane.
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-04-19 | 2020/21 |  | PO2W-210000001098 | 0 | 1650 | 20-31311-30-04 | 2021-04-19 | 000000020181372 | 1650 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 9.752% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane.
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-05-26 | 2020/21 |  | PO2W-210000001098 | 0 | 1732.5 | 20-31311-30-03 | 2021-05-26 | 000000020192519 | 1732.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 10.24% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane.
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-09-15 | 2021/22 |  | PO2W-210000001098 | 0 | 232.5 | 20-31311-30-05 | 2021-09-15 | 000000020259582 | 232.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 1.374% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane.
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2023-01-16 | 2021/22 | 21-2936 | PO2W-210000001098 | 6602.5 | 6602.5 |  |  |  | 0 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 0% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane.
Cedarlane-Interim Housing-FF & E | 1 | FF & E | Cedarlane | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2020-12-18 | 2020/21 |  | PO2W-200000004768 | 0 | 20580.53 | 30699 | 2020-12-18 | 000000020151932 | 20580.53 | 03-120587 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051102 | 3.336% | Furniture for Cedarlane - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Cedarlane-Interim Housing-FF & E | 1 | FF & E | Cedarlane | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 11760.3 | 30789 | 2021-05-07 | 000000020187154 | 11760.3 | 03-120587 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051102 | 1.906% | Furniture for Cedarlane - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Cedarlane-Interim Housing-FF & E | 1 | FF & E | Cedarlane | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 2940.07 | 31584 | 2021-05-25 | 000000020192063 | 2940.07 | 03-120587 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051102 | 0.4766% | Furniture for Cedarlane - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Cedarlane-Interim Housing-DSA Fees | 1 | DSA Fees | Cedarlane | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2020-01-28 | 2020-01-31 | 2019/20 | 2-7309 | PO2W-200000003716 | 0 | 3052.5 | Per email | 2020-01-31 | 000000020064667 | 3052.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9051102 | 100% | DSA plan check review fee for Cedarlane interim housing.
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-01-22 | 2020/21 |  | PO2W-210000000983 | 0 | 184120.83 | Pay app #1 | 2021-01-22 | 000000020158915 | 184120.83 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 4.826% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project with change order (xreq 22*5138) is 895,740.41
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-01-22 | 2020/21 |  | PO2W-210000000983 | 0 | 259777.5 | Pay app #2 | 2021-01-22 | 000000020158915 | 259777.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 6.809% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project with change order (xreq 22*5138) is 895,740.41
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-03-23 | 2020/21 |  | PO2W-210000000983 | 0 | 13195.5 | Pay app #3 | 2021-03-23 | 000000020174433 | 13195.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 0.3459% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project with change order (xreq 22*5138) is 895,740.41
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-04-07 | 2020/21 |  | PO2W-210000000983 | 0 | 247627 | Pay app #4 | 2021-04-07 | 000000020178357 | 247627 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 6.491% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project with change order (xreq 22*5138) is 895,740.41
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-05-21 | 2020/21 |  | PO2W-210000000983 | 0 | 64002.29 | Pay app #5 | 2021-05-21 | 000000020191176 | 64002.29 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 1.678% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project with change order (xreq 22*5138) is 895,740.41
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp | Contractor | 2020-10-23 | 2021-12-20 | 2021/22 |  | PO2W-210000000983 | 0 | 15026.88 | Pay app #6 | 2021-12-20 | 000000020370752 | 15026.88 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 0.3939% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project with change order (xreq 22*5138) is 895,740.41
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp | Contractor | 2020-10-23 | 2023-10-23 | 2021/22 | 21-2507 | PO2W-210000000983 | 41250 | 41250 |  |  |  | 0 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 0% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project with change order (xreq 22*5138) is 895,740.41
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp | Contractor | 2022-03-25 | 2024-07-11 | 2021/22 | 22-5138 |  | 70740.41 | 70740.41 |  |  |  | 0 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9051102 | 0% | Change order for classroom modifications at Cedarlane Interim Housing. Bid option #1. Addendum to PO2W-21*983. The total project with change order is $895,740.41
Cedarlane-Interim Housing-Modular Buildings | 1 | Modular Buildings | Cedarlane | Interim Housing | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-02-18 | 2019/20 | 2-2078 | PO2W-200000003188, PO2W-200000001048, 19-107585 | 0 | 218488.74 | R20530140 | 2020-02-18 | 000000020070593 | 218488.74 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9051102 | 100% | Puchase of 4 Portable classrooms - 24' x 40' DSA, install closure panels, new carpets, HVAC, T-8 lights lines, and delivery to Cedarlane.
Cedarlane-Interim Housing-Modular Buildings | 1 | Modular Buildings | Cedarlane | Interim Housing | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2021-02-05 | 2020/21 | 2-2078 | PO2W-200000003189, PO2W-200000001048, 19-107585 | 0 | 21300 | R20554228 | 2021-02-05 | 000000020162569 | 21300 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9051102 | 100% | For 4 portable classrooms - Block & level building, installation, and relocation of these classrooms at Cedarlane
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2018-10-12 | 2017/18 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 1146.66 | 513128 | 2018-10-12 | 24854124 | 1146.66 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 1.483% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2019-02-27 | 2018/19 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 8313.29 | 515588 | 2019-02-27 | 25120812 | 8313.29 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 10.75% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2019-05-23 | 2018/19 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 15479.91 | 516551 | 2019-05-23 | 25313243 | 15479.91 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 20.02% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2019-09-20 | 2018/19 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 8500 | 517420 | 2019-09-20 | 000000020017558 | 8500 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 10.99% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. Allowances for topographic survey.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2019-10-01 | 2019/20 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 9459.94 | 516992 | 2019-10-01 | 000000020021440 | 9459.94 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 12.23% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2020-08-18 | 2019/20 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 2579.99 | 524036 | 2020-08-18 | 000000020120086 | 2579.99 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 3.336% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2020-08-18 | 2019/20 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 9100 | 524036 | 2020-08-18 | 000000020120086 | 9100 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 11.77% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. Allowances for civil engineering.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2021-02-05 | 2020/21 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 143.33 | 525686 | 2021-02-05 | 000000020162570 | 143.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2021-02-05 | 2020/21 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 143.33 | 526210 | 2021-02-05 | 000000020162570 | 143.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 8033.3 | 526678 | 2022-01-26 | 000000020398558 | 8033.3 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 10.39% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. Payment includes allowances of $2,300.00 for civil engineering.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 3583.31 | 527232 | 2022-01-26 | 000000020398558 | 3583.31 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 4.634% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 1433.33 | 527747 | 2022-01-26 | 000000020398558 | 1433.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 1.853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 859.99 | 528250 | 2022-01-26 | 000000020398558 | 859.99 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 1.112% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 2006.66 | 528688 | 2022-01-26 | 000000020398558 | 2006.66 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 2.595% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 430 | 529657 | 2022-01-26 | 000000020398558 | 430 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.556% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 143.33 | 530147 | 2022-01-26 | 000000020398558 | 143.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 143.33 | 531271 | 2022-01-26 | 000000020398558 | 143.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2023-01-16 | 2021/22 | 2-524 | PO2W-200000001212, 19-100509, 18-109906 | 5833.3 | 5833.3 |  |  |  | 0 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00.
Cedarlane-Interim Housing-Advertisement | 1 | Advertisement | Cedarlane | Interim Housing | San Gabriel Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 2020/21 | 21-2253 | PO2W-210000000882 | 0 | 301.66 | 11412572 | 2020-10-19 | 000000020135642 | 301.66 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9051102 | 33.33% | Advertising for Bid 2020-21.01 HLPUSD Bid Bundle #2: 21st Century Classroom Improvements for Cedarlane, Mesa Robles, & Cedarlane Interim Housing. Publication dates: 09/22/20 & 09/28/20
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Suburban Water Systems | Fire flow testing | 2019-04-16 | 2019-04-17 | 2018/19 |  | 19-108466 | 0 | 212 | Per email | 2019-04-17 | 25234519 | 212 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051102 | 100% | Fee for fire flow testing performed or witnessed using Utility personnel for Cedarlane. This fees applies to tests performed on distrubution systems in the entire territory served by the Utility.
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Suburban Water Systems | Deposit to construct (1) 6" public fire hydrant | 2019-11-25 | 2019-12-10 | 2019/20 | 2-5824 | PO2W-200000002737 | 0 | 3000 | Per email | 2019-12-10 | 000000020047106 | 3000 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051102 | 100% | Deposit - Preliminary estimate to construct (1) 6" public fire hydrant at Cedarlane.
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202102-03:CMSIH | 2021-03-24 | 000000020174730 | 2880 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 1.427% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing.
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202103-05:CMSIH | 2021-03-24 | 000000020174730 | 2880 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 1.427% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing.
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 2736 | 202012-09:CMSIH | 2021-04-19 | 000000020181403 | 2736 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 1.355% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing.
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 3168 | 202101-06:CMSIH | 2021-04-19 | 000000020181403 | 3168 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 1.569% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing.
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-04-20 | 2020/21 | 21-2812 | PO2W-210000001035 | 0 | 3024 | 202104-04:CMSIH | 2021-04-20 | 000000020181749 | 3024 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 1.498% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing.
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15596.67 | 0173756-IN | 2019-10-10 | 000000020025135 | 15596.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9061101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6628.59 | 0175538-IN | 2019-10-10 | 000000020025135 | 6628.59 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9061101 | 0.1526% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 200 | 0173756-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173756-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 380 | 0173756-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173756-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173756-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173756-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 197.88 | 0175538-IN | 2019-10-10 | 000000020025135 | 197.88 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.004555% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 161.5 | 0175538-IN | 2019-10-10 | 000000020025135 | 161.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.003717% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 85 | 0175538-IN | 2019-10-10 | 000000020025135 | 85 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.001956% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 544.51 | 0175538-IN | 2019-10-10 | 000000020025135 | 544.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.01253% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 51 | 0175538-IN | 2019-10-10 | 000000020025135 | 51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.001174% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 25.5 | 0175538-IN | 2019-10-10 | 000000020025135 | 25.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.0005869% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 89680.91 | 0175097-IN | 2019-10-10 | 000000020025132 | 89680.91 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9061101 | 3.197% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 345 | 0175097-IN | 2019-10-10 | 000000020025132 | 345 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.0123% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 690 | 0175097-IN | 2019-10-10 | 000000020025132 | 690 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.02459% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1150 | 0175097-IN | 2019-10-10 | 000000020025132 | 1150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.04099% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2185 | 0175097-IN | 2019-10-10 | 000000020025132 | 2185 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.07788% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2677.2 | 0175097-IN | 2019-10-10 | 000000020025132 | 2677.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.09543% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7366.9 | 0175097-IN | 2019-10-10 | 000000020025132 | 7366.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.2626% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 2612.53 | 0175076-IN | 2019-10-08 | 000000020023867 | 2612.53 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9061101 | 0.3292% | Ergotron Zip40 Charging carts to store laptops at Del Valle. Total carts: 16
Del Valle-21st Century-Technology | 7 | Technology | Del Valle | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 18287.65 | 0175099-IN | 2019-10-08 | 000000020023867 | 18287.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9061101 | 2.305% | Ergotron Zip40 Charging carts to store laptops at Del Valle. Total carts: 16
Del Valle-21st Century-Contractor | 7 | Contractor | Del Valle | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 6372.24 | Pay app #3 | 2020-12-08 | 000000020148205 | 6372.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061101 | 1.415% | Prep & install Mohawk LVT, walk off mat & base at Del Valle for room #12
Del Valle-21st Century-Contractor | 7 | Contractor | Del Valle | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2020-11-30 | 2020/21 | 21-1830 | PO2W-210000000725 | 0 | 42500 | 2020-086AD | 2020-11-30 | 000000020145591 | 42500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061101 | 100% | Demo of ceiling tiles in 17 classrooms at Del Valle
Del Valle-21st Century-FF & E | 7 | FF & E | Del Valle | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 27193.65 | 3207761219 | 2020-02-03 | 000000020065147 | 27193.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9061101 | 6.319% | Furniture for Del Valle - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Del Valle-21st Century-FF & E | 7 | FF & E | Del Valle | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 14247.57 | 3207761219 | 2020-02-03 | 000000020065147 | 14247.57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9061101 | 3.311% | Furniture for Del Valle - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Del Valle-21st Century-Environ Consultant | 7 | Environ Consultant | Del Valle | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10240 | PO2W-200000005318 | 0 | 2600 | MCSI-4536 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9061101 | 100% | Asbestos & lead-based paint survey of Del Valle's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Del Valle-Ceiling replacement-Contractor | 7 | Contractor | Del Valle | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 31652.38 | Pay app #1 | 2019-12-17 | 000000020049998 | 31652.38 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061105 | 0.6921% | Ceiling replacement for Del Valle.
Del Valle-Ceiling replacement-Contractor | 7 | Contractor | Del Valle | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 94957.16 | Pay app #2 | 2020-10-21 | 000000020136454 | 94957.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061105 | 2.076% | Ceiling replacement for Del Valle.
Del Valle-Ceiling replacement-Contractor | 7 | Contractor | Del Valle | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 189914.31 | Pay app #3 | 2021-01-08 | 000000020155354 | 189914.31 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061105 | 4.153% | Ceiling replacement for Del Valle.
Del Valle-Ceiling replacement-Contractor | 7 | Contractor | Del Valle | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5060 | PO1-200000000729 | 16659.15 | 16659.15 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061105 | 0% | Ceiling replacement for Del Valle.
Del Valle-Fire alarm-DSA Fees | 7 | DSA Fees | Del Valle | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 870 | Per email | 2021-03-30 | 000000020176203 | 870 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9061103 | 12.26% | DSA plan check review fee for Del Valle fire alarm.
Del Valle-Fire alarm-Design | 7 | Design | Del Valle | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28228 | 2021-02-05 | 000000020162584 | 7275 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle.
Del Valle-Fire alarm-Design | 7 | Design | Del Valle | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28289 | 2021-02-09 | 000000020163360 | 7275 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle.
Del Valle-Fire alarm-Design | 7 | Design | Del Valle | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28385 | 2021-03-24 | 000000020174735 | 7275 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle.
Del Valle-Fire alarm-Design | 7 | Design | Del Valle | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28514 | 2021-05-26 | 000000020192536 | 2425 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle.
Del Valle-Fire alarm-Design | 7 | Design | Del Valle | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28608 | 2021-05-26 | 000000020192536 | 9700 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle.
Del Valle-Fire alarm-Design | 7 | Design | Del Valle | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28684 | 2021-06-23 | 000000020200466 | 1455 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0.3731% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle.
Del Valle-Fire alarm-Design | 7 | Design | Del Valle | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28833 | 2021-09-09 | 000000020255227 | 970 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0.2487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle.
Del Valle-Fire alarm-Design | 7 | Design | Del Valle | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2025-10-20 | 2021/22 | 21-2535 | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle.
Dibble-21st Century-Environ Consultant | 0 | Environ Consultant | Dibble | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 2020/21 | 21-1573 | PO1-210000000427 | 0 | 2700 | MCSI-4625 | 2020-10-20 | 000000020136035 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 7451101 | 6.553% | Asbestos & lead-based paint survey of Dibble's permanent buildings.
District Office-21st Century-Reprographics | 0 | Reprographics | District Office | 21st Century | ARC Document Solutions | Scanning/printing | 2019-05-13 | 2019-06-03 | 2018/19 |  | 19-109342 | 0 | 229.19 | 10193793 | 2019-06-03 | 25329661 | 229.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 100% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for the District office. Close-out PO.
District Office-21st Century-Reprographics | 0 | Reprographics | District Office | 21st Century | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2023-01-16 | 2021/22 | 21-2247 | PO1-210000000492 | 4037.85 | 4037.85 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for the District office.
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 16690.22 | 0174219-IN | 2019-10-10 | 000000020025135 | 16690.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 0.3842% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 215 | 0174219-IN | 2019-10-10 | 000000020025135 | 215 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.004949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 129 | 0174219-IN | 2019-10-10 | 000000020025135 | 129 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.002969% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 408.5 | 0174219-IN | 2019-10-10 | 000000020025135 | 408.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.009402% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 500.52 | 0174219-IN | 2019-10-10 | 000000020025135 | 500.52 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.01152% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1377.29 | 0174219-IN | 2019-10-10 | 000000020025135 | 1377.29 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.0317% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 64.5 | 0174219-IN | 2019-10-10 | 000000020025135 | 64.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.001485% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2020-02-07 | 2020-03-06 | 2019/20 |  | PO2W-200000004388 | 0 | 1164.44 | 0178870-IN | 2020-03-06 | 000000020078467 | 1164.44 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 43.14% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 6
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2020-02-07 | 2020-03-06 | 2019/20 |  | PO2W-200000004388 | 0 | 185.01 | 0178870-IN | 2020-03-06 | 000000020078467 | 185.01 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 6.855% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 6
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2020-02-07 | 2020-04-23 | 2019/20 | 2-7716 | PO2W-200000004388 | 0 | 1164.43 | 0181588-IN | 2020-04-23 | 000000020091968 | 1164.43 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 43.14% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 6
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2020-02-07 | 2020-04-23 | 2019/20 | 2-7716 | PO2W-200000004388 | 0 | 185.02 | 0181588-IN | 2020-04-23 | 000000020091968 | 185.02 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 6.855% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 6
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 37650.03 | 0176668-IN | 2019-11-21 | 000000020040910 | 37650.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 1.342% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 145.5 | 0176668-IN | 2019-11-21 | 000000020040910 | 145.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.005186% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 291 | 0176668-IN | 2019-11-21 | 000000020040910 | 291 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.01037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 485 | 0176668-IN | 2019-11-21 | 000000020040910 | 485 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.01729% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 921.5 | 0176668-IN | 2019-11-21 | 000000020040910 | 921.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.03285% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1129.08 | 0176668-IN | 2019-11-21 | 000000020040910 | 1129.08 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.04024% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 3106.91 | 0176668-IN | 2019-11-21 | 000000020040910 | 3106.91 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.1107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 13475.07 | TGH9705 | 2019-10-04 | 000000020022968 | 13475.07 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 3.657% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 11454.58 | TGH9705 | 2019-10-04 | 000000020022968 | 11454.58 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 3.108% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 9432.55 | TPH9179 | 2019-10-04 | 000000020022968 | 9432.55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 2.56% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 8316 | TGJ0727 | 2019-10-04 | 000000020022968 | 8316 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 2.257% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 13611.22 | TGJ0727 | 2019-10-04 | 000000020022968 | 13611.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 3.694% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 16.2 | TGQ7072 | 2019-10-04 | 000000020022968 | 16.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.004396% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 16.2 | TGQ7072 | 2019-10-04 | 000000020022968 | 16.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.004396% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 16.2 | TGQ7072 | 2019-10-04 | 000000020022968 | 16.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.004396% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 23.4 | TGQ7072 | 2019-10-04 | 000000020022968 | 23.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.00635% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 91.8 | TGQ7072 | 2019-10-04 | 000000020022968 | 91.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.02491% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 6.3 | TGQ7072 | 2019-10-04 | 000000020022968 | 6.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.00171% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 67375.35 | TGG6297 | 2019-10-08 | 000000020023870 | 67375.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 18.28% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 6132 | TGG6297 | 2019-10-08 | 000000020023870 | 6132 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 1.664% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 194041.01 | TLW3515 | 2019-10-08 | 000000020023870 | 194041.01 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 52.65% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 37730.2 | TMH3476 | 2019-10-08 | 000000020023870 | 37730.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 10.24% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 63 | TLW3515 | 2019-10-08 | 000000020023870 | 63 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.0171% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 6716.35 | TLW3515 | 2019-10-08 | 000000020023870 | 6716.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 1.823% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2020-06-17 | 2019/20 |  | PO2W-200000004768 | 0 | 55307.63 | 29473 | 2020-06-17 | 000000020106116 | 55307.63 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 8.965% | Furniture for 36 classrooms - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2020-06-17 | 2019/20 |  | PO2W-200000004768 | 0 | 21087.13 | 29473 | 2020-06-17 | 000000020106116 | 21087.13 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 3.418% | Furniture for 36 classrooms - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000761 | 0 | 3840 | 81350 | 2020-01-14 | 000000020057268 | 3840 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0.8533% | Construction management services for the District's bond projects as needed
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000761 | 0 | 14560 | 82274 | 2020-04-01 | 000000020085958 | 14560 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 3.236% | Construction management services for the District's bond projects as needed
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000761 | 0 | 12640 | 83069 | 2020-04-01 | 000000020085958 | 12640 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.809% | Construction management services for the District's bond projects as needed
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000761 | 0 | 11535 | 84568 | 2020-04-15 | 000000020089466 | 11535 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.563% | Construction management services for the District's bond projects as needed
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000761 | 0 | 12325 | 85325 | 2020-05-28 | 000000020100719 | 12325 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.739% | Construction management services for the District's bond projects as needed
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000761 | 0 | 11885 | 86424 | 2020-06-17 | 000000020106117 | 11885 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.641% | Construction management services for the District's bond projects as needed
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000761 | 0 | 22090 | 86866 | 2020-07-27 | 000000020116270 | 22090 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 4.909% | Construction management services for the District's bond projects as needed
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000761 | 0 | 18080 | 88481 | 2020-08-17 | 000000020119773 | 18080 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 4.018% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000761 | 0 | 19265 | 89360 | 2020-10-13 | 000000020134067 | 19265 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 4.281% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000761 | 0 | 14080 | 90127 | 2020-10-20 | 000000020136025 | 14080 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 3.129% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-17 | 2020/21 |  | PO1-200000000761 | 0 | 23495 | 90702 | 2020-12-17 | 000000020151520 | 23495 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 5.221% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-17 | 2020/21 |  | PO1-200000000761 | 0 | 23450 | 91823 | 2020-12-17 | 000000020151520 | 23450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 5.211% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000761 | 0 | 27150 | 92822 | 2021-02-08 | 000000020162981 | 27150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 6.033% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000761 | 0 | 34605 | 94013 | 2021-04-05 | 000000020177572 | 34605 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 7.69% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000761 | 0 | 38455 | 94920 | 2021-04-16 | 000000020181024 | 38455 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 8.546% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-07 | 2020/21 |  | PO1-200000000761 | 0 | 46550 | 95725 | 2021-05-07 | 000000020187158 | 46550 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 10.34% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000761 | 0 | 41875 | 96938 | 2021-05-25 | 000000020192064 | 41875 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 9.306% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000761 | 0 | 37625 | 98319 | 2021-06-22 | 000000020200048 | 37625 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 8.361% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-08 | 2021/22 |  | PO1-200000000761 | 0 | 11520 | 100272 | 2021-09-08 | 000000020253624 | 11520 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.56% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000761 | 0 | 24960 | 98429 | 2021-09-09 | 000000020255187 | 24960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 5.547% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4696 | PO1-200000000761 | 15 | 15 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2022-02-09 | 2022-02-28 | 2021/22 |  | PO1-220000000675 | 0 | 25600 | 107249 | 2022-02-28 | 000000020430482 | 25600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 8.533% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2022-02-09 | 2022-03-15 | 2021/22 |  | PO1-220000000675 | 0 | 25320 | 108242 | 2022-03-15 | 000000020443751 | 25320 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 8.44% | Construction management services for the District's bond projects as needed.
District Office-21st Century-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2022-02-09 | 2026-02-09 | 2021/22 | 22-4584 | PO1-220000000675 | 249080 | 249080 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Construction management services for the District's bond projects as needed.
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 2019/20 | 2-7592 | PO2W-200000004016 | 0 | 949.34 | EPS6017-2020 | 2020-04-22 | 000000020091373 | 949.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 50.33% | Covered vinyl tack boards (46" x 96") as sample for District. Each panel will be wrapped on 4 sides, no trim. Total tack boards for this PO: 8
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 2019/20 |  | PO2W-200000004016 | 0 | 264.04 | EPS6017-2020 | 2020-04-22 | 000000020091373 | 264.04 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 14% | Covered vinyl tack boards (46" x 96") as sample for District. Each panel will be wrapped on 4 sides, no trim. Total tack boards for this PO: 8
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 2019/20 |  | PO2W-200000004016 | 0 | 336.49 | EPS6017-2020 | 2020-04-22 | 000000020091373 | 336.49 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 17.84% | Covered vinyl tack boards (46" x 96") as sample for District. Each panel will be wrapped on 4 sides, no trim. Total tack boards for this PO: 8
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 2019/20 |  | PO2W-200000004016 | 0 | 336.49 | EPS6017-2020 | 2020-04-22 | 000000020091373 | 336.49 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 17.84% | Covered vinyl tack boards (46" x 96") as sample for District. Each panel will be wrapped on 4 sides, no trim. Total tack boards for this PO: 8
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2017-07-11 | 2017-12-19 | 2017/18 |  | 18-104648 | 0 | 1064 | 54830-3 | 2017-12-19 | 24246702 | 1064 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 100% | Legal services for the bond projects. Close-out PO.
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2018-07-11 | 2019-04-09 | 2018/19 |  | 19-100300 | 0 | 2375 | 62570-4 | 2019-04-09 | 25217951 | 2375 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 100% | Legal services for the bond projects. Close-out PO.
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-01-03 | 2019/20 |  | PO1-200000000812 | 0 | 7283.51 | 179385-5 | 2020-01-03 | 000000020053868 | 7283.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 36.42% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-01-08 | 2019/20 |  | PO1-200000000812 | 0 | 2112.68 | 178377-4 | 2020-01-08 | 000000020055186 | 2112.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 10.56% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-01-13 | 2019/20 |  | PO1-200000000812 | 0 | 10128 | 179785-4 | 2020-01-13 | 000000020056662 | 10128 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 50.64% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-03-03 | 2019/20 |  | PO1-200000000812 | 0 | 31.62 | 181255-3 | 2020-03-03 | 000000020076553 | 31.62 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0.1581% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-04-29 | 2019/20 | 2-6047 | PO1-200000000812 | -5.1159e-13 | 444.19 | 180616-2 | 2020-04-29 | 000000020093273 | 444.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 2.221% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2020-04-29 | 2019/20 |  | PO1-200000001126 | 0 | 6906.81 | 180616-2 | 2020-04-29 | 000000020093273 | 6906.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 100% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2020-06-30 | 2019/20 |  | PO1-200000001126 | 0 | 13093.19 |  |  |  | 13093.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 65.47% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2020-07-01 | 2020/21 |  | PO1-200000001126 | 0 | -13093.19 |  |  |  | -13093.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | -65.47% | Legal services for the bond projects. Reverse accrual from prior year
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2020-07-02 | 2020/21 |  | PO1-200000001126 | 13093.19 | 13093.19 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2021-06-30 | 2020/21 | 2-9052 | PO1-200000001126 | -13093.19 | -13093.19 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Close-out PO.
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2021-12-14 | 2021/22 |  | PO1-210000000260 | 0 | 1417.5 | 196338-1 | 2021-12-14 | 000000020360176 | 1417.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 2.835% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2021-12-23 | 2021/22 |  | PO1-210000000260 | 0 | 1799.5 | 197570-1 | 2021-12-23 | 000000020374043 | 1799.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 3.599% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2022-01-24 | 2021/22 |  | PO1-210000000260 | 0 | 5735 | 195670-4 | 2022-01-24 | 000000020395774 | 5735 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 11.47% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2022-01-28 | 2021/22 |  | PO1-210000000260 | 0 | 3513 | 197728-4 | 2022-01-28 | 000000020401406 | 3513 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 7.026% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2022-03-02 | 2021/22 |  | PO1-210000000260 | 0 | 2612.5 | 198458-2 | 2022-03-02 | 000000020432785 | 2612.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 5.225% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2022-07-31 | 2021/22 | 21-192 | PO1-210000000260 | 34922.5 | 34922.5 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-07-11 | 2019-08-21 | 2019/20 |  | PO2W-200000000134 | 0 | 90 | 64515-4 | 2019-08-21 | 000000020006819 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0.9% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-07-11 | 2019-08-28 | 2019/20 |  | PO2W-200000000134 | 0 | 3235 | 64302-2 | 2019-08-28 | 000000020008961 | 3235 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 32.35% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-07-11 | 2019-09-18 | 2019/20 |  | PO2W-200000000134 | 0 | 1387.5 | 176791-5 | 2019-09-18 | 000000020016440 | 1387.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 13.88% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-07-11 | 2020-01-03 | 2019/20 | 2-99 | PO2W-200000000134 | 0 | 5287.5 | 179385-5 | 2020-01-03 | 000000020053868 | 5287.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 52.88% | Legal services for the bond projects
District Office-21st Century-Contractor | 0 | Contractor | District Office | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-05-07 | 2019/20 |  | PO2W-200000004391 | 0 | 259042.4 | Pay app #1 | 2020-05-07 | 000000020095892 | 259042.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9851100 | 57.54% | Supply 38,400 SF Mohawk LVT and bond for District-wide use (30 classrooms)
District Office-21st Century-Contractor | 0 | Contractor | District Office | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2025-07-31 | 2021/22 | 2-8416 | PO2W-200000004391 | 19116.72 | 19116.72 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9851100 | 0% | Provide and install 38,400 SF Mohawk LVT. Supply & install 5,040 IF 4" rubber base, demo 4,266 sy carpet, prepare concrete. Supply & install 252 yd First step Up II for District's 30 classrooms.
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Global Industrial | Scissor lift | 2021-05-18 | 2021-06-03 | 2020/21 | 21-6450 | PO3W-210000002747 | 0 | 1665.5 | 117699325 | 2021-06-03 | 000000020194623 | 1665.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 100% | A Pneumatic-Hydraullic Mobile Scissor Lift Table AIR-800-D. 800 lb. capacity for District-wide use
District Office-21st Century-Technology | 0 | Technology | District Office | 21st Century | Home Depot | Hardware to install access point for classrooms | 2020-05-18 | 2020-06-17 | 2019/20 | 2-10194 | PO1-200000001148 | 0 | 198.23 | 8010077 | 2020-06-17 | 000000020106127 | 198.23 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 100% | Hardware to install access point for classrooms-Shelf brackets, screws, and drill bits for District-wide use
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Megaphone Ink | Decal | 2022-01-06 | 2022-01-24 | 2021/22 | 22-3836 | PO2W-220000001278 | 0 | 455.52 | 318278 | 2022-01-24 | 000000020395761 | 455.52 |  |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9851100 | 100% | 8 Decal for sign (46" x 30") for District Office
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-03-04 | 2019/20 |  | PO1-200000001027 | 0 | 4647.5 | 89592 | 2020-03-04 | 000000020077144 | 4647.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 53.22% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-04-07 | 2019/20 |  | PO1-200000001027 | 0 | 2286.63 | 89866 | 2020-04-07 | 000000020087145 | 2286.63 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 26.18% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-04-22 | 2019/20 |  | PO1-200000001027 | 0 | 1799 | 90267 | 2020-04-22 | 000000020091403 | 1799 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 20.6% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-06-30 | 2019/20 |  | PO1-200000001027 | 0 | 1266.87 |  |  |  | 1266.87 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 14.51% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-07-01 | 2020/21 |  | PO1-200000001027 | 0 | -1266.87 |  |  |  | -1266.87 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | -14.51% | Legal services for the bond projects. Reverse accrual from prior year
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-07-02 | 2020/21 |  | PO1-200000001027 | 1266.87 | 1266.87 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2021-06-30 | 2020/21 | 2-8365 | PO1-200000001027 | -1266.87 | -1266.87 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Close-out PO.
District Office-21st Century-Legal services | 0 | Legal services | District Office | 21st Century | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-01-29 | 2020-02-27 | 2019/20 | 2-7525 | PO2W-200000004282 | 0 | 3492.5 | 89468 | 2020-02-27 | 000000020074745 | 3492.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 100% | Legal services for the bond projects
District Office-21st Century-Advertisement | 0 | Advertisement | District Office | 21st Century | San Gabriel Tribune | Newspaper Advertisement | 2020-08-11 | 2020-10-22 | 2020/21 | 21-1254 | PO2W-210000000381 | 0 | 632 | 11403899 | 2020-10-22 | 000000020136840 | 632 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9851100 | 100% | Advertising seeking prequalification for contractors interested in bidding upcoming District's 21st Century modernization projects. Publication dates: 08/13/20 & 08/18/20
District Office-21st Century-Advertisement | 0 | Advertisement | District Office | 21st Century | Southern California News Group | Newspaper Advertisement | 2022-03-15 | 2023-03-15 | 2021/22 | 22-5575 |  | 611.25 | 611.25 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9851100 | 0% | Advertising seeking prequalification for contractors interested in bidding upcoming 21st Century modernization projects. Publication dates: 03/09/22 & 03/16/22
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Uline | Carts | 2020-12-01 | 2020-12-08 | 2020/21 | 21-3309 | PO3W-210000001074 | 0 | 791.69 | 127489647 | 2020-12-08 | 000000020148246 | 791.69 |  |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9851100 | 100% | Drywall cart - 23"x50" & Adjustable panel truck - 30"x60" for District-wide use. Total carts: 2.
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Uline | Hydraulic stacker | 2021-05-27 | 2021-06-04 | 2020/21 | 21-6552 | PO3W-210000002899 | 0 | 1834.13 | 134374802 | 2021-06-04 | 000000020195024 | 1834.13 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 100% | A hydraulic stacker for District-wide use
District Office-21st Century-FF & E | 0 | FF & E | District Office | 21st Century | Uline | Hydraulic stacker | 2021-06-08 | 2021-06-15 | 2020/21 | 21-6760 | PO3W-210000002998 | 0 | 1834.13 | 134874288 | 2021-06-15 | 000000020198046 | 1834.13 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 100% | A hydraulic stacker for District-wide use
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Avia Communications, Inc. | Printing & posting of POS/Os | 2017-07-11 | 2017-07-11 | 2017/18 |  | N/A | 0 | 1350.74 |  |  |  | 1350.74 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Printing & posting of POS/Os, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | California Municipal Statistics, Inc. | Demographic data | 2017-07-11 | 2017-07-11 | 2017/18 |  | N/A | 0 | 1700 |  |  |  | 1700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Demographic data, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Fitch Ratings, Inc. | Rating Agency Fee | 2017-08-03 | 2017-08-03 | 2017/18 |  | N/A | 0 | 45000 |  |  |  | 45000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Rating Agency Fee, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Hawkins Delafield & Wood LLP | Bond Counsel and Disclosure Counsel Fees | 2017-07-11 | 2017-07-11 | 2017/18 |  | N/A | 0 | 115000 |  |  |  | 115000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Bond Counsel and Disclosure Counsel Fees, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | LACOE | Remaining funds-dep. into District's debt service fund & close acct. | 2017-12-14 | 2017-12-14 | 2017/18 |  | N/A | 0 | 11211.58 |  |  |  | 11211.58 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Remaining funds-dep. into District's debt service fund & close acct., 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Montague DeRose and Associates, LLC | Municipal Advisory services | 2017-07-12 | 2017-07-12 | 2017/18 |  | N/A | 0 | 240 |  |  |  | 240 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 0.5615% | Municipal Advisory services, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Montague DeRose and Associates, LLC | Municipal Advisory services | 2017-07-12 | 2017-07-12 | 2017/18 |  | N/A | 0 | 42500 |  |  |  | 42500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 99.44% | Municipal Advisory services, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Moody's Investors Service, Inc. | Rating Agency Fee | 2017-07-31 | 2017-07-31 | 2017/18 |  | N/A | 0 | 37000 |  |  |  | 37000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Rating Agency Fee, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Rbc Capital Markets, LLC | Hotel reimb. during rating agency presentations in San Francisco | 2017-07-11 | 2017-07-11 | 2017/18 |  | N/A | 0 | 647.68 |  |  |  | 647.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Hotel reimb. during rating agency presentations in San Francisco, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Rbc Capital Markets, LLC | Reimb. Continuing Disclosure Report (DAC) | 2017-08-04 | 2017-08-04 | 2017/18 |  | N/A | 0 | 550 |  |  |  | 550 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Reimb. Continuing Disclosure Report (DAC), 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | S&P Global Ratings | Rating Agency Fee | 2017-08-03 | 2017-08-03 | 2017/18 |  | N/A | 0 | 35000 |  |  |  | 35000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Rating Agency Fee, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | U.S. Bank National Association | Trust fees | 2017-07-12 | 2017-07-12 | 2017/18 |  | N/A | 0 | 550 |  |  |  | 550 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Trust fees, 18-KT005
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Underwriter's fees | Underwriter's fees | 2017-07-12 | 2017-07-12 | 2019/20 |  | N/A | 0 | 175000 |  |  |  | 175000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Underwriter's fees, JVA21*384
District Office-Design guidelines-Design | 0 | Design | District Office | Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2018-09-17 | 2018/19 |  | PO2W-200000001205, 19-100491, 18-109571 | 0 | 16080 | 966301 | 2018-09-17 | 24789789 | 16080 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9851100 | 67% | Architect - Create design guidelines to serve as a set of guiding principles for District's 21st Century classroom projects.
District Office-Design guidelines-Design | 0 | Design | District Office | Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2018-10-19 | 2018/19 |  | PO2W-200000001205, 19-100491, 18-109571 | 0 | 6720 | 966422 | 2018-10-19 | 24871020 | 6720 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9851100 | 28% | Architect - Create design guidelines to serve as a set of guiding principles for District's 21st Century classroom projects.
District Office-Design guidelines-Design | 0 | Design | District Office | Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2021-06-02 | 2020/21 | 2-514 | PO2W-200000001205, 19-100491, 18-109571 | 0 | 1200 | 969692 | 2021-06-02 | 000000020194098 | 1200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9851100 | 5% | Architect - Create design guidelines to serve as a set of guiding principles for District's 21st Century classroom projects.
District Office-Design guidelines-Design | 0 | Design | District Office | Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2023-01-16 | 2021/22 | 2-516 | PO2W-200000001206, 19-103806 | 5500 | 5500 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9851100 | 0% | Architect - Additional services to create design guidelines to serve as a set of guiding principles for District's 21st Century classroom projects.
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15596.67 | 0173446-IN | 2019-10-10 | 000000020025135 | 15596.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15206.76 | 0175539-IN | 2019-10-10 | 000000020025135 | 15206.76 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 0.35% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 200 | 0173446-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173446-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 380 | 0173446-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173446-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173446-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173446-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 195 | 0175539-IN | 2019-10-10 | 000000020025135 | 195 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.004488% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 117 | 0175539-IN | 2019-10-10 | 000000020025135 | 117 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.002693% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 370.5 | 0175539-IN | 2019-10-10 | 000000020025135 | 370.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.008528% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 453.96 | 0175539-IN | 2019-10-10 | 000000020025135 | 453.96 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.01045% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1249.17 | 0175539-IN | 2019-10-10 | 000000020025135 | 1249.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.02875% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 58.5 | 0175539-IN | 2019-10-10 | 000000020025135 | 58.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.001346% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 17546.27 | 0173770-IN | 2019-10-21 | 000000020028933 | 17546.27 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 0.4039% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 135 | 0173770-IN | 2019-10-21 | 000000020028933 | 135 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.003107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 67.5 | 0173770-IN | 2019-10-21 | 000000020028933 | 67.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.001554% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 225 | 0173770-IN | 2019-10-21 | 000000020028933 | 225 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 427.5 | 0173770-IN | 2019-10-21 | 000000020028933 | 427.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.00984% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 523.8 | 0173770-IN | 2019-10-21 | 000000020028933 | 523.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.01206% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1441.35 | 0173770-IN | 2019-10-21 | 000000020028933 | 1441.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.03318% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 298286.51 | 0175159-IN | 2019-10-22 | 000000020029495 | 298286.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 10.63% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1147.5 | 0175159-IN | 2019-10-22 | 000000020029495 | 1147.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.0409% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2295 | 0175159-IN | 2019-10-22 | 000000020029495 | 2295 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.0818% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 3825 | 0175159-IN | 2019-10-22 | 000000020029495 | 3825 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.1363% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7267.5 | 0175159-IN | 2019-10-22 | 000000020029495 | 7267.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.259% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 8904.6 | 0175159-IN | 2019-10-22 | 000000020029495 | 8904.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.3174% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 24502.95 | 0175159-IN | 2019-10-22 | 000000020029495 | 24502.95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.8734% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1306.26 | 0173475-IN | 2019-09-23 | 000000020017958 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at Fairgrove. Total cart: 1
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 43106.72 | 0175372-IN | 2019-10-11 | 000000020025716 | 43106.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | 5.432% | Ergotron Zip40 Charging carts to store laptops at Fairgrove. Total carts: 35
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 2612.53 | 0175124-IN | 2019-10-15 | 000000020026572 | 2612.53 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | 0.3292% | Ergotron Zip40 Charging carts to store laptops at Fairgrove. Total carts: 35
Fairgrove-21st Century-Technology | 4 | Technology | Fairgrove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | -0.1 | 0175372-IN | 2019-10-15 | 000000020026572 | -0.1 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | -1.26e-05% | Ergotron Zip40 Charging carts to store laptops at Fairgrove. Total carts: 35. To offset over payment of $0.10 on invoice #175372
Fairgrove-21st Century-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 1440 | 100653 | 2021-09-08 | 000000020253624 | 1440 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 0.07872% | Construction management services for Fairgrove - phase 3 & 4. This PO includes allowances of $40,000.00
Fairgrove-21st Century-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 5120 | 101514 | 2021-09-29 | 000000020275054 | 5120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 0.2799% | Construction management services for Fairgrove - phase 3 & 4. This PO includes allowances of $40,000.00
Fairgrove-21st Century-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2024-07-01 | 2021/22 | 22-1057 | PO1-220000000334 | 400194 | 400194 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 0% | Construction management services for Fairgrove - phase 3 & 4. This PO includes allowances of $40,000.00
Fairgrove-21st Century-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862 | 0 | 6450 | 102578 | 2021-11-08 | 000000020325325 | 6450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 13.16% | Construction management services for Baldwin - phase 3 & 4. This PO is to pay invoice #102578 (Prof service from 09/01-09/30/21), dated 09/30/21
Fairgrove-21st Century-FF & E | 4 | FF & E | Fairgrove | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 27193.64 | 3207761219 | 2020-02-03 | 000000020065147 | 27193.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 6.319% | Furniture for Fairgrove - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Fairgrove-21st Century-FF & E | 4 | FF & E | Fairgrove | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 14247.57 | 3207761219 | 2020-02-03 | 000000020065147 | 14247.57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | 3.311% | Furniture for Fairgrove - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Fairgrove-21st Century-Environ Consultant | 4 | Environ Consultant | Fairgrove | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1575 | PO1-210000000427 | 0 | 2700 | MCSI-4606 | 2020-10-13 | 000000020134092 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9091101 | 6.553% | Asbestos & lead-based paint survey of Fairgrove's permanent buildings.
Fairgrove-21st Century-Design | 4 | Design | Fairgrove | 21st Century | PBK Architects | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6230 | PO1-210000000684 | 407500 | 407500 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091101 | 0% | Architect - Provide architectural/engineering services for the Fairgrove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Fairgrove.
Fairgrove-Drinking fountain replacement-DSA Inspection | 4 | DSA Inspection | Fairgrove | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6601 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9091104 | 0% | General inspection for the project as defined in Title 24 at Fairgrove. Replacement of 3-exterior drinking fountains
Fairgrove-Fire Alarm-DSA Fees | 4 | DSA Fees | Fairgrove | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3174 | PO2W-200000001056 | 0 | 1230 | Per email | 2019-09-13 | 000000020015010 | 1230 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9091103 | 100% | DSA plan check review fee for Fairgrove fire alarm.
Fairgrove-Fire alarm-Design | 4 | Design | Fairgrove | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28383 | 2021-03-24 | 000000020174735 | 2425 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The total architect contract for Fairgrove FA is $48,500.00
Fairgrove-Fire alarm-Design | 4 | Design | Fairgrove | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28470 | 2021-03-24 | 000000020174735 | 2425 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The total architect contract for Fairgrove FA is $48,500.00
Fairgrove-Fire alarm-Design | 4 | Design | Fairgrove | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28520 | 2021-05-26 | 000000020192536 | 2425 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The total architect contract for Fairgrove FA is $48,500.00
Fairgrove-Fire alarm-Design | 4 | Design | Fairgrove | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28614 | 2021-05-26 | 000000020192536 | 2425 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The total architect contract for Fairgrove FA is $48,500.00
Fairgrove-Fire alarm-Design | 4 | Design | Fairgrove | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1455 | 28735 | 2021-09-09 | 000000020255226 | 1455 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 0.8491% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The total architect contract for Fairgrove FA is $48,500.00
Fairgrove-Fire alarm-Design | 4 | Design | Fairgrove | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 2021/22 | 21-1992 | PO2W-210000000680 | 970 | 970 |  |  |  | 0 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The total architect contract for Fairgrove FA is $48,500.00
Fairgrove-Fire Alarm-DSA Inspection | 4 | DSA Inspection | Fairgrove | Fire Alarm | Team Inspections | General inspection | 2021-01-14 | 2021-10-19 | 2021/22 | 21-3784 | PO2W-210000001585 | 0 | 14350 | 202110-04:FFA | 2021-10-19 | 000000020302605 | 14350 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9091103 | 50% | General inspection for the project as defined in Title 24 at Fairgrove. Alterations to fire alarm system
Fairgrove-Fire Alarm-Contractor | 4 | Contractor | Fairgrove | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-03-18 | 2020/21 |  | PO2W-200000004930 | 0 | 301327.64 | Pay app #1 | 2021-03-18 | 000000020173348 | 301327.64 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 79.56% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project cost with change order is $395,460.03
Fairgrove-Fire Alarm-Contractor | 4 | Contractor | Fairgrove | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-05-21 | 2020/21 |  | PO2W-200000004930 | 0 | 31047.52 | Pay app #2 | 2021-05-21 | 000000020191188 | 31047.52 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 8.198% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project cost with change order is $395,460.03
Fairgrove-Fire Alarm-Contractor | 4 | Contractor | Fairgrove | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-05-21 | 2020/21 |  | PO2W-200000004930 | 0 | 21777.19 | Pay app #3 | 2021-05-21 | 000000020191188 | 21777.19 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 5.75% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project cost with change order is $395,460.03
Fairgrove-Fire Alarm-Contractor | 4 | Contractor | Fairgrove | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-11-05 | 2021/22 |  | PO2W-200000004930 | 0 | 21534.68 | Pay app #4 | 2021-11-05 | 000000020324297 | 21534.68 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 5.686% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project cost with change order is $395,460.03
Fairgrove-Fire Alarm-Contractor | 4 | Contractor | Fairgrove | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2023-07-11 | 2021/22 | 2-9609 | PO2W-200000004930 | 3048.76 | 3048.76 |  |  |  | 0 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 0% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project cost with change order is $395,460.03
Fairgrove-Interim Housing-Design | 4 | Design | Fairgrove | Interim Housing | PBK Architects | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6233 | PO1-210000000686 | 95400 | 95400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091102 | 0% | Architect - Provide architectural/engineering services for the Fairgrove Interim Housing project. Sitework will be limited to ADA access & path of travel requirements to the new portables.
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10479.91 | 0175540-IN | 2019-10-10 | 000000020025135 | 10479.91 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 0.2412% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 135 | 0175540-IN | 2019-10-10 | 000000020025135 | 135 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.003107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 81 | 0175540-IN | 2019-10-10 | 000000020025135 | 81 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.001864% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 256.5 | 0175540-IN | 2019-10-10 | 000000020025135 | 256.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.005904% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 314.28 | 0175540-IN | 2019-10-10 | 000000020025135 | 314.28 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.007234% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 864.81 | 0175540-IN | 2019-10-10 | 000000020025135 | 864.81 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.01991% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 40.5 | 0175540-IN | 2019-10-10 | 000000020025135 | 40.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.0009322% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7762.89 | 0173759-IN | 2019-10-21 | 000000020028933 | 7762.89 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 0.1787% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173759-IN | 2019-10-21 | 000000020028933 | 190 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173759-IN | 2019-10-21 | 000000020028933 | 100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173759-IN | 2019-10-21 | 000000020028933 | 60 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173759-IN | 2019-10-21 | 000000020028933 | 232.8 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173759-IN | 2019-10-21 | 000000020028933 | 640.6 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173759-IN | 2019-10-21 | 000000020028933 | 30 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 196013.05 | 0175497-IN | 2019-10-22 | 000000020029495 | 196013.05 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 6.987% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 757.5 | 0175497-IN | 2019-10-22 | 000000020029495 | 757.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.027% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1515 | 0175497-IN | 2019-10-22 | 000000020029495 | 1515 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.054% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2525 | 0175497-IN | 2019-10-22 | 000000020029495 | 2525 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.09% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 4797.5 | 0175497-IN | 2019-10-22 | 000000020029495 | 4797.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.171% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5878.2 | 0175497-IN | 2019-10-22 | 000000020029495 | 5878.2 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.2095% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 16175.15 | 0175497-IN | 2019-10-22 | 000000020029495 | 16175.15 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.5765% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1300.32 | 0175125-IN | 2019-10-22 | 000000020029495 | 1300.32 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 0.1639% | Ergotron Zip40 Charging carts to store laptops at Grandview. Total carts: 18
Grandview-21st Century-Technology | 2 | Technology | Grandview | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 22105.5 | 0175546-IN | 2019-10-22 | 000000020029495 | 22105.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 2.786% | Ergotron Zip40 Charging carts to store laptops at Grandview. Total carts: 18
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 7143.75 | 80804 | 2020-01-09 | 000000020055612 | 7143.75 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.4968% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3193.75 | 80796 | 2020-01-14 | 000000020057268 | 3193.75 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2221% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8131.25 | 81699 | 2020-01-14 | 000000020057268 | 8131.25 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5655% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 7692.5 | 83068 | 2020-04-01 | 000000020085959 | 7692.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.535% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8685 | 82273 | 2020-04-01 | 000000020085960 | 8685 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.604% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 7442.5 | 84567 | 2020-04-15 | 000000020089466 | 7442.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5176% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9460 | 85320 | 2020-05-28 | 000000020100719 | 9460 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.6579% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 7020 | 86240 | 2020-06-17 | 000000020106117 | 7020 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.4882% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 3765 | 86864 | 2020-07-27 | 000000020116270 | 3765 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2618% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 12733.4 | 88480 | 2020-08-17 | 000000020119773 | 12733.4 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.8856% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 12027.42 | 89359 | 2020-10-13 | 000000020134067 | 12027.42 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.8365% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 11395.42 | 90460 | 2020-10-20 | 000000020136025 | 11395.42 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.7925% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 12697.22 | 91321 | 2020-12-18 | 000000020151933 | 12697.22 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.883% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 10977.3 | 91964 | 2020-12-18 | 000000020151933 | 10977.3 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.7634% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 11738.76 | 92821 | 2021-02-08 | 000000020162981 | 11738.76 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.8164% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 8635.01 | 94011 | 2021-04-05 | 000000020177572 | 8635.01 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.6005% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 7312.3 | 94918 | 2021-04-16 | 000000020181024 | 7312.3 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5085% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 7809.22 | 95700 | 2021-05-25 | 000000020192064 | 7809.22 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5431% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 4528.58 | 96936 | 2021-05-25 | 000000020192064 | 4528.58 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.3149% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 9920 | 97857R1 | 2021-06-22 | 000000020200048 | 9920 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.6899% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-08 | 2021/22 |  | PO1-200000000640 | 0 | 4160 | 100426 | 2021-09-08 | 000000020253624 | 4160 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2893% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000640 | 0 | 6240 | 98430 | 2021-09-09 | 000000020255187 | 6240 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.434% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-03-15 | 2021/22 |  | PO1-200000000640 | 0 | 4086.62 | 108239 | 2022-03-15 | 000000020443751 | 4086.62 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2842% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4694 | PO1-200000000640 | 7410 | 7410 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00
Grandview-21st Century-DSA Fees | 2 | DSA Fees | Grandview | 21st Century | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 2020/21 | 21-3752 | PO2W-210000001571 | 0 | 35235.88 | Per email | 2021-01-20 | 000000020157908 | 35235.88 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9121101 | 61.28% | DSA plan check review fee for Grandview 21st Century.
Grandview-21st Century-FF & E | 2 | FF & E | Grandview | 21st Century | Education Products & Services | White board(s) | 2019-09-16 | 2019-09-25 | 2019/20 | 2-923 | PO2W-200000000102 | 0 | 1464.78 | EPS6083-2019 | 2019-09-25 | 000000020019023 | 1464.78 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 100% | Da-Lite IDEA Panoramic white board 16 x 10 format with panoramic screen surface for Grandview's room #61.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2018-07-24 | 2017/18 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2800 | 965679 | 2018-07-24 | 24699522 | 2800 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.564% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2019-02-19 | 2018/19 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 10110 | 967398R | 2019-02-19 | 25105194 | 10110 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 5.648% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. Allowances for site survey (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $27,331.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2019-09-16 | 2018/19 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 15400 | 968553R | 2019-09-16 | 000000020015463 | 15400 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 8.603% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2020-02-13 | 2019/20 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 19600 | 970824 | 2020-02-13 | 000000020070049 | 19600 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 10.95% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2020-06-04 | 2019/20 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 23100 | 971442 | 2020-06-04 | 000000020102538 | 23100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 12.91% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2020-12-08 | 2020/21 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 17221 | 971453R | 2020-12-08 | 000000020148211 | 17221 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 9.621% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. Allowances for civil engineering for all path of travel issues (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $27,331.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2021-05-07 | 2020/21 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 11550 | 972095R | 2021-05-07 | 000000020187161 | 11550 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 6.453% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2021-05-07 | 2020/21 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 11550 | 971724R | 2021-05-07 | 000000020187161 | 11550 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 6.453% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2021-06-23 | 2020/21 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 3500 | 975780 | 2021-06-23 | 000000020200446 | 3500 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.955% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2021-12-20 | 2021/22 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 1050 | 976674 | 2021-12-20 | 000000020370745 | 1050 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.5866% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2019-09-16 | 2018/19 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 265.07 |  |  |  | 265.07 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2019-09-16 | 2019/20 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | -265.07 |  |  |  | -265.07 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. Reverse accrual from prior year.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-01-16 | 2021/22 | 2-517 | PO2W-200000001207, 19-100507, 18-109551 | 63119 | 63119 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00.
Grandview-21st Century-Design | 2 | Design | Grandview | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2020-08-07 | 2020-12-08 | 2020/21 | 21-1214 | PO2W-210000000359 | 0 | 81300 | 972626 | 2020-12-08 | 000000020148209 | 81300 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 100% | Architect - Modifications to Architect services for Grandview 21st Century, per District's request. To pay for: Mod 3 - Restroom, Mod 5 - Mock-up room 61, Mod 6 - Contract deviations, & Mod 7 - New Standards. Addendum to PO2W-20*1207.
Grandview-21st Century-FF & E | 2 | FF & E | Grandview | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 3.16% | Furniture for Grandview - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Grandview-21st Century-FF & E | 2 | FF & E | Grandview | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 1.655% | Furniture for Grandview - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Grandview-21st Century-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2019/20 | 2-10467 | PO2W-200000005390 | 0 | 2900 | MCSI-4521 | 2020-06-19 | 000000020106917 | 2900 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 100% | Asbestos & lead-based paint survey of Grandview's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Grandview-21st Century-FF & E | 2 | FF & E | Grandview | 21st Century | Uline | Furniture | 2019-07-01 | 2019-07-30 | 2019/20 | 2-1363 | PO3W-200000000288 | 0 | 8041.68 | 110598716 | 2019-07-30 | 000000020001919 | 8041.68 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 100% | Furniture - Tables, casters, and shop stools for Grandview's room #61
Grandview-Fire alarm-DSA Fees | 2 | DSA Fees | Grandview | Fire alarm | Department of General Services (DGS) | DSA fees | 2021-07-21 | 2021-08-04 | 2021/22 | 22-742 | PO2W-220000000119 | 0 | 1451.25 | 12682 | 2021-08-04 | 000000020223410 | 1451.25 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9121103 | 45.76% | DGS plan/field review fee for Grandview fire alarm
Grandview-Fire Alarm-Environ Consultant | 2 | Environ Consultant | Grandview | Fire Alarm | Masek Consulting | Asbestos survey | 2020-04-13 | 2020-04-29 | 2019/20 | 2-9607 | PO2W-200000004873 | 0 | 850 | MCSI-4508 | 2020-04-29 | 000000020093275 | 850 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121103 | 100% | Limited asbestos survey of Grandview's permanent buildings.
Grandview-Fire alarm-Design | 2 | Design | Grandview | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28044 | 2020-10-14 | 000000020134523 | 2375 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The total architect contract for Grandview FA is $47,500.00
Grandview-Fire alarm-Design | 2 | Design | Grandview | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28116 | 2021-01-07 | 000000020154828 | 2375 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The total architect contract for Grandview FA is $47,500.00
Grandview-Fire alarm-Design | 2 | Design | Grandview | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28378 | 2021-03-24 | 000000020174735 | 2375 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The total architect contract for Grandview FA is $47,500.00
Grandview-Fire alarm-Design | 2 | Design | Grandview | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28463 | 2021-03-24 | 000000020174735 | 2375 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The total architect contract for Grandview FA is $47,500.00
Grandview-Fire alarm-Design | 2 | Design | Grandview | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28729 | 2021-09-09 | 000000020255226 | 1425 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 0.8316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The total architect contract for Grandview FA is $47,500.00
Grandview-Fire alarm-Design | 2 | Design | Grandview | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-11-17 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 28994 | 2021-11-17 | 000000020338267 | 950 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 0.5544% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The total architect contract for Grandview FA is $47,500.00
Grandview-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2020-05-26 | 2019/20 |  | PO2W-200000002809 | 0 | 2345 | 202005-03:GFA | 2020-05-26 | 000000020099846 | 2345 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 25.01% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system
Grandview-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2020-06-19 | 2019/20 |  | PO2W-200000002809 | 0 | 2345 | 202006-02:GFA | 2020-06-19 | 000000020106934 | 2345 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 25.01% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system
Grandview-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2020-10-14 | 2020/21 |  | PO2W-200000002809 | 0 | 2345 | 202009-09:GFA | 2020-10-14 | 000000020134520 | 2345 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 25.01% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system
Grandview-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2021-09-13 | 2020/21 |  | PO2W-200000002809 | 0 | 1840 | 20210630-06: GFA | 2021-09-13 | 000000020257046 | 1840 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 19.63% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system
Grandview-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2023-07-31 | 2021/22 | 2-5882 | PO2W-200000002809 | 500 | 500 |  |  |  | 0 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 0% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1578.9 | Pay app #1 | 2020-03-10 | 000000020079637 | 1578.9 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.1234% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 47652.48 | Pay app #4 | 2020-05-29 | 000000020101116 | 47652.48 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 3.724% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 35854.85 | Pay app #5 | 2020-07-30 | 000000020117024 | 35854.85 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 2.802% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 12251.63 | Pay app #6 | 2020-07-30 | 000000020117024 | 12251.63 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.9574% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-08-28 | 2020/21 |  | PO1-200000000662 | 0 | 28361.78 | Pay app #7 | 2020-08-28 | 000000020122656 | 28361.78 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 2.216% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 6786.8 | Pay app #12 | 2021-05-21 | 000000020191188 | 6786.8 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.5303% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 1365.7 | Pay app #14 | 2021-05-21 | 000000020191188 | 1365.7 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.1067% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 855 | Pay app #15 | 2021-05-21 | 000000020191188 | 855 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.06681% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 3650.96 | Pay app #16 | 2021-11-22 | 000000020341778 | 3650.96 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.2853% | Fire alarm and low voltage service for Grandview
Grandview-Fire Alarm-Contractor | 2 | Contractor | Grandview | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4502 | PO1-200000000662 | 8282.01 | 8282.01 |  |  |  | 0 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0% | Fire alarm and low voltage service for Grandview
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9315.47 | 0173712-IN | 2019-10-10 | 000000020025135 | 9315.47 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9131101 | 0.2144% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 126147.01 | 0174014-IN | 2019-10-10 | 000000020025135 | 126147.01 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9131101 | 2.903% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173712-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 72 | 0173712-IN | 2019-10-10 | 000000020025135 | 72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.001657% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 228 | 0173712-IN | 2019-10-10 | 000000020025135 | 228 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.005248% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 279.36 | 0173712-IN | 2019-10-10 | 000000020025135 | 279.36 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.00643% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 768.72 | 0173712-IN | 2019-10-10 | 000000020025135 | 768.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.01769% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 36 | 0173712-IN | 2019-10-10 | 000000020025135 | 36 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.0008286% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 487.5 | 0174014-IN | 2019-10-10 | 000000020025135 | 487.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.01122% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 975 | 0174014-IN | 2019-10-10 | 000000020025135 | 975 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.02244% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1625 | 0174014-IN | 2019-10-10 | 000000020025135 | 1625 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.0374% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3087.5 | 0174014-IN | 2019-10-10 | 000000020025135 | 3087.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.07106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3783 | 0174014-IN | 2019-10-10 | 000000020025135 | 3783 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.08707% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10409.75 | 0174014-IN | 2019-10-10 | 000000020025135 | 10409.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.2396% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 13003.23 | 0174099-IN | 2019-09-23 | 000000020017958 | 13003.23 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9131101 | 14.27% | Ergotron Zip40 Charging carts to store laptops at Grazide. Total carts: 10
Grazide-21st Century-Technology | 3 | Technology | Grazide | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 16904.22 | 0175152-IN | 2019-10-08 | 000000020023867 | 16904.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9131101 | 2.13% | Ergotron Zip40 Charging carts to store laptops at Grazide. Total carts: 13
Grazide-21st Century-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 800 | 100653 | 2021-09-08 | 000000020253624 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 0.04374% | Construction management services for Grazide - phase 3 & 4. This PO includes allowances of $40,000.00
Grazide-21st Century-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 3960 | 101514 | 2021-09-29 | 000000020275054 | 3960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 0.2165% | Construction management services for Grazide - phase 3 & 4. This PO includes allowances of $40,000.00
Grazide-21st Century-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2024-07-01 | 2021/22 | 22-1057 | PO1-220000000334 | 196192 | 196192 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 0% | Construction management services for Grazide - phase 3 & 4. This PO includes allowances of $40,000.00
Grazide-21st Century-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862 | 0 | 5650 | 102578 | 2021-11-08 | 000000020325325 | 5650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 11.52% | Construction management services for Baldwin - phase 3 & 4. This PO is to pay invoice #102578 (Prof service from 09/01-09/30/21), dated 09/30/21
Grazide-21st Century-Contractor | 3 | Contractor | Grazide | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2023-01-06 | 2020/21 | 21-3656 | PO2W-210000001556 | 0 | 37500 | 2021-006D | 2021-03-24 | 000000020174720 | 37500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131101 | 38.46% | Demo of ceiling tiles in 15 classrooms at Grazide
Grazide-21st Century-Environ Consultant | 3 | Environ Consultant | Grazide | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10241 | PO2W-200000005319 | 0 | 2550 | MCSI-4537 | 2020-08-17 | 000000020119790 | 2550 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9131101 | 100% | Asbestos & lead-based paint survey of Grazide's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Grazide-21st Century-Design | 3 | Design | Grazide | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002224 | 0 | 24121.52 | T8703 | 2021-09-09 | 000000020255214 | 24121.52 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131101 | 9.863% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Grazide. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Grazide-21st Century-Design | 3 | Design | Grazide | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002224 | 0 | 8978.93 | 3298 | 2021-10-19 | 000000020302604 | 8978.93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131101 | 3.671% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Grazide. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Grazide-21st Century-Design | 3 | Design | Grazide | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6239 | PO2W-210000002224 | 211457.55 | 211457.55 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Grazide. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Grazide-Ceiling replacement-Contractor | 3 | Contractor | Grazide | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 26751.81 | Pay app #1 | 2019-12-17 | 000000020049998 | 26751.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131105 | 0.5849% | Ceiling replacement for Grazide.
Grazide-Ceiling replacement-Contractor | 3 | Contractor | Grazide | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 80255.43 | Pay app #2 | 2020-10-21 | 000000020136454 | 80255.43 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131105 | 1.755% | Ceiling replacement for Grazide.
Grazide-Ceiling replacement-Contractor | 3 | Contractor | Grazide | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-04-27 | 2020/21 |  | PO1-200000000729 | 0 | 160510.86 | Pay app #3 | 2021-04-27 | 000000020183628 | 160510.86 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131105 | 3.51% | Ceiling replacement for Grazide.
Grazide-Ceiling replacement-Contractor | 3 | Contractor | Grazide | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5061 | PO1-200000000729 | 14079.9 | 14079.9 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131105 | 0% | Ceiling replacement for Grazide.
Grazide-Fire Alarm-DSA Fees | 3 | DSA Fees | Grazide | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6933 | PO1-200000000850 | 0 | 960 | Per email | 2020-02-13 | 000000020070035 | 960 | 03-120624 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9131103 | 100% | DSA plan check review fee for Grazide fire alarm.
Grazide-Fire Alarm-Design | 3 | Design | Grazide | Fire Alarm | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 2021/22 | 2-6865 | PO1-200000000846 | 12125 | 12125 |  |  |  | 0 | 03-120624 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grazide. Facilities paid PO2W-20*4418 in the amount of $36,375.00. The total architect contract for Grazide FA is $48,500.00
Grazide-Interim Housing-Design | 3 | Design | Grazide | Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6244 | PO2W-210000002229 | 79400 | 79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131102 | 0% | Architect - Prepare design documents for Grazide Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5822.17 | 0173555-IN | 2019-10-10 | 000000020025135 | 5822.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 0.134% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15525.78 | 0173802-IN | 2019-10-10 | 000000020025135 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 0.3574% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5822.17 | 0173880-IN | 2019-10-10 | 000000020025135 | 5822.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 0.134% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 388.16 | 0173881-IN | 2019-10-10 | 000000020025135 | 388.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 0.008934% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 58221.7 | 0173950-IN | 2019-10-10 | 000000020025135 | 58221.7 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 1.34% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 174.6 | 0173555-IN | 2019-10-10 | 000000020025135 | 174.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.004019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 142.5 | 0173555-IN | 2019-10-10 | 000000020025135 | 142.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.00328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 75 | 0173555-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 480.45 | 0173555-IN | 2019-10-10 | 000000020025135 | 480.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 45 | 0173555-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 22.5 | 0173555-IN | 2019-10-10 | 000000020025135 | 22.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 200 | 0173802-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173802-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173802-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 380 | 0173802-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173802-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173802-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 174.6 | 0173880-IN | 2019-10-10 | 000000020025135 | 174.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.004019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 142.5 | 0173880-IN | 2019-10-10 | 000000020025135 | 142.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.00328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 75 | 0173880-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 480.45 | 0173880-IN | 2019-10-10 | 000000020025135 | 480.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 45 | 0173880-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 22.5 | 0173880-IN | 2019-10-10 | 000000020025135 | 22.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 32.03 | 0173881-IN | 2019-10-10 | 000000020025135 | 32.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0007372% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 11.64 | 0173881-IN | 2019-10-10 | 000000020025135 | 11.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0002679% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9.5 | 0173881-IN | 2019-10-10 | 000000020025135 | 9.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5 | 0173881-IN | 2019-10-10 | 000000020025135 | 5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0001151% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3 | 0173881-IN | 2019-10-10 | 000000020025135 | 3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 6.905e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1.5 | 0173881-IN | 2019-10-10 | 000000020025135 | 1.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 3.452e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 225 | 0173950-IN | 2019-10-10 | 000000020025135 | 225 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 450 | 0173950-IN | 2019-10-10 | 000000020025135 | 450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 750 | 0173950-IN | 2019-10-10 | 000000020025135 | 750 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1425 | 0173950-IN | 2019-10-10 | 000000020025135 | 1425 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1746 | 0173950-IN | 2019-10-10 | 000000020025135 | 1746 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.04019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4804.5 | 0173950-IN | 2019-10-10 | 000000020025135 | 4804.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.1106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 2600.65 | 0173901-IN | 2019-09-23 | 000000020017958 | 2600.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 2.854% | Ergotron Zip40 Charging carts to store laptops at Kwis. Total carts: 8
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173905-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Kwis. Total carts: 8
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 6501.61 | 0173952-IN | 2019-09-23 | 000000020017958 | 6501.61 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 7.134% | Ergotron Zip40 Charging carts to store laptops at Kwis. Total carts: 8
Kwis-21st Century-Technology | 7 | Technology | Kwis | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 9102.26 | 0175117-IN | 2019-10-08 | 000000020023867 | 9102.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 1.147% | Ergotron Zip40 Charging carts to store laptops at Kwis. Total carts: 7
Kwis-21st Century-Contractor | 7 | Contractor | Kwis | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-04-06 | 2021-05-26 | 2020/21 | 21-5873 | PO2W-210000002060 | 0 | 42500 | 2021-044D | 2021-05-26 | 000000020192522 | 42500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161101 | 51.52% | Demo of ceiling tiles in 17 classrooms at Kwis
Kwis-21st Century-Contractor | 7 | Contractor | Kwis | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-06-14 | 2021-09-09 | 2021/22 | 21-6790 | PO2W-210000002615 | 0 | 6500 | 2021-088D | 2021-09-09 | 000000020255195 | 6500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161101 | 38.24% | Demo of ceiling tiles in 2 classrooms at Kwis for room #4 & 7
Kwis-21st Century-FF & E | 7 | FF & E | Kwis | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 23990.6 | 3207761219 | 2020-02-03 | 000000020065147 | 23990.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 5.575% | Furniture for Kwis - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Kwis-21st Century-FF & E | 7 | FF & E | Kwis | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 14247.57 | 3207761219 | 2020-02-03 | 000000020065147 | 14247.57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 3.311% | Furniture for Kwis - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Kwis-21st Century-Environ Consultant | 7 | Environ Consultant | Kwis | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10242 | PO2W-200000005320 | 0 | 2600 | MCSI-4538 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9161101 | 100% | Asbestos & lead-based paint survey of Kwis' permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Kwis-Ceiling replacement-Contractor | 7 | Contractor | Kwis | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 25747.66 | Pay app #1 | 2019-12-17 | 000000020049998 | 25747.66 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161105 | 0.563% | Ceiling replacement for Kwis.
Kwis-Ceiling replacement-Contractor | 7 | Contractor | Kwis | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 231728.94 | Pay app #5 | 2021-06-17 | 000000020198995 | 231728.94 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161105 | 5.067% | Ceiling replacement for Kwis.
Kwis-Ceiling replacement-Contractor | 7 | Contractor | Kwis | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5062 | PO1-200000000729 | 13551.4 | 13551.4 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161105 | 0% | Ceiling replacement for Kwis.
Kwis-Drinking fountain replacement-DSA Inspection | 7 | DSA Inspection | Kwis | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6602 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9161104 | 0% | General inspection for the project as defined in Title 24 at Kwis. Replacement of 3-exterior drinking fountains
Kwis-Fire alarm-DSA Fees | 7 | DSA Fees | Kwis | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 891 | Per email | 2021-03-30 | 000000020176202 | 891 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9161103 | 12.56% | DSA plan check review fee for Kwis fire alarm.
Kwis-Fire alarm-Design | 7 | Design | Kwis | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28229 | 2021-02-05 | 000000020162584 | 7275 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis.
Kwis-Fire alarm-Design | 7 | Design | Kwis | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28290 | 2021-02-09 | 000000020163360 | 7275 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis.
Kwis-Fire alarm-Design | 7 | Design | Kwis | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28386 | 2021-03-24 | 000000020174735 | 7275 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis.
Kwis-Fire alarm-Design | 7 | Design | Kwis | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28515 | 2021-05-26 | 000000020192536 | 2425 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis.
Kwis-Fire alarm-Design | 7 | Design | Kwis | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28609 | 2021-05-26 | 000000020192536 | 9700 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis.
Kwis-Fire alarm-Design | 7 | Design | Kwis | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28685 | 2021-06-23 | 000000020200466 | 1455 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0.3731% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis.
Kwis-Fire alarm-Design | 7 | Design | Kwis | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28834 | 2021-09-09 | 000000020255227 | 970 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0.2487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis.
Kwis-Fire alarm-Design | 7 | Design | Kwis | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2025-10-20 | 2021/22 | 21-2535 | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis.
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 13647.1 | 0173367-IN | 2019-10-10 | 000000020025135 | 13647.1 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9401101 | 0.3141% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 20275.68 | 0173639-IN | 2019-10-10 | 000000020025135 | 20275.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9401101 | 0.4667% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 366521.98 | 0174537-IN | 2019-10-10 | 000000020025135 | 366521.98 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9401101 | 8.436% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 175 | 0173367-IN | 2019-10-10 | 000000020025135 | 175 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.004028% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 105 | 0173367-IN | 2019-10-10 | 000000020025135 | 105 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.002417% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 52.5 | 0173367-IN | 2019-10-10 | 000000020025135 | 52.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.001208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 332.5 | 0173367-IN | 2019-10-10 | 000000020025135 | 332.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.007653% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 407.4 | 0173367-IN | 2019-10-10 | 000000020025135 | 407.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.009377% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1121.05 | 0173367-IN | 2019-10-10 | 000000020025135 | 1121.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.0258% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 156 | 0173639-IN | 2019-10-10 | 000000020025135 | 156 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.003591% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 78 | 0173639-IN | 2019-10-10 | 000000020025135 | 78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.001795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 260 | 0173639-IN | 2019-10-10 | 000000020025135 | 260 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.005984% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 494 | 0173639-IN | 2019-10-10 | 000000020025135 | 494 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.01137% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 605.28 | 0173639-IN | 2019-10-10 | 000000020025135 | 605.28 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.01393% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1665.56 | 0173639-IN | 2019-10-10 | 000000020025135 | 1665.56 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.03834% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1410 | 0174537-IN | 2019-10-10 | 000000020025135 | 1410 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.03245% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2820 | 0174537-IN | 2019-10-10 | 000000020025135 | 2820 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.06491% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4700 | 0174537-IN | 2019-10-10 | 000000020025135 | 4700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.1082% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 8930 | 0174537-IN | 2019-10-10 | 000000020025135 | 8930 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.2055% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10941.6 | 0174537-IN | 2019-10-10 | 000000020025135 | 10941.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.2518% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30108.2 | 0174537-IN | 2019-10-10 | 000000020025135 | 30108.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.693% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1306.26 | 0173476-IN | 2019-09-23 | 000000020017958 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9401101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at La Puente HS. Total cart: 1
La Puente HS-21st Century-Technology | 5 | Technology | La Puente HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 39187.83 | 0174704-IN | 2019-10-08 | 000000020023867 | 39187.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9401101 | 4.938% | Ergotron Zip40 Charging carts to store laptops at La Puente HS. Total carts: 30
La Puente HS-21st Century-Environ Consultant | 5 | Environ Consultant | La Puente HS | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2021-03-23 | 2020/21 | 21-1580 | PO1-210000000427 | 0 | 6900 | MCSI-4666 | 2021-03-23 | 000000020174432 | 6900 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9401101 | 16.75% | Asbestos & lead-based paint survey of La Puente HS permanent buildings.
La Puente HS-Drinking fountain replacement-DSA Inspection | 5 | DSA Inspection | La Puente HS | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6603 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9401104 | 0% | General inspection for the project as defined in Title 24 at La Puente HS. Replacement of 3-exterior drinking fountains
La Puente HS-Fire alarm-Design | 5 | Design | La Puente HS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 2021/22 | 21-1992 | PO2W-210000000680 | 14700 | 14700 |  |  |  | 0 | 03-119978 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9401103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for La Puente HS. Facilities paid PO1-20*905 & 19-109188 in the amount of $44,100.00. The total architect contract for La Puente HS FA is $58,800.00
La Puente HS-Fire Alarm-Contractor | 5 | Contractor | La Puente HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 | 2-4501 | PO1-200000000662 | 0 | 2717.95 | Pay app #1 | 2020-03-10 | 000000020079637 | 2717.95 | 03-119978 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9401103 | 0.2124% | Fire alarm and low voltage service for La Puente HS
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 11697.51 | 0173445-IN | 2019-10-10 | 000000020025135 | 11697.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 0.2692% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 11697.51 | 0173633-IN | 2019-10-10 | 000000020025135 | 11697.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 0.2692% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173801-IN | 2019-10-10 | 000000020025135 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 150118.05 | 0173980-IN | 2019-10-10 | 000000020025135 | 150118.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 3.455% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 150 | 0173445-IN | 2019-10-10 | 000000020025135 | 150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 90 | 0173445-IN | 2019-10-10 | 000000020025135 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 45 | 0173445-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 285 | 0173445-IN | 2019-10-10 | 000000020025135 | 285 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.00656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 349.2 | 0173445-IN | 2019-10-10 | 000000020025135 | 349.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.008037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 960.9 | 0173445-IN | 2019-10-10 | 000000020025135 | 960.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.02212% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 150 | 0173633-IN | 2019-10-10 | 000000020025135 | 150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 90 | 0173633-IN | 2019-10-10 | 000000020025135 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 45 | 0173633-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 285 | 0173633-IN | 2019-10-10 | 000000020025135 | 285 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.00656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 349.2 | 0173633-IN | 2019-10-10 | 000000020025135 | 349.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.008037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 960.9 | 0173633-IN | 2019-10-10 | 000000020025135 | 960.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.02212% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173801-IN | 2019-10-10 | 000000020025135 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173801-IN | 2019-10-10 | 000000020025135 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173801-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173801-IN | 2019-10-10 | 000000020025135 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173801-IN | 2019-10-10 | 000000020025135 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173801-IN | 2019-10-10 | 000000020025135 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 577.5 | 0173980-IN | 2019-10-10 | 000000020025135 | 577.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.01329% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1155 | 0173980-IN | 2019-10-10 | 000000020025135 | 1155 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.02658% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1925 | 0173980-IN | 2019-10-10 | 000000020025135 | 1925 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.04431% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3657.5 | 0173980-IN | 2019-10-10 | 000000020025135 | 3657.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.08418% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4481.4 | 0173980-IN | 2019-10-10 | 000000020025135 | 4481.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.1031% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 12331.55 | 0173980-IN | 2019-10-10 | 000000020025135 | 12331.55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.2838% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1306.26 | 0173471-IN | 2019-09-23 | 000000020017958 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at Lassalette. Total carts: 16
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1306.26 | 0174062-IN | 2019-09-23 | 000000020017958 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at Lassalette. Total carts: 16
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 18287.67 | 0174093-IN | 2019-09-23 | 000000020017958 | 18287.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 20.07% | Ergotron Zip40 Charging carts to store laptops at Lassalette. Total carts: 16
Lassalette-21st Century-Technology | 6 | Technology | Lassalette | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-11-07 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 11756.35 | 0174403-IN | 2019-11-07 | 000000020035575 | 11756.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 1.482% | Ergotron Zip40 Charging carts to store laptops at Lassalette. Total carts: 9
Lassalette-21st Century-FF & E | 6 | FF & E | Lassalette | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 3.16% | Furniture for Lassalette - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Lassalette-21st Century-FF & E | 6 | FF & E | Lassalette | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 1.655% | Furniture for Lassalette - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Lassalette-21st Century-Environ Consultant | 6 | Environ Consultant | Lassalette | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1576 | PO1-210000000427 | 0 | 2800 | MCSI-4609 | 2020-10-13 | 000000020134092 | 2800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9171101 | 6.796% | Asbestos & lead-based paint survey of Lassalette's permanent buildings.
Lassalette-Drinking fountain replacement-DSA Inspection | 6 | DSA Inspection | Lassalette | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6604 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9171104 | 0% | General inspection for the project as defined in Title 24 at Lassalette. Replacement of 2-exterior drinking fountains
Lassalette-Fire alarm-DSA Fees | 6 | DSA Fees | Lassalette | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 |  | PO1-200000000853 | 0 | 945 | Per email | 2020-02-13 | 000000020070037 | 945 | 03-120621 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9171103 | 100% | DSA plan check review fee for Lassalette fire alarm.
Lassalette-Fire alarm-DSA Fees | 6 | DSA Fees | Lassalette | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6934 | PO1-200000000853 | 0 | -945 | Per email | 2020-02-13 | 000000020070037 | -945 | 03-120621 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9171103 | -100% | We voided this check. Per Carolyn Loughrey @ tBP - email dated 06/08/20, somehow she had 2 checks with this amount and Lassalette is already paid for. She further said no replacement check is needed for this site. DSA plan check review fee for Lassalette fire alarm.
Lassalette-Fire Alarm-Design | 6 | Design | Lassalette | Fire Alarm | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 2021/22 | 2-6866 | PO1-200000000846 | 12375 | 12375 |  |  |  | 0 | 03-120621 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9171103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Lassalette. Facilities paid PO2W-20*4419 in the amount of $37,125.00. The total architect contract for Lassalette FA is $49,500.00
Los Altos ES-21st Century-Reprographics | 2 | Reprographics | Los Altos ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 2019/20 |  | PO1-200000000625 | 0 | 728.6 | 10597813 | 2020-04-22 | 000000020091358 | 728.6 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 36.43% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Los Altos ES.
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 8539.18 | 0173645-IN | 2019-10-10 | 000000020025135 | 8539.18 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9191101 | 0.1965% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 209 | 0173645-IN | 2019-10-10 | 000000020025135 | 209 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.00481% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 110 | 0173645-IN | 2019-10-10 | 000000020025135 | 110 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.002532% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 66 | 0173645-IN | 2019-10-10 | 000000020025135 | 66 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.001519% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 33 | 0173645-IN | 2019-10-10 | 000000020025135 | 33 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.0007595% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 256.08 | 0173645-IN | 2019-10-10 | 000000020025135 | 256.08 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.005894% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 704.66 | 0173645-IN | 2019-10-10 | 000000020025135 | 704.66 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.01622% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 114502.67 | 0175570-IN | 2019-10-22 | 000000020029495 | 114502.67 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9191101 | 4.081% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 442.5 | 0175570-IN | 2019-10-22 | 000000020029495 | 442.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.01577% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 885 | 0175570-IN | 2019-10-22 | 000000020029495 | 885 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.03154% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1475 | 0175570-IN | 2019-10-22 | 000000020029495 | 1475 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.05257% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2802.5 | 0175570-IN | 2019-10-22 | 000000020029495 | 2802.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.09989% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 3433.8 | 0175570-IN | 2019-10-22 | 000000020029495 | 3433.8 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.1224% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 9448.85 | 0175570-IN | 2019-10-22 | 000000020029495 | 9448.85 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.3368% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 27306.79 | 0175609-IN | 2019-10-22 | 000000020029495 | 27306.79 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 3.441% | Ergotron Zip40 Charging carts to store laptops at Los Altos ES. Total carts: 21
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 120 | 0189682-IN | 2020-10-01 | 000000020131103 | 120 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 0.09629% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Los Altos ES. Total monitors: 20
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 43574.21 | 0189682-IN | 2020-10-01 | 000000020131103 | 43574.21 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 34.96% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Los Altos ES. Total monitors: 20
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Camcor | Document camera(s) | 2020-07-01 | 2020-07-16 | 2020/21 | 21-309 | PO3W-210000000006 | 0 | 11954.12 | 2494523 | 2020-07-16 | 000000020114150 | 11954.12 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 35.09% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Los Altos ES. Total cameras: 20
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 319.35 | 8316064 | 2021-03-05 | 000000020169721 | 319.35 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 8.333% | C2G HDMI and USB pass through wall plates for Los Altos ES. Total items: 21
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 56.66 | 5725548 | 2021-03-05 | 000000020169721 | 56.66 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 1.478% | C2G HDMI and USB pass through wall plates for Los Altos ES. Total items: 21
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 267.85 | 8312741 | 2021-03-05 | 000000020169721 | 267.85 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 6.989% | C2G HDMI and USB pass through wall plates for Los Altos ES. Total items: 21
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2020-08-17 | 2020/21 |  | PO2W-200000005542 | 0 | 779.5 | 20-31197-30-0000001 | 2020-08-17 | 000000020119768 | 779.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 3.292% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2020-12-04 | 2020/21 |  | PO2W-200000005542 | 0 | 342.5 | 20-31197-30-0000002 | 2020-12-04 | 000000020147422 | 342.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 1.446% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2021-02-05 | 2020/21 |  | PO2W-200000005542 | 0 | 1153.5 | 20-31197-30-0000003 | 2021-02-05 | 000000020162565 | 1153.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 4.871% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2021-03-24 | 2020/21 |  | PO2W-200000005542 | 0 | 1722.5 | 20-31197-30-0000004 | 2021-03-24 | 000000020174717 | 1722.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 7.274% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2021-03-24 | 2020/21 |  | PO2W-200000005542 | 0 | 2565 | 20-31197-30-0000005 | 2021-03-24 | 000000020174717 | 2565 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 10.83% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2021-03-24 | 2020/21 |  | PO2W-200000005542 | 0 | 4936 | 20-31197-30-0000006 | 2021-03-24 | 000000020174717 | 4936 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 20.84% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2021-04-19 | 2020/21 |  | PO2W-200000005542 | 0 | 880 | 20-31197-30-0000007 | 2021-04-19 | 000000020181372 | 880 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 3.716% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2023-07-31 | 2021/22 | 2-10672 | PO2W-200000005542 | 11301 | 11301 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 0% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel
Los Altos ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century | Converse Consultants | Masonry inspection | 2020-10-28 | 2021-09-09 | 2021/22 | 21-2786 | PO2W-210000001034 | 0 | 2537.5 | 20-31197-61-0000001 | 2021-09-09 | 000000020255186 | 2537.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 30.48% | Masonry inspection of brick veneer repair for Los Altos ES 21st Century classroom modification program
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 45198.42 | 30789 | 2021-05-07 | 000000020187154 | 45198.42 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 7.326% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 25304.56 | 30789 | 2021-05-07 | 000000020187154 | 25304.56 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 4.102% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 40063.8 | 30790 | 2021-05-07 | 000000020187155 | 40063.8 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 6.494% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 22953.74 | 30790 | 2021-05-07 | 000000020187155 | 22953.74 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 3.721% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 22251.5 | 30860 | 2021-05-07 | 000000020187156 | 22251.5 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 3.607% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 | 2-9304 | PO2W-200000004768 | 0 | 615.5 | 30860 | 2021-05-07 | 000000020187156 | 615.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 0.09977% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. Close-out PO. Per Jessica Morley @ Cumming, all furniture received. Vendor did not send us an invoice for line item #9 & 13. Close-out PO.
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 192.72 | 31584 | 2021-05-25 | 000000020192063 | 192.72 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 0.03124% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-11-06 | 2021-02-09 | 2020/21 | 21-2938 | PO2W-210000001121 | 0 | 126666.16 | 30874 | 2021-02-09 | 000000020163346 | 126666.16 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 74.83% | Furniture for Los Altos ES. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2020-11-06 | 2021-02-09 | 2020/21 | 21-2938 | PO2W-210000001121 | 0 | 42608.94 | 30874 | 2021-02-09 | 000000020163346 | 42608.94 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 25.17% | Furniture for Los Altos ES. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2021-09-07 | 2021-11-16 | 2021/22 | 22-1683 | PO2W-220000000413 | 0 | 983.31 | 32994 | 2021-11-16 | 000000020337015 | 983.31 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 100% | Furniture for Los Altos ES. Student chairs.
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Culver Newlin | Furniture | 2021-09-07 | 2023-01-14 | 2021/22 | 22-3984 | PO2W-220000001345 | 19218.56 | 19218.56 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 0% | Mid-tower mobile storage with shelves & 2 locking doors for Los Altos ES. Total towers: 16
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 8571.25 | 80804 | 2020-01-09 | 000000020055612 | 8571.25 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.5961% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3268.75 | 80796 | 2020-01-14 | 000000020057268 | 3268.75 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2273% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 9428.75 | 81699 | 2020-01-14 | 000000020057268 | 9428.75 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.6557% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8872.5 | 83068 | 2020-04-01 | 000000020085959 | 8872.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.617% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8525 | 82273 | 2020-04-01 | 000000020085960 | 8525 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.5929% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 12647.5 | 84567 | 2020-04-15 | 000000020089466 | 12647.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.8796% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9337.5 | 85320 | 2020-05-28 | 000000020100719 | 9337.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.6494% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 9947.5 | 86240 | 2020-06-17 | 000000020106117 | 9947.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.6918% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 13287.5 | 86864 | 2020-07-27 | 000000020116270 | 13287.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.9241% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 5953.78 | 88480 | 2020-08-17 | 000000020119773 | 5953.78 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.4141% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 5623.68 | 89359 | 2020-10-13 | 000000020134067 | 5623.68 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.3911% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 5328.17 | 90460 | 2020-10-20 | 000000020136025 | 5328.17 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.3706% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 5936.86 | 91321 | 2020-12-18 | 000000020151933 | 5936.86 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.4129% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 5132.67 | 91964 | 2020-12-18 | 000000020151933 | 5132.67 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.357% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 5488.71 | 92821 | 2021-02-08 | 000000020162981 | 5488.71 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.3817% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 4037.49 | 94011 | 2021-04-05 | 000000020177572 | 4037.49 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2808% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 3419.03 | 94918 | 2021-04-16 | 000000020181024 | 3419.03 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2378% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 3651.37 | 95700 | 2021-05-25 | 000000020192064 | 3651.37 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2539% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 2117.43 | 96936 | 2021-05-25 | 000000020192064 | 2117.43 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.1473% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-30 | 2021/22 |  | PO1-200000000640 | 0 | 11952.82 | 101444 | 2021-09-30 | 000000020276415 | 11952.82 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.8313% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-10-18 | 2021/22 |  | PO1-200000000640 | 0 | 2897.99 | 102576 | 2021-10-18 | 000000020301535 | 2897.99 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2015% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4694 | PO1-200000000640 | 25.75 | 25.75 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 9695.44 | 10513843591 | 2021-08-27 | 000000020245275 | 9695.44 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 13.33% | PowerSwitch N2200-ON OS6 for Los Altos ES. Total power switch: 2
Los Altos ES-21st Century-DSA Fees | 2 | DSA Fees | Los Altos ES | 21st Century | Department of General Services (DGS) | DSA fees | 2021-12-15 | 2022-01-06 | 2021/22 | 22-3685 | PO2W-220000001228 | 0 | 15210.87 | 12901 | 2022-01-06 | 000000020378116 | 15210.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191101 | 100% | DGS plan/field review fee for Los Altos ES 21st Century
Los Altos ES-21st Century-DSA Fees | 2 | DSA Fees | Los Altos ES | 21st Century | Division of the State Architect (DSA) | DSA fees | 2019-06-11 | 2019-06-19 | 2018/19 |  | 19-109963 | 0 | 14918.24 | Per email | 2019-06-19 | 25365032 | 14918.24 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191101 | 100% | DSA plan check review fee for Los Altos ES 21st Century
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | GDL Best Contractors, Inc | Contractor | 2020-09-11 | 2021-03-26 | 2020/21 | 21-1847 | PO2W-210000000586 | 0 | 7950 | 6232 | 2021-03-26 | 000000020175473 | 7950 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191101 | 36.64% | Concrete work for wing A & B, per site walk with Richard Walsh at Los Altos ES
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | GDL Best Contractors, Inc | Contractor | 2020-09-11 | 2021-03-26 | 2020/21 | 21-1847 | PO2W-210000000586 | 0 | 13746 | 6233 | 2021-03-26 | 000000020175473 | 13746 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191101 | 63.36% | Concrete work for wing E & F, per site walk with Richard Walsh at Los Altos ES
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Graybar | Door hardware | 2020-12-14 | 2021-02-08 | 2020/21 | 21-3550 | PO3W-210000001162 | 0 | 246.82 | 9319230223 | 2021-02-08 | 000000020162991 | 246.82 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 33.33% | Mounting brackets & blank face plates for Los Altos ES
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 130.8 | 35256 | 2021-10-21 | 000000020304825 | 130.8 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9191101 | 4.24% | Walked and reviewed site for the wireless door contacts installation at Los Altos ES. Repair damage caused by bond work.
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5994 | PO3W-210000002406 | 0 | 1971.64 | 34985 | 2021-06-07 | 000000020195370 | 1971.64 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 23.61% | Equipment to repair & replace security system at Los Altos ES
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5994 | PO3W-210000002406 | 0 | 558.94 | 34985 | 2021-06-07 | 000000020195370 | 558.94 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 6.694% | Equipment to repair & replace security system at Los Altos ES
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-06-05 | 2020-08-18 | 2019/20 | 2-10679 | PO2W-200000005820 | 0 | 18000 | 2019-032A-8 | 2020-08-18 | 000000020120080 | 18000 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 100% | Asbestos abatement of floor tile at Los Altos ES classroom B3, C1, and work room between C1 & C2. Demolish and haul off casework.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-07-06 | 2020-10-13 | 2020/21 | 21-397 | PO2W-210000000146 | 0 | 32000 | 2019-032A-10 | 2020-10-13 | 000000020134080 | 32000 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 100% | Asbestos abatement of Los Altos ES floor tile in classroom E2, E3, E4, & F4. Demolish and haul off casework.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 2020/21 | 21-2378 | PO2W-210000000884 | 0 | 45000 | 2020-096D | 2020-11-20 | 000000020144493 | 45000 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 38.3% | Demo of ceiling tiles in 18 classrooms at Los Altos ES
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Integrated Pest Control Management | Termite service | 2020-08-07 | 2020-08-24 | 2020/21 | 21-1217 | PO2W-210000000362 | 0 | 785 | 25029 | 2020-08-24 | 000000020121275 | 785 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5570 | 9191101 | 100% | Termite service at room #A-4 for the interior open studs at Los Altos ES.
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-02-17 | 2020/21 | 21-2985 | PO2W-210000001120 | 0 | 27585.39 | 2979771220 | 2021-02-17 | 000000020165087 | 27585.39 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 46.37% | Furniture for Los Altos ES. Tables, chairs, stools, carpets, filing cabinets, etc
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-02-17 | 2020/21 | 21-2985 | PO2W-210000001120 | 0 | 31910.4 | 2979771220 | 2021-02-17 | 000000020165087 | 31910.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 53.63% | Furniture for Los Altos ES. Tables, chairs, stools, carpets, filing cabinets, etc
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 1401.61 | 6454842481 | 2020-07-27 | 000000020116281 | 1401.61 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 2.492% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Los Altos ES (4 year warranty). Total computers: 20
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-05 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 19688.1 | 6454893288 | 2020-08-05 | 000000020117729 | 19688.1 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 32.76% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Los Altos ES (4 year warranty). Total computers: 20
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 4292.4 | 128357 | 2020-07-23 | 000000020115778 | 4292.4 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 3.814% | Voice amplification system - Topcat, mounting kit & sensor clip for Los Altos ES. Total system: 20
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 35193.3 | 128357 | 2020-07-23 | 000000020115778 | 35193.3 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 31.27% | Voice amplification system - Topcat, mounting kit & sensor clip for Los Altos ES. Total system: 20
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI89941 | 2021-02-22 | 000000020166212 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.88 | RI90464 | 2021-02-22 | 000000020166212 | 136.88 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6609% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI90780 | 2021-02-22 | 000000020166212 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI90909 | 2021-02-22 | 000000020166212 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.86 | RI91366 | 2021-02-22 | 000000020166212 | 136.86 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI91626 | 2021-03-24 | 000000020174723 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 273.75 | RI91692 | 2021-03-24 | 000000020174723 | 273.75 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92159 | 2021-03-24 | 000000020174723 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92428 | 2021-03-24 | 000000020174723 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 273.75 | RI92503 | 2021-03-24 | 000000020174723 | 273.75 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI93275 | 2021-05-26 | 000000020192523 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92908 | 2021-05-26 | 000000020192523 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93188 | 2021-05-26 | 000000020192523 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93714 | 2021-05-26 | 000000020192523 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93942 | 2021-06-23 | 000000020200450 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI94010 | 2021-06-23 | 000000020200450 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94485 | 2021-06-23 | 000000020200450 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94728 | 2021-06-23 | 000000020200450 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI94798 | 2021-06-23 | 000000020200450 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-30 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI95214 | 2021-06-30 | 000000020202687 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI95450 | 2021-09-09 | 000000020255202 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 273.76 | RI95527 | 2021-09-09 | 000000020255202 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI95922 | 2021-09-09 | 000000020255202 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI96157 | 2021-09-09 | 000000020255202 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 | 21-4282 | PO1-210000000608 | 0 | 273.76 | RI96227 | 2021-09-09 | 000000020255202 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO.
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2020-05-06 | 2021-06-30 | 2019/20 |  | PO2W-200000005018 | 0 | 1357.8 | RI85306 | 2020-06-24 | 000000020108003 | 1357.8 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 40.79% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2020-05-06 | 2020-07-01 | 2020/21 | 2-10090 | PO2W-200000005018 | 0 | 1971 | RI85306 | 2020-06-24 | 000000020108003 | 1971 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 59.21% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2020-06-03 | 2020-08-18 | 2019/20 |  | PO2W-200000005483 | 0 | 678.9 | RI85947 | 2020-08-18 | 000000020120082 | 678.9 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 40.79% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2020-06-03 | 2020-08-18 | 2020/21 | 2-10620 | PO2W-200000005483 | 0 | 985.5 | RI85947 | 2020-08-18 | 000000020120082 | 985.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 59.21% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2020-07-06 | 2020-08-17 | 2020/21 | 21-400 | PO2W-210000000059 | 0 | 1664.4 | RI85718 | 2020-08-17 | 000000020119789 | 1664.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 100% | Rental of 1 - 40' dry container with lock box for 6 months (06/15-12/14/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Los Altos ES-21st Century-Move Management | 2 | Move Management | Los Altos ES | 21st Century | Martin Container | Rental of container(s) | 2020-07-06 | 2020-10-13 | 2020/21 | 21-1040 | PO2W-210000000340 | 0 | 1664.4 | RI87097 | 2020-10-13 | 000000020134091 | 1664.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 100% | Rental of 1 - 40' dry container with lock box for 6 months (08/01-01/31/21) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Los Altos ES-21st Century-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2019/20 | 2-9624 | PO2W-200000004874 | 0 | 2800 | MCSI-4517 | 2020-06-03 | 000000020102133 | 2800 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 100% | Asbestos & lead-based paint survey of Los Altos ES permanent buildings.
Los Altos ES-21st Century-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-07-06 | 2020-08-17 | 2019/20 |  | PO2W-210000000060 | 0 | 3475 | MCSI-4560 | 2020-08-17 | 000000020119790 | 3475 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 25% | Floor tile & mastic abatement oversight and clearance at Los Altos ES for room #C1, work room between C1 & C2, B3 in Phase I and E2, E3, E4, & F4 in phase II.
Los Altos ES-21st Century-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-07-06 | 2020-08-17 | 2020/21 |  | PO2W-210000000060 | 0 | 4300 | MCSI-4581 | 2020-08-17 | 000000020119790 | 4300 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 30.94% | Floor tile & mastic abatement oversight and clearance at Los Altos ES for room #C1, work room between C1 & C2, B3 in Phase I and E2, E3, E4, & F4 in phase II.
Los Altos ES-21st Century-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-07-06 | 2023-01-16 | 2021/22 | 21-401 | PO2W-210000000060 | 6125 | 6125 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 0% | Floor tile & mastic abatement oversight and clearance at Los Altos ES for room #C1, work room between C1 & C2, B3 in Phase I and E2, E3, E4, & F4 in phase II.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-07-31 | 2020/21 |  | PO2W-200000005828 | 0 | 680168.65 | Pay app #1 | 2020-07-31 | 000000020117168 | 680168.65 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 30.62% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-08-18 | 2020/21 |  | PO2W-200000005828 | 0 | 63129.4 | Pay app #2 | 2020-08-18 | 000000020120083 | 63129.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 2.842% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-09-28 | 2020/21 |  | PO2W-200000005828 | 0 | 306478.32 | Pay app #3 | 2020-09-28 | 000000020130229 | 306478.32 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 13.8% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-11-09 | 2020/21 |  | PO2W-200000005828 | 0 | 589220.4 | Pay app #4 | 2020-11-09 | 000000020141125 | 589220.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 26.53% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-12-18 | 2020/21 |  | PO2W-200000005828 | 0 | 187365.65 | Pay app #5 | 2020-12-18 | 000000020151937 | 187365.65 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 8.436% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2021-01-15 | 2020/21 |  | PO2W-200000005828 | 0 | 79831.6 | Pay app #6 | 2021-01-15 | 000000020157265 | 79831.6 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 3.594% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2021-03-16 | 2020/21 |  | PO2W-200000005828 | 0 | 153632.87 | Pay app #7 | 2021-03-16 | 000000020172578 | 153632.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 6.917% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2021-05-21 | 2020/21 |  | PO2W-200000005828 | 0 | 46286.31 | Pay app #8 | 2021-05-21 | 000000020191176 | 46286.31 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 2.084% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Contractor | 2 | Contractor | Los Altos ES | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2023-07-31 | 2021/22 | 2-10667 | PO2W-200000005828 | 114886.8 | 114886.8 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 0% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp.
Los Altos ES-21st Century-Technology | 2 | Technology | Los Altos ES | 21st Century | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 2020/21 | 21-3258 | PO2W-210000001349 | 0 | 1086.6 | 956466 | 2021-02-10 | 000000020163835 | 1086.6 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 100% | Computer cables for Los Altos ES
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2018-10-11 | 2018/19 |  | PO2W-200000000858, 19-100485 | 0 | 3514.68 | T8158R | 2018-10-11 | 24850693 | 3514.68 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 3.791% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $12,980.00 is requested by District (PO2W-20*5064). The total architect cost with change order is $105,694.72
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2019-01-28 | 2018/19 |  | PO2W-200000000858, 19-100485 | 0 | 3712 | R8227 | 2019-01-28 | 25052439 | 3712 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 4.004% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. Allowances for civil engineering. Change order of $12,980.00 is requested by District (PO2W-20*5064). The total architect cost with change order is $105,694.72
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2019-09-05 | 2018/19 |  | PO2W-200000000858, 19-100485 | 0 | 20209.46 | T8309 | 2019-09-05 | 000000020011699 | 20209.46 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 21.8% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $12,980.00 is requested by District (PO2W-20*5064). The total architect cost with change order is $105,694.72
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2019-09-13 | 2019/20 |  | PO2W-200000000858, 19-100485 | 0 | 28996.18 | T8352 | 2019-09-13 | 000000020015027 | 28996.18 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 31.27% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $12,980.00 is requested by District (PO2W-20*5064). The total architect cost with change order is $105,694.72
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2020-06-04 | 2019/20 |  | PO2W-200000000858, 19-100485 | 0 | 8786.73 | T8518 | 2020-06-04 | 000000020102555 | 8786.73 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 9.477% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $12,980.00 is requested by District (PO2W-20*5064). The total architect cost with change order is $105,694.72
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2021-02-05 | 2020/21 |  | PO2W-200000000858, 19-100485 | 0 | 18708.97 | T8573 | 2021-02-05 | 000000020162578 | 18708.97 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 20.18% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. Payment includes allowances of $1,135.53. Change order of $12,980.00 is requested by District (PO2W-20*5064). The total architect cost with change order is $105,694.72
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2021-04-19 | 2020/21 |  | PO2W-200000000858, 19-100485 | 0 | 4393.35 | T8635 | 2021-04-19 | 000000020181402 | 4393.35 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 4.739% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $12,980.00 is requested by District (PO2W-20*5064). The total architect cost with change order is $105,694.72
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2021-12-20 | 2021/22 | 2-531 | PO2W-200000000858, 19-100485 | 0 | 4393.35 | 3378 | 2021-12-20 | 000000020370769 | 4393.35 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 4.739% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $12,980.00 is requested by District (PO2W-20*5064). The total architect cost with change order is $105,694.72. Close-out PO.
Los Altos ES-21st Century-Design | 2 | Design | Los Altos ES | 21st Century | TDM Architects, Inc | Architect | 2020-05-11 | 2020-10-21 | 2020/21 | 2-10121 | PO2W-200000005064 | 0 | 12980 | T8578 | 2020-10-21 | 000000020136458 | 12980 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9191101 | 100% | Architect - These are additional changes requested by District since summer of 2019 for Los Altos ES. Changes to include replacing concrete walkway at classrooms in lieu of replacement of landing at door, revising new counter at new sink in classrooms, revising the electrical drawing, etc. Addendum to PO2W-20*858. The total architect cost with change order is $105,694.72
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 2019/20 |  | PO2W-200000004960 | 0 | 4410 | 20200630-07:NEM | 2020-06-19 | 000000020106934 | 4410 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 12.7% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-08-19 | 2020/21 |  | PO2W-200000004960 | 0 | 6440 | 202008-04:LAM | 2020-08-19 | 000000020120364 | 6440 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 18.55% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-10-14 | 2020/21 |  | PO2W-200000004960 | 0 | 5880 | 202009-04:LAM | 2020-10-14 | 000000020134520 | 5880 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 16.94% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-10-21 | 2020/21 |  | PO2W-200000004960 | 0 | 5880 | 202010-04:LAM | 2020-10-21 | 000000020136459 | 5880 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 16.94% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-02-05 | 2020/21 |  | PO2W-200000004960 | 0 | 3080 | 202011-04:LAM | 2021-02-05 | 000000020162579 | 3080 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 8.871% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-03-24 | 2020/21 |  | PO2W-200000004960 | 0 | 1610 | 202102-02:LAM | 2021-03-24 | 000000020174730 | 1610 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 4.637% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-03-24 | 2020/21 |  | PO2W-200000004960 | 0 | 420 | 202103-03:LAM | 2021-03-24 | 000000020174730 | 420 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 1.21% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 | 2-9867 | PO2W-200000004960 | 0 | 4480 | 202101-04:LAM | 2021-04-19 | 000000020181403 | 4480 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 12.9% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004960 | 0 | 2520 | 202012-04:LAM | 2021-04-19 | 000000020181403 | 2520 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 7.258% | General inspection for the project as defined in Title 24. Modernization of Los Altos ES.
Los Altos ES-21st Century-FF & E | 2 | FF & E | Los Altos ES | 21st Century | Warehouse | Paper towel dispenser | 2021-09-01 | 2021-09-03 | 2021/22 |  | XSRQ-220000000971 | 0 | 86.19 |  |  |  | 86.19 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 100% | Classroom paper towel dispensers (2) for Los Altos ES
Los Altos ES-Ceiling replacement-Contractor | 2 | Contractor | Los Altos ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 22069.45 | Pay app #1 | 2019-12-17 | 000000020049998 | 22069.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191105 | 0.4826% | Ceiling replacement for Los Altos ES.
Los Altos ES-Ceiling replacement-Contractor | 2 | Contractor | Los Altos ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 198625.05 | Pay app #3 | 2021-01-08 | 000000020155354 | 198625.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191105 | 4.343% | Ceiling replacement for Los Altos ES.
Los Altos ES-Ceiling replacement-Contractor | 2 | Contractor | Los Altos ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5063 | PO1-200000000729 | 11615.5 | 11615.5 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191105 | 0% | Ceiling replacement for Los Altos ES.
Los Altos ES-Drinking fountain replacement-DSA Fees | 2 | DSA Fees | Los Altos ES | Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7622 | PO1-200000000955 | 0 | 1050 | Per email | 2020-02-13 | 000000020070040 | 1050 | 03-120657 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191104 | 100% | DSA plan check review fee for Los Altos ES drinking fountain.
Los Altos ES-Fire alarm-Design | 2 | Design | Los Altos ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 4750 | 28381 | 2021-03-24 | 000000020174735 | 4750 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 2.772% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The total architect contract for Los Altos ES FA is $47,500.00
Los Altos ES-Fire alarm-Design | 2 | Design | Los Altos ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28466 | 2021-03-24 | 000000020174735 | 2375 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The total architect contract for Los Altos ES FA is $47,500.00
Los Altos ES-Fire alarm-Design | 2 | Design | Los Altos ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28605 | 2021-05-26 | 000000020192536 | 2375 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The total architect contract for Los Altos ES FA is $47,500.00
Los Altos ES-Fire alarm-Design | 2 | Design | Los Altos ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28732 | 2021-09-09 | 000000020255226 | 1425 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 0.8316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The total architect contract for Los Altos ES FA is $47,500.00
Los Altos ES-Fire alarm-Design | 2 | Design | Los Altos ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2022-01-19 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 29052 | 2022-01-19 | 000000020391276 | 950 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 0.5544% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The total architect contract for Los Altos ES FA is $47,500.00
Los Altos ES-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Fire Alarm | Team Inspections | General inspection | 2020-12-15 | 2021-02-09 | 2020/21 |  | PO2W-210000001492 | 0 | 3060 | 202101-12:LAFA | 2021-02-09 | 000000020163358 | 3060 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191103 | 12.49% | General inspection for the project as defined in Title 24 at Los Altos ES. Alterations to fire alarm system
Los Altos ES-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Fire Alarm | Team Inspections | General inspection | 2020-12-15 | 2021-04-19 | 2020/21 |  | PO2W-210000001492 | 0 | 6120 | 202102-10:LAFA | 2021-04-19 | 000000020181403 | 6120 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191103 | 24.98% | General inspection for the project as defined in Title 24 at Los Altos ES. Alterations to fire alarm system
Los Altos ES-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Fire Alarm | Team Inspections | General inspection | 2020-12-15 | 2021-09-09 | 2021/22 | 21-3568 | PO2W-210000001492 | 0 | 500 | 202108-06:LAFA | 2021-09-09 | 000000020255216 | 500 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191103 | 2.041% | General inspection for the project as defined in Title 24 at Los Altos ES. Alterations to fire alarm system
Los Altos ES-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Fire Alarm | Team Inspections | General inspection | 2020-12-15 | 2021-09-13 | 2020/21 |  | PO2W-210000001492 | 0 | 2570 | 20210630-09: LAFA | 2021-09-13 | 000000020257046 | 2570 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191103 | 10.49% | General inspection for the project as defined in Title 24 at Los Altos ES. Alterations to fire alarm system
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 943.35 | Pay app #1 | 2020-03-10 | 000000020079637 | 943.35 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.07372% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-12-18 | 2020/21 |  | PO1-200000000662 | 0 | 16828.3 | Pay app #10 | 2020-12-18 | 000000020151942 | 16828.3 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 1.315% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 39719.92 | Pay app #11 | 2021-05-21 | 000000020191188 | 39719.92 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 3.104% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 610.38 | Pay app #12 | 2021-05-21 | 000000020191188 | 610.38 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.0477% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 10073.04 | Pay app #13 | 2021-05-21 | 000000020191188 | 10073.04 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.7871% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 6352.51 | Pay app #14 | 2021-05-21 | 000000020191188 | 6352.51 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.4964% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 1710 | Pay app #15 | 2021-05-21 | 000000020191188 | 1710 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.1336% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 24679.6 | Pay app #16 | 2021-11-22 | 000000020341778 | 24679.6 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 1.929% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Fire Alarm-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4506 | PO1-200000000662 | 6311.43 | 6311.43 |  |  |  | 0 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0% | Fire alarm and low voltage service for Los Altos ES
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2026-01-16 | 2021/22 | 22-5814 | PO2W-220000001857 | 2782.5 | 2782.5 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month. Bay Alarm purchased Mijac Alarm.
Los Altos ES-Interim Housing-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | Interim Housing | Converse Consultants | Geotechnical | 2019-07-01 | 2019-12-11 | 2019/20 |  | PO2W-200000000203 | 0 | 5280.5 | 19-31241-30-0000001 | 2019-12-11 | 000000020047618 | 5280.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191102 | 36.34% | Geotechnical observation and testing, special inspection and material testing services for 4 portables at Los Altos ES.
Los Altos ES-Interim Housing-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | Interim Housing | Converse Consultants | Geotechnical | 2019-07-01 | 2023-01-16 | 2021/22 | 2-739 | PO2W-200000000203 | 9249.5 | 9249.5 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191102 | 0% | Geotechnical observation and testing, special inspection and material testing services for 4 portables at Los Altos ES.
Los Altos ES-Interim Housing-FF & E | 2 | FF & E | Los Altos ES | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 2450.06 | 30860 | 2021-05-07 | 000000020187156 | 2450.06 | 03-119857 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191102 | 0.3971% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Los Altos ES-Interim Housing-FF & E | 2 | FF & E | Los Altos ES | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 8036.2 | 31584 | 2021-05-25 | 000000020192063 | 8036.2 | 03-119857 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191102 | 1.303% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Los Altos ES-Interim Housing-DSA Fees | 2 | DSA Fees | Los Altos ES | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2019-03-18 | 2019-03-21 | 2018/19 |  | 19-107318 | 0 | 3481.54 | Per email | 2019-03-21 | 25172246 | 3481.54 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191102 | 100% | DSA plan check review fee for Los Altos ES interim housing.
Los Altos ES-Interim Housing-DSA Fees | 2 | DSA Fees | Los Altos ES | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2020-03-06 | 2020-03-11 | 2019/20 | 2-8781 | PO2W-200000004548 | 0 | 2687.5 | 11816 | 2020-03-11 | 000000020080278 | 2687.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191102 | 100% | DSA plan check review fee for Los Altos ES interim housing (Relocation of 4 modular buildings).
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | Education Products & Services | Contractor | 2019-10-14 | 2020-02-12 | 2019/20 | 2-4518 | PO2W-200000002196 | 0 | 1894.88 | EPS6097-2019 | 2020-02-12 | 000000020069435 | 1894.88 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 100% | Installation of 7 new horizontal 1" blinds in 4 portable classrooms at Los Altos ES.
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | GDL Best Contractors, Inc | Contractor | 2019-07-01 | 2019-11-06 | 2019/20 |  | PO2W-200000000121 | 0 | 183825 | Pay app #1 | 2019-11-06 | 000000020035020 | 183825 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 83.37% | 4 portable units at Los Altos ES - demolition,remove and dump grass, relocate existing irrigation, install base, asphalt, electrical service, fire alarm, condensation drains, drywell, metal guards at each HVAC, signage.
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | GDL Best Contractors, Inc | Contractor | 2019-07-01 | 2020-06-16 | 2019/20 | 2-724 | PO2W-200000000121 | 0 | 11025 | Pay app #3 | 2020-06-16 | 000000020105600 | 11025 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 5% | 4 portable units at Los Altos ES - demolition,remove and dump grass, relocate existing irrigation, install base, asphalt, electrical service, fire alarm, condensation drains, drywell, metal guards at each HVAC, signage.
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | GDL Best Contractors, Inc | Contractor | 2019-07-01 | 2020-06-16 | 2019/20 |  | PO2W-200000000121 | 0 | 25650 | Pay app #2 | 2020-06-16 | 000000020105600 | 25650 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 11.63% | 4 portable units at Los Altos ES - demolition,remove and dump grass, relocate existing irrigation, install base, asphalt, electrical service, fire alarm, condensation drains, drywell, metal guards at each HVAC, signage.
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2019-11-05 | 2019/20 |  | PO1-200000000617 | 0 | 79.5 | 446143 | 2019-11-05 | 000000020034486 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2020-01-14 | 2019/20 |  | PO1-200000000617 | 0 | 79.5 | 449936 | 2020-01-14 | 000000020057282 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2020-04-07 | 2019/20 |  | PO1-200000000617 | 0 | 79.5 | 454218 | 2020-04-07 | 000000020087144 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2020-08-17 | 2020/21 |  | PO1-200000000617 | 0 | 79.5 | 458282 | 2020-08-17 | 000000020119792 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2020-10-13 | 2020/21 |  | PO1-200000000617 | 0 | 79.5 | 462413 | 2020-10-13 | 000000020134095 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-01-15 | 2020/21 |  | PO1-200000000617 | 0 | 79.5 | 466515 | 2021-01-15 | 000000020157266 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-04-16 | 2020/21 |  | PO1-200000000617 | 0 | 79.5 | 470595 | 2021-04-16 | 000000020181033 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-11-30 | 2021/22 |  | PO1-200000000617 | 0 | 79.5 | 474504 | 2021-11-30 | 000000020345298 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-11-30 | 2021/22 | 2-4011 | PO1-200000000617 | 0 | 79.5 | 478578 | 2021-11-30 | 000000020345298 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring for 4 portables at Los Altos ES. From Oct 1, 2019 at $26.50/month. Close-out PO. Bay Alarm purchased Mijac.
Los Altos ES-Interim Housing-Modular Buildings | 2 | Modular Buildings | Los Altos ES | Interim Housing | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-01-16 | 2019/20 | 2-2084 | PO2W-200000001050, 19-107587 | 0 | 236959.74 | R20521588-1KR | 2020-01-16 | 000000020058725 | 236959.74 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9191102 | 100% | Purchase of 4 Portable classrooms - 24' x 40' DSA, install closure panels, new carpets, HVAC, T-8 lights lines, and delivery to Los Altos ES.
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | TDM Architects, Inc | Architect | 2018-07-17 | 2018-11-20 | 2018/19 |  | PO2W-200000000857, 19-100486 | 0 | 1515.6 | T8221 | 2018-11-20 | 24940853 | 1515.6 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 2.618% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00.
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | TDM Architects, Inc | Architect | 2018-07-17 | 2019-02-06 | 2018/19 |  | PO2W-200000000857, 19-100486 | 0 | 3410.12 | T8241 | 2019-02-06 | 25078803 | 3410.12 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 5.891% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00.
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | TDM Architects, Inc | Architect | 2018-07-17 | 2019-03-28 | 2018/19 |  | PO2W-200000000857, 19-100486 | 0 | 4774.16 | T8272 | 2019-03-28 | 25196520 | 4774.16 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 8.247% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00.
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | TDM Architects, Inc | Architect | 2018-07-17 | 2019-09-05 | 2018/19 |  | PO2W-200000000857, 19-100486 | 0 | 14928.74 | T8310 | 2019-09-05 | 000000020011699 | 14928.74 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 25.79% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00.
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | TDM Architects, Inc | Architect | 2018-07-17 | 2019-11-15 | 2019/20 |  | PO2W-200000000857, 19-100486 | 0 | 2816 | T8391 | 2019-11-15 | 000000020038501 | 2816 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 4.864% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. Allowances for topographic survey.
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | TDM Architects, Inc | Architect | 2018-07-17 | 2019-12-11 | 2019/20 |  | PO2W-200000000857, 19-100486 | 0 | 9472.55 | T8429 | 2019-12-11 | 000000020047665 | 9472.55 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 16.36% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00.
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | TDM Architects, Inc | Architect | 2018-07-17 | 2020-06-04 | 2019/20 |  | PO2W-200000000857, 19-100486 | 0 | 3789.01 | T8519 | 2020-06-04 | 000000020102555 | 3789.01 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 6.545% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00.
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | TDM Architects, Inc | Architect | 2018-07-17 | 2023-07-11 | 2021/22 | 2-529 | PO2W-200000000857, 19-100486 | 17184 | 17184 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 0% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00.
Los Altos ES-Interim Housing-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Interim Housing | Team Inspections | General inspection | 2019-07-01 | 2019-12-11 | 2019/20 |  | PO2W-200000000103 | 0 | 9900 | 201911-01:LAR | 2019-12-11 | 000000020047668 | 9900 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191102 | 75% | General inspection for the project as defined in Title 24 for Los Altos ES. Relocation of 4 modular classrooms
Los Altos ES-Interim Housing-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Interim Housing | Team Inspections | General inspection | 2019-07-01 | 2020-01-15 | 2019/20 | 2-737 | PO2W-200000000103 | 0 | 3300 | 201912-05:LAR | 2020-01-15 | 000000020057959 | 3300 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191102 | 25% | General inspection for the project as defined in Title 24 for Los Altos ES. Relocation of 4 modular classrooms
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | Universal Asphalt | Contractor | 2019-07-23 | 2019-08-05 | 2019/20 | 2 -1131 | PO2W-200000000237 | 0 | 13776 | 40499 | 2019-09-03 | 000000020010771 | 13776 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 100% | Furnish & install asphalatic concrete over 4,800 SF @ $2.87/SF at Los Altos ES.
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | Universal Asphalt | Contractor | 2019-07-23 | 2019-09-03 | 2019/20 | 2-2002 | PO2W-200000000632 | 0 | 4879 | 40500 | 2019-09-03 | 000000020010771 | 4879 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 100% | Additional work to furnish & install asphalatic concrete over 1,700 SF @ $2.87/SF at Los Altos ES.
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | Universal Asphalt | Contractor | 2019-09-26 | 2019-10-25 | 2019/20 | 2-3684 | PO2W-200000001460 | 0 | 13902 | 40610 | 2019-10-25 | 000000020031054 | 13902 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 100% | Grind & remove existing AC as needed for paving, haul off debris, & furnish & install 3" AC cover over 4" base 2,100 SF at $6.62/SF - ramp to portables at Los Altos ES.
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15525.78 | 0173444-IN | 2019-10-10 | 000000020025135 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9411101 | 0.3574% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 28334.56 | 0173701-IN | 2019-10-10 | 000000020025135 | 28334.56 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9411101 | 0.6522% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 388.14 | 0173889-IN | 2019-10-10 | 000000020025135 | 388.14 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9411101 | 0.008934% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 200 | 0173444-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173444-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173444-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 380 | 0173444-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173444-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173444-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 109.5 | 0173701-IN | 2019-10-10 | 000000020025135 | 109.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.00252% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 219 | 0173701-IN | 2019-10-10 | 000000020025135 | 219 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.005041% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 365 | 0173701-IN | 2019-10-10 | 000000020025135 | 365 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.008401% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 693.5 | 0173701-IN | 2019-10-10 | 000000020025135 | 693.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.01596% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 849.72 | 0173701-IN | 2019-10-10 | 000000020025135 | 849.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.01956% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2338.19 | 0173701-IN | 2019-10-10 | 000000020025135 | 2338.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.05382% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 32.03 | 0173889-IN | 2019-10-10 | 000000020025135 | 32.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.0007372% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 11.64 | 0173889-IN | 2019-10-10 | 000000020025135 | 11.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.0002679% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9.5 | 0173889-IN | 2019-10-10 | 000000020025135 | 9.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.0002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5 | 0173889-IN | 2019-10-10 | 000000020025135 | 5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.0001151% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3 | 0173889-IN | 2019-10-10 | 000000020025135 | 3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 6.905e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1.5 | 0173889-IN | 2019-10-10 | 000000020025135 | 1.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 3.452e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 580276.25 | 0174379-IN | 2019-10-10 | 000000020025136 | 580276.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9411101 | 13.36% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2242.5 | 0174379-IN | 2019-10-10 | 000000020025136 | 2242.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.05161% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4485 | 0174379-IN | 2019-10-10 | 000000020025136 | 4485 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.1032% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7475 | 0174379-IN | 2019-10-10 | 000000020025136 | 7475 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.172% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 14202.5 | 0174379-IN | 2019-10-10 | 000000020025136 | 14202.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.3269% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 17401.8 | 0174379-IN | 2019-10-10 | 000000020025136 | 17401.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.4005% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 47884.85 | 0174379-IN | 2019-10-10 | 000000020025136 | 47884.85 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 1.102% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173472-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9411101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Los Altos HS. Total cart: 1
Los Altos HS-21st Century-Technology | 5 | Technology | Los Altos HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-11-07 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 55913.91 | 0174574-IN | 2019-11-07 | 000000020035575 | 55913.91 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9411101 | 7.046% | Ergotron Zip40 Charging carts to store laptops at Los Altos HS. Total carts: 43
Los Altos HS-21st Century-Contractor | 5 | Contractor | Los Altos HS | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-03-24 | 2020/21 |  | PO2W-200000004391 | 0 | 19116.72 | Pay app #5 | 2021-03-24 | 000000020174719 | 19116.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9411101 | 4.246% | Prep & install Mohawk LVT, walk off mat & base at Los Altos HS for room #J10, J11, & J14
Los Altos HS-21st Century-Environ Consultant | 5 | Environ Consultant | Los Altos HS | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2021-01-19 | 2020/21 | 21-1581 | PO1-210000000427 | 0 | 4350 | MCSI-4658 | 2021-01-19 | 000000020157533 | 4350 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9411101 | 10.56% | Asbestos & lead-based paint survey of Los Altos HS permanent buildings.
Los Altos HS-Drinking fountain replacement-Contractor | 5 | Contractor | Los Altos HS | Drinking fountain replacement | Optima | Contractor | 2019-08-20 | 2020-02-10 | 2019/20 | 2-4817 | PO2W-200000002204 | 0 | 6600 | 5000187 | 2020-02-10 | 000000020068412 | 6600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9411104 | 100% | Provide & install 1 new drinking fountain at Los Altos HS.
Los Altos HS-Fire Alarm-DSA Fees | 5 | DSA Fees | Los Altos HS | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3167 | PO2W-200000001053 | 0 | 5500 | Per email | 2019-09-13 | 000000020015011 | 5500 | 03-120155 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9411103 | 100% | DSA plan check review fee for Los Altos HS fire alarm.
Los Altos HS-Fire alarm-Design | 5 | Design | Los Altos HS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 2021/22 | 21-1992 | PO2W-210000000680 | 13950 | 13950 |  |  |  | 0 | 03-120155 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9411103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos HS. Facilities paid PO1-20*907 & 19-109186 in the amount of $41,850.00. The total architect contract for Los Altos HS FA is $55,800.00
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 8927.33 | 0173684-IN | 2019-10-10 | 000000020025135 | 8927.33 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9201101 | 0.2055% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 115 | 0173684-IN | 2019-10-10 | 000000020025135 | 115 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.002647% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 69 | 0173684-IN | 2019-10-10 | 000000020025135 | 69 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.001588% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 34.5 | 0173684-IN | 2019-10-10 | 000000020025135 | 34.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.0007941% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 218.5 | 0173684-IN | 2019-10-10 | 000000020025135 | 218.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.005029% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 267.72 | 0173684-IN | 2019-10-10 | 000000020025135 | 267.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.006162% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 736.69 | 0173684-IN | 2019-10-10 | 000000020025135 | 736.69 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.01696% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 95095.44 | 0175473-IN | 2019-10-22 | 000000020029495 | 95095.44 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9201101 | 3.39% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 367.5 | 0175473-IN | 2019-10-22 | 000000020029495 | 367.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.0131% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 735 | 0175473-IN | 2019-10-22 | 000000020029495 | 735 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.0262% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1225 | 0175473-IN | 2019-10-22 | 000000020029495 | 1225 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.04366% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2327.5 | 0175473-IN | 2019-10-22 | 000000020029495 | 2327.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.08296% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2851.8 | 0175473-IN | 2019-10-22 | 000000020029495 | 2851.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.1016% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7847.35 | 0175473-IN | 2019-10-22 | 000000020029495 | 7847.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.2797% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245
Los Molinos-21st Century-Technology | 4 | Technology | Los Molinos | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 28607.12 | 0175494-IN | 2019-10-22 | 000000020029495 | 28607.12 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9201101 | 3.605% | Ergotron Zip40 Charging carts to store laptops at Los Molinos. Total carts: 22
Los Molinos-21st Century-FF & E | 4 | FF & E | Los Molinos | 21st Century | Culver Newlin | Furniture | 2019-10-22 | 2020-04-15 | 2019/20 | 2-4685 | PO3W-200000001600 | 0 | 12545.73 | 29073 | 2020-04-15 | 000000020089465 | 12545.73 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9201101 | 59.26% | Furniture for Los Molinos' room #6. Stackable desks, student chairs, tables, mobile tables, stools, cubbies, desks, and rugs
Los Molinos-21st Century-FF & E | 4 | FF & E | Los Molinos | 21st Century | Culver Newlin | Furniture | 2019-10-22 | 2020-04-15 | 2019/20 | 2-4685 | PO3W-200000001600 | 0 | 8623.69 | 29073 | 2020-04-15 | 000000020089465 | 8623.69 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9201101 | 40.74% | Furniture for Los Molinos' room #6. Stackable desks, student chairs, tables, mobile tables, stools, cubbies, desks, and rugs
Los Molinos-21st Century-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 960 | 100653 | 2021-09-08 | 000000020253624 | 960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 0.05248% | Construction management services for Los Molinos - phase 3 & 4. This PO includes allowances of $40,000.00
Los Molinos-21st Century-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 4280 | 101514 | 2021-09-29 | 000000020275054 | 4280 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 0.234% | Construction management services for Los Molinos - phase 3 & 4. This PO includes allowances of $40,000.00
Los Molinos-21st Century-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2024-07-01 | 2021/22 | 22-1057 | PO1-220000000334 | 270840 | 270840 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 0% | Construction management services for Los Molinos - phase 3 & 4. This PO includes allowances of $40,000.00
Los Molinos-21st Century-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862 | 0 | 5650 | 102578 | 2021-11-08 | 000000020325325 | 5650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 11.52% | Construction management services for Baldwin - phase 3 & 4. This PO is to pay invoice #102578 (Prof service from 09/01-09/30/21), dated 09/30/21
Los Molinos-21st Century-Contractor | 4 | Contractor | Los Molinos | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2023-01-06 | 2020/21 | 21-3656 | PO2W-210000001556 | 0 | 37500 | 2021-006D | 2021-03-24 | 000000020174720 | 37500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201101 | 38.46% | Demo of ceiling tiles in 15 classrooms at Los Molinos
Los Molinos-21st Century-Environ Consultant | 4 | Environ Consultant | Los Molinos | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10243 | PO2W-200000005321 | 0 | 2600 | MCSI-4539 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9201101 | 100% | Asbestos & lead-based paint survey of Los Molinos' permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Los Molinos-21st Century-Design | 4 | Design | Los Molinos | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002225 | 0 | 25060.16 | T8704 | 2021-09-09 | 000000020255214 | 25060.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201101 | 9.35% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Los Molinos. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Los Molinos-21st Century-Design | 4 | Design | Los Molinos | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002225 | 0 | 8326.87 | 3297 | 2021-10-19 | 000000020302604 | 8326.87 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201101 | 3.107% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Los Molinos. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Los Molinos-21st Century-Design | 4 | Design | Los Molinos | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6240 | PO2W-210000002225 | 234636.97 | 234636.97 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Los Molinos. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Los Molinos-Ceiling replacement-Contractor | 4 | Contractor | Los Molinos | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 34108.32 | Pay app #1 | 2019-12-17 | 000000020049998 | 34108.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201105 | 0.7458% | Ceiling replacement for Los Molinos.
Los Molinos-Ceiling replacement-Contractor | 4 | Contractor | Los Molinos | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 102324.98 | Pay app #2 | 2020-10-21 | 000000020136454 | 102324.98 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201105 | 2.237% | Ceiling replacement for Los Molinos.
Los Molinos-Ceiling replacement-Contractor | 4 | Contractor | Los Molinos | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-04-27 | 2020/21 |  | PO1-200000000729 | 0 | 204649.95 | Pay app #3 | 2021-04-27 | 000000020183628 | 204649.95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201105 | 4.475% | Ceiling replacement for Los Molinos.
Los Molinos-Ceiling replacement-Contractor | 4 | Contractor | Los Molinos | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5064 | PO1-200000000729 | 17951.75 | 17951.75 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201105 | 0% | Ceiling replacement for Los Molinos.
Los Molinos-Drinking fountain replacement-DSA Fees | 4 | DSA Fees | Los Molinos | Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-05-05 | 2020/21 | 21-6130 | PO2W-210000002164 | 0 | 1050 | Per email | 2021-05-05 | 000000020186221 | 1050 | 03-121641 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9201104 | 50% | DSA plan check review fee for Los Molinos' drinking fountain
Los Molinos-Fire alarm-Reprographics | 4 | Reprographics | Los Molinos | Fire alarm | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-02-08 | 2020/21 |  | PO1-210000000492 | 0 | 422.21 | 10842654 | 2021-02-08 | 000000020162966 | 422.21 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201103 | 8.444% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Los Molinos
Los Molinos-Fire Alarm-DSA Fees | 4 | DSA Fees | Los Molinos | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3176 | PO2W-200000001058 | 0 | 870 | Per email | 2019-09-13 | 000000020015014 | 870 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9201103 | 100% | DSA plan check review fee for Los Molinos fire alarm.
Los Molinos-Fire alarm-Design | 4 | Design | Los Molinos | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28384 | 2021-03-24 | 000000020174735 | 2425 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Mollinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The total architect contract for Los Molinos FA is $48,500.00
Los Molinos-Fire alarm-Design | 4 | Design | Los Molinos | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28471 | 2021-03-24 | 000000020174735 | 2425 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 1.415% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Mollinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The total architect contract for Los Molinos FA is $48,500.00
Los Molinos-Fire alarm-Design | 4 | Design | Los Molinos | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 4850 | 28607 | 2021-05-26 | 000000020192536 | 4850 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 2.83% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Mollinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The total architect contract for Los Molinos FA is $48,500.00
Los Molinos-Fire alarm-Design | 4 | Design | Los Molinos | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1455 | 28734 | 2021-09-09 | 000000020255226 | 1455 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 0.8491% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Mollinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The total architect contract for Los Molinos FA is $48,500.00
Los Molinos-Fire alarm-Design | 4 | Design | Los Molinos | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 2021/22 | 21-1992 | PO2W-210000000680 | 970 | 970 |  |  |  | 0 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Mollinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The total architect contract for Los Molinos FA is $48,500.00
Los Molinos-Fire Alarm-DSA Inspection | 4 | DSA Inspection | Los Molinos | Fire Alarm | Team Inspections | General inspection | 2021-01-14 | 2021-10-19 | 2021/22 | 21-3784 | PO2W-210000001585 | 0 | 14350 | 202110-05:LMFA | 2021-10-19 | 000000020302605 | 14350 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9201103 | 50% | General inspection for the project as defined in Title 24 at Los Molinos. Alterations to fire alarm system
Los Molinos-Fire Alarm-Contractor | 4 | Contractor | Los Molinos | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-03-18 | 2020/21 |  | PO2W-200000004929 | 0 | 102643.66 | Pay app #1 | 2021-03-18 | 000000020173348 | 102643.66 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9201103 | 54.33% | Installation of a new fire alarm devices on the existing fire alarm control panel at Los Molinos. Change order of $34,440.93 is created using Facilities' account string (PO2W-22*914). The total project cost with change order is $223,355.69
Los Molinos-Fire Alarm-Contractor | 4 | Contractor | Los Molinos | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-05-21 | 2020/21 |  | PO2W-200000004929 | 0 | 49407.6 | Pay app #2 | 2021-05-21 | 000000020191188 | 49407.6 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9201103 | 26.15% | Installation of a new fire alarm devices on the existing fire alarm control panel at Los Molinos. Change order of $34,440.93 is created using Facilities' account string (PO2W-22*914). The total project cost with change order is $223,355.69
Los Molinos-Fire Alarm-Contractor | 4 | Contractor | Los Molinos | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-05-21 | 2020/21 |  | PO2W-200000004929 | 0 | 26150.38 | Pay app #3 | 2021-05-21 | 000000020191188 | 26150.38 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9201103 | 13.84% | Installation of a new fire alarm devices on the existing fire alarm control panel at Los Molinos. Change order of $34,440.93 is created using Facilities' account string (PO2W-22*914). The total project cost with change order is $223,355.69
Los Molinos-Fire Alarm-Contractor | 4 | Contractor | Los Molinos | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2023-07-11 | 2021/22 | 2-9610 | PO2W-200000004929 | 10713.12 | 10713.12 |  |  |  | 0 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9201103 | 0% | Installation of a new fire alarm devices on the existing fire alarm control panel at Los Molinos. Change order of $34,440.93 is created using Facilities' account string (PO2W-22*914). The total project cost with change order is $223,355.69
Los Molinos-Interim Housing-Design | 4 | Design | Los Molinos | Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6245 | PO2W-210000002230 | 79400 | 79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201102 | 0% | Architect - Prepare design documents for Los Molinos Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4269.59 | 0173646-IN | 2019-10-10 | 000000020025135 | 4269.59 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9211101 | 0.09827% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 128.04 | 0173646-IN | 2019-10-10 | 000000020025135 | 128.04 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.002947% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 104.5 | 0173646-IN | 2019-10-10 | 000000020025135 | 104.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.002405% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 55 | 0173646-IN | 2019-10-10 | 000000020025135 | 55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.001266% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 33 | 0173646-IN | 2019-10-10 | 000000020025135 | 33 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.0007595% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 352.33 | 0173646-IN | 2019-10-10 | 000000020025135 | 352.33 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.008109% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 16.5 | 0173646-IN | 2019-10-10 | 000000020025135 | 16.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.0003798% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 50458.8 | 0175393-IN | 2019-10-22 | 000000020029495 | 50458.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9211101 | 1.799% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 195 | 0175393-IN | 2019-10-22 | 000000020029495 | 195 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.006951% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 390 | 0175393-IN | 2019-10-22 | 000000020029495 | 390 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.0139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 650 | 0175393-IN | 2019-10-22 | 000000020029495 | 650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.02317% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1235 | 0175393-IN | 2019-10-22 | 000000020029495 | 1235 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.04402% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1513.2 | 0175393-IN | 2019-10-22 | 000000020029495 | 1513.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.05394% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 4163.9 | 0175393-IN | 2019-10-22 | 000000020029495 | 4163.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.1484% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130
Los Robles-21st Century-Technology | 9 | Technology | Los Robles | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 13003.22 | 0175400-IN | 2019-10-15 | 000000020026572 | 13003.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9211101 | 1.639% | Ergotron Zip40 Charging carts to store laptops at Los Robles. Total carts: 10
Los Robles-21st Century-Contractor | 9 | Contractor | Los Robles | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-04-06 | 2021-05-26 | 2020/21 | 21-5873 | PO2W-210000002060 | 0 | 40000 | 2021-044D | 2021-05-26 | 000000020192522 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9211101 | 48.48% | Demo of ceiling tiles in 16 classrooms at Los Robles
Los Robles-21st Century-Environ Consultant | 9 | Environ Consultant | Los Robles | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10244 | PO2W-200000005322 | 0 | 2800 | MCSI-4540 | 2020-08-17 | 000000020119790 | 2800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9211101 | 100% | Asbestos & lead-based paint survey of Los Robles' permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Los Robles-Ceiling replacement-Contractor | 9 | Contractor | Los Robles | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 20840.81 | Pay app #1 | 2019-12-17 | 000000020049998 | 20840.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9211105 | 0.4557% | Ceiling replacement for Los Robles.
Los Robles-Ceiling replacement-Contractor | 9 | Contractor | Los Robles | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 187567.34 | Pay app #5 | 2021-06-17 | 000000020198995 | 187567.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9211105 | 4.101% | Ceiling replacement for Los Robles.
Los Robles-Ceiling replacement-Contractor | 9 | Contractor | Los Robles | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5065 | PO1-200000000729 | 10968.85 | 10968.85 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9211105 | 0% | Ceiling replacement for Los Robles.
Los Robles-Fire alarm-DSA Fees | 9 | DSA Fees | Los Robles | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 900 | Per email | 2021-03-30 | 000000020176204 | 900 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9211103 | 12.68% | DSA plan check review fee for Los Robles fire alarm.
Los Robles-Fire alarm-Design | 9 | Design | Los Robles | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28230 | 2021-02-05 | 000000020162584 | 7275 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles.
Los Robles-Fire alarm-Design | 9 | Design | Los Robles | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28291 | 2021-02-09 | 000000020163360 | 7275 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles.
Los Robles-Fire alarm-Design | 9 | Design | Los Robles | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28387 | 2021-03-24 | 000000020174735 | 7275 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles.
Los Robles-Fire alarm-Design | 9 | Design | Los Robles | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28516 | 2021-05-26 | 000000020192536 | 2425 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles.
Los Robles-Fire alarm-Design | 9 | Design | Los Robles | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28610 | 2021-05-26 | 000000020192536 | 9700 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles.
Los Robles-Fire alarm-Design | 9 | Design | Los Robles | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28686 | 2021-06-23 | 000000020200466 | 1455 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0.3731% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles.
Los Robles-Fire alarm-Design | 9 | Design | Los Robles | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28835 | 2021-09-09 | 000000020255227 | 970 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0.2487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles.
Los Robles-Fire alarm-Design | 9 | Design | Los Robles | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2025-10-20 | 2021/22 | 21-2535 | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles.
Mesa Robles-21st Century-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 40.84 | 10744155 | 2020-10-13 | 000000020134052 | 40.84 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.157% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles.
Mesa Robles-21st Century-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 20.51 | 10744848 | 2020-10-13 | 000000020134052 | 20.51 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.5809% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles.
Mesa Robles-21st Century-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 106.6 | 10742434 | 2020-10-13 | 000000020134052 | 106.6 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 3.019% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles.
Mesa Robles-21st Century-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 |  | PO1-200000001133 | 0 | 41.16 | 10746782 | 2020-10-20 | 000000020136011 | 41.16 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.166% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles.
Mesa Robles-21st Century-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 |  | PO1-200000001133 | 0 | 7.03 | 10746778 | 2020-10-20 | 000000020136011 | 7.03 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.1991% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles.
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 17854.66 | 0173717-IN | 2019-10-10 | 000000020025135 | 17854.66 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9221101 | 0.411% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 138 | 0173717-IN | 2019-10-10 | 000000020025135 | 138 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.003176% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 69 | 0173717-IN | 2019-10-10 | 000000020025135 | 69 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.001588% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 230 | 0173717-IN | 2019-10-10 | 000000020025135 | 230 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.005294% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 437 | 0173717-IN | 2019-10-10 | 000000020025135 | 437 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.01006% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 535.44 | 0173717-IN | 2019-10-10 | 000000020025135 | 535.44 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.01232% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1473.38 | 0173717-IN | 2019-10-10 | 000000020025135 | 1473.38 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.03391% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 357093.08 | 0175413-IN | 2019-10-22 | 000000020029495 | 357093.08 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9221101 | 12.73% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1380 | 0175413-IN | 2019-10-22 | 000000020029495 | 1380 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.04919% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2760 | 0175413-IN | 2019-10-22 | 000000020029495 | 2760 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.09838% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 4600 | 0175413-IN | 2019-10-22 | 000000020029495 | 4600 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.164% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 8740 | 0175413-IN | 2019-10-22 | 000000020029495 | 8740 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.3115% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 10708.8 | 0175413-IN | 2019-10-22 | 000000020029495 | 10708.8 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.3817% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 29467.6 | 0175413-IN | 2019-10-22 | 000000020029495 | 29467.6 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 1.05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 48111.97 | 0175412-IN | 2019-10-22 | 000000020029495 | 48111.97 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 6.063% | Ergotron Zip40 Charging carts to store laptops at Mesa Robles. Total carts: 37
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-12-02 | 2021-03-04 | 2020/21 |  | PO3W-210000001075 | 0 | 21084.19 | 0195589-IN | 2021-03-04 | 000000020169354 | 21084.19 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 15.32% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Mesa Robles. Total monitors: 38
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-12-02 | 2021-04-09 | 2020/21 | 21-3335 | PO3W-210000001075 | 0 | 61934.82 | 0196289-IN | 2021-04-09 | 000000020179111 | 61934.82 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 45% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Mesa Robles. Total monitors: 38
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | 3022.54 | 0193365-IN | 2021-01-22 | 000000020158901 | 3022.54 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 4.552% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Mesa Robles (4 year warranty). Total computers: 38
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | 37032.9 | 0193365-IN | 2021-01-22 | 000000020158901 | 37032.9 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 55.77% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Mesa Robles (4 year warranty). Total computers: 38
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-03-04 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | -4.16 | 193365C-CM | 2021-03-04 | 000000020169354 | -4.16 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | -0.006265% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Mesa Robles (4 year warranty). Total computers: 38. Credit memo from vendor
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2021-06-14 | 2022-02-04 | 2021/22 | 21-6817 | PO3W-210000003053 | 0 | 10923.55 | 0205447-IN | 2022-02-04 | 000000020406994 | 10923.55 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 100% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Mesa Robles. Total monitors: 5
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Camcor | Document camera(s) | 2020-12-02 | 2021-04-14 | 2020/21 | 21-3339 | PO3W-210000001076 | 0 | 23590.37 | 2508704 | 2021-04-14 | 000000020180213 | 23590.37 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 60.32% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Mesa Robles. Total cameras: 38
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 608.3 | 8316064 | 2021-03-05 | 000000020169721 | 608.3 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 15.87% | C2G HDMI and USB pass through wall plates for Mesa Robles. Total items: 40
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 107.92 | 5725548 | 2021-03-05 | 000000020169721 | 107.92 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 2.816% | C2G HDMI and USB pass through wall plates for Mesa Robles. Total items: 40
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 510.18 | 8312741 | 2021-03-05 | 000000020169721 | 510.18 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 13.31% | C2G HDMI and USB pass through wall plates for Mesa Robles. Total items: 40
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2020-11-30 | 2020/21 |  | PO2W-210000000935 | 0 | 194607.5 | Pay app #1 | 2020-11-30 | 000000020145581 | 194607.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 6.284% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-01-07 | 2020/21 |  | PO2W-210000000935 | 0 | 171275.5 | Pay app #2 | 2021-01-07 | 000000020154782 | 171275.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 5.53% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-02-11 | 2020/21 |  | PO2W-210000000935 | 0 | 216182 | Pay app #3 | 2021-02-11 | 000000020164229 | 216182 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 6.98% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-02-11 | 2020/21 |  | PO2W-210000000935 | 0 | 331075 | Pay app #4 | 2021-02-11 | 000000020164229 | 331075 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 10.69% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-03-16 | 2020/21 |  | PO2W-210000000935 | 0 | 299915 | Pay app #5 | 2021-03-16 | 000000020172574 | 299915 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 9.684% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-04-06 | 2020/21 |  | PO2W-210000000935 | 0 | 476649.8 | Pay app #6 | 2021-04-06 | 000000020177857 | 476649.8 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 15.39% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-05-17 | 2020/21 |  | PO2W-210000000935 | 0 | 481460 | Pay app #7 | 2021-05-17 | 000000020189638 | 481460 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 15.55% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-06-17 | 2020/21 |  | PO2W-210000000935 | 0 | 492670 | Pay app #8 | 2021-06-17 | 000000020198970 | 492670 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 15.91% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-07-08 | 2020/21 |  | PO2W-210000000935 | 0 | 134615 | Pay app #9 | 2021-07-08 | 000000020206245 | 134615 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 4.347% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-09-09 | 2021/22 |  | PO2W-210000000935 | 0 | 143700.2 | Pay app #10 | 2021-09-09 | 000000020255185 | 143700.2 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 4.64% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2022-01-05 | 2021/22 |  | PO2W-210000000935 | 0 | 130557.95 | Pay app #11 | 2022-01-05 | 000000020376882 | 130557.95 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 4.216% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2023-10-16 | 2021/22 | 21-2506 | PO2W-210000000935 | 24292.05 | 24292.05 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 0% | 21st Century classroom modification at Mesa Robles. Base bid #1. Change order amount is $137,429.42 (xreq 22-3690). The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Chalmers Construction Services, Inc. | Contractor | 2021-12-16 | 2023-12-16 | 2021/22 | 22-3690 | PO2W-220000001552 | 137429.42 | 137429.42 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221101 | 0% | Change orders for the 21st Century classroom at Mesa Robles. Change orders for the additional cost to change CAT 6 cables to CAT 6A, Frame, install plywood, and install new tackable wall on top section of windows, Demo of 2 portable bldgs, Relocate & rewire 4 thermostats, Bead blast classrm E4 floor for second time, Remove wire mold & tracing out existing circuits, Re-feed existing receptacle in library, Add pathways, wiring, programming & relays to interface the TOP CAT & fire alarm systems, Provide & install shut off valve for bldg H. Addendum to PO2W-21*935. The total project cost with change order is $3,234,429.42
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 233.02 | 30860 | 2021-05-07 | 000000020187156 | 233.02 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 0.03777% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-03-23 | 2020/21 |  | PO2W-210000001658 | 0 | 15400.08 | 31134 | 2021-03-23 | 000000020174427 | 15400.08 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 20.09% | Furniture for Mesa Robles students grade 1-3 (Room E-1 through E4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-03-23 | 2020/21 |  | PO2W-210000001658 | 0 | 9983.73 | 31134 | 2021-03-23 | 000000020174427 | 9983.73 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 13.03% | Furniture for Mesa Robles students grade 1-3 (Room E-1 through E4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-08-16 | 2021/22 | 21-4031 | PO2W-210000001658 | 0 | 40602.59 | 32079 | 2021-08-16 | 000000020230714 | 40602.59 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 52.98% | Furniture for Mesa Robles students grade 1-3 (Room E-1 through E4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-08-16 | 2021/22 | 21-4031 | PO2W-210000001658 | 0 | 10649.98 | 32079 | 2021-08-16 | 000000020230714 | 10649.98 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 13.9% | Furniture for Mesa Robles students grade 1-3 (Room E-1 through E4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 | 21-4036 | PO2W-210000001660 | 0 | 82847.7 | 31137 | 2021-03-24 | 000000020174718 | 82847.7 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 72.8% | Furniture for Mesa Robles students grade 4-8 (Room K-30 through K-33, & C-1, & C-2). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 |  | PO2W-210000001660 | 0 | 14975.59 | 31137 | 2021-03-24 | 000000020174718 | 14975.59 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 13.16% | Furniture for Mesa Robles students grade 4-8 (Room K-30 through K-33, & C-1, & C-2). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-01-28 | 2021-04-19 | 2020/21 | 21-4036 | PO2W-210000001660 | 0 | 15974.96 | 31182 | 2021-04-19 | 000000020181375 | 15974.96 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 14.04% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 | 21-6171 | PO2W-210000002169 | 0 | 113255.85 | 32252 | 2021-08-16 | 000000020230714 | 113255.85 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 73.21% | Furniture for Mesa Robles students grade 4-8 (Room D-12 through D-15, G-5, G-6, G-11, & G-12). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 |  | PO2W-210000002169 | 0 | 14687.37 | 32252 | 2021-08-16 | 000000020230714 | 14687.37 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 9.494% | Furniture for Mesa Robles students grade 4-8 (Room D-12 through D-15, G-5, G-6, G-11, & G-12). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 |  | PO2W-210000002169 | 0 | 20610.09 | 32275 | 2021-08-16 | 000000020230714 | 20610.09 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 13.32% | Furniture for Mesa Robles students grade 4-8 (Room D-12 through D-15, G-5, G-6, G-11, & G-12). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-04-29 | 2021-09-30 | 2021/22 | 21-6171 | PO2W-210000002169 | 0 | 6156.09 | 32477 | 2021-09-30 | 000000020276414 | 6156.09 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 3.979% | Furniture for Mesa Robles students grade 4-8 (Room D-12 through D-15, G-5, G-6, G-11, & G-12). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6364 | PO2W-210000002282 | 0 | 56627.92 | 32253 | 2021-08-16 | 000000020230714 | 56627.92 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 73.21% | Furniture for Mesa Robles students grade 1-3. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6364 | PO2W-210000002282 | 0 | 20726.78 | 32253 | 2021-08-16 | 000000020230714 | 20726.78 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 26.79% | Furniture for Mesa Robles students grade 1-3. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6365 | PO2W-210000002283 | 0 | 169883.76 | 32255 | 2021-08-16 | 000000020230714 | 169883.76 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 73.21% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6365 | PO2W-210000002283 | 0 | 62180.33 | 32255 | 2021-08-16 | 000000020230714 | 62180.33 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 26.79% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-09-07 | 2022-01-24 | 2021/22 | 22-1681 | PO2W-220000000464 | 0 | 29690.92 | 33532 | 2022-01-24 | 000000020395770 | 29690.92 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 72.65% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2021-09-07 | 2022-01-24 | 2021/22 | 22-1681 | PO2W-220000000464 | 0 | 11175.25 | 33532 | 2022-01-24 | 000000020395770 | 11175.25 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 27.35% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Culver Newlin | Furniture | 2022-01-14 | 2023-01-14 | 2021/22 | 22-3985 | PO2W-220000001346 | 44442.93 | 44442.93 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 0% | Mid-tower mobile storage with shelves & 2 locking doors for Mesa Robles. Total towers: 37
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 9691.25 | 80804 | 2020-01-09 | 000000020055612 | 9691.25 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.674% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3193.75 | 80796 | 2020-01-14 | 000000020057268 | 3193.75 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.2221% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8433.75 | 81699 | 2020-01-14 | 000000020057268 | 8433.75 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.5865% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 7932.5 | 83068 | 2020-04-01 | 000000020085959 | 7932.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.5517% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 12485 | 82273 | 2020-04-01 | 000000020085960 | 12485 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.8683% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 8200 | 84567 | 2020-04-15 | 000000020089466 | 8200 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.5703% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 12690 | 85320 | 2020-05-28 | 000000020100719 | 12690 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.8825% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 13470 | 86240 | 2020-06-17 | 000000020106117 | 13470 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.9368% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 15197.5 | 86864 | 2020-07-27 | 000000020116270 | 15197.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.057% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 16815.75 | 88480 | 2020-08-17 | 000000020119773 | 16815.75 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.169% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 15883.43 | 89359 | 2020-10-13 | 000000020134067 | 15883.43 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.105% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 15048.8 | 90460 | 2020-10-20 | 000000020136025 | 15048.8 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.047% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 16767.97 | 91321 | 2020-12-18 | 000000020151933 | 16767.97 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.166% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 14496.63 | 91964 | 2020-12-18 | 000000020151933 | 14496.63 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.008% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 15502.22 | 92821 | 2021-02-08 | 000000020162981 | 15502.22 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.078% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 11403.41 | 94011 | 2021-04-05 | 000000020177572 | 11403.41 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.7931% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 9656.64 | 94918 | 2021-04-16 | 000000020181024 | 9656.64 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.6716% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 10312.87 | 95700 | 2021-05-25 | 000000020192064 | 10312.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.7172% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 5980.44 | 96936 | 2021-05-25 | 000000020192064 | 5980.44 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.4159% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 3520 | 97857R1 | 2021-06-22 | 000000020200048 | 3520 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.2448% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000640 | 0 | 160 | 98430 | 2021-09-09 | 000000020255187 | 160 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.01113% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-10-18 | 2021/22 |  | PO1-200000000640 | 0 | 3182.01 | 102576 | 2021-10-18 | 000000020301535 | 3182.01 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.2213% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-12-13 | 2021/22 |  | PO1-200000000640 | 0 | 1280 | 104806 | 2021-12-13 | 000000020358822 | 1280 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.08902% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-01-24 | 2021/22 |  | PO1-200000000640 | 0 | 13920 | 105896 | 2022-01-24 | 000000020395771 | 13920 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.9681% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-02-11 | 2021/22 |  | PO1-200000000640 | 0 | 19869.83 | 106727 | 2022-02-11 | 000000020412897 | 19869.83 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.382% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4694 | PO1-200000000640 | 85.25 | 85.25 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 33934.03 | 10513843591 | 2021-08-27 | 000000020245275 | 33934.03 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 46.67% | PowerSwitch N2200-ON OS6 for Mesa Robles. Total power switch: 7
Mesa Robles-21st Century-DSA Fees | 1 | DSA Fees | Mesa Robles | 21st Century | Division of the State Architect (DSA) | DSA fees | 2020-04-13 | 2020-04-24 | 2019/20 | 2-9603 | PO1-200000001113 | 0 | 28009 | Per email | 2020-04-24 | 000000020092203 | 28009 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9221101 | 100% | DSA plan check review fee for Mesa Robles 21st Century.
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Graybar | Door hardware | 2021-06-16 | 2021-08-30 | 2021/22 |  | PO3W-210000003051 | 0 | 599.39 | 9322335589 | 2021-08-30 | 000000020246134 | 599.39 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 27.62% | Mounting brackets, faceplates, & mini com stereo for Mesa Robles
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Graybar | Door hardware | 2021-06-16 | 2021-09-23 | 2021/22 |  | PO3W-210000003051 | 0 | 571.14 | 9323008978 | 2021-09-23 | 000000020271037 | 571.14 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 26.32% | Mounting brackets, faceplates, & mini com stereo for Mesa Robles
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Graybar | Door hardware | 2021-06-16 | 2022-03-15 | 2021/22 | 21-6866 | PO3W-210000003051 | 0 | 162.45 | 9325677028 | 2022-03-15 | 000000020443754 | 162.45 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 7.486% | Mounting brackets, faceplates, & mini com stereo for Mesa Robles
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Haul-Away Rubbish Service Co | Rental of container(s) | 2021-02-11 | 2021-02-22 | 2020/21 | 21-4313 | PO1-210000000609 | 0 | 125.17 | 0CX00268 | 2021-02-22 | 000000020166211 | 125.17 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 100% | Rental of 1 container for Mesa Robles. Monthly rental is $65.17 for the first month to include taxes, delivery and pick-up fees. After the intial month, the monthly rental rate is $85.00/month through December 2021. Close-out PO.
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 479.6 | 35253 | 2021-10-21 | 000000020304825 | 479.6 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9221101 | 15.55% | Walked and reviewed site for the wireless door contacts installation at Mesa Robles. Repair damage caused by bond work.
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2021-04-22 | 2021-06-07 | 2020/21 | 21-6038 | PO3W-210000002442 | 0 | 2867.39 | 34986 | 2021-06-07 | 000000020195370 | 2867.39 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 83.69% | Equipment to repair & replace security system at Mesa Robles
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2021-04-22 | 2021-06-07 | 2020/21 | 21-6038 | PO3W-210000002442 | 0 | 558.94 | 34986 | 2021-06-07 | 000000020195370 | 558.94 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 16.31% | Equipment to repair & replace security system at Mesa Robles
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-05 | 2020/21 | 21-3579 | PO2W-210000001496 | 0 | 36780.56 | 2324500221 | 2021-04-05 | 000000020177583 | 36780.56 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 46.37% | Furniture for Mesa Robles - Tables, chairs, stools, carpets, filing cabinets, etc
Mesa Robles-21st Century-FF & E | 1 | FF & E | Mesa Robles | 21st Century | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-05 | 2020/21 | 21-3579 | PO2W-210000001496 | 0 | 42547.14 | 2324500221 | 2021-04-05 | 000000020177583 | 42547.14 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 53.63% | Furniture for Mesa Robles - Tables, chairs, stools, carpets, filing cabinets, etc
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Lightspeed | Voice amplification system | 2021-05-19 | 2021-09-02 | 2021/22 | 21-6461 | PO3W-210000002832 | 0 | 9198 | 135992 | 2021-09-02 | 000000020250616 | 9198 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 11.95% | Voice amplification system - Topcat, mounting kit & sensor clip for Mesa Robles. Total system: 42
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | Lightspeed | Voice amplification system | 2021-05-19 | 2021-09-02 | 2021/22 | 21-6461 | PO3W-210000002832 | 0 | 67789.31 | 135992 | 2021-09-02 | 000000020250616 | 67789.31 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 88.05% | Voice amplification system - Topcat, mounting kit & sensor clip for Mesa Robles. Total system: 42
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.86 | R90910 | 2021-02-22 | 000000020166212 | 136.86 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.88 | RI89942 | 2021-02-22 | 000000020166212 | 136.88 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6609% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 678.9 | RI90939 | 2021-02-22 | 000000020166212 | 678.9 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 3.278% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI91693 | 2021-03-24 | 000000020174723 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI91740 | 2021-03-24 | 000000020174723 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92504 | 2021-03-24 | 000000020174723 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI92539 | 2021-03-24 | 000000020174723 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93276 | 2021-05-26 | 000000020192523 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI93311 | 2021-05-26 | 000000020192523 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI94055 | 2021-05-26 | 000000020192523 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94011 | 2021-06-23 | 000000020200450 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 591.3 | RI94776 | 2021-06-23 | 000000020200450 | 591.3 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 2.855% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94799 | 2021-06-23 | 000000020200450 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI94835 | 2021-06-23 | 000000020200450 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 591.3 | RI95508 | 2021-09-09 | 000000020255202 | 591.3 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 2.855% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI95528 | 2021-09-09 | 000000020255202 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 197.1 | RI95559 | 2021-09-09 | 000000020255202 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 591.3 | RI96203 | 2021-09-09 | 000000020255202 | 591.3 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 2.855% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI96228 | 2021-09-09 | 000000020255202 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 | 21-4283 | PO1-210000000608 | 0 | 197.1 | RI96259 | 2021-09-09 | 000000020255202 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2020-05-06 | 2021-06-30 | 2019/20 |  | PO2W-200000005019 | 0 | 678.9 | RI85305 | 2020-06-24 | 000000020108003 | 678.9 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 40.79% | Rental of 1 - 40' dry container with lock box for 6 months (05/15-11/14/20) for Mesa Robles. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2020-05-06 | 2020-07-01 | 2020/21 | 2-10091 | PO2W-200000005019 | 0 | 985.5 | RI85305 | 2020-06-24 | 000000020108003 | 985.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 59.21% | Rental of 1 - 40' dry container with lock box for 6 months (05/15-11/14/20) for Mesa Robles. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees.
Mesa Robles-21st Century-Move Management | 1 | Move Management | Mesa Robles | 21st Century | Martin Container | Rental of container(s) | 2020-10-22 | 2021-02-05 | 2020/21 | 21-2653 | PO2W-210000000975 | 0 | 4993.2 | RI89503, RI89853, RI89908 | 2021-02-05 | 000000020162568 | 4993.2 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 100% | Rental of 3 - 40' dry containers with lock box for 6 months (11/01/20-04/30/21) for Mesa Robles. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2019/20 | 2-10468 | PO2W-200000005391 | 0 | 2950 | MCSI-4530 | 2020-06-19 | 000000020106917 | 2950 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 100% | Asbestos & lead-based paint survey of Mesa Robles' permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-10-22 | 2021-02-04 | 2020/21 |  | PO2W-210000000976 | 0 | 4400 | MCSI-4644 | 2021-02-04 | 000000020162190 | 4400 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 73.33% | Oversight asbestos abatement at Mesa Robles for room #2 & 4
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-10-22 | 2023-01-16 | 2021/22 | 21-2654 | PO2W-210000000976 | 1600 | 1600 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #2 & 4
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-10-23 | 2021-02-04 | 2020/21 | 21-2682 | PO2W-210000000986 | 0 | 1480 | MCSI-4640 | 2021-02-04 | 000000020162190 | 1480 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 100% | Asbestos & lead-based paint survey of Mesa Robles permanent portable building #25 & 26.
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-01-27 | 2021-03-22 | 2020/21 |  | PO2W-210000001656 | 0 | 4400 | MCSI-4683 | 2021-03-22 | 000000020174069 | 4400 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 26.27% | Oversight asbestos abatement at Mesa Robles for room #D12-D15 & G11
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-01-27 | 2023-01-27 | 2021/22 | 21-4009 | PO2W-210000001656 | 4900 | 4900 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #D12-D15 & G11
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-03-18 | 2021-04-16 | 2020/21 |  | PO2W-210000001978 | 0 | 7910 | MCSI-4709 | 2021-04-16 | 000000020181032 | 7910 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 84.6% | Oversight asbestos abatement at Mesa Robles for room #B21 & G8-G10.
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-03-18 | 2023-03-18 | 2021/22 | 21-5398 | PO2W-210000001978 | 1440 | 1440 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #B21 & G8-G10.
Mesa Robles-21st Century-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century | Masek Consulting | Oversight asbestos abatement | 2021-06-07 | 2023-06-07 | 2020/21 | 21-6713 | PO2W-210000002602 | 0 | 850 | MCSI-4724 | 2021-06-22 | 000000020200055 | 850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 66.67% | Oversight asbestos abatement for Mesa Robles' flooring at room #16 & 17 areas under the cabinets
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-02-26 | 2018/19 |  | 19-100488 | 0 | 7100 | 001 | 2019-02-26 | 25118280 | 7100 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 100% | Architect - Allowances for civil engineering in 21st Century classroom projects at Mesa Robles. Close-out PO.
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-06-28 | 2017/18 |  | 19-100492, 18-109572 | 0 | 4007.97 | 001 | 2018-06-28 | 24653404 | 4007.97 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 50% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles 21st Century. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration.
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-07-17 | 2017/18 |  | 19-100492, 18-109572 | 0 | 4007.97 | 002 | 2018-07-17 | 24688289 | 4007.97 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 50% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles 21st Century. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. Close-out PO.
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-10-28 | 2019/20 | 2-4236 | PO2W-200000001909 | 0 | 411.5 | 001 | 2019-10-28 | 000000020031417 | 411.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 100% | Architect - Reimbursement for digital scanning (ARC services) for Mesa Robles 21st Century (Allowances)
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2020-04-02 | 2019/20 |  | PO2W-200000000098 | 0 | 17328 | 521305 | 2020-04-02 | 000000020086381 | 17328 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 6.987% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2020-04-02 | 2019/20 |  | PO2W-200000000098 | 0 | 12312 | 521639 | 2020-04-02 | 000000020086381 | 12312 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 4.965% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2020-04-02 | 2019/20 |  | PO2W-200000000098 | 0 | 15960 | 522150 | 2020-04-02 | 000000020086381 | 15960 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 6.435% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2020-04-17 | 2019/20 |  | PO2W-200000000098 | 0 | 12768 | 522494 | 2020-04-17 | 000000020090429 | 12768 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 5.148% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2020-06-18 | 2019/20 |  | PO2W-200000000098 | 0 | 78432 | 523681 | 2020-06-18 | 000000020106518 | 78432 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 31.63% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2020-08-18 | 2019/20 |  | PO2W-200000000098 | 0 | 2850 | 524037 | 2020-08-18 | 000000020120086 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2020-10-13 | 2020/21 |  | PO2W-200000000098 | 0 | 1140 | 525159 | 2020-10-13 | 000000020134100 | 1140 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0.4597% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2020-10-13 | 2020/21 |  | PO2W-200000000098 | 0 | 2850 | 524656 | 2020-10-13 | 000000020134100 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2021-02-05 | 2020/21 |  | PO2W-200000000098 | 0 | 4560 | 525689 | 2021-02-05 | 000000020162570 | 4560 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.839% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 5700 | 526682 | 2022-01-25 | 000000020397386 | 5700 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 2.298% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 5700 | 527233R | 2022-01-25 | 000000020397386 | 5700 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 2.298% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 2850 | 527749 | 2022-01-25 | 000000020397386 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 3420 | 528252 | 2022-01-25 | 000000020397386 | 3420 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.379% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 5130 | 528689 | 2022-01-25 | 000000020397386 | 5130 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 2.069% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 2280 | 529090 | 2022-01-25 | 000000020397386 | 2280 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0.9194% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 3990 | 529658 | 2022-01-25 | 000000020397386 | 3990 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.609% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 7980 | 530149 | 2022-01-25 | 000000020397386 | 7980 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 3.218% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 14250 | 530839 | 2022-01-25 | 000000020397386 | 14250 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 5.746% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 2850 | 531274 | 2022-01-25 | 000000020397386 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 2850 | 531948 | 2022-01-25 | 000000020397386 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 4560 | 532302 | 2022-01-25 | 000000020397386 | 4560 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.839% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Design | 1 | Design | Mesa Robles | 21st Century | PBK Architects | Architect | 2019-07-01 | 2025-01-16 | 2021/22 | 2-887 | PO2W-200000000098 | 38240 | 38240 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | PI Manufacturing Corp. | Computer cables | 2020-12-03 | 2021-02-17 | 2020/21 |  | PO3W-210000001095 | 0 | 1710.17 | 956469 | 2021-02-17 | 000000020165094 | 1710.17 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 79.65% | Computer cables for Mesa Robles
Mesa Robles-21st Century-Technology | 1 | Technology | Mesa Robles | 21st Century | PI Manufacturing Corp. | Computer cables | 2020-12-03 | 2021-06-24 | 2020/21 | 21-3360 | PO3W-210000001095 | 0 | 436.91 | 962688 | 2021-06-24 | 000000020200891 | 436.91 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 20.35% | Computer cables for Mesa Robles
Mesa Robles-21st Century-Advertisement | 1 | Advertisement | Mesa Robles | 21st Century | San Gabriel Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 2020/21 | 21-2253 | PO2W-210000000882 | 0 | 301.67 | 11412572 | 2020-10-19 | 000000020135642 | 301.67 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9221101 | 33.33% | Advertising for Bid 2020-21.01 HLPUSD Bid Bundle #2: 21st Century Classroom Improvements for Cedarlane, Mesa Robles, & Cedarlane Interim Housing. Publication dates: 09/22/20 & 09/28/20
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 5760 | 202102-05:MRMSM | 2021-03-24 | 000000020174730 | 5760 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 2.853% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202103-07:MRMSM | 2021-03-24 | 000000020174730 | 2880 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 1.427% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 6336 | 202101-08:MRMSM | 2021-04-19 | 000000020181403 | 6336 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 3.138% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 5328 | 202012-11:MRMSM | 2021-04-19 | 000000020181403 | 5328 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 2.639% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-04-20 | 2020/21 |  | PO2W-210000001035 | 0 | 3600 | 202104-06:MRMSM | 2021-04-20 | 000000020181749 | 3600 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 1.783% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-05-26 | 2020/21 |  | PO2W-210000001035 | 0 | 6336 | 202105-05:MRMSM | 2021-05-26 | 000000020192532 | 6336 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 3.138% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-06-23 | 2020/21 |  | PO2W-210000001035 | 0 | 8640 | 202106-03:MRMSM | 2021-06-23 | 000000020200462 | 8640 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 4.28% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-09-09 | 2020/21 |  | PO2W-210000001035 | 0 | 9504 | 202107-03:MRMSM | 2021-09-09 | 000000020255215 | 9504 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 4.708% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-09-09 | 2021/22 |  | PO2W-210000001035 | 0 | 9072 | 202108-04:MRMSM | 2021-09-09 | 000000020255216 | 9072 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 4.494% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2021-09-22 | 2021/22 |  | PO2W-210000001035 | 0 | 288 | 202109-04:MRMSM | 2021-09-22 | 000000020269793 | 288 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 0.1427% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century | Team Inspections | General inspection | 2020-10-29 | 2025-07-11 | 2021/22 | 21-2812 | PO2W-210000001035 | 35856 | 35856 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 0% | General inspection for the project as defined in Title 24 for Mesa Robles modernization.
Mesa Robles-21st Century-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century | Warehouse | Boxes | 2020-10-20 | 2020-10-28 | 2020/21 |  | XSRQ-210000001813 | 0 | 265.1 |  |  |  | 265.1 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 100% | Boxes(200) for teachers' to pack their classrooms at Mesa Robles
Mesa Robles-21st Century-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century | Warehouse | Boxes | 2020-10-20 | 2020-11-17 | 2020/21 |  | XSRQ-210000002024 | 0 | 180.27 |  |  |  | 180.27 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 100% | Boxes(136) for teachers' to pack their classrooms at Mesa Robles
Mesa Robles-21st Century-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century | Warehouse | Boxes & tapes | 2020-12-08 | 2020-12-10 | 2020/21 |  | XSRQ-210000002249 | 0 | 759.34 |  |  |  | 759.34 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 100% | Boxes(400) & packing tapes (75) for teachers' to pack their classrooms at Mesa Robles
Mesa Robles-21st Century-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century | Warehouse | Boxes | 2021-02-04 | 2021-02-10 | 2020/21 |  | XSRQ-210000002810 | 0 | 648.09 |  |  |  | 648.09 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 100% | Boxes(500) for teachers' to pack their classrooms at Mesa Robles
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Wolverine Fence | Contractor | 2020-07-06 | 2020-11-02 | 2020/21 | 21-404 | PO2W-210000000063 | 0 | 3500 | 3955 | 2020-11-02 | 000000020139125 | 3500 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 100% | Remove approx 80 LF of 6' high chain link fencing. Cut post off at grade. Return at later date and install inside sleeves to remove post and weld to existing. Reinstall fencing at a later date at Mesa Robles.
Mesa Robles-21st Century-Contractor | 1 | Contractor | Mesa Robles | 21st Century | Wolverine Fence | Contractor | 2020-10-29 | 2021-01-15 | 2020/21 | 21-2813 | PO2W-210000001036 | 0 | 1500 | 4055 | 2021-01-15 | 000000020157276 | 1500 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 100% | Relocate 2 ea. 2 7/8" post to miss grounding box cover at electric enclosure at Mesa Robles
Mesa Robles-Drinking fountain replacement-DSA Fees | 1 | DSA Fees | Mesa Robles | Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7623 | PO1-200000000956 | 0 | 1050 | Per email | 2020-02-13 | 000000020070041 | 1050 | 03-120658 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9211104 | 100% | DSA plan check review fee for Mesa Robles drinking fountain. This check was originally issued for Los Robles drinking fountain project, but since this project was cancelled by District, tBP applied this payment to Mesa Robles.
Mesa Robles-Drinking fountain replacement-Contractor | 1 | Contractor | Mesa Robles | Drinking fountain replacement | Optima | Contractor | 2019-08-20 | 2020-02-10 | 2019/20 | 2-4816 | PO2W-200000002203 | 0 | 11000 | 5000191 | 2020-02-10 | 000000020068412 | 11000 | 03-120658 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221104 | 100% | Provide & install 1 new drinking fountain at Mesa Robles.
Mesa Robles-Fire alarm-DSA Fees | 1 | DSA Fees | Mesa Robles | Fire alarm | Department of General Services (DGS) | DSA fees | 2021-07-21 | 2021-08-04 | 2021/22 | 22-742 | PO2W-220000000119 | 0 | 1720 | 12681 | 2021-08-04 | 000000020223411 | 1720 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9221103 | 54.24% | DGS plan/field review fee for Mesa Robles fire alarm
Mesa Robles-Fire alarm-Design | 1 | Design | Mesa Robles | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28121 | 2021-01-07 | 000000020154828 | 2375 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The total architect contract for Mesa Robles FA is $47,500.00
Mesa Robles-Fire alarm-Design | 1 | Design | Mesa Robles | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28226 | 2021-02-05 | 000000020162584 | 2375 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The total architect contract for Mesa Robles FA is $47,500.00
Mesa Robles-Fire alarm-Design | 1 | Design | Mesa Robles | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28379 | 2021-03-24 | 000000020174735 | 2375 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The total architect contract for Mesa Robles FA is $47,500.00
Mesa Robles-Fire alarm-Design | 1 | Design | Mesa Robles | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28464 | 2021-03-24 | 000000020174735 | 2375 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The total architect contract for Mesa Robles FA is $47,500.00
Mesa Robles-Fire alarm-Design | 1 | Design | Mesa Robles | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28730 | 2021-09-09 | 000000020255226 | 1425 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 0.8316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The total architect contract for Mesa Robles FA is $47,500.00
Mesa Robles-Fire alarm-Design | 1 | Design | Mesa Robles | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-12-10 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 28931 | 2021-12-10 | 000000020346458 | 950 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 0.5544% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The total architect contract for Mesa Robles FA is $47,500.00
Mesa Robles-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Fire Alarm | Team Inspections | General inspection | 2020-05-13 | 2020-08-19 | 2020/21 |  | PO2W-200000005057 | 0 | 2065 | 202008-10:WHSFA | 2020-08-19 | 000000020120364 | 2065 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221103 | 25.03% | General inspection for the project as defined in Title 24 at Mesa Robles Alterations to 1 campus wide fire alarm system
Mesa Robles-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Fire Alarm | Team Inspections | General inspection | 2020-05-13 | 2020-10-14 | 2020/21 |  | PO2W-200000005057 | 0 | 2065 | 202009-10:WHSFA | 2020-10-14 | 000000020134520 | 2065 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221103 | 25.03% | General inspection for the project as defined in Title 24 at Mesa Robles Alterations to 1 campus wide fire alarm system
Mesa Robles-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Fire Alarm | Team Inspections | General inspection | 2020-05-13 | 2020-10-21 | 2020/21 |  | PO2W-200000005057 | 0 | 2065 | 202010-08:WHSFA | 2020-10-21 | 000000020136459 | 2065 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221103 | 25.03% | General inspection for the project as defined in Title 24 at Mesa Robles Alterations to 1 campus wide fire alarm system
Mesa Robles-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Fire Alarm | Team Inspections | General inspection | 2020-05-13 | 2021-09-13 | 2020/21 | 2-10147 | PO2W-200000005057 | 0 | 2055 | 20210630-07: WHSFA | 2021-09-13 | 000000020257046 | 2055 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221103 | 24.91% | General inspection for the project as defined in Title 24 at Mesa Robles Alterations to 1 campus wide fire alarm system
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1402.2 | Pay app #1 | 2020-03-10 | 000000020079637 | 1402.2 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.1096% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 5885.73 | Pay app #6 | 2020-07-30 | 000000020117024 | 5885.73 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.4599% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-08-28 | 2020/21 |  | PO1-200000000662 | 0 | 51687.41 | Pay app #7 | 2020-08-28 | 000000020122656 | 51687.41 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 4.039% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-10-13 | 2020/21 |  | PO1-200000000662 | 0 | 36702.12 | Pay app #8 | 2020-10-13 | 000000020134117 | 36702.12 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 2.868% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-11-04 | 2020/21 |  | PO1-200000000662 | 0 | 16603.41 | Pay app #9 | 2020-11-04 | 000000020139892 | 16603.41 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 1.297% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-12-18 | 2020/21 |  | PO1-200000000662 | 0 | 1402.96 | Pay app #10 | 2020-12-18 | 000000020151942 | 1402.96 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.1096% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 350.74 | Pay app #12 | 2021-05-21 | 000000020191188 | 350.74 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.02741% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 9897.1 | Pay app #14 | 2021-05-21 | 000000020191188 | 9897.1 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.7734% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 855 | Pay app #15 | 2021-05-21 | 000000020191188 | 855 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.06681% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 14270.46 | Pay app #16 | 2021-11-22 | 000000020341778 | 14270.46 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 1.115% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Fire Alarm-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4508 | PO1-200000000662 | 7736.48 | 7736.48 |  |  |  | 0 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0% | Fire alarm and low voltage service for Mesa Robles
Mesa Robles-Interim Housing-Reprographics | 1 | Reprographics | Mesa Robles | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-06-17 | 2019/20 |  | PO1-200000001133 | 0 | 1661.08 | 10644576 | 2020-06-17 | 000000020106104 | 1661.08 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221102 | 47.05% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles.
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2020-06-22 | 2019/20 |  | PO2W-200000004115 | 0 | 3705 | 20-31125-30-01 | 2020-06-22 | 000000020107232 | 3705 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 27.36% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles.
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2020-06-22 | 2019/20 |  | PO2W-200000004115 | 0 | 4077.5 | 20-31125-30-02 | 2020-06-22 | 000000020107232 | 4077.5 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 30.11% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles.
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2020-10-13 | 2020/21 |  | PO2W-200000004115 | 0 | 1050.5 | 20-31125-30-03 | 2020-10-13 | 000000020134066 | 1050.5 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 7.758% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles.
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2021-04-19 | 2020/21 |  | PO2W-200000004115 | 0 | 1052.5 | 20-31125-30-04 | 2021-04-19 | 000000020181372 | 1052.5 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 7.773% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles.
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2021-09-09 | 2021/22 |  | PO2W-200000004115 | 0 | 1445 | 20-31125-30-05 | 2021-09-09 | 000000020255186 | 1445 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 10.67% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles.
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2023-01-16 | 2021/22 | 2-7894 | PO2W-200000004115 | 2209.5 | 2209.5 |  |  |  | 0 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 0% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles.
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2020-09-28 | 2020/21 |  | PO2W-200000004768 | 0 | 56280.59 | 30164 | 2020-09-28 | 000000020130222 | 56280.59 | 03-120417 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221102 | 9.123% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2020-09-28 | 2020/21 |  | PO2W-200000004768 | 0 | 16869.7 | 30164 | 2020-09-28 | 000000020130222 | 16869.7 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221102 | 2.734% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 11760.3 | 30790 | 2021-05-07 | 000000020187155 | 11760.3 | 03-120417 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221102 | 1.906% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 1225.03 | 30860 | 2021-05-07 | 000000020187156 | 1225.03 | 03-120417 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221102 | 0.1986% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 715.92 | 31584 | 2021-05-25 | 000000020192063 | 715.92 | 03-120417 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221102 | 0.116% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Mesa Robles-Interim Housing-DSA Fees | 1 | DSA Fees | Mesa Robles | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2019-10-22 | 2019-10-28 | 2019/20 | 2-4764 | PO2W-200000001911 | 0 | 7425 | Per email | 2019-10-28 | 000000020031416 | 7425 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9221102 | 100% | DSA plan check review fee for Mesa Robles interim housing.
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc | Contractor | 2020-03-03 | 2020-07-28 | 2019/20 |  | PO2W-200000004670 | 0 | 382506.49 | Pay app #1 | 2020-07-28 | 000000020116619 | 382506.49 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 50.6% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. Change order is $17,420.13 (PO2W-22*897). The total project cost with change order is $773,385.54
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc | Contractor | 2020-03-03 | 2020-09-08 | 2019/20 |  | PO2W-200000004670 | 0 | 20131.92 | Pay app #2 | 2020-09-08 | 000000020124730 | 20131.92 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 2.663% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. Change order is $17,420.13 (PO2W-22*897). The total project cost with change order is $773,385.54
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc | Contractor | 2020-03-03 | 2020-09-08 | 2020/21 |  | PO2W-200000004670 | 0 | 282815.48 | Pay app #2 | 2020-09-08 | 000000020124730 | 282815.48 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 37.41% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. Change order is $17,420.13 (PO2W-22*897). The total project cost with change order is $773,385.54
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc | Contractor | 2020-03-03 | 2021-05-21 | 2020/21 |  | PO2W-200000004670 | 0 | 51574.48 | Pay app #3 | 2021-05-21 | 000000020191175 | 51574.48 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 6.822% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. Change order is $17,420.13 (PO2W-22*897). The total project cost with change order is $773,385.54
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc | Contractor | 2020-03-03 | 2022-01-28 | 2021/22 | 2-8610 | PO2W-200000004670 | 3.638e-11 | 18937.04 | Pay app #4 | 2022-01-28 | 000000020401407 | 18937.04 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 2.505% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. Change order is $17,420.13 (PO2W-22*897). The total project cost with change order is $773,385.54
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc | Contractor | 2021-11-02 | 2022-02-01 | 2021/22 | 22-2885 | PO2W-220000000897 | 0 | 17420.13 | Pay app #4 | 2022-02-01 | 000000020403713 | 17420.13 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221102 | 100% | Change orders to 10 portable replacement to the new interim housing at Mesa Robles - Short circuit coordination, install fuses, sawcut and remove asphalt against building, relocate and re-install markerboards, & remove existing locks and install new sets for 10 doors. Addendum to PO2W-20*4670. The total project cost with change order is $773,385.54
Mesa Robles-Interim Housing-Move Management | 1 | Move Management | Mesa Robles | Interim Housing | Martin Container | Move containers | 2020-05-27 | 2020-06-23 | 2019/20 | 2-10376 | PO2W-200000005377 | 0 | 500 | RI85308 | 2020-06-23 | 000000020107623 | 500 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221102 | 100% | Move 2 of District's existing containers from one location to another location in the campus at Mesa Robles.
Mesa Robles-Interim Housing-Environ Consultant | 1 | Environ Consultant | Mesa Robles | Interim Housing | Masek Consulting | Pre-demo asbestos & lead-based paint | 2020-01-31 | 2020-06-03 | 2019/20 | 2-7522 | PO2W-200000003739 | 0 | 1280 | MCSI-4490 | 2020-06-03 | 000000020102133 | 1280 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221102 | 100% | Pre-demolition asbestos & lead-based paint survey of Mesa Robles' old portable building #27 and 28.
Mesa Robles-Interim Housing-Modular Buildings | 1 | Modular Buildings | Mesa Robles | Interim Housing | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-02-18 | 2019/20 | 2-2086 | PO2W-200000003190, PO2W-200000001052, 19-107584 | 0 | 436977.48 | R20530141 | 2020-02-18 | 000000020070593 | 436977.48 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9221102 | 100% | Purchase of 8 Portable classrooms - 24' x 40' DSA, install closure panels, new carpets, HVAC, T-8 lights lines, and delivery to Mesa Robles.
Mesa Robles-Interim Housing-Modular Buildings | 1 | Modular Buildings | Mesa Robles | Interim Housing | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-08-18 | 2020/21 | 2-2086 | PO2W-200000003191, PO2W-200000001052, 19-107584 | 0 | 42600 | R20546442 | 2020-08-18 | 000000020120084 | 42600 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9221102 | 100% | For 8 portable classrooms - Block & level building, installation, and relocation of these classrooms at Mesa Robles
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-06-28 | 2017/18 |  | 19-100493, 18-109556 | 0 | 1286.49 | 001 | 2018-06-28 | 24653404 | 1286.49 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 50% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles Interim Housing. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-07-17 | 2017/18 |  | 19-100493, 18-109556 | 0 | 1286.49 | 002 | 2018-07-17 | 24688289 | 1286.49 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 50% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles Interim Housing. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. Close-out PO.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-10-28 | 2019/20 | 2-4246 | PO2W-200000001924 | 0 | 1000 | email | 2019-10-28 | 000000020031418 | 1000 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 25.67% | Architect - Reimbursement for fire hydrant services at Mesa Robles (Allowances)
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-10-28 | 2019/20 |  | PO2W-200000001924 | 0 | 2894.95 | 003 | 2019-10-28 | 000000020031418 | 2894.95 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 74.33% | Architect - Payment for schematic design & design development for Mesa Robles Interim Housing (Allowances)
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Suburban Water Systems | Fire flow testing | 2019-01-09 | 2019-01-11 | 2018/19 |  | 19-105188 | 0 | 636 | Per email | 2019-01-11 | 25024227 | 636 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221102 | 100% | Fee for 3 fire flow testing performed or witnessed using Utility personnel at Mesa Robles. This fees applies to tests performed on distrubution systems in the entire territory served by the Utility.
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Suburban Water Systems | Deposit for engineering costs to construct (1) 6" public fire hydrant | 2019-03-08 | 2019-03-12 | 2018/19 |  | 19-106996 | 0 | 2000 | Per email | 2019-03-12 | 25148637 | 2000 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221102 | 100% | Deposit - Preliminary estimate to construct (1) 6" public fire hydrant at Mesa Robles.
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Suburban Water Systems | Remaining balance to construct (1) 6" public fire hydrant | 2020-01-08 | 2020-01-16 | 2019/20 | 2-6708 | PO2W-200000003306 | 0 | 39498.69 | Per email | 2020-01-16 | 000000020058736 | 39498.69 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221102 | 100% | Remaining balance required to construct (1) 6" public fire hydrant for Mesa Robles. The winning bid amount has been adjusted to include estimates for engineering inspection, general administration, contingency, and tax gross-up costs.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2019-08-22 | 2018/19 |  | PO2W-200000000855, 19-109962 | 0 | 26100 | 27120 | 2019-08-22 | 000000020007292 | 26100 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 30% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2019-09-23 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 30450 | 27161 | 2019-09-23 | 000000020018005 | 30450 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 35% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-01-15 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 8700 | 27447 | 2020-01-15 | 000000020057976 | 8700 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 10% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-05-26 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 4350 | 27763 | 2020-05-26 | 000000020099864 | 4350 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 5% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-06-19 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 4350 | 27834 | 2020-06-19 | 000000020106941 | 4350 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 5% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-08-18 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 2610 | 27928 | 2020-08-18 | 000000020120112 | 2610 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 3% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-10-14 | 2020/21 |  | PO2W-200000000855, 19-109962 | 0 | 1740 | 27977 | 2020-10-14 | 000000020134523 | 1740 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 2% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-10-14 | 2020/21 |  | PO2W-200000000855, 19-109962 | 0 | 4350 | 28050 | 2020-10-14 | 000000020134523 | 4350 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 5% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2021-02-05 | 2020/21 |  | PO2W-200000000855, 19-109962 | 0 | 2610 | 28235 | 2021-02-05 | 000000020162584 | 2610 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 3% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2021-10-01 | 2021/22 | 2-523 | PO2W-200000000855, 19-109962 | 0 | 1740 | 28879 | 2021-10-01 | 000000020283689 | 1740 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 2% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles.
Mesa Robles-Interim Housing-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Interim Housing | Team Inspections | General inspection | 2020-02-13 | 2020-06-19 | 2019/20 |  | PO2W-200000004113 | 0 | 19870 | 202006-06:MRR | 2020-06-19 | 000000020106934 | 19870 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221102 | 50% | General inspection for the project as defined in Title 24 at Mesa Robles. Relocation of 9 classroom buildings.
Mesa Robles-Interim Housing-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Interim Housing | Team Inspections | General inspection | 2020-02-13 | 2020-08-19 | 2020/21 |  | PO2W-200000004113 | 0 | 9935 | 202008-09:MRR | 2020-08-19 | 000000020120364 | 9935 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221102 | 25% | General inspection for the project as defined in Title 24 at Mesa Robles. Relocation of 9 classroom buildings.
Mesa Robles-Interim Housing-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Interim Housing | Team Inspections | General inspection | 2020-02-13 | 2020-10-14 | 2020/21 |  | PO2W-200000004113 | 0 | 5960 | 202009-12:MRR | 2020-10-14 | 000000020134520 | 5960 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221102 | 15% | General inspection for the project as defined in Title 24 at Mesa Robles. Relocation of 9 classroom buildings.
Mesa Robles-Interim Housing-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Interim Housing | Team Inspections | General inspection | 2020-02-13 | 2021-04-20 | 2020/21 | 2-7889 | PO2W-200000004113 | 0 | 3975 | 202104-07:MRR | 2021-04-20 | 000000020181749 | 3975 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221102 | 10% | General inspection for the project as defined in Title 24 at Mesa Robles. Relocation of 9 classroom buildings.
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2020-03-03 | 2020-07-30 | 2019/20 |  | PO2W-200000004671 | 0 | 61268.26 | Pay app #1 | 2020-07-30 | 000000020117024 | 61268.26 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 22.44% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The change order amount is $11,783.70 (PO2W-21-1738 & 1875). The total project cost with change orders is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2020-03-03 | 2020-08-28 | 2020/21 |  | PO2W-200000004671 | 0 | 165673.54 | Pay app #2 | 2020-08-28 | 000000020122656 | 165673.54 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 60.68% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21 (JVER21-536). The change order amount is $11,783.70 (PO2W-21-1738 & 1875). The total project cost with change orders is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2020-03-03 | 2020-11-09 | 2020/21 |  | PO2W-200000004671 | 0 | 12873.64 | Pay app #3 | 2020-11-09 | 000000020141151 | 12873.64 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 4.715% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21 (JVER21-536). The change order amount is $11,783.70 (PO2W-21-1738 & 1875). The total project cost with change orders is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2020-03-03 | 2020-12-18 | 2020/21 |  | PO2W-200000004671 | 0 | 3965.31 | Pay app #4 | 2020-12-18 | 000000020151942 | 3965.31 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 1.452% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21 (JVER21-536). The change order amount is $11,783.70 (PO2W-21-1738 & 1875). The total project cost with change orders is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2020-03-03 | 2021-03-12 | 2020/21 |  | PO2W-200000004671 | 0 | 7229.21 | Pay app #5 | 2021-03-12 | 000000020171773 | 7229.21 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 2.648% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21 (JVER21-536). The change order amount is $11,783.70 (PO2W-21-1738 & 1875). The total project cost with change orders is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2020-03-03 | 2021-05-21 | 2020/21 |  | PO2W-200000004671 | 0 | 11526.54 | Pay app #6 | 2021-05-21 | 000000020191188 | 11526.54 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 4.222% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21 (JVER21-536). The change order amount is $11,783.70 (PO2W-21-1738 & 1875). The total project cost with change orders is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2020-03-03 | 2021-05-21 | 2020/21 |  | PO2W-200000004671 | 0 | 7566.56 | Pay app #7 | 2021-05-21 | 000000020191188 | 7566.56 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 2.771% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21 (JVER21-536). The change order amount is $11,783.70 (PO2W-21-1738 & 1875). The total project cost with change orders is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2020-03-03 | 2024-07-31 | 2021/22 | 2-8611 | PO2W-200000004671 | 2932.25 | 2932.25 |  |  |  | 0 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 0% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21 (JVER21-536). The change order amount is $11,783.70 (PO2W-21-1738 & 1875). The total project cost with change orders is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2021-02-04 | 2023-07-11 | 2021/22 | 21-4190 | PO2W-210000001738 | 4174.01 | 4174.01 |  |  |  | 0 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221102 | 0% | Change order for additional installation of telephone cable and data drops at Mesa Robles. Addendum to PO2W-20*4671. The total project cost with change order is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc | Contractor | 2021-03-08 | 2023-07-11 | 2021/22 | 21-5000 | PO2W-210000001875 | 7609.69 | 7609.69 |  |  |  | 0 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221102 | 0% | Change order for additional installation of 2 power supplies and 2 amplifiers at Mesa Robles. Addendum to PO2W-20*4671. The total project cost with change order is $284,819.01
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Universal Asphalt | Contractor | 2020-03-03 | 2020-07-29 | 2019/20 |  | PO2W-200000004878 | 0 | 32487.91 | Pay app #1 | 2020-07-29 | 000000020116861 | 32487.91 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 32.73% | Remove & replace 3" AC over 4" base 27,280 SF at $3.50/SF, furnish and install 2x4 redwood header, 800 L.F. at $3.50 at Mesa Robles. Change order of $7,275.00 is done on PO2W-21*545. The total project cost with change order is $106,537.80
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Universal Asphalt | Contractor | 2020-03-03 | 2020-10-13 | 2020/21 | 2-8608 | PO2W-200000004878 | 0 | 5326.89 | Pay app #3 | 2020-10-13 | 000000020134125 | 5326.89 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 5.366% | Remove & replace 3" AC over 4" base 27,280 SF at $3.50/SF, furnish and install 2x4 redwood header, 800 L.F. at $3.50 at Mesa Robles. Change order of $7,275.00 is done on PO2W-21*545. The total project cost with change order is $106,537.80
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Universal Asphalt | Contractor | 2020-03-03 | 2020-10-13 | 2020/21 |  | PO2W-200000004878 | 0 | 61448 | Pay app #2 | 2020-10-13 | 000000020134125 | 61448 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 61.9% | Remove & replace 3" AC over 4" base 27,280 SF at $3.50/SF, furnish and install 2x4 redwood header, 800 L.F. at $3.50 at Mesa Robles. Change order of $7,275.00 is done on PO2W-21*545. The total project cost with change order is $106,537.80
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Universal Asphalt | Contractor | 2020-09-03 | 2020-10-13 | 2020/21 | 21-1705 | PO2W-210000000545 | 0 | 7275 | Pay app #2 | 2020-10-13 | 000000020134125 | 7275 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221102 | 100% | Change order for 3 additional move ins at no cost and 97 additional tons of asphalt concrete used @75.00/ton at Mesa Robles. Addendum to PO2W-20*4878. The total project cost with change order is $106,537.80
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Wolverine Fence | Contractor | 2020-02-13 | 2020-11-20 | 2020/21 | 2-7893 | PO2W-200000004114 | 0 | 17340 | 4012 | 2020-11-20 | 000000020144501 | 17340 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221102 | 100% | Furnish & install 6' high chain link fence and gate at electrical 10'2" x 14'7" electrical enclosure and dividing fence and gate. Furnish and install 4' x 6' emergency exit gate with hardware at Mesa Robles (for ADA handrail).
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Wolverine Fence | Contractor | 2021-01-21 | 2021-03-24 | 2020/21 | 21-3861 | PO2W-210000001628 | 0 | 8100 | 4135 | 2021-03-24 | 000000020174734 | 8100 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221102 | 100% | Furnish and install handrail per ADA requirement for building #5, 6, & C at Mesa Robles
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Amazon | Wall plates | 2020-07-08 | 2020-07-21 | 2020/21 | 21-507 | PO3W-210000000037 | 0 | 64.06 | 191J-YKGF-FMKK | 2020-07-21 | 000000020115026 | 64.06 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 100% | C2G 39702 HDMI and USB pass through wall plates, white, for Nelson, room #C1
Nelson-21st Century-Reprographics | 1 | Reprographics | Nelson | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-30 | 2019/20 |  | PO1-200000000625 | 0 | 728.6 | 10583551 | 2020-04-30 | 000000020093653 | 728.6 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 36.43% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Nelson.
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173629-IN | 2019-10-10 | 000000020025135 | 7798.34 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173629-IN | 2019-10-10 | 000000020025135 | 190 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173629-IN | 2019-10-10 | 000000020025135 | 100 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173629-IN | 2019-10-10 | 000000020025135 | 60 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173629-IN | 2019-10-10 | 000000020025135 | 30 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173629-IN | 2019-10-10 | 000000020025135 | 232.8 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173629-IN | 2019-10-10 | 000000020025135 | 640.6 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15596.67 | 0173777-IN | 2019-10-21 | 000000020028933 | 15596.67 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 200 | 0173777-IN | 2019-10-21 | 000000020028933 | 200 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173777-IN | 2019-10-21 | 000000020028933 | 120 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173777-IN | 2019-10-21 | 000000020028933 | 60 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 380 | 0173777-IN | 2019-10-21 | 000000020028933 | 380 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173777-IN | 2019-10-21 | 000000020028933 | 465.6 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173777-IN | 2019-10-21 | 000000020028933 | 1281.2 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 85781.75 | 0175468-IN | 2019-10-22 | 000000020029495 | 85781.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 3.058% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 330 | 0175468-IN | 2019-10-22 | 000000020029495 | 330 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.01176% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 660 | 0175468-IN | 2019-10-22 | 000000020029495 | 660 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.02352% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1100 | 0175468-IN | 2019-10-22 | 000000020029495 | 1100 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.03921% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2090 | 0175468-IN | 2019-10-22 | 000000020029495 | 2090 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.0745% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2560.8 | 0175468-IN | 2019-10-22 | 000000020029495 | 2560.8 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.09128% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7046.6 | 0175468-IN | 2019-10-22 | 000000020029495 | 7046.6 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.2512% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 2612.53 | 0175485-IN | 2019-10-22 | 000000020029495 | 2612.53 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 0.3292% | Ergotron Zip40 Charging carts to store laptops at Nelson. Total carts: 18
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 20900.17 | 0175493-IN | 2019-10-22 | 000000020029495 | 20900.17 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 2.634% | Ergotron Zip40 Charging carts to store laptops at Nelson. Total carts: 18
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-06-05 | 2020-07-01 | 2019/20 | 2-10688 | PO3W-200000003014 | 0 | 2184.71 | 186220-IN | 2020-07-01 | 000000020109906 | 2184.71 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 100% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor - sample for Nelson room #C1. Total monitor: 1
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-09-16 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 60 | 0187656-IN | 2020-09-16 | 000000020127001 | 60 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 0.04814% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Nelson. Total monitors: 25
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-09-16 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 21886.59 | 0187656-IN | 2020-09-16 | 000000020127001 | 21886.59 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 17.56% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Nelson. Total monitors: 25
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 90 | 0189682-IN | 2020-10-01 | 000000020131103 | 90 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 0.07221% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Nelson. Total monitors: 25
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 32680.66 | 0189682-IN | 2020-10-01 | 000000020131103 | 32680.66 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 26.22% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Nelson. Total monitors: 25
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Camcor | Document camera(s) | 2020-07-01 | 2020-07-16 | 2020/21 | 21-309 | PO3W-210000000006 | 0 | 14942.64 | 2494523 | 2020-07-16 | 000000020114150 | 14942.64 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 43.86% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Nelson. Total cameras: 25
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | CDW-G Government Inc. | Document camera(s) | 2020-07-01 | 2020-08-21 | 2020/21 | 21-122 | PO3W-210000000002 | 0 | 706.28 | ZCT7823 | 2020-08-21 | 000000020120955 | 706.28 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 100% | Elmo TT-12W Stem Cam Document Camera - a sample for Nelson room #C1
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 304.15 | 8316064 | 2021-03-05 | 000000020169721 | 304.15 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 7.936% | C2G HDMI and USB pass through wall plates for Nelson. Total items: 20
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 53.96 | 5725548 | 2021-03-05 | 000000020169721 | 53.96 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 1.408% | C2G HDMI and USB pass through wall plates for Nelson. Total items: 20
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 255.09 | 8312741 | 2021-03-05 | 000000020169721 | 255.09 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 6.656% | C2G HDMI and USB pass through wall plates for Nelson. Total items: 20
Nelson-21st Century-DSA Special Inspection | 1 | DSA Special Inspection | Nelson | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2021-02-05 | 2020/21 |  | PO2W-200000005543 | 0 | 1117.5 | 20-31198-60-0000001 | 2021-02-05 | 000000020162565 | 1117.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9231101 | 5.36% | Provide materials testing and special inspection services at Nelson The project consists of alteration and upgrades to several existing classroom buildings including buildings A, B, C, D, & K and portable classroom buidings D5, D6, and E1 through E4, and other site works. Scope of services include reviewing, testing, and prepare reports for concrete and reinforcing steel.
Nelson-21st Century-DSA Special Inspection | 1 | DSA Special Inspection | Nelson | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2023-07-31 | 2021/22 | 2-10673 | PO2W-200000005543 | 19732.5 | 19732.5 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9231101 | 0% | Provide materials testing and special inspection services at Nelson The project consists of alteration and upgrades to several existing classroom buildings including buildings A, B, C, D, & K and portable classroom buidings D5, D6, and E1 through E4, and other site works. Scope of services include reviewing, testing, and prepare reports for concrete and reinforcing steel.
Nelson-21st Century-DSA Special Inspection | 1 | DSA Special Inspection | Nelson | 21st Century | Converse Consultants | Masonry inspection | 2020-10-28 | 2021-10-01 | 2021/22 | 21-2786 | PO2W-210000001034 | 0 | 5787.5 | 20-31198-61-0000001 | 2021-10-01 | 000000020283669 | 5787.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 69.52% | Masonry inspection of brick veneer repair for Nelson 21st Century classroom modification program
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2020-08-24 | 2020/21 |  | PO2W-200000004768 | 0 | 72270.22 | 29896 | 2020-08-24 | 000000020121270 | 72270.22 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 11.71% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2020-08-24 | 2020/21 |  | PO2W-200000004768 | 0 | 37326.95 | 29896 | 2020-08-24 | 000000020121270 | 37326.95 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 6.05% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 1854.45 | 30790 | 2021-05-07 | 000000020187155 | 1854.45 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 0.3006% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 23671.93 | 30860 | 2021-05-07 | 000000020187156 | 23671.93 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 3.837% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 3468.41 | 30860 | 2021-05-07 | 000000020187156 | 3468.41 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 0.5622% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 192.72 | 31584 | 2021-05-25 | 000000020192063 | 192.72 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 0.03124% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-06-01 | 2020/21 | 2-9304 | PO2W-200000004768 | 0 | 8499.94 | 31626 | 2021-06-01 | 000000020193670 | 8499.94 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 1.378% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. Close-out PO. Per Jessica Morley @ Cumming, all furniture received. Vendor did not send us an invoice for line item #9 & 13. Close-out PO.
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-11-06 | 2021-02-09 | 2020/21 | 21-2945 | PO2W-210000001122 | 0 | 97706.07 | 30925 | 2021-02-09 | 000000020163346 | 97706.07 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 74.24% | Furniture for Nelson. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2020-11-06 | 2021-02-09 | 2020/21 | 21-2945 | PO2W-210000001122 | 0 | 33893.46 | 30925 | 2021-02-09 | 000000020163346 | 33893.46 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 25.76% | Furniture for Nelson. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Culver Newlin | Furniture | 2022-01-14 | 2023-01-14 | 2021/22 | 22-3986 | PO2W-220000001347 | 19218.56 | 19218.56 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 0% | Mid-tower mobile storage with shelves & 2 locking doors for Nelson. Total towers: 16
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 8556.25 | 80804 | 2020-01-09 | 000000020055612 | 8556.25 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.5951% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3268.75 | 80796 | 2020-01-14 | 000000020057268 | 3268.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.2273% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 9568.75 | 81699 | 2020-01-14 | 000000020057268 | 9568.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.6655% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 10195 | 83068 | 2020-04-01 | 000000020085959 | 10195 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.709% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 9765 | 82273 | 2020-04-01 | 000000020085960 | 9765 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.6791% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 13455 | 84567 | 2020-04-15 | 000000020089466 | 13455 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.9357% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9450 | 85320 | 2020-05-28 | 000000020100719 | 9450 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.6572% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 10027.5 | 86240 | 2020-06-17 | 000000020106117 | 10027.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.6974% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 10887.5 | 86864 | 2020-07-27 | 000000020116270 | 10887.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.7572% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 6349.45 | 88480 | 2020-08-17 | 000000020119773 | 6349.45 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.4416% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 5997.42 | 89359 | 2020-10-13 | 000000020134067 | 5997.42 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.4171% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 5682.27 | 90460 | 2020-10-20 | 000000020136025 | 5682.27 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.3952% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 6331.41 | 91321 | 2020-12-18 | 000000020151933 | 6331.41 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.4403% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 5473.78 | 91964 | 2020-12-18 | 000000020151933 | 5473.78 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.3807% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 5853.48 | 92821 | 2021-02-08 | 000000020162981 | 5853.48 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.4071% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 4305.81 | 94011 | 2021-04-05 | 000000020177572 | 4305.81 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.2995% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 3646.24 | 94918 | 2021-04-16 | 000000020181024 | 3646.24 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.2536% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 3894.03 | 95700 | 2021-05-25 | 000000020192064 | 3894.03 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.2708% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 2258.15 | 96936 | 2021-05-25 | 000000020192064 | 2258.15 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.157% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-02-11 | 2021/22 |  | PO1-200000000640 | 0 | 2315.17 | 106727 | 2022-02-11 | 000000020412897 | 2315.17 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.161% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-03-15 | 2021/22 |  | PO1-200000000640 | 0 | 13530.29 | 108239 | 2022-03-15 | 000000020443751 | 13530.29 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.941% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4694 | PO1-200000000640 | 19.75 | 19.75 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 9695.44 | 10513843591 | 2021-08-27 | 000000020245275 | 9695.44 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 13.33% | PowerSwitch N2200-ON OS6 for Nelson. Total power switch: 2
Nelson-21st Century-DSA Fees | 1 | DSA Fees | Nelson | 21st Century | Department of General Services (DGS) | DSA fees | 2022-01-13 | 2022-01-28 | 2021/22 | 22-3947 | PO2W-220000001343 | 0 | 14670.45 | 12946 | 2022-01-28 | 000000020401402 | 14670.45 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9231101 | 100% | DGS plan/field review fee for Nelson 21st Century
Nelson-21st Century-DSA Fees | 1 | DSA Fees | Nelson | 21st Century | Division of the State Architect (DSA) | DSA fees | 2019-06-11 | 2019-06-19 | 2018/19 |  | 19-109964 | 0 | 15540.64 | Per email | 2019-06-19 | 25365030 | 15540.64 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9231101 | 100% | DSA plan check review fee for Nelson 21st Century.
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Education Products & Services | Sliding white boards | 2020-01-15 | 2020-04-23 | 2019/20 | 2-6913 | PO2W-200000003506 | 0 | 5465.85 | EPS6013-2020 | 2020-04-23 | 000000020091979 | 5465.85 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Provide labor and materials to install four (4) 44" x 60" Top mounted sliding white board to include track as sample for Nelson room #C1.
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Education Products & Services | White board(s) | 2020-01-31 | 2020-04-23 | 2019/20 | 2-7521 | PO2W-200000003738 | 0 | 1253.77 | EPS6021-2020 | 2020-04-23 | 000000020091979 | 1253.77 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Provide labor and materials to install two (2) 48" x 96" porcelain white boards with 1" map rail and blade style marker tray. 1/2" aluminum trim on 3 sides, mitered corners as sample for Nelson room #C1.
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Education Products & Services | Sink cabinet | 2020-01-31 | 2020-04-23 | 2019/20 | 2-7493 | PO2W-200000003740 | 0 | 3449.99 | EPS6022-2020 | 2020-04-23 | 000000020091979 | 3449.99 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Provide labor and material to install sink cabinet which include backsplash & countertop as a sample for Nelson room #C1. Cabinetwill be 48" wide x 24" deep x 34" high with a 7" front facia under the countertop in front of sink.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Floor Tech America (FTA) | Contractor | 2020-01-15 | 2020-04-23 | 2019/20 | 2-6914 | PO2W-200000003507 | 0 | 11175 | 12652 | 2020-04-23 | 000000020091981 | 11175 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Prepare and install new LVT. Supply and install 4" rubber topset base and 4 yards of First Step Up II at Nelson for room #C1.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | GDL Best Contractors, Inc | Contractor | 2020-02-03 | 2020-06-18 | 2019/20 | 2-7580 | PO2W-200000004356 | 0 | 14900 | 6071 | 2020-06-18 | 000000020106497 | 14900 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 100% | Prep existing doors & install new door hardware, provide & install tack board sheets, provide & install sink, faucet, & bubbler and plumbing, prime & paint existing window frames & door, provide & install TV bracket for Nelson room #C1.
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Graybar | Door hardware | 2020-12-14 | 2021-02-08 | 2020/21 | 21-3550 | PO3W-210000001162 | 0 | 246.82 | 9319230223 | 2021-02-08 | 000000020162991 | 246.82 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 33.33% | Mounting brackets & blank face plates for Nelson
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 141.7 | 35254 | 2021-10-21 | 000000020304825 | 141.7 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9231101 | 4.594% | Walked and reviewed site for the wireless door contacts installation at Nelson. Repair damage caused by bond work.
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5995 | PO3W-210000002406 | 0 | 2040.54 | 34985 | 2021-06-07 | 000000020195370 | 2040.54 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 24.44% | Equipment to repair & replace security system at Nelson
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5995 | PO3W-210000002406 | 0 | 558.94 | 34985 | 2021-06-07 | 000000020195370 | 558.94 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 6.694% | Equipment to repair & replace security system at Nelson
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Contractor | 2020-01-31 | 2020-04-02 | 2019/20 | 2-7494 | PO2W-200000003741 | 0 | 12975 | 2019-032A | 2020-04-02 | 000000020086380 | 12975 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 100% | Interior demolition and haul of flooring, ceiling, casework, tack board, and electrical data for Nelson room #C1.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-07-06 | 2020-10-13 | 2020/21 | 21-398 | PO2W-210000000145 | 0 | 27860 | 2019-032A-11 | 2020-10-13 | 000000020134080 | 27860 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 100% | Asbestos abatement of Nelson floor tile in classroom A1, B1, B3, & mastic under cabinets in classroom B2 & B4. Demolish and haul off casework.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 2020/21 | 21-2378 | PO2W-210000000884 | 0 | 45000 | 2020-097D | 2020-11-20 | 000000020144493 | 45000 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 38.3% | Demo of ceiling tiles in 18 classrooms at Nelson
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2020-08-12 | 2020/21 | 2-9319 | PO2W-200000004769 | 0 | 9237.16 | 3539770720 | 2020-08-12 | 000000020118972 | 9237.16 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 41.6% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2020-08-12 | 2020/21 | 2-9319 | PO2W-200000004769 | 0 | 10685.34 | 3539770720 | 2020-08-12 | 000000020118972 | 10685.34 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 58.4% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2021-03-23 | 2020/21 | 2-9327 | PO2W-200000004771 | 0 | 8762.52 | 3584031220 | 2021-03-23 | 000000020174431 | 8762.52 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 43.98% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2021-03-23 | 2020/21 | 2-9327 | PO2W-200000004771 | 0 | 11159.98 | 3584031220 | 2021-03-23 | 000000020174431 | 11159.98 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 56.02% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2020-08-12 | 2020/21 | 2-9328 | PO2W-200000004776 | 0 | 9237.16 | 3585880720 | 2020-08-12 | 000000020118972 | 9237.16 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 41.6% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2020-08-12 | 2020/21 | 2-9328 | PO2W-200000004776 | 0 | 10685.34 | 3585880720 | 2020-08-12 | 000000020118972 | 10685.34 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 58.4% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 27193.61 | 3207761219 | 2020-02-03 | 000000020065147 | 27193.61 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 6.319% | Furniture for Nelson - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Nelson-21st Century-FF & E | 1 | FF & E | Nelson | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 14247.61 | 3207761219 | 2020-02-03 | 000000020065147 | 14247.61 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 3.311% | Furniture for Nelson - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 1752 | 6454832194 | 2020-07-27 | 000000020116281 | 1752 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 2.804% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Nelson (4 year warranty). Total computers: 25
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-05 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 24610.13 | 6454893288 | 2020-08-05 | 000000020117729 | 24610.13 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 40.94% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Nelson (4 year warranty). Total computers: 25
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-20 | 2019/20 | 21-131 | PO3W-210000000005 | 0 | 55.85 | 6454678562 | 2020-08-20 | 000000020120647 | 55.85 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 5.369% | Desktop computer (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II (4 year warranty) - Nelson, room #C1-sample
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-20 | 2019/20 | 21-131 | PO3W-210000000005 | 0 | 984.41 | 6454728085 | 2020-08-20 | 000000020120647 | 984.41 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 94.63% | Desktop computer (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II (4 year warranty) - Nelson, room #C1-sample
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 5365.5 | 128357 | 2020-07-23 | 000000020115778 | 5365.5 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 4.768% | Voice amplification system - Topcat, mounting kit & sensor clip for Nelson. Total system: 25
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 43991.63 | 128357 | 2020-07-23 | 000000020115778 | 43991.63 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 39.09% | Voice amplification system - Topcat, mounting kit & sensor clip for Nelson. Total system: 25
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.86 | RI91367 | 2021-02-22 | 000000020166212 | 136.86 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.88 | RI90465 | 2021-02-22 | 000000020166212 | 136.88 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6609% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI90908 | 2021-02-22 | 000000020166212 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI89940 | 2021-02-22 | 000000020166212 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92160 | 2021-03-24 | 000000020174723 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 273.75 | RI91691 | 2021-03-24 | 000000020174723 | 273.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 273.75 | RI92502 | 2021-03-24 | 000000020174723 | 273.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92909 | 2021-05-26 | 000000020192523 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93715 | 2021-05-26 | 000000020192523 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI93274 | 2021-05-26 | 000000020192523 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI94009 | 2021-06-23 | 000000020200450 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94486 | 2021-06-23 | 000000020200450 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI94797 | 2021-06-23 | 000000020200450 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-30 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI95215 | 2021-06-30 | 000000020202687 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 273.76 | RI95526 | 2021-09-09 | 000000020255202 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI95923 | 2021-09-09 | 000000020255202 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 | 21-4284 | PO1-210000000608 | 0 | 273.76 | RI96226 | 2021-09-09 | 000000020255202 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2020-05-06 | 2021-06-30 | 2019/20 |  | PO2W-200000005020 | 0 | 1357.8 | RI85307 | 2020-06-24 | 000000020108003 | 1357.8 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 40.79% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2020-05-06 | 2020-07-01 | 2020/21 | 2-10092 | PO2W-200000005020 | 0 | 1971 | RI85307 | 2020-06-24 | 000000020108003 | 1971 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 59.21% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees.
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2020-06-03 | 2020-08-18 | 2019/20 |  | PO2W-200000005484 | 0 | 678.9 | RI85719 | 2020-08-18 | 000000020120082 | 678.9 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 40.79% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2020-06-03 | 2020-08-18 | 2020/21 | 2-10621 | PO2W-200000005484 | 0 | 985.5 | RI85719 | 2020-08-18 | 000000020120082 | 985.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 59.21% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2020-10-09 | 2022-03-07 | 2021/22 |  | PO2W-210000000883 | 1664.4 | 1664.4 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0% | Rental of 1 - 40' dry container with lock box for 6 months (10/15/20-04/14/21) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Nelson-21st Century-Move Management | 1 | Move Management | Nelson | 21st Century | Martin Container | Rental of container(s) | 2020-10-09 | 2022-03-07 | 2021/22 | 21-2375 | PO2W-210000000883 | -1664.4 | -1664.4 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0% | Rental of 1 - 40' dry container with lock box for 6 months (10/15/20-04/14/21) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees. Close-out PO.
Nelson-21st Century-Environ Consultant | 1 | Environ Consultant | Nelson | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2019/20 | 2-9625 | PO2W-200000004875 | 0 | 2530 | MCSI-4513 | 2020-06-03 | 000000020102133 | 2530 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9231101 | 100% | Asbestos & lead-based paint survey of Nelson's permanent buildings (exclude Admin & multi-purpose bldg) and old portable buildings. Walk through, collect samples, testing of samples, and prepare report.
Nelson-21st Century-Environ Consultant | 1 | Environ Consultant | Nelson | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-07-06 | 2020-10-13 | 2020/21 |  | PO2W-210000000061 | 0 | 3975 | MCSI-4591 | 2020-10-13 | 000000020134092 | 3975 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9231101 | 49.07% | Floor tile & mastic abatement abatement oversight and clearance at Nelson for room #A1, B1, B3, and under the cabinets in B2 & B4.
Nelson-21st Century-Environ Consultant | 1 | Environ Consultant | Nelson | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-07-06 | 2023-01-16 | 2021/22 | 21-402 | PO2W-210000000061 | 4125 | 4125 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9231101 | 0% | Floor tile & mastic abatement abatement oversight and clearance at Nelson for room #A1, B1, B3, and under the cabinets in B2 & B4.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-07-31 | 2019/20 |  | PO2W-200000005829 | 0 | 496863.78 | Pay app #1 | 2020-07-31 | 000000020117168 | 496863.78 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 22.69% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-08-18 | 2019/20 |  | PO2W-200000005829 | 0 | 26150.72 | Pay app #2 | 2020-08-18 | 000000020120083 | 26150.72 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 1.194% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-08-18 | 2020/21 |  | PO2W-200000005829 | 0 | 565926.8 | Pay app #2 | 2020-08-18 | 000000020120083 | 565926.8 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 25.84% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-09-28 | 2020/21 |  | PO2W-200000005829 | 0 | 301087.74 | Pay app #3 | 2020-09-28 | 000000020130229 | 301087.74 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 13.75% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2020-11-09 | 2020/21 |  | PO2W-200000005829 | 0 | 282947.52 | Pay app #4 | 2020-11-09 | 000000020141125 | 282947.52 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 12.92% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2021-01-15 | 2020/21 |  | PO2W-200000005829 | 0 | 177129.4 | Pay app #5 | 2021-01-15 | 000000020157265 | 177129.4 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 8.088% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2021-01-20 | 2020/21 |  | PO2W-200000005829 | 0 | 71383.63 | Pay app #6 | 2021-01-20 | 000000020157917 | 71383.63 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 3.26% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2021-03-16 | 2020/21 |  | PO2W-200000005829 | 0 | 107716.68 | Pay app #7 | 2021-03-16 | 000000020172578 | 107716.68 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 4.919% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2021-05-21 | 2020/21 |  | PO2W-200000005829 | 0 | 37289.79 | Pay app #8 | 2021-05-21 | 000000020191176 | 37289.79 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 1.703% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Masters Contracting Corp | Contractor | 2020-06-04 | 2023-07-31 | 2021/22 | 2-10671 | PO2W-200000005829 | 123503.94 | 123503.94 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 0% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules.
Nelson-21st Century-Technology | 1 | Technology | Nelson | 21st Century | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 2020/21 | 21-3264 | PO2W-210000001350 | 0 | 1023.66 | 956468 | 2021-02-10 | 000000020163835 | 1023.66 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 100% | Cables for Nelson
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2018-10-11 | 2018/19 |  | PO2W-200000000859, 19-100470 | 0 | 3699.66 | T8157R | 2018-10-11 | 24850693 | 3699.66 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 3.753% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $11,306.00 is requested by District (PO2W-20*5063). The total architect cost with change order is $109,894.72
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2019-01-28 | 2018/19 |  | PO2W-200000000859, 19-100470 | 0 | 4962 | R8235 | 2019-01-28 | 25052439 | 4962 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 5.033% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. Allowances for civil engineering. Change order of $11,306.00 is requested by District (PO2W-20*5063). The total architect cost with change order is $109,894.72
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2019-09-05 | 2018/19 |  | PO2W-200000000859, 19-100470 | 0 | 21272.98 | T8308 | 2019-09-05 | 000000020011699 | 21272.98 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 21.58% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $11,306.00 is requested by District (PO2W-20*5063). The total architect cost with change order is $109,894.72
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2019-09-11 | 2019/20 |  | PO2W-200000000859, 19-100470 | 0 | 30522.1 | T8351 | 2019-09-11 | 000000020013866 | 30522.1 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 30.96% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $11,306.00 is requested by District (PO2W-20*5063). The total architect cost with change order is $109,894.72
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2020-06-04 | 2019/20 |  | PO2W-200000000859, 19-100470 | 0 | 9249.12 | T8517 | 2020-06-04 | 000000020102555 | 9249.12 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 9.382% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $11,306.00 is requested by District (PO2W-20*5063). The total architect cost with change order is $109,894.72
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2020-10-21 | 2020/21 |  | PO2W-200000000859, 19-100470 | 0 | 19633.76 | T8572 | 2020-10-21 | 000000020136458 | 19633.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 19.91% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. Payment includes allowances of $1,135.52 for printing services from ARC. Change order of $11,306.00 is requested by District (PO2W-20*5063). The total architect cost with change order is $109,894.72
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2021-04-19 | 2020/21 |  | PO2W-200000000859, 19-100470 | 0 | 4624.55 | T8634 | 2021-04-19 | 000000020181402 | 4624.55 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 4.691% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $11,306.00 is requested by District (PO2W-20*5063). The total architect cost with change order is $109,894.72
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2018-07-17 | 2021-12-20 | 2021/22 | 2-532 | PO2W-200000000859, 19-100470 | 0 | 4624.55 | 3377 | 2021-12-20 | 000000020370769 | 4624.55 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 4.691% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. Change order of $11,306.00 is requested by District (PO2W-20*5063). The total architect cost with change order is $109,894.72. Close-out PO.
Nelson-21st Century-Design | 1 | Design | Nelson | 21st Century | TDM Architects, Inc | Architect | 2020-05-11 | 2020-10-21 | 2020/21 | 2-10122 | PO2W-200000005063 | 0 | 11306 | T8577 | 2020-10-21 | 000000020136458 | 11306 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9231101 | 100% | Architect - These are additional changes requested by District since summer of 2019 for Nelson. Changes to include replacing concrete walkway at classrooms in lieu of replacement of landing at door, revising new counter at new sink in classrooms, revising the electrical drawing, etc. Addendum to PO2W-20*859. The total architect cost with change order is $109,894.72
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 2019/20 |  | PO2W-200000004961 | 0 | 4410 | 20200630-06:NEM | 2020-06-19 | 000000020106934 | 4410 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 12.7% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-08-19 | 2020/21 |  | PO2W-200000004961 | 0 | 3360 | 202008-03:NEM | 2020-08-19 | 000000020120364 | 3360 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 9.677% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-10-14 | 2020/21 |  | PO2W-200000004961 | 0 | 2940 | 202009-03:NEM | 2020-10-14 | 000000020134520 | 2940 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 8.468% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-10-21 | 2020/21 |  | PO2W-200000004961 | 0 | 2940 | 202010-03:NEM | 2020-10-21 | 000000020136459 | 2940 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 8.468% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-02-05 | 2020/21 |  | PO2W-200000004961 | 0 | 6160 | 202011-03:NEM | 2021-02-05 | 000000020162579 | 6160 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 17.74% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-03-24 | 2020/21 |  | PO2W-200000004961 | 0 | 1890 | 202102-01:NEM | 2021-03-24 | 000000020174730 | 1890 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 5.444% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-03-24 | 2020/21 |  | PO2W-200000004961 | 0 | 2380 | 202103-04:NEM | 2021-03-24 | 000000020174730 | 2380 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 6.855% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004961 | 0 | 2520 | 202012-03:NEM | 2021-04-19 | 000000020181403 | 2520 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 7.258% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004961 | 0 | 2800 | 202101-03:NEM | 2021-04-19 | 000000020181403 | 2800 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 8.065% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-04-20 | 2020/21 |  | PO2W-200000004961 | 0 | 3220 | 202104-03:NEM | 2021-04-20 | 000000020181749 | 3220 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 9.274% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2023-07-31 | 2021/22 | 2-9868 | PO2W-200000004961 | 2100 | 2100 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 0% | General inspection for the project as defined in Title 24. Modernization of Nelson ES.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Telenet VOIP, Inc | Contractor | 2020-02-06 | 2020-03-19 | 2019/20 |  | PO2W-200000004053 | 0 | 13950.28 | Pay app #1 | 2020-03-19 | 000000020082827 | 13950.28 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 42.75% | Low voltage/classroom raceway for Nelson, room #C1. Remove/reinstall 1 existing smoke detector and 1 existing horn strobe. Installation of required 5400 raceway & fittings. Installation of #12 solid wire from outlets to new installed circuit breaker in existing electrical distribution panel. Install Cat 6 cable for 8 data drops and Cat 6A for 4 WAP data drops with 3" of service loop.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Telenet VOIP, Inc | Contractor | 2020-02-06 | 2020-04-23 | 2019/20 |  | PO2W-200000004053 | 0 | 6200.12 | Pay app #2 | 2020-04-23 | 000000020091991 | 6200.12 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 19% | Low voltage/classroom raceway for Nelson, room #C1. Remove/reinstall 1 existing smoke detector and 1 existing horn strobe. Installation of required 5400 raceway & fittings. Installation of #12 solid wire from outlets to new installed circuit breaker in existing electrical distribution panel. Install Cat 6 cable for 8 data drops and Cat 6A for 4 WAP data drops with 3" of service loop.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Telenet VOIP, Inc | Contractor | 2020-02-06 | 2020-05-29 | 2019/20 |  | PO2W-200000004053 | 0 | 10850.22 | Pay app #3 | 2020-05-29 | 000000020101116 | 10850.22 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 33.25% | Low voltage/classroom raceway for Nelson, room #C1. Remove/reinstall 1 existing smoke detector and 1 existing horn strobe. Installation of required 5400 raceway & fittings. Installation of #12 solid wire from outlets to new installed circuit breaker in existing electrical distribution panel. Install Cat 6 cable for 8 data drops and Cat 6A for 4 WAP data drops with 3" of service loop.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Telenet VOIP, Inc | Contractor | 2020-02-06 | 2021-01-07 | 2020/21 | 2-7677 | PO2W-200000004053 | -2.9559e-12 | 1631.61 | Pay app #4 | 2021-01-07 | 000000020154817 | 1631.61 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 5% | Low voltage/classroom raceway for Nelson, room #C1. Remove/reinstall 1 existing smoke detector and 1 existing horn strobe. Installation of required 5400 raceway & fittings. Installation of #12 solid wire from outlets to new installed circuit breaker in existing electrical distribution panel. Install Cat 6 cable for 8 data drops and Cat 6A for 4 WAP data drops with 3" of service loop.
Nelson-21st Century-Contractor | 1 | Contractor | Nelson | 21st Century | Wolverine Fence | Contractor | 2020-01-15 | 2020-04-02 | 2019/20 | 2-6912 | PO2W-200000003505 | 0 | 4725 | 3822 | 2020-04-02 | 000000020086388 | 4725 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Furnish & install 42' LF of 8' FT high chain link fencing and 1 each 4' FT swing gate -sample for Nelson room #C1.
Nelson-Ceiling replacement-Contractor | 1 | Contractor | Nelson | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 29425.87 | Pay app #1 | 2019-12-17 | 000000020049998 | 29425.87 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231105 | 0.6434% | Ceiling replacement for Nelson.
Nelson-Ceiling replacement-Contractor | 1 | Contractor | Nelson | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 264832.83 | Pay app #3 | 2021-01-08 | 000000020155354 | 264832.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231105 | 5.791% | Ceiling replacement for Nelson.
Nelson-Ceiling replacement-Contractor | 1 | Contractor | Nelson | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5066 | PO1-200000000729 | 15487.3 | 15487.3 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231105 | 0% | Ceiling replacement for Nelson.
Nelson-Drinking fountain replacement-DSA Fees | 1 | DSA Fees | Nelson | Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7624 | PO1-200000000957 | 0 | 1050 | Per email | 2020-02-13 | 000000020070042 | 1050 | 03-120659 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9231104 | 100% | DSA plan check review fee for Nelson drinking fountain.
Nelson-Fire alarm-Design | 1 | Design | Nelson | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 4750 | 28380 | 2021-03-24 | 000000020174735 | 4750 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 2.772% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The total architect contract for Nelson FA is $47,500.00
Nelson-Fire alarm-Design | 1 | Design | Nelson | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28465 | 2021-03-24 | 000000020174735 | 2375 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The total architect contract for Nelson FA is $47,500.00
Nelson-Fire alarm-Design | 1 | Design | Nelson | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28604 | 2021-05-26 | 000000020192536 | 2375 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The total architect contract for Nelson FA is $47,500.00
Nelson-Fire alarm-Design | 1 | Design | Nelson | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28731 | 2021-09-09 | 000000020255226 | 1425 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 0.8316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The total architect contract for Nelson FA is $47,500.00
Nelson-Fire alarm-Design | 1 | Design | Nelson | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2022-02-23 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 29184 | 2022-02-23 | 000000020425550 | 950 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 0.5544% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The total architect contract for Nelson FA is $47,500.00
Nelson-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Nelson | Fire Alarm | Team Inspections | General inspection | 2020-12-15 | 2021-02-09 | 2020/21 |  | PO2W-210000001492 | 0 | 9180 | 202101-11:NFA | 2021-02-09 | 000000020163358 | 9180 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231103 | 37.47% | General inspection for the project as defined in Title 24 at Nelson. Alterations to fire alarm system
Nelson-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Nelson | Fire Alarm | Team Inspections | General inspection | 2020-12-15 | 2021-09-09 | 2021/22 | 21-3568 | PO2W-210000001492 | 0 | 500 | 202108-05:NFA | 2021-09-09 | 000000020255216 | 500 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231103 | 2.041% | General inspection for the project as defined in Title 24 at Nelson. Alterations to fire alarm system
Nelson-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Nelson | Fire Alarm | Team Inspections | General inspection | 2020-12-15 | 2021-09-13 | 2020/21 |  | PO2W-210000001492 | 0 | 2570 | 20210630-08: NFA | 2021-09-13 | 000000020257046 | 2570 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231103 | 10.49% | General inspection for the project as defined in Title 24 at Nelson. Alterations to fire alarm system
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1017.45 | Pay app #1 | 2020-03-10 | 000000020079637 | 1017.45 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.07951% | Fire alarm and low voltage service for Nelson
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-12-18 | 2020/21 |  | PO1-200000000662 | 0 | 8907.87 | Pay app #10 | 2020-12-18 | 000000020151942 | 8907.87 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.6961% | Fire alarm and low voltage service for Nelson
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 47854.83 | Pay app #11 | 2021-05-21 | 000000020191188 | 47854.83 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 3.739% | Fire alarm and low voltage service for Nelson
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 5867.44 | Pay app #12 | 2021-05-21 | 000000020191188 | 5867.44 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.4585% | Fire alarm and low voltage service for Nelson
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 9127.55 | Pay app #13 | 2021-05-21 | 000000020191188 | 9127.55 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.7132% | Fire alarm and low voltage service for Nelson
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 7359.72 | Pay app #14 | 2021-05-21 | 000000020191188 | 7359.72 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.5751% | Fire alarm and low voltage service for Nelson
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 2263.16 | Pay app #15 | 2021-05-21 | 000000020191188 | 2263.16 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.1768% | Fire alarm and low voltage service for Nelson
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 29445.32 | Pay app #16 | 2021-11-22 | 000000020341778 | 29445.32 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 2.301% | Fire alarm and low voltage service for Nelson
Nelson-Fire Alarm-Contractor | 1 | Contractor | Nelson | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4509 | PO1-200000000662 | 7591.74 | 7591.74 |  |  |  | 0 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0% | Fire alarm and low voltage service for Nelson
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 13585.07 | 0173449-IN | 2019-10-10 | 000000020025135 | 13585.07 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9241101 | 0.3127% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10091.76 | 0173660-IN | 2019-10-10 | 000000020025135 | 10091.76 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9241101 | 0.2323% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 175 | 0173449-IN | 2019-10-10 | 000000020025135 | 175 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.004028% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 105 | 0173449-IN | 2019-10-10 | 000000020025135 | 105 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.002417% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 52.5 | 0173449-IN | 2019-10-10 | 000000020025135 | 52.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.001208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 332.5 | 0173449-IN | 2019-10-10 | 000000020025135 | 332.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.007653% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 407.4 | 0173449-IN | 2019-10-10 | 000000020025135 | 407.4 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.009377% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1121.05 | 0173449-IN | 2019-10-10 | 000000020025135 | 1121.05 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.0258% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 130 | 0173660-IN | 2019-10-10 | 000000020025135 | 130 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.002992% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 78 | 0173660-IN | 2019-10-10 | 000000020025135 | 78 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.001795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 39 | 0173660-IN | 2019-10-10 | 000000020025135 | 39 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.0008976% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 247 | 0173660-IN | 2019-10-10 | 000000020025135 | 247 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.005685% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 302.64 | 0173660-IN | 2019-10-10 | 000000020025135 | 302.64 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.006966% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 832.78 | 0173660-IN | 2019-10-10 | 000000020025135 | 832.78 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.01917% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 242590.4 | 0175374-IN | 2019-10-22 | 000000020029495 | 242590.4 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9241101 | 8.647% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 937.5 | 0175374-IN | 2019-10-22 | 000000020029495 | 937.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.03342% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1875 | 0175374-IN | 2019-10-22 | 000000020029495 | 1875 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.06683% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 3125 | 0175374-IN | 2019-10-22 | 000000020029495 | 3125 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.1114% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5937.5 | 0175374-IN | 2019-10-22 | 000000020029495 | 5937.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.2116% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7275 | 0175374-IN | 2019-10-22 | 000000020029495 | 7275 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.2593% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 20018.75 | 0175374-IN | 2019-10-22 | 000000020029495 | 20018.75 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.7135% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173474-IN | 2019-09-23 | 000000020017958 | 1300.32 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Newton. Total cart: 1
Newton-21st Century-Technology | 1 | Technology | Newton | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 20805.18 | 0175378-IN | 2019-10-15 | 000000020026572 | 20805.18 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 2.622% | Ergotron Zip40 Charging carts to store laptops at Newton. Total carts: 16
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 7376.25 | 80804 | 2020-01-09 | 000000020055612 | 7376.25 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.513% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3231.25 | 80796 | 2020-01-14 | 000000020057268 | 3231.25 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.2247% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8163.75 | 81699 | 2020-01-14 | 000000020057268 | 8163.75 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5678% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8072.5 | 83068 | 2020-04-01 | 000000020085959 | 8072.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5614% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 9405 | 82273 | 2020-04-01 | 000000020085960 | 9405 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6541% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 7480 | 84567 | 2020-04-15 | 000000020089466 | 7480 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5202% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9737.5 | 85320 | 2020-05-28 | 000000020100719 | 9737.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6772% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 8587.5 | 86240 | 2020-06-17 | 000000020106117 | 8587.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5972% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 6685 | 86864 | 2020-07-27 | 000000020116270 | 6685 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.4649% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 10803.44 | 88480 | 2020-08-17 | 000000020119773 | 10803.44 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.7513% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 10204.46 | 89359 | 2020-10-13 | 000000020134067 | 10204.46 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.7097% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 9668.25 | 90460 | 2020-10-20 | 000000020136025 | 9668.25 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6724% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 10772.74 | 91321 | 2020-12-18 | 000000020151933 | 10772.74 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.7492% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 9313.5 | 91964 | 2020-12-18 | 000000020151933 | 9313.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6477% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 9959.55 | 92821 | 2021-02-08 | 000000020162981 | 9959.55 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6926% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 7326.23 | 94011 | 2021-04-05 | 000000020177572 | 7326.23 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5095% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 6204 | 94918 | 2021-04-16 | 000000020181024 | 6204 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.4315% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 6625.6 | 95700 | 2021-05-25 | 000000020192064 | 6625.6 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.4608% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 3842.19 | 96936 | 2021-05-25 | 000000020192064 | 3842.19 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.2672% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 5920 | 97857R1 | 2021-06-22 | 000000020200048 | 5920 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.4117% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-08 | 2021/22 |  | PO1-200000000640 | 0 | 21440 | 100426 | 2021-09-08 | 000000020253624 | 21440 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 1.491% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000640 | 0 | 9760 | 98430 | 2021-09-09 | 000000020255187 | 9760 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6788% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4694 | PO1-200000000640 | -10125.71 | -10125.71 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00
Newton-21st Century-DSA Fees | 1 | DSA Fees | Newton | 21st Century | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 2020/21 | 21-3753 | PO2W-210000001572 | 0 | 28270.82 | Per email | 2021-01-20 | 000000020157907 | 28270.82 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9241101 | 100% | DSA plan check review fee for Newton 21st Century.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 2018/19 |  | PO2W-200000001210, 19-101980 | 0 | 2312.3 | 966481 | 2018-10-19 | 24871020 | 2312.3 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.705% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-09-16 | 2018/19 |  | PO2W-200000001210, 19-101980 | 0 | 12717.65 | 968552R | 2019-09-16 | 000000020015463 | 12717.65 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 9.378% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-02-13 | 2019/20 |  | PO2W-200000001210, 19-101980 | 0 | 16186.1 | 970829 | 2020-02-13 | 000000020070049 | 16186.1 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 11.94% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-06-04 | 2019/20 |  | PO2W-200000001210, 19-101980 | 0 | 19076.48 | 971445 | 2020-06-04 | 000000020102538 | 19076.48 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 14.07% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-09-10 | 2020/21 |  | PO2W-200000001210, 19-101980 | 0 | 11738 | 971454R | 2020-09-10 | 000000020125582 | 11738 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 8.655% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. Allowances for civil engineering for path of travel (Mod 1 dated 02/11/19).
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001210, 19-101980 | 0 | 9538.23 | 971723R | 2021-05-07 | 000000020187161 | 9538.23 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 7.033% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001210, 19-101980 | 0 | 9538.24 | 972096R | 2021-05-07 | 000000020187161 | 9538.24 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 7.033% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-06-23 | 2020/21 |  | PO2W-200000001210, 19-101980 | 0 | 2890.38 | 975779 | 2021-06-23 | 000000020200446 | 2890.38 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 2.131% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-12-20 | 2021/22 |  | PO2W-200000001210, 19-101980 | 0 | 867.11 | 96675 | 2021-12-20 | 000000020370745 | 867.11 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0.6394% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-01-16 | 2021/22 | 2-521 | PO2W-200000001210, 19-101980 | 50750.51 | 50750.51 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00.
Newton-21st Century-Design | 1 | Design | Newton | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2020-08-07 | 2020-09-10 | 2020/21 | 21-1215 | PO2W-210000000360 | 0 | 85965 | 972646 | 2020-09-10 | 000000020125582 | 85965 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 100% | Architect - Modifications to Architect services for Newton 21st Century, per District's request. To pay for : Mod 2 - CADD as builts, Mod 3 - Restrooms, Mod 4 - Contract deviations, & Mod 5 - New Standards. Addendum to PO2W-20*1210.
Newton-21st Century-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-10-13 | 2020/21 | 2-10469 | PO2W-200000005392 | 0 | 2950 | MCSI-4528 | 2020-10-13 | 000000020134092 | 2950 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 100% | Asbestos & lead-based paint survey of Newton's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Newton-21st Century-Contractor | 1 | Contractor | Newton | 21st Century | Williams Tree Service | Tree Service | 2020-10-27 | 2022-08-11 | 2020/21 | 21-2727 | PO2W-210000000996 | 0 | 3400 | Newton | 2020-11-04 | 000000020139894 | 3400 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5630 | 9241101 | 100% | Removed 3 palm trees and their stumps at Newton.
Newton-Fire alarm-DSA Fees | 1 | DSA Fees | Newton | Fire alarm | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-03-20 | 2020/21 | 21-4441 | PO2W-210000001789 | 0 | 645 | 12429 | 2021-03-20 | 000000020172261 | 645 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9241103 | 100% | DGS plan/field review fee for Newton fire alarm
Newton-Fire alarm-Design | 1 | Design | Newton | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2020-09-18 | 2020/21 |  | PO1-2000000000899, 19-104053, JVER21-187 | 0 | 7125 | 27975 | 2020-09-18 | 20122659 | 7125 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241103 | 100% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Newton. Facilities paid PO1-20*899 & 19-104053 in the amount of $38,000.00. The total architect contract for Newton FA is $47,500.00
Newton-Fire alarm-Design | 1 | Design | Newton | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28167 | 2021-02-05 | 000000020162584 | 1425 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241103 | 0.8316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Newton. Facilities paid PO1-20*899 & 19-104053 in the amount of $38,000.00. The total architect contract for Newton FA is $47,500.00
Newton-Fire alarm-Design | 1 | Design | Newton | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 | 21-1992 | PO2W-210000000680 | 0 | 950 | 28513 | 2021-05-26 | 000000020192536 | 950 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241103 | 0.5544% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Newton. Facilities paid PO1-20*899 & 19-104053 in the amount of $38,000.00. The total architect contract for Newton FA is $47,500.00
Newton-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Newton | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2020-05-26 | 2019/20 |  | PO2W-200000002811 | 0 | 6090 | 202005-05:NFA | 2020-05-26 | 000000020099846 | 6090 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241103 | 74.95% | General inspection for the project as defined in Title 24 at Newton. Alterations to 1 campus wide fire alarm upgrade
Newton-Fire Alarm-DSA Inspection | 1 | DSA Inspection | Newton | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2020-06-19 | 2019/20 | 2-5883 | PO2W-200000002811 | 0 | 2035 | 202006-04:NFA | 2020-06-19 | 000000020106934 | 2035 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241103 | 25.05% | General inspection for the project as defined in Title 24 at Newton. Alterations to 1 campus wide fire alarm upgrade
Newton-Fire Alarm-Contractor | 1 | Contractor | Newton | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 3359.2 | Pay app #1 | 2020-03-10 | 000000020079637 | 3359.2 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.2625% | Fire alarm and low voltage service for Newton
Newton-Fire Alarm-Contractor | 1 | Contractor | Newton | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-04-08 | 2019/20 |  | PO1-200000000662 | 0 | 21443.4 | Pay app #2 | 2020-04-08 | 000000020087746 | 21443.4 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 1.676% | Fire alarm and low voltage service for Newton
Newton-Fire Alarm-Contractor | 1 | Contractor | Newton | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-04-24 | 2019/20 |  | PO1-200000000662 | 0 | 17273.14 | Pay app #3 | 2020-04-24 | 000000020092209 | 17273.14 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 1.35% | Fire alarm and low voltage service for Newton
Newton-Fire Alarm-Contractor | 1 | Contractor | Newton | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 21295.68 | Pay app #4 | 2020-05-29 | 000000020101116 | 21295.68 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 1.664% | Fire alarm and low voltage service for Newton
Newton-Fire Alarm-Contractor | 1 | Contractor | Newton | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 3504.98 | Pay app #5 | 2020-07-30 | 000000020117024 | 3504.98 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.2739% | Fire alarm and low voltage service for Newton
Newton-Fire Alarm-Contractor | 1 | Contractor | Newton | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 10458.36 | Pay app #6 | 2020-07-30 | 000000020117024 | 10458.36 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.8172% | Fire alarm and low voltage service for Newton
Newton-Fire Alarm-Contractor | 1 | Contractor | Newton | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-08-28 | 2020/21 |  | PO1-200000000662 | 0 | 1211.25 | Pay app #7 | 2020-08-28 | 000000020122656 | 1211.25 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.09465% | Fire alarm and low voltage service for Newton
Newton-Fire Alarm-Contractor | 1 | Contractor | Newton | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4510 | PO1-200000000662 | 4134 | 4134 |  |  |  | 0 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0% | Fire alarm and low voltage service for Newton
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 2021/22 |  | PO1-210000000492 | 0 | 129.45 | 10959170 | 2021-09-08 | 000000020253617 | 129.45 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 2.589% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton.
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 2021/22 |  | PO1-210000000492 | 0 | 28.53 | 10973023 | 2021-09-08 | 000000020253617 | 28.53 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 0.5706% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton.
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 2021/22 |  | PO1-210000000492 | 0 | 15.58 | 10975113 | 2021-09-08 | 000000020253617 | 15.58 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 0.3116% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton.
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 2021/22 |  | PO1-210000000492 | 0 | 13.38 | 10978975 | 2021-09-08 | 000000020253617 | 13.38 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 0.2676% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton.
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-01-24 | 2021/22 |  | PO1-210000000492 | 0 | 353 | 11120655 | 2022-01-24 | 000000020395760 | 353 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 7.06% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton.
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-03-11 | 2021/22 |  | PO2W-220000001166 | 0 | 117420 | Pay app #1 | 2022-03-11 | 000000020441844 | 117420 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 29.47% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2025-12-08 | 2021/22 | 22-3543 | PO2W-220000001166 | 281080 | 281080 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 0% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30
Newton-Interim Housing-DSA Fees | 1 | DSA Fees | Newton | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-01-28 | 2019/20 | 2-6939 | PO1-200000000863 | 0 | 4175.44 | Per email | 2020-01-28 | 000000020062969 | 4175.44 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9241102 | 100% | DSA plan check review fee for Newton interim housing.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2021-12-15 | 2022-12-15 | 2021/22 | 22-3670 | PO1-220000000605 | 1725 | 1725 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 0% | Architect - Modifications to Architect services for Newton Interim Housing parking lot. Additional design service fee for the civil engineering to conduct topographic survey for redesigning the existing ADA parking stalls/accessible ramp (Mod 5 dated 12/06/21). Addendum to PO2W-20*1208.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 2018/19 |  | PO2W-200000001208, 19-101983 | 0 | 1006.76 | 966483 | 2018-10-19 | 24871020 | 1006.76 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 1.431% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-02-28 | 2018/19 |  | PO2W-200000001208, 19-101983 | 0 | 11511.5 | 967630 | 2019-02-28 | 25125651 | 11511.5 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 16.37% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. Allowances for site survey (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $24,520.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-09-16 | 2018/19 |  | PO2W-200000001208, 19-101983 | 0 | 12584.52 | 968554R | 2019-09-16 | 000000020015463 | 12584.52 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 17.89% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-04-02 | 2019/20 |  | PO2W-200000001208, 19-101983 | 0 | 16611.57 | 970837 | 2020-04-02 | 000000020086379 | 16611.57 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 23.62% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001208, 19-101983 | 0 | 8488.5 | 971456 | 2021-05-07 | 000000020187161 | 8488.5 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 12.07% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. Allowances for site survey (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $24,520.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-06-02 | 2020/21 |  | PO2W-200000001208, 19-101983 | 0 | 1258.45 | 972926 | 2021-06-02 | 000000020194098 | 1258.45 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 1.789% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-12-20 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 1258.45 | 976673 | 2021-12-20 | 000000020370745 | 1258.45 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 1.789% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-03-11 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 5033.81 | 978312 | 2022-03-11 | 000000020441852 | 5033.81 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 7.157% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-03-11 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 2516.9 | 978476 | 2022-03-11 | 000000020441852 | 2516.9 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 3.578% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-03-24 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 3146.13 | 978836 | 2022-03-24 | 000000020451058 | 3146.13 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 4.473% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-01-16 | 2021/22 | 2-518 | PO2W-200000001208, 19-101983 | 6921.49 | 6921.49 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 0% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-09-16 | 2018/19 |  | PO2W-200000001208, 19-101983 | 0 | 24.36 |  |  |  | 24.36 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 0% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-09-16 | 2019/20 |  | PO2W-200000001208, 19-101983 | 0 | -24.36 |  |  |  | -24.36 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 0% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. Reverse accrual from prior year
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2020-08-10 | 2021-05-07 | 2020/21 | 21-1247 | PO2W-210000000374 | 0 | 4520 | 971456R | 2021-05-07 | 000000020187161 | 4520 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 100% | Architect - Modifications to Architect services for Newton Interim Housing, per District's request (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $24,520.00. Addendum to PO2W-20*1208.
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2021-02-24 | 2021-05-07 | 2020/21 | 21-4651 | PO2W-210000001831 | 0 | 5000 | 972466R | 2021-05-07 | 000000020187161 | 5000 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 100% | Architect - Modifications to Architect services for Newton Interim Housing, to change fire alarm system to a non-voice evacuation type system (Mod 4 dated 06/01/20, revision 2). Addendum to PO2W-20*1208.
Newton-Interim Housing-Modular Buildings | 1 | Modular Buildings | Newton | Interim Housing | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-02-18 | 2019/20 | 2-2085 | PO2W-200000003192, PO2W-200000001051, 19-107586 | 0 | 218488.74 | R20530142 | 2020-02-18 | 000000020070593 | 218488.74 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9241102 | 100% | Purchase of 4 Portable classrooms - 24' x 40' DSA, install closure panels, new carpets, HVAC, T-8 lights lines, and delivery to Newton.
Newton-Interim Housing-Modular Buildings | 1 | Modular Buildings | Newton | Interim Housing | Mobile Modular Management Corp | Portable classrooms (4) | 2019-03-20 | 2022-03-16 | 2021/22 | 2-2085 | PO2W-2-00000003193, PO2W-200000001051, 19-107586 | 0 | 21300 | R20587497 | 2022-03-16 | 000000020444816 | 21300 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9241102 | 100% | For 4 portable classrooms - Block & level building, installation, and relocation of these classrooms at Newton
Newton-Interim Housing-Advertisement | 1 | Advertisement | Newton | Interim Housing | San Gabriel Tribune | Newspaper Advertisement | 2021-07-09 | 2021-07-30 | 2021/22 | 22-450 | PO2W-220000000052 | 0 | 1088 | 11469359 | 2021-07-30 | 000000020221431 | 1088 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9241102 | 100% | Advertising for Bid 2020-21.30 Newton Middle School Interim Housing. Publication dates: 06/15/21 & 06/21/21.
Newton-Interim Housing-Utilities | 1 | Utilities | Newton | Interim Housing | Southern California Edison Co (SCE) | Temporary power | 2022-01-10 | 2022-01-24 | 2021/22 | 22-3884 | PO2W-220000001329 | 0 | 1072 | 454421 | 2022-01-24 | 000000020395794 | 1072 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6233 | 9241102 | 100% | Temporary power for Newton Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Suburban Water Systems | Fire flow testing | 2020-01-14 | 2020-01-23 | 2019/20 | 2-6872 | PO2W-200000003382 | 0 | 212 | Per email | 2020-01-23 | 000000020061285 | 212 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 100% | Fee for fire flow testing performed or witnessed using Utility personnel at Newton. This fees applies to tests performed on distrubution systems in the entire territory served by the Utility.
Newton-Interim Housing-DSA Inspection | 1 | DSA Inspection | Newton | Interim Housing | Team Inspections | General inspection | 2020-07-01 | 2023-07-31 | 2021/22 | 21-307 | PO2W-210000000015 | 16000 | 16000 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241102 | 0% | General inspection for the project as defined in Title 24 at Newton. Alterations to (1) CR Buildings & relocation of (4) 24' x 40' relocatable CR buildings
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2019-07-29 | 2021-02-05 | 2020/21 |  | PO2W-200000000234 | 0 | 8497 | 71498 | 2021-02-05 | 000000020162580 | 8497 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 71.87% | Rental of power pole - Provide temporary power to portable classrooms and include 6 month of rents at Newton. After 6 months, rental is $150.00/month
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2019-07-29 | 2023-01-16 | 2021/22 | 2-1102 | PO2W-200000000234 | 3325 | 3325 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 0% | Rental of power pole - Provide temporary power to portable classrooms and include 6 month of rents at Newton. After 6 months, rental is $150.00/month
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-03-30 | 2025-07-11 | 2021/22 | 22-6075 |  | 7665 | 7665 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 0% | Change order for meter panel relocation & additional equipment. Provide temporary power to portable classrooms at Newton. Addendum to PO2W-20*234. The total project with change order is $19,487.00
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 13585.07 | 0173448-IN | 2019-10-10 | 000000020025135 | 13585.07 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9251101 | 0.3127% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6986.6 | 0173634-IN | 2019-10-10 | 000000020025135 | 6986.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9251101 | 0.1608% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 175 | 0173448-IN | 2019-10-10 | 000000020025135 | 175 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.004028% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 105 | 0173448-IN | 2019-10-10 | 000000020025135 | 105 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.002417% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 52.5 | 0173448-IN | 2019-10-10 | 000000020025135 | 52.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.001208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 332.5 | 0173448-IN | 2019-10-10 | 000000020025135 | 332.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.007653% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 407.4 | 0173448-IN | 2019-10-10 | 000000020025135 | 407.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.009377% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1121.05 | 0173448-IN | 2019-10-10 | 000000020025135 | 1121.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.0258% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 209.52 | 0173634-IN | 2019-10-10 | 000000020025135 | 209.52 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.004822% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 171 | 0173634-IN | 2019-10-10 | 000000020025135 | 171 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.003936% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 90 | 0173634-IN | 2019-10-10 | 000000020025135 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 54 | 0173634-IN | 2019-10-10 | 000000020025135 | 54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.001243% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 27 | 0173634-IN | 2019-10-10 | 000000020025135 | 27 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.0006214% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 576.54 | 0173634-IN | 2019-10-10 | 000000020025135 | 576.54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.01327% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 130028.46 | 0174900-IN | 2019-10-10 | 000000020025136 | 130028.46 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9251101 | 2.993% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 502.5 | 0174900-IN | 2019-10-10 | 000000020025136 | 502.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.01157% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1005 | 0174900-IN | 2019-10-10 | 000000020025136 | 1005 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.02313% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1675 | 0174900-IN | 2019-10-10 | 000000020025136 | 1675 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.03855% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3182.5 | 0174900-IN | 2019-10-10 | 000000020025136 | 3182.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.07325% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3899.4 | 0174900-IN | 2019-10-10 | 000000020025136 | 3899.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.08975% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10730.05 | 0174900-IN | 2019-10-10 | 000000020025136 | 10730.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.247% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 15525.78 | 0175595-IN | 2019-10-22 | 000000020029495 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9251101 | 0.5534% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 120 | 0175595-IN | 2019-10-22 | 000000020029495 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.004277% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 200 | 0175595-IN | 2019-10-22 | 000000020029495 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.007129% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 380 | 0175595-IN | 2019-10-22 | 000000020029495 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.01354% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 465.6 | 0175595-IN | 2019-10-22 | 000000020029495 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.0166% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1281.2 | 0175595-IN | 2019-10-22 | 000000020029495 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.04567% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 60 | 0175595-IN | 2019-10-22 | 000000020029495 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.002139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173479-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9251101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Orange Grove. Toatl carts: 2
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0175549-IN | 2019-10-22 | 000000020029495 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9251101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Orange Grove. Toatl carts: 2
Orange Grove-21st Century-Technology | 3 | Technology | Orange Grove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 13003.23 | 0175002-IN | 2019-10-08 | 000000020023867 | 13003.23 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9251101 | 1.639% | Ergotron Zip40 Charging carts to store laptops at Orange Grove. Total carts: 10
Orange Grove-21st Century-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 800 | 100653 | 2021-09-08 | 000000020253624 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 0.04374% | Construction management services for Orange Grove - phase 3 & 4. This PO includes allowances of $40,000.00
Orange Grove-21st Century-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 2960 | 101514 | 2021-09-29 | 000000020275054 | 2960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 0.1618% | Construction management services for Orange Grove - phase 3 & 4. This PO includes allowances of $40,000.00
Orange Grove-21st Century-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2024-07-01 | 2021/22 | 22-1057 | PO1-220000000334 | 197337 | 197337 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 0% | Construction management services for Orange Grove - phase 3 & 4. This PO includes allowances of $40,000.00
Orange Grove-21st Century-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862 | 0 | 5505 | 102578 | 2021-11-08 | 000000020325325 | 5505 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 11.23% | Construction management services for Baldwin - phase 3 & 4. This PO is to pay invoice #102578 (Prof service from 09/01-09/30/21), dated 09/30/21
Orange Grove-21st Century-Environ Consultant | 3 | Environ Consultant | Orange Grove | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1577 | PO1-210000000427 | 0 | 2800 | MCSI-4612 | 2020-10-13 | 000000020134092 | 2800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9251101 | 6.796% | Asbestos & lead-based paint survey of Orange Grove's permanent buildings.
Orange Grove-21st Century-Design | 3 | Design | Orange Grove | 21st Century | PBK Architects | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6231 | PO1-210000000685 | 222000 | 222000 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251101 | 0% | Architect - Provide architectural/engineering services for the Orange Grove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Orange Grove.
Orange Grove-Fire alarm-DSA Fees | 3 | DSA Fees | Orange Grove | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 1080 | Per email | 2021-03-30 | 000000020176205 | 1080 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9251103 | 15.22% | DSA plan check review fee for Orange Grove fire alarm.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7425 | 28231 | 2021-02-05 | 000000020162584 | 7425 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 1.904% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 4920 | 28292 | 2021-02-09 | 000000020163360 | 4920 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 1.262% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-22 | 2020/21 |  | PO2W-210000000984 | 0 | 30 | 28292 | 2021-02-22 | 000000020166218 | 30 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0.007692% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4950 | 28388 | 2021-03-24 | 000000020174735 | 4950 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 1.269% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4950 | 28472 | 2021-03-24 | 000000020174735 | 4950 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 1.269% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2475 | 28521 | 2021-05-26 | 000000020192536 | 2475 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0.6346% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9900 | 28615 | 2021-05-26 | 000000020192536 | 9900 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 2.538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1485 | 28688 | 2021-06-23 | 000000020200466 | 1485 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0.3808% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 990 | 28836 | 2021-09-09 | 000000020255227 | 990 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0.2538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Fire alarm-Design | 3 | Design | Orange Grove | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2025-10-20 | 2021/22 | 21-2535 | PO2W-210000000984 | 12375 | 12375 |  |  |  | 0 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove.
Orange Grove-Interim Housing-Design | 3 | Design | Orange Grove | Interim Housing | PBK Architects | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6235 | PO1-210000000687 | 95400 | 95400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251102 | 0% | Architect - Provide architectural/engineering services for the Orange Grove Interim Housing project. Sitework will be limited to ADA access & path of travel requirements to the new portables.
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5822.17 | 0173644-IN | 2019-10-10 | 000000020025135 | 5822.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9261101 | 0.134% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7762.89 | 0173803-IN | 2019-10-10 | 000000020025135 | 7762.89 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9261101 | 0.1787% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 67925.32 | 0174011-IN | 2019-10-10 | 000000020025135 | 67925.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9261101 | 1.563% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 174.6 | 0173644-IN | 2019-10-10 | 000000020025135 | 174.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.004019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 142.5 | 0173644-IN | 2019-10-10 | 000000020025135 | 142.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.00328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 75 | 0173644-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 45 | 0173644-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 22.5 | 0173644-IN | 2019-10-10 | 000000020025135 | 22.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.0005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 480.45 | 0173644-IN | 2019-10-10 | 000000020025135 | 480.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.01106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173803-IN | 2019-10-10 | 000000020025135 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173803-IN | 2019-10-10 | 000000020025135 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173803-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173803-IN | 2019-10-10 | 000000020025135 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173803-IN | 2019-10-10 | 000000020025135 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173803-IN | 2019-10-10 | 000000020025135 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 262.5 | 0174011-IN | 2019-10-10 | 000000020025135 | 262.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.006042% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 525 | 0174011-IN | 2019-10-10 | 000000020025135 | 525 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.01208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 875 | 0174011-IN | 2019-10-10 | 000000020025135 | 875 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.02014% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1662.5 | 0174011-IN | 2019-10-10 | 000000020025135 | 1662.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.03827% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2037 | 0174011-IN | 2019-10-10 | 000000020025135 | 2037 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.04688% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5605.25 | 0174011-IN | 2019-10-10 | 000000020025135 | 5605.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.129% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0174081-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9261101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Palm. Total carts: 7
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 7801.94 | 0174092-IN | 2019-09-23 | 000000020017958 | 7801.94 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9261101 | 8.561% | Ergotron Zip40 Charging carts to store laptops at Palm. Total carts: 7
Palm-21st Century-Technology | 6 | Technology | Palm | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 9102.26 | 0175150-IN | 2019-10-08 | 000000020023867 | 9102.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9261101 | 1.147% | Ergotron Zip40 Charging carts to store laptops at Palm. Total carts: 7
Palm-21st Century-Contractor | 6 | Contractor | Palm | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-08-28 | 2020/21 |  | PO2W-200000004391 | 0 | 2006.79 | Pay app #2 | 2020-08-28 | 000000020122640 | 2006.79 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261101 | 0.4457% | Demo 4,266 sy carpet, prepare concrete. Supply & install 252 yd First step Up II & bond at Palm for room #13
Palm-21st Century-Contractor | 6 | Contractor | Palm | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 4365.45 | Pay app #3 | 2020-12-08 | 000000020148205 | 4365.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261101 | 0.9696% | Prep & install Mohawk LVT, walk off mat & base at Palm for room #13
Palm-21st Century-Contractor | 6 | Contractor | Palm | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 2020/21 | 21-4688 | PO2W-210000001838 | 0 | 40000 | 2021-022D | 2021-04-23 | 000000020182905 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261101 | 30.77% | Demo of ceiling tiles in 16 classrooms at Palm
Palm-21st Century-FF & E | 6 | FF & E | Palm | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 11995.3 | 3207761219 | 2020-02-03 | 000000020065147 | 11995.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9261101 | 2.787% | Furniture for Palm - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Palm-21st Century-FF & E | 6 | FF & E | Palm | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9261101 | 1.655% | Furniture for Palm - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Palm-21st Century-Environ Consultant | 6 | Environ Consultant | Palm | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10245 | PO2W-200000005323 | 0 | 2500 | MCSI-4541 | 2020-08-17 | 000000020119790 | 2500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9261101 | 100% | Asbestos & lead-based paint survey of Palm's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Palm-Ceiling replacement-Contractor | 6 | Contractor | Palm | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 22069.45 | Pay app #1 | 2019-12-17 | 000000020049998 | 22069.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261105 | 0.4826% | Ceiling replacement for Palm.
Palm-Ceiling replacement-Contractor | 6 | Contractor | Palm | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 66208.35 | Pay app #2 | 2020-10-21 | 000000020136454 | 66208.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261105 | 1.448% | Ceiling replacement for Palm.
Palm-Ceiling replacement-Contractor | 6 | Contractor | Palm | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 132416.7 | Pay app #5 | 2021-06-17 | 000000020198995 | 132416.7 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261105 | 2.895% | Ceiling replacement for Palm.
Palm-Ceiling replacement-Contractor | 6 | Contractor | Palm | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5067 | PO1-200000000729 | 11615.5 | 11615.5 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261105 | 0% | Ceiling replacement for Palm.
Palm-Drinking fountain replacement-DSA Fees | 6 | DSA Fees | Palm | Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7625 | PO1-200000000958 | 0 | 1050 | Per email | 2020-02-13 | 000000020070043 | 1050 | 03-120660 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9261104 | 100% | DSA plan check review fee for Palm drinking fountain.
Palm-Fire alarm-DSA Fees | 6 | DSA Fees | Palm | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 870 | Per email | 2021-03-30 | 000000020176206 | 870 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9261103 | 12.26% | DSA plan check review fee for Palm fire alarm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28232 | 2021-02-05 | 000000020162584 | 7275 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28293 | 2021-02-09 | 000000020163360 | 7275 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4850 | 28389 | 2021-03-24 | 000000020174735 | 4850 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 1.244% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28473 | 2021-03-24 | 000000020174735 | 2425 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28522 | 2021-05-26 | 000000020192536 | 2425 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28616 | 2021-05-26 | 000000020192536 | 9700 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28689 | 2021-06-23 | 000000020200466 | 1455 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0.3731% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28837 | 2021-09-09 | 000000020255227 | 970 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0.2487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm-Fire alarm-Design | 6 | Design | Palm | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2025-10-20 | 2021/22 | 21-2535 | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm.
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1164.44 | 0173685-IN | 2019-10-10 | 000000020025135 | 1164.44 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 8031101 | 0.0268% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 96.09 | 0173685-IN | 2019-10-10 | 000000020025135 | 96.09 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.002212% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 34.92 | 0173685-IN | 2019-10-10 | 000000020025135 | 34.92 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.0008037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 28.5 | 0173685-IN | 2019-10-10 | 000000020025135 | 28.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.000656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15 | 0173685-IN | 2019-10-10 | 000000020025135 | 15 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.0003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9 | 0173685-IN | 2019-10-10 | 000000020025135 | 9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.0002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4.5 | 0173685-IN | 2019-10-10 | 000000020025135 | 4.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.0001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7762.89 | 0175575-IN | 2019-10-22 | 000000020029495 | 7762.89 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 8031101 | 0.2767% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 190 | 0175575-IN | 2019-10-22 | 000000020029495 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.006772% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 232.8 | 0175575-IN | 2019-10-22 | 000000020029495 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.008298% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 640.6 | 0175575-IN | 2019-10-22 | 000000020029495 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.02283% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 100 | 0175575-IN | 2019-10-22 | 000000020029495 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.003564% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 60 | 0175575-IN | 2019-10-22 | 000000020029495 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.002139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20
Palm Canyon-21st Century-Technology | 0 | Technology | Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 30 | 0175575-IN | 2019-10-22 | 000000020029495 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.001069% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6628.58 | 0173677-IN | 2019-10-10 | 000000020025135 | 6628.58 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9281101 | 0.1526% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 130622.2 | 0174861-IN | 2019-10-10 | 000000020025135 | 130622.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9281101 | 3.006% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 197.88 | 0173677-IN | 2019-10-10 | 000000020025135 | 197.88 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.004555% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 161.5 | 0173677-IN | 2019-10-10 | 000000020025135 | 161.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.003717% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 85 | 0173677-IN | 2019-10-10 | 000000020025135 | 85 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.001956% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 51 | 0173677-IN | 2019-10-10 | 000000020025135 | 51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.001174% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 25.5 | 0173677-IN | 2019-10-10 | 000000020025135 | 25.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.0005869% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 544.51 | 0173677-IN | 2019-10-10 | 000000020025135 | 544.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.01253% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 502.5 | 0174861-IN | 2019-10-10 | 000000020025135 | 502.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.01157% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1005 | 0174861-IN | 2019-10-10 | 000000020025135 | 1005 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.02313% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1675 | 0174861-IN | 2019-10-10 | 000000020025135 | 1675 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.03855% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3182.5 | 0174861-IN | 2019-10-10 | 000000020025135 | 3182.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.07325% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3899.4 | 0174861-IN | 2019-10-10 | 000000020025135 | 3899.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.08975% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10730.05 | 0174861-IN | 2019-10-10 | 000000020025135 | 10730.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.247% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352
Sierra Vista-21st Century-Technology | 8 | Technology | Sierra Vista | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 11756.35 | 0174873-IN | 2019-10-08 | 000000020023867 | 11756.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9281101 | 1.482% | Ergotron Zip40 Charging carts to store laptops at Sierra Vista. Total carts: 9
Sierra Vista-21st Century-Environ Consultant | 8 | Environ Consultant | Sierra Vista | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1578 | PO1-210000000427 | 0 | 3000 | MCSI-4613 | 2020-10-13 | 000000020134092 | 3000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9281101 | 7.282% | Asbestos & lead-based paint survey of Sierra Vista's permanent buildings.
Sierra Vista-Fire alarm-DSA Fees | 8 | DSA Fees | Sierra Vista | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 1050 | Per email | 2021-03-30 | 000000020176207 | 1050 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9281103 | 14.8% | DSA plan check review fee for Sierra Vista fire alarm.
Sierra Vista-Fire alarm-Design | 8 | Design | Sierra Vista | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 14850 | 28390 | 2021-03-24 | 000000020174735 | 14850 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 3.808% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista.
Sierra Vista-Fire alarm-Design | 8 | Design | Sierra Vista | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4950 | 28474 | 2021-03-24 | 000000020174735 | 4950 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 1.269% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista.
Sierra Vista-Fire alarm-Design | 8 | Design | Sierra Vista | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 4950 | 28523 | 2021-05-26 | 000000020192536 | 4950 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 1.269% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista.
Sierra Vista-Fire alarm-Design | 8 | Design | Sierra Vista | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9900 | 28617 | 2021-05-26 | 000000020192536 | 9900 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 2.538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista.
Sierra Vista-Fire alarm-Design | 8 | Design | Sierra Vista | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1485 | 28690 | 2021-06-23 | 000000020200466 | 1485 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 0.3808% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista.
Sierra Vista-Fire alarm-Design | 8 | Design | Sierra Vista | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 990 | 28838 | 2021-09-09 | 000000020255227 | 990 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 0.2538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista.
Sierra Vista-Fire alarm-Design | 8 | Design | Sierra Vista | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2025-10-20 | 2021/22 | 21-2535 | PO2W-210000000984 | 12375 | 12375 |  |  |  | 0 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista.
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7408.42 | 0173642-IN | 2019-10-08 | 000000020023867 | 7408.42 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9291101 | 0.1705% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 180.5 | 0173642-IN | 2019-10-08 | 000000020023867 | 180.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.004155% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 95 | 0173642-IN | 2019-10-08 | 000000020023867 | 95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 57 | 0173642-IN | 2019-10-08 | 000000020023867 | 57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.001312% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 28.5 | 0173642-IN | 2019-10-08 | 000000020023867 | 28.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.000656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 221.16 | 0173642-IN | 2019-10-08 | 000000020023867 | 221.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.00509% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 608.57 | 0173642-IN | 2019-10-08 | 000000020023867 | 608.57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.01401% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173778-IN | 2019-10-21 | 000000020028933 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9291101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173778-IN | 2019-10-21 | 000000020028933 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173778-IN | 2019-10-21 | 000000020028933 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173778-IN | 2019-10-21 | 000000020028933 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173778-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173778-IN | 2019-10-21 | 000000020028933 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173778-IN | 2019-10-21 | 000000020028933 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 113075.93 | 0175197-IN | 2019-10-22 | 000000020029495 | 113075.93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9291101 | 4.03% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 435 | 0175197-IN | 2019-10-22 | 000000020029495 | 435 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.0155% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 870 | 0175197-IN | 2019-10-22 | 000000020029495 | 870 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.03101% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1450 | 0175197-IN | 2019-10-22 | 000000020029495 | 1450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.05168% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2755 | 0175197-IN | 2019-10-22 | 000000020029495 | 2755 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.0982% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 3375.6 | 0175197-IN | 2019-10-22 | 000000020029495 | 3375.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.1203% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 9288.7 | 0175197-IN | 2019-10-22 | 000000020029495 | 9288.7 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.3311% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 22206.44 | 0175271-IN | 2019-10-11 | 000000020025716 | 22206.44 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9291101 | 2.798% | Ergotron Zip40 Charging carts to store laptops at Sparks ES. Total carts: 18
Sparks ES-21st Century-Technology | 7 | Technology | Sparks ES | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175272-IN | 2019-10-11 | 000000020025716 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9291101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Sparks ES. Total carts: 18
Sparks ES-21st Century-Contractor | 7 | Contractor | Sparks ES | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 19116.72 | Pay app #3 | 2020-12-08 | 000000020148205 | 19116.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291101 | 4.246% | Prep & install Mohawk LVT, walk off mat & base at Sparks ES for room #5, 9, & 14
Sparks ES-21st Century-Contractor | 7 | Contractor | Sparks ES | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2020-10-13 | 2020/21 | 21-1828 | PO2W-210000000726 | 0 | 40000 | 2020-085AD | 2020-10-13 | 000000020134080 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291101 | 100% | Demo of ceiling tiles in 17 classrooms at Sparks ES
Sparks ES-21st Century-Contractor | 7 | Contractor | Sparks ES | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-06-14 | 2021-09-09 | 2021/22 | 21-6790 | PO2W-210000002615 | 0 | 4000 | 2021-088D | 2021-09-09 | 000000020255195 | 4000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291101 | 23.53% | Demo of ceiling tiles in 1 classroom at Sparks ES for room #19
Sparks ES-21st Century-FF & E | 7 | FF & E | Sparks ES | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9291101 | 3.16% | Furniture for Sparks ES - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Sparks ES-21st Century-FF & E | 7 | FF & E | Sparks ES | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9291101 | 1.655% | Furniture for Sparks ES - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Sparks ES-21st Century-Environ Consultant | 7 | Environ Consultant | Sparks ES | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10246 | PO2W-200000005324 | 0 | 2670 | MCSI-4542 | 2020-08-17 | 000000020119790 | 2670 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9291101 | 100% | Asbestos & lead-based paint survey of Spark ES permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Sparks ES-Ceiling replacement-Contractor | 7 | Contractor | Sparks ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 24521.59 | Pay app #1 | 2019-12-17 | 000000020049998 | 24521.59 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291105 | 0.5362% | Ceiling replacement for Sparks ES.
Sparks ES-Ceiling replacement-Contractor | 7 | Contractor | Sparks ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 73564.77 | Pay app #2 | 2020-10-21 | 000000020136454 | 73564.77 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291105 | 1.609% | Ceiling replacement for Sparks ES.
Sparks ES-Ceiling replacement-Contractor | 7 | Contractor | Sparks ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 147129.54 | Pay app #3 | 2021-01-08 | 000000020155354 | 147129.54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291105 | 3.217% | Ceiling replacement for Sparks ES.
Sparks ES-Ceiling replacement-Contractor | 7 | Contractor | Sparks ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5068 | PO1-200000000729 | 12906.1 | 12906.1 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291105 | 0% | Ceiling replacement for Sparks ES.
Sparks ES-Drinking fountain replacement-DSA Inspection | 7 | DSA Inspection | Sparks ES | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6605 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9291104 | 0% | General inspection for the project as defined in Title 24 at Sparks ES. Replacement of 2-exterior drinking fountains
Sparks ES-Fire Alarm-DSA Fees | 7 | DSA Fees | Sparks ES | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6935 | PO1-200000000848 | 0 | 930 | Per email | 2020-02-13 | 000000020070033 | 930 | 03-120623 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9291103 | 100% | DSA plan check review fee for Sparks ES fire alarm.
Sparks ES-Fire Alarm-Design | 7 | Design | Sparks ES | Fire Alarm | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 2021/22 | 2-6867 | PO1-200000000846 | 12125 | 12125 |  |  |  | 0 | 03-120623 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9291103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks ES. Facilities paid PO2W-20*4420 in the amount of $36,375.00. The total architect contract for Spark ES FA is $48,500.00
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173640-IN | 2019-10-08 | 000000020023867 | 7798.34 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9301101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173640-IN | 2019-10-08 | 000000020023867 | 190 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173640-IN | 2019-10-08 | 000000020023867 | 100 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173640-IN | 2019-10-08 | 000000020023867 | 60 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173640-IN | 2019-10-08 | 000000020023867 | 30 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173640-IN | 2019-10-08 | 000000020023867 | 232.8 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173640-IN | 2019-10-08 | 000000020023867 | 640.6 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 220303.11 | 0174877-IN | 2019-10-10 | 000000020025135 | 220303.11 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9301101 | 5.071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 847.5 | 0174877-IN | 2019-10-10 | 000000020025135 | 847.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.01951% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1695 | 0174877-IN | 2019-10-10 | 000000020025135 | 1695 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.03901% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2825 | 0174877-IN | 2019-10-10 | 000000020025135 | 2825 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.06502% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5367.5 | 0174877-IN | 2019-10-10 | 000000020025135 | 5367.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.1235% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6576.6 | 0174877-IN | 2019-10-10 | 000000020025135 | 6576.6 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.1514% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 18096.95 | 0174877-IN | 2019-10-10 | 000000020025135 | 18096.95 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.4165% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20
Sparks MS-21st Century-Technology | 2 | Technology | Sparks MS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-04 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 18287.65 | 0174911-IN | 2019-10-04 | 000000020022961 | 18287.65 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 2.305% | Ergotron Zip40 Charging carts to store laptops at Sparks MS. Total carts: 14
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 8306.25 | 80804 | 2020-01-09 | 000000020055612 | 8306.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5777% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3231.25 | 80796 | 2020-01-14 | 000000020057268 | 3231.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.2247% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 7703.75 | 81699 | 2020-01-14 | 000000020057268 | 7703.75 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5358% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 7457.5 | 83068 | 2020-04-01 | 000000020085959 | 7457.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5186% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8765 | 82273 | 2020-04-01 | 000000020085960 | 8765 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.6096% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 7320 | 84567 | 2020-04-15 | 000000020089466 | 7320 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5091% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9337.5 | 85320 | 2020-05-28 | 000000020100719 | 9337.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.6494% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 6822.5 | 86240 | 2020-06-17 | 000000020106117 | 6822.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.4745% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 3765 | 86864 | 2020-07-27 | 000000020116270 | 3765 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.2618% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 8001.67 | 88480 | 2020-08-17 | 000000020119773 | 8001.67 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5565% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 7558.04 | 89359 | 2020-10-13 | 000000020134067 | 7558.04 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5256% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 7160.88 | 90460 | 2020-10-20 | 000000020136025 | 7160.88 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.498% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 7978.94 | 91321 | 2020-12-18 | 000000020151933 | 7978.94 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5549% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 6898.14 | 91964 | 2020-12-18 | 000000020151933 | 6898.14 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.4797% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 7376.64 | 92821 | 2021-02-08 | 000000020162981 | 7376.64 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.513% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 5426.24 | 94011 | 2021-04-05 | 000000020177572 | 5426.24 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.3774% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 4595.05 | 94918 | 2021-04-16 | 000000020181024 | 4595.05 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.3196% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 4907.32 | 95700 | 2021-05-25 | 000000020192064 | 4907.32 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.3413% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 2845.76 | 96936 | 2021-05-25 | 000000020192064 | 2845.76 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.1979% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 5760 | 97857R1 | 2021-06-22 | 000000020200048 | 5760 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.4006% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-08 | 2021/22 |  | PO1-200000000640 | 0 | 1600 | 100426 | 2021-09-08 | 000000020253624 | 1600 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.1113% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000640 | 0 | 8160 | 98430 | 2021-09-09 | 000000020255187 | 8160 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5675% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4694 | PO1-200000000640 | 4473.57 | 4473.57 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00
Sparks MS-21st Century-DSA Fees | 2 | DSA Fees | Sparks MS | 21st Century | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 2020/21 | 21-3754 | PO2W-210000001571 | 0 | 22264.25 | Per email | 2021-01-20 | 000000020157909 | 22264.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9301101 | 38.72% | DSA plan check review fee for Sparks MS 21st Century.
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 2018/19 |  | PO2W-200000001211, 19-101981 | 0 | 1757.34 | 966482 | 2018-10-19 | 24871020 | 1757.34 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.629% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-02-27 | 2018/19 |  | PO2W-200000001211, 19-101981 | 0 | 11610.5 | 967629 | 2019-02-27 | 25120799 | 11610.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 10.76% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. Allowances for site survey (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $22,616.00.
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-02-27 | 2019/20 |  | PO2W-200000001211, 19-101981 | 0 | 21966.75 | 970833 | 2020-02-13 | 000000020070049 | 21966.75 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 20.36% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-06-18 | 2019/20 |  | PO2W-200000001211, 19-101981 | 0 | 14498.06 | 971446 | 2020-06-18 | 000000020106504 | 14498.06 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 13.44% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-12-08 | 2020/21 |  | PO2W-200000001211, 19-101981 | 0 | 8389.5 | 971455R | 2020-12-08 | 000000020148212 | 8389.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 7.778% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. Allowances for civil engineering for all path of travel (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $22,616.00.
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001211, 19-101981 | 0 | 7249.02 | 971722R | 2021-05-07 | 000000020187161 | 7249.02 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 6.72% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001211, 19-101981 | 0 | 7249.03 | 972097R | 2021-05-07 | 000000020187161 | 7249.03 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 6.72% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-06-23 | 2020/21 |  | PO2W-200000001211, 19-101981 | 0 | 2196.68 | 975781 | 2021-06-23 | 000000020200446 | 2196.68 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 2.036% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-12-20 | 2021/22 |  | PO2W-200000001211, 19-101981 | 0 | 659 | 976676 | 2021-12-20 | 000000020370745 | 659 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0.6109% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-02-13 | 2018/19 |  | PO2W-200000001211, 19-101981 | 0 | 53.76 |  |  |  | 53.76 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-02-13 | 2019/20 |  | PO2W-200000001211, 19-101981 | 0 | -53.76 |  |  |  | -53.76 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. Reverse accrual from prior year
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-01-16 | 2021/22 | 2-522 | PO2W-200000001211, 19-101981 | 32291.12 | 32291.12 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2020-08-07 | 2020-12-08 | 2020/21 |  | PO2W-210000000403 | 0 | 64990 | 972635 | 2020-12-08 | 000000020148210 | 64990 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 96.13% | Architect - Modifications to Architect services for Sparks MS 21st Century, per District's request. To pay for: Mod 3 -Restrooms, Mod 4 - Contract deviations, & Mod 5 - New Standards. Addendum to PO2W-20*1211.
Sparks MS-21st Century-Design | 2 | Design | Sparks MS | 21st Century | Harley Ellis Devereaux (HED) | Architect | 2020-08-07 | 2020-12-08 | 2020/21 | 21-1216 | PO2W-210000000403 | 0 | 2616 | 971455R. | 2020-12-08 | 000000020148212 | 2616 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 3.869% | Architect - Modifications to Architect services for Sparks MS 21st Century, per District's request (Part of mod 1 - Site survey & mod 2 - civil engineering). Total charged for mod 1 & 2 is $22,616.00. Addendum to PO2W-20*1211.
Sparks MS-21st Century-Environ Consultant | 2 | Environ Consultant | Sparks MS | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2019/20 | 2-10470 | PO2W-200000005393 | 0 | 2950 | MCSI-4546 | 2020-06-19 | 000000020106917 | 2950 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9301101 | 100% | Asbestos & lead-based paint survey of Spark MS permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Sparks MS-Fire alarm-DSA Fees | 2 | DSA Fees | Sparks MS | Fire alarm | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-01-20 | 2020/21 | 21-3659 | PO2W-210000001557 | 0 | 860 | 12304 | 2021-01-20 | 000000020157906 | 860 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9301103 | 40% | DGS plan/field review fee for Sparks MS fire alarm
Sparks MS-Fire alarm-Design | 2 | Design | Sparks MS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2020/21 |  | PO2W-210000000680 | 0 | 2475 | 28044 | 2020-10-14 | 000000020134523 | 2475 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301103 | 1.444% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks MS. Facilities paid PO1-20*901 & 19-104054 in the amount of $44,550.00. The total architect contract for Spark MS FA is $49,500.00
Sparks MS-Fire alarm-Design | 2 | Design | Sparks MS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 1485 | 28166 | 2021-02-05 | 000000020162584 | 1485 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301103 | 0.8666% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks MS. Facilities paid PO1-20*901 & 19-104054 in the amount of $44,550.00. The total architect contract for Spark MS FA is $49,500.00
Sparks MS-Fire alarm-Design | 2 | Design | Sparks MS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 | 21-1992 | PO2W-210000000680 | 0 | 990 | 28462 | 2021-03-24 | 000000020174735 | 990 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301103 | 0.5778% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks MS. Facilities paid PO1-20*901 & 19-104054 in the amount of $44,550.00. The total architect contract for Spark MS FA is $49,500.00
Sparks MS-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Sparks MS | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2020-02-20 | 2019/20 |  | PO2W-200000002812 | 0 | 1720 | 202002-02:SFA | 2020-02-20 | 000000020071954 | 1720 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301103 | 25.02% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to 1 campus wide fire alarm system
Sparks MS-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Sparks MS | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2020-04-17 | 2019/20 |  | PO2W-200000002812 | 0 | 3440 | 202003-02:SFA | 2020-04-17 | 000000020090431 | 3440 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301103 | 50.04% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to 1 campus wide fire alarm system
Sparks MS-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Sparks MS | Fire Alarm | Team Inspections | General inspection | 2019-11-26 | 2020-06-19 | 2019/20 | 2-5884 | PO2W-200000002812 | 0 | 1715 | 202006-03:SFA | 2020-06-19 | 000000020106934 | 1715 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301103 | 24.95% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to 1 campus wide fire alarm system
Sparks MS-Fire Alarm-Contractor | 2 | Contractor | Sparks MS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 35460.79 | Pay app #1 | 2020-03-10 | 000000020079637 | 35460.79 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 2.771% | Fire alarm and low voltage service for Sparks MS
Sparks MS-Fire Alarm-Contractor | 2 | Contractor | Sparks MS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-04-08 | 2019/20 |  | PO1-200000000662 | 0 | 48832.8 | Pay app #2 | 2020-04-08 | 000000020087746 | 48832.8 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 3.816% | Fire alarm and low voltage service for Sparks MS
Sparks MS-Fire Alarm-Contractor | 2 | Contractor | Sparks MS | Fire Alarm | Telenet VoIP, Inc | Contractor | 2019-09-26 | 2020-04-24 | 2019/20 |  | PO1-200000000662 | 0 | 47231.15 | Pay app #3 | 2020-04-24 | 000000020092209 | 47231.15 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 3.691% | Fire alarm and low voltage service for Sparks MS
Sparks MS-Fire Alarm-Contractor | 2 | Contractor | Sparks MS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 3640.69 | Pay app #4 | 2020-05-29 | 000000020101116 | 3640.69 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 0.2845% | Fire alarm and low voltage service for Sparks MS
Sparks MS-Fire Alarm-Contractor | 2 | Contractor | Sparks MS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 9234.57 | Pay app #5 | 2020-07-30 | 000000020117024 | 9234.57 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 0.7216% | Fire alarm and low voltage service for Sparks MS
Sparks MS-Fire Alarm-Contractor | 2 | Contractor | Sparks MS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4511 | PO1-200000000662 | 7600 | 7600 |  |  |  | 0 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 0% | Fire alarm and low voltage service for Sparks MS
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2328.86 | 0173715-IN | 2019-10-10 | 000000020025135 | 2328.86 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 8021101 | 0.0536% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 192.18 | 0173715-IN | 2019-10-10 | 000000020025135 | 192.18 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.004423% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 69.84 | 0173715-IN | 2019-10-10 | 000000020025135 | 69.84 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.001607% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 57 | 0173715-IN | 2019-10-10 | 000000020025135 | 57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.001312% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173715-IN | 2019-10-10 | 000000020025135 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 18 | 0173715-IN | 2019-10-10 | 000000020025135 | 18 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.0004143% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9 | 0173715-IN | 2019-10-10 | 000000020025135 | 9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.0002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 15525.78 | 0175429-IN | 2019-10-22 | 000000020029495 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 8021101 | 0.5534% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 120 | 0175429-IN | 2019-10-22 | 000000020029495 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.004277% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 200 | 0175429-IN | 2019-10-22 | 000000020029495 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.007129% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 380 | 0175429-IN | 2019-10-22 | 000000020029495 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.01354% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 465.6 | 0175429-IN | 2019-10-22 | 000000020029495 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.0166% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1281.2 | 0175429-IN | 2019-10-22 | 000000020029495 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.04567% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40
Stimson-21st Century-Technology | 4 | Technology | Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 60 | 0175429-IN | 2019-10-22 | 000000020029495 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.002139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40
Stimson-21st Century-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 480 | 100653 | 2021-09-08 | 000000020253624 | 480 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 0.02624% | Construction management services for Stimson - phase 3 & 4. This PO includes allowances of $40,000.00
Stimson-21st Century-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 4800 | 101514 | 2021-09-29 | 000000020275054 | 4800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 0.2624% | Construction management services for Stimson - phase 3 & 4. This PO includes allowances of $40,000.00
Stimson-21st Century-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2024-07-01 | 2021/22 | 22-1057 | PO1-220000000334 | 64678 | 64678 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 0% | Construction management services for Stimson - phase 3 & 4. This PO includes allowances of $40,000.00
Stimson-21st Century-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862 | 0 | 5170 | 102578 | 2021-11-08 | 000000020325325 | 5170 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 10.54% | Construction management services for Baldwin - phase 3 & 4. This PO is to pay invoice #102578 (Prof service from 09/01-09/30/21), dated 09/30/21
Stimson-Fire Alarm-DSA Fees | 4 | DSA Fees | Stimson | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6937 | PO1-200000000851 | 0 | 375 | Per email | 2020-02-13 | 000000020070044 | 375 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 8021103 | 100% | DSA plan check review fee for Stimson fire alarm.
Stimson-Fire alarm-Design | 4 | Design | Stimson | Fire alarm | tBP Architecture | Architect | 2020-01-14 | 2020-05-26 | 2019/20 |  | PO1-200000000846 | 0 | 9875 | 27770 | 2020-05-26 | 000000020099863 | 9875 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 9.814% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson
Stimson-Fire alarm-Design | 4 | Design | Stimson | Fire alarm | tBP Architecture | Architect | 2020-01-14 | 2020-06-19 | 2019/20 |  | PO1-200000000846 | 0 | 9875 | 27839 | 2020-06-19 | 000000020106941 | 9875 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 9.814% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson
Stimson-Fire alarm-Design | 4 | Design | Stimson | Fire alarm | tBP Architecture | Architect | 2020-01-14 | 2020-10-14 | 2020/21 |  | PO1-200000000846 | 0 | 7900 | 27976 | 2020-10-14 | 000000020134523 | 7900 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 7.851% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson
Stimson-Fire alarm-Design | 4 | Design | Stimson | Fire alarm | tBP Architecture | Architect | 2020-01-14 | 2021-05-26 | 2020/21 |  | PO1-200000000846 | 0 | 1975 | 28601 | 2021-05-26 | 000000020192536 | 1975 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 1.963% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson
Stimson-Fire alarm-Design | 4 | Design | Stimson | Fire alarm | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 2021/22 | 2-6868 | PO1-200000000846 | 9875 | 9875 |  |  |  | 0 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5068.92 | 0173628-IN | 2019-10-10 | 000000020025135 | 5068.92 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9311101 | 0.1167% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 151.32 | 0173628-IN | 2019-10-10 | 000000020025135 | 151.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.003483% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 123.5 | 0173628-IN | 2019-10-10 | 000000020025135 | 123.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.002843% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 65 | 0173628-IN | 2019-10-10 | 000000020025135 | 65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.001496% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 39 | 0173628-IN | 2019-10-10 | 000000020025135 | 39 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.0008976% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 19.5 | 0173628-IN | 2019-10-10 | 000000020025135 | 19.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.0004488% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 416.39 | 0173628-IN | 2019-10-10 | 000000020025135 | 416.39 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.009584% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173780-IN | 2019-11-12 | 000000020036764 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9311101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173780-IN | 2019-11-12 | 000000020036764 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173780-IN | 2019-11-12 | 000000020036764 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173780-IN | 2019-11-12 | 000000020036764 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173780-IN | 2019-11-12 | 000000020036764 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173780-IN | 2019-11-12 | 000000020036764 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173780-IN | 2019-11-12 | 000000020036764 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-12-06 | 2019/20 | 2-5090 | PO2W-200000002766 | 0 | 1306.26 | 0175960-IN | 2019-12-06 | 000000020045865 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9311101 | 100% | Ergotron Zip40 Charging carts to store laptops at Sunset. Total cart: 1
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 70185.04 | 0175621-IN | 2019-10-22 | 000000020029495 | 70185.04 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9311101 | 2.502% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 270 | 0175621-IN | 2019-10-22 | 000000020029495 | 270 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.009624% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 540 | 0175621-IN | 2019-10-22 | 000000020029495 | 540 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.01925% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 900 | 0175621-IN | 2019-10-22 | 000000020029495 | 900 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.03208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1710 | 0175621-IN | 2019-10-22 | 000000020029495 | 1710 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.06095% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2095.2 | 0175621-IN | 2019-10-22 | 000000020029495 | 2095.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.07468% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5765.4 | 0175621-IN | 2019-10-22 | 000000020029495 | 5765.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.2055% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180
Sunset-21st Century-Technology | 4 | Technology | Sunset | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 10450.09 | 0175658-IN | 2019-10-22 | 000000020029495 | 10450.09 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9311101 | 1.317% | Ergotron Zip40 Charging carts to store laptops at Sunset. Total carts: 8
Sunset-21st Century-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 800 | 100653 | 2021-09-08 | 000000020253624 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 0.04374% | Construction management services for Sunset - phase 3 & 4. This PO includes allowances of $40,000.00
Sunset-21st Century-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 1600 | 101514 | 2021-09-29 | 000000020275054 | 1600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 0.08747% | Construction management services for Sunset - phase 3 & 4. This PO includes allowances of $40,000.00
Sunset-21st Century-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2024-07-01 | 2021/22 | 22-1057 | PO1-220000000334 | 198697 | 198697 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 0% | Construction management services for Sunset - phase 3 & 4. This PO includes allowances of $40,000.00
Sunset-21st Century-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862 | 0 | 5505 | 102578 | 2021-11-08 | 000000020325325 | 5505 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 11.23% | Construction management services for Baldwin - phase 3 & 4. This PO is to pay invoice #102578 (Prof service from 09/01-09/30/21), dated 09/30/21
Sunset-21st Century-Contractor | 4 | Contractor | Sunset | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2023-01-06 | 2020/21 | 21-3656 | PO2W-210000001556 | 0 | 22500 | 2021-006D | 2021-03-24 | 000000020174720 | 22500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311101 | 23.08% | Demo of ceiling tiles in 9 classrooms at Sunset
Sunset-21st Century-Contractor | 4 | Contractor | Sunset | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-07-16 | 2021-09-09 | 2021/22 | 22-321 | PO2W-220000000024 | 0 | 19000 | 2021-097D | 2021-09-09 | 000000020255195 | 19000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311101 | 100% | Demo of ceiling tiles in 7 classrooms at Sunset
Sunset-21st Century-FF & E | 4 | FF & E | Sunset | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9311101 | 3.16% | Furniture for Sunset - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Sunset-21st Century-FF & E | 4 | FF & E | Sunset | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9311101 | 1.655% | Furniture for Sunset - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Sunset-21st Century-Environ Consultant | 4 | Environ Consultant | Sunset | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10247 | PO2W-200000005325 | 0 | 2700 | MCSI-4543 | 2020-08-17 | 000000020119790 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9311101 | 100% | Asbestos & lead-based paint survey of Sunset's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Sunset-21st Century-Design | 4 | Design | Sunset | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002226 | 0 | 23712 | T8705 | 2021-09-09 | 000000020255214 | 23712 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311101 | 12.71% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Sunset. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Sunset-21st Century-Design | 4 | Design | Sunset | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002226 | 0 | 5833.89 | 3299 | 2021-10-19 | 000000020302604 | 5833.89 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311101 | 3.127% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Sunset. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Sunset-21st Century-Design | 4 | Design | Sunset | 21st Century | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6241 | PO2W-210000002226 | 157014.11 | 157014.11 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Sunset. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00.
Sunset-Ceiling replacement-Contractor | 4 | Contractor | Sunset | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 23073.6 | Pay app #1 | 2019-12-17 | 000000020049998 | 23073.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311105 | 0.5045% | Ceiling replacement for Sunset.
Sunset-Ceiling replacement-Contractor | 4 | Contractor | Sunset | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 69220.8 | Pay app #2 | 2020-10-21 | 000000020136454 | 69220.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311105 | 1.514% | Ceiling replacement for Sunset.
Sunset-Ceiling replacement-Contractor | 4 | Contractor | Sunset | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 138441.6 | Pay app #5 | 2021-06-17 | 000000020198995 | 138441.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311105 | 3.027% | Ceiling replacement for Sunset.
Sunset-Ceiling replacement-Contractor | 4 | Contractor | Sunset | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5069 | PO1-200000000729 | 12144 | 12144 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311105 | 0% | Ceiling replacement for Sunset.
Sunset-Drinking fountain replacement-Contractor | 4 | Contractor | Sunset | Drinking fountain replacement | Optima | Contractor | 2019-12-18 | 2021-04-23 | 2020/21 | 2-6493 | PO1-200000000833 | 0 | 18000 | Pay app #1 | 2021-04-23 | 000000020182911 | 18000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9311104 | 100% | Provide & install dual wall mount drinking fountain (hi & lo) at Sunset.
Sunset-Drinking fountain replacement-Contractor | 4 | Contractor | Sunset | Drinking fountain replacement | Wolverine Fence | Contractor | 2020-08-11 | 2022-08-11 | 2020/21 | 21-1261 | PO2W-210000000383 | 0 | 4800 | 3988 | 2020-10-21 | 000000020136462 | 4800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9311104 | 100% | Install 3 sets of handrails at 3 drinking fountains, including core drilling at Sunset.
Sunset-Fire alarm-DSA Fees | 4 | DSA Fees | Sunset | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 564 | Per email | 2021-03-30 | 000000020176208 | 564 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9311103 | 7.949% | DSA plan check review fee for Sunset fire alarm.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28233 | 2021-02-05 | 000000020162584 | 2425 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28294 | 2021-02-09 | 000000020163360 | 9700 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4850 | 28391 | 2021-03-24 | 000000020174735 | 4850 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 1.244% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28475 | 2021-03-24 | 000000020174735 | 2425 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 4850 | 28524 | 2021-05-26 | 000000020192536 | 4850 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 1.244% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28618 | 2021-05-26 | 000000020192536 | 9700 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28691 | 2021-06-23 | 000000020200466 | 1455 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0.3731% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28839 | 2021-09-09 | 000000020255227 | 970 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0.2487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Fire alarm-Design | 4 | Design | Sunset | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2025-10-20 | 2021/22 | 21-2535 | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset.
Sunset-Interim Housing-Design | 4 | Design | Sunset | Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 2021/22 | 21-6246 | PO2W-210000002231 | 97400 | 97400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311102 | 0% | Architect - Prepare design documents for Sunset Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6238.67 | 0173635-IN | 2019-10-08 | 000000020023867 | 6238.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 0.1436% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 186.24 | 0173635-IN | 2019-10-08 | 000000020023867 | 186.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.004287% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 152 | 0173635-IN | 2019-10-08 | 000000020023867 | 152 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.003499% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 80 | 0173635-IN | 2019-10-08 | 000000020023867 | 80 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.001841% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 48 | 0173635-IN | 2019-10-08 | 000000020023867 | 48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.001105% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 24 | 0173635-IN | 2019-10-08 | 000000020023867 | 24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.0005524% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 512.48 | 0173635-IN | 2019-10-08 | 000000020023867 | 512.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.0118% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173776-IN | 2019-10-21 | 000000020028933 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173776-IN | 2019-10-21 | 000000020028933 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173776-IN | 2019-10-21 | 000000020028933 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173776-IN | 2019-10-21 | 000000020028933 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173776-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173776-IN | 2019-10-21 | 000000020028933 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173776-IN | 2019-10-21 | 000000020028933 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 58487.55 | 0175196-IN | 2019-10-22 | 000000020029495 | 58487.55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 2.085% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7798.34 | 0175594-IN | 2019-10-22 | 000000020029495 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 0.278% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 225 | 0175196-IN | 2019-10-22 | 000000020029495 | 225 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.00802% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 450 | 0175196-IN | 2019-10-22 | 000000020029495 | 450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.01604% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 750 | 0175196-IN | 2019-10-22 | 000000020029495 | 750 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.02673% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1425 | 0175196-IN | 2019-10-22 | 000000020029495 | 1425 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.05079% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1746 | 0175196-IN | 2019-10-22 | 000000020029495 | 1746 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.06223% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 4804.5 | 0175196-IN | 2019-10-22 | 000000020029495 | 4804.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.1712% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 100 | 0175594-IN | 2019-10-22 | 000000020029495 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.003564% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 190 | 0175594-IN | 2019-10-22 | 000000020029495 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.006772% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 232.8 | 0175594-IN | 2019-10-22 | 000000020029495 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.008298% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 640.6 | 0175594-IN | 2019-10-22 | 000000020029495 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.02283% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 60 | 0175594-IN | 2019-10-22 | 000000020029495 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.002139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 30 | 0175594-IN | 2019-10-22 | 000000020029495 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.001069% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 16981.39 | 0175274-IN | 2019-10-11 | 000000020025716 | 16981.39 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9331101 | 2.14% | Ergotron Zip40 Charging carts to store laptops at Temple. Total carts: 14
Temple-21st Century-Technology | 8 | Technology | Temple | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175278-IN | 2019-10-11 | 000000020025716 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9331101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Temple. Total carts: 14
Temple-21st Century-FF & E | 8 | FF & E | Temple | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 3.16% | Furniture for Temple - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Temple-21st Century-FF & E | 8 | FF & E | Temple | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9331101 | 1.655% | Furniture for Temple - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Temple-21st Century-Environ Consultant | 8 | Environ Consultant | Temple | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10248 | PO2W-200000005326 | 0 | 2600 | MCSI-4544 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9331101 | 100% | Asbestos & lead-based paint survey of Temple's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Temple-Ceiling replacement-Contractor | 8 | Contractor | Temple | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 24518.64 | Pay app #1 | 2019-12-17 | 000000020049998 | 24518.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9331105 | 0.5361% | Ceiling replacement for Temple.
Temple-Ceiling replacement-Contractor | 8 | Contractor | Temple | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-04-27 | 2020/21 |  | PO1-200000000729 | 0 | 220667.81 | Pay app #3 | 2021-04-27 | 000000020183628 | 220667.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9331105 | 4.825% | Ceiling replacement for Temple.
Temple-Ceiling replacement-Contractor | 8 | Contractor | Temple | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5070 | PO1-200000000729 | 12904.55 | 12904.55 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9331105 | 0% | Ceiling replacement for Temple.
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15596.68 | 0173466-IN | 2019-10-08 | 000000020023867 | 15596.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 12087.43 | 0173675-IN | 2019-10-08 | 000000020023867 | 12087.43 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 0.2782% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 200 | 0173466-IN | 2019-10-08 | 000000020023867 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173466-IN | 2019-10-08 | 000000020023867 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173466-IN | 2019-10-08 | 000000020023867 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 380 | 0173466-IN | 2019-10-08 | 000000020023867 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173466-IN | 2019-10-08 | 000000020023867 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173466-IN | 2019-10-08 | 000000020023867 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 155 | 0173675-IN | 2019-10-08 | 000000020023867 | 155 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.003568% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 93 | 0173675-IN | 2019-10-08 | 000000020023867 | 93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.002141% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 46.5 | 0173675-IN | 2019-10-08 | 000000020023867 | 46.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.00107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 294.5 | 0173675-IN | 2019-10-08 | 000000020023867 | 294.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.006778% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 360.84 | 0173675-IN | 2019-10-08 | 000000020023867 | 360.84 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.008305% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 992.93 | 0173675-IN | 2019-10-08 | 000000020023867 | 992.93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.02285% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173760-IN | 2019-10-21 | 000000020028933 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173760-IN | 2019-10-21 | 000000020028933 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173760-IN | 2019-10-21 | 000000020028933 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173760-IN | 2019-10-21 | 000000020028933 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173760-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173760-IN | 2019-10-21 | 000000020028933 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173760-IN | 2019-10-21 | 000000020028933 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 159865.97 | 0175193-IN | 2019-10-22 | 000000020029495 | 159865.97 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 5.698% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 615 | 0175193-IN | 2019-10-22 | 000000020029495 | 615 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.02192% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1230 | 0175193-IN | 2019-10-22 | 000000020029495 | 1230 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.04384% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 2050 | 0175193-IN | 2019-10-22 | 000000020029495 | 2050 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.07307% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 3895 | 0175193-IN | 2019-10-22 | 000000020029495 | 3895 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.1388% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 4772.4 | 0175193-IN | 2019-10-22 | 000000020029495 | 4772.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.1701% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 13132.3 | 0175193-IN | 2019-10-22 | 000000020029495 | 13132.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.4681% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173478-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Valinda. Total cart: 1
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175126-IN | 2019-10-11 | 000000020025716 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Valinda. Total carts: 26
Valinda-21st Century-Technology | 6 | Technology | Valinda | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 32656.53 | 0175203-IN | 2019-10-11 | 000000020025716 | 32656.53 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 4.115% | Ergotron Zip40 Charging carts to store laptops at Valinda. Total carts: 26
Valinda-21st Century-FF & E | 6 | FF & E | Valinda | 21st Century | Education Products & Services | White board(s) | 2019-09-16 | 2019-10-01 | 2019/20 | 2-3418 | PO3W-200000000563 | 0 | 1464.78 | EPS6062-2019 | 2019-10-01 | 000000020021433 | 1464.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 100% | Da-Lite IDEA Panoramic white board 16 x 10 format with panoramic screen surface for Valinda - room #14.
Valinda-21st Century-FF & E | 6 | FF & E | Valinda | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 3.16% | Furniture for Valinda - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Valinda-21st Century-FF & E | 6 | FF & E | Valinda | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 1.655% | Furniture for Valinda - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Valinda-21st Century-Environ Consultant | 6 | Environ Consultant | Valinda | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1579 | PO1-210000000427 | 0 | 3000 | MCSI-4605 | 2020-10-13 | 000000020134092 | 3000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9341101 | 7.282% | Asbestos & lead-based paint survey of Valinda's permanent buildings.
Valinda-Fire Alarm-DSA Fees | 6 | DSA Fees | Valinda | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6938 | PO1-200000000852 | 0 | 1125 | Per email | 2020-02-13 | 000000020070036 | 1125 | 03-120622 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9341103 | 100% | DSA plan check review fee for Valinda fire alarm
Valinda-Fire Alarm-Design | 6 | Design | Valinda | Fire Alarm | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 2021/22 | 2-6869 | PO1-200000000846 | 12375 | 12375 |  |  |  | 0 | 03-120622 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9341103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valinda. Facilities paid PO2W-20*4421 in the amount of $37,125.00. The total architect contract for Valinda FA is $49,500.00
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6210.31 | 0173686-IN | 2019-10-10 | 000000020025135 | 6210.31 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9441101 | 0.1429% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 186.24 | 0173686-IN | 2019-10-10 | 000000020025135 | 186.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.004287% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 152 | 0173686-IN | 2019-10-10 | 000000020025135 | 152 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.003499% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 80 | 0173686-IN | 2019-10-10 | 000000020025135 | 80 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.001841% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 48 | 0173686-IN | 2019-10-10 | 000000020025135 | 48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.001105% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 24 | 0173686-IN | 2019-10-10 | 000000020025135 | 24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.0005524% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 512.48 | 0173686-IN | 2019-10-10 | 000000020025135 | 512.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.0118% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 62103.14 | 0175627-IN | 2019-10-22 | 000000020029495 | 62103.14 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9441101 | 2.214% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 240 | 0175627-IN | 2019-10-22 | 000000020029495 | 240 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.008554% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 480 | 0175627-IN | 2019-10-22 | 000000020029495 | 480 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.01711% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 800 | 0175627-IN | 2019-10-22 | 000000020029495 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.02851% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1520 | 0175627-IN | 2019-10-22 | 000000020029495 | 1520 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.05418% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1862.4 | 0175627-IN | 2019-10-22 | 000000020029495 | 1862.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.06638% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5124.8 | 0175627-IN | 2019-10-22 | 000000020029495 | 5124.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.1827% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609
Valley-21st Century-Technology | 8 | Technology | Valley | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 7801.94 | 0175663-IN | 2019-10-21 | 000000020028933 | 7801.94 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9441101 | 0.9832% | Ergotron Zip40 Charging carts to store laptops at Valley. Total carts: 6
Valley-21st Century-Contractor | 8 | Contractor | Valley | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-09-09 | 2021/22 |  | PO2W-200000004391 | 0 | 19116.72 | Pay app #7 | 2021-09-09 | 000000020255193 | 19116.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9441101 | 4.246% | Prep & install Mohawk LVT, walk off mat & base at Valley for room #5, 6, & 7
Valley-21st Century-Environ Consultant | 8 | Environ Consultant | Valley | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1584 | PO1-210000000427 | 0 | 2700 | MCSI-4621 | 2020-10-13 | 000000020134092 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9441101 | 6.553% | Asbestos & lead-based paint survey of Valley's permanent buildings.
Valley-Fire alarm-DSA Fees | 8 | DSA Fees | Valley | Fire alarm | Department of General Services (DGS) | DSA fees | 2021-07-13 | 2021-08-02 | 2021/22 | 22-527 | PO2W-220000000054 | 0 | 698.75 | 12664 | 2021-08-09 | 37503 | 698.75 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9441103 | 100% | DGS plan/field review fee for Valley fire alarm. We issued ck #20221968 dated 08/02/21 for this project; unfortunately, this check was inadvertently cashed by tBP. tBP issued this check #37503 to replaced our check that they cashed. On 01/31/22, the trial balance showed ck #20221968 was stale dated. We investigated and found that tBP reversed their deposit of our ck #20221968. On 02/22/22, we reimbursed tBP with ck #20424483.
Valley-Fire Alarm-DSA Fees | 8 | DSA Fees | Valley | Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3173 | PO2W-200000001055 | 0 | 630 | Per email | 2019-09-13 | 000000020015012 | 630 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9441103 | 100% | DSA plan check review fee for Valley fire alarm.
Valley-Fire alarm-Design | 8 | Design | Valley | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28044 | 2020-10-14 | 000000020134523 | 2275 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 1.328% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The total architect contract for Valley FA is $45,500.00
Valley-Fire alarm-Design | 8 | Design | Valley | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28118 | 2021-01-07 | 000000020154828 | 2275 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 1.328% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The total architect contract for Valley FA is $45,500.00
Valley-Fire alarm-Design | 8 | Design | Valley | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28162 | 2021-02-05 | 000000020162584 | 2275 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 1.328% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The total architect contract for Valley FA is $45,500.00
Valley-Fire alarm-Design | 8 | Design | Valley | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-09 | 2020/21 |  | PO2W-210000000680 | 0 | 3640 | 28274 | 2021-02-09 | 000000020163360 | 3640 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 2.124% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The total architect contract for Valley FA is $45,500.00
Valley-Fire alarm-Design | 8 | Design | Valley | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-10-28 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 910 | 28874 | 2021-10-28 | 000000020313182 | 910 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 0.5311% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The total architect contract for Valley FA is $45,500.00
Valley-Fire Alarm-DSA Inspection | 8 | DSA Inspection | Valley | Fire Alarm | Team Inspections | General inspection | 2020-08-19 | 2020-10-14 | 2020/21 |  | PO2W-210000000455 | 0 | 3675 | 202009-11:VAFA | 2020-10-14 | 000000020134520 | 3675 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9441103 | 50% | General inspection for the project as defined in Title 24 at Valley. Alterations to fire alarm system - buildings A, B, D, 2, 3, 4, & 5
Valley-Fire Alarm-DSA Inspection | 8 | DSA Inspection | Valley | Fire Alarm | Team Inspections | General inspection | 2020-08-19 | 2021-02-09 | 2020/21 | 21-1419 | PO2W-210000000455 | 0 | 3675 | 202012-12:VAFA | 2021-02-09 | 000000020163358 | 3675 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9441103 | 50% | General inspection for the project as defined in Title 24 at Valley. Alterations to fire alarm system - buildings A, B, D, 2, 3, 4, & 5
Valley-Fire Alarm-Contractor | 8 | Contractor | Valley | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2020-10-13 | 2020/21 |  | PO2W-200000004931 | 0 | 184497.98 | Pay app #1 | 2020-10-13 | 000000020134117 | 184497.98 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9441103 | 84.96% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at Valley. Change order amount is $14,841.51 (PO2W-21*2213). The total project cost with change order is $231,990.91
Valley-Fire Alarm-Contractor | 8 | Contractor | Valley | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2020-11-04 | 2020/21 |  | PO2W-200000004931 | 0 | 14431.45 | Pay app #2 | 2020-11-04 | 000000020139892 | 14431.45 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9441103 | 6.646% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at Valley. Change order amount is $14,841.51 (PO2W-21*2213). The total project cost with change order is $231,990.91
Valley-Fire Alarm-Contractor | 8 | Contractor | Valley | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2020-12-18 | 2020/21 |  | PO2W-200000004931 | 0 | 12210.58 | Pay app #3 | 2020-12-18 | 000000020151942 | 12210.58 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9441103 | 5.623% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at Valley. Change order amount is $14,841.51 (PO2W-21*2213). The total project cost with change order is $231,990.91
Valley-Fire Alarm-Contractor | 8 | Contractor | Valley | Fire Alarm | Telenet VOIP, Inc | Contractor | 2020-04-13 | 2021-05-07 | 2020/21 | 2-9611 | PO2W-200000004931 | -1.5461e-11 | 6009.39 | Pay app #4 | 2021-05-07 | 000000020187165 | 6009.39 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9441103 | 2.767% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at Valley. Change order amount is $14,841.51 (PO2W-21*2213). The total project cost with change order is $231,990.91
Valley-Fire alarm-Contractor | 8 | Contractor | Valley | Fire alarm | Telenet VOIP, Inc | Contractor | 2021-05-03 | 2021-05-07 | 2020/21 |  | PO2W-210000002213 | 0 | 819.47 | Pay app #4 | 2021-05-07 | 000000020187165 | 819.47 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9441103 | 5.521% | Change order to add and replace new heat detectors, install 1 new wall mounted speaker and new smoke detector at Valley. Addendum to PO2W-20*4931. The total project cost with change order is $231,990.91
Valley-Fire alarm-Contractor | 8 | Contractor | Valley | Fire alarm | Telenet VOIP, Inc | Contractor | 2021-05-03 | 2021-05-12 | 2020/21 |  | PO2W-210000002213 | 0 | 1947.5 | Pay app #5 | 2021-05-12 | 000000020188449 | 1947.5 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9441103 | 13.12% | Change order to add and replace new heat detectors, install 1 new wall mounted speaker and new smoke detector at Valley. Addendum to PO2W-20*4931. The total project cost with change order is $231,990.91
Valley-Fire alarm-Contractor | 8 | Contractor | Valley | Fire alarm | Telenet VOIP, Inc | Contractor | 2021-05-03 | 2023-07-11 | 2021/22 | 21-6251 | PO2W-210000002213 | 12074.54 | 12074.54 |  |  |  | 0 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9441103 | 0% | Change order to add and replace new heat detectors, install 1 new wall mounted speaker and new smoke detector at Valley. Addendum to PO2W-20*4931. The total project cost with change order is $231,990.91
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9703.62 | 0173714-IN | 2019-10-10 | 000000020025135 | 9703.62 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9351101 | 0.2233% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 125 | 0173714-IN | 2019-10-10 | 000000020025135 | 125 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.002877% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 75 | 0173714-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 37.5 | 0173714-IN | 2019-10-10 | 000000020025135 | 37.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.0008631% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 237.5 | 0173714-IN | 2019-10-10 | 000000020025135 | 237.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.005466% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 291 | 0173714-IN | 2019-10-10 | 000000020025135 | 291 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.006698% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 800.75 | 0173714-IN | 2019-10-10 | 000000020025135 | 800.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.01843% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 89273.27 | 0174906-IN | 2019-10-10 | 000000020025136 | 89273.27 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9351101 | 2.055% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 345 | 0174906-IN | 2019-10-10 | 000000020025136 | 345 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.007941% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 690 | 0174906-IN | 2019-10-10 | 000000020025136 | 690 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.01588% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1150 | 0174906-IN | 2019-10-10 | 000000020025136 | 1150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.02647% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2185 | 0174906-IN | 2019-10-10 | 000000020025136 | 2185 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.05029% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2677.2 | 0174906-IN | 2019-10-10 | 000000020025136 | 2677.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.06162% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7366.9 | 0174906-IN | 2019-10-10 | 000000020025136 | 7366.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.1696% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255
Wedgeworth-21st Century-Technology | 0 | Technology | Wedgeworth | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 31207.76 | 0175048-IN | 2019-10-08 | 000000020023867 | 31207.76 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9351101 | 3.933% | Ergotron Zip40 Charging carts to store laptops at Wedgeworth. Total carts: 24
Wedgeworth-21st Century-Contractor | 0 | Contractor | Wedgeworth | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-04-06 | 2020/21 |  | PO2W-200000004391 | 0 | 12744.48 | Pay app #6 | 2021-04-06 | 000000020177862 | 12744.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9351101 | 2.831% | Prep & install Mohawk LVT, walk off mat & base at Wedgeworth for room #5 & 6
Wedgeworth-Drinking fountain replacement-Contractor | 0 | Contractor | Wedgeworth | Drinking fountain replacement | Optima | Contractor | 2019-12-18 | 2021-04-07 | 2020/21 |  | PO1-200000000834 | 0 | 3502.75 | Pay app #1 | 2021-04-07 | 000000020178359 | 3502.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9351104 | 53.89% | Provide & install dual wall mount drinking fountain (hi & lo) at Wedgeworth.
Wedgeworth-Drinking fountain replacement-Contractor | 0 | Contractor | Wedgeworth | Drinking fountain replacement | Optima | Contractor | 2019-12-18 | 2023-12-18 | 2021/22 | 2-6495 | PO1-200000000834 | 2997.25 | 2997.25 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9351104 | 0% | Provide & install dual wall mount drinking fountain (hi & lo) at Wedgeworth.
Wedgeworth-Drinking fountain replacement-DSA Inspection | 0 | DSA Inspection | Wedgeworth | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6607 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9351104 | 0% | General inspection for the project as defined in Title 24 at Wedgeworth. Construction of 1 bottle filler at existing drinking fountain & 2 drinking fountain guardrails
Willow-21st Century-Environ Consultant | 0 | Environ Consultant | Willow | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 2020/21 | 21-1574 | PO1-210000000427 | 0 | 2700 | MCSI-4623 | 2020-10-20 | 000000020136035 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 7461101 | 6.553% | Asbestos & lead-based paint survey of Willow's permanent buildings.
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 22124.25 | 0173713-IN | 2019-10-10 | 000000020025135 | 22124.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9421101 | 0.5092% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 506528.77 | 0174691-IN | 2019-10-10 | 000000020025135 | 506528.77 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9421101 | 11.66% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 171 | 0173713-IN | 2019-10-10 | 000000020025135 | 171 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.003936% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 85.5 | 0173713-IN | 2019-10-10 | 000000020025135 | 85.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.001968% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 285 | 0173713-IN | 2019-10-10 | 000000020025135 | 285 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.00656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 541.5 | 0173713-IN | 2019-10-10 | 000000020025135 | 541.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.01246% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 663.48 | 0173713-IN | 2019-10-10 | 000000020025135 | 663.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.01527% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1825.71 | 0173713-IN | 2019-10-10 | 000000020025135 | 1825.71 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.04202% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1957.5 | 0174691-IN | 2019-10-10 | 000000020025135 | 1957.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.04506% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3915 | 0174691-IN | 2019-10-10 | 000000020025135 | 3915 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.09011% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6525 | 0174691-IN | 2019-10-10 | 000000020025135 | 6525 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.1502% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 12397.5 | 0174691-IN | 2019-10-10 | 000000020025135 | 12397.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.2853% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15190.2 | 0174691-IN | 2019-10-10 | 000000020025135 | 15190.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.3496% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 41799.15 | 0174691-IN | 2019-10-10 | 000000020025135 | 41799.15 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.9621% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 3881.45 | 0173890-IN | 2019-10-21 | 000000020028933 | 3881.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9421101 | 0.08934% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 116.4 | 0173890-IN | 2019-10-21 | 000000020028933 | 116.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.002679% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 95 | 0173890-IN | 2019-10-21 | 000000020028933 | 95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 50 | 0173890-IN | 2019-10-21 | 000000020028933 | 50 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.001151% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173890-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15 | 0173890-IN | 2019-10-21 | 000000020028933 | 15 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.0003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 320.3 | 0173890-IN | 2019-10-21 | 000000020028933 | 320.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.007372% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372
Wilson HS-21st Century-Technology | 5 | Technology | Wilson HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 53313.26 | 0174830-IN | 2019-10-08 | 000000020023867 | 53313.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9421101 | 6.719% | Ergotron Zip40 Charging carts to store laptops at Wilson HS. Total carts: 41
Wilson HS-21st Century-Contractor | 5 | Contractor | Wilson HS | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 12744.48 | Pay app #4 | 2020-12-08 | 000000020148205 | 12744.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9421101 | 2.831% | Prep & install Mohawk LVT, walk off mat & base at Wilson HS for room #B-6A & D-2
Wilson HS-21st Century-Contractor | 5 | Contractor | Wilson HS | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-04-06 | 2020/21 |  | PO2W-200000004391 | 0 | 6372.24 | Pay app #6 | 2021-04-06 | 000000020177862 | 6372.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9421101 | 1.415% | Prep & install Mohawk LVT, walk off mat & base at Wilson HS for room #T1
Wilson HS-21st Century-Environ Consultant | 5 | Environ Consultant | Wilson HS | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 2020/21 | 21-1582 | PO1-210000000427 | 0 | 3400 | MCSI-4627 | 2020-10-20 | 000000020136035 | 3400 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9421101 | 8.252% | Asbestos & lead-based paint survey of Wilson HS permanent buildings.
Wilson HS-Drinking fountain replacement-DSA Inspection | 5 | DSA Inspection | Wilson HS | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 2021/22 | 2-6608 | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421104 | 0% | General inspection for the project as defined in Title 24 at Wilson HS. Replacement of 3-exterior drinking fountains
Wilson HS-Fire alarm-Design | 5 | Design | Wilson HS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28122 | 2021-01-07 | 000000020154828 | 2275 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 1.328% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The total architect contract for Wilson HS FA is $45,500.00
Wilson HS-Fire alarm-Design | 5 | Design | Wilson HS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28164 | 2021-02-05 | 000000020162584 | 2275 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 1.328% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The total architect contract for Wilson HS FA is $45,500.00
Wilson HS-Fire alarm-Design | 5 | Design | Wilson HS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28468 | 2021-03-24 | 000000020174735 | 2275 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 1.328% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The total architect contract for Wilson HS FA is $45,500.00
Wilson HS-Fire alarm-Design | 5 | Design | Wilson HS | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 2021/22 | 21-1992 | PO2W-210000000680 | 4550 | 4550 |  |  |  | 0 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The total architect contract for Wilson HS FA is $45,500.00
Wilson HS-Fire Alarm-DSA Inspection | 5 | DSA Inspection | Wilson HS | Fire Alarm | Team Inspections | General inspection | 2020-05-13 | 2020-06-19 | 2019/20 |  | PO2W-200000005058 | 0 | 4125 | 202006-05:WHSFA | 2020-06-19 | 000000020106934 | 4125 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421103 | 25% | General inspection for the project as defined in Title 24 at Wilson HS. Alterations to 13 fire alarm upgrade buildings A, E, F, K, P, S, B, C (C1, C2, C3), D, G, H, N, T
Wilson HS-Fire Alarm-DSA Inspection | 5 | DSA Inspection | Wilson HS | Fire Alarm | Team Inspections | General inspection | 2020-05-13 | 2020-08-19 | 2020/21 |  | PO2W-200000005058 | 0 | 8250 | 202008-08:WHSFA | 2020-08-19 | 000000020120364 | 8250 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421103 | 50% | General inspection for the project as defined in Title 24 at Wilson HS. Alterations to 13 fire alarm upgrade buildings A, E, F, K, P, S, B, C (C1, C2, C3), D, G, H, N, T
Wilson HS-Fire Alarm-DSA Inspection | 5 | DSA Inspection | Wilson HS | Fire Alarm | Team Inspections | General inspection | 2020-05-13 | 2021-09-13 | 2020/21 |  | PO2W-200000005058 | 0 | 3625 | 20210630-10: WHSFA | 2021-09-13 | 000000020257046 | 3625 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421103 | 21.97% | General inspection for the project as defined in Title 24 at Wilson HS. Alterations to 13 fire alarm upgrade buildings A, E, F, K, P, S, B, C (C1, C2, C3), D, G, H, N, T
Wilson HS-Fire Alarm-DSA Inspection | 5 | DSA Inspection | Wilson HS | Fire Alarm | Team Inspections | General inspection | 2020-05-13 | 2023-07-31 | 2021/22 | 2-10148 | PO2W-200000005058 | 500 | 500 |  |  |  | 0 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421103 | 0% | General inspection for the project as defined in Title 24 at Wilson HS. Alterations to 13 fire alarm upgrade buildings A, E, F, K, P, S, B, C (C1, C2, C3), D, G, H, N, T
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 2997.25 | Pay app #1 | 2020-03-10 | 000000020079637 | 2997.25 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.2342% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 1723.3 | Pay app #4 | 2020-05-29 | 000000020101116 | 1723.3 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.1347% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 82411.36 | Pay app #5 | 2020-07-30 | 000000020117024 | 82411.36 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 6.44% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 79907.49 | Pay app #6 | 2020-07-30 | 000000020117024 | 79907.49 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 6.244% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-08-28 | 2020/21 |  | PO1-200000000662 | 0 | 25191.82 | Pay app #7 | 2020-08-28 | 000000020122656 | 25191.82 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 1.969% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-10-13 | 2020/21 |  | PO1-200000000662 | 0 | 25638.05 | Pay app #8 | 2020-10-13 | 000000020134117 | 25638.05 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 2.003% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-11-04 | 2020/21 |  | PO1-200000000662 | 0 | 12068.33 | Pay app #9 | 2020-11-04 | 000000020139892 | 12068.33 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.943% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 4520.48 | Pay app #13 | 2021-05-21 | 000000020191188 | 4520.48 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.3532% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 565.06 | Pay app #14 | 2021-05-21 | 000000020191188 | 565.06 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.04415% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 25768.03 | Pay app #16 | 2021-11-22 | 000000020341778 | 25768.03 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 2.014% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wilson HS-Fire Alarm-Contractor | 5 | Contractor | Wilson HS | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4505 | PO1-200000000662 | 21269.01 | 21269.01 |  |  |  | 0 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 is created using Facilities' account string (PO2W-22*915)
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6238.67 | 0173676-IN | 2019-10-08 | 000000020023867 | 6238.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9371101 | 0.1436% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173772-IN | 2019-10-08 | 000000020023867 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9371101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 186.24 | 0173676-IN | 2019-10-08 | 000000020023867 | 186.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.004287% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 152 | 0173676-IN | 2019-10-08 | 000000020023867 | 152 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.003499% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 80 | 0173676-IN | 2019-10-08 | 000000020023867 | 80 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.001841% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 48 | 0173676-IN | 2019-10-08 | 000000020023867 | 48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.001105% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 24 | 0173676-IN | 2019-10-08 | 000000020023867 | 24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.0005524% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 512.48 | 0173676-IN | 2019-10-08 | 000000020023867 | 512.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.0118% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173772-IN | 2019-10-08 | 000000020023867 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173772-IN | 2019-10-08 | 000000020023867 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173772-IN | 2019-10-08 | 000000020023867 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173772-IN | 2019-10-08 | 000000020023867 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173772-IN | 2019-10-08 | 000000020023867 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173772-IN | 2019-10-08 | 000000020023867 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 64336.31 | 0175131-IN | 2019-10-10 | 000000020025132 | 64336.31 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9371101 | 2.293% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 247.5 | 0175131-IN | 2019-10-10 | 000000020025132 | 247.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.008822% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 825 | 0175131-IN | 2019-10-10 | 000000020025132 | 825 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.02941% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1567.5 | 0175131-IN | 2019-10-10 | 000000020025132 | 1567.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.05587% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1920.6 | 0175131-IN | 2019-10-10 | 000000020025132 | 1920.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.06846% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5284.95 | 0175131-IN | 2019-10-10 | 000000020025132 | 5284.95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.1884% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 495 | 0175131-IN | 2019-10-10 | 000000020025132 | 495 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.01764% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-04 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175122-IN | 2019-10-04 | 000000020022961 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9371101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Wing Lane. Total carts: 15
Wing Lane-21st Century-Technology | 9 | Technology | Wing Lane | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-04 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 18287.65 | 0175143-IN | 2019-10-04 | 000000020022961 | 18287.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9371101 | 2.305% | Ergotron Zip40 Charging carts to store laptops at Wing Lane. Total carts: 15
Wing Lane-21st Century-Contractor | 9 | Contractor | Wing Lane | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 2020/21 | 21-4688 | PO2W-210000001838 | 0 | 40000 | 2021-022D | 2021-04-23 | 000000020182905 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9371101 | 30.77% | Demo of ceiling tiles in 16 classrooms at Wing Lane
Wing Lane-21st Century-FF & E | 9 | FF & E | Wing Lane | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9371101 | 3.16% | Furniture for Wing Lane - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Wing Lane-21st Century-FF & E | 9 | FF & E | Wing Lane | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9371101 | 1.655% | Furniture for Wing Lane - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Wing Lane-21st Century-Environ Consultant | 9 | Environ Consultant | Wing Lane | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10249 | PO2W-200000005327 | 0 | 2600 | MCSI-4545 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9371101 | 100% | Asbestos & lead-based paint survey of Wing Lane's permanent buildings. Walk through, collect samples, testing of samples, and prepare report.
Wing Lane-Ceiling replacement-Contractor | 9 | Contractor | Wing Lane | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 28760.11 | Pay app #1 | 2019-12-17 | 000000020049998 | 28760.11 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9371105 | 0.6289% | Ceiling replacement for Wing Lane.
Wing Lane-Ceiling replacement-Contractor | 9 | Contractor | Wing Lane | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-04-27 | 2020/21 |  | PO1-200000000729 | 0 | 258840.99 | Pay app #3 | 2021-04-27 | 000000020183628 | 258840.99 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9371105 | 5.66% | Ceiling replacement for Wing Lane.
Wing Lane-Ceiling replacement-Contractor | 9 | Contractor | Wing Lane | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5071 | PO1-200000000729 | 15136.9 | 15136.9 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9371105 | 0% | Ceiling replacement for Wing Lane.
Wing Lane-Drinking fountain replacement-Contractor | 9 | Contractor | Wing Lane | Drinking fountain replacement | Optima | Contractor | 2019-08-20 | 2020-02-20 | 2019/20 | 2-4814 | PO2W-200000002202 | 0 | 6800 | 5000190 | 2020-02-20 | 000000020071939 | 6800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9371104 | 100% | Provide & install 1 new drinking fountain at Wing Lane.
Wing Lane-Fire alarm-DSA Fees | 9 | DSA Fees | Wing Lane | Fire alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 870 | Per email | 2021-03-30 | 000000020176209 | 870 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9371103 | 12.26% | DSA plan check review fee for Wing Lane fire alarm.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28234 | 2021-02-05 | 000000020162584 | 7275 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28295 | 2021-02-09 | 000000020163360 | 7275 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 1.865% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28392 | 2021-03-24 | 000000020174735 | 2425 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28476 | 2021-03-24 | 000000020174735 | 2425 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0.6218% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 4850 | 28525 | 2021-05-26 | 000000020192536 | 4850 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 1.244% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28619 | 2021-05-26 | 000000020192536 | 9700 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28692 | 2021-06-23 | 000000020200466 | 1455 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0.3731% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28840 | 2021-09-09 | 000000020255227 | 970 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0.2487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Wing Lane-Fire alarm-Design | 9 | Design | Wing Lane | Fire alarm | tBP Architecture | Architect | 2020-10-20 | 2025-10-20 | 2021/22 | 21-2535 | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane.
Workman ES-21st Century-Reprographics | 2 | Reprographics | Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 2019/20 |  | PO1-200000000625 | 0 | 13.62 | 10580310 | 2020-04-22 | 000000020091358 | 13.62 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.681% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES.
Workman ES-21st Century-Reprographics | 2 | Reprographics | Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 2019/20 |  | PO1-200000000625 | 0 | 24.33 | 10589708 | 2020-04-22 | 000000020091358 | 24.33 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 1.216% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES.
Workman ES-21st Century-Reprographics | 2 | Reprographics | Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 2019/20 |  | PO1-200000000625 | 0 | 40.19 | 10597813 | 2020-04-22 | 000000020091358 | 40.19 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 2.009% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES.
Workman ES-21st Century-Reprographics | 2 | Reprographics | Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-30 | 2019/20 |  | PO1-200000000625 | 0 | 256.09 | 10583551 | 2020-04-30 | 000000020093653 | 256.09 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 12.8% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES.
Workman ES-21st Century-Reprographics | 2 | Reprographics | Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-30 | 2019/20 |  | PO1-200000000625 | 0 | 19.71 | 10583837 | 2020-04-30 | 000000020093653 | 19.71 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.9855% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES.
Workman ES-21st Century-Reprographics | 2 | Reprographics | Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-05-06 | 2019/20 | 2-3971 | PO1-200000000625 | 0 | 188.86 | 10568458 | 2020-05-06 | 000000020095031 | 188.86 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 9.443% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES.
Workman ES-21st Century-Reprographics | 2 | Reprographics | Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-05-06 | 2019/20 |  | PO1-200000001133 | 0 | 185.8 | 10568458 | 2020-05-06 | 000000020095031 | 185.8 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 5.262% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES.
Workman ES-21st Century-Reprographics | 2 | Reprographics | Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-08-17 | 2019/20 |  | PO1-200000001133 | 0 | 1251.62 | 10673862 | 2020-08-17 | 000000020119759 | 1251.62 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 35.45% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES.
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9747.93 | 0173465-IN | 2019-10-10 | 000000020025135 | 9747.93 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 0.2244% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7408.42 | 0173631-IN | 2019-10-10 | 000000020025135 | 7408.42 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 0.1705% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173774-IN | 2019-10-10 | 000000020025135 | 7798.34 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 125 | 0173465-IN | 2019-10-10 | 000000020025135 | 125 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.002877% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 75 | 0173465-IN | 2019-10-10 | 000000020025135 | 75 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 37.5 | 0173465-IN | 2019-10-10 | 000000020025135 | 37.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.0008631% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 237.5 | 0173465-IN | 2019-10-10 | 000000020025135 | 237.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.005466% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 291 | 0173465-IN | 2019-10-10 | 000000020025135 | 291 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.006698% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 800.75 | 0173465-IN | 2019-10-10 | 000000020025135 | 800.75 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.01843% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 180.5 | 0173631-IN | 2019-10-10 | 000000020025135 | 180.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.004155% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 95 | 0173631-IN | 2019-10-10 | 000000020025135 | 95 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 57 | 0173631-IN | 2019-10-10 | 000000020025135 | 57 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.001312% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 28.5 | 0173631-IN | 2019-10-10 | 000000020025135 | 28.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.000656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 221.16 | 0173631-IN | 2019-10-10 | 000000020025135 | 221.16 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.00509% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 608.57 | 0173631-IN | 2019-10-10 | 000000020025135 | 608.57 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.01401% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 190 | 0173774-IN | 2019-10-10 | 000000020025135 | 190 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 100 | 0173774-IN | 2019-10-10 | 000000020025135 | 100 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173774-IN | 2019-10-10 | 000000020025135 | 60 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173774-IN | 2019-10-10 | 000000020025135 | 30 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173774-IN | 2019-10-10 | 000000020025135 | 232.8 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173774-IN | 2019-10-10 | 000000020025135 | 640.6 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 62386.72 | 0175132-IN | 2019-10-10 | 000000020025132 | 62386.72 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 2.224% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 240 | 0175132-IN | 2019-10-10 | 000000020025132 | 240 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.008554% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 480 | 0175132-IN | 2019-10-10 | 000000020025132 | 480 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.01711% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 800 | 0175132-IN | 2019-10-10 | 000000020025132 | 800 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.02851% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1520 | 0175132-IN | 2019-10-10 | 000000020025132 | 1520 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.05418% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 1862.4 | 0175132-IN | 2019-10-10 | 000000020025132 | 1862.4 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.06638% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5124.8 | 0175132-IN | 2019-10-10 | 000000020025132 | 5124.8 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.1827% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1306.26 | 0173477-IN | 2019-09-23 | 000000020017958 | 1306.26 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 1.433% | Ergotron Zip40 Charging carts to store laptops Workman ES. Total cart: 1
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175123-IN | 2019-10-08 | 000000020023867 | 1306.26 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops Workman ES. Total carts: 17
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 20900.18 | 0175133-IN | 2019-10-08 | 000000020023867 | 20900.18 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 2.634% | Ergotron Zip40 Charging carts to store laptops Workman ES. Total carts: 17
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 72 | 0189682-IN | 2020-10-01 | 000000020131103 | 72 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 0.05777% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Workman ES. Total monitors: 12
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 26144.53 | 0189682-IN | 2020-10-01 | 000000020131103 | 26144.53 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 20.98% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Workman ES. Total monitors: 12
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2021-06-14 | 2022-02-11 | 2021/22 | 21-6818 | PO3W-210000003054 | 0 | 15362.62 | 0205446-IN | 2022-02-11 | 000000020412893 | 15362.62 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 100% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Mesa Robles. Total monitors: 7
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Camcor | Document camera(s) | 2020-07-01 | 2020-07-16 | 2020/21 | 21-309 | PO3W-210000000006 | 0 | 7172.46 | 2494523 | 2020-07-16 | 000000020114150 | 7172.46 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 21.05% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Workman ES. Total cameras: 12
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 288.93 | 8316064 | 2021-03-05 | 000000020169721 | 288.93 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 7.539% | C2G HDMI and USB pass through wall plates for Workman ES. Total items: 19
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 51.27 | 5725548 | 2021-03-05 | 000000020169721 | 51.27 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 1.338% | C2G HDMI and USB pass through wall plates for Workman ES. Total items: 19
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 242.34 | 8312741 | 2021-03-05 | 000000020169721 | 242.34 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 6.323% | C2G HDMI and USB pass through wall plates for Workman ES. Total items: 19
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Chatfield-Clarke | Tack boards | 2020-09-23 | 2020-11-03 | 2020/21 | 21-2077 | PO2W-210000000770 | 0 | 413.91 | 136701 | 2020-11-03 | 000000020139548 | 413.91 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 100% | Tack boards for Workman ES. Total tack boards: 5
Workman ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Workman ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2021-02-05 | 2020/21 |  | PO2W-200000005544 | 0 | 507.5 | 20-31196-60-0000001 | 2021-02-05 | 000000020162565 | 507.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9381101 | 3.057% | Provide materials testing and special inspection services at Workman ES. The project consists of alteration to 3 classroom buildings 1, 2, and 3 and 10 classroom buildings AP2 to AP11, and other site works. Scope of services include reviewing, inspecting, testing, and prepare reports for concrete and reinforcing steel.
Workman ES-21st Century-DSA Special Inspection | 2 | DSA Special Inspection | Workman ES | 21st Century | Converse Consultants | Geotechnical | 2020-06-05 | 2023-07-31 | 2021/22 | 2-10674 | PO2W-200000005544 | 16092.5 | 16092.5 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9381101 | 0% | Provide materials testing and special inspection services at Workman ES. The project consists of alteration to 3 classroom buildings 1, 2, and 3 and 10 classroom buildings AP2 to AP11, and other site works. Scope of services include reviewing, inspecting, testing, and prepare reports for concrete and reinforcing steel.
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2020-12-18 | 2020/21 |  | PO2W-200000004768 | 0 | 47603.64 | 30699 | 2020-12-18 | 000000020151932 | 47603.64 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 7.716% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2020-12-18 | 2020/21 |  | PO2W-200000004768 | 0 | 33109.53 | 30699 | 2020-12-18 | 000000020151932 | 33109.53 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 5.367% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 980.03 | 30789 | 2021-05-07 | 000000020187154 | 980.03 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 0.1589% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 19857.71 | 30860 | 2021-05-07 | 000000020187156 | 19857.71 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 3.219% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 2266.65 | 31584 | 2021-05-25 | 000000020192063 | 2266.65 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 0.3674% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2020-11-06 | 2021-04-19 | 2020/21 | 21-2946 | PO2W-210000001123 | 0 | 87940.71 | 30959 | 2021-04-19 | 000000020181375 | 87940.71 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 77.58% | Furniture for Workman ES. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2020-11-06 | 2021-04-19 | 2020/21 | 21-2946 | PO2W-210000001123 | 0 | 25420.1 | 30959 | 2021-04-19 | 000000020181375 | 25420.1 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 22.42% | Furniture for Workman ES. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2021-02-05 | 2021-05-25 | 2020/21 | 21-4243 | PO2W-210000001743 | 0 | 5321.7 | 31593 | 2021-05-25 | 000000020192063 | 5321.7 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 100% | Additional furniture for Workman ES - student chairs, total: 45
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Culver Newlin | Furniture | 2022-01-14 | 2022-03-23 | 2021/22 | 22-3988 | PO2W-220000001348 | 0 | 16893.03 | 34201 | 2022-03-23 | 000000020450077 | 16893.03 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 100% | Mid-tower mobile storage with shelves & 2 locking doors for Workman. Total towers: 14
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 9866.25 | 80804 | 2020-01-09 | 000000020055612 | 9866.25 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.6862% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3268.75 | 80796 | 2020-01-14 | 000000020057268 | 3268.75 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.2273% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8071.25 | 81699 | 2020-01-14 | 000000020057268 | 8071.25 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5613% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8765 | 83068 | 2020-04-01 | 000000020085959 | 8765 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.6096% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8365 | 82273 | 2020-04-01 | 000000020085960 | 8365 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5818% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 12972.5 | 84567 | 2020-04-15 | 000000020089466 | 12972.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.9022% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9657.5 | 85320 | 2020-05-28 | 000000020100719 | 9657.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.6716% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 9947.5 | 86240 | 2020-06-17 | 000000020106117 | 9947.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.6918% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 12327.5 | 86864 | 2020-07-27 | 000000020116270 | 12327.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.8573% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 8313.42 | 88480 | 2020-08-17 | 000000020119773 | 8313.42 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5782% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 7852.49 | 89359 | 2020-10-13 | 000000020134067 | 7852.49 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5461% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 7439.86 | 90460 | 2020-10-20 | 000000020136025 | 7439.86 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5174% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 8289.78 | 91321 | 2020-12-18 | 000000020151933 | 8289.78 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5765% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 7166.87 | 91964 | 2020-12-18 | 000000020151933 | 7166.87 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.4984% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 7664.02 | 92821 | 2021-02-08 | 000000020162981 | 7664.02 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.533% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 5637.64 | 94011 | 2021-04-05 | 000000020177572 | 5637.64 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.3921% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 4774.06 | 94918 | 2021-04-16 | 000000020181024 | 4774.06 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.332% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 5098.5 | 95700 | 2021-05-25 | 000000020192064 | 5098.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.3546% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 2956.63 | 96936 | 2021-05-25 | 000000020192064 | 2956.63 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.2056% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 480 | 97857R1 | 2021-06-22 | 000000020200048 | 480 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.03338% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-03-15 | 2021/22 |  | PO1-200000000640 | 0 | 5583.09 | 108239 | 2022-03-15 | 000000020443751 | 5583.09 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.3883% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2022-10-10 | 2021/22 | 2-4694 | PO1-200000000640 | 14709.39 | 14709.39 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 9695.44 | 10513843591 | 2021-08-27 | 000000020245275 | 9695.44 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 13.33% | PowerSwitch N2200-ON OS6 for Workman ES. Total power switch: 2
Workman ES-21st Century-DSA Fees | 2 | DSA Fees | Workman ES | 21st Century | Division of the State Architect (DSA) | DSA fees | 2019-04-16 | 2019-04-18 | 2018/19 |  | 19-108465 | 0 | 9500 | Per email | 2019-04-18 | 25237048 | 9500 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9381101 | 100% | DSA plan check review fee for Workman ES 21st Century.
Workman ES-21st Century-DSA Fees | 2 | DSA Fees | Workman ES | 21st Century | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-05-05 | 2020/21 | 21-6131 | PO2W-210000002165 | 0 | 800 | Per email | 2021-05-05 | 000000020186222 | 800 | 03-121545 | 73445-382 | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9381101 | 100% | DSA plan check review fee for Workman ES 21st Century Hardware replacement project (doors & locks).
Workman ES-21st Century-DSA Fees | 2 | DSA Fees | Workman ES | 21st Century | Division of the State Architect (DSA) | DSA fees | 2022-01-19 | 2022-01-28 | 2021/22 | 22-4020 | PO2W-220000001377 | 0 | 12085.87 | 12959 | 2022-01-28 | 000000020401405 | 12085.87 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9381101 | 100% | DGS plan/field review fee for Workman ES 21st Century
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Graybar | Door hardware | 2020-12-14 | 2021-02-08 | 2020/21 | 21-3550 | PO3W-210000001162 | 0 | 246.8 | 9319230223 | 2021-02-08 | 000000020162991 | 246.8 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 33.33% | Mounting brackets & blank face plates for Workman ES
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2020-11-30 | 2021-04-16 | 2020/21 |  | PO2W-210000001354 | 0 | 507.43 | 34750 | 2021-04-16 | 000000020181028 | 507.43 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 24.52% | Equipment to repair & replace security system at Workman ES
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2020-11-30 | 2021-04-16 | 2020/21 | 21-3242 | PO2W-210000001354 | 0 | 603.66 | 34750 | 2021-04-16 | 000000020181028 | 603.66 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 29.18% | Equipment to repair & replace security system at Workman ES
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | ICS Service Co. | Equipment to repair & replace security system | 2020-11-30 | 2023-01-16 | 2021/22 | 21-3242 | PO2W-210000001354 | 957.98 | 957.98 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 0% | Equipment to repair & replace security system at Workman ES
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-07-06 | 2020-08-18 | 2019/20 | 21-399 | PO2W-210000000144 | 0 | 32000 | 2019-032A-7 | 2020-08-18 | 000000020120080 | 32000 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 100% | Asbestos abatement of Workman ES floor tile in classroom #5,6,7, & 12. Demolish and haul off casework.
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement | 2020-09-18 | 2021-03-24 | 2020/21 | 21-2008 | PO2W-210000000675 | 0 | 4250 | 2020-093A | 2021-03-24 | 000000020174720 | 4250 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 100% | Asbestos abatement of flooring at Workman ES for the staff bathroom
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 2020/21 | 21-2378 | PO2W-210000000884 | 0 | 27500 | 2020-093A-2 | 2020-11-20 | 000000020144493 | 27500 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 23.4% | Demo of ceiling tiles in 11 classrooms at Workman ES
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9237.13 | 2902451120 | 2021-03-24 | 000000020174722 | 9237.13 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.273% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9826.74 | 2979801120 | 2021-03-24 | 000000020174722 | 9826.74 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.865% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9826.74 | 2979811120 | 2021-03-24 | 000000020174722 | 9826.74 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.865% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9826.74 | 2979821120 | 2021-03-24 | 000000020174722 | 9826.74 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.865% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9826.32 | 2979831120 | 2021-03-24 | 000000020174722 | 9826.32 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.865% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 10685.36 | 2902451120 | 2021-03-24 | 000000020174722 | 10685.36 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 10.73% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 11367.4 | 2979801120 | 2021-03-24 | 000000020174722 | 11367.4 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 11.41% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 11367.4 | 2979811120 | 2021-03-24 | 000000020174722 | 11367.4 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 11.41% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 11367.4 | 2979821120 | 2021-03-24 | 000000020174722 | 11367.4 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 11.41% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 11367.82 | 2979831120 | 2021-03-24 | 000000020174722 | 11367.82 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 11.41% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-04-16 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | -5086.56 | 5292870421 | 2021-04-16 | 000000020181030 | -5086.56 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | -5.106% | Furniture for Workman ES - Tables, chairs, stools, carpets, filing cabinets, etc. Credit memo from vendor
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 3.16% | Furniture for Workman ES - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Workman ES-21st Century-FF & E | 2 | FF & E | Workman ES | 21st Century | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 1.655% | Furniture for Workman ES - flex space chairs, mobile tchr desks, media tower, carpets, tables, tree seats, bin centers, etc.
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 840.96 | 6454842481 | 2020-07-27 | 000000020116281 | 840.96 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 1.35% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II (4 year warranty) for Workman ES. Total computers: 12
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-05 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 11812.86 | 6454893288 | 2020-08-05 | 000000020117729 | 11812.86 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 19.65% | Desktop computers (ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II (4 year warranty) for Workman ES. Total computers: 12
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 2575.44 | 128357 | 2020-07-23 | 000000020115778 | 2575.44 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 2.289% | Voice amplification system - Topcat, mounting kit & sensor clip for Workman ES. Total system: 12
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 21115.98 | 128357 | 2020-07-23 | 000000020115778 | 21115.98 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 18.76% | Voice amplification system - Topcat, mounting kit & sensor clip for Workman ES. Total system: 12
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI89943 | 2021-02-22 | 000000020166212 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI90466 | 2021-02-22 | 000000020166212 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI90911 | 2021-02-22 | 000000020166212 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI91368 | 2021-02-22 | 000000020166212 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI91694 | 2021-03-24 | 000000020174723 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI92161 | 2021-03-24 | 000000020174723 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI92505 | 2021-03-24 | 000000020174723 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI92910 | 2021-05-26 | 000000020192523 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI93716 | 2021-05-26 | 000000020192523 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI93277 | 2021-05-26 | 000000020192523 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI94012 | 2021-06-23 | 000000020200450 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI94487 | 2021-06-23 | 000000020200450 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI94800 | 2021-06-23 | 000000020200450 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI94935 | 2021-06-23 | 000000020200450 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-06-30 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI95216 | 2021-06-30 | 000000020202687 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 275.01 | RI95529 | 2021-09-09 | 000000020255202 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 137.5 | RI95924 | 2021-09-09 | 000000020255202 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 | 21-4285 | PO1-210000000608 | 0 | 275.01 | RI96229 | 2021-09-09 | 000000020255202 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2020-05-06 | 2021-06-30 | 2019/20 |  | PO2W-200000005021 | 0 | 1373 | RI85304 | 2020-06-24 | 000000020108003 | 1373 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 41.06% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Workman ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2020-05-06 | 2020-07-01 | 2020/21 | 2-10093 | PO2W-200000005021 | 0 | 1971 | RI85304 | 2020-07-01 | 000000020108003 | 1971 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 58.94% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Workman ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2020-06-03 | 2020-08-18 | 2019/20 |  | PO2W-200000005485 | 0 | 682 | RI85720 | 2020-08-18 | 000000020120082 | 682 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 40.79% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Workman ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2020-06-03 | 2020-08-18 | 2020/21 | 2-10622 | PO2W-200000005485 | 0 | 990 | RI85720 | 2020-08-18 | 000000020120082 | 990 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 59.21% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Workman ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-03-12 | 2021-03-30 | 2020/21 |  | PO2W-210000001957 | 0 | 137.5 | RI92642 | 2021-03-30 | 000000020176212 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-03-12 | 2021-05-26 | 2020/21 |  | PO2W-210000001957 | 0 | 137.5 | RI93429 | 2021-05-26 | 000000020192523 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-03-12 | 2021-05-26 | 2020/21 |  | PO2W-210000001957 | 0 | 137.5 | RI94169 | 2021-05-26 | 000000020192523 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-03-12 | 2021-09-09 | 2021/22 |  | PO2W-210000001957 | 0 | 137.5 | RI95656 | 2021-09-09 | 000000020255202 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021.
Workman ES-21st Century-Move Management | 2 | Move Management | Workman ES | 21st Century | Martin Container | Rental of container(s) | 2021-03-12 | 2021-09-09 | 2021/22 | 21-5282 | PO2W-210000001957 | 0 | 137.5 | RI96355 | 2021-09-09 | 000000020255202 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO.
Workman ES-21st Century-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2019/20 | 2-9626 | PO2W-200000004876 | 0 | 2500 | MCSI-4512 | 2020-06-03 | 000000020102133 | 2500 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 100% | Asbestos & lead-based paint survey of Workman ES permanent buildings and old portable buildings. Walk through, collect samples, testing of samples, and prepare report.
Workman ES-21st Century-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-06-03 | 2020-06-26 | 2019/20 | 2-10645 | PO2W-200000005541 | 0 | 1200 | MCSI-4519 | 2020-06-26 | 000000020108764 | 1200 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 100% | Asbestos & lead-based paint survey of Workman ES classrooms #P13 through P17, pre-demolition
Workman ES-21st Century-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-07-06 | 2020-08-17 | 2019/20 |  | PO2W-210000000062 | 0 | 6775 | MCSI-4561 | 2020-08-17 | 000000020119790 | 6775 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 61.17% | Floor tile & mastic abatement oversight at Workman ES for room #5, 6, 7, and 12
Workman ES-21st Century-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-07-06 | 2023-01-16 | 2021/22 | 21-403 | PO2W-210000000062 | 4300 | 4300 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 0% | Floor tile & mastic abatement oversight at Workman ES for room #5, 6, 7, and 12
Workman ES-21st Century-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-09-11 | 2020-11-19 | 2020/21 |  | PO2W-210000000585 | 0 | 825 | MCSI-4639 | 2020-11-19 | 000000020143747 | 825 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 89.19% | Oversight asbestos abatement of a small area next to staff restrooms at Workman ES
Workman ES-21st Century-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century | Masek Consulting | Oversight asbestos abatement | 2020-09-11 | 2023-09-11 | 2021/22 | 21-1846 | PO2W-210000000585 | 100 | 100 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 0% | Oversight asbestos abatement of a small area next to staff restrooms at Workman ES
Workman ES-21st Century-Technology | 2 | Technology | Workman ES | 21st Century | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 2020/21 | 21-3265 | PO2W-210000001351 | 0 | 1086.6 | 956471 | 2021-02-10 | 000000020163835 | 1086.6 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 100% | Cables for Workman ES
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2018-06-28 | 2017/18 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 2363.68 | 54895 | 2018-06-28 | 24653416 | 2363.68 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 2% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2019-04-03 | 2018/19 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 4581.84 | 55730 Revised | 2019-04-03 | 25206760 | 4581.84 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 3.877% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2019-09-05 | 2018/19 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 23782.32 | 55870 | 2019-09-05 | 000000020011695 | 23782.32 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 20.12% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2019-09-05 | 2018/19 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 30432.38 | 55871 | 2019-09-05 | 000000020011695 | 30432.38 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 25.75% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2019-10-25 | 2019/20 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 1950.04 | 20031048 | 2019-10-25 | 000000020031048 | 1950.04 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 1.65% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2019-10-25 | 2019/20 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 3900.07 | 20031048 | 2019-10-25 | 000000020031048 | 3900.07 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 3.3% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2020-05-26 | 2019/20 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 9809.27 | 56735R | 2020-05-26 | 000000020099838 | 9809.27 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 8.3% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2020-08-18 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 5909.2 | 56975 | 2020-08-18 | 000000020120097 | 5909.2 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 5% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2021-02-05 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 14773 | 57291 | 2021-02-05 | 000000020162573 | 14773 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 12.5% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2021-02-05 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 4431.9 | 57389 | 2021-02-05 | 000000020162573 | 4431.9 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 3.75% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2022-03-24 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 2954.6 | 57466R | 2022-03-24 | 000000020451068 | 2954.6 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 2.5% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2022-03-24 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 9750.18 | 57966R | 2022-03-24 | 000000020451068 | 9750.18 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 8.25% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2023-01-16 | 2021/22 | 2-526 | PO2W-200000001213, 19-100506, 18-109555 | 3545.52 | 3545.52 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 0% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2019-02-08 | 2018/19 |  | PO2W-200000001214, 19-101982 | 0 | 3450 | 55509 | 2019-02-08 | 25085117 | 3450 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 17.25% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2019-02-08 | 2018/19 |  | PO2W-200000001214, 19-101982 | 0 | 1450 | 55510 | 2019-02-08 | 25085117 | 1450 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 7.25% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2020-06-03 | 2019/20 |  | PO2W-200000001214, 19-101982 | 0 | 404.95 | 56736R | 2020-06-03 | 000000020102139 | 404.95 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 2.025% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | SVA Architects, Inc | Architect | 2018-06-01 | 2023-01-16 | 2021/22 | 2-527 | PO2W-200000001214, 19-101982 | 14695.05 | 14695.05 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 0% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES.
Workman ES-21st Century-DSA Fees | 2 | DSA Fees | Workman ES | 21st Century | SVA Architects, Inc | DSA fees | 2020-02-27 | 2020-04-02 | 2019/20 | 2-8457 | PO2W-200000004424 | 0 | 2250 | 56405 | 2020-04-02 | 000000020086382 | 2250 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9381101 | 100% | DSA plan check review fee for Workman ES 21st Century.
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | TDM Architects, Inc | Architect | 2021-04-08 | 2021-08-31 | 2021/22 | 21-5882 | PO2W-210000002075 | 0 | 8116.8 | T8665R | 2021-08-31 | 000000020248528 | 8116.8 | 03-121545 | 73445-382 | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 60% | Architect - Prepare design documents for Workman ES 21st Century Hardware replacement project (doors & locks).
Workman ES-21st Century-Design | 2 | Design | Workman ES | 21st Century | TDM Architects, Inc | Architect | 2021-04-08 | 2023-04-08 | 2021/22 | 21-5882 | PO2W-210000002075 | 5411.2 | 5411.2 |  |  |  | 0 | 03-121545 | 73445-382 | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 0% | Architect - Prepare design documents for Workman ES 21st Century Hardware replacement project (doors & locks).
Workman ES-21st Century-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 2019/20 |  | PO2W-200000004962 | 0 | 2940 | 20200630-05:WEM | 2020-06-19 | 000000020106934 | 2940 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 8.468% | General inspection for the project as defined in Title 24. Modernization of Workman ES.
Workman ES-21st Century-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-08-19 | 2020/21 |  | PO2W-200000004962 | 0 | 3080 | 202008-05:WEM | 2020-08-19 | 000000020120364 | 3080 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 8.871% | General inspection for the project as defined in Title 24. Modernization of Workman ES.
Workman ES-21st Century-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-10-14 | 2020/21 |  | PO2W-200000004962 | 0 | 3500 | 202009-05:WEM | 2020-10-14 | 000000020134520 | 3500 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 10.08% | General inspection for the project as defined in Title 24. Modernization of Workman ES.
Workman ES-21st Century-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2020-10-21 | 2020/21 |  | PO2W-200000004962 | 0 | 2940 | 202010-05:WEM | 2020-10-21 | 000000020136459 | 2940 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 8.468% | General inspection for the project as defined in Title 24. Modernization of Workman ES.
Workman ES-21st Century-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-02-05 | 2020/21 |  | PO2W-200000004962 | 0 | 3080 | 202011-05:WEM | 2021-02-05 | 000000020162579 | 3080 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 8.871% | General inspection for the project as defined in Title 24. Modernization of Workman ES.
Workman ES-21st Century-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004962 | 0 | 5040 | 202012-05:WEM | 2021-04-19 | 000000020181403 | 5040 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 14.52% | General inspection for the project as defined in Title 24. Modernization of Workman ES.
Workman ES-21st Century-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004962 | 0 | 4900 | 202101-05:WEM | 2021-04-19 | 000000020181403 | 4900 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 14.11% | General inspection for the project as defined in Title 24. Modernization of Workman ES.
Workman ES-21st Century-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century | Team Inspections | General inspection | 2020-04-29 | 2023-07-31 | 2021/22 | 2-9869 | PO2W-200000004962 | 9240 | 9240 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 0% | General inspection for the project as defined in Title 24. Modernization of Workman ES.
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | The Nazerian Group | Contractor | 2020-06-05 | 2020-10-13 | 2020/21 |  | PO2W-200000005821 | 0 | 369049.35 | Pay app #1 | 2020-10-13 | 000000020134121 | 369049.35 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 24.7% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project with change order (xreq 22-5141) is $1,533,416.51
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | The Nazerian Group | Contractor | 2020-06-05 | 2020-10-13 | 2020/21 |  | PO2W-200000005821 | 0 | 76902.5 | Pay app #2 | 2020-10-13 | 000000020134121 | 76902.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 5.147% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project with change order (xreq 22-5141) is $1,533,416.51
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | The Nazerian Group | Contractor | 2020-06-05 | 2021-02-05 | 2020/21 |  | PO2W-200000005821 | 0 | 766840 | Pay app #3 | 2021-02-05 | 000000020162581 | 766840 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 51.32% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project with change order (xreq 22-5141) is $1,533,416.51
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | The Nazerian Group | Contractor | 2020-06-05 | 2021-04-06 | 2020/21 |  | PO2W-200000005821 | 0 | 95237.5 | Pay app #4 | 2021-04-06 | 000000020177879 | 95237.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 6.374% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project with change order (xreq 22-5141) is $1,533,416.51
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | The Nazerian Group | Contractor | 2020-06-05 | 2023-07-31 | 2021/22 | 2-10690 | PO2W-200000005821 | 186093.65 | 186093.65 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 0% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project with change order (xreq 22-5141) is $1,533,416.51
Workman ES-21st Century-Contractor | 2 | Contractor | Workman ES | 21st Century | The Nazerian Group | Contractor | 2022-03-07 | 2024-07-11 | 2021/22 | 22-5141 |  | 39293.51 | 39293.51 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9381101 | 0% | Change orders for the 21st Classroom modifications at Workman ES. Bid bundle #1. Addendum to PO2W-20*5821. The total project with change order is $1,533,416.51
Workman ES-Ceiling replacement-Contractor | 2 | Contractor | Workman ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 23073.6 | Pay app #1 | 2019-12-17 | 000000020049998 | 23073.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381105 | 0.5045% | Ceiling replacement for Workman ES.
Workman ES-Ceiling replacement-Contractor | 2 | Contractor | Workman ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 69220.8 | Pay app #2 | 2020-10-21 | 000000020136454 | 69220.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381105 | 1.514% | Ceiling replacement for Workman ES.
Workman ES-Ceiling replacement-Contractor | 2 | Contractor | Workman ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 138441.6 | Pay app #3 | 2021-01-08 | 000000020155354 | 138441.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381105 | 3.027% | Ceiling replacement for Workman ES.
Workman ES-Ceiling replacement-Contractor | 2 | Contractor | Workman ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor | 2019-07-01 | 2025-01-16 | 2021/22 | 2-5072 | PO1-200000000729 | 12144 | 12144 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381105 | 0% | Ceiling replacement for Workman ES.
Workman ES-Drinking fountain replacement-DSA Inspection | 2 | DSA Inspection | Workman ES | Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2021-03-24 | 2020/21 | 2-6609 | PO2W-200000003303 | 0 | 1200 | 202103-10:WDF | 2021-03-24 | 000000020174730 | 1200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381104 | 10% | General inspection for the project as defined in Title 24 at Workman ES. Replacement of 2-exterior drinking fountains
Workman ES-Fire alarm-Design | 2 | Design | Workman ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28123 | 2021-01-07 | 000000020154828 | 2375 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The total architect contract for Workman ES FA is $47,500.00
Workman ES-Fire alarm-Design | 2 | Design | Workman ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 4750 | 28382 | 2021-03-24 | 000000020174735 | 4750 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 2.772% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The total architect contract for Workman ES FA is $47,500.00
Workman ES-Fire alarm-Design | 2 | Design | Workman ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28467 | 2021-03-24 | 000000020174735 | 2375 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 1.386% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The total architect contract for Workman ES FA is $47,500.00
Workman ES-Fire alarm-Design | 2 | Design | Workman ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28727 | 2021-09-09 | 000000020255226 | 1425 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 0.8316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The total architect contract for Workman ES FA is $47,500.00
Workman ES-Fire alarm-Design | 2 | Design | Workman ES | Fire alarm | tBP Architecture | Architect | 2018-07-01 | 2022-02-23 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 29185 | 2022-02-23 | 000000020425550 | 950 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 0.5544% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The total architect contract for Workman ES FA is $47,500.00
Workman ES-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Workman ES | Fire Alarm | Team Inspections | General inspection | 2021-01-13 | 2021-02-09 | 2020/21 |  | PO2W-210000001574 | 0 | 6120 | 202101-13:WFA | 2021-02-09 | 000000020163358 | 6120 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381103 | 49.96% | General inspection for the project as defined in Title 24 at Workman ES. Alterations to fire alarm system
Workman ES-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Workman ES | Fire Alarm | Team Inspections | General inspection | 2021-01-13 | 2021-04-19 | 2020/21 |  | PO2W-210000001574 | 0 | 3060 | 202102-11:WFA | 2021-04-19 | 000000020181403 | 3060 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381103 | 24.98% | General inspection for the project as defined in Title 24 at Workman ES. Alterations to fire alarm system
Workman ES-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Workman ES | Fire Alarm | Team Inspections | General inspection | 2021-01-13 | 2021-09-13 | 2020/21 |  | PO2W-210000001574 | 0 | 2570 | 20210630-11: WFA | 2021-09-13 | 000000020257046 | 2570 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381103 | 20.98% | General inspection for the project as defined in Title 24 at Workman ES. Alterations to fire alarm system
Workman ES-Fire Alarm-DSA Inspection | 2 | DSA Inspection | Workman ES | Fire Alarm | Team Inspections | General inspection | 2021-01-13 | 2022-07-31 | 2021/22 | 21-3772 | PO2W-210000001574 | 500 | 500 |  |  |  | 0 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381103 | 0% | General inspection for the project as defined in Title 24 at Workman ES. Alterations to fire alarm system
Workman ES-Fire Alarm-Contractor | 2 | Contractor | Workman ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1131.45 | Pay app #1 | 2020-03-10 | 000000020079637 | 1131.45 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0.08841% | Fire alarm and low voltage service for Workman ES
Workman ES-Fire Alarm-Contractor | 2 | Contractor | Workman ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 62754.38 | Pay app #12 | 2021-05-21 | 000000020191188 | 62754.38 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 4.904% | Fire alarm and low voltage service for Workman ES
Workman ES-Fire Alarm-Contractor | 2 | Contractor | Workman ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 13328.69 | Pay app #13 | 2021-05-21 | 000000020191188 | 13328.69 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 1.042% | Fire alarm and low voltage service for Workman ES
Workman ES-Fire Alarm-Contractor | 2 | Contractor | Workman ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 2235.78 | Pay app #14 | 2021-05-21 | 000000020191188 | 2235.78 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0.1747% | Fire alarm and low voltage service for Workman ES
Workman ES-Fire Alarm-Contractor | 2 | Contractor | Workman ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 6656.75 | Pay app #15 | 2021-05-21 | 000000020191188 | 6656.75 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0.5202% | Fire alarm and low voltage service for Workman ES
Workman ES-Fire Alarm-Contractor | 2 | Contractor | Workman ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 39885.71 | Pay app #16 | 2021-11-22 | 000000020341778 | 39885.71 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 3.117% | Fire alarm and low voltage service for Workman ES
Workman ES-Fire Alarm-Contractor | 2 | Contractor | Workman ES | Fire Alarm | Telenet VOIP, Inc | Contractor | 2019-09-26 | 2025-01-16 | 2021/22 | 2-4512 | PO1-200000000662 | 7774.25 | 7774.25 |  |  |  | 0 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0% | Fire alarm and low voltage service for Workman ES
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15525.78 | 0173366-IN | 2019-10-10 | 000000020025135 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9431101 | 0.3574% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 19795.37 | 0173630-IN | 2019-10-10 | 000000020025135 | 19795.37 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9431101 | 0.4556% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 359033.8 | 0174233-IN | 2019-10-10 | 000000020025135 | 359033.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9431101 | 8.264% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 200 | 0173366-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 120 | 0173366-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 60 | 0173366-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 380 | 0173366-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173366-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173366-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 153 | 0173630-IN | 2019-10-10 | 000000020025135 | 153 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.003522% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 76.5 | 0173630-IN | 2019-10-10 | 000000020025135 | 76.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.001761% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 255 | 0173630-IN | 2019-10-10 | 000000020025135 | 255 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.005869% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 484.5 | 0173630-IN | 2019-10-10 | 000000020025135 | 484.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.01115% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 593.64 | 0173630-IN | 2019-10-10 | 000000020025135 | 593.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.01366% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1633.53 | 0173630-IN | 2019-10-10 | 000000020025135 | 1633.53 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.0376% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1387.5 | 0174233-IN | 2019-10-10 | 000000020025136 | 1387.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.03194% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2775 | 0174233-IN | 2019-10-10 | 000000020025136 | 2775 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.06387% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4625 | 0174233-IN | 2019-10-10 | 000000020025136 | 4625 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.1065% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 8787.5 | 0174233-IN | 2019-10-10 | 000000020025136 | 8787.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.2023% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-513 | PO2W-200000000689, 19-109955 | 0 | 10767 | 0174233-IN | 2019-10-10 | 000000020025136 | 10767 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.2478% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-514 | PO2W-200000000689, 19-109955 | 0 | 29627.75 | 0174233-IN | 2019-10-10 | 000000020025136 | 29627.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.6819% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-515 | PO3W-200000000448 | 0 | 1300.32 | 0173473-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9431101 | 1.427% | Ergotron Zip40 Charging carts to store laptops Workman HS. Total cart: 1
Workman HS-21st Century-Technology | 5 | Technology | Workman HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-11-07 | 2019/20 | 2-516 | PO3W-200000000730 | 0 | 40310.03 | 0174342-IN | 2019-11-07 | 000000020035575 | 40310.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9431101 | 5.08% | Ergotron Zip40 Charging carts to store laptops Workman HS. Total carts: 31
Workman HS-21st Century-Contractor | 5 | Contractor | Workman HS | 21st Century | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-04-06 | 2020/21 |  | PO2W-200000004391 | 0 | 57350.16 | Pay app #6 | 2021-04-06 | 000000020177862 | 57350.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9431101 | 12.74% | Prep & install Mohawk LVT, walk off mat & base at Workman HS for room #A9-A12, A18, E25-E27, & F1
Workman HS-21st Century-Environ Consultant | 5 | Environ Consultant | Workman HS | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2021-01-19 | 2020/21 | 21-1583 | PO1-210000000427 | 0 | 4150 | MCSI-4657 | 2021-01-19 | 000000020157533 | 4150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9431101 | 10.07% | Asbestos & lead-based paint survey of Workman HS permanent buildings.
[11 empty] | TOTAL: | 6919563.56 | 47717129.11 |  |  |  | 40797565.55
Fixed Assets:
- | A plethora of furniture from Culver Newlin, Lakeshore, & Uline.
- | Carts: 2 from Uline for District-wide use.
- | Charging carts for laptops (Ergotron Zip40): 680 from Arey Jones (see below for break-down by site).
- | Desktop Computers (ThinkCentre M70q), brackets, & power supply cages: 2 from Arey Jones. Cedarlane: 2.
- | Desktop Computers (ThinkCentre M720q): 121 from Lenovo & Arey Jones. Lenovo (58) - Los Altos ES: 20, Nelson: 26, & Workman ES: 12. Arey Jones (63) - Cedarlane: 25 & Mesa: 38.
- | Document Cameras (Elmo TT-12W): 121 from CDW-G & Camcor. CDW-G (1) - Nelson: 1. Camcor (120) - Cedarlane: 25, Los Altos ES: 20, Mesa: 38, Nelson: 25, & Workman ES: 12.
- | Drinking fountains: 6 from Optima. Optima: 6 - Amar: 1, Los Altos HS: 1, Mesa: 1, Sunset: 1, Wedgeworth: 1, & Winglane: 1.
- | Equipment to repair & replace security system: 5 from ICS. Cedarlane: 1, Los Altos ES: 1, Mesa Robles: 1, Nelson: 1, & Workman ES: 1.
- | Hydraulic stacker: 2 from Uline for District-wide use.
- | Laptops (Lenovo 300e): 15,842 from Arey Jones (see below for break-down by site).
- | Monitors' bundle (ViewSonic ViewBoard IFP7550): 135 from Arey Jones. Cedarlane: 27, Los Altos ES: 20, Mesa: 43, Nelson: 26, & Workman ES: 19.
- | Portable buildings: 20 from Mobile Modular. Cedarlane: 4, Los Altos ES: 4, Mesa: 8, & Newton: 4.
- | Power switch (N2200-ON OS6): 15 from Dell. Cedarlane: 2, Los Altos ES: 2, Mesa: 7, Nelson: 2, & Workman ES: 2.
- | Rolling instrument storage cabinets: 2 from David M. Bertino, Mfg. Inc. Cedarlane: 2
- | Scissor lift table: 1 from Global Industrial for District-wide use.
- | Tack boards: 13 from Education Products & Chatfield. Education Products (8) - District: 8 & Chatfield (5) - Workman ES: 5.
- | Voice amplification systems (Topcat with Flexmike): 124 from Lightspeed. Cedarlane: 25, Los Altos ES: 20, Mesa Robles: 42, Nelson: 25, & Workman ES: 12.
- | White boards: 8 from Education Products. Grandview: 1, Nelson: 6, & Valinda: 1.
- | Wireless network equipment (HPE Aruba IAP-325 Wireless access point): 180 from CDW-G for District-wide use.
Arey Jones - Charging carts (Ergotron Zip40): 680.00 units | [5 empty] | Arey Jones - Laptops (Lenovo 300e): 15,842.00 units
Project Site |  | Unit |  |  |  | Project Site |  | Unit
Amar |  | 15 |  |  |  | Amar |  | 0
Baldwin |  | 27 |  |  |  | Baldwin |  | 469
Bixby |  | 14 |  |  |  | Bixby |  | 165
California |  | 16 |  |  |  | California |  | 253
Cedarlane |  | 22 |  |  |  | Cedarlane |  | 615
Del Valle |  | 16 |  |  |  | Del Valle |  | 287
Fairgrove |  | 36 |  |  |  | Fairgrove |  | 889
Grandview |  | 18 |  |  |  | Grandview |  | 552
Grazide |  | 23 |  |  |  | Grazide |  | 349
Kwis |  | 15 |  |  |  | Kwis |  | 221
Lassalette |  | 25 |  |  |  | Lassalette |  | 465
Los Altos ES |  | 21 |  |  |  | Los Altos ES |  | 317
Los Molinos |  | 22 |  |  |  | Los Molinos |  | 268
Los Robles |  | 10 |  |  |  | Los Robles |  | 141
Mesa Robles |  | 37 |  |  |  | Mesa Robles |  | 966
Nelson |  | 18 |  |  |  | Nelson |  | 280
Newton |  | 17 |  |  |  | Newton |  | 686
Orange Grove |  | 12 |  |  |  | Orange Grove |  | 428
Palm |  | 14 |  |  |  | Palm |  | 210
Sierra Vista |  | 9 |  |  |  | Sierra Vista |  | 352
Sparks ES |  | 18 |  |  |  | Sparks ES |  | 329
Sparks MS |  | 14 |  |  |  | Sparks MS |  | 585
Sunset |  | 9 |  |  |  | Sunset |  | 213
Temple |  | 14 |  |  |  | Temple |  | 206
Valinda |  | 27 |  |  |  | Valinda |  | 501
Wedgeworth |  | 24 |  |  |  | Wedgeworth |  | 255
Wing Lane |  | 15 |  |  |  | Wing Lane |  | 201
Workman ES |  | 18 |  |  |  | Workman ES |  | 224
La Puente HS |  | 31 |  |  |  | La Puente HS |  | 1027
Los Altos HS |  | 44 |  |  |  | Los Altos HS |  | 1609
Wilson HS |  | 41 |  |  |  | Wilson HS |  | 1372
Workman HS |  | 32 |  |  |  | Workman HS |  | 1016
Valley |  | 6 |  |  |  | Valley |  | 176
TOTAL: |  | 680 |  |  |  | District Office |  | 146
[6 empty] | Palm Canyon |  | 23
[6 empty] | Stimson |  | 46
[6 empty] | TOTAL: |  | 15842
Note on C1: Per Dan Franco @Cumming
Note on I2507: Nety Con: Fund 12 paid for 371 units @ Amar (PO2W-2*689) Amount paid: $167,909.78 Ok, per Annie Bui

## Detail_P
MEASURE BB
Project Site | Project Description | Vendor Name | Description (Services) | Est. start date | Est. end date | Completed Amount | Committed Amount | Total Exp. & Committed
Amar | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 19593.92 | 0 | 19593.92
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-01-31 | 14794.34 | 0 | 14794.34
[5 empty] | 2020-02-03 | 77885.63 | 0 | 77885.63
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 17165.07 | 163519.93 | 180685
| Drinking fountain replacement | Optima | Contractor |  |  | 8200 | 0 | 8200
|  | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
Amar Total | [5 empty] | 140238.96 | 164719.93 | 304958.89
Baldwin | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 18204.53 | 0 | 18204.53
[5 empty] | 2019-11-07 | 16981.39 | 0 | 16981.39
|  |  | Laptops | 2019-07-01 | 2019-10-08 | 30775.92 | 0 | 30775.92
[5 empty] | 2019-10-10 | 181485.61 | 0 | 181485.61
|  | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 960 | 0 | 960
[5 empty] | 2021-09-29 | 1760 | 0 | 1760
[5 empty] | 2024-07-01 | 0 | 292142 | 292142
|  |  |  | 2021-11-02 | 2021-11-08 | 5650 | 0 | 5650
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 50000 | 0 | 50000
|  |  |  | 2021-06-14 | 2021-09-09 | 6500 | 0 | 6500
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2019-12-19 | 23186.9 | 0 | 23186.9
[5 empty] | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
|  | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 29733.8 | 0 | 29733.8
[5 empty] | 2021-10-19 | 33815.5 | 0 | 33815.5
[5 empty] | 2024-05-03 | 0 | 273555.7 | 273555.7
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 299861.8 | 15782.2 | 315644
| Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 1050 | 0 | 1050
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 1020 | 0 | 1020
|  | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 0 | 12125 | 12125
| Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 0 | 79400 | 79400
Baldwin Total | [5 empty] | 724306.06 | 673004.9 | 1397310.96
Bixby | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 6501.61 | 0 | 6501.61
[5 empty] | 2019-10-08 | 11702.91 | 0 | 11702.91
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 74384.41 | 0 | 74384.41
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-05-11 | 2021-06-28 | 52500 | 0 | 52500
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 281964.75 | 14840.25 | 296805
| Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2021-04-27 | 2021-05-05 | 1050 | 0 | 1050
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 870 | 0 | 870
|  | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 0 | 12125 | 12125
Bixby Total | [5 empty] | 452294.29 | 26965.25 | 479259.54
California | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 20900.18 | 0 | 20900.18
|  |  | Laptops | 2019-07-01 | 2019-10-08 | 8146.57 | 0 | 8146.57
[5 empty] | 2019-10-21 | 94590.68 | 0 | 94590.68
[5 empty] | 2019-11-13 | 11767.26 | 0 | 11767.26
|  | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 800 | 0 | 800
[5 empty] | 2021-09-29 | 7360 | 0 | 7360
[5 empty] | 2024-07-01 | 0 | 170210 | 170210
|  |  |  | 2021-11-02 | 2021-11-08 | 9450 | 0 | 9450
|  | Floor Tech America (FTA) | Contractor |  |  | 12744.48 | 0 | 12744.48
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2022-09-14 | 40000 | 0 | 40000
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
|  | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 24160.2 | 0 | 24160.2
[5 empty] | 2021-10-01 | 18877.95 | 0 | 18877.95
[5 empty] | 2021-10-19 | 19695.11 | 0 | 19695.11
[5 empty] | 2024-05-03 | 0 | 182791.74 | 182791.74
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 225132.9 | 11849.1 | 236982
| Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 1050 | 0 | 1050
| Fire Alarm | Department of General Services (DGS) | DSA fees | 2021-08-25 | 2021-09-09 | 1290 | 0 | 1290
|  | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 780 | 0 | 780
|  | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 4850 | 0 | 4850
[5 empty] | 2021-03-24 | 2425 | 0 | 2425
[5 empty] | 2021-05-26 | 2425 | 0 | 2425
[5 empty] | 2021-09-09 | 1455 | 0 | 1455
[5 empty] | 2022-01-19 | 970 | 0 | 970
|  | Team Inspections | General inspection | 2020-10-22 | 2021-02-05 | 3060 | 0 | 3060
[5 empty] | 2021-02-09 | 6120 | 0 | 6120
[5 empty] | 2021-09-15 | 2570 | 0 | 2570
[5 empty] | 2022-10-22 | 0 | 500 | 500
|  | Telenet VOIP, Inc | Contractor |  |  | 214104.43 | 12468.65 | 226573.08
| Interim Housing | Suburban Water Systems | Fire flow testing | 2021-09-15 | 2021-09-27 | 0 | 0 | 0
|  | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 3096 | 0 | 3096
[5 empty] | 2021-10-19 | 1550.25 | 0 | 1550.25
[5 empty] | 2024-05-03 | 0 | 92753.75 | 92753.75
California Total | [5 empty] | 762691.62 | 470573.24 | 1233264.86
Cedarlane | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 167.96 | 0 | 167.96
[5 empty] | 2020-10-20 | 48.2 | 0 | 48.2
|  | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1300.32 | 0 | 1300.32
[5 empty] | 2019-10-15 | 27306.79 | 0 | 27306.79
|  |  | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 26352.28 | 0 | 26352.28
[5 empty] | 2021-03-04 | -2.74 | 0 | -2.74
|  |  |  | 2021-08-18 | 2022-02-08 | 2148.06 | 0 | 2148.06
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 33811.1 | 0 | 33811.1
[5 empty] | 2019-10-21 | 9016.29 | 0 | 9016.29
[5 empty] | 2019-10-22 | 234423.62 | 0 | 234423.62
|  |  | ViewSonic monitor(s) | 2020-12-02 | 2021-03-04 | 13871.18 | 0 | 13871.18
[5 empty] | 2021-04-09 | 40746.58 | 0 | 40746.58
|  |  |  | 2021-08-18 | 2022-02-08 | 4357.42 | 0 | 4357.42
|  |  | Web camera(s) | 2021-08-18 | 2022-02-08 | 175.21 | 0 | 175.21
|  | Camcor | Document camera(s) | 2020-12-02 | 2021-04-14 | 15519.98 | 0 | 15519.98
|  | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 766.5 | 0 | 766.5
|  | Culver Newlin | Furniture | 2021-01-28 | 2021-03-24 | 46391.14 | 0 | 46391.14
[5 empty] | 2021-04-19 | 5324.99 | 0 | 5324.99
[5 empty] | 2021-08-16 | 62853 | 0 | 62853
|  |  |  | 2021-04-29 | 2021-08-16 | 223009.81 | 0 | 223009.81
|  |  |  | 2021-05-10 | 2021-08-16 | 92964.9 | 0 | 92964.9
[5 empty] | 2021-09-30 | 3728.48 | 0 | 3728.48
|  |  |  | 2022-01-14 | 2023-01-14 | 0 | 28827.85 | 28827.85
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 9648.75 | 0 | 9648.75
[5 empty] | 2020-01-14 | 11572.5 | 0 | 11572.5
[5 empty] | 2020-04-01 | 18217.5 | 0 | 18217.5
[5 empty] | 2020-04-15 | 10562.5 | 0 | 10562.5
[5 empty] | 2020-05-28 | 10410 | 0 | 10410
[5 empty] | 2020-06-17 | 6977.5 | 0 | 6977.5
[5 empty] | 2020-07-27 | 14165 | 0 | 14165
[5 empty] | 2020-08-17 | 10209.09 | 0 | 10209.09
[5 empty] | 2020-10-13 | 9643.06 | 0 | 9643.06
[5 empty] | 2020-10-20 | 9136.35 | 0 | 9136.35
[5 empty] | 2020-12-18 | 18981.19 | 0 | 18981.19
[5 empty] | 2021-02-08 | 9411.62 | 0 | 9411.62
[5 empty] | 2021-04-05 | 6923.17 | 0 | 6923.17
[5 empty] | 2021-04-16 | 5862.68 | 0 | 5862.68
[5 empty] | 2021-05-25 | 9891.91 | 0 | 9891.91
[5 empty] | 2021-09-30 | 25487.18 | 0 | 25487.18
[5 empty] | 2022-10-10 | 0 | 22 | 22
|  | David M Bertino Mfg | Furniture | 2021-11-09 | 2022-01-11 | 3858.78 | 0 | 3858.78
|  | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 9695.45 | 0 | 9695.45
|  | Division of the State Architect (DSA) | DSA fees | 2020-04-13 | 2020-04-24 | 22159 | 0 | 22159
|  | Graybar | Door hardware | 2021-06-16 | 2021-08-30 | 376.36 | 0 | 376.36
[5 empty] | 2021-09-23 | 358.62 | 0 | 358.62
[5 empty] | 2022-03-15 | 101.99 | 0 | 101.99
|  | ICS Service Co. | Contractor |  |  | 2332.6 | 0 | 2332.6
|  |  | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 3219.62 | 0 | 3219.62
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  |  |  | 2020-12-16 | 2021-04-16 | 39663.86 | 0 | 39663.86
|  | Lightspeed | Voice amplification system | 2020-12-03 | 2021-04-13 | 45825.82 | 0 | 45825.82
|  | Martin Container | Rental of container(s) | 2021-02-10 | 2021-02-22 | 3328.8 | 0 | 3328.8
[5 empty] | 2021-09-09 | 394.2 | 0 | 394.2
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-10-13 | 2800 | 0 | 2800
|  |  | Oversight asbestos abatement | 2020-10-27 | 2021-02-04 | 6950 | 0 | 6950
[5 empty] | 2023-01-16 | 0 | 4850 | 4850
|  |  |  | 2021-01-27 | 2021-03-22 | 6950 | 0 | 6950
[5 empty] | 2023-01-27 | 0 | 500 | 500
|  |  |  | 2021-03-19 | 2021-04-16 | 4750 | 0 | 4750
[5 empty] | 2023-03-19 | 0 | 2200 | 2200
|  |  |  | 2021-05-06 | 2021-05-25 | 3050 | 0 | 3050
[5 empty] | 2021-09-08 | 2200 | 0 | 2200
[5 empty] | 2023-05-06 | 0 | 2300 | 2300
|  |  |  | 2021-06-07 | 2023-06-07 | 425 | 0 | 425
|  |  |  | 2021-08-10 | 2021-09-30 | 2200 | 0 | 2200
[5 empty] | 2023-08-10 | 0 | 400 | 400
|  | Masters Contracting Corp | Contractor |  |  | 2840500 | 149500 | 2990000
|  | PBK Architects | Architect | 2018-06-26 | 2018-10-12 | 2672 | 0 | 2672
[5 empty] | 2019-04-22 | 2672 | 0 | 2672
[5 empty] | 2019-10-10 | 21376 | 0 | 21376
[5 empty] | 2020-04-17 | 7481.6 | 0 | 7481.6
[5 empty] | 2020-06-22 | 45958.4 | 0 | 45958.4
[5 empty] | 2020-08-18 | 20770 | 0 | 20770
[5 empty] | 2020-10-13 | 2338 | 0 | 2338
[5 empty] | 2020-10-21 | 2672 | 0 | 2672
[5 empty] | 2021-02-05 | 3340 | 0 | 3340
[5 empty] | 2023-01-16 | 0 | 27286 | 27286
[5 empty] | 2022-01-25 | 11356 | 0 | 11356
[5 empty] | 2022-01-26 | 5678 | 0 | 5678
|  | PI Manufacturing Corp. | Computer cables | 2020-12-03 | 2021-02-10 | 1351.5 | 0 | 1351.5
|  | San Gabriel Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 301.67 | 0 | 301.67
|  | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 8640 | 0 | 8640
[5 empty] | 2021-04-19 | 8352 | 0 | 8352
[5 empty] | 2021-04-20 | 6624 | 0 | 6624
[5 empty] | 2021-06-09 | 6336 | 0 | 6336
[5 empty] | 2021-06-23 | 2880 | 0 | 2880
[5 empty] | 2021-09-09 | 3168 | 0 | 3168
[5 empty] | 2021-09-22 | 11520 | 0 | 11520
[5 empty] | 2021-10-22 | 6480 | 0 | 6480
[5 empty] | 2021-12-01 | 5760 | 0 | 5760
[5 empty] | 2025-07-11 | 0 | 24768 | 24768
[5 empty] | 2021-12-20 | 6048 | 0 | 6048
[5 empty] | 2022-01-12 | 3024 | 0 | 3024
|  | Warehouse | Boxes | 2020-10-20 | 2020-10-28 | 318.12 | 0 | 318.12
|  |  |  | 2021-01-14 | 2021-06-04 | 466.62 | 0 | 466.62
|  |  | Boxes & tapes | 2020-12-03 | 2020-12-08 | 484.13 | 0 | 484.13
|  |  |  | 2020-12-08 | 2020-12-10 | 484.13 | 0 | 484.13
|  |  |  | 2021-01-08 | 2021-01-12 | 795.26 | 0 | 795.26
|  |  | Paper towel dispenser | 2021-07-13 | 2021-07-22 | 918.52 | 0 | 918.52
|  |  | Soap dispensers | 2021-07-09 | 2021-07-12 | 0 | 0 | 0
| Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
| Fire Alarm | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-01-20 | 1290 | 0 | 1290
|  | Masek Consulting | Asbestos survey | 2020-04-13 | 2020-04-29 | 800 | 0 | 800
|  | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2375 | 0 | 2375
[5 empty] | 2021-02-05 | 1425 | 0 | 1425
[5 empty] | 2021-03-24 | 950 | 0 | 950
|  | Team Inspections | General inspection | 2020-02-07 | 2020-05-26 | 6185 | 0 | 6185
[5 empty] | 2020-10-14 | 2065 | 0 | 2065
|  | Telenet VOIP, Inc | Contractor |  |  | 101079.99 | 5320 | 106399.99
| Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-02-05 | 6702.5 | 0 | 6702.5
[5 empty] | 2021-04-19 | 1650 | 0 | 1650
[5 empty] | 2021-05-26 | 1732.5 | 0 | 1732.5
[5 empty] | 2021-09-15 | 232.5 | 0 | 232.5
[5 empty] | 2023-01-16 | 0 | 6602.5 | 6602.5
|  | Culver Newlin | Furniture | 2020-03-17 | 2020-12-18 | 20580.53 | 0 | 20580.53
[5 empty] | 2021-05-07 | 11760.3 | 0 | 11760.3
[5 empty] | 2021-05-25 | 2940.07 | 0 | 2940.07
|  | Division of the State Architect (DSA) | DSA fees | 2020-01-28 | 2020-01-31 | 3052.5 | 0 | 3052.5
|  | Masters Contracting Corp | Contractor |  |  | 783750 | 111990.41 | 895740.41
|  | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-02-18 | 218488.74 | 0 | 218488.74
[5 empty] | 2021-02-05 | 21300 | 0 | 21300
|  | PBK Architects | Architect | 2018-06-26 | 2018-10-12 | 1146.66 | 0 | 1146.66
[5 empty] | 2019-02-27 | 8313.29 | 0 | 8313.29
[5 empty] | 2019-05-23 | 15479.91 | 0 | 15479.91
[5 empty] | 2019-09-20 | 8500 | 0 | 8500
[5 empty] | 2019-10-01 | 9459.94 | 0 | 9459.94
[5 empty] | 2020-08-18 | 11679.99 | 0 | 11679.99
[5 empty] | 2021-02-05 | 286.66 | 0 | 286.66
[5 empty] | 2023-01-16 | 0 | 5833.3 | 5833.3
[5 empty] | 2022-01-26 | 16633.25 | 0 | 16633.25
|  | San Gabriel Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 301.66 | 0 | 301.66
|  | Suburban Water Systems | Deposit to construct (1) 6" public fire hydrant | 2019-11-25 | 2019-12-10 | 3000 | 0 | 3000
|  |  | Fire flow testing | 2019-04-16 | 2019-04-17 | 212 | 0 | 212
|  | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 5760 | 0 | 5760
[5 empty] | 2021-04-19 | 5904 | 0 | 5904
[5 empty] | 2021-04-20 | 3024 | 0 | 3024
Cedarlane Total | [5 empty] | 5531568.72 | 371600.06 | 5903168.78
Del Valle | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 20900.18 | 0 | 20900.18
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 129892.46 | 0 | 129892.46
|  | Floor Tech America (FTA) | Contractor |  |  | 6372.24 | 0 | 6372.24
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2020-11-30 | 42500 | 0 | 42500
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 41441.22 | 0 | 41441.22
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 316523.85 | 16659.15 | 333183
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 870 | 0 | 870
|  | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 7275 | 0 | 7275
[5 empty] | 2021-02-09 | 7275 | 0 | 7275
[5 empty] | 2021-03-24 | 7275 | 0 | 7275
[5 empty] | 2021-05-26 | 12125 | 0 | 12125
[5 empty] | 2021-06-23 | 1455 | 0 | 1455
[5 empty] | 2021-09-09 | 970 | 0 | 970
[5 empty] | 2025-10-20 | 0 | 12125 | 12125
Del Valle Total | [5 empty] | 597474.95 | 28784.15 | 626259.1
Dibble | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 2700 | 0 | 2700
Dibble Total | [5 empty] | 2700 | 0 | 2700
District Office | 21st Century | ARC Document Solutions | Scanning/printing | 2019-05-13 | 2019-06-03 | 229.19 | 0 | 229.19
|  |  |  | 2020-10-05 | 2023-01-16 | 0 | 4037.85 | 4037.85
|  | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 19385.03 | 0 | 19385.03
[5 empty] | 2019-11-21 | 43729.02 | 0 | 43729.02
|  |  |  | 2020-02-07 | 2020-03-06 | 1349.45 | 0 | 1349.45
[5 empty] | 2020-04-23 | 1349.45 | 0 | 1349.45
|  | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 56459.52 | 0 | 56459.52
[5 empty] | 2019-10-08 | 312057.91 | 0 | 312057.91
|  | Culver Newlin | Furniture | 2020-03-17 | 2020-06-17 | 76394.76 | 0 | 76394.76
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-14 | 3840 | 0 | 3840
[5 empty] | 2020-04-01 | 27200 | 0 | 27200
[5 empty] | 2020-04-15 | 11535 | 0 | 11535
[5 empty] | 2020-05-28 | 12325 | 0 | 12325
[5 empty] | 2020-06-17 | 11885 | 0 | 11885
[5 empty] | 2020-07-27 | 22090 | 0 | 22090
[5 empty] | 2020-08-17 | 18080 | 0 | 18080
[5 empty] | 2020-10-13 | 19265 | 0 | 19265
[5 empty] | 2020-10-20 | 14080 | 0 | 14080
[5 empty] | 2020-12-17 | 46945 | 0 | 46945
[5 empty] | 2021-02-08 | 27150 | 0 | 27150
[5 empty] | 2021-04-05 | 34605 | 0 | 34605
[5 empty] | 2021-04-16 | 38455 | 0 | 38455
[5 empty] | 2021-05-07 | 46550 | 0 | 46550
[5 empty] | 2021-05-25 | 41875 | 0 | 41875
[5 empty] | 2021-06-22 | 37625 | 0 | 37625
[5 empty] | 2021-09-08 | 11520 | 0 | 11520
[5 empty] | 2021-09-09 | 24960 | 0 | 24960
[5 empty] | 2022-10-10 | 0 | 15 | 15
|  |  |  | 2022-02-09 | 2026-02-09 | 0 | 249080 | 249080
[5 empty] | 2022-02-28 | 25600 | 0 | 25600
[5 empty] | 2022-03-15 | 25320 | 0 | 25320
|  | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 1886.36 | 0 | 1886.36
|  | Fagen Friedman & Fulfrost LLP | Attorney fees | 2017-07-11 | 2017-12-19 | 1064 | 0 | 1064
|  |  |  | 2018-07-11 | 2019-04-09 | 2375 | 0 | 2375
|  |  |  | 2019-07-11 | 2019-08-28 | 3235 | 0 | 3235
[5 empty] | 2019-09-18 | 1387.5 | 0 | 1387.5
[5 empty] | 2020-01-03 | 5287.5 | 0 | 5287.5
[5 empty] | 2019-08-21 | 90 | 0 | 90
|  |  |  | 2020-03-10 | 2020-04-29 | 6906.81 | 0 | 6906.81
[5 empty] | 2020-06-30 | 13093.19 | 0 | 13093.19
[5 empty] | 2020-07-01 | -13093.19 | 0 | -13093.19
[5 empty] | 2020-07-02 | 0 | 13093.19 | 13093.19
[5 empty] | 2021-06-30 | 0 | -13093.19 | -13093.19
|  |  |  | 2020-07-31 | 2022-07-31 | 0 | 34922.5 | 34922.5
[5 empty] | 2021-12-14 | 1417.5 | 0 | 1417.5
[5 empty] | 2021-12-23 | 1799.5 | 0 | 1799.5
[5 empty] | 2022-01-24 | 5735 | 0 | 5735
[5 empty] | 2022-01-28 | 3513 | 0 | 3513
[5 empty] | 2022-03-02 | 2612.5 | 0 | 2612.5
|  |  |  | 2019-12-30 | 2020-01-03 | 7283.51 | 0 | 7283.51
[5 empty] | 2020-01-08 | 2112.68 | 0 | 2112.68
[5 empty] | 2020-01-13 | 10128 | 0 | 10128
[5 empty] | 2020-03-03 | 31.62 | 0 | 31.62
[5 empty] | 2020-04-29 | 444.19 | -5.1159e-13 | 444.19
|  | Floor Tech America (FTA) | Contractor |  |  | 259042.4 | 19116.72 | 278159.12
|  | Global Industrial | Scissor lift | 2021-05-18 | 2021-06-03 | 1665.5 | 0 | 1665.5
|  | Home Depot | Hardware to install access point for classrooms | 2020-05-18 | 2020-06-17 | 198.23 | 0 | 198.23
|  | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-01-29 | 2020-02-27 | 3492.5 | 0 | 3492.5
|  |  |  | 2020-02-26 | 2020-03-04 | 4647.5 | 0 | 4647.5
[5 empty] | 2020-04-07 | 2286.63 | 0 | 2286.63
[5 empty] | 2020-04-22 | 1799 | 0 | 1799
[5 empty] | 2020-06-30 | 1266.87 | 0 | 1266.87
[5 empty] | 2020-07-01 | -1266.87 | 0 | -1266.87
[5 empty] | 2020-07-02 | 0 | 1266.87 | 1266.87
[5 empty] | 2021-06-30 | 0 | -1266.87 | -1266.87
|  | San Gabriel Tribune | Newspaper Advertisement | 2020-08-11 | 2020-10-22 | 632 | 0 | 632
|  | Uline | Carts | 2020-12-01 | 2020-12-08 | 791.69 | 0 | 791.69
|  |  | Hydraulic stacker | 2021-05-27 | 2021-06-04 | 1834.13 | 0 | 1834.13
|  |  |  | 2021-06-08 | 2021-06-15 | 1834.13 | 0 | 1834.13
|  | Megaphone Ink | Decal | 2022-01-06 | 2022-01-24 | 455.52 | 0 | 455.52
|  | Southern California News Group | Newspaper Advertisement | 2022-03-15 | 2023-03-15 | 0 | 611.25 | 611.25
| Cost of Issuance | Avia Communications, Inc. | Printing & posting of POS/Os | 2017-07-11 | 2017-07-11 | 1350.74 | 0 | 1350.74
|  | California Municipal Statistics, Inc. | Demographic data | 2017-07-11 | 2017-07-11 | 1700 | 0 | 1700
|  | Fitch Ratings, Inc. | Rating Agency Fee | 2017-08-03 | 2017-08-03 | 45000 | 0 | 45000
|  | Hawkins Delafield & Wood LLP | Bond Counsel and Disclosure Counsel Fees | 2017-07-11 | 2017-07-11 | 115000 | 0 | 115000
|  | LACOE | Remaining funds-dep. into District's debt service fund & close acct. | 2017-12-14 | 2017-12-14 | 11211.58 | 0 | 11211.58
|  | Montague DeRose and Associates, LLC | Municipal Advisory services | 2017-07-12 | 2017-07-12 | 42740 | 0 | 42740
|  | Moody's Investors Service, Inc. | Rating Agency Fee | 2017-07-31 | 2017-07-31 | 37000 | 0 | 37000
|  | Rbc Capital Markets, LLC | Hotel reimb. during rating agency presentations in San Francisco | 2017-07-11 | 2017-07-11 | 647.68 | 0 | 647.68
|  |  | Reimb. Continuing Disclosure Report (DAC) | 2017-08-04 | 2017-08-04 | 550 | 0 | 550
|  | S&P Global Ratings | Rating Agency Fee | 2017-08-03 | 2017-08-03 | 35000 | 0 | 35000
|  | U.S. Bank National Association | Trust fees | 2017-07-12 | 2017-07-12 | 550 | 0 | 550
|  | Underwriter's fees | Underwriter's fees | 2017-07-12 | 2017-07-12 | 175000 | 0 | 175000
| Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2018-09-17 | 16080 | 0 | 16080
[5 empty] | 2018-10-19 | 6720 | 0 | 6720
[5 empty] | 2021-06-02 | 1200 | 0 | 1200
[5 empty] | 2023-01-16 | 0 | 5500 | 5500
District Office Total | [5 empty] | 1837598.23 | 313283.32 | 2150881.55
Fairgrove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1306.26 | 0 | 1306.26
[5 empty] | 2019-10-11 | 43106.72 | 0 | 43106.72
[5 empty] | 2019-10-15 | 2612.43 | 0 | 2612.43
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 35754.36 | 0 | 35754.36
[5 empty] | 2019-10-21 | 20366.42 | 0 | 20366.42
[5 empty] | 2019-10-22 | 346229.06 | 0 | 346229.06
|  | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 1440 | 0 | 1440
[5 empty] | 2021-09-29 | 5120 | 0 | 5120
[5 empty] | 2024-07-01 | 0 | 400194 | 400194
|  |  |  | 2021-11-02 | 2021-11-08 | 6450 | 0 | 6450
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 41441.21 | 0 | 41441.21
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2700 | 0 | 2700
|  | PBK Architects | Architect | 2021-05-03 | 2024-05-03 | 0 | 407500 | 407500
| Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 1230 | 0 | 1230
|  | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 4850 | 0 | 4850
[5 empty] | 2021-05-26 | 4850 | 0 | 4850
[5 empty] | 2021-09-09 | 1455 | 0 | 1455
[5 empty] | 2023-07-31 | 0 | 970 | 970
|  | Team Inspections | General inspection | 2021-01-14 | 2021-10-19 | 14350 | 0 | 14350
|  | Telenet VOIP, Inc | Contractor |  |  | 375687.03 | 3048.76 | 378735.79
| Interim Housing | PBK Architects | Architect | 2021-05-03 | 2024-05-03 | 0 | 95400 | 95400
Fairgrove Total | [5 empty] | 908948.49 | 908312.76 | 1817261.25
Grandview | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 23405.82 | 0 | 23405.82
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 12172 | 0 | 12172
[5 empty] | 2019-10-21 | 9016.29 | 0 | 9016.29
[5 empty] | 2019-10-22 | 227661.4 | 0 | 227661.4
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 7143.75 | 0 | 7143.75
[5 empty] | 2020-01-14 | 11325 | 0 | 11325
[5 empty] | 2020-04-01 | 16377.5 | 0 | 16377.5
[5 empty] | 2020-04-15 | 7442.5 | 0 | 7442.5
[5 empty] | 2020-05-28 | 9460 | 0 | 9460
[5 empty] | 2020-06-17 | 7020 | 0 | 7020
[5 empty] | 2020-07-27 | 3765 | 0 | 3765
[5 empty] | 2020-08-17 | 12733.4 | 0 | 12733.4
[5 empty] | 2020-10-13 | 12027.42 | 0 | 12027.42
[5 empty] | 2020-10-20 | 11395.42 | 0 | 11395.42
[5 empty] | 2020-12-18 | 23674.52 | 0 | 23674.52
[5 empty] | 2021-02-08 | 11738.76 | 0 | 11738.76
[5 empty] | 2021-04-05 | 8635.01 | 0 | 8635.01
[5 empty] | 2021-04-16 | 7312.3 | 0 | 7312.3
[5 empty] | 2021-05-25 | 12337.8 | 0 | 12337.8
[5 empty] | 2021-06-22 | 9920 | 0 | 9920
[5 empty] | 2021-09-08 | 4160 | 0 | 4160
[5 empty] | 2021-09-09 | 6240 | 0 | 6240
[5 empty] | 2022-10-10 | 0 | 7410 | 7410
[5 empty] | 2022-03-15 | 4086.62 | 0 | 4086.62
|  | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 35235.88 | 0 | 35235.88
|  | Education Products & Services | White board(s) | 2019-09-16 | 2019-09-25 | 1464.78 | 0 | 1464.78
|  | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2018-07-24 | 2800 | 0 | 2800
[5 empty] | 2019-02-19 | 10110 | 0 | 10110
[5 empty] | 2019-09-16 | 15400 | 0 | 15400
[5 empty] | 2020-02-13 | 19600 | 0 | 19600
[5 empty] | 2020-06-04 | 23100 | 0 | 23100
[5 empty] | 2020-12-08 | 17221 | 0 | 17221
[5 empty] | 2021-05-07 | 23100 | 0 | 23100
[5 empty] | 2021-06-23 | 3500 | 0 | 3500
[5 empty] | 2023-01-16 | 0 | 63119 | 63119
[5 empty] | 2021-12-20 | 1050 | 0 | 1050
|  |  |  | 2020-08-07 | 2020-12-08 | 81300 | 0 | 81300
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2900 | 0 | 2900
|  | Uline | Furniture | 2019-07-01 | 2019-07-30 | 8041.68 | 0 | 8041.68
| Fire Alarm | Department of General Services (DGS) | DSA fees | 2021-07-21 | 2021-08-04 | 1451.25 | 0 | 1451.25
|  | Masek Consulting | Asbestos survey | 2020-04-13 | 2020-04-29 | 850 | 0 | 850
|  | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2375 | 0 | 2375
[5 empty] | 2021-01-07 | 2375 | 0 | 2375
[5 empty] | 2021-03-24 | 4750 | 0 | 4750
[5 empty] | 2021-09-09 | 1425 | 0 | 1425
[5 empty] | 2021-11-17 | 950 | 0 | 950
|  | Team Inspections | General inspection | 2019-11-26 | 2020-05-26 | 2345 | 0 | 2345
[5 empty] | 2020-06-19 | 2345 | 0 | 2345
[5 empty] | 2020-10-14 | 2345 | 0 | 2345
[5 empty] | 2021-09-13 | 1840 | 0 | 1840
[5 empty] | 2023-07-31 | 0 | 500 | 500
|  | Telenet VOIP, Inc | Contractor |  |  | 138358.1 | 8282.01 | 146640.11
Grandview Total | [5 empty] | 886003.81 | 79311.01 | 965314.82
Grazide | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 13003.23 | 0 | 13003.23
[5 empty] | 2019-10-08 | 16904.22 | 0 | 16904.22
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 157334.31 | 0 | 157334.31
|  | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 800 | 0 | 800
[5 empty] | 2021-09-29 | 3960 | 0 | 3960
[5 empty] | 2024-07-01 | 0 | 196192 | 196192
|  |  |  | 2021-11-02 | 2021-11-08 | 5650 | 0 | 5650
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2023-01-06 | 37500 | 0 | 37500
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2550 | 0 | 2550
|  | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 24121.52 | 0 | 24121.52
[5 empty] | 2021-10-19 | 8978.93 | 0 | 8978.93
[5 empty] | 2024-05-03 | 0 | 211457.55 | 211457.55
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 267518.1 | 14079.9 | 281598
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 960 | 0 | 960
|  | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 0 | 12125 | 12125
| Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 0 | 79400 | 79400
Grazide Total | [5 empty] | 539280.31 | 513254.45 | 1052534.76
Kwis | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 10402.58 | 0 | 10402.58
[5 empty] | 2019-10-08 | 9102.26 | 0 | 9102.26
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 99630.05 | 0 | 99630.05
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-04-06 | 2021-05-26 | 42500 | 0 | 42500
|  |  |  | 2021-06-14 | 2021-09-09 | 6500 | 0 | 6500
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 38238.17 | 0 | 38238.17
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 257476.6 | 13551.4 | 271028
| Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 891 | 0 | 891
|  | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 7275 | 0 | 7275
[5 empty] | 2021-02-09 | 7275 | 0 | 7275
[5 empty] | 2021-03-24 | 7275 | 0 | 7275
[5 empty] | 2021-05-26 | 12125 | 0 | 12125
[5 empty] | 2021-06-23 | 1455 | 0 | 1455
[5 empty] | 2021-09-09 | 970 | 0 | 970
[5 empty] | 2025-10-20 | 0 | 12125 | 12125
Kwis Total | [5 empty] | 503715.66 | 26876.4 | 530592.06
La Puente HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1306.26 | 0 | 1306.26
[5 empty] | 2019-10-08 | 39187.83 | 0 | 39187.83
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 464806.85 | 0 | 464806.85
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2021-03-23 | 6900 | 0 | 6900
| Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
| Fire Alarm | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 0 | 14700 | 14700
|  | Telenet VOIP, Inc | Contractor |  |  | 2717.95 | 0 | 2717.95
La Puente HS Total | [5 empty] | 514918.89 | 15900 | 530818.89
Lassalette | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 20900.19 | 0 | 20900.19
[5 empty] | 2019-11-07 | 11756.35 | 0 | 11756.35
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 210452.96 | 0 | 210452.96
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2800 | 0 | 2800
| Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 0 | 0 | 0
|  | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 0 | 12375 | 12375
Lassalette Total | [5 empty] | 266630.11 | 13575 | 280205.11
Los Altos ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 728.6 | 0 | 728.6
|  | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 27306.79 | 0 | 27306.79
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 9917.92 | 0 | 9917.92
[5 empty] | 2019-10-22 | 132990.32 | 0 | 132990.32
|  |  | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 43694.21 | 0 | 43694.21
|  | Camcor | Document camera(s) | 2020-07-01 | 2020-07-16 | 11954.12 | 0 | 11954.12
|  | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 643.86 | 0 | 643.86
|  | Converse Consultants | Geotechnical | 2020-06-05 | 2020-08-17 | 779.5 | 0 | 779.5
[5 empty] | 2020-12-04 | 342.5 | 0 | 342.5
[5 empty] | 2021-02-05 | 1153.5 | 0 | 1153.5
[5 empty] | 2021-03-24 | 9223.5 | 0 | 9223.5
[5 empty] | 2021-04-19 | 880 | 0 | 880
[5 empty] | 2023-07-31 | 0 | 11301 | 11301
|  |  | Masonry inspection | 2020-10-28 | 2021-09-09 | 2537.5 | 0 | 2537.5
|  | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 156387.52 | 0 | 156387.52
[5 empty] | 2021-05-25 | 192.72 | 0 | 192.72
|  |  |  | 2020-11-06 | 2021-02-09 | 169275.1 | 0 | 169275.1
|  |  |  | 2021-09-07 | 2021-11-16 | 983.31 | 0 | 983.31
[5 empty] | 2023-01-14 | 0 | 19218.56 | 19218.56
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 8571.25 | 0 | 8571.25
[5 empty] | 2020-01-14 | 12697.5 | 0 | 12697.5
[5 empty] | 2020-04-01 | 17397.5 | 0 | 17397.5
[5 empty] | 2020-04-15 | 12647.5 | 0 | 12647.5
[5 empty] | 2020-05-28 | 9337.5 | 0 | 9337.5
[5 empty] | 2020-06-17 | 9947.5 | 0 | 9947.5
[5 empty] | 2020-07-27 | 13287.5 | 0 | 13287.5
[5 empty] | 2020-08-17 | 5953.78 | 0 | 5953.78
[5 empty] | 2020-10-13 | 5623.68 | 0 | 5623.68
[5 empty] | 2020-10-20 | 5328.17 | 0 | 5328.17
[5 empty] | 2020-12-18 | 11069.53 | 0 | 11069.53
[5 empty] | 2021-02-08 | 5488.71 | 0 | 5488.71
[5 empty] | 2021-04-05 | 4037.49 | 0 | 4037.49
[5 empty] | 2021-04-16 | 3419.03 | 0 | 3419.03
[5 empty] | 2021-05-25 | 5768.8 | 0 | 5768.8
[5 empty] | 2021-09-30 | 11952.82 | 0 | 11952.82
[5 empty] | 2021-10-18 | 2897.99 | 0 | 2897.99
[5 empty] | 2022-10-10 | 0 | 25.75 | 25.75
|  | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 9695.44 | 0 | 9695.44
|  | Department of General Services (DGS) | DSA fees | 2021-12-15 | 2022-01-06 | 15210.87 | 0 | 15210.87
|  | Division of the State Architect (DSA) | DSA fees | 2019-06-11 | 2019-06-19 | 14918.24 | 0 | 14918.24
|  | GDL Best Contractors, Inc | Contractor |  |  | 21696 | 0 | 21696
|  | Graybar | Door hardware | 2020-12-14 | 2021-02-08 | 246.82 | 0 | 246.82
|  | ICS Service Co. | Contractor |  |  | 130.8 | 0 | 130.8
|  |  | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2530.58 | 0 | 2530.58
|  | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-06-05 | 2020-08-18 | 18000 | 0 | 18000
|  |  |  | 2020-07-06 | 2020-10-13 | 32000 | 0 | 32000
|  |  | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 45000 | 0 | 45000
|  | Integrated Pest Control Management | Termite service | 2020-08-07 | 2020-08-24 | 785 | 0 | 785
|  | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-02-17 | 59495.79 | 0 | 59495.79
|  | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 1401.61 | 0 | 1401.61
[5 empty] | 2020-08-05 | 19688.1 | 0 | 19688.1
|  | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 39485.7 | 0 | 39485.7
|  | Martin Container | Rental of container(s) | 2020-05-06 | 2020-07-01 | 1971 | 0 | 1971
[5 empty] | 2021-06-30 | 1357.8 | 0 | 1357.8
|  |  |  | 2020-06-03 | 2020-08-18 | 1664.4 | 0 | 1664.4
|  |  |  | 2020-07-06 | 2020-08-17 | 1664.4 | 0 | 1664.4
[5 empty] | 2020-10-13 | 1664.4 | 0 | 1664.4
|  |  |  | 2021-02-10 | 2021-02-22 | 958.13 | 0 | 958.13
[5 empty] | 2021-03-24 | 958.11 | 0 | 958.11
[5 empty] | 2021-05-26 | 684.37 | 0 | 684.37
[5 empty] | 2021-06-23 | 958.13 | 0 | 958.13
[5 empty] | 2021-06-30 | 136.87 | 0 | 136.87
[5 empty] | 2021-09-09 | 958.13 | 0 | 958.13
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2800 | 0 | 2800
|  |  | Oversight asbestos abatement | 2020-07-06 | 2020-08-17 | 7775 | 0 | 7775
[5 empty] | 2023-01-16 | 0 | 6125 | 6125
|  | Masters Contracting Corp | Contractor |  |  | 2106113.2 | 114886.8 | 2221000
|  | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 1086.6 | 0 | 1086.6
|  | TDM Architects, Inc | Architect | 2018-07-17 | 2018-10-11 | 3514.68 | 0 | 3514.68
[5 empty] | 2019-01-28 | 3712 | 0 | 3712
[5 empty] | 2019-09-05 | 20209.46 | 0 | 20209.46
[5 empty] | 2019-09-13 | 28996.18 | 0 | 28996.18
[5 empty] | 2020-06-04 | 8786.73 | 0 | 8786.73
[5 empty] | 2021-02-05 | 18708.97 | 0 | 18708.97
[5 empty] | 2021-04-19 | 4393.35 | 0 | 4393.35
[5 empty] | 2021-12-20 | 4393.35 | 0 | 4393.35
|  |  |  | 2020-05-11 | 2020-10-21 | 12980 | 0 | 12980
|  | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 4410 | 0 | 4410
[5 empty] | 2020-08-19 | 6440 | 0 | 6440
[5 empty] | 2020-10-14 | 5880 | 0 | 5880
[5 empty] | 2020-10-21 | 5880 | 0 | 5880
[5 empty] | 2021-02-05 | 3080 | 0 | 3080
[5 empty] | 2021-03-24 | 2030 | 0 | 2030
[5 empty] | 2021-04-19 | 7000 | 0 | 7000
|  | Warehouse | Paper towel dispenser | 2021-09-01 | 2021-09-03 | 86.19 | 0 | 86.19
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 220694.5 | 11615.5 | 232310
| Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 1050 | 0 | 1050
| Fire Alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 7125 | 0 | 7125
[5 empty] | 2021-05-26 | 2375 | 0 | 2375
[5 empty] | 2021-09-09 | 1425 | 0 | 1425
[5 empty] | 2022-01-19 | 950 | 0 | 950
|  | Team Inspections | General inspection | 2020-12-15 | 2021-02-09 | 3060 | 0 | 3060
[5 empty] | 2021-04-19 | 6120 | 0 | 6120
[5 empty] | 2021-09-09 | 500 | 0 | 500
[5 empty] | 2021-09-13 | 2570 | 0 | 2570
|  | Telenet VOIP, Inc | Contractor |  |  | 100917.1 | 6311.43 | 107228.53
| Interim Housing | Converse Consultants | Geotechnical | 2019-07-01 | 2019-12-11 | 5280.5 | 0 | 5280.5
[5 empty] | 2023-01-16 | 0 | 9249.5 | 9249.5
|  | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 2450.06 | 0 | 2450.06
[5 empty] | 2021-05-25 | 8036.2 | 0 | 8036.2
|  | Division of the State Architect (DSA) | DSA fees | 2019-03-18 | 2019-03-21 | 3481.54 | 0 | 3481.54
|  |  |  | 2020-03-06 | 2020-03-11 | 2687.5 | 0 | 2687.5
|  | Education Products & Services | Contractor |  |  | 1894.88 | 0 | 1894.88
|  | GDL Best Contractors, Inc | Contractor |  |  | 220500 | 0 | 220500
|  | Mijac Alarm | Alarm for portables | 2019-10-01 | 2019-11-05 | 79.5 | 0 | 79.5
[5 empty] | 2020-01-14 | 79.5 | 0 | 79.5
[5 empty] | 2020-04-07 | 79.5 | 0 | 79.5
[5 empty] | 2020-08-17 | 79.5 | 0 | 79.5
[5 empty] | 2020-10-13 | 79.5 | 0 | 79.5
[5 empty] | 2021-01-15 | 79.5 | 0 | 79.5
[5 empty] | 2021-04-16 | 79.5 | 0 | 79.5
[5 empty] | 2021-11-30 | 159 | 0 | 159
|  | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-01-16 | 236959.74 | 0 | 236959.74
|  | TDM Architects, Inc | Architect | 2018-07-17 | 2018-11-20 | 1515.6 | 0 | 1515.6
[5 empty] | 2019-02-06 | 3410.12 | 0 | 3410.12
[5 empty] | 2019-03-28 | 4774.16 | 0 | 4774.16
[5 empty] | 2019-09-05 | 14928.74 | 0 | 14928.74
[5 empty] | 2019-11-15 | 2816 | 0 | 2816
[5 empty] | 2019-12-11 | 9472.55 | 0 | 9472.55
[5 empty] | 2020-06-04 | 3789.01 | 0 | 3789.01
[5 empty] | 2023-07-11 | 0 | 17184 | 17184
|  | Team Inspections | General inspection | 2019-07-01 | 2019-12-11 | 9900 | 0 | 9900
[5 empty] | 2020-01-15 | 3300 | 0 | 3300
|  | Universal Asphalt | Contractor |  |  | 32557 | 0 | 32557
|  | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2026-01-16 | 0 | 2782.5 | 2782.5
Los Altos ES Total | [5 empty] | 4181209.32 | 198700.04 | 4379909.36
Los Altos HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1300.32 | 0 | 1300.32
[5 empty] | 2019-11-07 | 55913.91 | 0 | 55913.91
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 725360.76 | 0 | 725360.76
|  | Floor Tech America (FTA) | Contractor |  |  | 19116.72 | 0 | 19116.72
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2021-01-19 | 4350 | 0 | 4350
| Drinking fountain replacement | Optima | Contractor |  |  | 6600 | 0 | 6600
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 5500 | 0 | 5500
|  | tBP Architecture | Architect | 2018-07-01 | 2023-07-31 | 0 | 13950 | 13950
Los Altos HS Total | [5 empty] | 818141.71 | 13950 | 832091.71
Los Molinos | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 28607.12 | 0 | 28607.12
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 10368.74 | 0 | 10368.74
[5 empty] | 2019-10-22 | 110449.59 | 0 | 110449.59
|  | Culver Newlin | Furniture | 2019-10-22 | 2020-04-15 | 21169.42 | 0 | 21169.42
|  | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 960 | 0 | 960
[5 empty] | 2021-09-29 | 4280 | 0 | 4280
[5 empty] | 2024-07-01 | 0 | 270840 | 270840
|  |  |  | 2021-11-02 | 2021-11-08 | 5650 | 0 | 5650
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2023-01-06 | 37500 | 0 | 37500
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
|  | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 25060.16 | 0 | 25060.16
[5 empty] | 2021-10-19 | 8326.87 | 0 | 8326.87
[5 empty] | 2024-05-03 | 0 | 234636.97 | 234636.97
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 341083.25 | 17951.75 | 359035
| Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-05-05 | 1050 | 0 | 1050
| Fire Alarm | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-02-08 | 422.21 | 0 | 422.21
|  | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 870 | 0 | 870
|  | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 4850 | 0 | 4850
[5 empty] | 2021-05-26 | 4850 | 0 | 4850
[5 empty] | 2021-09-09 | 1455 | 0 | 1455
[5 empty] | 2023-07-31 | 0 | 970 | 970
|  | Team Inspections | General inspection | 2021-01-14 | 2021-10-19 | 14350 | 0 | 14350
|  | Telenet VOIP, Inc | Contractor |  |  | 178201.64 | 10713.12 | 188914.76
| Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 0 | 79400 | 79400
Los Molinos Total | [5 empty] | 802104 | 614511.84 | 1416615.84
Los Robles | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 13003.22 | 0 | 13003.22
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 4958.96 | 0 | 4958.96
[5 empty] | 2019-10-22 | 58605.9 | 0 | 58605.9
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-04-06 | 2021-05-26 | 40000 | 0 | 40000
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2800 | 0 | 2800
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 208408.15 | 10968.85 | 219377
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 900 | 0 | 900
|  | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 7275 | 0 | 7275
[5 empty] | 2021-02-09 | 7275 | 0 | 7275
[5 empty] | 2021-03-24 | 7275 | 0 | 7275
[5 empty] | 2021-05-26 | 12125 | 0 | 12125
[5 empty] | 2021-06-23 | 1455 | 0 | 1455
[5 empty] | 2021-09-09 | 970 | 0 | 970
[5 empty] | 2025-10-20 | 0 | 12125 | 12125
Los Robles Total | [5 empty] | 365051.23 | 23093.85 | 388145.08
Mesa Robles | 21st Century | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 167.95 | 0 | 167.95
[5 empty] | 2020-10-20 | 48.19 | 0 | 48.19
|  | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 48111.97 | 0 | 48111.97
|  |  | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 40055.44 | 0 | 40055.44
[5 empty] | 2021-03-04 | -4.16 | 0 | -4.16
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 20737.48 | 0 | 20737.48
[5 empty] | 2019-10-22 | 414749.48 | 0 | 414749.48
|  |  | ViewSonic monitor(s) | 2020-12-02 | 2021-03-04 | 21084.19 | 0 | 21084.19
[5 empty] | 2021-04-09 | 61934.82 | 0 | 61934.82
|  |  |  | 2021-06-14 | 2022-02-04 | 10923.55 | 0 | 10923.55
|  | Camcor | Document camera(s) | 2020-12-02 | 2021-04-14 | 23590.37 | 0 | 23590.37
|  | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 1226.4 | 0 | 1226.4
|  | Chalmers Construction Services, Inc. | Contractor |  |  | 3072707.95 | 161721.47 | 3234429.42
|  | Culver Newlin | Furniture | 2020-03-17 | 2021-05-07 | 233.02 | 0 | 233.02
|  |  |  | 2021-01-28 | 2021-03-23 | 25383.81 | 0 | 25383.81
[5 empty] | 2021-03-24 | 97823.29 | 0 | 97823.29
[5 empty] | 2021-04-19 | 15974.96 | 0 | 15974.96
[5 empty] | 2021-08-16 | 51252.57 | 0 | 51252.57
|  |  |  | 2021-04-29 | 2021-08-16 | 148553.31 | 0 | 148553.31
[5 empty] | 2021-09-30 | 6156.09 | 0 | 6156.09
|  |  |  | 2021-05-10 | 2021-08-16 | 309418.79 | 0 | 309418.79
|  |  |  | 2021-09-07 | 2022-01-24 | 40866.17 | 0 | 40866.17
|  |  |  | 2022-01-14 | 2023-01-14 | 0 | 44442.93 | 44442.93
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 9691.25 | 0 | 9691.25
[5 empty] | 2020-01-14 | 11627.5 | 0 | 11627.5
[5 empty] | 2020-04-01 | 20417.5 | 0 | 20417.5
[5 empty] | 2020-04-15 | 8200 | 0 | 8200
[5 empty] | 2020-05-28 | 12690 | 0 | 12690
[5 empty] | 2020-06-17 | 13470 | 0 | 13470
[5 empty] | 2020-07-27 | 15197.5 | 0 | 15197.5
[5 empty] | 2020-08-17 | 16815.75 | 0 | 16815.75
[5 empty] | 2020-10-13 | 15883.43 | 0 | 15883.43
[5 empty] | 2020-10-20 | 15048.8 | 0 | 15048.8
[5 empty] | 2020-12-18 | 31264.6 | 0 | 31264.6
[5 empty] | 2021-02-08 | 15502.22 | 0 | 15502.22
[5 empty] | 2021-04-05 | 11403.41 | 0 | 11403.41
[5 empty] | 2021-04-16 | 9656.64 | 0 | 9656.64
[5 empty] | 2021-05-25 | 16293.31 | 0 | 16293.31
[5 empty] | 2021-06-22 | 3520 | 0 | 3520
[5 empty] | 2021-09-09 | 160 | 0 | 160
[5 empty] | 2021-10-18 | 3182.01 | 0 | 3182.01
[5 empty] | 2022-10-10 | 0 | 85.25 | 85.25
[5 empty] | 2021-12-13 | 1280 | 0 | 1280
[5 empty] | 2022-01-24 | 13920 | 0 | 13920
[5 empty] | 2022-02-11 | 19869.83 | 0 | 19869.83
|  | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 33934.03 | 0 | 33934.03
|  | Division of the State Architect (DSA) | DSA fees | 2020-04-13 | 2020-04-24 | 28009 | 0 | 28009
|  | Graybar | Door hardware | 2021-06-16 | 2021-08-30 | 599.39 | 0 | 599.39
[5 empty] | 2021-09-23 | 571.14 | 0 | 571.14
[5 empty] | 2022-03-15 | 162.45 | 0 | 162.45
|  | Haul-Away Rubbish Service Co | Rental of container(s) | 2021-02-11 | 2021-02-22 | 125.17 | 0 | 125.17
|  | ICS Service Co. | Contractor |  |  | 479.6 | 0 | 479.6
|  |  | Equipment to repair & replace security system | 2021-04-22 | 2021-06-07 | 3426.33 | 0 | 3426.33
|  | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-05 | 79327.7 | 0 | 79327.7
|  | Lightspeed | Voice amplification system | 2021-05-19 | 2021-09-02 | 76987.31 | 0 | 76987.31
|  | Martin Container | Rental of container(s) | 2020-05-06 | 2020-07-01 | 985.5 | 0 | 985.5
[5 empty] | 2021-06-30 | 678.9 | 0 | 678.9
|  |  |  | 2020-10-22 | 2021-02-05 | 4993.2 | 0 | 4993.2
|  |  |  | 2021-02-10 | 2021-02-22 | 952.64 | 0 | 952.64
[5 empty] | 2021-03-24 | 667.94 | 0 | 667.94
[5 empty] | 2021-05-26 | 531.07 | 0 | 531.07
[5 empty] | 2021-06-23 | 1062.14 | 0 | 1062.14
[5 empty] | 2021-09-09 | 1850.54 | 0 | 1850.54
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2950 | 0 | 2950
|  |  |  | 2020-10-23 | 2021-02-04 | 1480 | 0 | 1480
|  |  | Oversight asbestos abatement | 2020-10-22 | 2021-02-04 | 4400 | 0 | 4400
[5 empty] | 2023-01-16 | 0 | 1600 | 1600
|  |  |  | 2021-01-27 | 2021-03-22 | 4400 | 0 | 4400
[5 empty] | 2023-01-27 | 0 | 4900 | 4900
|  |  |  | 2021-03-18 | 2021-04-16 | 7910 | 0 | 7910
[5 empty] | 2023-03-18 | 0 | 1440 | 1440
|  |  |  | 2021-06-07 | 2023-06-07 | 850 | 0 | 850
|  | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-06-28 | 4007.97 | 0 | 4007.97
[5 empty] | 2018-07-17 | 4007.97 | 0 | 4007.97
|  |  |  | 2018-07-01 | 2019-02-26 | 7100 | 0 | 7100
[5 empty] | 2019-10-28 | 411.5 | 0 | 411.5
|  | PBK Architects | Architect | 2019-07-01 | 2020-04-02 | 45600 | 0 | 45600
[5 empty] | 2020-04-17 | 12768 | 0 | 12768
[5 empty] | 2020-06-18 | 78432 | 0 | 78432
[5 empty] | 2020-08-18 | 2850 | 0 | 2850
[5 empty] | 2020-10-13 | 3990 | 0 | 3990
[5 empty] | 2021-02-05 | 4560 | 0 | 4560
[5 empty] | 2025-01-16 | 0 | 38240 | 38240
[5 empty] | 2022-01-25 | 61560 | 0 | 61560
|  | PI Manufacturing Corp. | Computer cables | 2020-12-03 | 2021-02-17 | 1710.17 | 0 | 1710.17
[5 empty] | 2021-06-24 | 436.91 | 0 | 436.91
|  | San Gabriel Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 301.67 | 0 | 301.67
|  | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 8640 | 0 | 8640
[5 empty] | 2021-04-19 | 11664 | 0 | 11664
[5 empty] | 2021-04-20 | 3600 | 0 | 3600
[5 empty] | 2021-05-26 | 6336 | 0 | 6336
[5 empty] | 2021-06-23 | 8640 | 0 | 8640
[5 empty] | 2021-09-09 | 18576 | 0 | 18576
[5 empty] | 2021-09-22 | 288 | 0 | 288
[5 empty] | 2025-07-11 | 0 | 35856 | 35856
|  | Warehouse | Boxes | 2020-10-20 | 2020-10-28 | 265.1 | 0 | 265.1
[5 empty] | 2020-11-17 | 180.27 | 0 | 180.27
|  |  |  | 2021-02-04 | 2021-02-10 | 648.09 | 0 | 648.09
|  |  | Boxes & tapes | 2020-12-08 | 2020-12-10 | 759.34 | 0 | 759.34
|  | Wolverine Fence | Contractor |  |  | 5000 | 0 | 5000
| Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 1050 | 0 | 1050
|  | Optima | Contractor |  |  | 11000 | 0 | 11000
| Fire Alarm | Department of General Services (DGS) | DSA fees | 2021-07-21 | 2021-08-04 | 1720 | 0 | 1720
|  | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2375 | 0 | 2375
[5 empty] | 2021-02-05 | 2375 | 0 | 2375
[5 empty] | 2021-03-24 | 4750 | 0 | 4750
[5 empty] | 2021-09-09 | 1425 | 0 | 1425
[5 empty] | 2021-12-10 | 950 | 0 | 950
|  | Team Inspections | General inspection | 2020-05-13 | 2020-08-19 | 2065 | 0 | 2065
[5 empty] | 2020-10-14 | 2065 | 0 | 2065
[5 empty] | 2020-10-21 | 2065 | 0 | 2065
[5 empty] | 2021-09-13 | 2055 | 0 | 2055
|  | Telenet VOIP, Inc | Contractor |  |  | 139057.13 | 7736.48 | 146793.61
| Interim Housing | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-06-17 | 1661.08 | 0 | 1661.08
|  | Converse Consultants | Geotechnical | 2020-02-13 | 2020-06-22 | 7782.5 | 0 | 7782.5
[5 empty] | 2020-10-13 | 1050.5 | 0 | 1050.5
[5 empty] | 2021-04-19 | 1052.5 | 0 | 1052.5
[5 empty] | 2021-09-09 | 1445 | 0 | 1445
[5 empty] | 2023-01-16 | 0 | 2209.5 | 2209.5
|  | Culver Newlin | Furniture | 2020-03-17 | 2020-09-28 | 73150.29 | 0 | 73150.29
[5 empty] | 2021-05-07 | 12985.33 | 0 | 12985.33
[5 empty] | 2021-05-25 | 715.92 | 0 | 715.92
|  | Division of the State Architect (DSA) | DSA fees | 2019-10-22 | 2019-10-28 | 7425 | 0 | 7425
|  | GDL Best Contractors, Inc | Contractor |  |  | 773385.54 | 3.638e-11 | 773385.54
|  | Martin Container | Move containers | 2020-05-27 | 2020-06-23 | 500 | 0 | 500
|  | Masek Consulting | Pre-demo asbestos & lead-based paint | 2020-01-31 | 2020-06-03 | 1280 | 0 | 1280
|  | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-02-18 | 436977.48 | 0 | 436977.48
[5 empty] | 2020-08-18 | 42600 | 0 | 42600
|  | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-06-28 | 1286.49 | 0 | 1286.49
[5 empty] | 2018-07-17 | 1286.49 | 0 | 1286.49
|  |  |  | 2018-07-01 | 2019-10-28 | 3894.95 | 0 | 3894.95
|  | Suburban Water Systems | Deposit for engineering costs to construct (1) 6" public fire hydrant | 2019-03-08 | 2019-03-12 | 2000 | 0 | 2000
|  |  | Fire flow testing | 2019-01-09 | 2019-01-11 | 636 | 0 | 636
|  |  | Remaining balance to construct (1) 6" public fire hydrant | 2020-01-08 | 2020-01-16 | 39498.69 | 0 | 39498.69
|  | tBP Architecture | Architect | 2019-06-11 | 2019-08-22 | 26100 | 0 | 26100
[5 empty] | 2019-09-23 | 30450 | 0 | 30450
[5 empty] | 2020-01-15 | 8700 | 0 | 8700
[5 empty] | 2020-05-26 | 4350 | 0 | 4350
[5 empty] | 2020-06-19 | 4350 | 0 | 4350
[5 empty] | 2020-08-18 | 2610 | 0 | 2610
[5 empty] | 2020-10-14 | 6090 | 0 | 6090
[5 empty] | 2021-02-05 | 2610 | 0 | 2610
[5 empty] | 2021-10-01 | 1740 | 0 | 1740
|  | Team Inspections | General inspection | 2020-02-13 | 2020-06-19 | 19870 | 0 | 19870
[5 empty] | 2020-08-19 | 9935 | 0 | 9935
[5 empty] | 2020-10-14 | 5960 | 0 | 5960
[5 empty] | 2021-04-20 | 3975 | 0 | 3975
|  | Telenet VOIP, Inc | Contractor |  |  | 270103.06 | 14715.95 | 284819.01
|  | Universal Asphalt | Contractor |  |  | 106537.8 | 0 | 106537.8
|  | Wolverine Fence | Contractor |  |  | 25440 | 0 | 25440
Mesa Robles Total | [5 empty] | 7338143.18 | 312947.58 | 7651090.76
Nelson | 21st Century | Amazon | Wall plates | 2020-07-08 | 2020-07-21 | 64.06 | 0 | 64.06
|  | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-30 | 728.6 | 0 | 728.6
|  | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 23512.7 | 0 | 23512.7
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 9051.74 | 0 | 9051.74
[5 empty] | 2019-10-21 | 18103.47 | 0 | 18103.47
[5 empty] | 2019-10-22 | 99569.15 | 0 | 99569.15
|  |  | ViewSonic monitor(s) | 2020-06-05 | 2020-07-01 | 2184.71 | 0 | 2184.71
|  |  |  | 2020-07-01 | 2020-09-16 | 21946.59 | 0 | 21946.59
[5 empty] | 2020-10-01 | 32770.66 | 0 | 32770.66
|  | Camcor | Document camera(s) | 2020-07-01 | 2020-07-16 | 14942.64 | 0 | 14942.64
|  | CDW-G Government Inc. | Document camera(s) | 2020-07-01 | 2020-08-21 | 706.28 | 0 | 706.28
|  |  | Wall plates | 2020-12-09 | 2021-03-05 | 613.2 | 0 | 613.2
|  | Converse Consultants | Geotechnical | 2020-06-05 | 2021-02-05 | 1117.5 | 0 | 1117.5
[5 empty] | 2023-07-31 | 0 | 19732.5 | 19732.5
|  |  | Masonry inspection | 2020-10-28 | 2021-10-01 | 5787.5 | 0 | 5787.5
|  | Culver Newlin | Furniture | 2020-03-17 | 2020-08-24 | 109597.17 | 0 | 109597.17
[5 empty] | 2021-05-07 | 28994.79 | 0 | 28994.79
[5 empty] | 2021-05-25 | 192.72 | 0 | 192.72
[5 empty] | 2021-06-01 | 8499.94 | 0 | 8499.94
|  |  |  | 2020-11-06 | 2021-02-09 | 131599.53 | 0 | 131599.53
|  |  |  | 2022-01-14 | 2023-01-14 | 0 | 19218.56 | 19218.56
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 8556.25 | 0 | 8556.25
[5 empty] | 2020-01-14 | 12837.5 | 0 | 12837.5
[5 empty] | 2020-04-01 | 19960 | 0 | 19960
[5 empty] | 2020-04-15 | 13455 | 0 | 13455
[5 empty] | 2020-05-28 | 9450 | 0 | 9450
[5 empty] | 2020-06-17 | 10027.5 | 0 | 10027.5
[5 empty] | 2020-07-27 | 10887.5 | 0 | 10887.5
[5 empty] | 2020-08-17 | 6349.45 | 0 | 6349.45
[5 empty] | 2020-10-13 | 5997.42 | 0 | 5997.42
[5 empty] | 2020-10-20 | 5682.27 | 0 | 5682.27
[5 empty] | 2020-12-18 | 11805.19 | 0 | 11805.19
[5 empty] | 2021-02-08 | 5853.48 | 0 | 5853.48
[5 empty] | 2021-04-05 | 4305.81 | 0 | 4305.81
[5 empty] | 2021-04-16 | 3646.24 | 0 | 3646.24
[5 empty] | 2021-05-25 | 6152.18 | 0 | 6152.18
[5 empty] | 2022-10-10 | 0 | 19.75 | 19.75
[5 empty] | 2022-02-11 | 2315.17 | 0 | 2315.17
[5 empty] | 2022-03-15 | 13530.29 | 0 | 13530.29
|  | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 9695.44 | 0 | 9695.44
|  | Department of General Services (DGS) | DSA fees | 2022-01-13 | 2022-01-28 | 14670.45 | 0 | 14670.45
|  | Division of the State Architect (DSA) | DSA fees | 2019-06-11 | 2019-06-19 | 15540.64 | 0 | 15540.64
|  | Education Products & Services | Sink cabinet | 2020-01-31 | 2020-04-23 | 3449.99 | 0 | 3449.99
|  |  | Sliding white boards | 2020-01-15 | 2020-04-23 | 5465.85 | 0 | 5465.85
|  |  | White board(s) | 2020-01-31 | 2020-04-23 | 1253.77 | 0 | 1253.77
|  | Floor Tech America (FTA) | Contractor |  |  | 11175 | 0 | 11175
|  | GDL Best Contractors, Inc | Contractor |  |  | 14900 | 0 | 14900
|  | Graybar | Door hardware | 2020-12-14 | 2021-02-08 | 246.82 | 0 | 246.82
|  | ICS Service Co. | Contractor |  |  | 141.7 | 0 | 141.7
|  |  | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2599.48 | 0 | 2599.48
|  | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-07-06 | 2020-10-13 | 27860 | 0 | 27860
|  |  | Contractor |  |  | 12975 | 0 | 12975
|  |  | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 45000 | 0 | 45000
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 41441.22 | 0 | 41441.22
|  |  |  | 2020-03-17 | 2020-08-12 | 39845 | 0 | 39845
[5 empty] | 2021-03-23 | 19922.5 | 0 | 19922.5
|  | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 1752 | 0 | 1752
[5 empty] | 2020-08-05 | 24610.13 | 0 | 24610.13
[5 empty] | 2020-08-20 | 1040.26 | 0 | 1040.26
|  | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 49357.13 | 0 | 49357.13
|  | Martin Container | Rental of container(s) | 2020-05-06 | 2020-07-01 | 1971 | 0 | 1971
[5 empty] | 2021-06-30 | 1357.8 | 0 | 1357.8
|  |  |  | 2020-06-03 | 2020-08-18 | 1664.4 | 0 | 1664.4
|  |  |  | 2020-10-09 | 2022-03-07 | 0 | 0 | 0
|  |  |  | 2021-02-10 | 2021-02-22 | 821.26 | 0 | 821.26
[5 empty] | 2021-03-24 | 684.37 | 0 | 684.37
[5 empty] | 2021-05-26 | 547.5 | 0 | 547.5
[5 empty] | 2021-06-23 | 684.39 | 0 | 684.39
[5 empty] | 2021-06-30 | 136.87 | 0 | 136.87
[5 empty] | 2021-09-09 | 684.39 | 0 | 684.39
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2530 | 0 | 2530
|  |  | Oversight asbestos abatement | 2020-07-06 | 2020-10-13 | 3975 | 0 | 3975
[5 empty] | 2023-01-16 | 0 | 4125 | 4125
|  | Masters Contracting Corp | Contractor |  |  | 2066496.06 | 123503.94 | 2190000
|  | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 1023.66 | 0 | 1023.66
|  | TDM Architects, Inc | Architect | 2018-07-17 | 2018-10-11 | 3699.66 | 0 | 3699.66
[5 empty] | 2019-01-28 | 4962 | 0 | 4962
[5 empty] | 2019-09-05 | 21272.98 | 0 | 21272.98
[5 empty] | 2019-09-11 | 30522.1 | 0 | 30522.1
[5 empty] | 2020-06-04 | 9249.12 | 0 | 9249.12
[5 empty] | 2020-10-21 | 19633.76 | 0 | 19633.76
[5 empty] | 2021-04-19 | 4624.55 | 0 | 4624.55
[5 empty] | 2021-12-20 | 4624.55 | 0 | 4624.55
|  |  |  | 2020-05-11 | 2020-10-21 | 11306 | 0 | 11306
|  | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 4410 | 0 | 4410
[5 empty] | 2020-08-19 | 3360 | 0 | 3360
[5 empty] | 2020-10-14 | 2940 | 0 | 2940
[5 empty] | 2020-10-21 | 2940 | 0 | 2940
[5 empty] | 2021-02-05 | 6160 | 0 | 6160
[5 empty] | 2021-03-24 | 4270 | 0 | 4270
[5 empty] | 2021-04-19 | 5320 | 0 | 5320
[5 empty] | 2021-04-20 | 3220 | 0 | 3220
[5 empty] | 2023-07-31 | 0 | 2100 | 2100
|  | Telenet VOIP, Inc | Contractor |  |  | 32632.23 | -2.9559e-12 | 32632.23
|  | Wolverine Fence | Contractor |  |  | 4725 | 0 | 4725
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 294258.7 | 15487.3 | 309746
| Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 1050 | 0 | 1050
| Fire Alarm | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 7125 | 0 | 7125
[5 empty] | 2021-05-26 | 2375 | 0 | 2375
[5 empty] | 2021-09-09 | 1425 | 0 | 1425
[5 empty] | 2022-02-23 | 950 | 0 | 950
|  | Team Inspections | General inspection | 2020-12-15 | 2021-02-09 | 9180 | 0 | 9180
[5 empty] | 2021-09-09 | 500 | 0 | 500
[5 empty] | 2021-09-13 | 2570 | 0 | 2570
|  | Telenet VOIP, Inc | Contractor |  |  | 111843.34 | 7591.74 | 119435.08
Nelson Total | [5 empty] | 3697462.27 | 191778.79 | 3889241.06
Newton | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1300.32 | 0 | 1300.32
[5 empty] | 2019-10-15 | 20805.18 | 0 | 20805.18
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 27499.7 | 0 | 27499.7
[5 empty] | 2019-10-22 | 281759.15 | 0 | 281759.15
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 7376.25 | 0 | 7376.25
[5 empty] | 2020-01-14 | 11395 | 0 | 11395
[5 empty] | 2020-04-01 | 17477.5 | 0 | 17477.5
[5 empty] | 2020-04-15 | 7480 | 0 | 7480
[5 empty] | 2020-05-28 | 9737.5 | 0 | 9737.5
[5 empty] | 2020-06-17 | 8587.5 | 0 | 8587.5
[5 empty] | 2020-07-27 | 6685 | 0 | 6685
[5 empty] | 2020-08-17 | 10803.44 | 0 | 10803.44
[5 empty] | 2020-10-13 | 10204.46 | 0 | 10204.46
[5 empty] | 2020-10-20 | 9668.25 | 0 | 9668.25
[5 empty] | 2020-12-18 | 20086.24 | 0 | 20086.24
[5 empty] | 2021-02-08 | 9959.55 | 0 | 9959.55
[5 empty] | 2021-04-05 | 7326.23 | 0 | 7326.23
[5 empty] | 2021-04-16 | 6204 | 0 | 6204
[5 empty] | 2021-05-25 | 10467.79 | 0 | 10467.79
[5 empty] | 2021-06-22 | 5920 | 0 | 5920
[5 empty] | 2021-09-08 | 21440 | 0 | 21440
[5 empty] | 2021-09-09 | 9760 | 0 | 9760
[5 empty] | 2022-10-10 | 0 | -10125.71 | -10125.71
|  | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 28270.82 | 0 | 28270.82
|  | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 2312.3 | 0 | 2312.3
[5 empty] | 2019-09-16 | 12717.65 | 0 | 12717.65
[5 empty] | 2020-02-13 | 16186.1 | 0 | 16186.1
[5 empty] | 2020-06-04 | 19076.48 | 0 | 19076.48
[5 empty] | 2020-09-10 | 11738 | 0 | 11738
[5 empty] | 2021-05-07 | 19076.47 | 0 | 19076.47
[5 empty] | 2021-06-23 | 2890.38 | 0 | 2890.38
[5 empty] | 2023-01-16 | 0 | 50750.51 | 50750.51
[5 empty] | 2021-12-20 | 867.11 | 0 | 867.11
|  |  |  | 2020-08-07 | 2020-09-10 | 85965 | 0 | 85965
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-10-13 | 2950 | 0 | 2950
|  | Williams Tree Service | Tree Service | 2020-10-27 | 2022-08-11 | 3400 | 0 | 3400
| Fire Alarm | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-03-20 | 645 | 0 | 645
|  | tBP Architecture | Architect | 2018-07-01 | 2020-09-18 | 7125 | 0 | 7125
[5 empty] | 2021-02-05 | 1425 | 0 | 1425
[5 empty] | 2021-05-26 | 950 | 0 | 950
|  | Team Inspections | General inspection | 2019-11-26 | 2020-05-26 | 6090 | 0 | 6090
[5 empty] | 2020-06-19 | 2035 | 0 | 2035
|  | Telenet VOIP, Inc | Contractor |  |  | 78546.01 | 4134 | 82680.01
| Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 186.94 | 0 | 186.94
[5 empty] | 2022-01-24 | 353 | 0 | 353
|  | Chalmers Construction Services, Inc. | Contractor |  |  | 117420 | 281080 | 398500
|  | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-01-28 | 4175.44 | 0 | 4175.44
|  | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 1006.76 | 0 | 1006.76
[5 empty] | 2019-02-28 | 11511.5 | 0 | 11511.5
[5 empty] | 2019-09-16 | 12584.52 | 0 | 12584.52
[5 empty] | 2020-04-02 | 16611.57 | 0 | 16611.57
[5 empty] | 2021-05-07 | 8488.5 | 0 | 8488.5
[5 empty] | 2021-06-02 | 1258.45 | 0 | 1258.45
[5 empty] | 2023-01-16 | 0 | 6921.49 | 6921.49
[5 empty] | 2021-12-20 | 1258.45 | 0 | 1258.45
[5 empty] | 2022-03-11 | 7550.71 | 0 | 7550.71
[5 empty] | 2022-03-24 | 3146.13 | 0 | 3146.13
|  |  |  | 2020-08-10 | 2021-05-07 | 4520 | 0 | 4520
|  |  |  | 2021-02-24 | 2021-05-07 | 5000 | 0 | 5000
|  |  |  | 2021-12-15 | 2022-12-15 | 0 | 1725 | 1725
|  | Mobile Modular Management Corp | Portable classrooms | 2019-03-20 | 2020-02-18 | 218488.74 | 0 | 218488.74
|  |  | Portable classrooms (4) | 2019-03-20 | 2022-03-16 | 21300 | 0 | 21300
|  | San Gabriel Tribune | Newspaper Advertisement | 2021-07-09 | 2021-07-30 | 1088 | 0 | 1088
|  | Suburban Water Systems | Fire flow testing | 2020-01-14 | 2020-01-23 | 212 | 0 | 212
|  | Team Inspections | General inspection | 2020-07-01 | 2023-07-31 | 0 | 16000 | 16000
|  | Temp Power Sytems | Rental of power pole | 2019-07-29 | 2021-02-05 | 8497 | 0 | 8497
[5 empty] | 2023-01-16 | 0 | 3325 | 3325
|  |  |  | 2022-03-30 | 2025-07-11 | 0 | 7665 | 7665
|  | Southern California Edison Co (SCE) | Temporary power | 2022-01-10 | 2022-01-24 | 1072 | 0 | 1072
Newton Total | [5 empty] | 1269939.09 | 361475.29 | 1631414.38
Orange Grove | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1300.32 | 0 | 1300.32
[5 empty] | 2019-10-08 | 13003.23 | 0 | 13003.23
[5 empty] | 2019-10-22 | 1300.32 | 0 | 1300.32
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 174916.09 | 0 | 174916.09
[5 empty] | 2019-10-22 | 18032.58 | 0 | 18032.58
|  | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 800 | 0 | 800
[5 empty] | 2021-09-29 | 2960 | 0 | 2960
[5 empty] | 2024-07-01 | 0 | 197337 | 197337
|  |  |  | 2021-11-02 | 2021-11-08 | 5505 | 0 | 5505
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2800 | 0 | 2800
|  | PBK Architects | Architect | 2021-05-03 | 2024-05-03 | 0 | 222000 | 222000
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 1080 | 0 | 1080
|  | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 7425 | 0 | 7425
[5 empty] | 2021-02-09 | 4920 | 0 | 4920
[5 empty] | 2021-02-22 | 30 | 0 | 30
[5 empty] | 2021-03-24 | 9900 | 0 | 9900
[5 empty] | 2021-05-26 | 12375 | 0 | 12375
[5 empty] | 2021-06-23 | 1485 | 0 | 1485
[5 empty] | 2021-09-09 | 990 | 0 | 990
[5 empty] | 2025-10-20 | 0 | 12375 | 12375
| Interim Housing | PBK Architects | Architect | 2021-05-03 | 2024-05-03 | 0 | 95400 | 95400
Orange Grove Total | [5 empty] | 258822.54 | 527112 | 785934.54
Palm | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 9102.26 | 0 | 9102.26
[5 empty] | 2019-10-08 | 9102.26 | 0 | 9102.26
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 94671.08 | 0 | 94671.08
|  | Floor Tech America (FTA) | Contractor |  |  | 6372.24 | 0 | 6372.24
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 40000 | 0 | 40000
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 19119.08 | 0 | 19119.08
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2500 | 0 | 2500
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 220694.5 | 11615.5 | 232310
| Drinking fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 1050 | 0 | 1050
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 870 | 0 | 870
|  | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 7275 | 0 | 7275
[5 empty] | 2021-02-09 | 7275 | 0 | 7275
[5 empty] | 2021-03-24 | 7275 | 0 | 7275
[5 empty] | 2021-05-26 | 12125 | 0 | 12125
[5 empty] | 2021-06-23 | 1455 | 0 | 1455
[5 empty] | 2021-09-09 | 970 | 0 | 970
[5 empty] | 2025-10-20 | 0 | 12125 | 12125
Palm Total | [5 empty] | 439856.42 | 23740.5 | 463596.92
Palm Canyon | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 1352.45 | 0 | 1352.45
[5 empty] | 2019-10-22 | 9016.29 | 0 | 9016.29
Palm Canyon Total | [5 empty] | 10368.74 | 0 | 10368.74
Sierra Vista | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 11756.35 | 0 | 11756.35
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 159310.62 | 0 | 159310.62
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 3000 | 0 | 3000
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 1050 | 0 | 1050
|  | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 19800 | 0 | 19800
[5 empty] | 2021-05-26 | 14850 | 0 | 14850
[5 empty] | 2021-06-23 | 1485 | 0 | 1485
[5 empty] | 2021-09-09 | 990 | 0 | 990
[5 empty] | 2025-10-20 | 0 | 12375 | 12375
Sierra Vista Total | [5 empty] | 212241.97 | 12375 | 224616.97
Sparks ES | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 23512.7 | 0 | 23512.7
|  |  | Laptops | 2019-07-01 | 2019-10-08 | 8599.15 | 0 | 8599.15
[5 empty] | 2019-10-21 | 9051.74 | 0 | 9051.74
[5 empty] | 2019-10-22 | 131250.23 | 0 | 131250.23
|  | Floor Tech America (FTA) | Contractor |  |  | 19116.72 | 0 | 19116.72
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2020-10-13 | 40000 | 0 | 40000
|  |  |  | 2021-06-14 | 2021-09-09 | 4000 | 0 | 4000
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2670 | 0 | 2670
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 245215.9 | 12906.1 | 258122
| Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 930 | 0 | 930
|  | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 0 | 12125 | 12125
Sparks ES Total | [5 empty] | 505067.05 | 26231.1 | 531298.15
Sparks MS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-04 | 18287.65 | 0 | 18287.65
|  |  | Laptops | 2019-07-01 | 2019-10-08 | 9051.74 | 0 | 9051.74
[5 empty] | 2019-10-10 | 255711.66 | 0 | 255711.66
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 8306.25 | 0 | 8306.25
[5 empty] | 2020-01-14 | 10935 | 0 | 10935
[5 empty] | 2020-04-01 | 16222.5 | 0 | 16222.5
[5 empty] | 2020-04-15 | 7320 | 0 | 7320
[5 empty] | 2020-05-28 | 9337.5 | 0 | 9337.5
[5 empty] | 2020-06-17 | 6822.5 | 0 | 6822.5
[5 empty] | 2020-07-27 | 3765 | 0 | 3765
[5 empty] | 2020-08-17 | 8001.67 | 0 | 8001.67
[5 empty] | 2020-10-13 | 7558.04 | 0 | 7558.04
[5 empty] | 2020-10-20 | 7160.88 | 0 | 7160.88
[5 empty] | 2020-12-18 | 14877.08 | 0 | 14877.08
[5 empty] | 2021-02-08 | 7376.64 | 0 | 7376.64
[5 empty] | 2021-04-05 | 5426.24 | 0 | 5426.24
[5 empty] | 2021-04-16 | 4595.05 | 0 | 4595.05
[5 empty] | 2021-05-25 | 7753.08 | 0 | 7753.08
[5 empty] | 2021-06-22 | 5760 | 0 | 5760
[5 empty] | 2021-09-08 | 1600 | 0 | 1600
[5 empty] | 2021-09-09 | 8160 | 0 | 8160
[5 empty] | 2022-10-10 | 0 | 4473.57 | 4473.57
|  | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 22264.25 | 0 | 22264.25
|  | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 1757.34 | 0 | 1757.34
[5 empty] | 2019-02-27 | 33577.25 | 0 | 33577.25
[5 empty] | 2020-02-13 | 0 | 0 | 0
[5 empty] | 2020-06-18 | 14498.06 | 0 | 14498.06
[5 empty] | 2020-12-08 | 8389.5 | 0 | 8389.5
[5 empty] | 2021-05-07 | 14498.05 | 0 | 14498.05
[5 empty] | 2021-06-23 | 2196.68 | 0 | 2196.68
[5 empty] | 2023-01-16 | 0 | 32291.12 | 32291.12
[5 empty] | 2021-12-20 | 659 | 0 | 659
|  |  |  | 2020-08-07 | 2020-12-08 | 67606 | 0 | 67606
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2950 | 0 | 2950
| Fire Alarm | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-01-20 | 860 | 0 | 860
|  | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2475 | 0 | 2475
[5 empty] | 2021-02-05 | 1485 | 0 | 1485
[5 empty] | 2021-03-24 | 990 | 0 | 990
|  | Team Inspections | General inspection | 2019-11-26 | 2020-02-20 | 1720 | 0 | 1720
[5 empty] | 2020-04-17 | 3440 | 0 | 3440
[5 empty] | 2020-06-19 | 1715 | 0 | 1715
|  | Telenet VOIP, Inc | Contractor |  |  | 144400 | 7600 | 152000
Sparks MS Total | [5 empty] | 749509.61 | 44364.69 | 793874.3
Stimson | 21st Century | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2704.88 | 0 | 2704.88
[5 empty] | 2019-10-22 | 18032.58 | 0 | 18032.58
|  | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 480 | 0 | 480
[5 empty] | 2021-09-29 | 4800 | 0 | 4800
[5 empty] | 2024-07-01 | 0 | 64678 | 64678
|  |  |  | 2021-11-02 | 2021-11-08 | 5170 | 0 | 5170
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 375 | 0 | 375
|  | tBP Architecture | Architect | 2020-01-14 | 2020-05-26 | 9875 | 0 | 9875
[5 empty] | 2020-06-19 | 9875 | 0 | 9875
[5 empty] | 2020-10-14 | 7900 | 0 | 7900
[5 empty] | 2021-05-26 | 1975 | 0 | 1975
[5 empty] | 2023-07-31 | 0 | 9875 | 9875
Stimson Total | [5 empty] | 61187.46 | 74553 | 135740.46
Sunset | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 10450.09 | 0 | 10450.09
[5 empty] | 2019-12-06 | 1306.26 | 0 | 1306.26
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 5883.63 | 0 | 5883.63
[5 empty] | 2019-10-22 | 81465.64 | 0 | 81465.64
[5 empty] | 2019-11-12 | 9051.74 | 0 | 9051.74
|  | Cumming Construction Management, Inc | Construction mgmt services | 2021-07-01 | 2021-09-08 | 800 | 0 | 800
[5 empty] | 2021-09-29 | 1600 | 0 | 1600
[5 empty] | 2024-07-01 | 0 | 198697 | 198697
|  |  |  | 2021-11-02 | 2021-11-08 | 5505 | 0 | 5505
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2023-01-06 | 22500 | 0 | 22500
|  |  |  | 2021-07-16 | 2021-09-09 | 19000 | 0 | 19000
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2700 | 0 | 2700
|  | TDM Architects, Inc | Architect | 2021-05-03 | 2021-09-09 | 23712 | 0 | 23712
[5 empty] | 2021-10-19 | 5833.89 | 0 | 5833.89
[5 empty] | 2024-05-03 | 0 | 157014.11 | 157014.11
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 230736 | 12144 | 242880
| Drinking fountain replacement | Optima | Contractor |  |  | 18000 | 0 | 18000
|  | Wolverine Fence | Contractor |  |  | 4800 | 0 | 4800
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 564 | 0 | 564
|  | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2425 | 0 | 2425
[5 empty] | 2021-02-09 | 9700 | 0 | 9700
[5 empty] | 2021-03-24 | 7275 | 0 | 7275
[5 empty] | 2021-05-26 | 14550 | 0 | 14550
[5 empty] | 2021-06-23 | 1455 | 0 | 1455
[5 empty] | 2021-09-09 | 970 | 0 | 970
[5 empty] | 2025-10-20 | 0 | 12125 | 12125
| Interim Housing | TDM Architects, Inc | Architect | 2021-05-03 | 2024-05-03 | 0 | 97400 | 97400
Sunset Total | [5 empty] | 501003.86 | 477380.11 | 978383.97
Temple | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 18287.65 | 0 | 18287.65
|  |  | Laptops | 2019-07-01 | 2019-10-08 | 7241.39 | 0 | 7241.39
[5 empty] | 2019-10-21 | 9051.74 | 0 | 9051.74
[5 empty] | 2019-10-22 | 76939.79 | 0 | 76939.79
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 245186.45 | 12904.55 | 258091
Temple Total | [5 empty] | 380027.63 | 12904.55 | 392932.18
Valinda | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1300.32 | 0 | 1300.32
[5 empty] | 2019-10-11 | 33962.79 | 0 | 33962.79
|  |  | Laptops | 2019-07-01 | 2019-10-08 | 32133.68 | 0 | 32133.68
[5 empty] | 2019-10-21 | 9051.74 | 0 | 9051.74
[5 empty] | 2019-10-22 | 185560.67 | 0 | 185560.67
|  | Education Products & Services | White board(s) | 2019-09-16 | 2019-10-01 | 1464.78 | 0 | 1464.78
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 3000 | 0 | 3000
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 1125 | 0 | 1125
|  | tBP Architecture | Architect | 2020-01-14 | 2023-07-31 | 0 | 12375 | 12375
Valinda Total | [5 empty] | 288319.59 | 12375 | 300694.59
Valley | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 7801.94 | 0 | 7801.94
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 7213.03 | 0 | 7213.03
[5 empty] | 2019-10-22 | 72130.34 | 0 | 72130.34
|  | Floor Tech America (FTA) | Contractor |  |  | 19116.72 | 0 | 19116.72
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2700 | 0 | 2700
| Fire Alarm | Department of General Services (DGS) | DSA fees | 2021-07-13 | 2021-08-02 | 698.75 | 0 | 698.75
|  | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 630 | 0 | 630
|  | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2275 | 0 | 2275
[5 empty] | 2021-01-07 | 2275 | 0 | 2275
[5 empty] | 2021-02-05 | 2275 | 0 | 2275
[5 empty] | 2021-02-09 | 3640 | 0 | 3640
[5 empty] | 2021-10-28 | 910 | 0 | 910
|  | Team Inspections | General inspection | 2020-08-19 | 2020-10-14 | 3675 | 0 | 3675
[5 empty] | 2021-02-09 | 3675 | 0 | 3675
|  | Telenet VOIP, Inc | Contractor |  |  | 219916.37 | 12074.54 | 231990.91
Valley Total | [5 empty] | 348932.15 | 12074.54 | 361006.69
Wedgeworth | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 31207.76 | 0 | 31207.76
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 114957.74 | 0 | 114957.74
|  | Floor Tech America (FTA) | Contractor |  |  | 12744.48 | 0 | 12744.48
| Drinking fountain replacement | Optima | Contractor |  |  | 3502.75 | 2997.25 | 6500
|  | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
Wedgeworth Total | [5 empty] | 162412.73 | 4197.25 | 166609.98
Willow | 21st Century | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 2700 | 0 | 2700
Willow Total | [5 empty] | 2700 | 0 | 2700
Wilson HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 53313.26 | 0 | 53313.26
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 614009.56 | 0 | 614009.56
[5 empty] | 2019-10-21 | 4508.15 | 0 | 4508.15
|  | Floor Tech America (FTA) | Contractor |  |  | 19116.72 | 0 | 19116.72
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 3400 | 0 | 3400
| Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-07-11 | 0 | 1200 | 1200
| Fire Alarm | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2275 | 0 | 2275
[5 empty] | 2021-02-05 | 2275 | 0 | 2275
[5 empty] | 2021-03-24 | 2275 | 0 | 2275
[5 empty] | 2023-07-31 | 0 | 4550 | 4550
|  | Team Inspections | General inspection | 2020-05-13 | 2020-06-19 | 4125 | 0 | 4125
[5 empty] | 2020-08-19 | 8250 | 0 | 8250
[5 empty] | 2021-09-13 | 3625 | 0 | 3625
[5 empty] | 2023-07-31 | 0 | 500 | 500
|  | Telenet VOIP, Inc | Contractor |  |  | 260791.17 | 21269.01 | 282060.18
Wilson HS Total | [5 empty] | 977963.86 | 27519.01 | 1005482.87
Wing Lane | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-04 | 19593.91 | 0 | 19593.91
|  |  | Laptops | 2019-07-01 | 2019-10-08 | 16293.13 | 0 | 16293.13
[5 empty] | 2019-10-10 | 74676.86 | 0 | 74676.86
|  | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 40000 | 0 | 40000
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2600 | 0 | 2600
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 287601.1 | 15136.9 | 302738
| Drinking fountain replacement | Optima | Contractor |  |  | 6800 | 0 | 6800
| Fire Alarm | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 870 | 0 | 870
|  | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 7275 | 0 | 7275
[5 empty] | 2021-02-09 | 7275 | 0 | 7275
[5 empty] | 2021-03-24 | 4850 | 0 | 4850
[5 empty] | 2021-05-26 | 14550 | 0 | 14550
[5 empty] | 2021-06-23 | 1455 | 0 | 1455
[5 empty] | 2021-09-09 | 970 | 0 | 970
[5 empty] | 2025-10-20 | 0 | 12125 | 12125
Wing Lane Total | [5 empty] | 505530.61 | 27261.9 | 532792.51
Workman ES | 21st Century | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 78.14 | 0 | 78.14
[5 empty] | 2020-04-30 | 275.8 | 0 | 275.8
[5 empty] | 2020-05-06 | 188.86 | 0 | 188.86
|  |  |  | 2020-04-28 | 2020-05-06 | 185.8 | 0 | 185.8
[5 empty] | 2020-08-17 | 1251.62 | 0 | 1251.62
|  | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1306.26 | 0 | 1306.26
[5 empty] | 2019-10-08 | 22206.44 | 0 | 22206.44
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 101379.49 | 0 | 101379.49
|  |  | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 26216.53 | 0 | 26216.53
|  |  |  | 2021-06-14 | 2022-02-11 | 15362.62 | 0 | 15362.62
|  | Camcor | Document camera(s) | 2020-07-01 | 2020-07-16 | 7172.46 | 0 | 7172.46
|  | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 582.54 | 0 | 582.54
|  | Chatfield-Clarke | Tack boards | 2020-09-23 | 2020-11-03 | 413.91 | 0 | 413.91
|  | Converse Consultants | Geotechnical | 2020-06-05 | 2021-02-05 | 507.5 | 0 | 507.5
[5 empty] | 2023-07-31 | 0 | 16092.5 | 16092.5
|  | Culver Newlin | Furniture | 2020-03-17 | 2020-12-18 | 80713.17 | 0 | 80713.17
[5 empty] | 2021-05-07 | 20837.74 | 0 | 20837.74
[5 empty] | 2021-05-25 | 2266.65 | 0 | 2266.65
|  |  |  | 2020-11-06 | 2021-04-19 | 113360.81 | 0 | 113360.81
|  |  |  | 2021-02-05 | 2021-05-25 | 5321.7 | 0 | 5321.7
|  |  |  | 2022-01-14 | 2022-03-23 | 16893.03 | 0 | 16893.03
|  | Cumming Construction Management, Inc | Construction mgmt services | 2019-10-10 | 2020-01-09 | 9866.25 | 0 | 9866.25
[5 empty] | 2020-01-14 | 11340 | 0 | 11340
[5 empty] | 2020-04-01 | 17130 | 0 | 17130
[5 empty] | 2020-04-15 | 12972.5 | 0 | 12972.5
[5 empty] | 2020-05-28 | 9657.5 | 0 | 9657.5
[5 empty] | 2020-06-17 | 9947.5 | 0 | 9947.5
[5 empty] | 2020-07-27 | 12327.5 | 0 | 12327.5
[5 empty] | 2020-08-17 | 8313.42 | 0 | 8313.42
[5 empty] | 2020-10-13 | 7852.49 | 0 | 7852.49
[5 empty] | 2020-10-20 | 7439.86 | 0 | 7439.86
[5 empty] | 2020-12-18 | 15456.65 | 0 | 15456.65
[5 empty] | 2021-02-08 | 7664.02 | 0 | 7664.02
[5 empty] | 2021-04-05 | 5637.64 | 0 | 5637.64
[5 empty] | 2021-04-16 | 4774.06 | 0 | 4774.06
[5 empty] | 2021-05-25 | 8055.13 | 0 | 8055.13
[5 empty] | 2021-06-22 | 480 | 0 | 480
[5 empty] | 2022-10-10 | 0 | 14709.39 | 14709.39
[5 empty] | 2022-03-15 | 5583.09 | 0 | 5583.09
|  | Dell Technologies | Networking power switches | 2021-05-12 | 2021-08-27 | 9695.44 | 0 | 9695.44
|  | Division of the State Architect (DSA) | DSA fees | 2019-04-16 | 2019-04-18 | 9500 | 0 | 9500
|  |  |  | 2021-03-17 | 2021-05-05 | 800 | 0 | 800
|  |  |  | 2022-01-19 | 2022-01-28 | 12085.87 | 0 | 12085.87
|  | Graybar | Door hardware | 2020-12-14 | 2021-02-08 | 246.8 | 0 | 246.8
|  | ICS Service Co. | Equipment to repair & replace security system | 2020-11-30 | 2021-04-16 | 1111.09 | 0 | 1111.09
[5 empty] | 2023-01-16 | 0 | 957.98 | 957.98
|  | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement | 2020-09-18 | 2021-03-24 | 4250 | 0 | 4250
|  |  | Asbestos abatement & demolition | 2020-07-06 | 2020-08-18 | 32000 | 0 | 32000
|  |  | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 27500 | 0 | 27500
|  | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 20720.61 | 0 | 20720.61
|  |  |  | 2020-11-10 | 2021-03-24 | 104699.05 | 0 | 104699.05
[5 empty] | 2021-04-16 | -5086.56 | 0 | -5086.56
|  | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 840.96 | 0 | 840.96
[5 empty] | 2020-08-05 | 11812.86 | 0 | 11812.86
|  | Lightspeed | Voice amplification system | 2020-07-07 | 2020-07-23 | 23691.42 | 0 | 23691.42
|  | Martin Container | Rental of container(s) | 2020-05-06 | 2020-07-01 | 1971 | 0 | 1971
[5 empty] | 2021-06-30 | 1373 | 0 | 1373
|  |  |  | 2020-06-03 | 2020-08-18 | 1672 | 0 | 1672
|  |  |  | 2021-02-10 | 2021-02-22 | 825.02 | 0 | 825.02
[5 empty] | 2021-03-24 | 687.52 | 0 | 687.52
[5 empty] | 2021-05-26 | 550.01 | 0 | 550.01
[5 empty] | 2021-06-23 | 825.02 | 0 | 825.02
[5 empty] | 2021-06-30 | 137.5 | 0 | 137.5
[5 empty] | 2021-09-09 | 687.52 | 0 | 687.52
|  |  |  | 2021-03-12 | 2021-03-30 | 137.5 | 0 | 137.5
[5 empty] | 2021-05-26 | 275 | 0 | 275
[5 empty] | 2021-09-09 | 275 | 0 | 275
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2500 | 0 | 2500
|  |  |  | 2020-06-03 | 2020-06-26 | 1200 | 0 | 1200
|  |  | Oversight asbestos abatement | 2020-07-06 | 2020-08-17 | 6775 | 0 | 6775
[5 empty] | 2023-01-16 | 0 | 4300 | 4300
|  |  |  | 2020-09-11 | 2020-11-19 | 825 | 0 | 825
[5 empty] | 2023-09-11 | 0 | 100 | 100
|  | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 1086.6 | 0 | 1086.6
|  | SVA Architects, Inc | Architect | 2018-06-01 | 2018-06-28 | 2363.68 | 0 | 2363.68
[5 empty] | 2019-02-08 | 4900 | 0 | 4900
[5 empty] | 2019-04-03 | 4581.84 | 0 | 4581.84
[5 empty] | 2019-09-05 | 54214.7 | 0 | 54214.7
[5 empty] | 2019-10-25 | 5850.11 | 0 | 5850.11
[5 empty] | 2020-05-26 | 9809.27 | 0 | 9809.27
[5 empty] | 2020-06-03 | 404.95 | 0 | 404.95
[5 empty] | 2020-08-18 | 5909.2 | 0 | 5909.2
[5 empty] | 2021-02-05 | 19204.9 | 0 | 19204.9
[5 empty] | 2023-01-16 | 0 | 18240.57 | 18240.57
[5 empty] | 2022-03-24 | 12704.78 | 0 | 12704.78
|  |  | DSA fees | 2020-02-27 | 2020-04-02 | 2250 | 0 | 2250
|  | TDM Architects, Inc | Architect | 2021-04-08 | 2021-08-31 | 8116.8 | 0 | 8116.8
[5 empty] | 2023-04-08 | 0 | 5411.2 | 5411.2
|  | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 2940 | 0 | 2940
[5 empty] | 2020-08-19 | 3080 | 0 | 3080
[5 empty] | 2020-10-14 | 3500 | 0 | 3500
[5 empty] | 2020-10-21 | 2940 | 0 | 2940
[5 empty] | 2021-02-05 | 3080 | 0 | 3080
[5 empty] | 2021-04-19 | 9940 | 0 | 9940
[5 empty] | 2023-07-31 | 0 | 9240 | 9240
|  | The Nazerian Group | Contractor |  |  | 1308029.35 | 225387.16 | 1533416.51
| Ceiling replacement | Schneider Electric Buildings Americas, Inc | Contractor |  |  | 230736 | 12144 | 242880
| Drinking fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2021-03-24 | 1200 | 0 | 1200
| Fire Alarm | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2375 | 0 | 2375
[5 empty] | 2021-03-24 | 7125 | 0 | 7125
[5 empty] | 2021-09-09 | 1425 | 0 | 1425
[5 empty] | 2022-02-23 | 950 | 0 | 950
|  | Team Inspections | General inspection | 2021-01-13 | 2021-02-09 | 6120 | 0 | 6120
[5 empty] | 2021-04-19 | 3060 | 0 | 3060
[5 empty] | 2021-09-13 | 2570 | 0 | 2570
[5 empty] | 2022-07-31 | 0 | 500 | 500
|  | Telenet VOIP, Inc | Contractor |  |  | 125992.76 | 7774.25 | 133767.01
Workman ES Total | [5 empty] | 2692062.25 | 314857.05 | 3006919.3
Workman HS | 21st Century | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 1300.32 | 0 | 1300.32
[5 empty] | 2019-11-07 | 40310.03 | 0 | 40310.03
|  |  | Laptops | 2019-07-01 | 2019-10-10 | 458027.67 | 0 | 458027.67
|  | Floor Tech America (FTA) | Contractor |  |  | 57350.16 | 0 | 57350.16
|  | Masek Consulting | Asbestos & lead-based paint survey | 2020-08-26 | 2021-01-19 | 4150 | 0 | 4150
Workman HS Total | [5 empty] | 561138.18 | 0 | 561138.18
Grand Total: | [5 empty] | 40797565.55 | 6919563.56 | 47717129.11

## Summary_P
Category | (All)
Project Site | (All)
Vendor Name | PO Number | Description (Services) | Completed Amount | Committed Amount | Total Exp. & Committed | % Completion
Amazon | PO3W-210000000037 | Wall plates | 64.06 | 0 | 64.06 | 100%
ARC Document Solutions | 19-109342 | Scanning/printing | 229.19 | 0 | 229.19 | 100%
| PO1-200000000625 | Scanning/printing | 2000 | 0 | 2000 | 100%
| PO1-200000001133 | Scanning/printing | 3530.8 | 0 | 3530.8 | 100%
| PO1-210000000492 | Scanning/printing | 962.15 | 4037.85 | 5000 | 19.24%
Arey Jones Educational Solutions | PO2W-200000000689, 19-109955 | Laptops | 4344683.25 | 0 | 4344683.25 | 100%
| PO2W-200000002766 | Charging carts | 1306.26 | 0 | 1306.26 | 100%
| PO2W-200000004388 | Laptops | 2698.9 | 0 | 2698.9 | 100%
| PO3W-200000000332 | Laptops | 2805547.86 | 0 | 2805547.86 | 100%
| PO3W-200000000448 | Charging carts | 91135.42 | 0 | 91135.42 | 100%
| PO3W-200000000730 | Charging carts | 793517.95 | 0 | 793517.95 | 100%
| PO3W-200000003014 | ViewSonic monitor(s) | 2184.71 | 0 | 2184.71 | 100%
| PO3W-210000000003 | ViewSonic monitor(s) | 124627.99 | 0 | 124627.99 | 100%
| PO3W-210000001075 | ViewSonic monitor(s) | 137636.77 | 0 | 137636.77 | 100%
| PO3W-210000001078 | Desktop computer(s) | 66400.82 | 0 | 66400.82 | 100%
| PO3W-210000003053 | ViewSonic monitor(s) | 10923.55 | 0 | 10923.55 | 100%
| PO3W-210000003054 | ViewSonic monitor(s) | 15362.62 | 0 | 15362.62 | 100%
| PO3W-220000000256 | Desktop computer(s) | 2148.06 | 0 | 2148.06 | 32.15%
|  | ViewSonic monitor(s) | 4357.42 | 0 | 4357.42 | 65.22%
|  | Web camera(s) | 175.21 | 0 | 175.21 | 2.623%
Avia Communications, Inc. | N/A | Printing & posting of POS/Os | 1350.74 | 0 | 1350.74 | 100%
California Municipal Statistics, Inc. | N/A | Demographic data | 1700 | 0 | 1700 | 100%
Camcor | PO3W-210000000006 | Document camera(s) | 34069.22 | 0 | 34069.22 | 100%
| PO3W-210000001076 | Document camera(s) | 39110.35 | 0 | 39110.35 | 100%
CDW-G Government Inc. | PO2W-200000000348 | Wireless network equipment | 368517.43 | 0 | 368517.43 | 100%
| PO3W-210000000002 | Document camera(s) | 706.28 | 0 | 706.28 | 100%
| PO3W-210000001145 | Wall plates | 3832.5 | 0 | 3832.5 | 100%
Chalmers Construction Services, Inc. | PO2W-210000000935 | Contractor | 3072707.95 | 24292.05 | 3097000 | 99.22%
| PO2W-220000001166 | Contractor | 117420 | 281080 | 398500 | 29.47%
| PO2W-220000001552 | Contractor | 0 | 137429.42 | 137429.42 | 0%
Chatfield-Clarke | PO2W-210000000770 | Tack boards | 413.91 | 0 | 413.91 | 100%
Converse Consultants | PO2W-200000000203 | Geotechnical | 5280.5 | 9249.5 | 14530 | 36.34%
| PO2W-200000004115 | Geotechnical | 11330.5 | 2209.5 | 13540 | 83.68%
| PO2W-200000005542 | Geotechnical | 12379 | 11301 | 23680 | 52.28%
| PO2W-200000005543 | Geotechnical | 1117.5 | 19732.5 | 20850 | 5.36%
| PO2W-200000005544 | Geotechnical | 507.5 | 16092.5 | 16600 | 3.057%
| PO2W-210000001034 | Masonry inspection | 8325 | 0 | 8325 | 100%
| PO2W-210000001098 | Geotechnical | 10317.5 | 6602.5 | 16920 | 60.98%
Culver Newlin | PO2W-200000004768 | Furniture | 616928.9 | 0 | 616928.9 | 100%
| PO2W-210000001121 | Furniture | 169275.1 | 0 | 169275.1 | 100%
| PO2W-210000001122 | Furniture | 131599.53 | 0 | 131599.53 | 100%
| PO2W-210000001123 | Furniture | 113360.81 | 0 | 113360.81 | 100%
| PO2W-210000001657 | Furniture | 76636.38 | 0 | 76636.38 | 100%
| PO2W-210000001658 | Furniture | 76636.38 | 0 | 76636.38 | 100%
| PO2W-210000001659 | Furniture | 37932.75 | 0 | 37932.75 | 100%
| PO2W-210000001660 | Furniture | 113798.25 | 0 | 113798.25 | 100%
| PO2W-210000001743 | Furniture | 5321.7 | 0 | 5321.7 | 100%
| PO2W-210000002168 | Furniture | 223009.81 | 0 | 223009.81 | 100%
| PO2W-210000002169 | Furniture | 154709.4 | 0 | 154709.4 | 100%
| PO2W-210000002280 | Furniture | 58016.03 | 0 | 58016.03 | 100%
| PO2W-210000002281 | Furniture | 38677.35 | 0 | 38677.35 | 100%
| PO2W-210000002282 | Furniture | 77354.7 | 0 | 77354.7 | 100%
| PO2W-210000002283 | Furniture | 232064.09 | 0 | 232064.09 | 100%
| PO2W-220000000413 | Furniture | 983.31 | 0 | 983.31 | 100%
| PO2W-220000000464 | Furniture | 40866.17 | 0 | 40866.17 | 100%
| PO3W-200000001600 | Furniture | 21169.42 | 0 | 21169.42 | 100%
| PO2W-220000001344 | Furniture | 0 | 28827.85 | 28827.85 | 0%
| PO2W-220000001345 | Furniture | 0 | 19218.56 | 19218.56 | 0%
| PO2W-220000001346 | Furniture | 0 | 44442.93 | 44442.93 | 0%
| PO2W-220000001347 | Furniture | 0 | 19218.56 | 19218.56 | 0%
| PO2W-220000001348 | Furniture | 16893.03 | 0 | 16893.03 | 100%
Cumming Construction Management, Inc | PO1-200000000640 | Construction mgmt services | 1421280 | 16620 | 1437900 | 98.84%
| PO1-200000000761 | Construction mgmt services | 449985 | 15 | 450000 | 100%
| PO1-220000000334 | Construction mgmt services | 38880 | 1790290 | 1829170 | 2.126%
| PO2W-220000000862 | Construction mgmt services | 49030 | 0 | 49030 | 100%
| PO1-220000000675 | Construction mgmt services | 50920 | 249080 | 300000 | 16.97%
David M Bertino Mfg | PO2W-220000000940 | Furniture | 3858.78 | 0 | 3858.78 | 100%
Dell Technologies | PO3W-210000002719 | Networking power switches | 72715.8 | 0 | 72715.8 | 100%
Department of General Services (DGS) | PO2W-210000001557 | DSA fees | 2150 | 0 | 2150 | 100%
| PO2W-210000001789 | DSA fees | 645 | 0 | 645 | 100%
| PO2W-220000000054 | DSA fees | 698.75 | 0 | 698.75 | 100%
| PO2W-220000000119 | DSA fees | 3171.25 | 0 | 3171.25 | 100%
| PO2W-220000000367 | DSA fees | 1290 | 0 | 1290 | 100%
| PO2W-220000001228 | DSA fees | 15210.87 | 0 | 15210.87 | 100%
| PO2W-220000001343 | DSA fees | 14670.45 | 0 | 14670.45 | 100%
Division of the State Architect (DSA) | 19-107318 | DSA fees | 3481.54 | 0 | 3481.54 | 100%
| 19-108465 | DSA fees | 9500 | 0 | 9500 | 100%
| 19-109963 | DSA fees | 14918.24 | 0 | 14918.24 | 100%
| 19-109964 | DSA fees | 15540.64 | 0 | 15540.64 | 100%
| PO1-200000000848 | DSA fees | 930 | 0 | 930 | 100%
| PO1-200000000849 | DSA fees | 870 | 0 | 870 | 100%
| PO1-200000000850 | DSA fees | 960 | 0 | 960 | 100%
| PO1-200000000851 | DSA fees | 375 | 0 | 375 | 100%
| PO1-200000000852 | DSA fees | 1125 | 0 | 1125 | 100%
| PO1-200000000853 | DSA fees | 0 | 0 | 0 | 0%
| PO1-200000000863 | DSA fees | 4175.44 | 0 | 4175.44 | 100%
| PO1-200000000953 | DSA fees | 1050 | 0 | 1050 | 100%
| PO1-200000000954 | DSA fees | 1050 | 0 | 1050 | 100%
| PO1-200000000955 | DSA fees | 1050 | 0 | 1050 | 100%
| PO1-200000000956 | DSA fees | 1050 | 0 | 1050 | 100%
| PO1-200000000957 | DSA fees | 1050 | 0 | 1050 | 100%
| PO1-200000000958 | DSA fees | 1050 | 0 | 1050 | 100%
| PO1-200000001113 | DSA fees | 28009 | 0 | 28009 | 100%
| PO2W-200000001053 | DSA fees | 5500 | 0 | 5500 | 100%
| PO2W-200000001054 | DSA fees | 780 | 0 | 780 | 100%
| PO2W-200000001055 | DSA fees | 630 | 0 | 630 | 100%
| PO2W-200000001056 | DSA fees | 1230 | 0 | 1230 | 100%
| PO2W-200000001057 | DSA fees | 1020 | 0 | 1020 | 100%
| PO2W-200000001058 | DSA fees | 870 | 0 | 870 | 100%
| PO2W-200000001911 | DSA fees | 7425 | 0 | 7425 | 100%
| PO2W-200000003716 | DSA fees | 3052.5 | 0 | 3052.5 | 100%
| PO2W-200000004548 | DSA fees | 2687.5 | 0 | 2687.5 | 100%
| PO2W-200000004897 | DSA fees | 22159 | 0 | 22159 | 100%
| PO2W-210000001571 | DSA fees | 57500.13 | 0 | 57500.13 | 100%
| PO2W-210000001572 | DSA fees | 28270.82 | 0 | 28270.82 | 100%
| PO2W-210000001958 | DSA fees | 7095 | 0 | 7095 | 100%
| PO2W-210000002164 | DSA fees | 2100 | 0 | 2100 | 100%
| PO2W-210000002165 | DSA fees | 800 | 0 | 800 | 100%
| PO2W-220000001377 | DSA fees | 12085.87 | 0 | 12085.87 | 100%
Education Products & Services | PO2W-200000000102 | White board(s) | 1464.78 | 0 | 1464.78 | 100%
| PO2W-200000002196 | Contractor | 1894.88 | 0 | 1894.88 | 100%
| PO2W-200000003506 | Sliding white boards | 5465.85 | 0 | 5465.85 | 100%
| PO2W-200000003738 | White board(s) | 1253.77 | 0 | 1253.77 | 100%
| PO2W-200000003740 | Sink cabinet | 3449.99 | 0 | 3449.99 | 100%
| PO2W-200000004016 | Tack boards | 1886.36 | 0 | 1886.36 | 100%
| PO3W-200000000563 | White board(s) | 1464.78 | 0 | 1464.78 | 100%
Fagen Friedman & Fulfrost LLP | 18-104648 | Attorney fees | 1064 | 0 | 1064 | 100%
| 19-100300 | Attorney fees | 2375 | 0 | 2375 | 100%
| PO1-200000000812 | Attorney fees | 20000 | -5.1159e-13 | 20000 | 100%
| PO1-200000001126 | Attorney fees | 6906.81 | 0 | 6906.81 | 100%
| PO1-210000000260 | Attorney fees | 15077.5 | 34922.5 | 50000 | 30.16%
| PO2W-200000000134 | Attorney fees | 10000 | 0 | 10000 | 100%
Fitch Ratings, Inc. | N/A | Rating Agency Fee | 45000 | 0 | 45000 | 100%
Floor Tech America (FTA) | PO2W-200000003507 | Contractor | 11175 | 0 | 11175 | 100%
| PO2W-200000004391 | Contractor | 431092.88 | 19116.72 | 450209.6 | 95.75%
GDL Best Contractors, Inc | PO2W-200000000121 | Contractor | 220500 | 0 | 220500 | 100%
| PO2W-200000004356 | Contractor | 14900 | 0 | 14900 | 100%
| PO2W-200000004670 | Contractor | 755965.41 | 3.638e-11 | 755965.41 | 100%
| PO2W-210000000586 | Contractor | 21696 | 0 | 21696 | 100%
| PO2W-220000000897 | Contractor | 17420.13 | 0 | 17420.13 | 100%
Global Industrial | PO3W-210000002747 | Scissor lift | 1665.5 | 0 | 1665.5 | 100%
Graybar | PO3W-210000001162 | Door hardware | 740.44 | 0 | 740.44 | 100%
| PO3W-210000003051 | Door hardware | 2169.95 | 0 | 2169.95 | 100%
Harley Ellis Devereaux (HED) | PO2W-200000001205, 19-100491, 18-109571 | Architect | 24000 | 0 | 24000 | 100%
| PO2W-200000001206, 19-103806 | Architect | 0 | 5500 | 5500 | 0%
| PO2W-200000001207, 19-100507, 18-109551 | Architect | 115881 | 63119 | 179000 | 64.74%
| PO2W-200000001208, 19-101983 | Architect | 63416.59 | 6921.49 | 70338.08 | 90.16%
| PO2W-200000001210, 19-101980 | Architect | 84864.49 | 50750.51 | 135615 | 62.58%
| PO2W-200000001211, 19-101981 | Architect | 75575.88 | 32291.12 | 107867 | 70.06%
| PO2W-210000000359 | Architect | 81300 | 0 | 81300 | 100%
| PO2W-210000000360 | Architect | 85965 | 0 | 85965 | 100%
| PO2W-210000000374 | Architect | 4520 | 0 | 4520 | 100%
| PO2W-210000000403 | Architect | 67606 | 0 | 67606 | 100%
| PO2W-210000001831 | Architect | 5000 | 0 | 5000 | 100%
| PO1-220000000605 | Architect | 0 | 1725 | 1725 | 0%
Haul-Away Rubbish Service Co | PO1-210000000609 | Rental of container(s) | 125.17 | 0 | 125.17 | 100%
Hawkins Delafield & Wood LLP | N/A | Bond Counsel and Disclosure Counsel Fees | 115000 | 0 | 115000 | 100%
Home Depot | PO1-200000001148 | Hardware to install access point for classrooms | 198.23 | 0 | 198.23 | 100%
ICS Service Co. | PO2W-210000001354 | Equipment to repair & replace security system | 1111.09 | 957.98 | 2069.07 | 53.7%
| PO2W-220000000706 | Contractor | 3084.7 | 0 | 3084.7 | 100%
| PO3W-210000002406 | Equipment to repair & replace security system | 8349.68 | 0 | 8349.68 | 100%
| PO3W-210000002442 | Equipment to repair & replace security system | 3426.33 | 0 | 3426.33 | 100%
Integrated Demolition & Remediation, Inc. (IDR) | PO2W-200000003741 | Contractor | 12975 | 0 | 12975 | 100%
| PO2W-200000005820 | Asbestos abatement & demolition | 18000 | 0 | 18000 | 100%
| PO2W-210000000144 | Asbestos abatement & demolition | 32000 | 0 | 32000 | 100%
| PO2W-210000000145 | Asbestos abatement & demolition | 27860 | 0 | 27860 | 100%
| PO2W-210000000146 | Asbestos abatement & demolition | 32000 | 0 | 32000 | 100%
| PO2W-210000000658 | Demo ceiling tiles | 40000 | 0 | 40000 | 100%
| PO2W-210000000675 | Asbestos abatement | 4250 | 0 | 4250 | 100%
| PO2W-210000000725 | Demo ceiling tiles | 42500 | 0 | 42500 | 100%
| PO2W-210000000726 | Demo ceiling tiles | 40000 | 0 | 40000 | 100%
| PO2W-210000000884 | Demo ceiling tiles | 117500 | 0 | 117500 | 100%
| PO2W-210000001556 | Demo ceiling tiles | 97500 | 0 | 97500 | 100%
| PO2W-210000001838 | Demo ceiling tiles | 130000 | 0 | 130000 | 100%
| PO2W-210000002060 | Demo ceiling tiles | 82500 | 0 | 82500 | 100%
| PO2W-210000002308 | Demo ceiling tiles | 52500 | 0 | 52500 | 100%
| PO2W-210000002615 | Demo ceiling tiles | 17000 | 0 | 17000 | 100%
| PO2W-220000000024 | Demo ceiling tiles | 19000 | 0 | 19000 | 100%
Integrated Pest Control Management | PO2W-210000000362 | Termite service | 785 | 0 | 785 | 100%
LACOE | N/A | Remaining funds-dep. into District's debt service fund & close acct. | 11211.58 | 0 | 11211.58 | 100%
Lakeshore Learning Materials | PO2W-200000004769 | Furniture | 19922.5 | 0 | 19922.5 | 100%
| PO2W-200000004771 | Furniture | 19922.5 | 0 | 19922.5 | 100%
| PO2W-200000004776 | Furniture | 19922.5 | 0 | 19922.5 | 100%
| PO2W-210000001119 | Furniture | 99612.49 | 0 | 99612.49 | 100%
| PO2W-210000001120 | Furniture | 59495.79 | 0 | 59495.79 | 100%
| PO2W-210000001495 | Furniture | 39663.86 | 0 | 39663.86 | 100%
| PO2W-210000001496 | Furniture | 79327.7 | 0 | 79327.7 | 100%
| PO3W-200000001592 | Furniture | 70376.3 | 0 | 70376.3 | 100%
| PO3W-200000001593 | Furniture | 23186.9 | 0 | 23186.9 | 100%
| PO3W-200000001595 | Furniture | 7509.33 | 0 | 7509.33 | 100%
| PO3W-200000001596 | Furniture | 430328.22 | 0 | 430328.22 | 100%
| PO3W-200000001597 | Furniture | 14794.34 | 0 | 14794.34 | 100%
Lenovo Education | PO3W-210000000004 | Desktop computer(s) | 60105.66 | 0 | 60105.66 | 100%
| PO3W-210000000005 | Desktop computer(s) | 1040.26 | 0 | 1040.26 | 100%
Lightspeed | PO3W-210000000029 | Voice amplification system | 112534.25 | 0 | 112534.25 | 100%
| PO3W-210000001079 | Voice amplification system | 45825.82 | 0 | 45825.82 | 100%
| PO3W-210000002832 | Voice amplification system | 76987.31 | 0 | 76987.31 | 100%
Martin Container | PO1-210000000608 | Rental of container(s) | 20712.44 | 0 | 20712.44 | 100%
| PO2W-200000005018 | Rental of container(s) | 3328.8 | 0 | 3328.8 | 100%
| PO2W-200000005019 | Rental of container(s) | 1664.4 | 0 | 1664.4 | 100%
| PO2W-200000005020 | Rental of container(s) | 3328.8 | 0 | 3328.8 | 100%
| PO2W-200000005021 | Rental of container(s) | 3344 | 0 | 3344 | 100%
| PO2W-200000005377 | Move containers | 500 | 0 | 500 | 100%
| PO2W-200000005483 | Rental of container(s) | 1664.4 | 0 | 1664.4 | 100%
| PO2W-200000005484 | Rental of container(s) | 1664.4 | 0 | 1664.4 | 100%
| PO2W-200000005485 | Rental of container(s) | 1672 | 0 | 1672 | 100%
| PO2W-210000000059 | Rental of container(s) | 1664.4 | 0 | 1664.4 | 100%
| PO2W-210000000340 | Rental of container(s) | 1664.4 | 0 | 1664.4 | 100%
| PO2W-210000000883 | Rental of container(s) | 0 | 0 | 0 | 0%
| PO2W-210000000975 | Rental of container(s) | 4993.2 | 0 | 4993.2 | 100%
| PO2W-210000001957 | Rental of container(s) | 687.5 | 0 | 687.5 | 100%
Masek Consulting | PO1-210000000427 | Asbestos & lead-based paint survey | 41200 | 0 | 41200 | 100%
| PO2W-200000003739 | Pre-demo asbestos & lead-based paint | 1280 | 0 | 1280 | 100%
| PO2W-200000004872 | Asbestos survey | 800 | 0 | 800 | 100%
| PO2W-200000004873 | Asbestos survey | 850 | 0 | 850 | 100%
| PO2W-200000004874 | Asbestos & lead-based paint survey | 2800 | 0 | 2800 | 100%
| PO2W-200000004875 | Asbestos & lead-based paint survey | 2530 | 0 | 2530 | 100%
| PO2W-200000004876 | Asbestos & lead-based paint survey | 2500 | 0 | 2500 | 100%
| PO2W-200000005314 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005315 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005316 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005317 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005318 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005319 | Asbestos & lead-based paint survey | 2550 | 0 | 2550 | 100%
| PO2W-200000005320 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005321 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005322 | Asbestos & lead-based paint survey | 2800 | 0 | 2800 | 100%
| PO2W-200000005323 | Asbestos & lead-based paint survey | 2500 | 0 | 2500 | 100%
| PO2W-200000005324 | Asbestos & lead-based paint survey | 2670 | 0 | 2670 | 100%
| PO2W-200000005325 | Asbestos & lead-based paint survey | 2700 | 0 | 2700 | 100%
| PO2W-200000005326 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005327 | Asbestos & lead-based paint survey | 2600 | 0 | 2600 | 100%
| PO2W-200000005389 | Asbestos & lead-based paint survey | 2800 | 0 | 2800 | 100%
| PO2W-200000005390 | Asbestos & lead-based paint survey | 2900 | 0 | 2900 | 100%
| PO2W-200000005391 | Asbestos & lead-based paint survey | 2950 | 0 | 2950 | 100%
| PO2W-200000005392 | Asbestos & lead-based paint survey | 2950 | 0 | 2950 | 100%
| PO2W-200000005393 | Asbestos & lead-based paint survey | 2950 | 0 | 2950 | 100%
| PO2W-200000005541 | Asbestos & lead-based paint survey | 1200 | 0 | 1200 | 100%
| PO2W-210000000060 | Oversight asbestos abatement | 7775 | 6125 | 13900 | 55.94%
| PO2W-210000000061 | Oversight asbestos abatement | 3975 | 4125 | 8100 | 49.07%
| PO2W-210000000062 | Oversight asbestos abatement | 6775 | 4300 | 11075 | 61.17%
| PO2W-210000000585 | Oversight asbestos abatement | 825 | 100 | 925 | 89.19%
| PO2W-210000000976 | Oversight asbestos abatement | 4400 | 1600 | 6000 | 73.33%
| PO2W-210000000986 | Asbestos & lead-based paint survey | 1480 | 0 | 1480 | 100%
| PO2W-210000000995 | Oversight asbestos abatement | 6950 | 4850 | 11800 | 58.9%
| PO2W-210000001656 | Oversight asbestos abatement | 11350 | 5400 | 16750 | 67.76%
| PO2W-210000001978 | Oversight asbestos abatement | 7910 | 1440 | 9350 | 84.6%
| PO2W-210000001982 | Oversight asbestos abatement | 4750 | 2200 | 6950 | 68.35%
| PO2W-210000002278 | Oversight asbestos abatement | 5250 | 2300 | 7550 | 69.54%
| PO2W-210000002602 | Oversight asbestos abatement | 1275 | 0 | 1275 | 100%
| PO2W-220000000246 | Oversight asbestos abatement | 2200 | 400 | 2600 | 84.62%
Masters Contracting Corp | PO2W-200000005828 | Contractor | 2106113.2 | 114886.8 | 2221000 | 94.83%
| PO2W-200000005829 | Contractor | 2066496.06 | 123503.94 | 2190000 | 94.36%
| PO2W-210000000983 | Contractor | 3624250 | 190750 | 3815000 | 95%
| (blank) | Contractor | 0 | 70740.41 | 70740.41 | 0%
Mijac Alarm | PO1-200000000617 | Alarm for portables | 715.5 | 0 | 715.5 | 100%
Mobile Modular Management Corp | PO2W-200000001050, 19-107587 | Portable classrooms | 236959.74 | 0 | 236959.74 | 100%
| PO2W-200000003188, PO2W-200000001048, 19-107585 | Portable classrooms | 218488.74 | 0 | 218488.74 | 100%
| PO2W-200000003189, PO2W-200000001048, 19-107585 | Portable classrooms | 21300 | 0 | 21300 | 100%
| PO2W-200000003190, PO2W-200000001052, 19-107584 | Portable classrooms | 436977.48 | 0 | 436977.48 | 100%
| PO2W-200000003191, PO2W-200000001052, 19-107584 | Portable classrooms | 42600 | 0 | 42600 | 100%
| PO2W-200000003192, PO2W-200000001051, 19-107586 | Portable classrooms | 218488.74 | 0 | 218488.74 | 100%
| PO2W-2-00000003193, PO2W-200000001051, 19-107586 | Portable classrooms (4) | 21300 | 0 | 21300 | 100%
Montague DeRose and Associates, LLC | N/A | Municipal Advisory services | 42740 | 0 | 42740 | 100%
Moody's Investors Service, Inc. | N/A | Rating Agency Fee | 37000 | 0 | 37000 | 100%
Office p.S. Architecture + Urbanism + Design | 19-100488 | Architect | 7100 | 0 | 7100 | 100%
| 19-100492, 18-109572 | Architect | 8015.94 | 0 | 8015.94 | 100%
| 19-100493, 18-109556 | Architect | 2572.98 | 0 | 2572.98 | 100%
| PO2W-200000001909 | Architect | 411.5 | 0 | 411.5 | 100%
| PO2W-200000001924 | Architect | 3894.95 | 0 | 3894.95 | 100%
Optima | PO1-200000000833 | Contractor | 18000 | 0 | 18000 | 100%
| PO1-200000000834 | Contractor | 3502.75 | 2997.25 | 6500 | 53.89%
| PO2W-200000002201 | Contractor | 8200 | 0 | 8200 | 100%
| PO2W-200000002202 | Contractor | 6800 | 0 | 6800 | 100%
| PO2W-200000002203 | Contractor | 11000 | 0 | 11000 | 100%
| PO2W-200000002204 | Contractor | 6600 | 0 | 6600 | 100%
Orbach Huff Suarez + Henderson, LLP | PO1-200000001027 | Attorney fees | 8733.13 | 0 | 8733.13 | 100%
| PO2W-200000004282 | Attorney fees | 3492.5 | 0 | 3492.5 | 100%
PBK Architects | PO1-210000000684 | Architect | 0 | 407500 | 407500 | 0%
| PO1-210000000685 | Architect | 0 | 222000 | 222000 | 0%
| PO1-210000000686 | Architect | 0 | 95400 | 95400 | 0%
| PO1-210000000687 | Architect | 0 | 95400 | 95400 | 0%
| PO2W-200000000098 | Architect | 209760 | 38240 | 248000 | 84.58%
| PO2W-200000000856, 19-100508, 18-109907 | Architect | 126314 | 27286 | 153600 | 82.24%
| PO2W-200000001212, 19-100509, 18-109906 | Architect | 71499.7 | 5833.3 | 77333 | 92.46%
PI Manufacturing Corp. | PO2W-210000001349 | Computer cables | 1086.6 | 0 | 1086.6 | 100%
| PO2W-210000001350 | Computer cables | 1023.66 | 0 | 1023.66 | 100%
| PO2W-210000001351 | Computer cables | 1086.6 | 0 | 1086.6 | 100%
| PO3W-210000001095 | Computer cables | 2147.08 | 0 | 2147.08 | 100%
| PO3W-210000001096 | Computer cables | 1351.5 | 0 | 1351.5 | 100%
Rbc Capital Markets, LLC | N/A | Hotel reimb. during rating agency presentations in San Francisco | 647.68 | 0 | 647.68 | 100%
|  | Reimb. Continuing Disclosure Report (DAC) | 550 | 0 | 550 | 100%
S&P Global Ratings | N/A | Rating Agency Fee | 35000 | 0 | 35000 | 100%
San Gabriel Tribune | PO2W-210000000381 | Newspaper Advertisement | 632 | 0 | 632 | 100%
| PO2W-210000000882 | Newspaper Advertisement | 905 | 0 | 905 | 100%
| PO2W-220000000052 | Newspaper Advertisement | 1088 | 0 | 1088 | 100%
Schneider Electric Buildings Americas, Inc | PO1-200000000729 | Contractor | 4190257.62 | 383156.38 | 4573414 | 91.62%
Suburban Water Systems | 19-105188 | Fire flow testing | 636 | 0 | 636 | 100%
| 19-106996 | Deposit for engineering costs to construct (1) 6" public fire hydrant | 2000 | 0 | 2000 | 100%
| 19-108466 | Fire flow testing | 212 | 0 | 212 | 100%
| PO2W-200000002737 | Deposit to construct (1) 6" public fire hydrant | 3000 | 0 | 3000 | 100%
| PO2W-200000003306 | Remaining balance to construct (1) 6" public fire hydrant | 39498.69 | 0 | 39498.69 | 100%
| PO2W-200000003382 | Fire flow testing | 212 | 0 | 212 | 100%
| PO2W-220000000489 | Fire flow testing | 0 | 0 | 0 | 0%
SVA Architects, Inc | PO2W-200000001213, 19-100506, 18-109555 | Architect | 114638.48 | 3545.52 | 118184 | 97%
| PO2W-200000001214, 19-101982 | Architect | 5304.95 | 14695.05 | 20000 | 26.52%
| PO2W-200000004424 | DSA fees | 2250 | 0 | 2250 | 100%
tBP Architecture | PO1-2000000000899, 19-104053, JVER21-187 | Architect | 7125 | 0 | 7125 | 100%
| PO1-200000000846 | Architect | 29625 | 71000 | 100625 | 29.44%
| PO2W-200000000855, 19-109962 | Architect | 87000 | 0 | 87000 | 100%
| PO2W-210000000680 | Architect | 124085 | 47265 | 171350 | 72.42%
| PO2W-210000000984 | Architect | 292500 | 97500 | 390000 | 75%
TDM Architects, Inc | PO2W-200000000857, 19-100486 | Architect | 40706.18 | 17184 | 57890.18 | 70.32%
| PO2W-200000000858, 19-100485 | Architect | 92714.72 | 0 | 92714.72 | 100%
| PO2W-200000000859, 19-100470 | Architect | 98588.72 | 0 | 98588.72 | 100%
| PO2W-200000005063 | Architect | 11306 | 0 | 11306 | 100%
| PO2W-200000005064 | Architect | 12980 | 0 | 12980 | 100%
| PO2W-210000002075 | Architect | 8116.8 | 5411.2 | 13528 | 60%
| PO2W-210000002222 | Architect | 63549.3 | 273555.7 | 337105 | 18.85%
| PO2W-210000002223 | Architect | 62733.26 | 182791.74 | 245525 | 25.55%
| PO2W-210000002224 | Architect | 33100.45 | 211457.55 | 244558 | 13.53%
| PO2W-210000002225 | Architect | 33387.03 | 234636.97 | 268024 | 12.46%
| PO2W-210000002226 | Architect | 29545.89 | 157014.11 | 186560 | 15.84%
| PO2W-210000002227 | Architect | 0 | 79400 | 79400 | 0%
| PO2W-210000002228 | Architect | 4646.25 | 92753.75 | 97400 | 4.77%
| PO2W-210000002229 | Architect | 0 | 79400 | 79400 | 0%
| PO2W-210000002230 | Architect | 0 | 79400 | 79400 | 0%
| PO2W-210000002231 | Architect | 0 | 97400 | 97400 | 0%
Team Inspections | PO2W-200000000103 | General inspection | 13200 | 0 | 13200 | 100%
| PO2W-200000002809 | General inspection | 8875 | 500 | 9375 | 94.67%
| PO2W-200000002811 | General inspection | 8125 | 0 | 8125 | 100%
| PO2W-200000002812 | General inspection | 6875 | 0 | 6875 | 100%
| PO2W-200000003303 | General inspection | 1200 | 10800 | 12000 | 10%
| PO2W-200000004017 | General inspection | 8250 | 0 | 8250 | 100%
| PO2W-200000004113 | General inspection | 39740 | 0 | 39740 | 100%
| PO2W-200000004960 | General inspection | 34720 | 0 | 34720 | 100%
| PO2W-200000004961 | General inspection | 32620 | 2100 | 34720 | 93.95%
| PO2W-200000004962 | General inspection | 25480 | 9240 | 34720 | 73.39%
| PO2W-200000005057 | General inspection | 8250 | 0 | 8250 | 100%
| PO2W-200000005058 | General inspection | 16000 | 500 | 16500 | 96.97%
| PO2W-210000000015 | General inspection | 0 | 16000 | 16000 | 0%
| PO2W-210000000455 | General inspection | 7350 | 0 | 7350 | 100%
| PO2W-210000000977 | General inspection | 11750 | 500 | 12250 | 95.92%
| PO2W-210000001035 | General inspection | 141264 | 60624 | 201888 | 69.97%
| PO2W-210000001492 | General inspection | 24500 | 0 | 24500 | 100%
| PO2W-210000001574 | General inspection | 11750 | 500 | 12250 | 95.92%
| PO2W-210000001585 | General inspection | 28700 | 0 | 28700 | 100%
Telenet VOIP, Inc | PO1-200000000662 | Contractor | 1203703.55 | 76018.92 | 1279722.47 | 94.06%
| PO2W-200000004053 | Contractor | 32632.23 | -2.9559e-12 | 32632.23 | 100%
| PO2W-200000004671 | Contractor | 270103.06 | 2932.25 | 273035.31 | 98.93%
| PO2W-200000004928 | Contractor | 214104.43 | 12468.65 | 226573.08 | 94.5%
| PO2W-200000004929 | Contractor | 178201.64 | 10713.12 | 188914.76 | 94.33%
| PO2W-200000004930 | Contractor | 375687.03 | 3048.76 | 378735.79 | 99.2%
| PO2W-200000004931 | Contractor | 217149.4 | -1.5461e-11 | 217149.4 | 100%
| PO2W-210000001738 | Contractor | 0 | 4174.01 | 4174.01 | 0%
| PO2W-210000001875 | Contractor | 0 | 7609.69 | 7609.69 | 0%
| PO2W-210000002213 | Contractor | 2766.97 | 12074.54 | 14841.51 | 18.64%
Temp Power Sytems | PO2W-200000000234 | Rental of power pole | 8497 | 3325 | 11822 | 71.87%
| (blank) | Rental of power pole | 0 | 7665 | 7665 | 0%
The Nazerian Group | PO2W-200000005821 | Contractor | 1308029.35 | 186093.65 | 1494123 | 87.54%
| (blank) | Contractor | 0 | 39293.51 | 39293.51 | 0%
U.S. Bank National Association | N/A | Trust fees | 550 | 0 | 550 | 100%
Uline | PO3W-200000000288 | Furniture | 8041.68 | 0 | 8041.68 | 100%
| PO3W-210000001074 | Carts | 791.69 | 0 | 791.69 | 100%
| PO3W-210000002899 | Hydraulic stacker | 1834.13 | 0 | 1834.13 | 100%
| PO3W-210000002998 | Hydraulic stacker | 1834.13 | 0 | 1834.13 | 100%
Underwriter's fees | N/A | Underwriter's fees | 175000 | 0 | 175000 | 100%
Universal Asphalt | PO2W-200000000237 | Contractor | 13776 | 0 | 13776 | 100%
| PO2W-200000000632 | Contractor | 4879 | 0 | 4879 | 100%
| PO2W-200000001460 | Contractor | 13902 | 0 | 13902 | 100%
| PO2W-200000004878 | Contractor | 99262.8 | 0 | 99262.8 | 100%
| PO2W-210000000545 | Contractor | 7275 | 0 | 7275 | 100%
Warehouse | XSRQ-210000001812 | Boxes | 318.12 | 0 | 318.12 | 100%
| XSRQ-210000001813 | Boxes | 265.1 | 0 | 265.1 | 100%
| XSRQ-210000002024 | Boxes | 180.27 | 0 | 180.27 | 100%
| XSRQ-210000002207 | Boxes & tapes | 484.13 | 0 | 484.13 | 100%
| XSRQ-210000002247 | Boxes & tapes | 484.13 | 0 | 484.13 | 100%
| XSRQ-210000002249 | Boxes & tapes | 759.34 | 0 | 759.34 | 100%
| XSRQ-210000002484 | Boxes & tapes | 795.26 | 0 | 795.26 | 100%
| XSRQ-210000002565 | Boxes | 466.62 | 0 | 466.62 | 100%
| XSRQ-210000002810 | Boxes | 648.09 | 0 | 648.09 | 100%
| XSRQ-220000000064 | Soap dispensers | 0 | 0 | 0 | 100%
| XSRQ-220000000112 | Paper towel dispenser | 918.52 | 0 | 918.52 | 100%
| XSRQ-220000000971 | Paper towel dispenser | 86.19 | 0 | 86.19 | 100%
Williams Tree Service | PO2W-210000000996 | Tree Service | 3400 | 0 | 3400 | 100%
Wolverine Fence | PO2W-200000003505 | Contractor | 4725 | 0 | 4725 | 100%
| PO2W-200000004114 | Contractor | 17340 | 0 | 17340 | 100%
| PO2W-210000000063 | Contractor | 3500 | 0 | 3500 | 100%
| PO2W-210000000383 | Contractor | 4800 | 0 | 4800 | 100%
| PO2W-210000001036 | Contractor | 1500 | 0 | 1500 | 100%
| PO2W-210000001628 | Contractor | 8100 | 0 | 8100 | 100%
Megaphone Ink | PO2W-220000001278 | Decal | 455.52 | 0 | 455.52 | 100%
Southern California Edison Co (SCE) | PO2W-220000001329 | Temporary power | 1072 | 0 | 1072 | 100%
Southern California News Group | (blank) | Newspaper Advertisement | 0 | 611.25 | 611.25 | 0%
Bay Alarm Company | PO2W-220000001857 | Alarm for portables | 0 | 2782.5 | 2782.5 | 0%
Total: |  |  | 40797565.55 | 6919563.56 | 47717129.11 | 332.3769

## Measure BB_Comparison_Data
Combined Headers | Phase | Project Site | Project Description | Category | Preliminary Budget | Proposed Budget | Total Exp. & Committed | Completed Amount | % Completion
Amar-21st Century-Advertisement | 0 | Amar | 21st Century | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Asbestos oversight/survey/abatement | 0 | Amar | 21st Century | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-CM/PM Management | 0 | Amar | 21st Century | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Construction Contingency | 0 | Amar | 21st Century | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Contractor | 0 | Amar | 21st Century | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Design | 0 | Amar | 21st Century | Design | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-DSA Fees | 0 | Amar | 21st Century | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-DSA Inspection | 0 | Amar | 21st Century | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-DSA Special Inspection | 0 | Amar | 21st Century | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Environ Consultant | 0 | Amar | 21st Century | Environ Consultant | 0 | 0 | 2600 | 2600 | 100%
Amar-21st Century-FF & E | 0 | Amar | 21st Century | FF & E | N/A | No Proposal Provided | 92679.97 | 92679.97 | 100%
Amar-21st Century-Legal Services | 0 | Amar | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Move classroom | 0 | Amar | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Move Management | 0 | Amar | 21st Century | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Reprographics | 0 | Amar | 21st Century | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century-Technology | 0 | Amar | 21st Century | Technology | N/A | N/A | 19593.92 | 19593.92 | 100%
Amar-Ceiling replacement-CM/PM Management | 0 | Amar | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Ceiling replacement-Contractor | 0 | Amar | Ceiling replacement | Contractor | 180685 | 180685 | 180685 | 17165.07 | 9.5%
Amar-Drinking fountain replacement-Advertisement | 0 | Amar | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking fountain replacement-Contractor | 0 | Amar | Drinking fountain replacement | Contractor | 8200 | 8200 | 8200 | 8200 | 100%
Amar-Drinking fountain replacement-Design | 0 | Amar | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking fountain replacement-DSA Fees | 0 | Amar | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking fountain replacement-DSA Inspection | 0 | Amar | Drinking fountain replacement | DSA Inspection | 0 | 0 | 1200 | 0 | 0%
Amar-Drinking fountain replacement-DSA Special Inspection | 0 | Amar | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking fountain replacement-Environ Consultant | 0 | Amar | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking fountain replacement-Reprographics | 0 | Amar | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm-Advertisement | 0 | Amar | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm-Contractor | 0 | Amar | Fire Alarm | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm-Design | 0 | Amar | Fire Alarm | Design | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm-DSA Fees | 0 | Amar | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm-DSA Inspection | 0 | Amar | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm-Environ Consultant | 0 | Amar | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm-Reprographics | 0 | Amar | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Advertisement | 0 | Amar | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Alarm | 0 | Amar | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-CM/PM Management | 0 | Amar | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Construction Contingency | 0 | Amar | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Contractor | 0 | Amar | Interim Housing | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Design | 0 | Amar | Interim Housing | Design | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-DSA Fees | 0 | Amar | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-DSA Inspection | 0 | Amar | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-DSA Special Inspection | 0 | Amar | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Environ Consultant | 0 | Amar | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-FF & E | 0 | Amar | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Legal Services | 0 | Amar | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Modular Buildings | 0 | Amar | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Move Management | 0 | Amar | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Reprographics | 0 | Amar | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Technology | 0 | Amar | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century-Advertisement | 3 | Baldwin | 21st Century | Advertisement | 2001.44 | N/A | 0 | 0 | #DIV/0!
Baldwin-21st Century-Asbestos oversight/survey/abatement | 3 | Baldwin | 21st Century | Asbestos oversight/survey/abatement | 105000 | N/A | 0 | 0 | #DIV/0!
Baldwin-21st Century-CM/PM Management | 3 | Baldwin | 21st Century | CM/PM Management | 319939.4 | N/A | 300512 | 8370 | 2.785%
Baldwin-21st Century-Construction Contingency | 3 | Baldwin | 21st Century | Construction Contingency | 311903.6 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century-Contractor | 3 | Baldwin | 21st Century | Contractor | 3327075.7 | N/A | 56500 | 56500 | 100%
Baldwin-21st Century-Design | 3 | Baldwin | 21st Century | Design | 382092.83 | 325287 | 337105 | 63549.3 | 18.85%
Baldwin-21st Century-DSA Fees | 3 | Baldwin | 21st Century | DSA Fees | 63682.14 | N/A | 0 | 0 | #DIV/0!
Baldwin-21st Century-DSA Inspection | 3 | Baldwin | 21st Century | DSA Inspection | 54584.69 | N/A | 0 | 0 | #DIV/0!
Baldwin-21st Century-DSA Special Inspection | 3 | Baldwin | 21st Century | DSA Special Inspection | 45487.24 | N/A | 0 | 0 | #DIV/0!
Baldwin-21st Century-Environ Consultant | 3 | Baldwin | 21st Century | Environ Consultant | 16011.51 | N/A | 2600 | 2600 | 100%
Baldwin-21st Century-FF & E | 3 | Baldwin | 21st Century | FF & E | 580000 | No Proposal Provided | 43907.51 | 43907.51 | 100%
Baldwin-21st Century-Legal Services | 3 | Baldwin | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century-Move classroom | 3 | Baldwin | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century-Move Management | 3 | Baldwin | 21st Century | Move Management | 14555.92 | N/A | 0 | 0 | #DIV/0!
Baldwin-21st Century-Reprographics | 3 | Baldwin | 21st Century | Reprographics | 2001.44 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century-Technology | 3 | Baldwin | 21st Century | Technology | 580000 | No Proposal Provided | 247447.45 | 247447.45 | 100%
Baldwin-Ceiling replacement-CM/PM Management | 3 | Baldwin | Ceiling replacement | CM/PM Management | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Ceiling replacement-Contractor | 3 | Baldwin | Ceiling replacement | Contractor | 315644 | 315644 | 315644 | 299861.8 | 95%
Baldwin-Drinking fountain replacement-Advertisement | 3 | Baldwin | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking fountain replacement-Contractor | 3 | Baldwin | Drinking fountain replacement | Contractor | 22500 | N/A | 0 | 0 | #DIV/0!
Baldwin-Drinking fountain replacement-Design | 3 | Baldwin | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking fountain replacement-DSA Fees | 3 | Baldwin | Drinking fountain replacement | DSA Fees | 0 | No Proposal Provided | 1050 | 1050 | 100%
Baldwin-Drinking fountain replacement-DSA Inspection | 3 | Baldwin | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking fountain replacement-DSA Special Inspection | 3 | Baldwin | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking fountain replacement-Environ Consultant | 3 | Baldwin | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking fountain replacement-Reprographics | 3 | Baldwin | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm-Advertisement | 3 | Baldwin | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm-Contractor | 3 | Baldwin | Fire Alarm | Contractor | 435000 | 338939 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm-Design | 3 | Baldwin | Fire Alarm | Design | 0 | No Proposal Provided | 12125 | 0 | 0%
Baldwin-Fire Alarm-DSA Fees | 3 | Baldwin | Fire Alarm | DSA Fees | 0 | No Proposal Provided | 1020 | 1020 | 100%
Baldwin-Fire Alarm-DSA Inspection | 3 | Baldwin | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm-Environ Consultant | 3 | Baldwin | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm-Reprographics | 3 | Baldwin | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Advertisement | 3 | Baldwin | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Alarm | 3 | Baldwin | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-CM/PM Management | 3 | Baldwin | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Construction Contingency | 3 | Baldwin | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Contractor | 3 | Baldwin | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Design | 3 | Baldwin | Interim Housing | Design | 80000 | N/A | 79400 | 0 | 0%
Baldwin-Interim Housing-DSA Fees | 3 | Baldwin | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-DSA Inspection | 3 | Baldwin | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-DSA Special Inspection | 3 | Baldwin | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Environ Consultant | 3 | Baldwin | Interim Housing | Environ Consultant | N/A | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-FF & E | 3 | Baldwin | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Legal Services | 3 | Baldwin | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Modular Buildings | 3 | Baldwin | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Move Management | 3 | Baldwin | Interim Housing | Move Management | N/A | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Reprographics | 3 | Baldwin | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Technology | 3 | Baldwin | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century-Advertisement | 6 | Bixby | 21st Century | Advertisement | 1477.85 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-Asbestos oversight/survey/abatement | 6 | Bixby | 21st Century | Asbestos oversight/survey/abatement | 73500 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-CM/PM Management | 6 | Bixby | 21st Century | CM/PM Management | 235166.16 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-Construction Contingency | 6 | Bixby | 21st Century | Construction Contingency | 230307.4 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-Contractor | 6 | Bixby | 21st Century | Contractor | 2456689.04 | N/A | 52500 | 52500 | 100%
Bixby-21st Century-Design | 6 | Bixby | 21st Century | Design | 282134.63 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-DSA Fees | 6 | Bixby | 21st Century | DSA Fees | 47022.44 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-DSA Inspection | 6 | Bixby | 21st Century | DSA Inspection | 40304.95 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-DSA Special Inspection | 6 | Bixby | 21st Century | DSA Special Inspection | 20152.47 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-Environ Consultant | 6 | Bixby | 21st Century | Environ Consultant | 11822.78 | No Proposal Provided | 2600 | 2600 | 100%
Bixby-21st Century-FF & E | 6 | Bixby | 21st Century | FF & E | 420000 | No Proposal Provided | 20720.61 | 20720.61 | 100%
Bixby-21st Century-Legal Services | 6 | Bixby | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century-Move classroom | 6 | Bixby | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century-Move Management | 6 | Bixby | 21st Century | Move Management | 10747.99 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-Reprographics | 6 | Bixby | 21st Century | Reprographics | 1477.85 | N/A | 0 | 0 | #DIV/0!
Bixby-21st Century-Technology | 6 | Bixby | 21st Century | Technology | 420000 | No Proposal Provided | 92588.93 | 92588.93 | 100%
Bixby-Ceiling replacement-CM/PM Management | 6 | Bixby | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Ceiling replacement-Contractor | 6 | Bixby | Ceiling replacement | Contractor | 296805 | 296805 | 296805 | 281964.75 | 95%
Bixby-Drinking fountain replacement-Advertisement | 6 | Bixby | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking fountain replacement-Contractor | 6 | Bixby | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Bixby-Drinking fountain replacement-Design | 6 | Bixby | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking fountain replacement-DSA Fees | 6 | Bixby | Drinking fountain replacement | DSA Fees | 0 | 0 | 1050 | 1050 | 100%
Bixby-Drinking fountain replacement-DSA Inspection | 6 | Bixby | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking fountain replacement-DSA Special Inspection | 6 | Bixby | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking fountain replacement-Environ Consultant | 6 | Bixby | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking fountain replacement-Reprographics | 6 | Bixby | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm-Advertisement | 6 | Bixby | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm-Contractor | 6 | Bixby | Fire Alarm | Contractor | 315000 | N/A | 0 | 0 | #DIV/0!
Bixby-Fire Alarm-Design | 6 | Bixby | Fire Alarm | Design | 12125 | No Proposal Provided | 12125 | 0 | 0%
Bixby-Fire Alarm-DSA Fees | 6 | Bixby | Fire Alarm | DSA Fees | 0 | 0 | 870 | 870 | 100%
Bixby-Fire Alarm-DSA Inspection | 6 | Bixby | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm-Environ Consultant | 6 | Bixby | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm-Reprographics | 6 | Bixby | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Advertisement | 6 | Bixby | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Alarm | 6 | Bixby | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-CM/PM Management | 6 | Bixby | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Construction Contingency | 6 | Bixby | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Contractor | 6 | Bixby | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Design | 6 | Bixby | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-DSA Fees | 6 | Bixby | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-DSA Inspection | 6 | Bixby | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-DSA Special Inspection | 6 | Bixby | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Environ Consultant | 6 | Bixby | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-FF & E | 6 | Bixby | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Legal Services | 6 | Bixby | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Modular Buildings | 6 | Bixby | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Move Management | 6 | Bixby | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Reprographics | 6 | Bixby | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Technology | 6 | Bixby | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
California-21st Century-Advertisement | 3 | California | 21st Century | Advertisement | 2752.27 | 0 | 0 | 0 | #DIV/0!
California-21st Century-Asbestos oversight/survey/abatement | 3 | California | 21st Century | Asbestos oversight/survey/abatement | 52500 | N/A | 0 | 0 | #DIV/0!
California-21st Century-CM/PM Management | 3 | California | 21st Century | CM/PM Management | 173510.81 | N/A | 187820 | 17610 | 9.376%
California-21st Century-Construction Contingency | 3 | California | 21st Century | Construction Contingency | 200164.87 | N/A | 0 | 0 | #DIV/0!
California-21st Century-Contractor | 3 | California | 21st Century | Contractor | 2168827.2 | No Proposal Provided | 52744.48 | 52744.48 | 100%
California-21st Century-Design | 3 | California | 21st Century | Design | 210173.13 | 270392 | 245525 | 62733.26 | 25.55%
California-21st Century-DSA Fees | 3 | California | 21st Century | DSA Fees | 40032.98 | N/A | 0 | 0 | #DIV/0!
California-21st Century-DSA Inspection | 3 | California | 21st Century | DSA Inspection | 35028.85 | N/A | 0 | 0 | #DIV/0!
California-21st Century-DSA Special Inspection | 3 | California | 21st Century | DSA Special Inspection | 15012.37 | N/A | 0 | 0 | #DIV/0!
California-21st Century-Environ Consultant | 3 | California | 21st Century | Environ Consultant | 28125 | No Proposal Provided | 2600 | 2600 | 100%
California-21st Century-FF & E | 3 | California | 21st Century | FF & E | 300000 | No Proposal Provided | 20720.61 | 20720.61 | 100%
California-21st Century-Legal Services | 3 | California | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
California-21st Century-Move classroom | 3 | California | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
California-21st Century-Move Management | 3 | California | 21st Century | Move Management | 8006.6 | N/A | 0 | 0 | #DIV/0!
California-21st Century-Reprographics | 3 | California | 21st Century | Reprographics | 2752.27 | N/A | 0 | 0 | #DIV/0!
California-21st Century-Technology | 3 | California | 21st Century | Technology | 300000 | No Proposal Provided | 135404.69 | 135404.69 | 100%
California-Ceiling replacement-CM/PM Management | 3 | California | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
California-Ceiling replacement-Contractor | 3 | California | Ceiling replacement | Contractor | 236982 | 236982 | 236982 | 225132.9 | 95%
California-Drinking fountain replacement-Advertisement | 3 | California | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking fountain replacement-Contractor | 3 | California | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
California-Drinking fountain replacement-Design | 3 | California | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking fountain replacement-DSA Fees | 3 | California | Drinking fountain replacement | DSA Fees | 1050 | No Proposal Provided | 1050 | 1050 | 100%
California-Drinking fountain replacement-DSA Inspection | 3 | California | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking fountain replacement-DSA Special Inspection | 3 | California | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking fountain replacement-Environ Consultant | 3 | California | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking fountain replacement-Reprographics | 3 | California | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
California-Fire Alarm-Advertisement | 3 | California | Fire Alarm | Advertisement | 400 | 0 | 0 | 0 | #DIV/0!
California-Fire Alarm-Contractor | 3 | California | Fire Alarm | Contractor | 225000 | 226573.08 | 226573.08 | 214104.43 | 94.5%
California-Fire Alarm-Design | 3 | California | Fire Alarm | Design | 12125 | No Proposal Provided | 12125 | 12125 | 100%
California-Fire Alarm-DSA Fees | 3 | California | Fire Alarm | DSA Fees | 780 | No Proposal Provided | 2070 | 2070 | 100%
California-Fire Alarm-DSA Inspection | 3 | California | Fire Alarm | DSA Inspection | 12250 | No Proposal Provided | 12250 | 11750 | 95.92%
California-Fire Alarm-Environ Consultant | 3 | California | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
California-Fire Alarm-Reprographics | 3 | California | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Advertisement | 3 | California | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Alarm | 3 | California | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-CM/PM Management | 3 | California | Interim Housing | CM/PM Management | 51590 | N/A | 0 | 0 | #DIV/0!
California-Interim Housing-Construction Contingency | 3 | California | Interim Housing | Construction Contingency | 77000 | N/A | 0 | 0 | #DIV/0!
California-Interim Housing-Contractor | 3 | California | Interim Housing | Contractor | 770000 | N/A | 0 | 0 | #DIV/0!
California-Interim Housing-Design | 3 | California | Interim Housing | Design | 80000 | N/A | 97400 | 4646.25 | 4.77%
California-Interim Housing-DSA Fees | 3 | California | Interim Housing | DSA Fees | 16100 | N/A | 0 | 0 | #DIV/0!
California-Interim Housing-DSA Inspection | 3 | California | Interim Housing | DSA Inspection | 13800 | N/A | 0 | 0 | #DIV/0!
California-Interim Housing-DSA Special Inspection | 3 | California | Interim Housing | DSA Special Inspection | 13800 | N/A | 0 | 0 | #DIV/0!
California-Interim Housing-Environ Consultant | 3 | California | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-FF & E | 3 | California | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Legal Services | 3 | California | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Modular Buildings | 3 | California | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
California-Interim Housing-Move Management | 3 | California | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Reprographics | 3 | California | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
California-Interim Housing-Technology | 3 | California | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-21st Century-Advertisement | 1 | Cedarlane | 21st Century | Advertisement | 1728.75 | No Proposal Provided | 301.67 | 301.67 | 100%
Cedarlane-21st Century-Asbestos oversight/survey/abatement | 1 | Cedarlane | 21st Century | Asbestos oversight/survey/abatement | 100000 | Incl in GC | 0 | 0 | #DIV/0!
Cedarlane-21st Century-CM/PM Management | 1 | Cedarlane | 21st Century | CM/PM Management | 276221.51 | 187122 | 187122 | 187100 | 99.99%
Cedarlane-21st Century-Construction Contingency | 1 | Cedarlane | 21st Century | Construction Contingency | 269407.5 | 299000 | 0 | 0 | #DIV/0!
Cedarlane-21st Century-Contractor | 1 | Cedarlane | 21st Century | Contractor | 2873769.8 | 2990000 | 2992332.6 | 2842832.6 | 95%
Cedarlane-21st Century-Design | 1 | Cedarlane | 21st Century | Design | 330033.62 | 153600 | 153600 | 126314 | 82.24%
Cedarlane-21st Century-DSA Fees | 1 | Cedarlane | 21st Century | DSA Fees | 55005.6 | No Proposal Provided | 22159 | 22159 | 100%
Cedarlane-21st Century-DSA Inspection | 1 | Cedarlane | 21st Century | DSA Inspection | 47147.66 | 93600 | 93600 | 68832 | 73.54%
Cedarlane-21st Century-DSA Special Inspection | 1 | Cedarlane | 21st Century | DSA Special Inspection | 23573 | N/A | 0 | 0 | #DIV/0!
Cedarlane-21st Century-Environ Consultant | 1 | Cedarlane | 21st Century | Environ Consultant | 13829.98 | 0 | 39575 | 29325 | 74.1%
Cedarlane-21st Century-FF & E | 1 | Cedarlane | 21st Century | FF & E | 500000 | 453688.26 | 529098.91 | 500271.06 | 94.55%
Cedarlane-21st Century-Legal Services | 1 | Cedarlane | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-21st Century-Move classroom | 1 | Cedarlane | 21st Century | Move classroom | 0 | 0 | 2548.26 | 2548.26 | 100%
Cedarlane-21st Century-Move Management | 1 | Cedarlane | 21st Century | Move Management | 12572.71 | 0 | 3723 | 3723 | 100%
Cedarlane-21st Century-Reprographics | 1 | Cedarlane | 21st Century | Reprographics | 1728.75 | 0 | 216.16 | 216.16 | 100%
Cedarlane-21st Century-Technology | 1 | Cedarlane | 21st Century | Technology | 500000 | 54618.01 | 469884.98 | 469884.98 | 100%
Cedarlane-Ceiling replacement-CM/PM Management | 1 | Cedarlane | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Ceiling replacement-Contractor | 1 | Cedarlane | Ceiling replacement | Contractor | N/A | N/A | 0 | 0 | #DIV/0!
Cedarlane-Drinking fountain replacement-Advertisement | 1 | Cedarlane | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking fountain replacement-Contractor | 1 | Cedarlane | Drinking fountain replacement | Contractor | 18000 | N/A | 0 | 0 | #DIV/0!
Cedarlane-Drinking fountain replacement-Design | 1 | Cedarlane | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking fountain replacement-DSA Fees | 1 | Cedarlane | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking fountain replacement-DSA Inspection | 1 | Cedarlane | Drinking fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 1200 | 0 | 0%
Cedarlane-Drinking fountain replacement-DSA Special Inspection | 1 | Cedarlane | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking fountain replacement-Environ Consultant | 1 | Cedarlane | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking fountain replacement-Reprographics | 1 | Cedarlane | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Fire Alarm-Advertisement | 1 | Cedarlane | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Fire Alarm-Contractor | 1 | Cedarlane | Fire Alarm | Contractor | 116400 | 116400 | 106399.99 | 101079.99 | 95%
Cedarlane-Fire Alarm-Design | 1 | Cedarlane | Fire Alarm | Design | 47500 | 47500 | 4750 | 4750 | 100%
Cedarlane-Fire Alarm-DSA Fees | 1 | Cedarlane | Fire Alarm | DSA Fees | 1290 | No Proposal Provided | 1290 | 1290 | 100%
Cedarlane-Fire Alarm-DSA Inspection | 1 | Cedarlane | Fire Alarm | DSA Inspection | 8250 | No Proposal Provided | 8250 | 8250 | 100%
Cedarlane-Fire Alarm-Environ Consultant | 1 | Cedarlane | Fire Alarm | Environ Consultant | 0 | 0 | 800 | 800 | 100%
Cedarlane-Fire Alarm-Reprographics | 1 | Cedarlane | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Advertisement | 1 | Cedarlane | Interim Housing | Advertisement | 850 | 0 | 301.66 | 301.66 | 100%
Cedarlane-Interim Housing-Alarm | 1 | Cedarlane | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-CM/PM Management | 1 | Cedarlane | Interim Housing | CM/PM Management | Incl in 21st | Incl in 21st | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Construction Contingency | 1 | Cedarlane | Interim Housing | Construction Contingency | 82500 | 82500 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Contractor | 1 | Cedarlane | Interim Housing | Contractor | 825000 | 825000 | 898952.41 | 786962 | 87.54%
Cedarlane-Interim Housing-Design | 1 | Cedarlane | Interim Housing | Design | 100000 | 117105 | 77333 | 71499.7 | 92.46%
Cedarlane-Interim Housing-DSA Fees | 1 | Cedarlane | Interim Housing | DSA Fees | 17000 | No Proposal Provided | 3052.5 | 3052.5 | 100%
Cedarlane-Interim Housing-DSA Inspection | 1 | Cedarlane | Interim Housing | DSA Inspection | 14875 | 14688 | 14688 | 14688 | 100%
Cedarlane-Interim Housing-DSA Special Inspection | 1 | Cedarlane | Interim Housing | DSA Special Inspection | 10625 | 16920 | 16920 | 10317.5 | 60.98%
Cedarlane-Interim Housing-Environ Consultant | 1 | Cedarlane | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-FF & E | 1 | Cedarlane | Interim Housing | FF & E | 0 | 0 | 35280.9 | 35280.9 | 100%
Cedarlane-Interim Housing-Legal Services | 1 | Cedarlane | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Modular Buildings | 1 | Cedarlane | Interim Housing | Modular Buildings | 239788.74 | 239788.74 | 239788.74 | 239788.74 | 100%
Cedarlane-Interim Housing-Move Management | 1 | Cedarlane | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Reprographics | 1 | Cedarlane | Interim Housing | Reprographics | 850 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Technology | 1 | Cedarlane | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century-Advertisement | 7 | Del Valle | 21st Century | Advertisement | 1217.69 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century-Asbestos oversight/survey/abatement | 7 | Del Valle | 21st Century | Asbestos oversight/survey/abatement | 48872.24 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century-CM/PM Management | 7 | Del Valle | 21st Century | CM/PM Management | 192978.68 | N/A | 0 | 0 | #DIV/0!
Del Valle-21st Century-Construction Contingency | 7 | Del Valle | 21st Century | Construction Contingency | 189763.3 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century-Contractor | 7 | Del Valle | 21st Century | Contractor | 2024205.12 | 0 | 48872.24 | 48872.24 | 100%
Del Valle-21st Century-Design | 7 | Del Valle | 21st Century | Design | 232466.68 | N/A | 0 | 0 | #DIV/0!
Del Valle-21st Century-DSA Fees | 7 | Del Valle | 21st Century | DSA Fees | 38744.45 | N/A | 0 | 0 | #DIV/0!
Del Valle-21st Century-DSA Inspection | 7 | Del Valle | 21st Century | DSA Inspection | 33209.53 | N/A | 0 | 0 | #DIV/0!
Del Valle-21st Century-DSA Special Inspection | 7 | Del Valle | 21st Century | DSA Special Inspection | 16604.76 | N/A | 0 | 0 | #DIV/0!
Del Valle-21st Century-Environ Consultant | 7 | Del Valle | 21st Century | Environ Consultant | 12176.83 | N/A | 2600 | 2600 | 100%
Del Valle-21st Century-FF & E | 7 | Del Valle | 21st Century | FF & E | 340000 | No Request for Proposal | 41441.22 | 41441.22 | 100%
Del Valle-21st Century-Legal Services | 7 | Del Valle | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century-Move classroom | 7 | Del Valle | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century-Move Management | 7 | Del Valle | 21st Century | Move Management | 8855.87 | N/A | 0 | 0 | #DIV/0!
Del Valle-21st Century-Reprographics | 7 | Del Valle | 21st Century | Reprographics | 1217.69 | N/A | 0 | 0 | #DIV/0!
Del Valle-21st Century-Technology | 7 | Del Valle | 21st Century | Technology | 340000 | 0 | 150792.64 | 150792.64 | 100%
Del Valle-Ceiling replacement-CM/PM Management | 7 | Del Valle | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Ceiling replacement-Contractor | 7 | Del Valle | Ceiling replacement | Contractor | 333183 | 333183 | 333183 | 316523.85 | 95%
Del Valle-Drinking fountain replacement-Advertisement | 7 | Del Valle | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking fountain replacement-Contractor | 7 | Del Valle | Drinking fountain replacement | Contractor | 15000 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking fountain replacement-Design | 7 | Del Valle | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking fountain replacement-DSA Fees | 7 | Del Valle | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking fountain replacement-DSA Inspection | 7 | Del Valle | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking fountain replacement-DSA Special Inspection | 7 | Del Valle | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking fountain replacement-Environ Consultant | 7 | Del Valle | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking fountain replacement-Reprographics | 7 | Del Valle | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm-Advertisement | 7 | Del Valle | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm-Contractor | 7 | Del Valle | Fire Alarm | Contractor | 255000 | N/A | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm-Design | 7 | Del Valle | Fire Alarm | Design | 48500 | 48500 | 48500 | 36375 | 75%
Del Valle-Fire Alarm-DSA Fees | 7 | Del Valle | Fire Alarm | DSA Fees | 0 | 0 | 870 | 870 | 100%
Del Valle-Fire Alarm-DSA Inspection | 7 | Del Valle | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm-Environ Consultant | 7 | Del Valle | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm-Reprographics | 7 | Del Valle | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Advertisement | 7 | Del Valle | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Alarm | 7 | Del Valle | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-CM/PM Management | 7 | Del Valle | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Construction Contingency | 7 | Del Valle | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Contractor | 7 | Del Valle | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Design | 7 | Del Valle | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-DSA Fees | 7 | Del Valle | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-DSA Inspection | 7 | Del Valle | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-DSA Special Inspection | 7 | Del Valle | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Environ Consultant | 7 | Del Valle | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-FF & E | 7 | Del Valle | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Legal Services | 7 | Del Valle | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Modular Buildings | 7 | Del Valle | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Move Management | 7 | Del Valle | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Reprographics | 7 | Del Valle | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Technology | 7 | Del Valle | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Advertisement | 0 | Dibble | 21st Century | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Asbestos oversight/survey/abatement | 0 | Dibble | 21st Century | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-CM/PM Management | 0 | Dibble | 21st Century | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Construction Contingency | 0 | Dibble | 21st Century | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Contractor | 0 | Dibble | 21st Century | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Design | 0 | Dibble | 21st Century | Design | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-DSA Fees | 0 | Dibble | 21st Century | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-DSA Inspection | 0 | Dibble | 21st Century | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-DSA Special Inspection | 0 | Dibble | 21st Century | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Environ Consultant | 0 | Dibble | 21st Century | Environ Consultant | 2700 | No Proposal Provided | 2700 | 2700 | 100%
Dibble-21st Century-FF & E | 0 | Dibble | 21st Century | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Legal Services | 0 | Dibble | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Move classroom | 0 | Dibble | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Move Management | 0 | Dibble | 21st Century | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Reprographics | 0 | Dibble | 21st Century | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century-Technology | 0 | Dibble | 21st Century | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Ceiling replacement-CM/PM Management | 0 | Dibble | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Ceiling replacement-Contractor | 0 | Dibble | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking fountain replacement-Advertisement | 0 | Dibble | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking fountain replacement-Contractor | 0 | Dibble | Drinking fountain replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking fountain replacement-Design | 0 | Dibble | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking fountain replacement-DSA Fees | 0 | Dibble | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking fountain replacement-DSA Inspection | 0 | Dibble | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking fountain replacement-DSA Special Inspection | 0 | Dibble | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking fountain replacement-Environ Consultant | 0 | Dibble | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking fountain replacement-Reprographics | 0 | Dibble | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm-Advertisement | 0 | Dibble | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm-Contractor | 0 | Dibble | Fire Alarm | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm-Design | 0 | Dibble | Fire Alarm | Design | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm-DSA Fees | 0 | Dibble | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm-DSA Inspection | 0 | Dibble | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm-Environ Consultant | 0 | Dibble | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm-Reprographics | 0 | Dibble | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Advertisement | 0 | Dibble | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Alarm | 0 | Dibble | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-CM/PM Management | 0 | Dibble | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Construction Contingency | 0 | Dibble | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Contractor | 0 | Dibble | Interim Housing | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Design | 0 | Dibble | Interim Housing | Design | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-DSA Fees | 0 | Dibble | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-DSA Inspection | 0 | Dibble | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-DSA Special Inspection | 0 | Dibble | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Environ Consultant | 0 | Dibble | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-FF & E | 0 | Dibble | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Legal Services | 0 | Dibble | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Modular Buildings | 0 | Dibble | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Move Management | 0 | Dibble | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Reprographics | 0 | Dibble | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Technology | 0 | Dibble | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century-Advertisement | 0 | District Office | 21st Century | Advertisement | 0 | 0 | 1243.25 | 632 | 50.83%
District Office-21st Century-Asbestos oversight/survey/abatement | 0 | District Office | 21st Century | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century-CM/PM Management | 0 | District Office | 21st Century | CM/PM Management | 450000 | 450000 | 750000 | 500905 | 66.79%
District Office-21st Century-Construction Contingency | 0 | District Office | 21st Century | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century-Contractor | 0 | District Office | 21st Century | Contractor | 392859.44 | No Proposal Provided | 278159.12 | 259042.4 | 93.13%
District Office-21st Century-Design | 0 | District Office | 21st Century | Design | 2022.86 | 2022.86 | 0 | 0 | #DIV/0!
District Office-21st Century-DSA Fees | 0 | District Office | 21st Century | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century-DSA Inspection | 0 | District Office | 21st Century | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century-DSA Special Inspection | 0 | District Office | 21st Century | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century-Environ Consultant | 0 | District Office | 21st Century | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century-FF & E | 0 | District Office | 21st Century | FF & E | 2678.05 | No Proposal Provided | 84862.09 | 84862.09 | 100%
District Office-21st Century-Legal Services | 0 | District Office | 21st Century | Legal Services | 774388.14 | No Proposal Provided | 102571.44 | 67648.94 | 65.95%
District Office-21st Century-Move classroom | 0 | District Office | 21st Century | Move classroom | 146130.33 | N/A | 0 | 0 | #DIV/0!
District Office-21st Century-Move Management | 0 | District Office | 21st Century | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century-Reprographics | 0 | District Office | 21st Century | Reprographics | 7950.01 | No Proposal Provided | 4267.04 | 229.19 | 5.371%
District Office-21st Century-Technology | 0 | District Office | 21st Century | Technology | 434528.6 | No Proposal Provided | 434528.61 | 434528.61 | 100%
District Office-Ceiling replacement-CM/PM Management | 0 | District Office | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Ceiling replacement-Contractor | 0 | District Office | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Cost of Issuance-Issuance costs | 0 | District Office | Cost of Issuance | Issuance costs | 1572741.59 | No Proposal Provided | 465750 | 465750 | 100%
District Office-Design guidelines-Design | 0 | District Office | Design guidelines | Design | 29500 | 29500 | 29500 | 24000 | 81.36%
District Office-Fire Alarm-Advertisement | 0 | District Office | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm-Contractor | 0 | District Office | Fire Alarm | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm-Design | 0 | District Office | Fire Alarm | Design | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm-DSA Fees | 0 | District Office | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm-DSA Inspection | 0 | District Office | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm-Environ Consultant | 0 | District Office | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm-Reprographics | 0 | District Office | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Advertisement | 0 | District Office | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Alarm | 0 | District Office | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-CM/PM Management | 0 | District Office | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Construction Contingency | 0 | District Office | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Contractor | 0 | District Office | Interim Housing | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Design | 0 | District Office | Interim Housing | Design | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-DSA Fees | 0 | District Office | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-DSA Inspection | 0 | District Office | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-DSA Special Inspection | 0 | District Office | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Environ Consultant | 0 | District Office | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-FF & E | 0 | District Office | Interim Housing | FF & E | 621114.33 | 621114.33 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Legal Services | 0 | District Office | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Modular Buildings | 0 | District Office | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Move Management | 0 | District Office | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Reprographics | 0 | District Office | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Technology | 0 | District Office | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Advertisement | 4 | Fairgrove | 21st Century | Advertisement | 2585.85 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Asbestos oversight/survey/abatement | 4 | Fairgrove | 21st Century | Asbestos oversight/survey/abatement | 129500 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-CM/PM Management | 4 | Fairgrove | 21st Century | CM/PM Management | 412143.23 | N/A | 413204 | 13010 | 3.149%
Fairgrove-21st Century-Construction Contingency | 4 | Fairgrove | 21st Century | Construction Contingency | 402977.3 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Contractor | 4 | Fairgrove | 21st Century | Contractor | 4298558.86 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Design | 4 | Fairgrove | 21st Century | Design | 493661.3 | N/A | 407500 | 0 | 0%
Fairgrove-21st Century-DSA Fees | 4 | Fairgrove | 21st Century | DSA Fees | 82276.88 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-DSA Inspection | 4 | Fairgrove | 21st Century | DSA Inspection | 70523.04 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-DSA Special Inspection | 4 | Fairgrove | 21st Century | DSA Special Inspection | 35261.52 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Environ Consultant | 4 | Fairgrove | 21st Century | Environ Consultant | 20686.76 | N/A | 2700 | 2700 | 100%
Fairgrove-21st Century-FF & E | 4 | Fairgrove | 21st Century | FF & E | 740000 | 0 | 41441.21 | 41441.21 | 100%
Fairgrove-21st Century-Legal Services | 4 | Fairgrove | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Move classroom | 4 | Fairgrove | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Move Management | 4 | Fairgrove | 21st Century | Move Management | 18806.14 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Reprographics | 4 | Fairgrove | 21st Century | Reprographics | 2585.85 | N/A | 0 | 0 | #DIV/0!
Fairgrove-21st Century-Technology | 4 | Fairgrove | 21st Century | Technology | 740000 | 0 | 449375.25 | 449375.25 | 100%
Fairgrove-Ceiling replacement-CM/PM Management | 4 | Fairgrove | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Ceiling replacement-Contractor | 4 | Fairgrove | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking fountain replacement-Advertisement | 4 | Fairgrove | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking fountain replacement-Contractor | 4 | Fairgrove | Drinking fountain replacement | Contractor | 30000 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking fountain replacement-Design | 4 | Fairgrove | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking fountain replacement-DSA Fees | 4 | Fairgrove | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking fountain replacement-DSA Inspection | 4 | Fairgrove | Drinking fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 1200 | 0 | 0%
Fairgrove-Drinking fountain replacement-DSA Special Inspection | 4 | Fairgrove | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking fountain replacement-Environ Consultant | 4 | Fairgrove | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking fountain replacement-Reprographics | 4 | Fairgrove | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Fire Alarm-Advertisement | 4 | Fairgrove | Fire Alarm | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Fire Alarm-Contractor | 4 | Fairgrove | Fire Alarm | Contractor | 555000 | 378735.79 | 378735.79 | 375687.03 | 99.2%
Fairgrove-Fire Alarm-Design | 4 | Fairgrove | Fire Alarm | Design | 12125 | No Proposal Provided | 12125 | 11155 | 92%
Fairgrove-Fire Alarm-DSA Fees | 4 | Fairgrove | Fire Alarm | DSA Fees | 1230 | No Proposal Provided | 1230 | 1230 | 100%
Fairgrove-Fire Alarm-DSA Inspection | 4 | Fairgrove | Fire Alarm | DSA Inspection | 14350 | No Proposal Provided | 14350 | 14350 | 100%
Fairgrove-Fire Alarm-Environ Consultant | 4 | Fairgrove | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Fire Alarm-Reprographics | 4 | Fairgrove | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Advertisement | 4 | Fairgrove | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Alarm | 4 | Fairgrove | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-CM/PM Management | 4 | Fairgrove | Interim Housing | CM/PM Management | 37150 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Construction Contingency | 4 | Fairgrove | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Contractor | 4 | Fairgrove | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Design | 4 | Fairgrove | Interim Housing | Design | 80000 | N/A | 95400 | 0 | 0%
Fairgrove-Interim Housing-DSA Fees | 4 | Fairgrove | Interim Housing | DSA Fees | 12250 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-DSA Inspection | 4 | Fairgrove | Interim Housing | DSA Inspection | 10500 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-DSA Special Inspection | 4 | Fairgrove | Interim Housing | DSA Special Inspection | 10500 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Environ Consultant | 4 | Fairgrove | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-FF & E | 4 | Fairgrove | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Legal Services | 4 | Fairgrove | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Modular Buildings | 4 | Fairgrove | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Move Management | 4 | Fairgrove | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Reprographics | 4 | Fairgrove | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Technology | 4 | Fairgrove | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-21st Century-Advertisement | 2 | Grandview | 21st Century | Advertisement | 2087.79 | N/A | 0 | 0 | #DIV/0!
Grandview-21st Century-Asbestos oversight/survey/abatement | 2 | Grandview | 21st Century | Asbestos oversight/survey/abatement | 105000 | N/A | 0 | 0 | #DIV/0!
Grandview-21st Century-CM/PM Management | 2 | Grandview | 21st Century | CM/PM Management | 333089.53 | 194205 | 194205 | 186795 | 96.18%
Grandview-21st Century-Construction Contingency | 2 | Grandview | 21st Century | Construction Contingency | 325360 | N/A | 0 | 0 | #DIV/0!
Grandview-21st Century-Contractor | 2 | Grandview | 21st Century | Contractor | 3470615.12 | N/A | 0 | 0 | #DIV/0!
Grandview-21st Century-Design | 2 | Grandview | 21st Century | Design | 398577.39 | 248631 | 260300 | 197181 | 75.75%
Grandview-21st Century-DSA Fees | 2 | Grandview | 21st Century | DSA Fees | 66429.56 | 35235.88 | 35235.88 | 35235.88 | 100%
Grandview-21st Century-DSA Inspection | 2 | Grandview | 21st Century | DSA Inspection | 56939.63 | N/A | 0 | 0 | #DIV/0!
Grandview-21st Century-DSA Special Inspection | 2 | Grandview | 21st Century | DSA Special Inspection | 28469.81 | N/A | 0 | 0 | #DIV/0!
Grandview-21st Century-Environ Consultant | 2 | Grandview | 21st Century | Environ Consultant | 16702.29 | No Proposal Provided | 2900 | 2900 | 100%
Grandview-21st Century-FF & E | 2 | Grandview | 21st Century | FF & E | 600000 | No Proposal Provided | 30227.07 | 30227.07 | 100%
Grandview-21st Century-Legal Services | 2 | Grandview | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-21st Century-Move classroom | 2 | Grandview | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-21st Century-Move Management | 2 | Grandview | 21st Century | Move Management | 15183.9 | N/A | 0 | 0 | #DIV/0!
Grandview-21st Century-Reprographics | 2 | Grandview | 21st Century | Reprographics | 2087.79 | N/A | 0 | 0 | #DIV/0!
Grandview-21st Century-Technology | 2 | Grandview | 21st Century | Technology | 600000 | No Proposal Provided | 272255.51 | 272255.51 | 100%
Grandview-Ceiling replacement-CM/PM Management | 2 | Grandview | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Ceiling replacement-Contractor | 2 | Grandview | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking fountain replacement-Advertisement | 2 | Grandview | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking fountain replacement-Contractor | 2 | Grandview | Drinking fountain replacement | Contractor | 30000 | N/A | 0 | 0 | #DIV/0!
Grandview-Drinking fountain replacement-Design | 2 | Grandview | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking fountain replacement-DSA Fees | 2 | Grandview | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking fountain replacement-DSA Inspection | 2 | Grandview | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking fountain replacement-DSA Special Inspection | 2 | Grandview | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking fountain replacement-Environ Consultant | 2 | Grandview | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking fountain replacement-Reprographics | 2 | Grandview | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Fire Alarm-Advertisement | 2 | Grandview | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Fire Alarm-Contractor | 2 | Grandview | Fire Alarm | Contractor | 450000 | 152797 | 146640.11 | 138358.1 | 94.35%
Grandview-Fire Alarm-Design | 2 | Grandview | Fire Alarm | Design | 11875 | No Proposal Provided | 11875 | 11875 | 100%
Grandview-Fire Alarm-DSA Fees | 2 | Grandview | Fire Alarm | DSA Fees | 1230 | No Proposal Provided | 1451.25 | 1451.25 | 100%
Grandview-Fire Alarm-DSA Inspection | 2 | Grandview | Fire Alarm | DSA Inspection | 0 | 0 | 9375 | 8875 | 94.67%
Grandview-Fire Alarm-Environ Consultant | 2 | Grandview | Fire Alarm | Environ Consultant | 0 | 0 | 850 | 850 | 100%
Grandview-Fire Alarm-Reprographics | 2 | Grandview | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Advertisement | 2 | Grandview | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Alarm | 2 | Grandview | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-CM/PM Management | 2 | Grandview | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Construction Contingency | 2 | Grandview | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Contractor | 2 | Grandview | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Design | 2 | Grandview | Interim Housing | Design | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-DSA Fees | 2 | Grandview | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-DSA Inspection | 2 | Grandview | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-DSA Special Inspection | 2 | Grandview | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Environ Consultant | 2 | Grandview | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-FF & E | 2 | Grandview | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Legal Services | 2 | Grandview | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Modular Buildings | 2 | Grandview | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Move Management | 2 | Grandview | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Reprographics | 2 | Grandview | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Technology | 2 | Grandview | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Advertisement | 3 | Grazide | 21st Century | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Asbestos oversight/survey/abatement | 3 | Grazide | 21st Century | Asbestos oversight/survey/abatement | 70000 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-CM/PM Management | 3 | Grazide | 21st Century | CM/PM Management | 0 | 0 | 206602 | 10410 | 5.039%
Grazide-21st Century-Construction Contingency | 3 | Grazide | 21st Century | Construction Contingency | 218338 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Contractor | 3 | Grazide | 21st Century | Contractor | 2329011.45 | No Proposal Provided | 37500 | 37500 | 100%
Grazide-21st Century-Design | 3 | Grazide | 21st Century | Design | 267471.69 | 285705 | 244558 | 33100.45 | 13.53%
Grazide-21st Century-DSA Fees | 3 | Grazide | 21st Century | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-DSA Inspection | 3 | Grazide | 21st Century | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-DSA Special Inspection | 3 | Grazide | 21st Century | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Environ Consultant | 3 | Grazide | 21st Century | Environ Consultant | 0 | 0 | 2550 | 2550 | 100%
Grazide-21st Century-FF & E | 3 | Grazide | 21st Century | FF & E | 400000 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Legal Services | 3 | Grazide | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Move classroom | 3 | Grazide | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Move Management | 3 | Grazide | 21st Century | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Reprographics | 3 | Grazide | 21st Century | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century-Technology | 3 | Grazide | 21st Century | Technology | 400000 | 0 | 187241.76 | 187241.76 | 100%
Grazide-Ceiling replacement-CM/PM Management | 3 | Grazide | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Ceiling replacement-Contractor | 3 | Grazide | Ceiling replacement | Contractor | 0 | 0 | 281598 | 267518.1 | 95%
Grazide-Drinking fountain replacement-Advertisement | 3 | Grazide | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking fountain replacement-Contractor | 3 | Grazide | Drinking fountain replacement | Contractor | 15000 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking fountain replacement-Design | 3 | Grazide | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking fountain replacement-DSA Fees | 3 | Grazide | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking fountain replacement-DSA Inspection | 3 | Grazide | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking fountain replacement-DSA Special Inspection | 3 | Grazide | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking fountain replacement-Environ Consultant | 3 | Grazide | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking fountain replacement-Reprographics | 3 | Grazide | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm-Advertisement | 3 | Grazide | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm-Contractor | 3 | Grazide | Fire Alarm | Contractor | 300000 | N/A | 0 | 0 | #DIV/0!
Grazide-Fire Alarm-Design | 3 | Grazide | Fire Alarm | Design | 0 | 0 | 12125 | 0 | 0%
Grazide-Fire Alarm-DSA Fees | 3 | Grazide | Fire Alarm | DSA Fees | 0 | 0 | 960 | 960 | 100%
Grazide-Fire Alarm-DSA Inspection | 3 | Grazide | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm-Environ Consultant | 3 | Grazide | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm-Reprographics | 3 | Grazide | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Advertisement | 3 | Grazide | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Alarm | 3 | Grazide | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-CM/PM Management | 3 | Grazide | Interim Housing | CM/PM Management | 33600 | N/A | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Construction Contingency | 3 | Grazide | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Contractor | 3 | Grazide | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Design | 3 | Grazide | Interim Housing | Design | 80000 | N/A | 79400 | 0 | 0%
Grazide-Interim Housing-DSA Fees | 3 | Grazide | Interim Housing | DSA Fees | 15750 | N/A | 0 | 0 | #DIV/0!
Grazide-Interim Housing-DSA Inspection | 3 | Grazide | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Grazide-Interim Housing-DSA Special Inspection | 3 | Grazide | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Environ Consultant | 3 | Grazide | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-FF & E | 3 | Grazide | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Legal Services | 3 | Grazide | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Modular Buildings | 3 | Grazide | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Move Management | 3 | Grazide | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Reprographics | 3 | Grazide | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Technology | 3 | Grazide | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century-Advertisement | 7 | Kwis | 21st Century | Advertisement | 1344.05 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-Asbestos oversight/survey/abatement | 7 | Kwis | 21st Century | Asbestos oversight/survey/abatement | 66500 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-CM/PM Management | 7 | Kwis | 21st Century | CM/PM Management | 213618.67 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-Construction Contingency | 7 | Kwis | 21st Century | Construction Contingency | 209456.6 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-Contractor | 7 | Kwis | 21st Century | Contractor | 2234273.55 | N/A | 49000 | 49000 | 100%
Kwis-21st Century-Design | 7 | Kwis | 21st Century | Design | 256591.67 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-DSA Fees | 7 | Kwis | 21st Century | DSA Fees | 42765.28 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-DSA Inspection | 7 | Kwis | 21st Century | DSA Inspection | 36655.95 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-DSA Special Inspection | 7 | Kwis | 21st Century | DSA Special Inspection | 18327.98 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-Environ Consultant | 7 | Kwis | 21st Century | Environ Consultant | 10752.41 | No Proposal Provided | 2600 | 2600 | 100%
Kwis-21st Century-FF & E | 7 | Kwis | 21st Century | FF & E | 380000 | No Proposal Provided | 38238.17 | 38238.17 | 100%
Kwis-21st Century-Legal Services | 7 | Kwis | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century-Move classroom | 7 | Kwis | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century-Move Management | 7 | Kwis | 21st Century | Move Management | 9774.92 | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century-Reprographics | 7 | Kwis | 21st Century | Reprographics | 1344.05 | N/A | 0 | 0 | #DIV/0!
Kwis-21st Century-Technology | 7 | Kwis | 21st Century | Technology | 380000 | No Proposal Provided | 119134.89 | 119134.89 | 100%
Kwis-Ceiling replacement-CM/PM Management | 7 | Kwis | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Ceiling replacement-Contractor | 7 | Kwis | Ceiling replacement | Contractor | 271028 | 271208 | 271028 | 257476.6 | 95%
Kwis-Drinking fountain replacement-Advertisement | 7 | Kwis | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking fountain replacement-Contractor | 7 | Kwis | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Kwis-Drinking fountain replacement-Design | 7 | Kwis | Drinking fountain replacement | Design | 0 | N/A | 0 | 0 | #DIV/0!
Kwis-Drinking fountain replacement-DSA Fees | 7 | Kwis | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking fountain replacement-DSA Inspection | 7 | Kwis | Drinking fountain replacement | DSA Inspection | 0 | 0 | 1200 | 0 | 0%
Kwis-Drinking fountain replacement-DSA Special Inspection | 7 | Kwis | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking fountain replacement-Environ Consultant | 7 | Kwis | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking fountain replacement-Reprographics | 7 | Kwis | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm-Advertisement | 7 | Kwis | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm-Contractor | 7 | Kwis | Fire Alarm | Contractor | 285000 | N/A | 0 | 0 | #DIV/0!
Kwis-Fire Alarm-Design | 7 | Kwis | Fire Alarm | Design | 48500 | No Proposal Provided | 48500 | 36375 | 75%
Kwis-Fire Alarm-DSA Fees | 7 | Kwis | Fire Alarm | DSA Fees | 0 | 0 | 891 | 891 | 100%
Kwis-Fire Alarm-DSA Inspection | 7 | Kwis | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm-Environ Consultant | 7 | Kwis | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm-Reprographics | 7 | Kwis | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Advertisement | 7 | Kwis | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Alarm | 7 | Kwis | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-CM/PM Management | 7 | Kwis | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Construction Contingency | 7 | Kwis | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Contractor | 7 | Kwis | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Design | 7 | Kwis | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-DSA Fees | 7 | Kwis | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-DSA Inspection | 7 | Kwis | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-DSA Special Inspection | 7 | Kwis | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Environ Consultant | 7 | Kwis | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-FF & E | 7 | Kwis | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Legal Services | 7 | Kwis | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Modular Buildings | 7 | Kwis | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Move Management | 7 | Kwis | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Reprographics | 7 | Kwis | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Technology | 7 | Kwis | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Advertisement | 5 | La Puente HS | 21st Century | Advertisement | 5093.8 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Asbestos oversight/survey/abatement | 5 | La Puente HS | 21st Century | Asbestos oversight/survey/abatement | 224000 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-CM/PM Management | 5 | La Puente HS | 21st Century | CM/PM Management | 788769.21 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Construction Contingency | 5 | La Puente HS | 21st Century | Construction Contingency | 793815.6 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Contractor | 5 | La Puente HS | 21st Century | Contractor | 8467631.01 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Design | 5 | La Puente HS | 21st Century | Design | 972451.89 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-DSA Fees | 5 | La Puente HS | 21st Century | DSA Fees | 162075.32 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-DSA Inspection | 5 | La Puente HS | 21st Century | DSA Inspection | 138921.7 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-DSA Special Inspection | 5 | La Puente HS | 21st Century | DSA Special Inspection | 69460.85 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Environ Consultant | 5 | La Puente HS | 21st Century | Environ Consultant | 40750.37 | No Proposal Provided | 6900 | 6900 | 100%
La Puente HS-21st Century-FF & E | 5 | La Puente HS | 21st Century | FF & E | 1280000 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Legal Services | 5 | La Puente HS | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Move classroom | 5 | La Puente HS | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Move Management | 5 | La Puente HS | 21st Century | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Reprographics | 5 | La Puente HS | 21st Century | Reprographics | 5093.8 | N/A | 0 | 0 | #DIV/0!
La Puente HS-21st Century-Technology | 5 | La Puente HS | 21st Century | Technology | 1280000 | N/A | 505300.94 | 505300.94 | 100%
La Puente HS-Ceiling replacement-CM/PM Management | 5 | La Puente HS | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Ceiling replacement-Contractor | 5 | La Puente HS | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking fountain replacement-Advertisement | 5 | La Puente HS | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking fountain replacement-Contractor | 5 | La Puente HS | Drinking fountain replacement | Contractor | 60000 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Drinking fountain replacement-Design | 5 | La Puente HS | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking fountain replacement-DSA Fees | 5 | La Puente HS | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking fountain replacement-DSA Inspection | 5 | La Puente HS | Drinking fountain replacement | DSA Inspection | 0 | 0 | 1200 | 0 | 0%
La Puente HS-Drinking fountain replacement-DSA Special Inspection | 5 | La Puente HS | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking fountain replacement-Environ Consultant | 5 | La Puente HS | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking fountain replacement-Reprographics | 5 | La Puente HS | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm-Advertisement | 5 | La Puente HS | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm-Contractor | 5 | La Puente HS | Fire Alarm | Contractor | 1152000 | No Proposal Provided | 2717.95 | 2717.95 | 100%
La Puente HS-Fire Alarm-Design | 5 | La Puente HS | Fire Alarm | Design | 0 | 0 | 14700 | 0 | 0%
La Puente HS-Fire Alarm-DSA Fees | 5 | La Puente HS | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm-DSA Inspection | 5 | La Puente HS | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm-Environ Consultant | 5 | La Puente HS | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm-Reprographics | 5 | La Puente HS | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Advertisement | 5 | La Puente HS | Interim Housing | Advertisement | 412.5 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Alarm | 5 | La Puente HS | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-CM/PM Management | 5 | La Puente HS | Interim Housing | CM/PM Management | 54275 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Construction Contingency | 5 | La Puente HS | Interim Housing | Construction Contingency | 82500 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Contractor | 5 | La Puente HS | Interim Housing | Contractor | 825000 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Design | 5 | La Puente HS | Interim Housing | Design | 82500 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-DSA Fees | 5 | La Puente HS | Interim Housing | DSA Fees | 14437.5 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-DSA Inspection | 5 | La Puente HS | Interim Housing | DSA Inspection | 15750 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-DSA Special Inspection | 5 | La Puente HS | Interim Housing | DSA Special Inspection | 15750 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Environ Consultant | 5 | La Puente HS | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-FF & E | 5 | La Puente HS | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Legal Services | 5 | La Puente HS | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Modular Buildings | 5 | La Puente HS | Interim Housing | Modular Buildings | 225000 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Move Management | 5 | La Puente HS | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Reprographics | 5 | La Puente HS | Interim Housing | Reprographics | 412.5 | N/A | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Technology | 5 | La Puente HS | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century-Advertisement | 6 | Lassalette | 21st Century | Advertisement | 2881.28 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-Asbestos oversight/survey/abatement | 6 | Lassalette | 21st Century | Asbestos oversight/survey/abatement | 94500 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-CM/PM Management | 6 | Lassalette | 21st Century | CM/PM Management | 304893.42 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-Construction Contingency | 6 | Lassalette | 21st Century | Construction Contingency | 299345.3 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-Contractor | 6 | Lassalette | 21st Century | Contractor | 3193116.32 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-Design | 6 | Lassalette | 21st Century | Design | 366708.47 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-DSA Fees | 6 | Lassalette | 21st Century | DSA Fees | 61118.08 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-DSA Inspection | 6 | Lassalette | 21st Century | DSA Inspection | 52386.92 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-DSA Special Inspection | 6 | Lassalette | 21st Century | DSA Special Inspection | 26193.46 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-Environ Consultant | 6 | Lassalette | 21st Century | Environ Consultant | 15366.83 | N/A | 2800 | 2800 | 100%
Lassalette-21st Century-FF & E | 6 | Lassalette | 21st Century | FF & E | 540000 | No Proposal Provided | 20720.61 | 20720.61 | 100%
Lassalette-21st Century-Legal Services | 6 | Lassalette | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century-Move classroom | 6 | Lassalette | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century-Move Management | 6 | Lassalette | 21st Century | Move Management | 13969.85 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-Reprographics | 6 | Lassalette | 21st Century | Reprographics | 2881.28 | N/A | 0 | 0 | #DIV/0!
Lassalette-21st Century-Technology | 6 | Lassalette | 21st Century | Technology | 540000 | No Proposal Provided | 243109.5 | 243109.5 | 100%
Lassalette-Ceiling replacement-CM/PM Management | 6 | Lassalette | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Ceiling replacement-Contractor | 6 | Lassalette | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking fountain replacement-Advertisement | 6 | Lassalette | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking fountain replacement-Contractor | 6 | Lassalette | Drinking fountain replacement | Contractor | 30000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Drinking fountain replacement-Design | 6 | Lassalette | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking fountain replacement-DSA Fees | 6 | Lassalette | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking fountain replacement-DSA Inspection | 6 | Lassalette | Drinking fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 1200 | 0 | 0%
Lassalette-Drinking fountain replacement-DSA Special Inspection | 6 | Lassalette | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking fountain replacement-Environ Consultant | 6 | Lassalette | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking fountain replacement-Reprographics | 6 | Lassalette | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm-Advertisement | 6 | Lassalette | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm-Contractor | 6 | Lassalette | Fire Alarm | Contractor | 405000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm-Design | 6 | Lassalette | Fire Alarm | Design | 12375 | No Proposal Provided | 12375 | 0 | 0%
Lassalette-Fire Alarm-DSA Fees | 6 | Lassalette | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm-DSA Inspection | 6 | Lassalette | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm-Environ Consultant | 6 | Lassalette | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm-Reprographics | 6 | Lassalette | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Advertisement | 6 | Lassalette | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Alarm | 6 | Lassalette | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-CM/PM Management | 6 | Lassalette | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Construction Contingency | 6 | Lassalette | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Contractor | 6 | Lassalette | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Design | 6 | Lassalette | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-DSA Fees | 6 | Lassalette | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-DSA Inspection | 6 | Lassalette | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-DSA Special Inspection | 6 | Lassalette | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Environ Consultant | 6 | Lassalette | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-FF & E | 6 | Lassalette | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Legal Services | 6 | Lassalette | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Modular Buildings | 6 | Lassalette | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Move Management | 6 | Lassalette | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Reprographics | 6 | Lassalette | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Technology | 6 | Lassalette | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century-Advertisement | 2 | Los Altos ES | 21st Century | Advertisement | 1328.33 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century-Asbestos oversight/survey/abatement | 2 | Los Altos ES | 21st Century | Asbestos oversight/survey/abatement | 66500 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century-CM/PM Management | 2 | Los Altos ES | 21st Century | CM/PM Management | 211697.5 | 145452 | 145452 | 145426.25 | 99.98%
Los Altos ES-21st Century-Construction Contingency | 2 | Los Altos ES | 21st Century | Construction Contingency | 207006.2 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century-Contractor | 2 | Los Altos ES | 21st Century | Contractor | 2208135.14 | 2288481 | 2338611.8 | 2223725 | 95.09%
Los Altos ES-21st Century-Design | 2 | Los Altos ES | 21st Century | Design | 0 | 0 | 105694.72 | 105694.72 | 100%
Los Altos ES-21st Century-DSA Fees | 2 | Los Altos ES | 21st Century | DSA Fees | 42264.97 | No Proposal Provided | 30129.11 | 30129.11 | 100%
Los Altos ES-21st Century-DSA Inspection | 2 | Los Altos ES | 21st Century | DSA Inspection | 36227.12 | No Proposal Provided | 34720 | 34720 | 100%
Los Altos ES-21st Century-DSA Special Inspection | 2 | Los Altos ES | 21st Century | DSA Special Inspection | 18113.56 | No Proposal Provided | 26217.5 | 14916.5 | 56.9%
Los Altos ES-21st Century-Environ Consultant | 2 | Los Altos ES | 21st Century | Environ Consultant | 10626.62 | 13900 | 16700 | 10575 | 63.32%
Los Altos ES-21st Century-FF & E | 2 | Los Altos ES | 21st Century | FF & E | 380000 | 249195.59 | 405886.01 | 386667.45 | 95.27%
Los Altos ES-21st Century-Legal Services | 2 | Los Altos ES | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century-Move classroom | 2 | Los Altos ES | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century-Move Management | 2 | Los Altos ES | 21st Century | Move Management | 9660.57 | 0 | 12975.74 | 12975.74 | 100%
Los Altos ES-21st Century-Reprographics | 2 | Los Altos ES | 21st Century | Reprographics | 1328.33 | 0 | 728.6 | 728.6 | 100%
Los Altos ES-21st Century-Technology | 2 | Los Altos ES | 21st Century | Technology | 380000 | 43694.21 | 300395.25 | 300395.25 | 100%
Los Altos ES-Ceiling replacement-CM/PM Management | 2 | Los Altos ES | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Ceiling replacement-Contractor | 2 | Los Altos ES | Ceiling replacement | Contractor | 232310 | 232310 | 232310 | 220694.5 | 95%
Los Altos ES-Drinking fountain replacement-Advertisement | 2 | Los Altos ES | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking fountain replacement-Contractor | 2 | Los Altos ES | Drinking fountain replacement | Contractor | 15000 | Incl in GC | 0 | 0 | #DIV/0!
Los Altos ES-Drinking fountain replacement-Design | 2 | Los Altos ES | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking fountain replacement-DSA Fees | 2 | Los Altos ES | Drinking fountain replacement | DSA Fees | 1050 | No Proposal Provided | 1050 | 1050 | 100%
Los Altos ES-Drinking fountain replacement-DSA Inspection | 2 | Los Altos ES | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking fountain replacement-DSA Special Inspection | 2 | Los Altos ES | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking fountain replacement-Environ Consultant | 2 | Los Altos ES | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking fountain replacement-Reprographics | 2 | Los Altos ES | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Fire Alarm-Advertisement | 2 | Los Altos ES | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Fire Alarm-Contractor | 2 | Los Altos ES | Fire Alarm | Contractor | 285000 | 91250 | 107228.53 | 100917.1 | 94.11%
Los Altos ES-Fire Alarm-Design | 2 | Los Altos ES | Fire Alarm | Design | 0 | 0 | 11875 | 11875 | 100%
Los Altos ES-Fire Alarm-DSA Fees | 2 | Los Altos ES | Fire Alarm | DSA Fees | 945 | No Proposal Provided | 0 | 0 | #DIV/0!
Los Altos ES-Fire Alarm-DSA Inspection | 2 | Los Altos ES | Fire Alarm | DSA Inspection | 12250 | No Proposal Provided | 12250 | 12250 | 100%
Los Altos ES-Fire Alarm-Environ Consultant | 2 | Los Altos ES | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Fire Alarm-Reprographics | 2 | Los Altos ES | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Advertisement | 2 | Los Altos ES | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Alarm | 2 | Los Altos ES | Interim Housing | Alarm | 3498 | No Proposal Provided | 3498 | 715.5 | 20.45%
Los Altos ES-Interim Housing-CM/PM Management | 2 | Los Altos ES | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Construction Contingency | 2 | Los Altos ES | Interim Housing | Construction Contingency | 59526 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Contractor | 2 | Los Altos ES | Interim Housing | Contractor | 254951.88 | 254951.88 | 254951.88 | 254951.88 | 100%
Los Altos ES-Interim Housing-Design | 2 | Los Altos ES | Interim Housing | Design | 57890.18 | 57890.18 | 57890.18 | 40706.18 | 70.32%
Los Altos ES-Interim Housing-DSA Fees | 2 | Los Altos ES | Interim Housing | DSA Fees | 6169.04 | No Proposal Provided | 6169.04 | 6169.04 | 100%
Los Altos ES-Interim Housing-DSA Inspection | 2 | Los Altos ES | Interim Housing | DSA Inspection | 19369.04 | No Proposal Provided | 13200 | 13200 | 100%
Los Altos ES-Interim Housing-DSA Special Inspection | 2 | Los Altos ES | Interim Housing | DSA Special Inspection | 14530 | No Proposal Provided | 14530 | 5280.5 | 36.34%
Los Altos ES-Interim Housing-Environ Consultant | 2 | Los Altos ES | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-FF & E | 2 | Los Altos ES | Interim Housing | FF & E | 1894.88 | 0 | 10486.26 | 10486.26 | 100%
Los Altos ES-Interim Housing-Legal Services | 2 | Los Altos ES | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Modular Buildings | 2 | Los Altos ES | Interim Housing | Modular Buildings | 236959.74 | 236959.74 | 236959.74 | 236959.74 | 100%
Los Altos ES-Interim Housing-Move Management | 2 | Los Altos ES | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Reprographics | 2 | Los Altos ES | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Technology | 2 | Los Altos ES | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Advertisement | 5 | Los Altos HS | 21st Century | Advertisement | 5394.01 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Asbestos oversight/survey/abatement | 5 | Los Altos HS | 21st Century | Asbestos oversight/survey/abatement | 224000 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-CM/PM Management | 5 | Los Altos HS | 21st Century | CM/PM Management | 835850.17 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Construction Contingency | 5 | Los Altos HS | 21st Century | Construction Contingency | 840601.2 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Contractor | 5 | Los Altos HS | 21st Century | Contractor | 8966693 | N/A | 19116.72 | 19116.72 | 100%
Los Altos HS-21st Century-Design | 5 | Los Altos HS | 21st Century | Design | 1029765.89 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-DSA Fees | 5 | Los Altos HS | 21st Century | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-DSA Inspection | 5 | Los Altos HS | 21st Century | DSA Inspection | 147109.41 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-DSA Special Inspection | 5 | Los Altos HS | 21st Century | DSA Special Inspection | 73554.71 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Environ Consultant | 5 | Los Altos HS | 21st Century | Environ Consultant | 43152.09 | No Proposal Provided | 4350 | 4350 | 100%
Los Altos HS-21st Century-FF & E | 5 | Los Altos HS | 21st Century | FF & E | 1360000 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Legal Services | 5 | Los Altos HS | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Move classroom | 5 | Los Altos HS | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Move Management | 5 | Los Altos HS | 21st Century | Move Management | 39229.18 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Reprographics | 5 | Los Altos HS | 21st Century | Reprographics | 5394.01 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-21st Century-Technology | 5 | Los Altos HS | 21st Century | Technology | 1360000 | N/A | 782574.99 | 782574.99 | 100%
Los Altos HS-Ceiling replacement-CM/PM Management | 5 | Los Altos HS | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Ceiling replacement-Contractor | 5 | Los Altos HS | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking fountain replacement-Advertisement | 5 | Los Altos HS | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking fountain replacement-Contractor | 5 | Los Altos HS | Drinking fountain replacement | Contractor | 60000 | 0 | 6600 | 6600 | 100%
Los Altos HS-Drinking fountain replacement-Design | 5 | Los Altos HS | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking fountain replacement-DSA Fees | 5 | Los Altos HS | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking fountain replacement-DSA Inspection | 5 | Los Altos HS | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking fountain replacement-DSA Special Inspection | 5 | Los Altos HS | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking fountain replacement-Environ Consultant | 5 | Los Altos HS | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking fountain replacement-Reprographics | 5 | Los Altos HS | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm-Advertisement | 5 | Los Altos HS | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm-Contractor | 5 | Los Altos HS | Fire Alarm | Contractor | 1224000 | 1144366.69 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm-Design | 5 | Los Altos HS | Fire Alarm | Design | 0 | 0 | 13950 | 0 | 0%
Los Altos HS-Fire Alarm-DSA Fees | 5 | Los Altos HS | Fire Alarm | DSA Fees | 0 | 0 | 5500 | 5500 | 100%
Los Altos HS-Fire Alarm-DSA Inspection | 5 | Los Altos HS | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm-Environ Consultant | 5 | Los Altos HS | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm-Reprographics | 5 | Los Altos HS | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Advertisement | 5 | Los Altos HS | Interim Housing | Advertisement | 412.5 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Alarm | 5 | Los Altos HS | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-CM/PM Management | 5 | Los Altos HS | Interim Housing | CM/PM Management | 55275 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Construction Contingency | 5 | Los Altos HS | Interim Housing | Construction Contingency | 82500 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Contractor | 5 | Los Altos HS | Interim Housing | Contractor | 825000 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Design | 5 | Los Altos HS | Interim Housing | Design | 82500 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-DSA Fees | 5 | Los Altos HS | Interim Housing | DSA Fees | 14437 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-DSA Inspection | 5 | Los Altos HS | Interim Housing | DSA Inspection | 15750 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-DSA Special Inspection | 5 | Los Altos HS | Interim Housing | DSA Special Inspection | 15750 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Environ Consultant | 5 | Los Altos HS | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-FF & E | 5 | Los Altos HS | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Legal Services | 5 | Los Altos HS | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Modular Buildings | 5 | Los Altos HS | Interim Housing | Modular Buildings | 225000 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Move Management | 5 | Los Altos HS | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Reprographics | 5 | Los Altos HS | Interim Housing | Reprographics | 412.5 | N/A | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Technology | 5 | Los Altos HS | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century-Advertisement | 4 | Los Molinos | 21st Century | Advertisement | 1282.02 | N/A | 0 | 0 | #DIV/0!
Los Molinos-21st Century-Asbestos oversight/survey/abatement | 4 | Los Molinos | 21st Century | Asbestos oversight/survey/abatement | 80500 | N/A | 0 | 0 | #DIV/0!
Los Molinos-21st Century-CM/PM Management | 4 | Los Molinos | 21st Century | CM/PM Management | 260826.25 | N/A | 281730 | 10890 | 3.865%
Los Molinos-21st Century-Construction Contingency | 4 | Los Molinos | 21st Century | Construction Contingency | 256403.7 | N/A | 0 | 0 | #DIV/0!
Los Molinos-21st Century-Contractor | 4 | Los Molinos | 21st Century | Contractor | 2735058.27 | No Proposal Provided | 37500 | 37500 | 100%
Los Molinos-21st Century-Design | 4 | Los Molinos | 21st Century | Design | 314103.51 | 281510 | 268024 | 33387.03 | 12.46%
Los Molinos-21st Century-DSA Fees | 4 | Los Molinos | 21st Century | DSA Fees | 52350.58 | N/A | 0 | 0 | #DIV/0!
Los Molinos-21st Century-DSA Inspection | 4 | Los Molinos | 21st Century | DSA Inspection | 44871.93 | N/A | 0 | 0 | #DIV/0!
Los Molinos-21st Century-DSA Special Inspection | 4 | Los Molinos | 21st Century | DSA Special Inspection | 22435.96 | N/A | 0 | 0 | #DIV/0!
Los Molinos-21st Century-Environ Consultant | 4 | Los Molinos | 21st Century | Environ Consultant | 13162.43 | No Proposal Provided | 2600 | 2600 | 100%
Los Molinos-21st Century-FF & E | 4 | Los Molinos | 21st Century | FF & E | 460000 | 0 | 21169.42 | 21169.42 | 100%
Los Molinos-21st Century-Legal Services | 4 | Los Molinos | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century-Move classroom | 4 | Los Molinos | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century-Move Management | 4 | Los Molinos | 21st Century | Move Management | 11965.85 | N/A | 0 | 0 | #DIV/0!
Los Molinos-21st Century-Reprographics | 4 | Los Molinos | 21st Century | Reprographics | 1282.02 | N/A | 0 | 0 | #DIV/0!
Los Molinos-21st Century-Technology | 4 | Los Molinos | 21st Century | Technology | 460000 | N/A | 149425.45 | 149425.45 | 100%
Los Molinos-Ceiling replacement-CM/PM Management | 4 | Los Molinos | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Ceiling replacement-Contractor | 4 | Los Molinos | Ceiling replacement | Contractor | 359035 | 359035 | 359035 | 341083.25 | 95%
Los Molinos-Drinking fountain replacement-Advertisement | 4 | Los Molinos | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking fountain replacement-Contractor | 4 | Los Molinos | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Drinking fountain replacement-Design | 4 | Los Molinos | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking fountain replacement-DSA Fees | 4 | Los Molinos | Drinking fountain replacement | DSA Fees | 0 | 0 | 1050 | 1050 | 100%
Los Molinos-Drinking fountain replacement-DSA Inspection | 4 | Los Molinos | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking fountain replacement-DSA Special Inspection | 4 | Los Molinos | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking fountain replacement-Environ Consultant | 4 | Los Molinos | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking fountain replacement-Reprographics | 4 | Los Molinos | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Fire Alarm-Advertisement | 4 | Los Molinos | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Fire Alarm-Contractor | 4 | Los Molinos | Fire Alarm | Contractor | 345000 | 188914.76 | 188914.76 | 178201.64 | 94.33%
Los Molinos-Fire Alarm-Design | 4 | Los Molinos | Fire Alarm | Design | 12125 | No Proposal Provided | 12125 | 11155 | 92%
Los Molinos-Fire Alarm-DSA Fees | 4 | Los Molinos | Fire Alarm | DSA Fees | 870 | No Proposal Provided | 870 | 870 | 100%
Los Molinos-Fire Alarm-DSA Inspection | 4 | Los Molinos | Fire Alarm | DSA Inspection | 0 | No Proposal Provided | 14350 | 14350 | 100%
Los Molinos-Fire Alarm-Environ Consultant | 4 | Los Molinos | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Fire Alarm-Reprographics | 4 | Los Molinos | Fire Alarm | Reprographics | 0 | No Proposal Provided | 422.21 | 422.21 | 100%
Los Molinos-Interim Housing-Advertisement | 4 | Los Molinos | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Alarm | 4 | Los Molinos | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-CM/PM Management | 4 | Los Molinos | Interim Housing | CM/PM Management | 37350 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Construction Contingency | 4 | Los Molinos | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Contractor | 4 | Los Molinos | Interim Housing | Contractor | 55000 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Design | 4 | Los Molinos | Interim Housing | Design | 80000 | N/A | 79400 | 0 | 0%
Los Molinos-Interim Housing-DSA Fees | 4 | Los Molinos | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-DSA Inspection | 4 | Los Molinos | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-DSA Special Inspection | 4 | Los Molinos | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Environ Consultant | 4 | Los Molinos | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-FF & E | 4 | Los Molinos | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Legal Services | 4 | Los Molinos | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Modular Buildings | 4 | Los Molinos | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Move Management | 4 | Los Molinos | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Reprographics | 4 | Los Molinos | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Technology | 4 | Los Molinos | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century-Advertisement | 9 | Los Robles | 21st Century | Advertisement | 1222.31 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-Asbestos oversight/survey/abatement | 9 | Los Robles | 21st Century | Asbestos oversight/survey/abatement | 59500 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-CM/PM Management | 9 | Los Robles | 21st Century | CM/PM Management | 193544.35 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-Construction Contingency | 9 | Los Robles | 21st Century | Construction Contingency | 190484 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-Contractor | 9 | Los Robles | 21st Century | Contractor | 2031901.36 | N/A | 40000 | 40000 | 100%
Los Robles-21st Century-Design | 9 | Los Robles | 21st Century | Design | 233350.55 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-DSA Fees | 9 | Los Robles | 21st Century | DSA Fees | 38891.76 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-DSA Inspection | 9 | Los Robles | 21st Century | DSA Inspection | 33335.79 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-DSA Special Inspection | 9 | Los Robles | 21st Century | DSA Special Inspection | 16667.9 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-Environ Consultant | 9 | Los Robles | 21st Century | Environ Consultant | 9778.5 | No Proposal Provided | 2800 | 2800 | 100%
Los Robles-21st Century-FF & E | 9 | Los Robles | 21st Century | FF & E | 340000 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-Legal Services | 9 | Los Robles | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century-Move classroom | 9 | Los Robles | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century-Move Management | 9 | Los Robles | 21st Century | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century-Reprographics | 9 | Los Robles | 21st Century | Reprographics | 1222.31 | N/A | 0 | 0 | #DIV/0!
Los Robles-21st Century-Technology | 9 | Los Robles | 21st Century | Technology | 340000 | N/A | 76568.08 | 76568.08 | 100%
Los Robles-Ceiling replacement-CM/PM Management | 9 | Los Robles | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Ceiling replacement-Contractor | 9 | Los Robles | Ceiling replacement | Contractor | 219377 | 219377 | 219377 | 208408.15 | 95%
Los Robles-Drinking fountain replacement-Advertisement | 9 | Los Robles | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking fountain replacement-Contractor | 9 | Los Robles | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Drinking fountain replacement-Design | 9 | Los Robles | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking fountain replacement-DSA Fees | 9 | Los Robles | Drinking fountain replacement | DSA Fees | 1050 | No Proposal Provided | 0 | 0 | #DIV/0!
Los Robles-Drinking fountain replacement-DSA Inspection | 9 | Los Robles | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking fountain replacement-DSA Special Inspection | 9 | Los Robles | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking fountain replacement-Environ Consultant | 9 | Los Robles | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking fountain replacement-Reprographics | 9 | Los Robles | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm-Advertisement | 9 | Los Robles | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm-Contractor | 9 | Los Robles | Fire Alarm | Contractor | 255000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm-Design | 9 | Los Robles | Fire Alarm | Design | 48500 | No Proposal Provided | 48500 | 36375 | 75%
Los Robles-Fire Alarm-DSA Fees | 9 | Los Robles | Fire Alarm | DSA Fees | 0 | 0 | 900 | 900 | 100%
Los Robles-Fire Alarm-DSA Inspection | 9 | Los Robles | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm-Environ Consultant | 9 | Los Robles | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm-Reprographics | 9 | Los Robles | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Advertisement | 9 | Los Robles | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Alarm | 9 | Los Robles | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-CM/PM Management | 9 | Los Robles | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Construction Contingency | 9 | Los Robles | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Contractor | 9 | Los Robles | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Design | 9 | Los Robles | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-DSA Fees | 9 | Los Robles | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-DSA Inspection | 9 | Los Robles | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-DSA Special Inspection | 9 | Los Robles | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Environ Consultant | 9 | Los Robles | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-FF & E | 9 | Los Robles | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Legal Services | 9 | Los Robles | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Modular Buildings | 9 | Los Robles | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Move Management | 9 | Los Robles | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Reprographics | 9 | Los Robles | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Technology | 9 | Los Robles | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century-Advertisement | 1 | Mesa Robles | 21st Century | Advertisement | 2276.66 | 0 | 301.67 | 301.67 | 100%
Mesa Robles-21st Century-Asbestos oversight/survey/abatement | 1 | Mesa Robles | 21st Century | Asbestos oversight/survey/abatement | 108000 | 12480 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century-CM/PM Management | 1 | Mesa Robles | 21st Century | CM/PM Management | 371765.88 | 265179 | 265179 | 265093.75 | 99.97%
Mesa Robles-21st Century-Construction Contingency | 1 | Mesa Robles | 21st Century | Construction Contingency | 354793.28 | 309700 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century-Contractor | 1 | Mesa Robles | 21st Century | Contractor | 3784579.12 | 3097000 | 3239909.02 | 3078187.55 | 95.01%
Mesa Robles-21st Century-Design | 1 | Mesa Robles | 21st Century | Design | 434634.19 | 269527.44 | 263527.44 | 225287.44 | 85.49%
Mesa Robles-21st Century-DSA Fees | 1 | Mesa Robles | 21st Century | DSA Fees | 72439.03 | 0 | 28009 | 28009 | 100%
Mesa Robles-21st Century-DSA Inspection | 1 | Mesa Robles | 21st Century | DSA Inspection | 62090.6 | 93600 | 93600 | 57744 | 61.69%
Mesa Robles-21st Century-DSA Special Inspection | 1 | Mesa Robles | 21st Century | DSA Special Inspection | 31045 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century-Environ Consultant | 1 | Mesa Robles | 21st Century | Environ Consultant | 0 | 0 | 29930 | 21990 | 73.47%
Mesa Robles-21st Century-FF & E | 1 | Mesa Robles | 21st Century | FF & E | 720000 | 656535.85 | 820765.62 | 776322.69 | 94.59%
Mesa Robles-21st Century-Legal Services | 1 | Mesa Robles | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century-Move classroom | 1 | Mesa Robles | 21st Century | Move classroom | 0 | 0 | 1852.8 | 1852.8 | 100%
Mesa Robles-21st Century-Move Management | 1 | Mesa Robles | 21st Century | Move Management | 16557.49 | 0 | 11847.1 | 11847.1 | 100%
Mesa Robles-21st Century-Reprographics | 1 | Mesa Robles | 21st Century | Reprographics | 2276.66 | 0 | 216.14 | 216.14 | 100%
Mesa Robles-21st Century-Technology | 1 | Mesa Robles | 21st Century | Technology | 720000 | 83019.38 | 758904.29 | 758904.29 | 100%
Mesa Robles-Ceiling replacement-CM/PM Management | 1 | Mesa Robles | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Ceiling replacement-Contractor | 1 | Mesa Robles | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking fountain replacement-Advertisement | 1 | Mesa Robles | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking fountain replacement-Contractor | 1 | Mesa Robles | Drinking fountain replacement | Contractor | 24000 | 16000 | 11000 | 11000 | 100%
Mesa Robles-Drinking fountain replacement-Design | 1 | Mesa Robles | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking fountain replacement-DSA Fees | 1 | Mesa Robles | Drinking fountain replacement | DSA Fees | 0 | 0 | 1050 | 1050 | 100%
Mesa Robles-Drinking fountain replacement-DSA Inspection | 1 | Mesa Robles | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking fountain replacement-DSA Special Inspection | 1 | Mesa Robles | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking fountain replacement-Environ Consultant | 1 | Mesa Robles | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking fountain replacement-Reprographics | 1 | Mesa Robles | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Fire Alarm-Advertisement | 1 | Mesa Robles | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Fire Alarm-Contractor | 1 | Mesa Robles | Fire Alarm | Contractor | 540000 | 408743.31 | 146793.61 | 139057.13 | 94.73%
Mesa Robles-Fire Alarm-Design | 1 | Mesa Robles | Fire Alarm | Design | 0 | 55800 | 11875 | 11875 | 100%
Mesa Robles-Fire Alarm-DSA Fees | 1 | Mesa Robles | Fire Alarm | DSA Fees | 0 | 0 | 1720 | 1720 | 100%
Mesa Robles-Fire Alarm-DSA Inspection | 1 | Mesa Robles | Fire Alarm | DSA Inspection | 8250 | No Proposal Provided | 8250 | 8250 | 100%
Mesa Robles-Fire Alarm-Environ Consultant | 1 | Mesa Robles | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Fire Alarm-Reprographics | 1 | Mesa Robles | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Advertisement | 1 | Mesa Robles | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Alarm | 1 | Mesa Robles | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-CM/PM Management | 1 | Mesa Robles | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Construction Contingency | 1 | Mesa Robles | Interim Housing | Construction Contingency | 87894 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Contractor | 1 | Mesa Robles | Interim Housing | Contractor | 879842.2 | 879842.2 | 1232317.04 | 1217601.09 | 98.81%
Mesa Robles-Interim Housing-Design | 1 | Mesa Robles | Interim Housing | Design | 93467.93 | 93467.93 | 93467.93 | 93467.93 | 100%
Mesa Robles-Interim Housing-DSA Fees | 1 | Mesa Robles | Interim Housing | DSA Fees | 7425 | 7425 | 7425 | 7425 | 100%
Mesa Robles-Interim Housing-DSA Inspection | 1 | Mesa Robles | Interim Housing | DSA Inspection | 39740 | 39740 | 39740 | 39740 | 100%
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | Mesa Robles | Interim Housing | DSA Special Inspection | 13540 | 13540 | 13540 | 11330.5 | 83.68%
Mesa Robles-Interim Housing-Environ Consultant | 1 | Mesa Robles | Interim Housing | Environ Consultant | 1280 | No Proposal Provided | 1280 | 1280 | 100%
Mesa Robles-Interim Housing-FF & E | 1 | Mesa Robles | Interim Housing | FF & E | 0 | 0 | 86851.54 | 86851.54 | 100%
Mesa Robles-Interim Housing-Legal Services | 1 | Mesa Robles | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Modular Buildings | 1 | Mesa Robles | Interim Housing | Modular Buildings | 479577.48 | 0 | 479577.48 | 479577.48 | 100%
Mesa Robles-Interim Housing-Move Management | 1 | Mesa Robles | Interim Housing | Move Management | 0 | 0 | 500 | 500 | 100%
Mesa Robles-Interim Housing-Reprographics | 1 | Mesa Robles | Interim Housing | Reprographics | 1661.08 | 1661.08 | 1661.08 | 1661.08 | 100%
Mesa Robles-Interim Housing-Technology | 1 | Mesa Robles | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century-Advertisement | 1 | Nelson | 21st Century | Advertisement | 1306.06 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century-Asbestos oversight/survey/abatement | 1 | Nelson | 21st Century | Asbestos oversight/survey/abatement | 85835 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century-CM/PM Management | 1 | Nelson | 21st Century | CM/PM Management | 208976.71 | 150831 | 150831 | 150811.25 | 99.99%
Nelson-21st Century-Construction Contingency | 1 | Nelson | 21st Century | Construction Contingency | 203535.9 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century-Contractor | 1 | Nelson | 21st Century | Contractor | 2234549.68 | 2253432.23 | 2339408.93 | 2215904.99 | 94.72%
Nelson-21st Century-Design | 1 | Nelson | 21st Century | Design | 249338.6 | 127727.2 | 109894.72 | 109894.72 | 100%
Nelson-21st Century-DSA Fees | 1 | Nelson | 21st Century | DSA Fees | 41556.43 | No Proposal Provided | 30211.09 | 30211.09 | 100%
Nelson-21st Century-DSA Inspection | 1 | Nelson | 21st Century | DSA Inspection | 35619.8 | 34720 | 34720 | 32620 | 93.95%
Nelson-21st Century-DSA Special Inspection | 1 | Nelson | 21st Century | DSA Special Inspection | 17809.9 | 26880 | 26637.5 | 6905 | 25.92%
Nelson-21st Century-Environ Consultant | 1 | Nelson | 21st Century | Environ Consultant | 10448.47 | 0 | 10630 | 6505 | 61.19%
Nelson-21st Century-FF & E | 1 | Nelson | 21st Century | FF & E | 380000 | 131001.36 | 409727.86 | 390509.3 | 95.31%
Nelson-21st Century-Legal Services | 1 | Nelson | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century-Move classroom | 1 | Nelson | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century-Move Management | 1 | Nelson | 21st Century | Move Management | 9498.61 | 0 | 8551.98 | 8551.98 | 100%
Nelson-21st Century-Reprographics | 1 | Nelson | 21st Century | Reprographics | 1306.06 | No Proposal Provided | 728.6 | 728.6 | 100%
Nelson-21st Century-Technology | 1 | Nelson | 21st Century | Technology | 380000 | 54617.76 | 313543.3 | 313543.3 | 100%
Nelson-Ceiling replacement-CM/PM Management | 1 | Nelson | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Ceiling replacement-Contractor | 1 | Nelson | Ceiling replacement | Contractor | 309746 | 309746 | 309746 | 294258.7 | 95%
Nelson-Drinking fountain replacement-Advertisement | 1 | Nelson | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking fountain replacement-Contractor | 1 | Nelson | Drinking fountain replacement | Contractor | 30000 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking fountain replacement-Design | 1 | Nelson | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking fountain replacement-DSA Fees | 1 | Nelson | Drinking fountain replacement | DSA Fees | 0 | 0 | 1050 | 1050 | 100%
Nelson-Drinking fountain replacement-DSA Inspection | 1 | Nelson | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking fountain replacement-DSA Special Inspection | 1 | Nelson | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking fountain replacement-Environ Consultant | 1 | Nelson | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking fountain replacement-Reprographics | 1 | Nelson | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Fire Alarm-Advertisement | 1 | Nelson | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Fire Alarm-Contractor | 1 | Nelson | Fire Alarm | Contractor | 285000 | 98440 | 119435.08 | 111843.34 | 93.64%
Nelson-Fire Alarm-Design | 1 | Nelson | Fire Alarm | Design | 11875 | No Proposal Provided | 11875 | 11875 | 100%
Nelson-Fire Alarm-DSA Fees | 1 | Nelson | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Fire Alarm-DSA Inspection | 1 | Nelson | Fire Alarm | DSA Inspection | 0 | 0 | 12250 | 12250 | 100%
Nelson-Fire Alarm-Environ Consultant | 1 | Nelson | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Fire Alarm-Reprographics | 1 | Nelson | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Advertisement | 1 | Nelson | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Alarm | 1 | Nelson | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-CM/PM Management | 1 | Nelson | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Construction Contingency | 1 | Nelson | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Contractor | 1 | Nelson | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Design | 1 | Nelson | Interim Housing | Design | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-DSA Fees | 1 | Nelson | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-DSA Inspection | 1 | Nelson | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-DSA Special Inspection | 1 | Nelson | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Environ Consultant | 1 | Nelson | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-FF & E | 1 | Nelson | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Legal Services | 1 | Nelson | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Modular Buildings | 1 | Nelson | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Move Management | 1 | Nelson | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Reprographics | 1 | Nelson | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Technology | 1 | Nelson | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-Advertisement | 1 | Newton | 21st Century | Advertisement | 1380.36 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-Asbestos oversight/survey/abatement | 1 | Newton | 21st Century | Asbestos oversight/survey/abatement | 66500 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-CM/PM Management | 1 | Newton | 21st Century | CM/PM Management | 220654.2 | 180453 | 180453 | 190578.71 | 105.6%
Newton-21st Century-Construction Contingency | 1 | Newton | 21st Century | Construction Contingency | 215114 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-Contractor | 1 | Newton | 21st Century | Contractor | 2294621.04 | No Proposal Provided | 3400 | 3400 | 100%
Newton-21st Century-Design | 1 | Newton | 21st Century | Design | 263522.18 | 232763 | 221580 | 170829.49 | 77.1%
Newton-21st Century-DSA Fees | 1 | Newton | 21st Century | DSA Fees | 43920.36 | 28270.82 | 28270.82 | 28270.82 | 100%
Newton-21st Century-DSA Inspection | 1 | Newton | 21st Century | DSA Inspection | 37646.03 | N/A | 0 | 0 | #DIV/0!
Newton-21st Century-DSA Special Inspection | 1 | Newton | 21st Century | DSA Special Inspection | 18823.01 | N/A | 0 | 0 | #DIV/0!
Newton-21st Century-Environ Consultant | 1 | Newton | 21st Century | Environ Consultant | 0 | 0 | 2950 | 2950 | 100%
Newton-21st Century-FF & E | 1 | Newton | 21st Century | FF & E | 400000 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-Legal Services | 1 | Newton | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-Move classroom | 1 | Newton | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-Move Management | 1 | Newton | 21st Century | Move Management | 10038.94 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-Reprographics | 1 | Newton | 21st Century | Reprographics | 1380.36 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century-Technology | 1 | Newton | 21st Century | Technology | 400000 | 0 | 331364.35 | 331364.35 | 100%
Newton-Ceiling replacement-CM/PM Management | 1 | Newton | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Ceiling replacement-Contractor | 1 | Newton | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking fountain replacement-Advertisement | 1 | Newton | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking fountain replacement-Contractor | 1 | Newton | Drinking fountain replacement | Contractor | 30000 | N/A | 0 | 0 | #DIV/0!
Newton-Drinking fountain replacement-Design | 1 | Newton | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking fountain replacement-DSA Fees | 1 | Newton | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking fountain replacement-DSA Inspection | 1 | Newton | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking fountain replacement-DSA Special Inspection | 1 | Newton | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking fountain replacement-Environ Consultant | 1 | Newton | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking fountain replacement-Reprographics | 1 | Newton | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Fire Alarm-Advertisement | 1 | Newton | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Fire Alarm-Contractor | 1 | Newton | Fire Alarm | Contractor | 285000 | 102680 | 82680.01 | 78546.01 | 95%
Newton-Fire Alarm-Design | 1 | Newton | Fire Alarm | Design | 47500 | No Proposal Provided | 9500 | 9500 | 100%
Newton-Fire Alarm-DSA Fees | 1 | Newton | Fire Alarm | DSA Fees | 0 | 0 | 645 | 645 | 100%
Newton-Fire Alarm-DSA Inspection | 1 | Newton | Fire Alarm | DSA Inspection | 8125 | No Proposal Provided | 8125 | 8125 | 100%
Newton-Fire Alarm-Environ Consultant | 1 | Newton | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Fire Alarm-Reprographics | 1 | Newton | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Advertisement | 1 | Newton | Interim Housing | Advertisement | 0 | 0 | 1088 | 1088 | 100%
Newton-Interim Housing-Alarm | 1 | Newton | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-CM/PM Management | 1 | Newton | Interim Housing | CM/PM Management | Incl in 21st | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Construction Contingency | 1 | Newton | Interim Housing | Construction Contingency | 31300 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Contractor | 1 | Newton | Interim Housing | Contractor | 313100.97 | 0 | 418199 | 126129 | 30.16%
Newton-Interim Housing-Design | 1 | Newton | Interim Housing | Design | 75338.08 | 75338.08 | 81583.08 | 72936.59 | 89.4%
Newton-Interim Housing-DSA Fees | 1 | Newton | Interim Housing | DSA Fees | 32799.17 | No Proposal Provided | 4175.44 | 4175.44 | 100%
Newton-Interim Housing-DSA Inspection | 1 | Newton | Interim Housing | DSA Inspection | 16000 | 0 | 16000 | 0 | 0%
Newton-Interim Housing-DSA Special Inspection | 1 | Newton | Interim Housing | DSA Special Inspection | 12000 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Environ Consultant | 1 | Newton | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-FF & E | 1 | Newton | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Legal Services | 1 | Newton | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Modular Buildings | 1 | Newton | Interim Housing | Modular Buildings | 239959.74 | 239959.74 | 239788.74 | 239788.74 | 100%
Newton-Interim Housing-Move Management | 1 | Newton | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Reprographics | 1 | Newton | Interim Housing | Reprographics | 0 | 0 | 539.94 | 539.94 | 100%
Newton-Interim Housing-Technology | 1 | Newton | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Utilities | 1 | Newton | Interim Housing | Utilities | 0 | 0 | 1072 | 1072 | 100%
Orange Grove-21st Century-Advertisement | 3 | Orange Grove | 21st Century | Advertisement | 1231.11 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Asbestos oversight/survey/abatement | 3 | Orange Grove | 21st Century | Asbestos oversight/survey/abatement | 49000 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-CM/PM Management | 3 | Orange Grove | 21st Century | CM/PM Management | 194619.4 | N/A | 206602 | 9265 | 4.484%
Orange Grove-21st Century-Construction Contingency | 3 | Orange Grove | 21st Century | Construction Contingency | 191856 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Contractor | 3 | Orange Grove | 21st Century | Contractor | 2046527.95 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Design | 3 | Orange Grove | 21st Century | Design | 223838.4 | N/A | 222000 | 0 | 0%
Orange Grove-21st Century-DSA Fees | 3 | Orange Grove | 21st Century | DSA Fees | 39171.72 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-DSA Inspection | 3 | Orange Grove | 21st Century | DSA Inspection | 33575.76 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-DSA Special Inspection | 3 | Orange Grove | 21st Century | DSA Special Inspection | 16787.88 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Environ Consultant | 3 | Orange Grove | 21st Century | Environ Consultant | 12311.11 | No Proposal Provided | 2800 | 2800 | 100%
Orange Grove-21st Century-FF & E | 3 | Orange Grove | 21st Century | FF & E | 340000 | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Legal Services | 3 | Orange Grove | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Move classroom | 3 | Orange Grove | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Move Management | 3 | Orange Grove | 21st Century | Move Management | 8953.54 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Reprographics | 3 | Orange Grove | 21st Century | Reprographics | 1231.11 | N/A | 0 | 0 | #DIV/0!
Orange Grove-21st Century-Technology | 3 | Orange Grove | 21st Century | Technology | 340000 | 0 | 208552.54 | 208552.54 | 100%
Orange Grove-Ceiling replacement-CM/PM Management | 3 | Orange Grove | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Ceiling replacement-Contractor | 3 | Orange Grove | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking fountain replacement-Advertisement | 3 | Orange Grove | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking fountain replacement-Contractor | 3 | Orange Grove | Drinking fountain replacement | Contractor | 22500 | N/A | 0 | 0 | #DIV/0!
Orange Grove-Drinking fountain replacement-Design | 3 | Orange Grove | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking fountain replacement-DSA Fees | 3 | Orange Grove | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking fountain replacement-DSA Inspection | 3 | Orange Grove | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking fountain replacement-DSA Special Inspection | 3 | Orange Grove | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking fountain replacement-Environ Consultant | 3 | Orange Grove | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking fountain replacement-Reprographics | 3 | Orange Grove | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm-Advertisement | 3 | Orange Grove | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm-Contractor | 3 | Orange Grove | Fire Alarm | Contractor | 255000 | N/A | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm-Design | 3 | Orange Grove | Fire Alarm | Design | 49500 | No Proposal Provided | 49500 | 37125 | 75%
Orange Grove-Fire Alarm-DSA Fees | 3 | Orange Grove | Fire Alarm | DSA Fees | 0 | 0 | 1080 | 1080 | 100%
Orange Grove-Fire Alarm-DSA Inspection | 3 | Orange Grove | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm-Environ Consultant | 3 | Orange Grove | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm-Reprographics | 3 | Orange Grove | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Advertisement | 3 | Orange Grove | Interim Housing | Advertisement | 400 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Alarm | 3 | Orange Grove | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-CM/PM Management | 3 | Orange Grove | Interim Housing | CM/PM Management | 42410 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Construction Contingency | 3 | Orange Grove | Interim Housing | Construction Contingency | 65000 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Contractor | 3 | Orange Grove | Interim Housing | Contractor | 650000 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Design | 3 | Orange Grove | Interim Housing | Design | 80000 | 0 | 95400 | 0 | 0%
Orange Grove-Interim Housing-DSA Fees | 3 | Orange Grove | Interim Housing | DSA Fees | 14000 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-DSA Inspection | 3 | Orange Grove | Interim Housing | DSA Inspection | 12000 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-DSA Special Inspection | 3 | Orange Grove | Interim Housing | DSA Special Inspection | 12000 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Environ Consultant | 3 | Orange Grove | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-FF & E | 3 | Orange Grove | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Legal Services | 3 | Orange Grove | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Modular Buildings | 3 | Orange Grove | Interim Housing | Modular Buildings | 150000 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Move Management | 3 | Orange Grove | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Reprographics | 3 | Orange Grove | Interim Housing | Reprographics | 400 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Technology | 3 | Orange Grove | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Advertisement | 0 | Palm Canyon | 21st Century | Advertisement | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Asbestos oversight/survey/abatement | 0 | Palm Canyon | 21st Century | Asbestos oversight/survey/abatement | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-CM/PM Management | 0 | Palm Canyon | 21st Century | CM/PM Management | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Construction Contingency | 0 | Palm Canyon | 21st Century | Construction Contingency | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Contractor | 0 | Palm Canyon | 21st Century | Contractor | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Design | 0 | Palm Canyon | 21st Century | Design | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-DSA Fees | 0 | Palm Canyon | 21st Century | DSA Fees | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-DSA Inspection | 0 | Palm Canyon | 21st Century | DSA Inspection | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-DSA Special Inspection | 0 | Palm Canyon | 21st Century | DSA Special Inspection | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Environ Consultant | 0 | Palm Canyon | 21st Century | Environ Consultant | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-FF & E | 0 | Palm Canyon | 21st Century | FF & E | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Legal Services | 0 | Palm Canyon | 21st Century | Legal Services | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Move classroom | 0 | Palm Canyon | 21st Century | Move classroom | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Move Management | 0 | Palm Canyon | 21st Century | Move Management | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Reprographics | 0 | Palm Canyon | 21st Century | Reprographics | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century-Technology | 0 | Palm Canyon | 21st Century | Technology | 10368.74 | No Proposal Provided | 10368.74 | 10368.74 | 100%
Palm Canyon-Ceiling replacement-CM/PM Management | 0 | Palm Canyon | Ceiling replacement | CM/PM Management | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Ceiling replacement-Contractor | 0 | Palm Canyon | Ceiling replacement | Contractor | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking fountain replacement-Advertisement | 0 | Palm Canyon | Drinking fountain replacement | Advertisement | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking fountain replacement-Contractor | 0 | Palm Canyon | Drinking fountain replacement | Contractor | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking fountain replacement-Design | 0 | Palm Canyon | Drinking fountain replacement | Design | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking fountain replacement-DSA Fees | 0 | Palm Canyon | Drinking fountain replacement | DSA Fees | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking fountain replacement-DSA Inspection | 0 | Palm Canyon | Drinking fountain replacement | DSA Inspection | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking fountain replacement-DSA Special Inspection | 0 | Palm Canyon | Drinking fountain replacement | DSA Special Inspection | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking fountain replacement-Environ Consultant | 0 | Palm Canyon | Drinking fountain replacement | Environ Consultant | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking fountain replacement-Reprographics | 0 | Palm Canyon | Drinking fountain replacement | Reprographics | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm-Advertisement | 0 | Palm Canyon | Fire Alarm | Advertisement | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm-Contractor | 0 | Palm Canyon | Fire Alarm | Contractor | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm-Design | 0 | Palm Canyon | Fire Alarm | Design | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm-DSA Fees | 0 | Palm Canyon | Fire Alarm | DSA Fees | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm-DSA Inspection | 0 | Palm Canyon | Fire Alarm | DSA Inspection | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm-Environ Consultant | 0 | Palm Canyon | Fire Alarm | Environ Consultant | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm-Reprographics | 0 | Palm Canyon | Fire Alarm | Reprographics | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Advertisement | 0 | Palm Canyon | Interim Housing | Advertisement | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Alarm | 0 | Palm Canyon | Interim Housing | Alarm | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-CM/PM Management | 0 | Palm Canyon | Interim Housing | CM/PM Management | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Construction Contingency | 0 | Palm Canyon | Interim Housing | Construction Contingency | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Contractor | 0 | Palm Canyon | Interim Housing | Contractor | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Design | 0 | Palm Canyon | Interim Housing | Design | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-DSA Fees | 0 | Palm Canyon | Interim Housing | DSA Fees | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-DSA Inspection | 0 | Palm Canyon | Interim Housing | DSA Inspection | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-DSA Special Inspection | 0 | Palm Canyon | Interim Housing | DSA Special Inspection | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Environ Consultant | 0 | Palm Canyon | Interim Housing | Environ Consultant | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-FF & E | 0 | Palm Canyon | Interim Housing | FF & E | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Legal Services | 0 | Palm Canyon | Interim Housing | Legal Services | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Modular Buildings | 0 | Palm Canyon | Interim Housing | Modular Buildings | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Move Management | 0 | Palm Canyon | Interim Housing | Move Management | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Reprographics | 0 | Palm Canyon | Interim Housing | Reprographics | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Technology | 0 | Palm Canyon | Interim Housing | Technology | No Scope Established | 0 | 0 | 0 | #DIV/0!
Palm-21st Century-Advertisement | 6 | Palm | 21st Century | Advertisement | 1393.47 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century-Asbestos oversight/survey/abatement | 6 | Palm | 21st Century | Asbestos oversight/survey/abatement | 70000 | N/A | 0 | 0 | #DIV/0!
Palm-21st Century-CM/PM Management | 6 | Palm | 21st Century | CM/PM Management | 222256.74 | N/A | 0 | 0 | #DIV/0!
Palm-21st Century-Construction Contingency | 6 | Palm | 21st Century | Construction Contingency | 217158 | N/A | 0 | 0 | #DIV/0!
Palm-21st Century-Contractor | 6 | Palm | 21st Century | Contractor | 2316424.39 | No Proposal Provided | 46372.24 | 46372.24 | 100%
Palm-21st Century-Design | 6 | Palm | 21st Century | Design | 266026.15 | N/A | 0 | 0 | #DIV/0!
Palm-21st Century-DSA Fees | 6 | Palm | 21st Century | DSA Fees | 44337.69 | N/A | 0 | 0 | #DIV/0!
Palm-21st Century-DSA Inspection | 6 | Palm | 21st Century | DSA Inspection | 38003.74 | N/A | 0 | 0 | #DIV/0!
Palm-21st Century-DSA Special Inspection | 6 | Palm | 21st Century | DSA Special Inspection | 19001.87 | N/A | 0 | 0 | #DIV/0!
Palm-21st Century-Environ Consultant | 6 | Palm | 21st Century | Environ Consultant | 11147.76 | No Proposal Provided | 2500 | 2500 | 100%
Palm-21st Century-FF & E | 6 | Palm | 21st Century | FF & E | 400000 | No Proposal Provided | 19119.08 | 19119.08 | 100%
Palm-21st Century-Legal Services | 6 | Palm | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century-Move classroom | 6 | Palm | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century-Move Management | 6 | Palm | 21st Century | Move Management | 10134.33 | N/A | 0 | 0 | #DIV/0!
Palm-21st Century-Reprographics | 6 | Palm | 21st Century | Reprographics | 1393.47 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century-Technology | 6 | Palm | 21st Century | Technology | 400000 | No Proposal Provided | 112875.6 | 112875.6 | 100%
Palm-Ceiling replacement-CM/PM Management | 6 | Palm | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Ceiling replacement-Contractor | 6 | Palm | Ceiling replacement | Contractor | 232310 | 232310 | 232310 | 220694.5 | 95%
Palm-Drinking fountain replacement-Advertisement | 6 | Palm | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking fountain replacement-Contractor | 6 | Palm | Drinking fountain replacement | Contractor | 30000 | N/A | 0 | 0 | #DIV/0!
Palm-Drinking fountain replacement-Design | 6 | Palm | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking fountain replacement-DSA Fees | 6 | Palm | Drinking fountain replacement | DSA Fees | 1050 | No Proposal Provided | 1050 | 1050 | 100%
Palm-Drinking fountain replacement-DSA Inspection | 6 | Palm | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking fountain replacement-DSA Special Inspection | 6 | Palm | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking fountain replacement-Environ Consultant | 6 | Palm | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking fountain replacement-Reprographics | 6 | Palm | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm-Advertisement | 6 | Palm | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm-Contractor | 6 | Palm | Fire Alarm | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm-Design | 6 | Palm | Fire Alarm | Design | 48500 | No Proposal Provided | 48500 | 36375 | 75%
Palm-Fire Alarm-DSA Fees | 6 | Palm | Fire Alarm | DSA Fees | 0 | 0 | 870 | 870 | 100%
Palm-Fire Alarm-DSA Inspection | 6 | Palm | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm-Environ Consultant | 6 | Palm | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm-Reprographics | 6 | Palm | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Advertisement | 6 | Palm | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Alarm | 6 | Palm | Interim Housing | Alarm | 400 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-CM/PM Management | 6 | Palm | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Construction Contingency | 6 | Palm | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-Contractor | 6 | Palm | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-Design | 6 | Palm | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-DSA Fees | 6 | Palm | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-DSA Inspection | 6 | Palm | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-DSA Special Inspection | 6 | Palm | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-Environ Consultant | 6 | Palm | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-FF & E | 6 | Palm | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Legal Services | 6 | Palm | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Modular Buildings | 6 | Palm | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-Move Management | 6 | Palm | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Reprographics | 6 | Palm | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Palm-Interim Housing-Technology | 6 | Palm | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Advertisement | 8 | Sierra Vista | 21st Century | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Asbestos oversight/survey/abatement | 8 | Sierra Vista | 21st Century | Asbestos oversight/survey/abatement | 59500 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-CM/PM Management | 8 | Sierra Vista | 21st Century | CM/PM Management | 196289.63 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Construction Contingency | 8 | Sierra Vista | 21st Century | Construction Contingency | 190476.3 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Contractor | 8 | Sierra Vista | 21st Century | Contractor | 2031810.69 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Design | 8 | Sierra Vista | 21st Century | Design | 233340.13 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-DSA Fees | 8 | Sierra Vista | 21st Century | DSA Fees | 38890.02 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-DSA Inspection | 8 | Sierra Vista | 21st Century | DSA Inspection | 33334.3 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-DSA Special Inspection | 8 | Sierra Vista | 21st Century | DSA Special Inspection | 16667.15 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Environ Consultant | 8 | Sierra Vista | 21st Century | Environ Consultant | 9778.06 | No Proposal Provided | 3000 | 3000 | 100%
Sierra Vista-21st Century-FF & E | 8 | Sierra Vista | 21st Century | FF & E | 340000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Legal Services | 8 | Sierra Vista | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Move classroom | 8 | Sierra Vista | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Move Management | 8 | Sierra Vista | 21st Century | Move Management | 8889.15 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Reprographics | 8 | Sierra Vista | 21st Century | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century-Technology | 8 | Sierra Vista | 21st Century | Technology | 340000 | No Proposal Provided | 171066.97 | 171066.97 | 100%
Sierra Vista-Ceiling replacement-CM/PM Management | 8 | Sierra Vista | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Ceiling replacement-Contractor | 8 | Sierra Vista | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking fountain replacement-Advertisement | 8 | Sierra Vista | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking fountain replacement-Contractor | 8 | Sierra Vista | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Drinking fountain replacement-Design | 8 | Sierra Vista | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking fountain replacement-DSA Fees | 8 | Sierra Vista | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking fountain replacement-DSA Inspection | 8 | Sierra Vista | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking fountain replacement-DSA Special Inspection | 8 | Sierra Vista | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking fountain replacement-Environ Consultant | 8 | Sierra Vista | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking fountain replacement-Reprographics | 8 | Sierra Vista | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm-Advertisement | 8 | Sierra Vista | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm-Contractor | 8 | Sierra Vista | Fire Alarm | Contractor | 255000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm-Design | 8 | Sierra Vista | Fire Alarm | Design | 49500 | No Proposal Provided | 49500 | 37125 | 75%
Sierra Vista-Fire Alarm-DSA Fees | 8 | Sierra Vista | Fire Alarm | DSA Fees | 0 | 0 | 1050 | 1050 | 100%
Sierra Vista-Fire Alarm-DSA Inspection | 8 | Sierra Vista | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm-Environ Consultant | 8 | Sierra Vista | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm-Reprographics | 8 | Sierra Vista | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Advertisement | 8 | Sierra Vista | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Alarm | 8 | Sierra Vista | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-CM/PM Management | 8 | Sierra Vista | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Construction Contingency | 8 | Sierra Vista | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Contractor | 8 | Sierra Vista | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Design | 8 | Sierra Vista | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-DSA Fees | 8 | Sierra Vista | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-DSA Inspection | 8 | Sierra Vista | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-DSA Special Inspection | 8 | Sierra Vista | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Environ Consultant | 8 | Sierra Vista | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-FF & E | 8 | Sierra Vista | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Legal Services | 8 | Sierra Vista | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Modular Buildings | 8 | Sierra Vista | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Move Management | 8 | Sierra Vista | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Reprographics | 8 | Sierra Vista | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Technology | 8 | Sierra Vista | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Advertisement | 7 | Sparks ES | 21st Century | Advertisement | 1408.87 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Asbestos oversight/survey/abatement | 7 | Sparks ES | 21st Century | Asbestos oversight/survey/abatement | 70000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-CM/PM Management | 7 | Sparks ES | 21st Century | CM/PM Management | 224138.39 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Construction Contingency | 7 | Sparks ES | 21st Century | Construction Contingency | 219558 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Contractor | 7 | Sparks ES | 21st Century | Contractor | 2342025.19 | No Proposal Provided | 63116.72 | 63116.72 | 100%
Sparks ES-21st Century-Design | 7 | Sparks ES | 21st Century | Design | 268966.23 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-DSA Fees | 7 | Sparks ES | 21st Century | DSA Fees | 44827.71 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-DSA Inspection | 7 | Sparks ES | 21st Century | DSA Inspection | 38423.75 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-DSA Special Inspection | 7 | Sparks ES | 21st Century | DSA Special Inspection | 19211.87 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Environ Consultant | 7 | Sparks ES | 21st Century | Environ Consultant | 11270.97 | No Proposal Provided | 2670 | 2670 | 100%
Sparks ES-21st Century-FF & E | 7 | Sparks ES | 21st Century | FF & E | 400000 | No Proposal Provided | 20720.61 | 20720.61 | 100%
Sparks ES-21st Century-Legal Services | 7 | Sparks ES | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Move classroom | 7 | Sparks ES | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Move Management | 7 | Sparks ES | 21st Century | Move Management | 10246.33 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Reprographics | 7 | Sparks ES | 21st Century | Reprographics | 1408.87 | N/A | 0 | 0 | #DIV/0!
Sparks ES-21st Century-Technology | 7 | Sparks ES | 21st Century | Technology | 400000 | No Proposal Provided | 172413.82 | 172413.82 | 100%
Sparks ES-Ceiling replacement-CM/PM Management | 7 | Sparks ES | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Ceiling replacement-Contractor | 7 | Sparks ES | Ceiling replacement | Contractor | 258122 | 258122 | 258122 | 245215.9 | 95%
Sparks ES-Drinking fountain replacement-Advertisement | 7 | Sparks ES | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking fountain replacement-Contractor | 7 | Sparks ES | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Drinking fountain replacement-Design | 7 | Sparks ES | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking fountain replacement-DSA Fees | 7 | Sparks ES | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking fountain replacement-DSA Inspection | 7 | Sparks ES | Drinking fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 1200 | 0 | 0%
Sparks ES-Drinking fountain replacement-DSA Special Inspection | 7 | Sparks ES | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking fountain replacement-Environ Consultant | 7 | Sparks ES | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking fountain replacement-Reprographics | 7 | Sparks ES | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm-Advertisement | 7 | Sparks ES | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm-Contractor | 7 | Sparks ES | Fire Alarm | Contractor | 300000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm-Design | 7 | Sparks ES | Fire Alarm | Design | 12125 | No Proposal Provided | 12125 | 0 | 0%
Sparks ES-Fire Alarm-DSA Fees | 7 | Sparks ES | Fire Alarm | DSA Fees | 0 | 0 | 930 | 930 | 100%
Sparks ES-Fire Alarm-DSA Inspection | 7 | Sparks ES | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm-Environ Consultant | 7 | Sparks ES | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm-Reprographics | 7 | Sparks ES | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Advertisement | 7 | Sparks ES | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Alarm | 7 | Sparks ES | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-CM/PM Management | 7 | Sparks ES | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Construction Contingency | 7 | Sparks ES | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Contractor | 7 | Sparks ES | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Design | 7 | Sparks ES | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-DSA Fees | 7 | Sparks ES | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-DSA Inspection | 7 | Sparks ES | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-DSA Special Inspection | 7 | Sparks ES | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Environ Consultant | 7 | Sparks ES | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-FF & E | 7 | Sparks ES | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Legal Services | 7 | Sparks ES | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Modular Buildings | 7 | Sparks ES | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Move Management | 7 | Sparks ES | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Reprographics | 7 | Sparks ES | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Technology | 7 | Sparks ES | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Advertisement | 2 | Sparks MS | 21st Century | Advertisement | 1181.31 | N/A | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Asbestos oversight/survey/abatement | 2 | Sparks MS | 21st Century | Asbestos oversight/survey/abatement | 56000 | N/A | 0 | 0 | #DIV/0!
Sparks MS-21st Century-CM/PM Management | 2 | Sparks MS | 21st Century | CM/PM Management | 204134.44 | 0 | 145451 | 140977.43 | 96.92%
Sparks MS-21st Century-Construction Contingency | 2 | Sparks MS | 21st Century | Construction Contingency | 184094.8 | N/A | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Contractor | 2 | Sparks MS | 21st Century | Contractor | 1963739.23 | N/A | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Design | 2 | Sparks MS | 21st Century | Design | 225522.57 | 150523 | 175473 | 143181.88 | 81.6%
Sparks MS-21st Century-DSA Fees | 2 | Sparks MS | 21st Century | DSA Fees | 0 | 0 | 22264.25 | 22264.25 | 100%
Sparks MS-21st Century-DSA Inspection | 2 | Sparks MS | 21st Century | DSA Inspection | 32217.51 | N/A | 0 | 0 | #DIV/0!
Sparks MS-21st Century-DSA Special Inspection | 2 | Sparks MS | 21st Century | DSA Special Inspection | 16108.76 | N/A | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Environ Consultant | 2 | Sparks MS | 21st Century | Environ Consultant | 9450.47 | No Proposal Provided | 2950 | 2950 | 100%
Sparks MS-21st Century-FF & E | 2 | Sparks MS | 21st Century | FF & E | 460000 | 0 | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Legal Services | 2 | Sparks MS | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Move classroom | 2 | Sparks MS | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Move Management | 2 | Sparks MS | 21st Century | Move Management | 8591.34 | N/A | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Reprographics | 2 | Sparks MS | 21st Century | Reprographics | 1181.31 | N/A | 0 | 0 | #DIV/0!
Sparks MS-21st Century-Technology | 2 | Sparks MS | 21st Century | Technology | 460000 | No Proposal Provided | 283051.05 | 283051.05 | 100%
Sparks MS-Ceiling replacement-CM/PM Management | 2 | Sparks MS | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Ceiling replacement-Contractor | 2 | Sparks MS | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking fountain replacement-Advertisement | 2 | Sparks MS | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking fountain replacement-Contractor | 2 | Sparks MS | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Sparks MS-Drinking fountain replacement-Design | 2 | Sparks MS | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking fountain replacement-DSA Fees | 2 | Sparks MS | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking fountain replacement-DSA Inspection | 2 | Sparks MS | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking fountain replacement-DSA Special Inspection | 2 | Sparks MS | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking fountain replacement-Environ Consultant | 2 | Sparks MS | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking fountain replacement-Reprographics | 2 | Sparks MS | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Fire Alarm-Advertisement | 2 | Sparks MS | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Fire Alarm-Contractor | 2 | Sparks MS | Fire Alarm | Contractor | 240000 | 162000 | 152000 | 144400 | 95%
Sparks MS-Fire Alarm-Design | 2 | Sparks MS | Fire Alarm | Design | 4950 | No Proposal Provided | 4950 | 4950 | 100%
Sparks MS-Fire Alarm-DSA Fees | 2 | Sparks MS | Fire Alarm | DSA Fees | 0 | 0 | 860 | 860 | 100%
Sparks MS-Fire Alarm-DSA Inspection | 2 | Sparks MS | Fire Alarm | DSA Inspection | 6875 | No Proposal Provided | 6875 | 6875 | 100%
Sparks MS-Fire Alarm-Environ Consultant | 2 | Sparks MS | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Fire Alarm-Reprographics | 2 | Sparks MS | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Advertisement | 2 | Sparks MS | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Alarm | 2 | Sparks MS | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-CM/PM Management | 2 | Sparks MS | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Construction Contingency | 2 | Sparks MS | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Contractor | 2 | Sparks MS | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Design | 2 | Sparks MS | Interim Housing | Design | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-DSA Fees | 2 | Sparks MS | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-DSA Inspection | 2 | Sparks MS | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-DSA Special Inspection | 2 | Sparks MS | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Environ Consultant | 2 | Sparks MS | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-FF & E | 2 | Sparks MS | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Legal Services | 2 | Sparks MS | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Modular Buildings | 2 | Sparks MS | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Move Management | 2 | Sparks MS | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Reprographics | 2 | Sparks MS | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Technology | 2 | Sparks MS | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century-Advertisement | 4 | Stimson | 21st Century | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century-Asbestos oversight/survey/abatement | 4 | Stimson | 21st Century | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century-CM/PM Management | 4 | Stimson | 21st Century | CM/PM Management | 72491 | N/A | 75128 | 10450 | 13.91%
Stimson-21st Century-Construction Contingency | 4 | Stimson | 21st Century | Construction Contingency | 79796.4 | N/A | 0 | 0 | #DIV/0!
Stimson-21st Century-Contractor | 4 | Stimson | 21st Century | Contractor | 851188.2 | N/A | 0 | 0 | #DIV/0!
Stimson-21st Century-Design | 4 | Stimson | 21st Century | Design | 41893.11 | N/A | 0 | 0 | #DIV/0!
Stimson-21st Century-DSA Fees | 4 | Stimson | 21st Century | DSA Fees | 16292.23 | N/A | 0 | 0 | #DIV/0!
Stimson-21st Century-DSA Inspection | 4 | Stimson | 21st Century | DSA Inspection | 13964.77 | N/A | 0 | 0 | #DIV/0!
Stimson-21st Century-DSA Special Inspection | 4 | Stimson | 21st Century | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century-Environ Consultant | 4 | Stimson | 21st Century | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century-FF & E | 4 | Stimson | 21st Century | FF & E | 240000 | N/A | 0 | 0 | #DIV/0!
Stimson-21st Century-Legal Services | 4 | Stimson | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century-Move classroom | 4 | Stimson | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century-Move Management | 4 | Stimson | 21st Century | Move Management | 3723.94 | N/A | 0 | 0 | #DIV/0!
Stimson-21st Century-Reprographics | 4 | Stimson | 21st Century | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century-Technology | 4 | Stimson | 21st Century | Technology | 240000 | No Proposal Provided | 20737.46 | 20737.46 | 100%
Stimson-Ceiling replacement-CM/PM Management | 4 | Stimson | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Ceiling replacement-Contractor | 4 | Stimson | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking fountain replacement-Advertisement | 4 | Stimson | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking fountain replacement-Contractor | 4 | Stimson | Drinking fountain replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking fountain replacement-Design | 4 | Stimson | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking fountain replacement-DSA Fees | 4 | Stimson | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking fountain replacement-DSA Inspection | 4 | Stimson | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking fountain replacement-DSA Special Inspection | 4 | Stimson | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking fountain replacement-Environ Consultant | 4 | Stimson | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking fountain replacement-Reprographics | 4 | Stimson | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm-Advertisement | 4 | Stimson | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm-Contractor | 4 | Stimson | Fire Alarm | Contractor | 180000 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm-Design | 4 | Stimson | Fire Alarm | Design | 39500 | No Proposal Provided | 39500 | 29625 | 75%
Stimson-Fire Alarm-DSA Fees | 4 | Stimson | Fire Alarm | DSA Fees | 375 | No Proposal Provided | 375 | 375 | 100%
Stimson-Fire Alarm-DSA Inspection | 4 | Stimson | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm-Environ Consultant | 4 | Stimson | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm-Reprographics | 4 | Stimson | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Advertisement | 4 | Stimson | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Alarm | 4 | Stimson | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-CM/PM Management | 4 | Stimson | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Construction Contingency | 4 | Stimson | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Contractor | 4 | Stimson | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Design | 4 | Stimson | Interim Housing | Design | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-DSA Fees | 4 | Stimson | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-DSA Inspection | 4 | Stimson | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-DSA Special Inspection | 4 | Stimson | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Environ Consultant | 4 | Stimson | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-FF & E | 4 | Stimson | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Legal Services | 4 | Stimson | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Modular Buildings | 4 | Stimson | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Move Management | 4 | Stimson | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Reprographics | 4 | Stimson | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Technology | 4 | Stimson | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century-Advertisement | 4 | Sunset | 21st Century | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century-Asbestos oversight/survey/abatement | 4 | Sunset | 21st Century | Asbestos oversight/survey/abatement | 42000 | N/A | 0 | 0 | #DIV/0!
Sunset-21st Century-CM/PM Management | 4 | Sunset | 21st Century | CM/PM Management | 139528.37 | N/A | 206602 | 7905 | 3.826%
Sunset-21st Century-Construction Contingency | 4 | Sunset | 21st Century | Construction Contingency | 138170 | N/A | 0 | 0 | #DIV/0!
Sunset-21st Century-Contractor | 4 | Sunset | 21st Century | Contractor | 1473859.39 | No Proposal Provided | 41500 | 41500 | 100%
Sunset-21st Century-Design | 4 | Sunset | 21st Century | Design | 169263.09 | 225488 | 186560 | 29545.89 | 15.84%
Sunset-21st Century-DSA Fees | 4 | Sunset | 21st Century | DSA Fees | 28210.51 | N/A | 0 | 0 | #DIV/0!
Sunset-21st Century-DSA Inspection | 4 | Sunset | 21st Century | DSA Inspection | 24180.44 | N/A | 0 | 0 | #DIV/0!
Sunset-21st Century-DSA Special Inspection | 4 | Sunset | 21st Century | DSA Special Inspection | 12090.22 | N/A | 0 | 0 | #DIV/0!
Sunset-21st Century-Environ Consultant | 4 | Sunset | 21st Century | Environ Consultant | 7092.93 | No Proposal Provided | 2700 | 2700 | 100%
Sunset-21st Century-FF & E | 4 | Sunset | 21st Century | FF & E | 240000 | No Proposal Provided | 20720.61 | 20720.61 | 100%
Sunset-21st Century-Legal Services | 4 | Sunset | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century-Move classroom | 4 | Sunset | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century-Move Management | 4 | Sunset | 21st Century | Move Management | 6448.12 | N/A | 0 | 0 | #DIV/0!
Sunset-21st Century-Reprographics | 4 | Sunset | 21st Century | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century-Technology | 4 | Sunset | 21st Century | Technology | 240000 | No Proposal Provided | 108157.36 | 108157.36 | 100%
Sunset-Ceiling replacement-CM/PM Management | 4 | Sunset | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Ceiling replacement-Contractor | 4 | Sunset | Ceiling replacement | Contractor | 242880 | 242880 | 242880 | 230736 | 95%
Sunset-Drinking fountain replacement-Advertisement | 4 | Sunset | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking fountain replacement-Contractor | 4 | Sunset | Drinking fountain replacement | Contractor | 15000 | No Proposal Provided | 22800 | 22800 | 100%
Sunset-Drinking fountain replacement-Design | 4 | Sunset | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking fountain replacement-DSA Fees | 4 | Sunset | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking fountain replacement-DSA Inspection | 4 | Sunset | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking fountain replacement-DSA Special Inspection | 4 | Sunset | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking fountain replacement-Environ Consultant | 4 | Sunset | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking fountain replacement-Reprographics | 4 | Sunset | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm-Advertisement | 4 | Sunset | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm-Contractor | 4 | Sunset | Fire Alarm | Contractor | 180000 | N/A | 0 | 0 | #DIV/0!
Sunset-Fire Alarm-Design | 4 | Sunset | Fire Alarm | Design | 48500 | No Proposal Provided | 48500 | 36375 | 75%
Sunset-Fire Alarm-DSA Fees | 4 | Sunset | Fire Alarm | DSA Fees | 0 | 0 | 564 | 564 | 100%
Sunset-Fire Alarm-DSA Inspection | 4 | Sunset | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm-Environ Consultant | 4 | Sunset | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm-Reprographics | 4 | Sunset | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Advertisement | 4 | Sunset | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Alarm | 4 | Sunset | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-CM/PM Management | 4 | Sunset | Interim Housing | CM/PM Management | 51650 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Construction Contingency | 4 | Sunset | Interim Housing | Construction Contingency | 77000 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Contractor | 4 | Sunset | Interim Housing | Contractor | 770000 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Design | 4 | Sunset | Interim Housing | Design | 80000 | N/A | 97400 | 0 | 0%
Sunset-Interim Housing-DSA Fees | 4 | Sunset | Interim Housing | DSA Fees | 16100 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-DSA Inspection | 4 | Sunset | Interim Housing | DSA Inspection | 13800 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-DSA Special Inspection | 4 | Sunset | Interim Housing | DSA Special Inspection | 13800 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Environ Consultant | 4 | Sunset | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-FF & E | 4 | Sunset | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Legal Services | 4 | Sunset | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Modular Buildings | 4 | Sunset | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Move Management | 4 | Sunset | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Reprographics | 4 | Sunset | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Technology | 4 | Sunset | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Temple-21st Century-Advertisement | 8 | Temple | 21st Century | Advertisement | 1347.71 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-Asbestos oversight/survey/abatement | 8 | Temple | 21st Century | Asbestos oversight/survey/abatement | 66500 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-CM/PM Management | 8 | Temple | 21st Century | CM/PM Management | 214065.56 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-Construction Contingency | 8 | Temple | 21st Century | Construction Contingency | 210026.6 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-Contractor | 8 | Temple | 21st Century | Contractor | 2240353.74 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-Design | 8 | Temple | 21st Century | Design | 257289.94 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-DSA Fees | 8 | Temple | 21st Century | DSA Fees | 42881.66 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-DSA Inspection | 8 | Temple | 21st Century | DSA Inspection | 36755.71 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-DSA Special Inspection | 8 | Temple | 21st Century | DSA Special Inspection | 18377.85 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-Environ Consultant | 8 | Temple | 21st Century | Environ Consultant | 13477.09 | No Proposal Provided | 2600 | 2600 | 100%
Temple-21st Century-FF & E | 8 | Temple | 21st Century | FF & E | 380000 | No Proposal Provided | 20720.61 | 20720.61 | 100%
Temple-21st Century-Legal Services | 8 | Temple | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Temple-21st Century-Move classroom | 8 | Temple | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Temple-21st Century-Move Management | 8 | Temple | 21st Century | Move Management | 9801.52 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-Reprographics | 8 | Temple | 21st Century | Reprographics | 1347.71 | N/A | 0 | 0 | #DIV/0!
Temple-21st Century-Technology | 8 | Temple | 21st Century | Technology | 380000 | No Proposal Provided | 111520.57 | 111520.57 | 100%
Temple-Ceiling replacement-CM/PM Management | 8 | Temple | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Ceiling replacement-Contractor | 8 | Temple | Ceiling replacement | Contractor | 0 | 0 | 258091 | 245186.45 | 95%
Temple-Drinking fountain replacement-Advertisement | 8 | Temple | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking fountain replacement-Contractor | 8 | Temple | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Temple-Drinking fountain replacement-Design | 8 | Temple | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking fountain replacement-DSA Fees | 8 | Temple | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking fountain replacement-DSA Inspection | 8 | Temple | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking fountain replacement-DSA Special Inspection | 8 | Temple | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking fountain replacement-Environ Consultant | 8 | Temple | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking fountain replacement-Reprographics | 8 | Temple | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm-Advertisement | 8 | Temple | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm-Contractor | 8 | Temple | Fire Alarm | Contractor | 285000 | N/A | 0 | 0 | #DIV/0!
Temple-Fire Alarm-Design | 8 | Temple | Fire Alarm | Design | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm-DSA Fees | 8 | Temple | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm-DSA Inspection | 8 | Temple | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm-Environ Consultant | 8 | Temple | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm-Reprographics | 8 | Temple | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Advertisement | 8 | Temple | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Alarm | 8 | Temple | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-CM/PM Management | 8 | Temple | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Construction Contingency | 8 | Temple | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Contractor | 8 | Temple | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Design | 8 | Temple | Interim Housing | Design | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-DSA Fees | 8 | Temple | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-DSA Inspection | 8 | Temple | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-DSA Special Inspection | 8 | Temple | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Environ Consultant | 8 | Temple | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-FF & E | 8 | Temple | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Legal Services | 8 | Temple | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Modular Buildings | 8 | Temple | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Move Management | 8 | Temple | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Reprographics | 8 | Temple | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Technology | 8 | Temple | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century-Advertisement | 6 | Valinda | 21st Century | Advertisement | 2198.02 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-Asbestos oversight/survey/abatement | 6 | Valinda | 21st Century | Asbestos oversight/survey/abatement | 108500 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-CM/PM Management | 6 | Valinda | 21st Century | CM/PM Management | 349157.78 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-Construction Contingency | 6 | Valinda | 21st Century | Construction Contingency | 342538.4 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-Contractor | 6 | Valinda | 21st Century | Contractor | 3653857.11 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-Design | 6 | Valinda | 21st Century | Design | 419621.53 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-DSA Fees | 6 | Valinda | 21st Century | DSA Fees | 69936.92 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-DSA Inspection | 6 | Valinda | 21st Century | DSA Inspection | 59945.93 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-DSA Special Inspection | 6 | Valinda | 21st Century | DSA Special Inspection | 29972.97 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-Environ Consultant | 6 | Valinda | 21st Century | Environ Consultant | 17584.14 | No Proposal Provided | 3000 | 3000 | 100%
Valinda-21st Century-FF & E | 6 | Valinda | 21st Century | FF & E | 620000 | No Proposal Provided | 22185.39 | 22185.39 | 100%
Valinda-21st Century-Legal Services | 6 | Valinda | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century-Move classroom | 6 | Valinda | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century-Move Management | 6 | Valinda | 21st Century | Move Management | 15985.58 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-Reprographics | 6 | Valinda | 21st Century | Reprographics | 2198.02 | N/A | 0 | 0 | #DIV/0!
Valinda-21st Century-Technology | 6 | Valinda | 21st Century | Technology | 620000 | No Proposal Provided | 262009.2 | 262009.2 | 100%
Valinda-Ceiling replacement-CM/PM Management | 6 | Valinda | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Ceiling replacement-Contractor | 6 | Valinda | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking fountain replacement-Advertisement | 6 | Valinda | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking fountain replacement-Contractor | 6 | Valinda | Drinking fountain replacement | Contractor | 30000 | N/A | 0 | 0 | #DIV/0!
Valinda-Drinking fountain replacement-Design | 6 | Valinda | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking fountain replacement-DSA Fees | 6 | Valinda | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking fountain replacement-DSA Inspection | 6 | Valinda | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking fountain replacement-DSA Special Inspection | 6 | Valinda | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking fountain replacement-Environ Consultant | 6 | Valinda | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking fountain replacement-Reprographics | 6 | Valinda | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm-Advertisement | 6 | Valinda | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm-Contractor | 6 | Valinda | Fire Alarm | Contractor | 465000 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm-Design | 6 | Valinda | Fire Alarm | Design | 12375 | No Proposal Provided | 12375 | 0 | 0%
Valinda-Fire Alarm-DSA Fees | 6 | Valinda | Fire Alarm | DSA Fees | 0 | 0 | 1125 | 1125 | 100%
Valinda-Fire Alarm-DSA Inspection | 6 | Valinda | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm-Environ Consultant | 6 | Valinda | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm-Reprographics | 6 | Valinda | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Advertisement | 6 | Valinda | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Alarm | 6 | Valinda | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-CM/PM Management | 6 | Valinda | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Construction Contingency | 6 | Valinda | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Contractor | 6 | Valinda | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Design | 6 | Valinda | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-DSA Fees | 6 | Valinda | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-DSA Inspection | 6 | Valinda | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-DSA Special Inspection | 6 | Valinda | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Environ Consultant | 6 | Valinda | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-FF & E | 6 | Valinda | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Legal Services | 6 | Valinda | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Modular Buildings | 6 | Valinda | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Move Management | 6 | Valinda | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Reprographics | 6 | Valinda | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Technology | 6 | Valinda | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Valley-21st Century-Advertisement | 8 | Valley | 21st Century | Advertisement | 894.83 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-Asbestos oversight/survey/abatement | 8 | Valley | 21st Century | Asbestos oversight/survey/abatement | 42000 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-CM/PM Management | 8 | Valley | 21st Century | CM/PM Management | 140531.3 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-Construction Contingency | 8 | Valley | 21st Century | Construction Contingency | 139449.2 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-Contractor | 8 | Valley | 21st Century | Contractor | 1487504.62 | N/A | 19116.72 | 19116.72 | 100%
Valley-21st Century-Design | 8 | Valley | 21st Century | Design | 170830.15 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-DSA Fees | 8 | Valley | 21st Century | DSA Fees | 28471.69 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-DSA Inspection | 8 | Valley | 21st Century | DSA Inspection | 24404.31 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-DSA Special Inspection | 8 | Valley | 21st Century | DSA Special Inspection | 12202.15 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-Environ Consultant | 8 | Valley | 21st Century | Environ Consultant | 8948.25 | No Proposal Provided | 2700 | 2700 | 100%
Valley-21st Century-FF & E | 8 | Valley | 21st Century | FF & E | 240000 | 0 | 0 | 0 | #DIV/0!
Valley-21st Century-Legal Services | 8 | Valley | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Valley-21st Century-Move classroom | 8 | Valley | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Valley-21st Century-Move Management | 8 | Valley | 21st Century | Move Management | 6507.82 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-Reprographics | 8 | Valley | 21st Century | Reprographics | 894.83 | N/A | 0 | 0 | #DIV/0!
Valley-21st Century-Technology | 8 | Valley | 21st Century | Technology | 240000 | 0 | 87145.31 | 87145.31 | 100%
Valley-Ceiling replacement-CM/PM Management | 8 | Valley | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Ceiling replacement-Contractor | 8 | Valley | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking fountain replacement-Advertisement | 8 | Valley | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking fountain replacement-Contractor | 8 | Valley | Drinking fountain replacement | Contractor | 15000 | N/A | 0 | 0 | #DIV/0!
Valley-Drinking fountain replacement-Design | 8 | Valley | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking fountain replacement-DSA Fees | 8 | Valley | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking fountain replacement-DSA Inspection | 8 | Valley | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking fountain replacement-DSA Special Inspection | 8 | Valley | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking fountain replacement-Environ Consultant | 8 | Valley | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking fountain replacement-Reprographics | 8 | Valley | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Fire Alarm-Advertisement | 8 | Valley | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Fire Alarm-Contractor | 8 | Valley | Fire Alarm | Contractor | 216000 | 217149.4 | 231990.91 | 219916.37 | 94.8%
Valley-Fire Alarm-Design | 8 | Valley | Fire Alarm | Design | 11375 | No Proposal Provided | 11375 | 11375 | 100%
Valley-Fire Alarm-DSA Fees | 8 | Valley | Fire Alarm | DSA Fees | 630 | No Proposal Provided | 1328.75 | 1328.75 | 100%
Valley-Fire Alarm-DSA Inspection | 8 | Valley | Fire Alarm | DSA Inspection | 7350 | No Proposal Provided | 7350 | 7350 | 100%
Valley-Fire Alarm-Environ Consultant | 8 | Valley | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Fire Alarm-Reprographics | 8 | Valley | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Advertisement | 8 | Valley | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-Alarm | 8 | Valley | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-CM/PM Management | 8 | Valley | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-Construction Contingency | 8 | Valley | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-Contractor | 8 | Valley | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-Design | 8 | Valley | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-DSA Fees | 8 | Valley | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-DSA Inspection | 8 | Valley | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-DSA Special Inspection | 8 | Valley | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-Environ Consultant | 8 | Valley | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-FF & E | 8 | Valley | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Legal Services | 8 | Valley | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Modular Buildings | 8 | Valley | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-Move Management | 8 | Valley | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Reprographics | 8 | Valley | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | #DIV/0!
Valley-Interim Housing-Technology | 8 | Valley | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Advertisement | 0 | Wedgeworth | 21st Century | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Asbestos oversight/survey/abatement | 0 | Wedgeworth | 21st Century | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-CM/PM Management | 0 | Wedgeworth | 21st Century | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Construction Contingency | 0 | Wedgeworth | 21st Century | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Contractor | 0 | Wedgeworth | 21st Century | Contractor | 0 | 0 | 12744.48 | 12744.48 | 100%
Wedgeworth-21st Century-Design | 0 | Wedgeworth | 21st Century | Design | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-DSA Fees | 0 | Wedgeworth | 21st Century | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-DSA Inspection | 0 | Wedgeworth | 21st Century | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-DSA Special Inspection | 0 | Wedgeworth | 21st Century | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Environ Consultant | 0 | Wedgeworth | 21st Century | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-FF & E | 0 | Wedgeworth | 21st Century | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Legal Services | 0 | Wedgeworth | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Move classroom | 0 | Wedgeworth | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Move Management | 0 | Wedgeworth | 21st Century | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Reprographics | 0 | Wedgeworth | 21st Century | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century-Technology | 0 | Wedgeworth | 21st Century | Technology | 0 | 0 | 146165.5 | 146165.5 | 100%
Wedgeworth-Ceiling replacement-CM/PM Management | 0 | Wedgeworth | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Ceiling replacement-Contractor | 0 | Wedgeworth | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking fountain replacement-Advertisement | 0 | Wedgeworth | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking fountain replacement-Contractor | 0 | Wedgeworth | Drinking fountain replacement | Contractor | 0 | 0 | 6500 | 3502.75 | 53.89%
Wedgeworth-Drinking fountain replacement-Design | 0 | Wedgeworth | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking fountain replacement-DSA Fees | 0 | Wedgeworth | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking fountain replacement-DSA Inspection | 0 | Wedgeworth | Drinking fountain replacement | DSA Inspection | 0 | 0 | 1200 | 0 | 0%
Wedgeworth-Drinking fountain replacement-DSA Special Inspection | 0 | Wedgeworth | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking fountain replacement-Environ Consultant | 0 | Wedgeworth | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking fountain replacement-Reprographics | 0 | Wedgeworth | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm-Advertisement | 0 | Wedgeworth | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm-Contractor | 0 | Wedgeworth | Fire Alarm | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm-Design | 0 | Wedgeworth | Fire Alarm | Design | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm-DSA Fees | 0 | Wedgeworth | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm-DSA Inspection | 0 | Wedgeworth | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm-Environ Consultant | 0 | Wedgeworth | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm-Reprographics | 0 | Wedgeworth | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Advertisement | 0 | Wedgeworth | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Alarm | 0 | Wedgeworth | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-CM/PM Management | 0 | Wedgeworth | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Construction Contingency | 0 | Wedgeworth | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Contractor | 0 | Wedgeworth | Interim Housing | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Design | 0 | Wedgeworth | Interim Housing | Design | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-DSA Fees | 0 | Wedgeworth | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-DSA Inspection | 0 | Wedgeworth | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-DSA Special Inspection | 0 | Wedgeworth | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Environ Consultant | 0 | Wedgeworth | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-FF & E | 0 | Wedgeworth | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Legal Services | 0 | Wedgeworth | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Modular Buildings | 0 | Wedgeworth | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Move Management | 0 | Wedgeworth | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Reprographics | 0 | Wedgeworth | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Technology | 0 | Wedgeworth | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Advertisement | 0 | Willow | 21st Century | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Asbestos oversight/survey/abatement | 0 | Willow | 21st Century | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-CM/PM Management | 0 | Willow | 21st Century | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Construction Contingency | 0 | Willow | 21st Century | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Contractor | 0 | Willow | 21st Century | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Design | 0 | Willow | 21st Century | Design | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-DSA Fees | 0 | Willow | 21st Century | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-DSA Inspection | 0 | Willow | 21st Century | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-DSA Special Inspection | 0 | Willow | 21st Century | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Environ Consultant | 0 | Willow | 21st Century | Environ Consultant | 0 | 0 | 2700 | 2700 | 100%
Willow-21st Century-FF & E | 0 | Willow | 21st Century | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Legal Services | 0 | Willow | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Move classroom | 0 | Willow | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Move Management | 0 | Willow | 21st Century | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Reprographics | 0 | Willow | 21st Century | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century-Technology | 0 | Willow | 21st Century | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Ceiling replacement-CM/PM Management | 0 | Willow | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Ceiling replacement-Contractor | 0 | Willow | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking fountain replacement-Advertisement | 0 | Willow | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking fountain replacement-Contractor | 0 | Willow | Drinking fountain replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking fountain replacement-Design | 0 | Willow | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking fountain replacement-DSA Fees | 0 | Willow | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking fountain replacement-DSA Inspection | 0 | Willow | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking fountain replacement-DSA Special Inspection | 0 | Willow | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking fountain replacement-Environ Consultant | 0 | Willow | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking fountain replacement-Reprographics | 0 | Willow | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm-Advertisement | 0 | Willow | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm-Contractor | 0 | Willow | Fire Alarm | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm-Design | 0 | Willow | Fire Alarm | Design | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm-DSA Fees | 0 | Willow | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm-DSA Inspection | 0 | Willow | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm-Environ Consultant | 0 | Willow | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm-Reprographics | 0 | Willow | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Advertisement | 0 | Willow | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Alarm | 0 | Willow | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-CM/PM Management | 0 | Willow | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Construction Contingency | 0 | Willow | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Contractor | 0 | Willow | Interim Housing | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Design | 0 | Willow | Interim Housing | Design | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-DSA Fees | 0 | Willow | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-DSA Inspection | 0 | Willow | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-DSA Special Inspection | 0 | Willow | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Environ Consultant | 0 | Willow | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-FF & E | 0 | Willow | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Legal Services | 0 | Willow | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Modular Buildings | 0 | Willow | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Move Management | 0 | Willow | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Reprographics | 0 | Willow | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Technology | 0 | Willow | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Advertisement | 5 | Wilson HS | 21st Century | Advertisement | 5225.48 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Asbestos oversight/survey/abatement | 5 | Wilson HS | 21st Century | Asbestos oversight/survey/abatement | 231000 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-CM/PM Management | 5 | Wilson HS | 21st Century | CM/PM Management | 810058.76 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Construction Contingency | 5 | Wilson HS | 21st Century | Construction Contingency | 814337.4 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Contractor | 5 | Wilson HS | 21st Century | Contractor | 8686537.05 | No Proposal Provided | 19116.72 | 19116.72 | 100%
Wilson HS-21st Century-Design | 5 | Wilson HS | 21st Century | Design | 997591.82 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-DSA Fees | 5 | Wilson HS | 21st Century | DSA Fees | 166265.3 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-DSA Inspection | 5 | Wilson HS | 21st Century | DSA Inspection | 142513.12 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-DSA Special Inspection | 5 | Wilson HS | 21st Century | DSA Special Inspection | 71256.56 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Environ Consultant | 5 | Wilson HS | 21st Century | Environ Consultant | 52254.81 | N/A | 3400 | 3400 | 100%
Wilson HS-21st Century-FF & E | 5 | Wilson HS | 21st Century | FF & E | 1320000 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Legal Services | 5 | Wilson HS | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Move classroom | 5 | Wilson HS | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Move Management | 5 | Wilson HS | 21st Century | Move Management | 38003.5 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Reprographics | 5 | Wilson HS | 21st Century | Reprographics | 5225.48 | N/A | 0 | 0 | #DIV/0!
Wilson HS-21st Century-Technology | 5 | Wilson HS | 21st Century | Technology | 1320000 | N/A | 671830.97 | 671830.97 | 100%
Wilson HS-Ceiling replacement-CM/PM Management | 5 | Wilson HS | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Ceiling replacement-Contractor | 5 | Wilson HS | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking fountain replacement-Advertisement | 5 | Wilson HS | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking fountain replacement-Contractor | 5 | Wilson HS | Drinking fountain replacement | Contractor | 60000 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Drinking fountain replacement-Design | 5 | Wilson HS | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking fountain replacement-DSA Fees | 5 | Wilson HS | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking fountain replacement-DSA Inspection | 5 | Wilson HS | Drinking fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 1200 | 0 | 0%
Wilson HS-Drinking fountain replacement-DSA Special Inspection | 5 | Wilson HS | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking fountain replacement-Environ Consultant | 5 | Wilson HS | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking fountain replacement-Reprographics | 5 | Wilson HS | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Fire Alarm-Advertisement | 5 | Wilson HS | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Fire Alarm-Contractor | 5 | Wilson HS | Fire Alarm | Contractor | 1188000 | 291000 | 282060.18 | 260791.17 | 92.46%
Wilson HS-Fire Alarm-Design | 5 | Wilson HS | Fire Alarm | Design | 0 | 0 | 11375 | 6825 | 60%
Wilson HS-Fire Alarm-DSA Fees | 5 | Wilson HS | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Fire Alarm-DSA Inspection | 5 | Wilson HS | Fire Alarm | DSA Inspection | 16500 | No Proposal Provided | 16500 | 16000 | 96.97%
Wilson HS-Fire Alarm-Environ Consultant | 5 | Wilson HS | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Fire Alarm-Reprographics | 5 | Wilson HS | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Advertisement | 5 | Wilson HS | Interim Housing | Advertisement | 1000 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Alarm | 5 | Wilson HS | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-CM/PM Management | 5 | Wilson HS | Interim Housing | CM/PM Management | 55275 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Construction Contingency | 5 | Wilson HS | Interim Housing | Construction Contingency | 82500 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Contractor | 5 | Wilson HS | Interim Housing | Contractor | 825000 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Design | 5 | Wilson HS | Interim Housing | Design | 82500 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-DSA Fees | 5 | Wilson HS | Interim Housing | DSA Fees | 14437.5 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-DSA Inspection | 5 | Wilson HS | Interim Housing | DSA Inspection | 15750 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-DSA Special Inspection | 5 | Wilson HS | Interim Housing | DSA Special Inspection | 15750 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Environ Consultant | 5 | Wilson HS | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-FF & E | 5 | Wilson HS | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Legal Services | 5 | Wilson HS | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Modular Buildings | 5 | Wilson HS | Interim Housing | Modular Buildings | 225000 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Move Management | 5 | Wilson HS | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Reprographics | 5 | Wilson HS | Interim Housing | Reprographics | 1000 | N/A | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Technology | 5 | Wilson HS | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Advertisement | 9 | Wing Lane | 21st Century | Advertisement | 1482.47 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Asbestos oversight/survey/abatement | 9 | Wing Lane | 21st Century | Asbestos oversight/survey/abatement | 73500 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-CM/PM Management | 9 | Wing Lane | 21st Century | CM/PM Management | 235730.26 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Construction Contingency | 9 | Wing Lane | 21st Century | Construction Contingency | 231026.9 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Contractor | 9 | Wing Lane | 21st Century | Contractor | 2464363.94 | N/A | 40000 | 40000 | 100%
Wing Lane-21st Century-Design | 9 | Wing Lane | 21st Century | Design | 283016.04 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-DSA Fees | 9 | Wing Lane | 21st Century | DSA Fees | 47169.34 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-DSA Inspection | 9 | Wing Lane | 21st Century | DSA Inspection | 40430.86 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-DSA Special Inspection | 9 | Wing Lane | 21st Century | DSA Special Inspection | 20215.43 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Environ Consultant | 9 | Wing Lane | 21st Century | Environ Consultant | 11859.72 | N/A | 2600 | 2600 | 100%
Wing Lane-21st Century-FF & E | 9 | Wing Lane | 21st Century | FF & E | 420000 | No Proposal Provided | 20720.61 | 20720.61 | 100%
Wing Lane-21st Century-Legal Services | 9 | Wing Lane | 21st Century | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Move classroom | 9 | Wing Lane | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Move Management | 9 | Wing Lane | 21st Century | Move Management | 10781.56 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Reprographics | 9 | Wing Lane | 21st Century | Reprographics | 1482.47 | N/A | 0 | 0 | #DIV/0!
Wing Lane-21st Century-Technology | 9 | Wing Lane | 21st Century | Technology | 420000 | No Proposal Provided | 110563.9 | 110563.9 | 100%
Wing Lane-Ceiling replacement-CM/PM Management | 9 | Wing Lane | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Ceiling replacement-Contractor | 9 | Wing Lane | Ceiling replacement | Contractor | 302738 | 302738 | 302738 | 287601.1 | 95%
Wing Lane-Drinking fountain replacement-Advertisement | 9 | Wing Lane | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking fountain replacement-Contractor | 9 | Wing Lane | Drinking fountain replacement | Contractor | 15000 | 0 | 6800 | 6800 | 100%
Wing Lane-Drinking fountain replacement-Design | 9 | Wing Lane | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking fountain replacement-DSA Fees | 9 | Wing Lane | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking fountain replacement-DSA Inspection | 9 | Wing Lane | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking fountain replacement-DSA Special Inspection | 9 | Wing Lane | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking fountain replacement-Environ Consultant | 9 | Wing Lane | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking fountain replacement-Reprographics | 9 | Wing Lane | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm-Advertisement | 9 | Wing Lane | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm-Contractor | 9 | Wing Lane | Fire Alarm | Contractor | 315000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm-Design | 9 | Wing Lane | Fire Alarm | Design | 48500 | No Proposal Provided | 48500 | 36375 | 75%
Wing Lane-Fire Alarm-DSA Fees | 9 | Wing Lane | Fire Alarm | DSA Fees | 0 | 0 | 870 | 870 | 100%
Wing Lane-Fire Alarm-DSA Inspection | 9 | Wing Lane | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm-Environ Consultant | 9 | Wing Lane | Fire Alarm | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm-Reprographics | 9 | Wing Lane | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Advertisement | 9 | Wing Lane | Interim Housing | Advertisement | 1000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Alarm | 9 | Wing Lane | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-CM/PM Management | 9 | Wing Lane | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Construction Contingency | 9 | Wing Lane | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Contractor | 9 | Wing Lane | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Design | 9 | Wing Lane | Interim Housing | Design | 80000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-DSA Fees | 9 | Wing Lane | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-DSA Inspection | 9 | Wing Lane | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-DSA Special Inspection | 9 | Wing Lane | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Environ Consultant | 9 | Wing Lane | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-FF & E | 9 | Wing Lane | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Legal Services | 9 | Wing Lane | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Modular Buildings | 9 | Wing Lane | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Move Management | 9 | Wing Lane | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Reprographics | 9 | Wing Lane | Interim Housing | Reprographics | 1000 | N/A | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Technology | 9 | Wing Lane | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century-Advertisement | 2 | Workman ES | 21st Century | Advertisement | 1328.8 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century-Asbestos oversight/survey/abatement | 2 | Workman ES | 21st Century | Asbestos oversight/survey/abatement | 66500 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century-CM/PM Management | 2 | Workman ES | 21st Century | CM/PM Management | 211755.44 | 169207 | 169207 | 154497.61 | 91.31%
Workman ES-21st Century-Construction Contingency | 2 | Workman ES | 21st Century | Construction Contingency | 207080.1 | 152162.3 | 0 | 0 | #DIV/0!
Workman ES-21st Century-Contractor | 2 | Workman ES | 21st Century | Contractor | 2208923.43 | 1521623 | 1597166.51 | 1371779.35 | 85.89%
Workman ES-21st Century-Design | 2 | Workman ES | 21st Century | Design | 253680.37 | 138184 | 151712 | 128060.23 | 84.41%
Workman ES-21st Century-DSA Fees | 2 | Workman ES | 21st Century | DSA Fees | 42280.06 | 11750 | 24635.87 | 24635.87 | 100%
Workman ES-21st Century-DSA Inspection | 2 | Workman ES | 21st Century | DSA Inspection | 36240.05 | 0 | 34720 | 25480 | 73.39%
Workman ES-21st Century-DSA Special Inspection | 2 | Workman ES | 21st Century | DSA Special Inspection | 18120.03 | 0 | 16600 | 507.5 | 3.057%
Workman ES-21st Century-Environ Consultant | 2 | Workman ES | 21st Century | Environ Consultant | 10630.42 | 0 | 15700 | 11300 | 71.97%
Workman ES-21st Century-FF & E | 2 | Workman ES | 21st Century | FF & E | 380000 | 209239.26 | 360386.91 | 360386.91 | 100%
Workman ES-21st Century-Legal Services | 2 | Workman ES | 21st Century | Legal Services | 5315.21 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century-Move classroom | 2 | Workman ES | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century-Move Management | 2 | Workman ES | 21st Century | Move Management | 9664.01 | No Proposal Provided | 9416.09 | 9416.09 | 100%
Workman ES-21st Century-Reprographics | 2 | Workman ES | 21st Century | Reprographics | 1328.8 | 0 | 1980.22 | 1980.22 | 100%
Workman ES-21st Century-Technology | 2 | Workman ES | 21st Century | Technology | 380000 | 26216.56 | 223422.69 | 222464.71 | 99.57%
Workman ES-Ceiling replacement-CM/PM Management | 2 | Workman ES | Ceiling replacement | CM/PM Management | 206440.23 | 0 | 0 | 0 | #DIV/0!
Workman ES-Ceiling replacement-Contractor | 2 | Workman ES | Ceiling replacement | Contractor | 2428800 | 242880 | 242880 | 230736 | 95%
Workman ES-Drinking fountain replacement-Advertisement | 2 | Workman ES | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking fountain replacement-Contractor | 2 | Workman ES | Drinking fountain replacement | Contractor | 12600 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking fountain replacement-Design | 2 | Workman ES | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking fountain replacement-DSA Fees | 2 | Workman ES | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking fountain replacement-DSA Inspection | 2 | Workman ES | Drinking fountain replacement | DSA Inspection | 1200 | 0 | 1200 | 1200 | 100%
Workman ES-Drinking fountain replacement-DSA Special Inspection | 2 | Workman ES | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking fountain replacement-Environ Consultant | 2 | Workman ES | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking fountain replacement-Reprographics | 2 | Workman ES | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Fire Alarm-Advertisement | 2 | Workman ES | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Fire Alarm-Contractor | 2 | Workman ES | Fire Alarm | Contractor | 109500 | 109500 | 133767.01 | 125992.76 | 94.19%
Workman ES-Fire Alarm-Design | 2 | Workman ES | Fire Alarm | Design | 11875 | No Proposal Provided | 11875 | 11875 | 100%
Workman ES-Fire Alarm-DSA Fees | 2 | Workman ES | Fire Alarm | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Fire Alarm-DSA Inspection | 2 | Workman ES | Fire Alarm | DSA Inspection | 12250 | 12250 | 12250 | 11750 | 95.92%
Workman ES-Fire Alarm-Environ Consultant | 2 | Workman ES | Fire Alarm | Environ Consultant | N/A | 0 | 0 | 0 | #DIV/0!
Workman ES-Fire Alarm-Reprographics | 2 | Workman ES | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Advertisement | 2 | Workman ES | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Alarm | 2 | Workman ES | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-CM/PM Management | 2 | Workman ES | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Construction Contingency | 2 | Workman ES | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Contractor | 2 | Workman ES | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Design | 2 | Workman ES | Interim Housing | Design | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-DSA Fees | 2 | Workman ES | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-DSA Inspection | 2 | Workman ES | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-DSA Special Inspection | 2 | Workman ES | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Environ Consultant | 2 | Workman ES | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-FF & E | 2 | Workman ES | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Legal Services | 2 | Workman ES | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Modular Buildings | 2 | Workman ES | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Move Management | 2 | Workman ES | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Reprographics | 2 | Workman ES | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Technology | 2 | Workman ES | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Advertisement | 5 | Workman HS | 21st Century | Advertisement | 9515.36 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Asbestos oversight/survey/abatement | 5 | Workman HS | 21st Century | Asbestos oversight/survey/abatement | 206500 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-CM/PM Management | 5 | Workman HS | 21st Century | CM/PM Management | 715671.39 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Construction Contingency | 5 | Workman HS | 21st Century | Construction Contingency | 741435.6 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Contractor | 5 | Workman HS | 21st Century | Contractor | 7414356 | 0 | 57350.16 | 57350.16 | 100%
Workman HS-21st Century-Design | 5 | Workman HS | 21st Century | Design | 908284.56 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-DSA Fees | 5 | Workman HS | 21st Century | DSA Fees | 151380.76 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-DSA Inspection | 5 | Workman HS | 21st Century | DSA Inspection | 129754.94 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-DSA Special Inspection | 5 | Workman HS | 21st Century | DSA Special Inspection | 64877.47 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Environ Consultant | 5 | Workman HS | 21st Century | Environ Consultant | 38061.45 | 0 | 4150 | 4150 | 100%
Workman HS-21st Century-FF & E | 5 | Workman HS | 21st Century | FF & E | 1180000 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Legal Services | 5 | Workman HS | 21st Century | Legal Services | 19030.72 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Move classroom | 5 | Workman HS | 21st Century | Move classroom | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Move Management | 5 | Workman HS | 21st Century | Move Management | 34601.32 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Reprographics | 5 | Workman HS | 21st Century | Reprographics | 9515.36 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century-Technology | 5 | Workman HS | 21st Century | Technology | 1180000 | 0 | 499638.02 | 499638.02 | 100%
Workman HS-Ceiling replacement-CM/PM Management | 5 | Workman HS | Ceiling replacement | CM/PM Management | no scope | 0 | 0 | 0 | #DIV/0!
Workman HS-Ceiling replacement-Contractor | 5 | Workman HS | Ceiling replacement | Contractor | no scope | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking fountain replacement-Advertisement | 5 | Workman HS | Drinking fountain replacement | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking fountain replacement-Contractor | 5 | Workman HS | Drinking fountain replacement | Contractor | 48000 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking fountain replacement-Design | 5 | Workman HS | Drinking fountain replacement | Design | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking fountain replacement-DSA Fees | 5 | Workman HS | Drinking fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking fountain replacement-DSA Inspection | 5 | Workman HS | Drinking fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking fountain replacement-DSA Special Inspection | 5 | Workman HS | Drinking fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking fountain replacement-Environ Consultant | 5 | Workman HS | Drinking fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking fountain replacement-Reprographics | 5 | Workman HS | Drinking fountain replacement | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm-Advertisement | 5 | Workman HS | Fire Alarm | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm-Contractor | 5 | Workman HS | Fire Alarm | Contractor | 1062000 | 300000 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm-Design | 5 | Workman HS | Fire Alarm | Design | 68600 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm-DSA Fees | 5 | Workman HS | Fire Alarm | DSA Fees | 18585 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm-DSA Inspection | 5 | Workman HS | Fire Alarm | DSA Inspection | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm-Environ Consultant | 5 | Workman HS | Fire Alarm | Environ Consultant | 0 | N/A | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm-Reprographics | 5 | Workman HS | Fire Alarm | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Advertisement | 5 | Workman HS | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Alarm | 5 | Workman HS | Interim Housing | Alarm | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-CM/PM Management | 5 | Workman HS | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Construction Contingency | 5 | Workman HS | Interim Housing | Construction Contingency | 82500 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Contractor | 5 | Workman HS | Interim Housing | Contractor | 825000 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Design | 5 | Workman HS | Interim Housing | Design | 82500 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-DSA Fees | 5 | Workman HS | Interim Housing | DSA Fees | 14437.5 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-DSA Inspection | 5 | Workman HS | Interim Housing | DSA Inspection | 15750 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-DSA Special Inspection | 5 | Workman HS | Interim Housing | DSA Special Inspection | 15750 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Environ Consultant | 5 | Workman HS | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-FF & E | 5 | Workman HS | Interim Housing | FF & E | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Legal Services | 5 | Workman HS | Interim Housing | Legal Services | 1650 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Modular Buildings | 5 | Workman HS | Interim Housing | Modular Buildings | 225000 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Move Management | 5 | Workman HS | Interim Housing | Move Management | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Reprographics | 5 | Workman HS | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Technology | 5 | Workman HS | Interim Housing | Technology | 0 | 0 | 0 | 0 | #DIV/0!
|  |  |  | Total: | 226017114.27 | 32074506.9 | 47717129.11 | 40797565.55
Note on E1: Per Dan Franco @Cumming
Note on F1: Data from Dan Franco & Jessica Morley @Cumming updated as of 10/08/21
Note on G1: Data from Dan Franco & Jessica Morley @Cumming updated as of 10/08/21

## Comparison_P
MEASURE BB
Project Description | Preliminary Budget | Proposed Budget | Total Exp. & Committed | Completed Amount | Category | Preliminary Budget | Proposed Budget | Total Exp. & Committed | Completed Amount |  | Category | Total Exp. & Committed | Completed Amount
21st Century | 177333135.47 | 19677470.97 | 34190682.31 | 29112099.27 | Advertisement | 74642.95 | 0 | 3236.25 | 2625 |  | Utilities | 1072 | 1072
Ceiling replacement | 6426085.23 | 4033905 | 4573414 | 4190257.62 | Alarm | 3898 | 0 | 3498 | 715.5 |  | Technology | 9238954.48 | 9237996.5
Cost of Issuance | 1572741.59 | 0 | 465750 | 465750 | Asbestos oversight/survey/abatement | 2901207.24 | 12480 | 0 | 0 |  | Reprographics | 10759.99 | 6722.14
Design guidelines | 29500 | 29500 | 29500 | 24000 | CM/PM Management | 10909889.37 | 1742449 | 4066100 | 2010095 |  | Move Management | 47013.91 | 47013.91
Drinking fountain replacement | 782200 | 24200 | 82300 | 68502.75 | Construction Contingency | 11261001.45 | 843362.3 | 0 | 0 |  | Move classroom | 4401.06 | 4401.06
Fire Alarm | 13626510 | 4491539.03 | 3148874.22 | 2816785.23 | Contractor | 137944881.2 | 22495924.34 | 23227709.8 | 21514339.73 |  | Modular Buildings | 1196114.7 | 1196114.7
Interim Housing | 26246941.98 | 3817891.9 | 5226608.58 | 4120170.68 | Design | 14294886.36 | 3236461.69 | 4985728.07 | 2189351.06 |  | Legal Services | 102571.44 | 67648.94
Total: | 226017114.27 | 32074506.9 | 47717129.11 | 40797565.55 | DSA Fees | 2118169.18 | 82681.7 | 279477 | 279477 |  | Issuance costs | 465750 | 465750
[5 empty] | DSA Inspection | 2131082.83 | 288598 | 529413 | 428649 |  | FF & E | 3238799.41 | 3127091.51
[5 empty] | DSA Special Inspection | 1163678.71 | 57340 | 114445 | 49257.5 |  | Environ Consultant | 202085 | 169245
[5 empty] | Environ Consultant | 491240.05 | 13900 | 202085 | 169245 |  | DSA Special Inspection | 114445 | 49257.5
[5 empty] | FF & E | 17705687.26 | 2320774.65 | 3238799.41 | 3127091.51 |  | DSA Inspection | 529413 | 428649
[5 empty] | Issuance costs | 1572741.59 | 0 | 465750 | 465750 |  | DSA Fees | 279477 | 279477
[5 empty] | Legal Services | 800384.07 | 0 | 102571.44 | 67648.94 |  | Design | 4985728.07 | 2189351.06
[5 empty] | Modular Buildings | 4496285.7 | 716708.22 | 1196114.7 | 1196114.7 |  | Contractor | 23227709.8 | 21514339.73
[5 empty] | Move classroom | 146130.33 | 0 | 4401.06 | 4401.06 |  | Construction Contingency | 0 | 0
[5 empty] | Move Management | 391756.6 | 0 | 47013.91 | 47013.91 |  | CM/PM Management | 4066100 | 2010095
[5 empty] | Reprographics | 84654.04 | 1661.08 | 10759.99 | 6722.14 |  | Asbestos oversight/survey/abatement | 0 | 0
[5 empty] | Technology | 17524897.34 | 262165.92 | 9238954.48 | 9237996.5 |  | Alarm | 3498 | 715.5
[5 empty] | Utilities | 0 | 0 | 1072 | 1072 |  | Advertisement | 3236.25 | 2625
[5 empty] | Total: | 226017114.27 | 32074506.9 | 47717129.11 | 40797565.55 | FF & E: Furniture, Fixtures & Equipment | Total: | 47717129.11 | 40797565.55
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.