## Slide 1: 21st Century Classroom Improvements
March 24, 2022 Board Update

## Slide 2
INTERIM HOUSING |  |  |  |  |  |  | 21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION |  | SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
75%
Newton Middle School
INTERIM HOUSING
SYSTEMS INSTALLATION
Project Status
Interim Housing Construction Nearing Completion
Current Tasks
  Electrical Near Complete
  Low Voltage
  Fire Alarm
  Seal Coat
  Plumbing
NOTES
100%
100%
100%
100%
100%
100%
100%
100%
UNDER CONSTRUCTION

## Slide 3
PROGRESS TRACKING
Chart: Newton Middle School Interim Housing Budget
| BILLED | REMAINING
Interim Housing | 50 | 50
$475.95 K
Chart: Construction Progress - % of Completion
| % Complete
Work Completed | 75
Budget and Schedule
Project Status
$475.95 K
Total Budget
$951.9 K

## Slide 4
Newton Middle School Interim Housing Schedule
Fixture change out during Spring break
Supply change equipment delay fire alarm panel only

## Slide 5
Grandview Academy, Newton, Sparks MS
Programming & Qualifying
Project Status
  21st Century Classroom Projects APPROVED BY DSA
  Newton Middle School 6-30-21
  Grandview College Prep 6-30-21
  Sparks Middle School 6-30-21
  Scope review meetings to gain stakeholder input per the Board's guidance at the Special Board Meeting on October 21, 2021
  Re-Programing with Associations, Teachers and Principals
    Storage
    Furniture
    Technology
    Wall Surface/Windows
Contractor Pre-Qualifications Underway
Public Qualification Period is Currently Open

## Slide 6
PROGRESS TRACKING
Chart: Newton Middle School 21st Century Classroom Improvements Budget
| REMAINING | PAID OUT | TOTAL
Interim Housing | 0.8 | 0.2 | 0
Budget and Schedule
Project Status
$0.82 M
$3.24 M
Chart: Construction Progress - % of Completion
| % Complete
Work Completed | 0

## Slide 7
PROGRESS TRACKING
Chart: Sparks Middle School 21st Century Classroom Improvements Budget
| PAID OUT | REMAINING | TOTAL
Column2 | 0.2 | 0.8
$0.74 M
$2.92 M
Budget and Schedule
Project Status
Total Budget
$3.66 M
Chart: Construction Progress - % of Completion
| % Complete
Work Completed | 0

## Slide 8
PROGRESS TRACKING
Chart: Grandview College Prep 21st Century Classroom Improvements Budget
| PAID OUT | REMAINING | TOTAL
Interim Housing | 0.15 | 0.85
$0.88 M
$5.12 M
Budget and Schedule
Project Status
Total Budget
$6.00 M
Chart: Construction Progress - % of Completion
| % Complete
Work Completed | 0

## Slide 9
Newton MS 21st Century Projected Schedule 5/22/22 to 11/20/23
Sparks MS 21st Century Projected Schedule 5/22/22 to 3/2/23
Grandview 21st Century Projected Schedule 5/22/22 to 8/5/23

## Slide 10
Questions + answers