## Slide 1: 21st Century Classroom Improvements
January 25, 2022 Board Update

## Slide 2
PROJECT CERTIFIED
21st Century Classroom Improvements

## Slide 3
INTERIM HOUSING |  |  |  |  |  |  | 21st CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | CONSTRUCTION | DSA APPROVAL | OCCUPANCY |  | SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
100%
100%
Cedarlane Academy
SUBSTANTIALLY COMPLETE
Project Status
Interim Housing Complete Close Out Phase
21st Century Classroom Improvements Complete
CLOSEOUT & DSA CERTIFICATION
NOTES

## Slide 4
INTERIM HOUSING |  |  |  |  |  |  | 21st CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION |  | SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
25%
Newton Middle School
SITE WORK & BUILDING PLACEMENT
Project Status
Interim Housing
Construction In Progress
Current Tasks
  Grading
  Paving
  Accessible walks
  Placing Buildings
  Electrical & Communications
NOTES
100%
100%
100%
100%
100%
100%
100%
100%
UNDER CONSTRUCTION

## Slide 5
Accessible Walkway “B” Wing
Under Construction
After
Newton Middle School

## Slide 6
Accessible Walk “B” Wing
New Steps “C” Wing
Newton Middle School

## Slide 7
Building Pads
North Parking Lot
Accessible Walks- Main Entry
Newton Middle School

## Slide 8
PROJECT DASHBOARD: SITE FINANCIALS

## Slide 9
PROJECT DASHBOARD: SITE SCHEDULE

## Slide 10
Grandview Academy, Newton, Sparks MS
Programming & Qualifying
Project Status
  21st Century Classroom Projects APPROVED BY DSA
  Newton Middle School 6-30-21
  Grandview College Prep 6-30-21
  Sparks Middle School 6-30-21
  Scope review meetings with sites to gain stakeholder input per the Board's guidance at the Special Board Meeting
  Re-Programing with Associations, Teachers and Principals
    Storage
    Furniture
    Technology
Preparing New Annual Contractor Pre-Qualifications Package

## Slide 11
Newton 21st Century Projected Schedule
3-23-22 to 6-30-23
Sparks MS 21st Century Projected Schedule
3-23-22 to 2-23-23
Grandview 21st Century Projected Schedule
3-23-22 to 4-22-23

## Slide 12
Questions + answers