## Slide 1: 21st CENTURY CLASSROOM IMPROVEMENTS | PHASES 1 & 2
BOND UPDATES
February 25, 2021

## Slide 2: MESA ROBLES SCHOOL
NOTES:
Interim Classrooms
  COMPLETE
21st Century Classroom Improvements
NTP issued October 19
  Demolition Complete Phase 1 and Phase 1A
  Construction Phase 2 started January 13 is nearly complete
  Phase 3 to begin March 30
PROJECT STATUS
100%
25%
PROJECT STATUS
UNDER CONSTRUCTION
INTERIM HOUSING |  |  |  |  |  |  | 21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | CONSTRUCTION | DSA APPROVAL | OCCUPANCY |  | SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION

## Slide 3
MESA ROBLES SCHOOL
Interim Housing
Middle School Side
PHASING PLAN
Elementary School Side
CONSTRUCTION PHASE 2
Phase 2, 4 CR Middle School Side B-20, B-21, B-23 and B-24 1-13-21 to 3-29-21
Phase 2, 4 CR: G-4, G-5 and G-11, G-12 1-13-21 to 3-29-21

## Slide 4
• NEW LVT FLOORING
• NEW WALL BASE
• NEW TACKABLE WALL BOARD
• NEW COUNTER AND SINK
• NEW PLUMBING VALVES PER FIXTURE
• NEW WHITE BOARDS
• NEW INTERACTIVE MONITOR
• NEW ENHANCED WHOLE CLASS AUDIO TECHNOLOGY
• NEW UPGRADED WIRE CABLING INFRASTRUCTURE
MESA ROBLES SCHOOL
21st CENTURY CLASSROOM IMPROVEMENTS

## Slide 5: MESA ROBLES SCHOOL
ADA ACCESS IMPROVEMENTS
21st CENTURY CLASSROOM IMPROVEMENTS
BEFORE
IN PROGRESS
ACCESS DOOR D-12
NEW ACCESSIBLE DOOR & WALKWAY

## Slide 6
MESA ROBLES SCHOOL
21st CENTURY CLASSROOM IMPROVEMENTS
CLASSROOM DEMOLITION

## Slide 7
MESA ROBLES SCHOOL
21st CENTURY CLASSROOM IMPROVEMENTS
CLASSROOM IMPROVEMENT CONSTRUCTION

## Slide 8: CEDARLANE ACADEMY
PROJECT STATUS
INTERIM HOUSING |  |  |  |  |  |  | 21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | CONSTRUCTION | DSA APPROVAL | OCCUPANCY |  | SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
50%
23%
NOTES:
N.T.P. October 19
Demolition East Courtyard
  Interior site work phase 1 and 1A East Courtyard Complete
  Interior Demolition and Abatement Phase 2 Complete
  Interior Construction Nearing Completion
UNDER CONSTRUCTION

## Slide 9
CEDARLANE ACADEMY
PROJECT STATUS
START PHASING PLAN & INTERIM HOUSING
CONSTRUCTION PHASE 2
Phase 2, 5 CR East Side E-1, E-2, E-3, E-4 and H-3

## Slide 10: CEDARLANE ACADEMY
PROJECT STATUS
INTERIOR IMPROVEMENTS
CLASSROOM INTERIOR IMPROVEMENTS
BEFORE
AFTER

## Slide 11
CEDARLANE ACADEMY
PROJECT STATUS
PHASE 1 CLASSROOM IMPROVEMENTS COMPLETE
NEW FLOORING
NEW WALL FINISH
NEW PLUMBING
NEW WHITE BOARDS
NEW TECHNOLOGY

## Slide 12: LOS ALTOS ELEMENTARY SCHOOL
NOTES:
Interim Housing Project is 100% complete
21st Century Walkways Complete
  Access Ramp Railing Installation
  Phase 2 & 3 Substantial Punch list Items
Finish Plumbing and Electrical; Low Voltage In Progress
Finishes Completed
PROJECT STATUS
INTERIM HOUSING |  |  |  |  |  |  | 21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | CONSTRUCTION | DSA APPROVAL | OCCUPANCY |  | SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
UNDER CONSTRUCTION
95%

## Slide 13
LOS ALTOS ELEMENTARY SCHOOL
PROJECT STATUS
CLASSROOM INTERIORS NEARLY COMPLETE

## Slide 14: LOS ALTOS ELEMENTARY SCHOOL
PROJECT STATUS
DRINKING FOUNTAINS & BOTTLE FILLERS IN BRICK VENEER
SITE IMPROVEMENTS
BEFORE
READY FOR FIXTURE MOUNT
PROGRESS

## Slide 15
LOS ALTOS ELEMENTARY SCHOOL
PROJECT STATUS
ACCESS IMPROVEMENTS COMPLETE

## Slide 16: NELSON ELEMENTARY SCHOOL
PROJECT STATUS
21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
95%
NOTES:
Notice to Proceed on 6-8-20
Construction Phases 2 and 3 Substantially Complete 12/18/20 Punch List Issued By Architect
Site Concrete corrections completed
Lighting and Fire Alarm Began by Unit Cost Service Providers
Technology installation near completion
UNDER CONSTRUCTION

## Slide 17: NELSON ELEMENTARY SCHOOL
FURNISHING ARRIVING
PROJECT STATUS
SUBSTANTIALLY COMPLETE

## Slide 18: NELSON ELEMENTARY SCHOOL
SITE WORK COMPLETE
PROJECT STATUS
SITE WORK SUBSTANTIALLY COMPLETE

## Slide 19: WORKMAN ELEMENTARY SCHOOL
PROJECT STATUS
21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
UNDER CONSTRUCTION
99%
NOTES:
21st Century Classroom Improvements Started Construction 6-15-2020; Construction Phases 2 & 3 Punch List
  SUBSTANTIALLY COMPLETE

## Slide 20
PROJECT STATUS
WORKMAN ELEMENTARY SCHOOL
DELIVERY & SET UP
UPPER GRADE FURNITURE

## Slide 21: WORKMAN ELEMENTARY SCHOOL
PROJECT STATUS
NEW FURNITURE INSTALLED
CLASSROOM INTERIORS NEARLY COMPLETE

## Slide 22: NEWTON MIDDLE SCHOOL
PROJECT STATUS
INTERIM HOUSING |  |  |  |  |  |  | 21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | CONSTRUCTION | DSA APPROVAL | OCCUPANCY |  | SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
90%
95%
NOTES:
Interim Housing Construction Documents are DSA approved
Temp power installation complete
DSA Project Inspector assigned
21st Century Classroom Improvements
  DSA Submittal Date February 25, 2021
BID #3

## Slide 23: GRANDVIEW ACADEMY
PROJECT STATUS
21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
85%
NOTES:
21st Century Classroom Project Construction Documents are 85% complete
DSA Project Inspector assigned
21st Century Classroom Improvements
  DSA Submittal Date February 25, 2021
BID #3

## Slide 24: SPARKS MIDDLE SCHOOL
PROJECT STATUS
21ST CENTURY CLASSROOM |  |  |  |  | 
SCHEMATIC DESIGN | DESIGN DEVELOPMENT | CONSTRUCTION DOCUMENTS | DSA APPROVAL | CONSTRUCTION | COMPLETION
85%
NOTES:
Construction Documents for the 21st Century Classroom Improvements are 85% complete
DSA Project Inspector assigned
21st Century Classroom Improvements
  DSA Submittal Date February 25, 2021
BID #3

## Slide 25: QUESTIONS & ANSWERS