Timeline for District Accreditation and Strategic Planning

Clayton County Public Schools

2017-2018

Items highlighted in peach have been completed

| July 19, 2017 | Improvement Journey Committee Meeting (Initial) |
| --- | --- |
| July 28, 2017 | Committee Meeting Training |
| July 31, 2017 | Board Presentation – Information regarding new Accreditation process and Strategic Improvement Plan |
| August 7-25, 2017 | AdvancED Surveys (Parents, Students, Teachers/Staff) |
| August 15, 2017 | Principals’ Meeting – Information regarding new Accreditation process |
| August 16, 2017 | Assistant Principals’ Meeting – Information regarding new Accreditation process |
| August 17, 2017 | Principals’ designee training on eleot and new website portal |
| August 22, 2017 | CFT – Standards training and rating (District) |
| August 28, 2017 | Board Presentation – Update (AdvancED Surveys and Training) |
| September 1-15, 2017 | AdvancED Inventories (Teachers and students) |
| September 1-30, 2017 | eleot observations (School and district personnel) |
| September 12, 2017 | Principals’ Meeting – Standards review & rating |
| September 13, 2017 | Assistant Principals’ Meeting – Standards review and rating |
| September 19, 2017 | CFT – Analysis of Surveys/Inventories |
| September 21, 2017 | School/District Quality Factors leadership meeting and training (District Leadership) |
| September 25, 2017 | Board Presentation – Update (AdvancED Inventories) |
| September 30, 2017 | Community Staff/Meeting – Input and Engagement with Strategic Plan and AdvancED (participants will development “new” mission/vision, Strategic goals, core beliefs, etc.) – 9:00AM-4:00PM |
| October 2-31, 2017 | School/District Quality Factors individual team meetings |
| October 17, 2017 | CFT – Analysis of eleot observations |
| October 17, 2017 (Week of) | Board input on proposed mission/vision, goals, and beliefs (multiple meeting sessions at BOE) |
| October 23-November 3, 2017 | Strategic Plan survey – Mission/Vision, Beliefs, and Goals |
| October 30, 2017 | Board Presentation – Update (AdvancED eleot and Community Meeting) |
| November 6, 2017 | District SQF Report due to Dr. Monika Wiley from leadership team |
| November 7, 2017 | CFT Meeting to discuss proposed mission/vision, beliefs and goals |
| November 13, 2017 | Cabinet Meeting to discuss proposed mission/vision, beliefs and goals. |
| November 27, 2017 | Board Presentation – Update (District SQF Report) Board Presentation – Recommendation for Mission/Vision, Beliefs and Goals |
| December 4, 2017 | Board Vote – Mission/Vision, Beliefs and Goals |
| December 15, 2017 | Electronic artifacts due to Dr. Monika Wiley |
| December 15, 2017 | Schools’ SQF Due in eProve |
| January 1-31, 2018 | eleot observations (School and district personnel) |
| January – April 2018 | Strategic Plan – District Committees (Performance Objections, Initiatives, and Action Steps) |
| January 2018 | Board Presentation (Work Session) – Update on AdvancED submissions |
| February 1-18, 2018 | Submit AdvancED Documents |
| February 20, 2018 | CFT – Analysis of eleot observations |
| March 18-21, 2018 | District’s Engagement Review |
| April 2018, 2018 | Board Presentation (Work Session) – Update on completed Strategic Plan |