## 2023-08-02 Pending Active
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 9/22/23 Update | 8/2/23 Update | 5/3/23 Update | 1/31/23 Update | 11/8/22 Update | 8/24/22 Update | 5/4/22 Update
Security Upgrades - Phase II | All schools | Security Bond | 110000 | Phase I Complete - Phase II In Progress | 2024-08-01 | Bid in Spring 2024 | Estimate of 500 door locksets needed. Will exceed budget. Looking at way to phase for available funds. Bid next summer. | Architect performing survey of remaining door locks at High School. Will bid lock replacements for summer 23. | Miscellaneous additional cameras and door swipes being installed. New computers for Security desks needed. | Omni Data completed. Received proposal for design services for lock project. | Omni Data completing additional security cameras. Working with architect and lock manufacturer's rep on remaining keying plan. | Initiated a requisition for purchase order to Omni Data for additional camera locations
Bathroom stalls | All ES/MS | 2022 Capital 2023 Capital | 280000 | Complete | 2023-08-01 | Completed at Jane Ryan, Hillcrest, Madison, Middlebrook and Daniels Farm. | Jane Ryan and Hillcrest complete. Madison, MIddlebrook and Daniels Farm underway. | Jane Ryan and Hillcrest awarded. BH, MB, MMS and DF out to bid. Bid Date - 5/4/23. | Capital approved. Re-packaging for bidding this spring. | Tashua stalls complete. Will rebid in Spring 2023 | Tashua Elementary only project under budget. Will request additional capital for next year | Awaiting bid drawings and specifications from architect
Drainage design and construction | BH | 2021 Capital | 515000 | Complete | 2023-06-01 | Complete. Field is back in use. | Complete. | Contractor re-establishing field with topsoil and seeding during April break. | Contractor started over Christmas break. All underground work complete. Will return in spring to re-establiish field. | Contractor holding off until late Spring 2023 | Bid and awarded. Commencing in September | Borings completed on site
Wellness/Fitness Center | THS | 2021 Capital 2022 Capital Grant | 135000 | Conceptual Design Complete | TBD | Building Committee creating 503C for donations | Awaiting next building committee meeting to plan next steps for funding. | Awaiting next building committee meeting to plan next steps for funding. | Awaiting next building committee meeting to plan next steps for funding. | Awaiting capital authorization for full project and approval to apply for grant | Conceptual design accepted by Building Committee. Developinig cost estimate. | Antinozzi Associates retained for conceptual design, ed spec, cost estimate - Meeting with AD and coaches 5/5/22
Gym Floor Refinishing | FT, AG | 2023 Capital | 75000 | Complete | 2023-08-01 | Complete. Field is back in use. | Complete. | FT gym and AG foyer awarded. Work at FT to begin 6/19/23 | Requested proposal from architect for bid docs for spring | Requesting funds in CY2023 for Frenchtown gym and Agriscience Lobby |  | Preliminary drawings received
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 150000 | In Progress | 2023-08-01 | Abatement complete. Re-insulation in progress. | Abatement complete. Re-insulation in progress. | Abatement bid package submitted to Purchasing. Awaiting Wage Rate schedule to set bid date and advertise. | Working to re-package abatement bid with reduced scope | Will bid reduced scope/area in Spring 2023 | Bids received were over-budget. Re-insulation estimate very high. Will repackage for abatement of accessed rooms in basement only. | Awaiting bid package from consultant
Roof Replacement | MB | 2021 Capital Grant | 2100000 | In Progress | 2023-08-01 | Work complete. Close out documentation being prepared. | In progress. | Contractor's tentative schedule is to start 6/27/23 and finish 8/25/23 | Contractor to start staging materials in April | Building Committee selected Silktown Roofing for award | Awaiting grant approval. | Applying for State School Construction Grant this week - New grant amount $2,386,259
Roof Replacement | BH | 2022 Capital Grant | 2600000 | In Progress | 2024-08-01 | In design. Funding authorization needed for grant application. | In design. Funding authorization needed for grant application. | In design. Funding authorization needed for grant application. | Building Committee requesting approval of grant resolutions from Town Council | Building Committee formed. Requested additional capital for CY2024 but will ask to move up to CY2023
Greenhouse Roof Replacement | AG | 2021 Capital | 75000 | In Progress | 2024-08-01 | Bid in Spring for Summer 24. | Bid in Spring for Summer 24. | Architect preparing bid documents. | Requested proposal from architect for bid docs for spring
THS Auditorium Improvements (spotlights and house lights) | THS | 2021 Capital | 297500 | In Progress | 6699857 | Low bidder breaking out follow spots from house lights. Awaiting proposal. | Bids received. Overbudget. Working with Purchasing to award portion and request additional funding for next summer. | Engineer preparing bid documents. | Arranging meeting with designers and auditorium manager | Requested funding in CY2023 plan; $90,000 for follow spots | Will request additional funds for lighting. Not proceeding with platforms. | Supertech researching how to best replace follow spots - House lighting replacement cost $129,850
Softball Field Lighting | THS | 2023 Capital | 250000 | In Progress | 2023-12-01 | Shock Electric awarded. Submittal review in process. Contractor expecting to complete this fall. | Bids received. Overbudget. Working with Finance to transfer funds to award. | Engineer preparing bid documents. | Working with on-call architectural-engineering consultant to develop plans and specifications for bidding.
Tilework and foundation around the rear entrance of the Ag Science building | AG | 2024 Capital | 65596 | Postponed - 2024 | 2024-08-01 | On hold for funding. | Will request in new capital plan | Will request in new capital plan | Will request in new capital plan | Postponed again | Will request in new capital plan
HVAC Improvements | MB | 2023 Capital/Grant | 4300000 | Awaiting Funding and Grant Approval | 2024-12-01 | Grant application to be filed by 12/31/23. | Waiting for grant application process to open | Not awarded due to deficiencies in application documents. Will re-apply. | Grant application submitted. Building Committee formed but hasn't convened | Awaiting resolutions for application to State HVAC Grant Program
Fence Replacement | AG | 2022 Capital | 75000 | In Progress | 2024-08-01 | Completed front pen area. Will look to other areas with available funding. | Completed front pen area. Will look to other areas with available funding. | Recommending award to Total Fence to replace split rail fencing at front corral.
Parking Lot and Drainage work | JR | 2022 Capital | 1450000 | In Progress | 2023-10-01 | Sidewalks, curbs and paving complete. Railings in progress | Paving and re-striping is complete. Seeking proposals for railings. | Repaving underway.
Parking Lot and Drainage work | TA | 2023 Capital | 1210000 | In Progress | 2024-08-01 | Drainage, sidewalks and curbs complete. Portables removed. Pavement reclamation next summer. | Drainage work underway. Portables have been removed. | Town Engineer preparing documents for drainage, curbing and sidewalk replacement
Parking Lot and Drainage work | DF | 2024 Capital | 1436000 | Pending | 2025-08-01 | Pending approval in Capital Plan
Parking Lot and Drainage work | THS | 2024 Capital | 2500000 | Pending | 2025-08-01 | Pending approval in Capital Plan
Artificial Turf and Track Replacement | THS | 2024 Capital | 3000000 | Pending | 2025-08-02 | Pending approval in Capital Plan

## 2023-05-03 Pending Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 5/3/23 Update | 1/31/23 Update | 11/8/22 Update | 8/24/22 Update | 5/4/22 Update
Security Upgrades - Phase II | All schools | Security Bond | 110000 | Phase I Complete - Phase II In Progress | 2023-08-01 | Architect performing survey of remaining door locks at High School. Will bid lock replacements for summer 23. | Miscellaneous additional cameras and door swipes being installed. New computers for Security desks needed. | Omni Data completed. Received proposal for design services for lock project. | Omni Data completing additional security cameras. Working with architect and lock manufacturer's rep on remaining keying plan. | Initiated a requisition for purchase order to Omni Data for additional camera locations
Bathroom stalls | All ES/MS | 2022 Capital 2023 Capital | 280000 | In Progress | 2023-08-01 | Jane Ryan and Hillcrest awarded. BH, MB, MMS and DF out to bid. Bid Date - 5/4/23. | Capital approved. Re-packaging for bidding this spring. | Tashua stalls complete. Will rebid in Spring 2023 | Tashua Elementary only project under budget. Will request additional capital for next year | Awaiting bid drawings and specifications from architect
Drainage design and construction | BH | 2021 Capital | 515000 | In Progress | 2023-06-01 | Contractor re-establishing field with topsoil and seeding during April break. | Contractor started over Christmas break. All underground work complete. Will return in spring to re-establiish field. | Contractor holding off until late Spring 2023 | Bid and awarded. Commencing in September | Borings completed on site
Wellness/Fitness Center | THS | 2021 Capital 2022 Capital Grant | 135000 | Conceptual Design Complete | TBD | Awaiting next building committee meeting to plan next steps for funding. | Awaiting next building committee meeting to plan next steps for funding. | Awaiting capital authorization for full project and approval to apply for grant | Conceptual design accepted by Building Committee. Developinig cost estimate. | Antinozzi Associates retained for conceptual design, ed spec, cost estimate - Meeting with AD and coaches 5/5/22
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | Paving Complete Additional landscaping pending | 2023-05-01 | Complete. | Awaiting spring/warmer weather | Considering courtyard area pavers and plantings with remaining funds | Pavement complete. Town working on curbing and striping. | Engineer doing layout for driveway cut
Gym Floor Refinishing | FT, AG | 2023 Capital | 75000 | In Progress | 2023-08-01 | FT gym and AG foyer awarded. Work at FT to begin 6/19/23 | Requested proposal from architect for bid docs for spring | Requesting funds in CY2023 for Frenchtown gym and Agriscience Lobby |  | Preliminary drawings received
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 150000 | In Progress | 2023-08-01 | Abatement bid package submitted to Purchasing. Awaiting Wage Rate schedule to set bid date and advertise. | Working to re-package abatement bid with reduced scope | Will bid reduced scope/area in Spring 2023 | Bids received were over-budget. Re-insulation estimate very high. Will repackage for abatement of accessed rooms in basement only. | Awaiting bid package from consultant
Roof Replacement | MB | 2021 Capital Grant | 2100000 | In Progress | 2023-08-01 | Contractor's tentative schedule is to start 6/27/23 and finish 8/25/23 | Contractor to start staging materials in April | Building Committee selected Silktown Roofing for award | Awaiting grant approval. | Applying for State School Construction Grant this week - New grant amount $2,386,259
Roof Replacement | BH | 2022 Capital Grant | 2600000 | In Progress | 2024-08-01 | In design. Funding authorization needed for grant application. | Building Committee requesting approval of grant resolutions from Town Council | Building Committee formed. Requested additional capital for CY2024 but will ask to move up to CY2023
Greenhouse Roof Replacement | AG | 2021 Capital | 75000 | In Progress | 2023-08-01 | Architect preparing bid documents. | Requested proposal from architect for bid docs for spring
THS Auditorium Improvements (spotlights and house lights) | THS | 2021 Capital | 297500 | In Progress | 2023-08-01 | Engineer preparing bid documents. | Arranging meeting with designers and auditorium manager | Requested funding in CY2023 plan; $90,000 for follow spots | Will request additional funds for lighting. Not proceeding with platforms. | Supertech researching how to best replace follow spots - House lighting replacement cost $129,850
Softball Field Lighting | THS | 2023 Capital | 250000 | In Progress | 2023-08-01 | Engineer preparing bid documents. | Working with on-call architectural-engineering consultant to develop plans and specifications for bidding.
Tilework and foundation around the rear entrance of the Ag Science building | AG | 2024 Capital | 65596 | Postponed - 2024 |  | Will request in new capital plan | Will request in new capital plan | Postponed again | Will request in new capital plan
HVAC Improvements | MB | 2023 Capital/Grant | 4300000 | Awaiting Funding and Grant Approval | 2024-12-01 | Not awarded due to deficiencies in application documents. Will re-apply. | Grant application submitted. Building Committee formed but hasn't convened | Awaiting resolutions for application to State HVAC Grant Program
Fence Replacement | AG | 2022 Capital | 75000 | In Progress | 2024-08-01 | Recommending award to Total Fence to replace split rail fencing at front corral.
Parking Lot and Drainage work | TA | 2023 Capital | 410000 | In Progress | 2024-08-01 | Town Engineer preparing documents for drainage, curbing and sidewalk replacement

## 2023-01-31 Pending Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 1/31/23 Update | 11/8/22 Update | 8/24/22 Update | 5/4/22 Update | 2/9/22 Update | 4/5/22 Update | 11/16/21 Update | 10/13/21 Update | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes | 7/13/21 Update
Security Upgrades - Phase II | All schools | Security Bond | 254823 | Phase I Complete - Phase II In Progress | 2022-08-01 | Miscellaneous additional cameras and door swipes being installed. New computers for Security desks needed. | Omni Data completed. Received proposal for design services for lock project. | Omni Data completing additional security cameras. Working with architect and lock manufacturer's rep on remaining keying plan. | Initiated a requisition for purchase order to Omni Data for additional camera locations | Developing priorities for addtional security measures including cameras and door locks | Received proposal for additional cameras - awaiting authorization for funding |  | Phase I completed. Preparing bid specifications for Phase II. |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Bathroom stalls | All ES/MS | 2022 Capital 2023 Capital | 280000 | In Progress | 2023-08-01 | Capital approved. Re-packaging for bidding this spring. | Tashua stalls complete. Will rebid in Spring 2023 | Tashua Elementary only project under budget. Will request additional capital for next year | Awaiting bid drawings and specifications from architect | Requested in CY2022 Bond Issue | Architect retained to develop drawings and specifications for bidding |  | To be added to FY2022 Capital Plan |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital? |  |  | No progress
Drainage design and construction | BH | 2021 Capital | 515000 | In Progress | 2023-06-01 | Contractor started over Christmas break. All underground work complete. Will return in spring to re-establiish field. | Contractor holding off until late Spring 2023 | Bid and awarded. Commencing in September | Borings completed on site |  |  |  | Preliminary Design received. Comments provided to Engineering | Town led project
Boiler replacements | AG | 2021 Capital | 425000 | Complete | 2022-08-01 | Complete. | Equipment installed and running; punch list created by engineer; contractor returning next week to complete | Awaiting breeching installation to complete. Added replacement of domestic hot water heater due to failure | Boilers being installled - awaiting two circulation pumps | Awarded only greenhouse boilers due to bids being over budget; additional funds requested in CY2022 | Additional funding approved in CY 2022 request. Awarded remainder of contract work to Southport | Bids due 11/23 | Bid Package forwarded to Purchasing Agent. Will advertise for bid next week. | PO to S&P for design and bid docs | [6 empty] | Shortage of equipment & manpower is causing a delay in starting this project.
Wellness/Fitness Center | THS | 2021 Capital 2022 Capital Grant | 135000 | Conceptual Design Complete | TBD | Awaiting next building committee meeting to plan next steps for funding. | Awaiting capital authorization for full project and approval to apply for grant | Conceptual design accepted by Building Committee. Developinig cost estimate. | Antinozzi Associates retained for conceptual design, ed spec, cost estimate - Meeting with AD and coaches 5/5/22 | Building Committee appointed; working with Chair for initial meeeting. | Building committee met twice - developing scope for architect-engineer - conceptual cost estimate |  | Awaiting Building Committee. Preparing RFQ for Architect | Marty and Mike King are writing specifications and working to select an architect; | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | Paving Complete Additional landscaping pending | 2023-05-01 | Awaiting spring/warmer weather | Considering courtyard area pavers and plantings with remaining funds | Pavement complete. Town working on curbing and striping. | Engineer doing layout for driveway cut |  | Phase II underway - connecting rain leaders to storm drainage system then paving | Sewer complete. Paving in spring 22 | Sewer work planned for 10/8-10/11. Completion delayed due to obstructions in trench and crew availability. | Town led project; drains and waste lines tested and potential septic lines blocked; discovered paying for sewers at the same time.
Gym Floor Refinishing | FT, AG | 2023 Capital | 75000 | Madison, Middlebrook complete. FT/AG in progress | 2023-08-01 | Requested proposal from architect for bid docs for spring | Requesting funds in CY2023 for Frenchtown gym and Agriscience Lobby |  | Preliminary drawings received | Requested $165,000 in CY2022 bond issue | Preparing bid package for Madison and Middlebrook |  | To be added to FY2022 Capital Plan | Going out to bid for Madison and Frenchtown. Getting a preliminary estimate from a contractor. | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting | [5 empty] | Quotes for refinishing came in over $60k, making it prohibitively expensive for this year.
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 150000 | In Progress | 2023-08-01 | Working to re-package abatement bid with reduced scope | Will bid reduced scope/area in Spring 2023 | Bids received were over-budget. Re-insulation estimate very high. Will repackage for abatement of accessed rooms in basement only. | Awaiting bid package from consultant | Preparing scope of work for bidding | Bid package ready mid-April 2022 |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***
Roof Replacement | MB | 2021 Capital Grant | 2100000 | In Progress | 2023-08-01 | Contractor to start staging materials in April | Building Committee selected Silktown Roofing for award | Awaiting grant approval. | Applying for State School Construction Grant this week - New grant amount $2,386,259 | State OSCG&R Plan Review 2/2/2022 Revisions underway; awaiting approval to go to bid | Bids received were overbudget - State grant withdrawn - New grant application with revised estimate in early May 2022 |  |  |  | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7. | [5 empty] | Building committee has delayed project to 2022 and is pursuing state reimbursement.
Roof Replacement | BH | 2022 Capital Grant | 2600000 | In Progress | 2023-08-01 | Building Committee requesting approval of grant resolutions from Town Council | Building Committee formed. Requested additional capital for CY2024 but will ask to move up to CY2023 | [7 empty] | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7. | [5 empty] | Building committee has delayed project to 2022 and is pursuing state reimbursement.
Greenhouse Roof Replacement | AG | 2021 Capital | 75000 | In Progress | 2023-08-01 | Requested proposal from architect for bid docs for spring
THS Auditorium Improvements (spotlights and house lights) | THS | 2021 Capital | 297500 | In Progress | 2023-08-01 | Arranging meeting with designers and auditorium manager | Requested funding in CY2023 plan; $90,000 for follow spots | Will request additional funds for lighting. Not proceeding with platforms. | Supertech researching how to best replace follow spots - House lighting replacement cost $129,850 | Seeking proposals for curtain and house lighting | Awaiting proposal from Supertech |  |  | On hold due to duct replacement in that area. | John working with Kevin Bova to develop bid package | [5 empty] | ***Pushed to 2022***
Softball Field Lighting | THS | 2023 Capital | 250000 | In Progress | 2023-08-01 | Working with on-call architectural-engineering consultant to develop plans and specifications for bidding.
Tilework and foundation around the rear entrance of the Ag Science building | AG | 2024 Capital | 65596 | Postponed - 2024 |  | Will request in new capital plan | Postponed again | Will request in new capital plan | [5 empty] | Have estimate. will need to go out to bid. Should go in 2022 Capital plan. | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor |  |  |  |  | 65596
HVAC Improvements | MB | 2023 Capital/Grant | 4300000 | Awaiting Funding and Grant Approval | 2024-12-01 | Grant application submitted. Building Committee formed but hasn't convened | Awaiting resolutions for application to State HVAC Grant Program

## 2022-11-03 Pending Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 11/8/22 Update | 8/24/22 Update | 2/9/22 Update | 4/5/22 Update | 11/16/21 Update | 10/13/21 Update | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes | 7/13/21 Update
Security Upgrades - Phase II | All schools | Security Bond | 254823 | Phase I Complete - Phase II Complete | 2022-08-01 | Omni Data completed. Received proposal for design services for lock project. | Omni Data completing additional security cameras. Working with architect and lock manufacturer's rep on remaining keying plan. | Developing priorities for addtional security measures including cameras and door locks | Received proposal for additional cameras - awaiting authorization for funding |  | Phase I completed. Preparing bid specifications for Phase II. |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Bathroom stalls | All ES | 2022 Capital 2023 Capital | $170,000 CY22 $110,000 CY23 | Awaiting Additional Capital funding | 2023-08-01 | Tashua stalls complete. Will rebid in Spring 2023 | Tashua Elementary only project under budget. Will request additional capital for next year | Requested in CY2022 Bond Issue | Architect retained to develop drawings and specifications for bidding |  | To be added to FY2022 Capital Plan |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital? |  |  | No progress
Elevator Single bottom Cylinder Upgrade(code) | JR | 2021 Capital 2023 Capital | 90000 | Complete | 2022-03-01 | Complete | Work complete. Close out of contract still pending receipt of warranties. | Delayed until late February due to supply issues | Work Complete. Project closeout - no issues | Parts on order | Awarded to Eagle Elevator. Eagle to perform field measuring/verification week of 10/18/21 | Two quotes received; assembling scope of work to go out to bid | [6 empty] | Architect completed scope of work
Drainage design and construction | BH | 2021 Capital | 515000 | In progress | 2023-08-01 | Contractor holding off until late Spring 2023 | Bid and awarded. Commencing in September |  |  |  | Preliminary Design received. Comments provided to Engineering | Town led project
Cooling Tower Replacement | FT | 2021 Capital | 225775 | In progress | 2022-04-01 | Complete | Work complete. Close out of contract still pending receipt of warranties. | Submittals received and approved by Engineer | Towers being replaced now - should be completed by 4/15/22 | Awarded to Action Air Systems, Inc. | Awaiting transfer of funds to recommend award to Action Air $206,900 bid. | [7 empty] | Waiting on scope of work from Silver & Petrucelli. hopefully schedule after cooling season
Boiler replacements | AG | 2021 Capital | 425000 | In progress | 2022-08-01 | Equipment installed and running; punch list created by engineer; contractor returning next week to complete | Awaiting breeching installation to complete. Added replacement of domestic hot water heater due to failure | Awarded only greenhouse boilers due to bids being over budget; additional funds requested in CY2022 | Additional funding approved in CY 2022 request. Awarded remainder of contract work to Southport | Bids due 11/23 | Bid Package forwarded to Purchasing Agent. Will advertise for bid next week. | PO to S&P for design and bid docs | [6 empty] | Shortage of equipment & manpower is causing a delay in starting this project.
Wellness/Fitness Center | THS | 2021 Capital | 35000 | Conceptual Design Complete | TBD | Awaiting capital authorization for full project and approval to apply for grant | Conceptual design accepted by Building Committee. Developinig cost estimate. | Building Committee appointed; working with Chair for initial meeeting. | Building committee met twice - developing scope for architect-engineer - conceptual cost estimate |  | Awaiting Building Committee. Preparing RFQ for Architect | Marty and Mike King are writing specifications and working to select an architect; | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | Complete | 2023-05-01 | Considering courtyard area pavers and plantings with remaining funds | Pavement complete. Town working on curbing and striping. |  | Phase II underway - connecting rain leaders to storm drainage system then paving | Sewer complete. Paving in spring 22 | Sewer work planned for 10/8-10/11. Completion delayed due to obstructions in trench and crew availability. | Town led project; drains and waste lines tested and potential septic lines blocked; discovered paying for sewers at the same time.
Parking Lot and Drainage work | JR | 2022/2023 Capital | 2067000 | Phase I Complete - Phase II Scheduled | 2023-08-01 | Drainage and sidewalks complete. Paving to start in June
Parking Lot and Drainage work | TA | 2023 Capital | 410000 | In Progress | 2024-08-01 | Drainage and sidewalks scheduled. Demolition/removal of portables first year
Gym Floor Refinishing | MAD, MB | Capital | 125000 | Complete | 2022-08-01 | Requesting funds in CY2023 for Frenchtown gym and Agriscience Lobby |  | Requested $165,000 in CY2022 bond issue | Preparing bid package for Madison and Middlebrook |  | To be added to FY2022 Capital Plan | Going out to bid for Madison and Frenchtown. Getting a preliminary estimate from a contractor. | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting | [5 empty] | Quotes for refinishing came in over $60k, making it prohibitively expensive for this year.
Asbestos (Flooring and Insulation) | HC | 2021 Capital | 40000 | Postponed - 2022 |  |  |  | Preparing scope of work for bidding |  |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***; potential $20k savings vs. budget; much smaller job than anticipated.
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 150000 | In Progress | 2023-08-01 | Will bid reduced scope/area in Spring 2023 | Bids received were over-budget. Re-insulation estimate very high. Will repackage for abatement of accessed rooms in basement only. | Preparing scope of work for bidding | Bid package ready mid-April 2022 |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***
Roof Replacement | MB | 2021 Capital | 2100000 | In Progress | 2023-08-01 | Building Committee selected Silktown Roofing for award | Awaiting grant approval. | State OSCG&R Plan Review 2/2/2022 Revisions underway; awaiting approval to go to bid | Bids received were overbudget - State grant withdrawn - New grant application with revised estimate in early May 2022 |  |  |  | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7. | [5 empty] | Building committee has delayed project to 2022 and is pursuing state reimbursement.
Roof Replacement | BH | 2022 Capital | 2600000 | Awaiting Additional Capital funding | 2023-08-01 | Building Committee formed. Requested additional capital for CY2024 but will ask to move up to CY2023 | [6 empty] | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7. | [5 empty] | Building committee has delayed project to 2022 and is pursuing state reimbursement.
THS Auditorium Improvements (spotlight platforms) | THS | 2021 Capital | 57500 | Awaiting Funding | 2023-08-01 | Requested funding in CY2023 plan; $90,000 for follow spots | Will request additional funds for lighting. Not proceeding with platforms. | Seeking proposals for curtain and house lighting | Awaiting proposal from Supertech |  |  | On hold due to duct replacement in that area. | John working with Kevin Bova to develop bid package | [5 empty] | ***Pushed to 2022***
Tilework and foundation around the rear entrance of the Ag Science building | AG | 2023Capital | 65596 | Postponed - 2024 |  | Postponed again | Will request in new capital plan |  |  |  |  | Have estimate. will need to go out to bid. Should go in 2022 Capital plan. | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor |  |  |  |  | 65596
HVAC Improvements | MB | 2023 Capital | 3400000 | Awaiting Funding and Grant Approval | 2024-12-01 | Ap

## 2022-08-24 Pending Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 8/24/22 Update | 5/4/22 Update | 2/9/22 Update | 4/5/22 Update | 11/16/21 Update | 10/13/21 Update | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes | 7/13/21 Update
Security Upgrades - Phase II | All schools | Security Bond | 254823 | Phase I Complete - Phase II In Progress | 2022-08-01 | Omni Data completing additional security cameras. Working with architect and lock manufacturer's rep on remaining keying plan. | Initiated a requisition for purchase order to Omni Data for additional camera locations | Developing priorities for addtional security measures including cameras and door locks | Received proposal for additional cameras - awaiting authorization for funding |  | Phase I completed. Preparing bid specifications for Phase II. |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Bathroom stalls | All ES | 2022 Capital | 170000 | In Progress | 2022-08-01 | Tashua Elementary only project under budget. Will request additional capital for next year | Awaiting bid drawings and specifications from architect | Requested in CY2022 Bond Issue | Architect retained to develop drawings and specifications for bidding |  | To be added to FY2022 Capital Plan |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital? |  |  | No progress
Elevator Single bottom Cylinder Upgrade(code) | JR | 2021 Capital | 90000 | Complete | 2022-03-01 | Work complete. Close out of contract still pending receipt of warranties. |  | Delayed until late February due to supply issues | Work Complete. Project closeout - no issues | Parts on order | Awarded to Eagle Elevator. Eagle to perform field measuring/verification week of 10/18/21 | Two quotes received; assembling scope of work to go out to bid | [6 empty] | Architect completed scope of work
Drainage design and construction | BH | 2021 Capital | 515000 | In progress |  | Bid and awarded. Commencing in September | Borings completed on site |  |  |  | Preliminary Design received. Comments provided to Engineering | Town led project
Cooling Tower Replacement | FT | 2021 Capital | 225775 | In progress | 2022-04-01 | Work complete. Close out of contract still pending receipt of warranties. | Contractor near complete - filling system, testing and balancing | Submittals received and approved by Engineer | Towers being replaced now - should be completed by 4/15/22 | Awarded to Action Air Systems, Inc. | Awaiting transfer of funds to recommend award to Action Air $206,900 bid. | [7 empty] | Waiting on scope of work from Silver & Petrucelli. hopefully schedule after cooling season
Boiler replacements | AG | 2021 Capital | 425000 | In progress | 2022-08-01 | Awaiting breeching installation to complete. Added replacement of domestic hot water heater due to failure | Boilers being installled - awaiting two circulation pumps | Awarded only greenhouse boilers due to bids being over budget; additional funds requested in CY2022 | Additional funding approved in CY 2022 request. Awarded remainder of contract work to Southport | Bids due 11/23 | Bid Package forwarded to Purchasing Agent. Will advertise for bid next week. | PO to S&P for design and bid docs | [6 empty] | Shortage of equipment & manpower is causing a delay in starting this project.
Wellness/Fitness Center | THS | 2021 Capital | 35000 | In progress |  | Conceptual design accepted by Building Committee. Developinig cost estimate. | Antinozzi Associates retained for conceptual design, ed spec, cost estimate - Meeting with AD and coaches 5/5/22 | Building Committee appointed; working with Chair for initial meeeting. | Building committee met twice - developing scope for architect-engineer - conceptual cost estimate |  | Awaiting Building Committee. Preparing RFQ for Architect | Marty and Mike King are writing specifications and working to select an architect; | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | In Progress |  | Pavement complete. Town working on curbing and striping. | Engineer doing layout for driveway cut |  | Phase II underway - connecting rain leaders to storm drainage system then paving | Sewer complete. Paving in spring 22 | Sewer work planned for 10/8-10/11. Completion delayed due to obstructions in trench and crew availability. | Town led project; drains and waste lines tested and potential septic lines blocked; discovered paying for sewers at the same time.
Domestic Hot Water at THS | THS | Operating | 87360 | Complete | 2022-04-01 | Completed. | Completed |  | New boilers received by contractor - installation scheduled for week of 4/18 | Awarded to A&B Mechancial - Heater on order | Awaiting BOF approval of Non-Lapsing Fund |  | THS has two DHW tanks; one is down. This project will need to be prioritized. | [5 empty] | No progress
Summer Project List |  | Operating |  | Complete | [6 empty] | Complete. Jane Ryan Courtyard cleaned and brush cleared. Middlebrook gas line sanded and painted. | Tashual kitchen; THS waste lines; playground mulch; stored furniture moved back to buildings. Planning on 7 summer interns. AC compressors at MB; Scrape and repaint gas lines at Middlebrook | John preparing a list of incremental summer projects whether for custodial staff or interns. Committee to advocate for summer help funding. | [5 empty] | Jane Ryan Courtyard, stored furniture,Middlebrook gas line all in progress.Tashua water lines complete.
Gym Floor Refinishing | MAD, MB | Capital | 125000 | In Progress | 2022-08-01 |  | Preliminary drawings received | Requested $165,000 in CY2022 bond issue | Preparing bid package for Madison and Middlebrook |  | To be added to FY2022 Capital Plan | Going out to bid for Madison and Frenchtown. Getting a preliminary estimate from a contractor. | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting | [5 empty] | Quotes for refinishing came in over $60k, making it prohibitively expensive for this year.
Asbestos (Flooring and Insulation) | HC | 2021 Capital | 40000 | Postponed - 2022 |  |  |  | Preparing scope of work for bidding |  |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***; potential $20k savings vs. budget; much smaller job than anticipated.
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 150000 | In Progress | 2022-08-01 | Bids received were over-budget. Re-insulation estimate very high. Will repackage for abatement of accessed rooms in basement only. | Awaiting bid package from consultant | Preparing scope of work for bidding | Bid package ready mid-April 2022 |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***
Roof Replacement | MB | 2021 Capital | 1725000 | In Progress | 2023-08-01 | Awaiting grant approval. | Applying for State School Construction Grant this week - New grant amount $2,386,259 | State OSCG&R Plan Review 2/2/2022 Revisions underway; awaiting approval to go to bid | Bids received were overbudget - State grant withdrawn - New grant application with revised estimate in early May 2022 |  |  |  | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7. | [5 empty] | Building committee has delayed project to 2022 and is pursuing state reimbursement.
THS Auditorium Improvements (spotlight platforms) | THS | 2021 Capital | 57500 | In Progress | 2022-08-01 | Will request additional funds for lighting. Not proceeding with platforms. | Supertech researching how to best replace follow spots - House lighting replacement cost $129,850 | Seeking proposals for curtain and house lighting | Awaiting proposal from Supertech |  |  | On hold due to duct replacement in that area. | John working with Kevin Bova to develop bid package | [5 empty] | ***Pushed to 2022***
Tilework and foundation around the rear entrance of the Ag Science building | AG | 2023Capital | 65596 | Postponed - 2023 |  | Will request in new capital plan | [5 empty] | Have estimate. will need to go out to bid. Should go in 2022 Capital plan. | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor |  |  |  |  | 65596
THS Baseball/Softball Press Boxes | THS | 2022 Capital | 25000 | In Progress | 2022-06-01 | Complete. | Stairs at Softball press box complete - Baseball press box residing awaiting materials | [11 empty] | ***Pushed to 2022***

## 2022-04-05 Pending Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 4/5/22 Update | 2/9/22 Update | 11/16/21 Update | 10/13/21 Update | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes | 7/13/21 Update
Auditorium Lighting / AV | THS | Operating | 8000 | No Funding |  |  |  |  | In progress. Electrician scheduling to complete as soon as possible | Received lights, wrong side panels were sent. | Aisle lighting being address in operational budget. Hussey seating. Materials coming in April | Are there some items that should be completed as part of the 21-22 budget? | Need engineer to review the spotlight platforms; 50k to replace aisle lighting; quoted | Reached out to contractor to construct spot light positions off the floor. | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20 | Ceiling lighting repaired, seat side panels and aisle lighting in progress
Security Upgrades - Phase II | All schools | Security Bond | 254823 | Phase I Complete |  | Received proposal for additional cameras - awaiting authorization for funding | Developing priorities for addtional security measures including cameras and door locks |  | Phase I completed. Preparing bid specifications for Phase II. |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Madison Vestibule | MAD | Safety & Security Grant | 68000 | Complete |  |  |  |  | Complete | Bizmark complete. Meeting JKS 5/19 10:00 for panic hardware/swipes ect. | Bismark is working on the project. Estimated completion is the beginning of May. | Awarded to Bismark; securing permits; ordering materials; scheduled for some. Updated cost estimate to come. | Bid is out Saturday. Meetings start Monday. Closes 12/3 | Potential reopening of project to be covered by recently discovered security bonds. Schedule for holiday break? | No funding | Looking to get a portion into 2019-20 | Cable and harware ordered 6/4, all backordered as of 7/2
Bathroom stalls | All ES | 2022 Capital | 170000 | In Progress | 2022-08-01 | Architect retained to develop drawings and specifications for bidding | Requested in CY2022 Bond Issue |  | To be added to FY2022 Capital Plan |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital? |  |  | No progress
Remove ext. concrete shade panels | HC | 2021 Capital | 92000 | Complete |  |  |  | Complete | Contract Closeout. Final Waiver of Liens and Claims needed from Contractor. | Scope of work is complete, going out to bid | [6 empty] | Starting Mid/End July; potential $22k savings vs. budget
Elevator Single bottom Cylinder Upgrade(code) | JR | 2021 Capital | 90000 | In progress | 2022-03-01 | Work Complete. Project closeout - no issues | Delayed until late February due to supply issues | Parts on order | Awarded to Eagle Elevator. Eagle to perform field measuring/verification week of 10/18/21 | Two quotes received; assembling scope of work to go out to bid | [6 empty] | Architect completed scope of work
Drainage design and construction | BH | 2021 Capital | 515000 | In progress |  |  |  |  | Preliminary Design received. Comments provided to Engineering | Town led project
Cooling Tower Replacement | FT | 2021 Capital | 150000 | In progress | 2022-04-01 | Towers being replaced now - should be completed by 4/15/22 | Submittals received and approved by Engineer | Awarded to Action Air Systems, Inc. | Awaiting transfer of funds to recommend award to Action Air $206,900 bid. | [7 empty] | Waiting on scope of work from Silver & Petrucelli. hopefully schedule after cooling season
Boiler replacements | AG | 2021 Capital | 425000 | In progress | 2022-08-01 | Additional funding approved in CY 2022 request. Awarded remainder of contract work to Southport | Awarded only greenhouse boilers due to bids being over budget; additional funds requested in CY2022 | Bids due 11/23 | Bid Package forwarded to Purchasing Agent. Will advertise for bid next week. | PO to S&P for design and bid docs | [6 empty] | Shortage of equipment & manpower is causing a delay in starting this project.
Wellness/Fitness Center | THS | 2021 Capital | 35000 | In progress |  | Building committee met twice - developing scope for architect-engineer - conceptual cost estimate | Building Committee appointed; working with Chair for initial meeeting. |  | Awaiting Building Committee. Preparing RFQ for Architect | Marty and Mike King are writing specifications and working to select an architect; | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
Cooling tower sump replacement | THS | 2021 Capital | 120000 | Complete |  |  |  |  | A&B Mechanical to make repairs. Proposal for $12,680 to patch steel and line sump with epoxy | [7 empty] | Doing minor repairs in house
Vehicle Replacements/Grounds | DW | 2021 Capital | 120000 | Complete |  |  |  | Complete | Backhoe received 10/6/2021 | Tractor on order | [6 empty] | ETA September 2021
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | In Progress |  | Phase II underway - connecting rain leaders to storm drainage system then paving |  | Sewer complete. Paving in spring 22 | Sewer work planned for 10/8-10/11. Completion delayed due to obstructions in trench and crew availability. | Town led project; drains and waste lines tested and potential septic lines blocked; discovered paying for sewers at the same time.
Domestic Hot Water at THS | THS | Operating | 87360 | In Progress | 2022-04-01 | New boilers received by contractor - installation scheduled for week of 4/18 |  | Awarded to A&B Mechancial - Heater on order | Awaiting BOF approval of Non-Lapsing Fund |  | THS has two DHW tanks; one is down. This project will need to be prioritized. | [5 empty] | No progress
Summer Project List |  | Operating |  | Complete |  |  |  |  | Complete. Jane Ryan Courtyard cleaned and brush cleared. Middlebrook gas line sanded and painted. | Tashual kitchen; THS waste lines; playground mulch; stored furniture moved back to buildings. Planning on 7 summer interns. AC compressors at MB; Scrape and repaint gas lines at Middlebrook | John preparing a list of incremental summer projects whether for custodial staff or interns. Committee to advocate for summer help funding. | [5 empty] | Jane Ryan Courtyard, stored furniture,Middlebrook gas line all in progress.Tashua water lines complete.
Gym Floor Refinishing | MAD, MB | Capital |  | In Progress | 2022-08-01 | Preparing bid package for Madison and Middlebrook | Requested $165,000 in CY2022 bond issue |  | To be added to FY2022 Capital Plan | Going out to bid for Madison and Frenchtown. Getting a preliminary estimate from a contractor. | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting | [5 empty] | Quotes for refinishing came in over $60k, making it prohibitively expensive for this year.
Replacing Concrete Stairs at the Bus Depot | Bus Depot | Operating | 68400 | Complete |  |  |  | Shop drawings rejected first time; in fabrication | Concrete poured on 10/11/21. Railings to be completed in two weeks. | Securing bids | [6 empty] | Titan Enterprise
Replacement of Ramps THS Portables | THS |  | 42557 | Complete |  |  |  |  | Complete | [7 empty] | Replacing wood with alluminum ramps
Sewer Connection Long Hill | LH |  | $55,00.00 | Complete |  |  |  | Sewer Complete | Burns Construction installing new sewer line and manholes from lateral at back of building. Completion delayed due to obstructions in trench and crew availability. | [7 empty] | Prerequisite project for the Long Hill paving; capital funding being identified among other projects (Asbestos and HS shade panels)
Duct Replacement RAHU-1 THS | THS |  | 210000 | Complete |  |  |  | Complete | Work complete. Contract closeout in progress. | [7 empty] | RZ Design
Tile & Carpet Replacement Frenchtown | FT |  | 45053 | Complete |  |  |  | Complete | Complete | [7 empty] | Tile is lifting up, requiring to be taped down.
Asbestos (Flooring and Insulation) | HC | 2021 Capital | 40000 | Postponed - 2022 |  |  | Preparing scope of work for bidding |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***; potential $20k savings vs. budget; much smaller job than anticipated.
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 75000 | In Progress | 2022-08-01 | Bid package ready mid-April 2022 | Preparing scope of work for bidding |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***
Roof Replacement | MB | 2021 Capital | 1725000 | In Progress | 2023-08-01 | Bids received were overbudget - State grant withdrawn - New grant application with revised estimate in early May 2022 | State OSCG&R Plan Review 2/2/2022 Revisions underway; awaiting approval to go to bid |  |  |  | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7. | [5 empty] | Building committee has delayed project to 2022 and is pursuing state reimbursement.
THS Auditorium Improvements (spotlight platforms) | THS | 2021 Capital | 57500 | In Progress | 2022-08-01 | Awaiting proposal from Supertech | Seeking proposals for curtain and house lighting |  |  | On hold due to duct replacement in that area. | John working with Kevin Bova to develop bid package | [5 empty] | ***Pushed to 2022***
Tilework and foundation around the rear entrance of the Ag Science building | AG | 2023Capital | 65596 | Postponed - 2023 | [5 empty] | Have estimate. will need to go out to bid. Should go in 2022 Capital plan. | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor |  |  |  |  | 65596

## 2022-02-09 Pending-Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 2/9/22 Update | 11/16/21 Update | 10/13/21 Update | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes | 7/13/21 Update
Auditorium Lighting / AV | THS | Operating | 8000 | No Funding |  |  |  | In progress. Electrician scheduling to complete as soon as possible | Received lights, wrong side panels were sent. | Aisle lighting being address in operational budget. Hussey seating. Materials coming in April | Are there some items that should be completed as part of the 21-22 budget? | Need engineer to review the spotlight platforms; 50k to replace aisle lighting; quoted | Reached out to contractor to construct spot light positions off the floor. | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20 | Ceiling lighting repaired, seat side panels and aisle lighting in progress
Security Upgrades - Phase II | All schools | Security Bond | 254823 | Phase I Complete |  | Developing priorities for addtional security measures including cameras and door locks |  | Phase I completed. Preparing bid specifications for Phase II. |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Madison Vestibule | MAD | Safety & Security Grant | 68000 | Complete |  |  |  | Complete | Bizmark complete. Meeting JKS 5/19 10:00 for panic hardware/swipes ect. | Bismark is working on the project. Estimated completion is the beginning of May. | Awarded to Bismark; securing permits; ordering materials; scheduled for some. Updated cost estimate to come. | Bid is out Saturday. Meetings start Monday. Closes 12/3 | Potential reopening of project to be covered by recently discovered security bonds. Schedule for holiday break? | No funding | Looking to get a portion into 2019-20 | Cable and harware ordered 6/4, all backordered as of 7/2
Bathroom stalls | All ES | 2022 Capital | 170000 | Awaiting Funding |  | Requested in CY2022 Bond Issue |  | To be added to FY2022 Capital Plan |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital? |  |  | No progress
Remove ext. concrete shade panels | HC | 2021 Capital | 92000 | Complete |  |  | Complete | Contract Closeout. Final Waiver of Liens and Claims needed from Contractor. | Scope of work is complete, going out to bid | [6 empty] | Starting Mid/End July; potential $22k savings vs. budget
Elevator Single bottom Cylinder Upgrade(code) | JR | 2021 Capital | 90000 | In progress | 2022-03-01 | Delayed until late February due to supply issues | Parts on order | Awarded to Eagle Elevator. Eagle to perform field measuring/verification week of 10/18/21 | Two quotes received; assembling scope of work to go out to bid | [6 empty] | Architect completed scope of work
Drainage design and construction | BH | 2021 Capital | 515000 | In progress |  |  |  | Preliminary Design received. Comments provided to Engineering | Town led project
Cooling Tower Replacement | FT | 2021 Capital | 150000 | In progress | 2021-05-01 | Submittals received and approved by Engineer | Awarded to Action Air Systems, Inc. | Awaiting transfer of funds to recommend award to Action Air $206,900 bid. | [7 empty] | Waiting on scope of work from Silver & Petrucelli. hopefully schedule after cooling season
Boiler replacements | AG | 2021 Capital | 275000 | In progress | 2022-06-01 | Awarded only greenhouse boilers due to bids being over budget; additional funds requested in CY2022 | Bids due 11/23 | Bid Package forwarded to Purchasing Agent. Will advertise for bid next week. | PO to S&P for design and bid docs | [6 empty] | Shortage of equipment & manpower is causing a delay in starting this project.
Wellness/Fitness Center | THS | 2021 Capital | 35000 | In progress |  | Building Committee appointed; working with Chair for initial meeeting. |  | Awaiting Building Committee. Preparing RFQ for Architect | Marty and Mike King are writing specifications and working to select an architect; | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
Cooling tower sump replacement | THS | 2021 Capital | 120000 | Complete |  |  |  | A&B Mechanical to make repairs. Proposal for $12,680 to patch steel and line sump with epoxy | [7 empty] | Doing minor repairs in house
Vehicle Replacements/Grounds | DW | 2021 Capital | 120000 | Complete |  |  | Complete | Backhoe received 10/6/2021 | Tractor on order | [6 empty] | ETA September 2021
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | In Progress |  |  | Sewer complete. Paving in spring 22 | Sewer work planned for 10/8-10/11. Completion delayed due to obstructions in trench and crew availability. | Town led project; drains and waste lines tested and potential septic lines blocked; discovered paying for sewers at the same time.
Domestic Hot Water at THS | THS | Operating |  | 2022-02-01 |  |  | Awarded to A&B Mechancial - Heater on order | Awaiting BOF approval of Non-Lapsing Fund |  | THS has two DHW tanks; one is down. This project will need to be prioritized. | [5 empty] | No progress
Summer Project List |  | Operating |  | Complete |  |  |  | Complete. Jane Ryan Courtyard cleaned and brush cleared. Middlebrook gas line sanded and painted. | Tashual kitchen; THS waste lines; playground mulch; stored furniture moved back to buildings. Planning on 7 summer interns. AC compressors at MB; Scrape and repaint gas lines at Middlebrook | John preparing a list of incremental summer projects whether for custodial staff or interns. Committee to advocate for summer help funding. | [5 empty] | Jane Ryan Courtyard, stored furniture,Middlebrook gas line all in progress.Tashua water lines complete.
Gym Floor Refinishing | MAD, FT | Capital |  | Awaiting Funding |  | Requested $165,000 in CY2022 bond issue |  | To be added to FY2022 Capital Plan | Going out to bid for Madison and Frenchtown. Getting a preliminary estimate from a contractor. | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting | [5 empty] | Quotes for refinishing came in over $60k, making it prohibitively expensive for this year.
Replacing Concrete Stairs at the Bus Depot | Bus Depot | Operating | 68400 | Complete | 2021-10-31 |  | Shop drawings rejected first time; in fabrication | Concrete poured on 10/11/21. Railings to be completed in two weeks. | Securing bids | [6 empty] | Titan Enterprise
Replacement of Ramps THS Portables |  |  | 42557 | Complete |  |  |  | Complete | [7 empty] | Replacing wood with alluminum ramps
Sewer Connection Long Hill |  |  | $55,00.00 | Complete | 2021-10-22 |  | Sewer Complete | Burns Construction installing new sewer line and manholes from lateral at back of building. Completion delayed due to obstructions in trench and crew availability. | [7 empty] | Prerequisite project for the Long Hill paving; capital funding being identified among other projects (Asbestos and HS shade panels)
Duct Replacement RAHU-1 THS |  |  | 210000 | Complete |  |  | Complete | Work complete. Contract closeout in progress. | [7 empty] | RZ Design
Tile & Carpet Replacement Frenchtown |  |  | 45053 | Complete |  |  | Complete | Complete | [7 empty] | Tile is lifting up, requiring to be taped down.
Asbestos (Flooring and Insulation) | HC | 2021 Capital | 40000 | Postponed - 2022 | 2022-07-31 | Preparing scope of work for bidding |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***; potential $20k savings vs. budget; much smaller job than anticipated.
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 75000 | Postponed - 2022 | 2022-07-31 | Preparing scope of work for bidding |  |  | Meeting contractors early June | [6 empty] | ***Pushed to 2022***
Roof Replacement | MB | 2021 Capital | 1725000 | Postponed - 2022 | 2022-07-31 | State OSCG&R Plan Review 2/2/2022 Revisions underway; awaiting approval to go to bid |  |  |  | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7. | [5 empty] | Building committee has delayed project to 2022 and is pursuing state reimbursement.
THS Auditorium Improvements (spotlight platforms) | THS | 2021 Capital | 57500 | Postponed - 2022 |  | Seeking proposals for curtain and house lighting |  |  | On hold due to duct replacement in that area. | John working with Kevin Bova to develop bid package | [5 empty] | ***Pushed to 2022***
Tilework and foundation around the rear entrance of the Ag Science building | AG | 2022 Capital | 65596 | Postponed - 2022 |  |  |  |  | Have estimate. will need to go out to bid. Should go in 2022 Capital plan. | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor |  |  |  |  | 65596

## Completed-Cancelled
Name of Project | Facility | Importance / Urgency | Status of Project | Planned / Final Completion Date | Estimated Cost | Notes
Kone Elevator | MAD | High / Med | Complete | Complete | 29000
Fencing Repairs | AG | Med / Med | Cancelled |  |  | Summer interns focused on school buidling readiness
Drainage / Culvert cleanout | ? | Med / Med | Cancelled |  |  | Summer interns focused on school buidling readiness
Mold Remediation | MB TLC; MB classroom; TECEC roof drain | High / High | Complete |  |  | Repaired and air quality tested
Total Communications (Intercom upgrades/improvements) | THS and others | High / High | Complete | 2020-11-12
Asbestos Abatement | BH, JR, MAD, HC | High / Med | Complete | 2020-10-08 | 190000
FT Cooling Towers Replacement | FT | High / High | Pending - 2021 Cap |  | 150000 | Remove
Agriscience Greenhouse Roof | AG | Low / Med | Pending - 2022 Cap |  | 53700 | Remove pending funding; summer project
Agriscience Boilers | Ag |  | Pending - 2021 Cap |  | 275000 | Remove pending funding; summer project
Replac e RTU's | JR & BH | High / High | ?? (Are not incl in 2021 Cap) |  | 20k per with installed | Remove. Currently reflected in 2022 Capital Plan
Boiler Water Treatment | 9 boilers | High / High | In progress |  | ~12,000 | Contract with OSC; ongoing maintenance program
THS/AG LED Lighting | THS & AG | Capital | Complete | 2021-02-28
RAHU 2 - THS | THS | CRF Grant | Complete | 2021-04-30 | 50000 | Complete
Name of Project | Facility | Funding | Estimated Cost | Planned / Final Completion Date | Estimated Cost
Bathroom sinks - touchless faucets | MAD, MB | CRF Grant | Number should be in grant | 2021-03-31 |  | Complete
Split Systems | DF and Tashua | CRF Grant |  | 2021-03-31 |  | Complete

## 2021-10-13 Pending - Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 10/13/2021 Update | 7/13/21 Update | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes
Auditorium Lighting / AV | THS | Operating | 8000 | In progress |  |  | Ceiling lighting repaired, seat side panels and aisle lighting in progress | Received lights, wrong side panels were sent. | Aisle lighting being address in operational budget. Hussey seating. Materials coming in April | Are there some items that should be completed as part of the 21-22 budget? | Need engineer to review the spotlight platforms; 50k to replace aisle lighting; quoted | Reached out to contractor to construct spot light positions off the floor. | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20
Builders Hardware/Phase 2 | All schools | Security Bond | 111815 | In progress |  |  |  |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Madison Vestibule | MAD | Safety & Security Grant | 68000 | In progress |  |  | Cable and harware ordered 6/4, all backordered as of 7/2 | Bizmark complete. Meeting JKS 5/19 10:00 for panic hardware/swipes ect. | Bismark is working on the project. Estimated completion is the beginning of May. | Awarded to Bismark; securing permits; ordering materials; scheduled for some. Updated cost estimate to come. | Bid is out Saturday. Meetings start Monday. Closes 12/3 | Potential reopening of project to be covered by recently discovered security bonds. Schedule for holiday break? | No funding | Looking to get a portion into 2019-20
Bathroom stalls | All ES | Operating | 150000 | In progress |  |  | No progress |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital?
Bathroom sinks - touchless faucets | MAD, MB | CRF Grant | Number should be in grant | Complete | 2021-03-31 |  | Complete | Completed 3 schools in house. Contractor 90% complete with 3 schools | Finishing up MB; MAD complete Contractor is working on other schools (TA, DF, HC) | Some projects are in-house; 3 others are contracted out.
Tilework and foundation around the rear entrance of the Ag Science building | AG | TBD | 65596 | Researching |  |  | 65596 | Have estimate. will need to go out to bid. Should go in 2022 Capital plan. | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor
Asbestos (Flooring and Insulation) | HC | 2021 Capital | 40000 | Postponed - 2022 | 2022-07-31 |  | ***Pushed to 2022***; potential $20k savings vs. budget; much smaller job than anticipated. | Meeting contractors early June
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 75000 | Postponed - 2022 | 2022-07-31 |  | ***Pushed to 2022*** | Meeting contractors early June
Remove ext. concrete shade panels | HC | 2021 Capital | 92000 | Bonding Approved |  |  | Starting Mid/End July; potential $22k savings vs. budget | Scope of work is complete, going out to bid
Roof Replacement | MB | 2021 Capital | 1725000 | Postponed - 2022 | 2022-07-31 |  | Building committee has delayed project to 2022 and is pursuing state reimbursement. |  | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7.
Elevator Single bottom Cylinder Upgrade(code) | JR | 2021 Capital | 90000 | Quotes received |  |  | Architect completed scope of work | Two quotes received; assembling scope of work to go out to bid
Drainage design and construction | BH | 2021 Capital | 540000 | Bonding Approved |  |  |  | Town led project
Cooling Tower Replacement | FT | 2021 Capital | 150000 | In progress |  |  | Waiting on scope of work from Silver & Petrucelli. hopefully schedule after cooling season
Boiler replacements | AG | 2021 Capital | 275000 | In progress |  |  | Shortage of equipment & manpower is causing a delay in starting this project. | PO to S&P for design and bid docs
Wellness/Fitness Center | THS | 2021 Capital | 35000 | In progress |  |  |  | Marty and Mike King are writing specifications and working to select an architect; | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
THS Auditorium Improvements (spotlight platforms) | THS | 2021 Capital | 57500 | Postponed - 2022 |  |  | ***Pushed to 2022*** | On hold due to duct replacement in that area. | John working with Kevin Bova to develop bid package
Cooling tower sump replacement | THS | 2021 Capital | 120000 | Bonding Approved |  |  | Doing minor repairs in house
Vehicle Replacements/Grounds | DW | 2021 Capital | 120000 | In Progress |  |  | ETA September 2021 | Tractor on order
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | In Progress |  |  |  | Town led project; drains and waste lines tested and potential septic lines blocked; discovered paying for sewers at the same time.
Split Systems | DF and Tashua | CRF Grant |  | Complete | 2021-03-31 |  | Complete | Ongoing | Once complete, each ES will have one classroom per grade air conditioned.
Domestic Hot Water at THS | THS | Operating |  | Pending |  |  | No progress |  | THS has two DHW tanks; one is down. This project will need to be prioritized.
Summer Project List |  | Operating |  | In Progress |  |  | Jane Ryan Courtyard, stored furniture,Middlebrook gas line all in progress.Tashua water lines complete. | Tashual kitchen; THS waste lines; playground mulch; stored furniture moved back to buildings. Planning on 7 summer interns. AC compressors at MB; Scrape and repaint gas lines at Middlebrook | John preparing a list of incremental summer projects whether for custodial staff or interns. Committee to advocate for summer help funding.
Gym Floor Refinishing | MAD, FT | Operating |  | In Progress |  |  | Quotes for refinishing came in over $60k, making it prohibitively expensive for this year. | Going out to bid for Madison and Frenchtown. Getting a preliminary estimate from a contractor. | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting
Replacing Concrete Stairs at the Bus Depot | Bus Depot | Operating | 68400 | In Progress | End of August |  | Titan Enterprise | Securing bids
Replacement of Ramps THS Portables |  |  | 42557 | In Progress |  |  | Replacing wood with alluminum ramps
Sewer Connection Long Hill |  |  | $55,00.00 | Securing Funds |  |  | Prerequisite project for the Long Hill paving; capital funding being identified among other projects (Asbestos and HS shade panels)
Duct Replacement RAHU-1 THS |  |  | 210000 | In Progress | End of August |  | RZ Design
Tile & Carpet Replacement Frenchtown |  |  | Approx $46,000.00 | In Progress |  |  | Tile is lifting up, requiring to be taped down.

## 2021-07-13 Pending-Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 7/13/21 Update | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes
Auditorium Lighting / AV | THS | Operating | 8000 | In progress |  | Ceiling lighting repaired, seat side panels and aisle lighting in progress | Received lights, wrong side panels were sent. | Aisle lighting being address in operational budget. Hussey seating. Materials coming in April | Are there some items that should be completed as part of the 21-22 budget? | Need engineer to review the spotlight platforms; 50k to replace aisle lighting; quoted | Reached out to contractor to construct spot light positions off the floor. | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20
Builders Hardware/Phase 2 | All schools | Security Bond | 111815 | In progress |  |  |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Madison Vestibule | MAD | Safety & Security Grant | 68000 | In progress |  | Cable and harware ordered 6/4, all backordered as of 7/2 | Bizmark complete. Meeting JKS 5/19 10:00 for panic hardware/swipes ect. | Bismark is working on the project. Estimated completion is the beginning of May. | Awarded to Bismark; securing permits; ordering materials; scheduled for some. Updated cost estimate to come. | Bid is out Saturday. Meetings start Monday. Closes 12/3 | Potential reopening of project to be covered by recently discovered security bonds. Schedule for holiday break? | No funding | Looking to get a portion into 2019-20
Bathroom stalls | All ES | Operating | 150000 | In progress |  | No progress |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital?
Bathroom sinks - touchless faucets | MAD, MB | CRF Grant | Number should be in grant | Complete | 2021-03-31 | Complete | Completed 3 schools in house. Contractor 90% complete with 3 schools | Finishing up MB; MAD complete Contractor is working on other schools (TA, DF, HC) | Some projects are in-house; 3 others are contracted out.
Tilework and foundation around the rear entrance of the Ag Science building | AG | TBD | 65596 | Researching |  | 65596 | Have estimate. will need to go out to bid. Should go in 2022 Capital plan. | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor
Asbestos (Flooring and Insulation) | HC | 2021 Capital | 40000 | Postponed - 2022 | 2022-07-31 | ***Pushed to 2022***; potential $20k savings vs. budget; much smaller job than anticipated. | Meeting contractors early June
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 75000 | Postponed - 2022 | 2022-07-31 | ***Pushed to 2022*** | Meeting contractors early June
Remove ext. concrete shade panels | HC | 2021 Capital | 92000 | Bonding Approved |  | Starting Mid/End July; potential $22k savings vs. budget | Scope of work is complete, going out to bid
Roof Replacement | MB | 2021 Capital | 1725000 | Postponed - 2022 | 2022-07-31 | Building committee has delayed project to 2022 and is pursuing state reimbursement. |  | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7.
Elevator Single bottom Cylinder Upgrade(code) | JR | 2021 Capital | 90000 | Quotes received |  | Architect completed scope of work | Two quotes received; assembling scope of work to go out to bid
Drainage design and construction | BH | 2021 Capital | 540000 | Bonding Approved |  |  | Town led project
Cooling Tower Replacement | FT | 2021 Capital | 150000 | In progress |  | Waiting on scope of work from Silver & Petrucelli. hopefully schedule after cooling season
Boiler replacements | AG | 2021 Capital | 275000 | In progress |  | Shortage of equipment & manpower is causing a delay in starting this project. | PO to S&P for design and bid docs
Wellness/Fitness Center | THS | 2021 Capital | 35000 | In progress |  |  | Marty and Mike King are writing specifications and working to select an architect; | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
THS Auditorium Improvements (spotlight platforms) | THS | 2021 Capital | 57500 | Postponed - 2022 |  | ***Pushed to 2022*** | On hold due to duct replacement in that area. | John working with Kevin Bova to develop bid package
Cooling tower sump replacement | THS | 2021 Capital | 120000 | Bonding Approved |  | Doing minor repairs in house
Vehicle Replacements/Grounds | DW | 2021 Capital | 120000 | In Progress |  | ETA September 2021 | Tractor on order
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | In Progress |  |  | Town led project; drains and waste lines tested and potential septic lines blocked; discovered paying for sewers at the same time.
Split Systems | DF and Tashua | CRF Grant |  | Complete | 2021-03-31 | Complete | Ongoing | Once complete, each ES will have one classroom per grade air conditioned.
Domestic Hot Water at THS | THS | Operating |  | Pending |  | No progress |  | THS has two DHW tanks; one is down. This project will need to be prioritized.
Summer Project List |  | Operating |  | In Progress |  | Jane Ryan Courtyard, stored furniture,Middlebrook gas line all in progress.Tashua water lines complete. | Tashual kitchen; THS waste lines; playground mulch; stored furniture moved back to buildings. Planning on 7 summer interns. AC compressors at MB; Scrape and repaint gas lines at Middlebrook | John preparing a list of incremental summer projects whether for custodial staff or interns. Committee to advocate for summer help funding.
Gym Floor Refinishing | MAD, FT | Operating |  | In Progress |  | Quotes for refinishing came in over $60k, making it prohibitively expensive for this year. | Going out to bid for Madison and Frenchtown. Getting a preliminary estimate from a contractor. | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting
Replacing Concrete Stairs at the Bus Depot | Bus Depot | Operating | 68400 | In Progress | End of August | Titan Enterprise | Securing bids
Replacement of Ramps THS Portables |  |  | 42557 | In Progress |  | Replacing wood with alluminum ramps
Sewer Connection Long Hill |  |  | $55,00.00 | Securing Funds |  | Prerequisite project for the Long Hill paving; capital funding being identified among other projects (Asbestos and HS shade panels)
Duct Replacement RAHU-1 THS |  |  | 210000 | In Progress | End of August | RZ Design
Tile & Carpet Replacement Frenchtown |  |  | Approx $46,000.00 | In Progress |  | Tile is lifting up, requiring to be taped down.

## 2021-05-20 Pending-Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes
Auditorium Lighting / AV | THS | Operating | 8000 | In progress |  | Received lights, wrong side panels were sent. | Aisle lighting being address in operational budget. Hussey seating. Materials coming in April | Are there some items that should be completed as part of the 21-22 budget? | Need engineer to review the spotlight platforms; 50k to replace aisle lighting; quoted | Reached out to contractor to construct spot light positions off the floor. | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20
Builders Hardware/Phase 2 | All schools | Security Bond | 111815 | In progress |  |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Madison Vestibule | MAD | Safety & Security Grant | 68000 | In progress | FDOS 2021 | Bizmark complete. Meeting JKS 5/19 10:00 for panic hardware/swipes ect. | Bismark is working on the project. Estimated completion is the beginning of May. | Awarded to Bismark; securing permits; ordering materials; scheduled for some. Updated cost estimate to come. | Bid is out Saturday. Meetings start Monday. Closes 12/3 | Potential reopening of project to be covered by recently discovered security bonds. Schedule for holiday break? | No funding | Looking to get a portion into 2019-20
Bathroom stalls | All ES | Operating | 150000 | In progress |  |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital?
RAHU 2 - THS | THS | CRF Grant | 50000 | In progress | 4/30/21? | Complete | 99% complete; insulation is on backorder | New duct work installed; temp heating unit removed; waiting on a sound attenuator. Vibration analysis. Completion mid Feb | Ron Batherick, RZ Design Associates; If we use CRF funds we need a bid waiver. Kevin Bova denied. Vicki looking into it. | Potential safety issue given the previous spilled glycol incidents. | No funding in 2020 | Met with engineer; HVAC repairs in 2021
Bathroom sinks - touchless faucets | MAD, MB | CRF Grant | Number should be in grant | In Progress | 2021-03-31 | Completed 3 schools in house. Contractor 90% complete with 3 schools | Finishing up MB; MAD complete Contractor is working on other schools (TA, DF, HC) | Some projects are in-house; 3 others are contracted out.
Tilework and foundation around the rear entrance of the Ag Science building | AG | TBD |  | Researching |  | Have estimate. will need to go out to bid. Should go in 2022 Capital plan. | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor
Asbestos (Flooring and Insulation) | HC | 2021 Capital | 40000 | Bonding Approved |  | Meeting contractors early June
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 75000 | Bonding Approved |  | Meeting contractors early June
Remove ext. concrete shade panels | HC | 2021 Capital | 92000 | Bonding Approved |  | Scope of work is complete, going out to bid
Roof Replacement | MB | 2021 Capital | 1725000 | Bonding Approved | 2021-07-31 |  | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7.
Elevator Single bottom Cylinder Upgrade(code) | JR | 2021 Capital | 90000 | Quotes received |  | Two quotes received; assembling scope of work to go out to bid
Drainage design and construction | BH | 2021 Capital | 540000 | Bonding Approved |  | Town led project
Cooling Tower Replacement | FT | 2021 Capital | 150000 | Bonding Approved
Boiler replacements | AG | 2021 Capital | 275000 | Bonding Approved |  | PO to S&P for design and bid docs
Wellness/Fitness Center | THS | 2021 Capital | 35000 | Bonding Approved |  | Marty and Mike King are writing specifications and working to select an architect; | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
THS Auditorium Improvements (spotlight platforms) | THS | 2021 Capital | 57500 | Bonding Approved |  | On hold due to duct replacement in that area. | John working with Kevin Bova to develop bid package
Cooling tower sump replacement | THS | 2021 Capital | 120000 | Bonding Approved
Vehicle Replacements/Grounds | DW | 2021 Capital | 120000 | In Progress |  | Tractor on order
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | In Progress |  | Town led project; drains and waste lines tested and potential septic lines blocked; discovered paying for sewers at the same time.
Split Systems | DF and Tashua | CRF Grant |  | In Progress | 2021-03-31 | Ongoing | Once complete, each ES will have one classroom per grade air conditioned.
Domestic Hot Water at THS | THS | Operating |  | Pending |  |  | THS has two DHW tanks; one is down. This project will need to be prioritized.
Summer Project List |  | Operating |  | Planned |  | Tashual kitchen; THS waste lines; playground mulch; stored furniture moved back to buildings. Planning on 7 summer interns. AC compressors at MB; Scrape and repaint gas lines at Middlebrook | John preparing a list of incremental summer projects whether for custodial staff or interns. Committee to advocate for summer help funding.
Gym Floor Refinishing | MAD, FT | Operating |  | In Progress |  | Going out to bid for Madison and Frenchtown. Getting a preliminary estimate from a contractor. | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting
Replacing Concrete Stairs at the Bus Depot | Bus Depot | Operating |  | Out to bid |  | Securing bids

## 2021-03-18 Pending-Active
TPS Facilities Project List
Name of Project | Facility | Funding | Estimated Cost | Status of Project | Planned / Final Completion Date | 5/20/21 Update | 3/18/21 Update | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes
Auditorium Lighting / AV | THS | Operating | 8000 | In progress |  |  | Aisle lighting being address in operational budget. Hussey seating. Materials coming in April | Are there some items that should be completed as part of the 21-22 budget? | Need engineer to review the spotlight platforms; 50k to replace aisle lighting; quoted | Reached out to contractor to construct spot light positions off the floor. | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20
Builders Hardware/Phase 2 | All schools | Security Bond | 111815 | In progress |  |  | Add ons to phase 1 have been started; Survey for Phase 2 in progress. | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Madison Vestibule | MAD | Safety & Security Grant | 68000 | In progress | Beginning of May |  | Bismark is working on the project. Estimated completion is the beginning of May. | Awarded to Bismark; securing permits; ordering materials; scheduled for some. Updated cost estimate to come. | Bid is out Saturday. Meetings start Monday. Closes 12/3 | Potential reopening of project to be covered by recently discovered security bonds. Schedule for holiday break? | No funding | Looking to get a portion into 2019-20
Bathroom stalls | All ES | Operating | 150000 | In progress |  |  | Started survey of buildings / bathrooms need the most work. | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital?
RAHU 2 - THS | THS | CRF Grant | 50000 | In progress | 4/30/21? |  | 99% complete; insulation is on backorder | New duct work installed; temp heating unit removed; waiting on a sound attenuator. Vibration analysis. Completion mid Feb | Ron Batherick, RZ Design Associates; If we use CRF funds we need a bid waiver. Kevin Bova denied. Vicki looking into it. | Potential safety issue given the previous spilled glycol incidents. | No funding in 2020 | Met with engineer; HVAC repairs in 2021
THS/AG LED Lighting | THS & AG | Capital |  | Complete | 2021-02-28 |  | Finished THS high last month | Ag is done; still working on Trumbull High. Another two months tops | Still working on THS almost done | Ag is done; THS in progress | AG is done; Scheduling HS; consideration of incremental cleaning costs | Coming before BOE on 6/16
Bathroom sinks - touchless faucets | MAD, MB | CRF Grant | Number should be in grant | In Progress | 2021-03-31 |  | Finishing up MB; MAD complete Contractor is working on other schools (TA, DF, HC) | Some projects are in-house; 3 others are contracted out.
Tilework and foundation around the rear entrance of the Ag Science building | AG | TBD |  | Researching |  |  | Working with contractors to scope the issue and project. | There is water damage at this doorway that has impacted tile and subfloor
Asbestos (Flooring and Insulation) | HC | 2021 Capital | 40000 | Bonding Approved
Asbestos (Flooring and Insulation) | MAD | 2021 Capital | 75000 | Bonding Approved
Remove ext. concrete shade panels | HC | 2021 Capital | 92000 | Bonding Approved
Roof Replacement | MB | 2021 Capital | 1725000 | Bonding Approved | 2021-07-31 | Building Committee agreed to postpone this project until summer 2022; bid package being prepared and considering request for state grant funding. | Building Committee met for the first time on 3/17/21; selecting an architect next week, bids out in a month, final TC approval 6/7.
Elevator Single bottom Cylinder Upgrade(code) | JR | 2021 Capital | 90000 | Bonding Approved
Drainage design and construction | BH | 2021 Capital | 540000 | Bonding Approved
Cooling Tower Replacement | FT | 2021 Capital | 150000 | Bonding Approved
Boiler replacements | AG | 2021 Capital | 275000 | Bonding Approved
Wellness/Fitness Center | THS | 2021 Capital | 35000 | Bonding Approved |  |  | John to work with Kevin Bova to select an architect to do design work. Lucinda reported that there is a committee at the high school looking into fundraising opportunities.
THS Auditorium Improvements (spotlight platforms) | THS | 2021 Capital | 57500 | Bonding Approved |  |  | John working with Kevin Bova to develop bid package
Cooling tower sump replacement | THS | 2021 Capital | 120000 | Bonding Approved
Vehicle Replacements/Grounds | DW | 2021 Capital | 120000 | Bonding Approved
Parking Lot and Drainage work | LH | 2021 Capital | 290000 | Bonding Approved
Split Systems | DF and Tashua | CRF Grant |  | In Progress | 2021-03-31 |  | Once complete, each ES will have one classroom per grade air conditioned.
Domestic Hot Water at THS | THS | Operating |  | Pending |  |  | THS has two DHW tanks; one is down. This project will need to be prioritized.
Summer Project List |  | Operating |  | Waiting to see how many summer kids are approved - budgeted. |  |  | John preparing a list of incremental summer projects whether for custodial staff or interns. Committee to advocate for summer help funding.
Gym Floor Refinishing | MAD, FT | Operating |  | Pending Summer |  |  | John recommends using an outside contractor, at least for Madison which requires more work due to heavy use. Update at next meeting

## 2021-01-20 Pending-Active
TPS Facilities Project List
Name of Project | Facility | Importance / Urgency | Status of Project | Planned / Final Completion Date | Estimated Cost | 1/20/21 Meeting Notes | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes
Auditorium Lighting / AV |  | High / High | Pending 2021 Cap |  | 175000 | Are there some items that should be completed as part of the 21-22 budget? | Need engineer to review the spotlight platforms; 50k to replace aisle lighting; quoted | Reached out to contractor to construct spot light positions off the floor. | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20
Boiler Water Treatment | 9 boilers | High / High | In progress |  | ~12,000 | Contract with OSC; ongoing maintenance program. Remove from active list. | EMC; working through all the units | Scheduling monthly checks by vendor; internal staff doing required plumbing work.
Builders Hardware/Phase 2 | All schools | High / High | On Hold |  | 111815 | Re-walked THS; remediated THS; Covid closures have paused work | Issues have arisen with Phase I; Phase 1 is not paid; holding off on phase II. | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
FT Cooling Towers Replacement | FT | High / High | Pending - 2021 Cap |  | 150000 | Remove; in capital plan |  | In-house repairs this summer. Review capital submission schedule. | Priority for next capital request | Replace vs. repair. High priority. In captital plan for 2021
Madison Vestibule | MAD | High / High | In progress |  | 68000 | Awarded to Bismark; securing permits; ordering materials; scheduled for summer | Bid is out Saturday. Meetings start Monday. Closes 12/3 | Potential reopening of project to be covered by recently discovered security bonds. Schedule for holiday break? | No funding | Looking to get a portion into 2019-20
Replac e RTU's | JR & BH | High / High | ?? (Are not incl in 2021 Cap) |  | 20k per with installed | Currently reflected in 2022 Capital Plan |  |  | No funding available; 12k each | 2 at JR and 2 at BH; as high a priority as FT
Bathroom stalls | All ES | High / Med | Planned 2021-22 |  | 150000 | 2 contractors slated to walk the buildings to bid | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital?
RAHU 2 - THS | THS | High / Med | Pending Funding - CRF Grant |  | 50000 | New duct work installed; temp heating unit removed; waiting on a sound attenuator. Vibration analysis. Completion mid Feb | Ron Batherick, RZ Design Associates; If we use CRF funds we need a bid waiver. Kevin Bova denied. Vicki looking into it. | Potential safety issue given the previous spilled glycol incidents. | No funding in 2020 | Met with engineer; HVAC repairs in 2021
Agriscience Greenhouse Roof | AG | Low / Med | Pending - 2022 Cap |  | 53700 | Remove pending funding; summer project | There are other more urgent priorities at Ag (boilers) | There is an active leak. Exceeded life expectancy. Adding to 20-21 capital request. | Proposal being reviewed | Waiting on final proposal
THS/AG LED Lighting | THS & AG | Med / Med | In Progress |  |  | Ag is done; still working on Trumbull High. Another two months tops | Still working on THS almost done | Ag is done; THS in progress | AG is done; Scheduling HS; consideration of incremental cleaning costs | Coming before BOE on 6/16
Agriscience Boilers | Ag |  | Pending - 2021 Cap |  | 275000 | Remove pending funding; summer project
Bathroom sinks - touchless faucets | Madisson, Middlebrook |  |  |  | Number should be in grant | Some projects are in-house; 3 others are contracted out.
Tilework and foundation around the rear entrance of the Ag Science building | AG |  | Researching |  |  | There is water damage at this doorway (#8) that has impacted tile and subfloor

## 2020-11-12 Pending-Active
TPS Facilities Project List
Name of Project | Facility | Importance / Urgency | Status of Project | Planned / Final Completion Date | Estimated Cost | 11/12/20 Meeting Notes | 10/8/20 Meeting Notes | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes
Total Communications (Intercom upgrades/improvements) | THS and others | High / High | Complete | unknown |  | Complete | Owe vendor 53k; Middlebrook girls, faculty bathroom BH. Speakers in restrooms. | Need to check on 2 schools (MAD, DFS, AG) before calling the project complete. | THS intercom system repairs
THS/AG LED Lighting | THS & AG | Med / Med | In-Progress |  |  | Still working on THS almost done | Ag is done; THS in progress | AG is done; Scheduling HS; consideration of incremental cleaning costs | Coming before BOE on 6/16
Builders Hardware/Phase 2 | All schools | High / High | Pending Funding (Security Grant) |  | 111815 | Issues have arisen with Phase I; Phase 1 is not paid | Potential reopening of project to be covered by recently discovered security bonds. | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Asbestos Abatement | BH, JR, MAD, HC | High / Med | Complete | end of 2020 summer | 190000 |  | Complete | 80% complete with new tile installation | Starting 6/18-19; BH, JR, MAD, HC; bonded project
Madison Vestibule | MAD | High / High | Pending Funding (Security Grant) |  | 68000 | Bid is out Saturday. Meetings start Monday. Closes 12/3 | Potential reopening of project to be covered by recently discovered security bonds. Schedule for holiday break? | No funding | Looking to get a portion into 2019-20
Auditorium Lighting / AV |  | High / High | Pending / Research |  |  | Need engineer to review the spotlight platforms; 50k to replace aisle lighting; quoted | Reached out to contractor to construct spot light positions off the floor. | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20
Boiler Water Treatment | 9 boilers | High / High | In progress |  | ~12,000 | EMC; working through all the units | Scheduling monthly checks by vendor; internal staff doing required plumbing work.
Bathroom stalls | All ES | High / Med | Planned 2021-22 |  |  | Money added to next year's operating budget | Schedule for 2021-22 school year. Capital?
Agriscience Greenhouse Roof | AG | Low / Med | Pending - 2021 Cap |  | 53700 |  | There is an active leak. Exceeded life expectancy. Adding to 20-21 capital request. | Proposal being reviewed | Waiting on final proposal
FT Cooling Tower Repair | FT | High / High | Pending - 2021 Cap |  | $75,000+/ea |  | In-house repairs this summer. Review capital submission schedule. | Priority for next capital request | Replace vs. repair. High priority. In captital plan for 2021
RAHU 2 - THS | THS | High / Med | Pending Funding - CRF Grant |  | 50000 | Ron Batherick, RZ Design Associates; If we use CRF funds we need a bid waiver. Kevin Bova denied. Vicki looking into it. | Potential safety issue given the previous spilled glycol incidents. | No funding in 2020 | Met with engineer; HVAC repairs in 2021
Replac e RTU's | JR & BH | High / High | Pending - 2021 Cap |  | 20k per with installed |  |  | No funding available; 12k each | 2 at JR and 2 at BH; as high a priority as FT
Agriscience Boilers | Ag |  | Pending - 2021 Cap

## 2020-08-20 Pending-Active
Running TPS Facilities Project List
Name of Project | Facility | Importance / Urgency | Status of Project | Planned / Final Completion Date | Estimated Cost | 8-20-20 Meeting Notes | 6/11/20 Meeting Notes
Total Communications (Intercom upgrades/improvements) | THS and others | High / High | In-progress | unknown |  | Need to check on 2 schools (MAD, DFS, AG) before calling the project complete. | THS intercom system repairs
Replac e RTU's | JR & BH | High / High | Pending Funding |  | ~12k each | No funding available; 12k each | 2 at JR and 2 at BH; as high a priority as FT
FT Cooling Tower Repair | FT | High / High | Pending - 2021 Cap |  | $75,000+/ea | Priority for next capital request | Replace vs. repair. High priority. In captital plan for 2021
Agriscience Greenhouse Roof | AG | Low / Med | Proposal received |  | 53700 | Proposal being reviewed | Waiting on final proposal
THS/AG LED Lighting | THS & AG | Med / Med | In-Progress |  |  | AG is done; Scheduling HS; consideration of incremental cleaning costs | Coming before BOE on 6/16
Builders Hardware/Phase 2 | All schools | High / High | Pending Funding |  | 111815 | No Funding; delay project | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Abatement | BH, JR, MAD, HC | High / Med | In progress | end of 2020 summer | 190000 | 80% complete with new tile installation | Starting 6/18-19; BH, JR, MAD, HC; bonded project
Madison Vestibule | MAD | High / High | Pending Funding |  | 68000 | No funding | Looking to get a portion into 2019-20
RAHU 2 - THS | THS | High / Med | Pending Funding |  | 50000 | No funding in 2020 | Met with engineer; HVAC repairs in 2021
Fencing Repairs | AG | Med / Med | Cancelled |  |  | Summer interns focused on school buidling readiness | 7 summer crew (2-3 maintainence)
Drainage / Culvert cleanout | ? | Med / Med | Cancelled |  |  | Summer interns focused on school buidling readiness
Auditorium Lighting / AV |  |  | Pending / Research |  |  | No progress; Concerned about spotlight scaffolding | Received request to research 6/14/20
Mold Remediation | MB TLC; MB classroom; TECEC roof drain | High / High | In Progress |  |  | Classroom with bathroom; Facilities study of mold risk

## 2020-06-11 List
Name of Project | Facility | Importance / Urgency | Status of Project | Planned / Final Completion Date | Estimated Cost | 6/11/20 Meeting Notes
Total Communications | THS | High / High | In-progress | unknown |  | THS intercom system repairs
Kone Elevator | MAD | High / Med | Complete | Complete | 29000 | Madison
Replac e RTU's | JR & BH | High / High | Pending funding |  | ~20k each | 2 at JR and 2 at BH; as high a priority as FT
FT Cooling Tower Repair | FT | High / High | Pending - 2021 Cap |  | $75,000+/ea | Replace vs. repair. High priority. In captital plan for 2021
Agriscience Greenhouse Roof | AG | High / Med | Awaiting proposal |  |  | Waiting on final proposal
THS/AG LED Lighting | THS & AG | Med / Med | Pending approval |  |  | Coming before BOE on 6/16
Builders Hardware/Phase 2 | All schools | High / High | summer 5 weeks to order |  | 111815 | not incl THS. Phase 1 was classrooms; Phase 2 is common areas (conference rooms, guidance)
Abatement | BH, JR, MAD, HC | High / Med | In progress | end of 2020 summer | 190000 | Starting 6/18-19; BH, JR, MAD, HC; bonded project
Madison Vestibule | MAD | High / High | Pending - funding |  | 68000 | Looking to get a portion into 2019-20
RAHU 2 - THS | THS | Med / Med | Pending - 2021 Rep |  | 50000 | Met with engineer; HVAC repairs in 2021
Fencing Repairs | AG | Med / Med | Summer Interns |  |  | 7 summer crew (2-3 maintainence)
Drainage / Culvert cleanout | ? | Med / Med | Summer Interns
Auditorium Lighing/AV |  |  | Pending / Research |  |  | Received request to research 6/14/20