# Comprehensive School Improvement Plan (CSIP)

## Rationale

​School improvement efforts are a collaborative process involving multiple stakeholders. Through the improvement planning process, leaders focus on priority needs, funding, and closing achievement gaps among identified subgroups of students. When implemented with fidelity, the Comprehensive School Improvement Plan (CSIP) cultivates an environment that promotes student growth and achievement.

While the focus of continuous improvement is student performance, the work must be guided by the aspects of teaching and learning that affect performance. An effective improvement process should address the contributing factors creating the learning environment (inputs) and the performance data (outcomes). Through the Needs Assessment for Schools, priorities were identified and processes, practices, and/or conditions were chosen for focus. This goal building template will assist your improvement team to address those priorities and outline your targets and the activities intended to produce the desired changes. Progress monitoring details will ensure that your plan is being reviewed regularly to determine the success of each strategy.

Please note that the objectives (short-term targets) set by your school under the Achievement Gap section of this planning template will be used by the district’s superintendent to determine whether or not your school met its targets to reduce the gap in student achievement for any student group for two consecutive years as required by KRS 158.649. Likewise, operational definitions for each required planning component can be found on page 2 of the planning template.

For those schools operating a Title I Schoolwide Program, this plan meets the requirements of Section 1114 of the Every Student Succeeds Act as well as state requirements under 703 KAR 5:225. No separate Schoolwide Program Plan is required.

## Requirements for Building an Improvement Plan

- The required school goals include the following:

  - For elementary/middle school, these include proficiency, separate academic indicators, achievement gap, and growth.

  - For high school, these include proficiency, separate academic indicators, achievement gap, graduation rate, and transition readiness.

## 1: Proficiency

| Goal 1 (State your proficiency goal.): Increase the number of students scoring proficient/distinguished on KPREP for reading and math at the elementary and middle grades level (Elementary Reading from 31.4 in 2021 to 50 in 2024, Elementary Math from 18.4 in 2021 to 45 in 2024; Middle Grades Reading from 47.5 in 2021 to 65 in 2024, Middle Grades Math from 26.3 in 2021 to 50 in 2024). |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1: Increase the number of students scoring proficient/distinguished on KPREP in elementary reading from 31.4 in 2021 to 38 in 2022 and middle grades reading from 47.5 in 2021 to 53 in 2022. | KCWP 2: Design and Deliver | Research Based Curriculum and Instructional Strategies for Reading K-8 teachers will implement the research based Success for All reading program with fidelity. | Observation data by SFA Facilitator & Reading Principal Observations by SFA district coach & SFA Consultant |  | Elgin/District |  |
|  |  | Save the Children Literacy Program Students identified by program assessment performing below grade level in K-6th grade will be provided tutorials in phonics, sight word growth, comprehension, and vocabulary enhancement. | Improved reading proficiency |  | STC Funding |  |
|  | KCWP 1: Design and Deploy Standards KCWP 5: Design, Align, and Deliver Support | Professional Learning Communities Reading teachers will participate in school level reading PLCs to discuss curriculum, strategies, assessment, and data analysis. | Assessment Data (SFA Member Center, Reading Mastery Placement Tests, Roots Assessments) |  | No Funding Needed |  |
|  |  | RTI/CCEIS Coaching A district instructional coach will provide on-site coaching and monitoring of intervention instruction in reading. | Data from Intervention Central |  | District Funding |  |
|  | KCWP 4: Review, Analyze and Apply Data KCWP 5: Design, Align, and Deliver Support | SFA Reading Data Teachers and reading facilitator will use Member Center to track lesson cycles, student growth, and overall grade level growth in quarterly reports. | Reading teachers and SFA Facilitator Student placement data Quarterly Reports |  | District Funding |  |
|  |  | Blending Learning Reading teachers will incorporate blending learning strategies to engage all learners. (Use of Clever apps- Google, Flocabulary, etc) Response to Intervention (RTI K-3) K-2 students will be instructed using the Reading Mastery Program and 3rd grade will receive instruction from Novel Studies. | Increased student engagement Data from virtual platforms Observations during RTI class period. RTI data/placement assessments |  | District/School Funding |  |
| Objective 2: Increase the number of students scoring proficient/distinguished on KPREP in math elementary from 18.4 in 2021 to 27 in 2022 and middle grades from 26.3 in 2021 to 35 in 2022. | KCWP 2: Design and Deliver Instruction | C-P-A Initiative All math teachers will focus on the (CPA) Concrete-Pictorial-Abstract method to help develop a deep and sustainable approach to math by using visual and physical aids. | Observations Lesson plans |  | No Funding Needed |  |
|  |  | Math in Focus Teachers will implement a K-8 comprehensive program that develops strong algebraic concepts and problem solving skills. Instructional strategies incorporate direct instruction, cooperative learning, and guided and independent practice. | Classroom observations |  | Title IV |  |
|  | KCWP: 4 Review, Analyze, and Apply Data | MAP Accelerator Math teachers in grades 6-8 use Map Accelerator to differentiate instruction and provide tailored support based on pathways connected to the NWEA/MAP assessments. | Progress data and NWEA reports |  | District Funding |  |
|  | KCWP: 5 Design, Align, and Deliver Support | Supplemental Resources and Interventions Math teachers will utilize Automaticity, Moby Max, Prodigy, and Problem Attic to support our core math program. | Progress data and reports |  | District Funding |  |

## 2: Separate Academic Indicator

| Goal 2 (State your separate academic indicator goal.): Increase the number of students scoring proficient/distinguished on KPREP in science in elementary (4th grade) from 26.7 in 2021 to 50 in 2024 and at the middle grades level (7th grade) from 20.4 in 2021 to 45 in 2024; on-demand writing in elementary (5th grade) from 31.3 in 2021 to 51 in 2024 and at the middle grades level (8th grade) from 65 in 2021 to 75 in 2024. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1: Increase the number of students scoring proficient/distinguished on KPREP in elementary science from 26.7 in 2021 to 34 in 2022 and in middle grades science from 20.4 in 2021 to 28 in 2022. | KCWP 2: Design and Deliver Instruction | IQWST 5-8 Science Teacher will implement IQWST to promote a phenomenon-driven, 3-Dimensional learning experience that is aligned with the NGSS standards. | More rigorous science lessons that are aligned with the NGSS standards. |  | Title IV Funding |  |
|  |  | Mystery Science K-5 Science teachers will utilize the Mystery Science program to explore a given phenomena and analyze data. | Classroom observations and lesson plans |  | Title IV Funding |  |
| Objective 2: Increase the number of students scoring proficient/distinguished on KPREP in on-demand writing in elementary from 31.3 in 2021 to 38 in 2022 and in middle grades on-demand writing from 65 in 2021 to 68 in 2022. | KCWP 2: Design and Deliver Instruction | Scope Magazine Middle Grades ELA teachers will use writing resources (such as Scope Magazine) to elevate student interest in current topics that may be used in creating informative and argumentative writing prompts and responses. Scope is aligned to ELA standards with leveled resources. |  |  | School $300 |  |
|  |  | No Red Ink ELA teacher will use the standards based program No Red Ink to help build stronger writers through interest-based curriculum, adaptive exercises, and actionable data. |  |  | School $500 |  |

## 3: Achievement Gap

## KRS 158.649 requires the school-based decision making (SBDM) council, or the principal if no council exists, to set the school's yearly targets for eliminating any achievement gap. The targets should be established with input from parents, faculty, and staff and submitted to the superintendent for consideration and the local board of education for adoption. In addition to being a statutory requirement, intentionally focusing on the achievement gaps that exist among a school’s underserved student populations is also a vital component of the continuous improvement process. Schools should use a variety of measures and analysis when conducting its review of its achievement gaps, including a review of the school’s climate and culture. Schools are not required to establish long term achievement gap goals; however, schools must establish yearly targets (objectives).

| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Decrease the number of economically disadvantaged students scoring novice on KPREP in elementary reading and math by 30%. (Reading 36.5 % in 2021 to 26% in 2022; Math 39.7% in 2021 to 27% in 2022) | KCWP 4: Review, Analyze, and Apply Data | Supplemental and ESS K-5 students scoring below grade level on MAP reading and math assessments will receive remediation through the use of Moby Max, Prodigy, Problem Attic, and/or Intervention Central. | Reduced achievement gaps |  | District Funding |
|  |  | RTI/CCEIS Coaching A district instructional coach will provide on-site coaching and monitoring of intervention instruction in reading. | Visits/observations |  | District Funding |
|  | KCWP 2: Design and Deliver | Reading Mastery |  |  |  |
|  |  | K-2 reading teachers will use the Reading Mastery program to provide direct instruction in an explicit, systematic approach to raise reading performance of their struggling readers. | Reading Mastery binder and progress data |  | District Funding |
|  |  | Save the Children Literacy Program Students who are performing below grade level in K-6th grade will be provided tutorials in phonics, sight word growth, comprehension, and vocabulary enhancement. | STC Instructor & data |  | STC Grant |
| Objective 2: Decrease the number of economically disadvantaged students scoring novice on KPREP in middle grades reading and math by 30%. (Reading 23.8% in 2021 to 17% in 2022; Math 33.6% in 2021 to 24% in 2022. | KCWP 4: Review, Analyze, and Apply Data | Blending Learning Reading and math teachers will incorporate blending learning strategies to engage all learners. (Use of technology platforms) | Observations/progress data |  | No Funding Needed |
|  |  | MAP Accelerator Math teachers in grades 6-8 will use Map Accelerator to differentiate instruction and provide tailored support based on pathways connected to the NWEA/MAP assessments. | NWEA reports/data |  | District |

## 4: Growth

| Goal 4 (State your growth goal.): Increase the number of students K-8 maintaining/making growth on the district MAP Assessment, thus increasing the percentage of students benchmarking in Reading and Math from Fall 2021 to Spring 2022. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1: Increase the composite benchmark percentage in reading from 47.39 in Fall 2021 to 53 in Spring 2022 (based on MAP Assessment). | KCWP 4 – Review, Analyze, and Apply Data | MAP Data Reading and math teachers along with school administrators will review and analyze data to determine group and individual needs and implications for instruction. | Elgin Graphic Organizer |  | No Funding Needed |  |
|  |  | SFA Reading Data Teachers and reading facilitators will gather reading data (fluency checks, read and respond, cycle assessments, etc.) and submit to SFA Facilitators in each school. Data will be used to adjust reading groups according to student needs. | Accurate student placement based on data Reading teachers and facilitators |  | District Funding |  |
|  | KCWP 5 – Design, Align, and Deliver Support | Save the Children Reading Intervention initiative to be implemented with K-6. | School Administrators and Save the Children instructor |  | STC Grant |  |
|  |  | Administration Observations with feedback Administrators will use a Google Form during weekly walkthroughs to provide immediate feedback to the teacher. Teachers will provide a reflection. | Google Form observation data spreadsheet |  | No Funding Needed |  |
| Objective 2: Increase the composite benchmark percentage in math from 41.3 in Fall 2021 to 48 in Spring 2022 (based on MAP Assessment) | KCWP 6- Establishing Learning Culture and Environment | MAP Goal Setting Teachers will conference with students to set goals for improving and planning ways to support academic growth. | Teachers, NWEA Reports |  | No Funding Needed |  |
|  |  | Progress Monitoring Parents will be informed of their child’s progress through the following: MAP individual reporting, KPREP, six weeks progress reports. Open House will be scheduled for the 1st, 3rd, & 5th six weeks of school if Covid guidelines do not prohibit it. | Improved parent communication |  | No Funding Needed |  |
|  |  | Social Media Teachers and administration will utilize the school webpage, school Facebook page, and Google Classroom to increase parent involvement and provide information about activities, instruction, and to make announcements. | Improved parent/community participation |  | No Funding Needed |  |

## 5: Transition Readiness

| Goal 5 (State your transition readiness goal.): |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1 |  |  |  |  |  |  |
| Objective 2 |  |  |  |  |  |  |

## 6: Graduation Rate

| Goal 6 (State your graduation rate goal.): |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1 |  |  |  |  |  |  |
| Objective 2 |  |  |  |  |  |  |

## 7: Other (Optional)

| Goal 7 (State your separate goal.): |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1 |  |  |  |  |  |  |
| Objective 2 |  |  |  |  |  |  |

## Special Considerations for Targeted Support and Improvement (TSI) including Additional Targeted Support and Improvement (ATSI) Schools

TSI schools (including ATSI schools) must embed their subgroup(s) plan for improvement within their CSIPs. TSI stakeholders, including the principal and other school leaders, teachers, and parents, should carefully consider what must be done to ensure the subgroup(s) perform(s) at high levels in the state accountability system. In addition to identifying strategies and activities within the CSIP that address the specific needs of underperforming groups, provide narrative information regarding the additional requirements for TSI schools in the following chart:

Components of Turnaround Leadership Development and Support:

Consider: How will you ensure that school leadership has or develops the skills and disposition to achieve accelerated, meaningful, and sustainable increases in student achievement for underperforming subgroups? Response:

Identification of Critical Resources Inequities:

Consider: Describe the process used to review the allocation and use of resources (people, time, and money), any resource inequities that were identified that may contribute to underperformance, and how identified resource inequities will be addressed. Response:

Targeted Subgroups and Evidence-Based Interventions:

Consider: Identify the areas of need revealed by the analysis of academic and non-academic data that will be addressed through CSIP activities for your targeted subgroup(s). What evidence-based practice(s) will the school incorporate that specifically targets the subgroup(s) achievement that contributed to the TSI identification? How will we monitor the evidence-based practice to ensure it is implemented with fidelity? Complete the table below to document the evidence that supports the Activities outlined in this plan. Additional rows may be added to accommodate additional pieces of evidence. Response: Evidence-based Activity; Evidence Citation; Uploaded in eProve. Train staff to implement inductive teaching strategies.; Hattie, J. (2009). Visible Learning: a synthesis of over 800 meta-analyses relating to achievement. Routledge: New York, NY.; ☒. ☐. ☐. ☐. ☐.

Additional Actions That Address the Causes of Consistently Underperforming Subgroups Of Students

Consider: Describe the process used to review the learning culture related to your targeted subgroup(s) and any additional actions that were determined to address the causes of underperformance. Response:

## Special Considerations for Comprehensive Support and Improvement (CSI) Schools

Schools identified for Comprehensive Support and Improvement (CSI) must complete the CSIP process and meet all applicable deadlines while identified for Comprehensive Support and Improvement (CSI). Following the completion of the school audit, CSI schools must revise their CSIP to account for the improvement priorities identified by the audit team.  The newly revised CSIP, referred to as a Turnaround Plan, must include the following items: (1) evidence-based interventions to be utilized to increase student performance and address the critical needs identified in the school audit, (2) a comprehensive list of persons and entities involved in the turnaround efforts and the specific roles each shall play in the school’s turnaround process, and (3) a review of resource inequities, which shall include an analysis of school level budgeting to ensure resources are adequately channeled towards school improvement (703 KAR 5:280). Each of the three aforementioned requirements must be embedded throughout the CSIP document. Once the CSIP has been revised, the turnaround plan must be submitted to the LEA for approval before it is submitted to the Commissioner of Education for final approval.

## Evidence-based Practices

The Every Student Succeeds Act (2015) created new expectations for evidence-based decision making at school and district levels. More specific information regarding evidence-based practices and requirements can be found on the Kentucky Department of Education’s Evidence-based Practices website. While evidence documentation in the CSIP is only required for schools identified for Targeted Support and Improvement (TSI) and Comprehensive Support and Improvement (CSI), KDE encourages all school leaders to review evidence related to new programs, practices, or interventions being implemented in the school. In addition to documenting the evidence below, TSI and CSI schools are expected to upload a description of their evidence review process, the findings of their evidence review, and a discussion of the local implications into eProve. Specific directions regarding the documentation requirements can be found in the “Documenting Evidence under ESSA” resource available on KDE’s Evidence-based Practices website.

Complete the table below to document the evidence that supports the Activities outlined in this plan. Additional rows may be added to accommodate additional pieces of evidence.

| Evidence-based Activity | Evidence Citation | Uploaded in eProve |
| --- | --- | --- |
| Train staff to implement inductive teaching strategies. | Hattie, J. (2009). Visible Learning: a synthesis of over 800 meta-analyses relating to achievement. Routledge: New York, NY. | ☒ |
|  |  | ☐ |
|  |  | ☐ |
|  |  | ☐ |
|  |  | ☐ |