## FINAL Recommendation
Assumptions:
Debt Service |  | Maintain $2.24/$1,000 AV through 2027
Rate drops to $1.50/$1,000 AV in 2028
4.2% AV Growth 2018
4.3% AV Growth 2019
4.4% AV Growth 2020
4.4% AV Growth 2021
3.5% AV Growth 2022-2038
Bond Proceeds |  | 408000000
FINAL BOND ADVISORY COMMITTEE RECOMMENDATION
April 12th Bond Advisory Committee Meeting
$2.24/$1,000 AV
|  | Description | Totals based on Escalation
1 | Safety & Security |  | 68254830 | 16.72%
|  | School Safety Upgrades | 11465846
|  | School Seismic Upgrades | 45164771
|  | Parent/Bus Drop-Off Improvements | 9179025
|  | Playground Upgrades | 1701000
|  | Install Cameras and GPS on All Buses | 744188
2 | Educational Technology |  | 30221197.99 | 7.403%
|  | Technology-Classroom | 14288697.99
|  | Technology-Infrastructure | 15932500
3 | New Capacity |  | 178455286 | 43.71%
|  | New Elementary School in North Plains | 38587500
|  | New Elementary School in South Hillsboro 1 | 38587500
|  | Evergreen Middle School Addition | 18786600
|  | Glencoe Addition | 18600276
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 20400000
|  | Construct New Modular Cafeteria/Kitchen-Reedville Elementary | 1500000
|  | Brookwood Elementary | 41993410
4 | Student Achievement |  | 24000000 | 5.879%
|  | High School Career/Technical Education (CTE) Investment | 14000000
|  | Flexible Classroom Furniture | 10000000
5 | Current Infrastructure Improvements |  | 89735218 | 21.98%
|  | Hillsboro High School Remodel | 11011248
|  | Roofing | 19486385
|  | Add Air Conditioning | 11822270
|  | Upgrade HVAC | 3488307
|  | Add Heat to HVAC | 194378
|  | Water Pipe Replacement | 3487086
|  | Boiler Replacement | 2619705
|  | Direct Digital Controls (DDC) | 4657735
|  | Walk-In Freezer | 86392
|  | Upgrade Electrical Service/Generator | 554112
|  | New Parking Lot - Reedville | 1300000
|  | Rooftop Condensor Replacement | 114604
|  | Chiller Replacement | 957211
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 4429695
|  | Replace Flooring - Reedville | 350000
|  | Construct New Track | 1823259
|  | Satellite Transportation Facility | 16352831
|  | Construction of Lighted Turf Fields and other Athletic Field Improvements | 7000000
|  | TOTALS | 390666531.99
6 | Bond Issuance Cost (1.5%) |  | 5859997.9798 | 1.435%
7 | District Bond Costs (3.0%) |  | 11719995.9597 | 2.871%
|  |  | 408246525.9295 | 100%
|  | Mandatory Items: Life/Safety and Capacity/Bond Program Costs | 188772486.9395
|  | Strongly Recommended: Necessary Infrastructure not possible from General Fund | 41946007
|  | TOTAL Mandatory/Strongly Recommended | 230718493.9395
$2.24 Bond Package |  |  | Priority Projects if Money is available:
* Funding Level - $408.0 Million |  |  | * Pavement/Sidewalk/Hardscape Replacement
* Notable Projects: Two new Elementary Schools (N. Plains |  |  | * Add Resurface/Replace Tennis Courts
and S. Hillsboro), satellite transportation facility, Hilhi |  |  | * Replace Single Pane Windows
upgrade and Glencoe and Evergreen Addition |  |  | * Replace additional Portable Buildings w/ Permanent Structures
* Improvements to Hillsboro High School and Reedville Elementary |  |  | * Land Purchase for future school sites
* All Seismic and Safety Upgrades |  |  | * Upgrade new gymnasiums to "immediate occupancy" seismic standard
* All Parent/Bus Drop-off Improvements
* Install Cameras on All Buses
* All Playground Upgrades
* All Classroom and Technology Infrastructure
* All Mechanical/Electrical/Plumbing Upgrades
* Construct New Gymnasiums at Elementary Schools
* CTE Investments at High Schools
* Replace portable classrooms in "poorest" condition on District inventory
* Construct Lighted Turf Fields at Century, Hilhi and Glencoe

## FINAL Bond Package by Bldg
| Column | 1 |  |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Row | School/Facility | School Safety and Security Enhancements | Distributed Antennae System | Entry Vestibule | School Seismic Upgrades | Parent/Bus Drop-Off Improvements | Install Cameras on all Buses | Playground Replacements | Technology | Convert Secondary Libraries to Instructional Learning Centers | Capacity | CTE Infrastructure | Replace Classroom Furniture | Roofing | Add AC | Upgrade HVAC | Add Heat to HVAC | Water Pipe Replacement | Boiler Replacement | DDC | Walk-In Freezer | Upgrade Electrical Service/ Generator | Pavement/ Sidewalks/ Hardscape | Rooftop Condenser Replacement | Chiller Replacement | Tennis Court Resurface/ Replacement | Athletic Field Drainage/Repair Irrigation/Storm Drain | New Artificial Turf Field | Replace Gym Bleachers | Remodel Grandstands/ Lockerrooms/ Restrooms | Remodel Health Rooms | Building Brick Sealer | Paint Building Exterior | Replace Windows | Replace Maintenance Equipment and Vehicles | Replace Gym Floor/Other Flooring | Construct New Track | Replace Scoreboards | Replace Portable Classrooms w/ Permanent Structures | Replacements | Construct New Gymnasium-Eliminate Cafeteria/Gymnasium | Other | TOTALS | School/Facility
3 | Brookwood Elementary School | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41993410 | 0 | 0 | 41993410 | Brookwood
4 | Butternut Creek Elementary School | 200501 |  |  | 477509 | 1209437 | 0 | 189000 | 340759.92 | 0 | 0 | 0 | 205492.8906 | 83259.0138 | 658374.7248 | 0 | 0 | 311261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295313 | 0 | 0 | 0 | 3970907.5492 | Butternut Creek
5 | Eastwood Elementary School | 278154 |  |  | 1773834 | 744188 | 0 | 189000 | 337597.19 | 0 | 0 | 0 | 244640.0281 | 1013331.8136 | 0 | 0 | 60673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295313 | 0 | 2550000 | 0 | 7486731.0317 | Eastwood
6 | Farmington View Elementary School | 196796 |  |  | 903879 | 1182431 | 0 | 189000 | 207473.08 | 0 | 0 | 0 | 157440.1535 | 67429.3234 | 418913.6038 | 0 | 0 | 165484 | 161178 | 260796 | 50109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295313 | 0 | 0 | 0 | 4256242.1607 | Farmington View
7 | Free Orchards Elementary School | 258150 |  |  | 0 | 0 | 0 | 0 | 284304.28 | 0 | 0 | 0 | 198826.6626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741280.9426 | Free Orchards
8 | Groner K-8 | 218791 |  |  | 2191401 | 0 | 0 | 189000 | 214487.04 | 0 | 0 | 0 | 112295.2776 | 96007.8184 | 0 | 0 | 0 | 202761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3224743.136 | Groner
9 | Imlay Elementary School | 281303 |  |  | 0 | 0 | 0 | 0 | 491341.81 | 0 | 0 | 0 | 273290.0938 | 116884.5515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1162819.4553 | Imlay
10 | Indian Hills Elementary School | 178737 |  |  | 592216 | 0 | 0 | 0 | 332245.52 | 0 | 0 | 0 | 238326.0268 | 0 | 831736.5161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295313 | 0 | 0 | 0 | 2468574.0629 | Indian Hills
11 | Jackson Elementary School | 283942 |  |  | 1238588 | 826875 | 0 | 0 | 380674.5 | 0 | 0 | 0 | 283869.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550000 | 0 | 5563949.4375 | Jackson
12 | Ladd Acres Elementary School | 448001 |  |  | 503592 | 1103051 | 0 | 189000 | 366755.13 | 0 | 0 | 0 | 269549.2972 | 0 | 1477734.803 | 0 | 0 | 165297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550000 | 0 | 7072980.2302 | Ladd Acres
13 | Lenox Elementary School | 504678 |  |  | 715020 | 1212199 | 0 | 0 | 331976.41 | 0 | 0 | 0 | 238517.1023 | 317669.6286 | 1118703.7117 | 0 | 68498 | 0 | 0 | 456435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4963696.8525 | Lenox
14 | Lincoln Street Elementary School | 286130 |  |  | 0 | 0 | 0 | 0 | 337189.33 | 0 | 0 | 0 | 263179.5655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 886498.8955 | Lincoln Street
15 | McKinney Elementary School | 254381 |  |  | 1689555 | 744188 | 0 | 0 | 308403.59 | 0 | 0 | 0 | 235585.082 | 70627.8347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590626 | 0 | 2550000 | 0 | 6443366.5068 | McKinney
16 | Minter Bridge Elementary School | 234933 |  |  | 2280979 | 694575 | 0 | 0 | 348420.37 | 0 | 0 | 0 | 241180.354 | 102644.6162 | 0 | 0 | 65207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295313 | 0 | 2550000 | 0 | 6813252.3403 | Minter Bridge
17 | Mooberry Elementary School | 218791 |  |  | 1332341 | 0 | 0 | 189000 | 357188.73 | 0 | 0 | 0 | 232310.7182 | 102924.2032 | 975162.5508 | 0 | 0 | 497370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295313 | 0 | 2550000 | 0 | 6750401.2022 | Mooberry
18 | North Plains Elementary School | 228515 |  |  | 2704402 | 0 | 0 | 0 | 277501.68 | 0 | 0 | 0 | 166479.7256 | 707915.1526 | 0 | 0 | 0 | 0 | 0 | 334785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550000 | 0 | 6969598.5582 | North Plains
19 | Orenco Elementary School | 313601 |  |  | 0 | 0 | 0 | 0 | 395982.29 | 0 | 0 | 0 | 332643.1884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099528.4784 | Orenco
20 | Patterson Elementary School | 289290 |  |  | 0 | 0 | 0 | 0 | 398868.84 | 0 | 0 | 0 | 230448.0068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975908.8468 | Patterson
21 | Quatama Elementary School | 288075 |  |  | 0 | 0 | 0 | 0 | 320483.98 | 0 | 0 | 0 | 252098.5605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860657.5405 | Quatama
22 | Reedville Elementary School | 305421 |  |  | 1160508 | 0 | 0 | 189000 | 198089.64 | 0 | 0 | 0 | 122064.2859 | 316589.2827 | 654057.124 | 0 | 0 | 0 | 0 | 182413 | 0 | 53380 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 1476565 | 0 | 1500000 | 0 | 7808087.3326 | Reedville
23 | Rosedale Elementary School | 276953 |  |  | 0 | 0 | 0 | 0 | 297315.18 | 0 | 0 | 0 | 221261.8337 | 60798.8592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856328.8729 | Rosedale
24 | Tobias Elementary School | 218244 |  |  | 0 | 303877 | 0 | 0 | 413457.18 | 0 | 0 | 0 | 221953.6587 | 1503698.4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2661230.2712 | Tobias
25 | West Union Elementary School | 317794 |  |  | 1360381 | 0 | 0 | 189000 | 280138.1 | 0 | 0 | 0 | 202175.6996 | 126542.5174 | 845536.9996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3321568.3166 | West Union
26 | Witch Hazel Elementary School | 310136 |  |  | 0 | 0 | 0 | 0 | 375707.9 | 0 | 0 | 0 | 275993.4275 | 134128.4633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095965.7908 | Witch Hazel
27 | WL Henry Elementary School | 419897 |  |  | 609594 | 1158204 | 0 | 189000 | 338638.41 | 0 | 0 | 0 | 173970.9276 | 87233.854 | 919953.2838 | 0 | 0 | 618790 | 371987 | 667523 | 0 | 52708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590626 | 0 | 2550000 | 0 | 8748125.4754 | WL Henry
28 | South Meadows Middle School | 368845 |  |  | 0 | 0 | 0 | 0 | 404666.86 | 0 | 0 | 0 | 370549.1589 | 73591.0948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1424729.1137 | South Meadows
29 | Poynter Middle School | 410963 |  |  | 11311973 | 0 | 0 | 0 | 528262.32 | 0 | 0 | 0 | 381104.8501 | 1313192.9275 | 2070363.643 | 858551 | 0 | 669122 | 761807 | 1234438 | 36283 | 65555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19641615.7406 | Poynter
30 | Brown Middle School | 368845 |  |  | 2520000 | 0 | 0 | 0 | 466157.2 | 0 | 0 | 0 | 364016.9556 | 1391837.3987 | 1278520.937 | 747494 | 0 | 616092 | 587447 | 1101704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9442114.4913 | Brown
31 | Evergreen Middle School | 356083 |  |  | 1621827 | 0 | 0 | 0 | 540834.34 | 0 | 18786600 | 0 | 423521.0961 | 2637477.0435 | 0 | 764543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25130885.4796 | Evergreen
32 | Century High School | 643246 |  |  | 0 | 0 | 0 | 0 | 1099137.83 | 0 | 0 | 3500000 | 816249.0507 | 2714335.4154 | 0 | 111049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11217350.6295 | Century
33 | Glencoe High School | 470374 |  |  | 2049450 | 0 | 0 | 0 | 1209444.11 | 0 | 18600276 | 3500000 | 808301.7568 | 1776436.8943 | 0 | 564293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31311909.0944 | Glencoe
34 | Hillsboro High School | 568871 |  |  | 3272743 | 0 | 0 | 0 | 1007841.15 | 0 | 11011248 | 3500000 | 660571.1685 | 2960543.8771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83990 | 0 | 0 | 0 | 0 | 0 | 2333333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1823259 | 0 | 0 | 0 | 0 | 0 | 27222400.529 | Hilhi
35 | Liberty High School | 548099 |  |  | 0 | 0 | 0 | 0 | 970178.08 | 0 | 0 | 3500000 | 782093.4594 | 104087.7918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6861669.3312 | Liberty
36 | Miller-Big Picture | 226476 |  |  | 3838888 | 0 | 0 | 0 | 61541 | 0 | 0 | 0 | 0 | 625115.7835 | 0 | 171482 | 0 | 181005 | 737286 | 284483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6126276.7835 | Miller Ed West
37 | Miller Ed-East Campus | 179573 |  |  | 328557 | 0 | 0 | 0 | 65635 | 0 | 0 | 0 | 0 | 190708.1831 | 573212.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1337685.2854 | Miller Ed East
38 | Peter Boscow | 91127 |  |  | 687534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615952.7498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394613.7498 | Peter Boscow
39 | Transportation | 0 |  |  | 0 | 0 | 744188 | 0 | 0 | 0 | 0 | 0 | 0 | 175420.4753 | 0 | 270895 | 0 | 0 | 0 | 135158 | 0 | 91402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417063.4753 | Transportation
40 | Admin Center | 322963 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322963 | Admin Center
41 | Hare Field | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59904 | Hare Field
42 | Facilities | 99167 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99167 | Facilities
43 | Districtwide Technology | 0 |  |  | 0 | 0 | 0 | 0 | 15932500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15932500 | Districtwide Technology
44 | New Elementary School #1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38587500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38587500 | New Elementary School #1
45 | New Elementary School #2 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 38587500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38587500 | New Elementary School #2
46 | Satellite Transportation/Maintenance Facility | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16352831 | 16352831 | Satellite Transportation/Maintenance Facility
| TOTALS | 11465846 |  |  | 45164771 | 9179025 | 744188 | 1701000 | 30221197.99 | 0 | 125573124 | 14000000 | 10000000 | 19486385 | 11822270 | 3488307 | 194378 | 3487086 | 2619705 | 4657735 | 86392 | 554112 | 1300000 | 114604 | 957211 | 0 | 0 | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 1823259 | 0 | 4429695 | 41993410 | 21900000 | 16352831 | 390666531.99
0

## New Elementary #1
FINAL BOND RECOMMENDATION - New Elementary #1 |  | Begin | Project
New Capacity |  | Pre-Design | Complete
New Elementary School #1 | 38587500 | Nov, 2018 | July, 2021
TOTALS | 38587500
0

## New Elementary #2
FINAL BOND RECOMMENDATION - New Elementary #2 |  | Begin | Project
New Capacity |  | Pre-Design | Complete
New Elementary School #2 | 38587500 | Nov, 2019 | July, 2022
TOTALS | 38587500
0

## Brookwood ES
FINAL BOND RECOMMENDATION - BROOKWOOD |  | Begin | Project
New Capacity |  | Pre-Design | Complete
Replace Brookwood Elementary | 41993410 | Dec, 2017 | July, 2020
TOTALS | 41993410
0

## Butternut Creek ES
|  | FINAL BOND RECOMMENDATION - BUTTERNUT CREEK |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 200501
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Strobes, Visuail Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Security Fencing |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 477509 | Jul, 2019 | Aug, 2020
| Parent/Bus Drop-Off Improvements |  | 1209437 | Jul, 2019 | Aug, 2020
| Playground Upgrades |  | 189000 | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 340759.92
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 205492.8906
Current Infrastructure Improvements
|  | Roofing | 83259.0138 | Jul, 2019 | Aug, 2020
|  | Add Air Conditioning | 658374.7248 | Jul, 2019 | Aug, 2020
|  | Water Pipe Replacement | 311261 | Jul, 2019 | Aug, 2020
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 295313 | Jul, 2019 | Aug, 2020
|  | TOTALS | 3970907.5492
0

## Eastwood ES
|  | FINAL BOND RECOMMENDATION - EASTWOOD |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 278154
|  | Interior Door Locks - Classrooms |  | Jun, 2018 | Aug, 2019
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jun, 2018 | Aug, 2019
|  | Strobes, Visuail Warning Inside and Outside |  | Jun, 2018 | Aug, 2019
|  | Security Cameras |  | Jun, 2018 | Aug, 2019
|  | Improve Line of Sight From Office to Front Door |  | Jun, 2018 | Aug, 2019
|  | Card Key Access - Exterior Doors |  | Jun, 2018 | Aug, 2019
|  | Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Fire Doors on Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Main Door |  | Jun, 2018 | Aug, 2019
|  | Glas Film at Other Windows |  | Jun, 2018 | Aug, 2019
|  | Upgrade In Building Radio Communication |  | Jun, 2018 | Aug, 2019
| School Seismic Upgrades |  | 1773834 | Jun, 2018 | Aug, 2019
| Parent/Bus Drop-Off Improvements |  | 744188 | Oct, 2017 | Aug, 2018
| Playground Upgrades |  | 189000 | Jun, 2018 | Aug, 2019
Educational Technology
| Technology-Classroom |  | 337597.19
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 244640.0281
Current Infrastructure Improvements
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 2550000 | Jun, 2018 | Aug, 2019
|  | Roofing | 1013331.8136 | Jun, 2018 | Aug, 2019
|  | Add Heat to HVAC | 60673 | Jun, 2018 | Aug, 2019
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 295313 | Jun, 2018 | Aug, 2019
|  | TOTALS | 7486731.0317
0

## Farmington View ES
|  | FINAL BOND RECOMMENDATION - FARMINGTON VIEW |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 196796
|  | Interior Door Locks - Classrooms |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 903879 | Jul, 2019 | Aug, 2020
| Parent/Bus Drop-Off Improvements |  | 1182431 | Jul, 2019 | Aug, 2020
| Playground Upgrades |  | 189000 | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 207473.08
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 157440.1535
Current Infrastructure Improvements
|  | Roofing | 67429.3234 | Jul, 2019 | Aug, 2020
|  | Add Air Conditioning | 418913.6038 | Jul, 2019 | Aug, 2020
|  | Water Pipe Replacement | 165484 | Jul, 2019 | Aug, 2020
|  | Boiler Replacement | 161178 | Jul, 2019 | Aug, 2020
|  | Direct Digital Controls (DDC) | 260796 | Jul, 2019 | Aug, 2020
|  | Walk-In Freezer | 50109 | Jul, 2019 | Aug, 2020
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 295313 | Oct, 2017 | Aug, 2018
|  | TOTALS | 4256242.1607
0

## Free Orchards ES
|  | FINAL BOND RECOMMENDATION - FREE ORCHARDS |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 258150
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2021 | Aug, 2022
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2021 | Aug, 2022
|  | Security Cameras |  | Jul, 2021 | Aug, 2022
|  | Card Key Access - Exterior Doors |  | Jul, 2021 | Aug, 2022
|  | Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Main Door |  | Jul, 2021 | Aug, 2022
|  | Upgrade In Building Radio Communication |  | Jul, 2021 | Aug, 2022
|  | Improve In Building Public Safety Communication Capability |  | Jul, 2021 | Aug, 2022
Educational Technology
| Technology-Classroom |  | 284304.28
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 198826.6626
|  | TOTALS | 741280.9426
0

## Groner K-8
|  | FINAL BOND RECOMMENDATION - GRONER |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 218791
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 2191401 | Jul, 2019 | Aug, 2020
| Playground Upgrades |  | 189000 | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 214487.04
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 112295.2776
Current Infrastructure Improvements
|  | Roofing | 96007.8184 | Jul, 2019 | Aug, 2020
|  | Water Pipe Replacement | 202761 | Jul, 2019 | Aug, 2020
|  | TOTALS | 3224743.136
0

## Imlay ES
|  | FINAL BOND RECOMMENDATION - IMLAY |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 281303
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
|  | Improve In Building Public Safety Communication Capability |  | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 491341.81
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 273290.0938
Current Infrastructure Improvements
|  | Roofing | 116884.5515 | Jul, 2019 | Aug, 2020
|  | TOTALS | 1162819.4553
0

## Indian Hills ES
|  | FINAL BOND RECOMMENDATION - INDIAN HILLS |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 178737
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 592216 | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 332245.52
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 238326.0268
Current Infrastructure Improvements
|  | Add Air Conditioning | 831736.5161 | Jul, 2019 | Aug, 2020
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 295313 | Jul, 2019 | Aug, 2020
|  | TOTALS | 2468574.0629
0

## Jackson ES
|  | FINAL BOND RECOMMENDATION - JACKSON |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 283942
|  | Interior Door Locks - Classrooms |  | Jul, 2019 | Aug, 2020
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Other Windows |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 1238588 | Jul, 2019 | Aug, 2020
| Parent/Bus Drop-Off Improvements |  | 826875 | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 380674.5
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 283869.9375
Current Infrastructure Improvements
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 2550000 | Jul, 2019 | Aug, 2020
|  | TOTALS | 5563949.4375
0

## Ladd Acres ES
|  | FINAL BOND RECOMMENDATION - LADD ACRES |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 448001
|  | Upgrade PA System |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Security Fencing |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 503592 | Jul, 2019 | Aug, 2020
| Parent/Bus Drop-Off Improvement |  | 1103051 | Oct, 2017 | Aug, 2018
| Playground Upgrades |  | 189000 | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 366755.13
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 269549.2972
Current Infrastructure Improvements
|  | Add Air Conditioning | 1477734.803 | Jul, 2019 | Aug, 2020
|  | Water Pipe Replacement | 165297 | Oct, 2017 | Aug, 2018
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 2550000 | Jul, 2019 | Aug, 2020
|  | TOTALS | 7072980.2302
0

## Lenox ES
|  | FINAL BOND RECOMMENDATION - LENOX |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 504678
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jun, 2018 | Aug, 2019
|  | Stobes, Visual Warning Inside and Outside |  | Jun, 2018 | Aug, 2019
|  | Security Cameras |  | Jun, 2018 | Aug, 2019
|  | Improve Line of Sight From Office to Front Door |  | Jun, 2018 | Aug, 2019
|  | Card Key Access - Exterior Doors |  | Jun, 2018 | Aug, 2019
|  | Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Security Fencing |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Main Door |  | Jun, 2018 | Aug, 2019
|  | Upgrade In Building Radio Communication |  | Jun, 2018 | Aug, 2019
| School Seismic Upgrades |  | 715020 | Jun, 2018 | Aug, 2019
| Parent/Bus Drop-Off Improvement |  | 1212199 | Jun, 2018 | Aug, 2019
Educational Technology
| Technology-Classroom |  | 331976.41
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 238517.1023
Current Infrastructure Improvements
|  | Roofing | 317669.6286 | Jun, 2018 | Aug, 2019
|  | Add Air Conditioning | 1118703.7117 | Jun, 2018 | Aug, 2019
|  | Add Heat to HVAC | 68498 | Jun, 2018 | Aug, 2019
|  | Direct Digital Controls (DDC) | 456435 | Jun, 2018 | Aug, 2019
|  | TOTALS | 4963696.8525
0

## Lincoln Street ES
|  | FINAL BOND RECOMMENDATION - LINCOLN STREET |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 286130
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2021 | Aug, 2022
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2021 | Aug, 2022
|  | Security Cameras |  | Jul, 2021 | Aug, 2022
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2021 | Aug, 2022
|  | Card Key Access - Exterior Doors |  | Jul, 2021 | Aug, 2022
|  | Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Main Door |  | Jul, 2021 | Aug, 2022
|  | Upgrade In Building Radio Communication |  | Jul, 2021 | Aug, 2022
|  | Improve In Building Public Safety Communication Capability |  | Jul, 2021 | Aug, 2022
Educational Technology
| Technology-Classroom |  | 337189.33
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 263179.5655
|  | TOTALS | 886498.8955
0

## McKinney ES
|  | FINAL BOND RECOMMENDATION - MCKINNEY |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 254381
|  | Interior Door Locks - Classrooms |  | Jul, 2019 | Aug, 2020
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Other Windows |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 1689555 | Jul, 2019 | Aug, 2020
| Parent/Bus Drop-Off Improvement |  | 744188 | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 308403.59
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 235585.082
Current Infrastructure Improvements
|  | Roofing | 70627.8347 | Jul, 2019 | Aug, 2020
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 590626 | Oct, 2017 | Aug, 2018
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 2550000 | Jul, 2019 | Aug, 2020
|  | TOTALS | 6443366.5068
0

## Minter Bridge ES
|  | FINAL BOND RECOMMENDATION - MINTER BRIDGE |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 234933
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Other Windows |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 2280979 | Jul, 2019 | Aug, 2020
| Parent/Bus Drop-Off Improvement |  | 694575 | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 348420.37
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 241180.354
Current Infrastructure Improvements
|  | Roofing | 102644.6162 | Jul, 2019 | Aug, 2020
|  | Add Heat to HVAC | 65207 | Jul, 2019 | Aug, 2020
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 295313 | Jul, 2019 | Aug, 2020
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 2550000 | Jul, 2019 | Aug, 2020
|  | TOTALS | 6813252.3403
0

## Mooberry ES
|  | FINAL BOND RECOMMENDATION - MOOBERRY |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 218791
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Other Windows |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 1332341 | Jul, 2019 | Aug, 2020
| Playground Upgrades |  | 189000 | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 357188.73
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 232310.7182
Current Infrastructure Enhancements
|  | Roofing | 102924.2032 | Jul, 2019 | Aug, 2020
|  | Add Air Conditioning | 975162.5508 | Jul, 2019 | Aug, 2020
|  | Water Pipe Replacement | 497370 | Jul, 2019 | Aug, 2020
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 295313 | Jul, 2019 | Aug, 2020
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 2550000 | Jul, 2019 | Aug, 2020
|  | TOTALS | 6750401.2022
0

## North Plains ES
|  | FINAL BOND RECOMMENDATION - NORTH PLAINS |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 228515
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Upgrade PA System |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 2704402 | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 277501.68
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 166479.7256
Current Infrastructure Improvements
|  | Roofing | 707915.1526 | Jul, 2019 | Aug, 2020
|  | Direct Digital Controls (DDC) | 334785 | Jul, 2019 | Aug, 2020
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 2550000 | Jul, 2019 | Aug, 2020
|  | TOTALS | 6969598.5582
0

## Orenco ES
|  | FINAL BOND RECOMMENDATION - ORENCO |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 313601
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2021 | Aug, 2022
|  | Security Cameras |  | Jul, 2021 | Aug, 2022
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2021 | Aug, 2022
|  | Card Key Access - Exterior Doors |  | Jul, 2021 | Aug, 2022
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Security Fencing |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Main Door |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Other Windows |  | Jul, 2021 | Aug, 2022
|  | Upgrade In Building Radio Communication |  | Jul, 2021 | Aug, 2022
|  | Improve In Building Public Safety Communication Capability |  | Jul, 2021 | Aug, 2022
Educational Technology
| Technology-Classroom |  | 395982.29
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 332643.1884
Current Infrastructure Improvements
|  | Rooftop Condensor Replacement | 57302
|  | TOTALS | 1099528.4784
0

## Patterson ES
|  | FINAL BOND RECOMMENDATION - PATTERSON |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 289290
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2021 | Aug, 2022
|  | Security Cameras |  | Jul, 2021 | Aug, 2022
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2021 | Aug, 2022
|  | Card Key Access - Exterior Doors |  | Jul, 2021 | Aug, 2022
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Main Door |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Other Windows |  | Jul, 2021 | Aug, 2022
|  | Upgrade In Building Radio Communication |  | Jul, 2021 | Aug, 2022
|  | Improve In Building Public Safety Communication Capability |  | Jul, 2021 | Aug, 2022
Educational Technology
| Technology-Classroom |  | 398868.84
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 230448.0068
Current Infrastructure Improvements
|  | Rooftop Condensor Replacement | 57302 | Jul, 2021 | Aug, 2022
|  | TOTALS | 975908.8468
0

## Quatama ES
|  | FINAL BOND RECOMMENDATION - QUATAMA |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 288075
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2021 | Aug, 2022
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2021 | Aug, 2022
|  | Security Cameras |  | Jul, 2021 | Aug, 2022
|  | Card Key Access - Exterior Doors |  | Jul, 2021 | Aug, 2022
|  | Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Main Door |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Other Windows |  | Jul, 2021 | Aug, 2022
|  | Upgrade In Building Radio Communication |  | Jul, 2021 | Aug, 2022
|  | Improve In Building Public Safety Communication Capability |  | Jul, 2021 | Aug, 2022
Educational Technology
| Technology-Classroom |  | 320483.98
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 252098.5605
|  | TOTALS | 860657.5405
0

## Reedville ES
|  | FINAL BOND RECOMMENDATION - REEDVILLE |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 305421
Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc)
Stobes, Visual Warning Inside and Outside
Security Cameras
Improve Line of Sight From Office to Front Door
Card Key Access - Exterior Doors
Alert Button at Front Desk
Glass Film at Main Door
Upgrade In Building Radio Communication
| School Seismic Upgrades |  | 1160508
| Playground Upgrades |  | 189000
Educational Technology
| Technology-Classroom |  | 198089.64
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 122064.2859
Current Infrastructure Improvements
|  | Roofing | 316589.2827 | Oct, 2017 | Aug, 2018
|  | Add Air Conditioning | 654057.124 | Oct, 2017 | Aug, 2018
|  | Direct Digital Controls (DDC) | 182413 | Oct, 2017 | Aug, 2018
|  | Upgrade Electrical Service/Generator | 53380 | Oct, 2017 | Aug, 2018
|  | Construct New Parking Lot | 1300000 | Oct, 2017 | Aug, 2018
|  | Replacing Flooring | 350000 | Oct, 2017 | Aug, 2018
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 1476565 | Oct, 2017 | Aug, 2018
|  | New Modular Cafeteria w/ Kitchen | 1500000 | Oct, 2017 | Aug, 2018
|  | TOTALS | 7808087.3326
0

## Rosedale ES
|  | FINAL BOND RECOMMENDATION - ROSEDALE |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 276953
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Other Windows |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
|  | Improve In Building Public Safety Communication Capability |  | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 297315.18
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 221261.8337
Current Infrastructure Improvements
|  | Roofing | 60798.8592 | Jul, 2019 | Aug, 2020
|  | TOTALS | 856328.8729
0

## Tobias ES
|  | FINAL BOND RECOMMENDATION - TOBIAS |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 218244
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| Parent/Bus Drop-Off Improvement |  | 303877 | Jul, 2019 | Aug, 2020
Educational Technology
| Technology-Classroom |  | 413457.18
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 221953.6587
Current Infrastructure Improvements
|  | Roofing | 1503698.4326 | Jul, 2019 | Aug, 2020
|  | TOTALS | 2661230.2712
0

## West Union ES
|  | FINAL BOND RECOMMENDATION - WEST UNION |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 317794
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jun, 2018 | Aug, 2019
|  | Stobes, Visual Warning Inside and Outside |  | Jun, 2018 | Aug, 2019
|  | Security Cameras |  | Jun, 2018 | Aug, 2019
|  | Improve Line of Sight From Office to Front Door |  | Jun, 2018 | Aug, 2019
|  | Card Key Access - Exterior Doors |  | Jun, 2018 | Aug, 2019
|  | Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Main Door |  | Jun, 2018 | Aug, 2019
|  | Upgrade In Building Radio Communication |  | Jun, 2018 | Aug, 2019
| School Seismic Upgrades |  | 1360381 | Jun, 2018 | Aug, 2019
| Playground Upgrades |  | 189000 | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 280138.1
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 202175.6996
Current Infrastructure Improvements
|  | Roofing | 126542.5174 | Jun, 2018 | Aug, 2019
|  | Add Air Conditioning | 845536.9996 | Jun, 2018 | Aug, 2019
|  | TOTALS | 3321568.3166
0

## Witch Hazel ES
|  | FINAL BOND RECOMMENDATION - WITCH HAZEL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 310136
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2021 | Aug, 2022
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2021 | Aug, 2022
|  | Security Cameras |  | Jul, 2021 | Aug, 2022
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2021 | Aug, 2022
|  | Card Key Access - Exterior Doors |  | Jul, 2021 | Aug, 2022
|  | Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Main Door |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Other Windows |  | Jul, 2021 | Aug, 2022
|  | Upgrade In Building Radio Communication |  | Jul, 2021 | Aug, 2022
|  | Improve In Building Public Safety Communication Capability |  | Jul, 2021 | Aug, 2022
Educational Technology
| Technology-Classroom |  | 375707.9
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 275993.4275
Current Infrastructure Improvements
|  | Roofing | 134128.4633 | Jul, 2021 | Aug, 2022
|  | TOTALS | 1095965.7908
0

## WL Henry ES
|  | FINAL BOND RECOMMENDATION - WL HENRY |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 419897
|  | Interior Door Locks - Classrooms |  | Jul, 2019 | Aug, 2020
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2019 | Aug, 2020
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2019 | Aug, 2020
|  | Security Cameras |  | Jul, 2019 | Aug, 2020
|  | Improve Line of Sight From Office to Front Door |  | Jul, 2019 | Aug, 2020
|  | Card Key Access - Exterior Doors |  | Jul, 2019 | Aug, 2020
|  | Alert Button at Front Desk |  | Jul, 2019 | Aug, 2020
|  | Glass Film at Main Door |  | Jul, 2019 | Aug, 2020
|  | Upgrade In Building Radio Communication |  | Jul, 2019 | Aug, 2020
| School Seismic Upgrades |  | 609594 | Jul, 2019 | Aug, 2020
| Parent/Bus Drop-Off Improvement |  | 1158204 | Jul, 2019 | Aug, 2020
| Playground Upgrades |  | 189000 | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 338638.41
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Elementary Gymnasium Audio/Visual System
Student Achievement
|  | Flexible Classroom Furniture | 173970.9276
Current Infrastructure Improvements
|  | Roofing | 87233.854 | Jul, 2019 | Aug, 2020
|  | Add Air Conditioning | 919953.2838 | Jul, 2019 | Aug, 2020
|  | Water Pipe Replacement | 618790 | Jul, 2019 | Aug, 2020
|  | Boiler Replacement | 371987 | Jul, 2019 | Aug, 2020
|  | Direct Digital Controls (DDC) | 667523 | Jul, 2019 | Aug, 2020
|  | Upgrade Electrical Service/Generator | 52708 | Jul, 2019 | Aug, 2020
|  | Replace "Poor" condition Portable Buildings w/ Permanent Structures | 590626 | Oct, 2017 | Aug, 2018
|  | Construct New Gymnasiums-Eliminate Gymacafetoriums | 2550000 | Jul, 2019 | Aug, 2020
|  | TOTALS | 8748125.4754
0

## South Meadows MS
|  | FINAL BOND RECOMMENDATION - SOUTH MEADOWS MIDDLE SCHOOL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 368845
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jul, 2021 | Aug, 2022
|  | Stobes, Visual Warning Inside and Outside |  | Jul, 2021 | Aug, 2022
|  | Security Cameras |  | Oct, 2017 | Aug, 2018
|  | Card Key Access - Exterior Doors |  | Jul, 2021 | Aug, 2022
|  | Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Fire Doors on Alert Button at Front Desk |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Main Door |  | Jul, 2021 | Aug, 2022
|  | Glass Film at Other Windows |  | Jul, 2021 | Aug, 2022
|  | Upgrade In Building Radio Communication |  | Jul, 2021 | Aug, 2022
|  | Improve In Building Public Safety Communication Capability |  | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 404666.86
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Student Audio/Video Production Devices - Media/Learning Center
Student Achievement
|  | Replacement of Classroom Furniture | 370549.1589
Current Infrastructure Improvements
|  | Roofing | 73591.0948 | Jul, 2021 | Aug, 2022
|  | Upgrade Electrical Service/Generator | 207077 | Jul, 2021 | Aug, 2022
|  | TOTALS | 1424729.1137
0

## Brown MS
|  | FINAL BOND RECOMMENDATION - BROWN MIDDLE SCHOOL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 368845
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jun, 2018 | Aug, 2019
|  | Stobes, Visual Warning Inside and Outside |  | Jun, 2018 | Aug, 2019
|  | Security Cameras |  | Oct, 2017 | Aug, 2018
|  | Improve Line of Sight From Office to Front Door |  | Jun, 2018 | Aug, 2019
|  | Card Key Access - Exterior Doors |  | Jun, 2018 | Aug, 2019
|  | Local Door Alarms for Outside Doors |  | Jun, 2018 | Aug, 2019
|  | Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Fire Doors on Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Main Door |  | Jun, 2018 | Aug, 2019
|  | Upgrade In Building Radio Communication |  | Jun, 2018 | Aug, 2019
|  | Improve In Building Public Safety Communication Capability |  | Jun, 2018 | Aug, 2019
| School Seismic Upgrades |  | 2520000 | Jun, 2018 | Aug, 2019
Educational Technology
| Technology-Classroom |  | 466157.2
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Student Audio/Video Production Devices - Media/Learning Center
Student Achievement
|  | Replacement of Classroom Furniture | 364016.9556
Current Infrastructure Improvements
|  | Roofing | 1391837.3987 | Jun, 2018 | Aug, 2019
|  | Add Air Conditioning | 1278520.937 | Jun, 2018 | Aug, 2019
|  | Upgrade HVAC | 747494 | Jun, 2018 | Aug, 2019
|  | Water Pipe Replacement | 616092 | Jun, 2018 | Aug, 2019
|  | Boiler Replacement | 587447 | Jun, 2018 | Aug, 2019
|  | Direct Digital Controls (DDC) | 1101704 | Jun, 2018 | Aug, 2019
|  | TOTALS | 9442114.4913
0

## Poynter MS
|  | FINAL BOND RECOMMENDATION - POYNTER MIDDLE SCHOOL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 410963
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jun, 2018 | Aug, 2019
|  | Stobes, Visual Warning Inside and Outside |  | Jun, 2018 | Aug, 2019
|  | Security Cameras |  | Oct, 2017 | Aug, 2018
|  | Card Key Access - Exterior Doors |  | Jun, 2018 | Aug, 2019
|  | Local Door Alarms for Outside Doors |  | Jun, 2018 | Aug, 2019
|  | Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Fire Doors on Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Main Door |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Other Windows |  | Jun, 2018 | Aug, 2019
|  | Upgrade In Building Radio Communication |  | Jun, 2018 | Aug, 2019
|  | Improve In Building Public Safety Communication Capability |  | Jun, 2018 | Aug, 2019
| School Seismic Upgrades |  | 11311973 | Jun, 2018 | Aug, 2019
Educational Technology
| Technology-Classroom |  | 528262.32
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Student Audio/Video Production Devices - Media/Learning Center
Student Achievement
|  | Replacement of Classroom Furniture | 381104.8501
Current Infrastructure Improvements
|  | Roofing | 1313192.9275 | Jun, 2018 | Aug, 2019
|  | Add Air Conditioning | 2070363.643 | Jun, 2018 | Aug, 2019
|  | Upgrade HVAC | 858551 | Jun, 2018 | Aug, 2019
|  | Water Pipe Replacement | 669122 | Jun, 2018 | Aug, 2019
|  | Boiler Replacement | 761807 | Jun, 2018 | Aug, 2019
|  | Direct Digital Controls (DDC) | 1234438 | Jun, 2018 | Aug, 2019
|  | Walk-In Freezer | 36283 | Jun, 2018 | Aug, 2019
|  | Upgrade Electrical Service/Generator | 65555 | Jun, 2018 | Aug, 2019
|  | TOTALS | 19641615.7406
0

## Evergreen MS
|  | FINAL BOND RECOMMENDATION - EVERGREEN MIDDLE SCHOOL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 356083
Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc)
Stobes, Visual Warning Inside and Outside
|  | Security Cameras |  | Oct, 2017 | Aug, 2018
Improve Line of Sight From Office to Front Door
Card Key Access - Exterior Doors
Local Door Alarms for Outside Doors
Alert Button at Front Desk
Fire Doors on Alert Button at Front Desk
Glass Film at Main Door
Upgrade In Building Radio Communication
Improve In Building Public Safety Communication Capability
| School Seismic Upgrades |  | 1621827
Educational Technology
| Technology-Classroom |  | 540834.34
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Student Audio/Video Production Devices - Media/Learning Center
Student Achievement
|  | Replacement of Classroom Furniture | 423521.0961
New Capacity
|  | Evergreen Middle School Addition | 18786600 | Feb, 2018 | July, 2020
Current Infrastructure Improvements
|  | Roofing | 2637477.0435
|  | Upgrade HVAC | 764543
|  | TOTALS | 25130885.4796
0

## Century HS
|  | FINAL BOND RECOMMENDATION - CENTURY HIGH SCHOOL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 643246
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jun, 2018 | Aug, 2019
|  | Stobes, Visual Warning Inside and Outside |  | Jun, 2018 | Aug, 2019
|  | Security Cameras |  | Jun, 2018 | Aug, 2019
|  | Improve Line of Sight From Office to Front Door |  | Oct, 2017 | Aug, 2018
|  | Card Key Access - Exterior Doors |  | Jun, 2018 | Aug, 2019
|  | Local Door Alarms for Outside Doors |  | Jun, 2018 | Aug, 2019
|  | Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Fire Doors on Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Main Door |  | Jun, 2018 | Aug, 2019
|  | Upgrade In Building Radio Communication |  | Jun, 2018 | Aug, 2019
|  | Improve In Building Public Safety Communication Capability |  | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 1099137.83
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Student Audio/Video Production Devices - Media/Learning Center
Student Achievement
| High School CTE Infrastructure |  | 3500000 | Jun, 2018 | Aug, 2019
Marketing
Hospitality & Tourism
Health Sciences
Early Childhood Education
Engineering Technology
Information & Communications Technology
Graphic Design
Media Arts
Leadership
Social Services
Accounting
| Replacement of Classroom Furniture |  | 816249.0507
Current Infrastructure Improvements
|  | Roofing | 2714335.4154 | Jun, 2018 | Aug, 2019
|  | Upgrade HVAC | 111049 | Jun, 2018 | Aug, 2019
|  | Construct lighted Artificial Turf Field and Other Athletic Field Improvements | 2333333.3333 | Jun, 2018 | Aug, 2019
|  | TOTALS | 11217350.6295
0

## Glencoe HS
|  | FINAL BOND RECOMMENDATION - GLENCOE HIGH SCHOOL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 470374
Stobes, Visual Warning Inside and Outside
Security Cameras
|  | Improve Line of Sight From Office to Front Door |  | Oct, 2017 | Aug, 2018
Card Key Access - Exterior Doors
Local Door Alarms for Outside Doors
Alert Button at Front Desk
Fire Doors on Alert Button at Front Desk
Glass Film at Main Door
Upgrade In Building Radio Communication
|  | Improve In Building Public Safety Communication Capability |  | Oct, 2017 | Aug, 2018
| School Seismic Upgrades |  | 2049450
Educational Technology
| Technology-Classroom |  | 1209444.11
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Student Audio/Video Production Devices - Media/Learning Center
New Capacity
|  | Glencoe High School Addition | 18600276 | Feb, 2018 | Jul, 2020
Student Achievement
| High School CTE Infrastructure |  | 3500000
Finance
Marketing
Health Sciences
Early Childhood Education
Technology/Drafting
Manufacturing Technology
Graphic Design
Construction Technology
| Replacement of Classroom Furniture |  | 808301.7568
Current Infrastructure Improvements
|  | Roofing | 1776436.8943
|  | Upgrade HVAC | 564293
|  | Construct lighted Artificial Turf Field and Other Athletic Field Improvements | 2333333.3333 | Oct, 2017 | Aug, 2018
|  | TOTALS | 31311909.0944
0

## Hilhi HS
|  | FINAL BOND RECOMMENDATION - HILLSBORO HIGH SCHOOL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 568871
Interior Door Locks - Classrooms
Stobes, Visual Warning Inside and Outside
Security Cameras
Card Key Access - Exterior Doors
Local Door Alarms for Outside Doors
Alert Button at Front Desk
Glass Film at Main Door
Upgrade In Building Radio Communication
Improve In Building Public Safety Communication Capability
| School Seismic Upgrades |  | 3272743
Educational Technology
| Technology-Classroom |  | 1007841.15
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Student Audio/Video Production Devices - Media/Learning Center
Student Achievement
| High School CTE Infrastructure Investments |  | 3500000
Auto Technology
Early Childhood Education
Business & Marketing
Horticulture
Graphic Design
Drafting
Robotics
Visual Arts
Sports Medicine
Performing Arts
Computer Science
Biotechnology
Animal Sciences
Information and Communications Technology
| Hillsboro High School Upgrade |  | 11011248 | Feb, 2018 | Jul, 2020
| Replacement of Classroom Furniture |  | 660571.1685
Current Infrastructure Improvements
|  | Roofing | 2960543.8771
|  | Upgrade Electrical Service/Generator | 83990
|  | Construct lighted Artificial Turf Field and Other Athletic Field Improvements | 2333333.3333 | Oct, 2017 | Aug, 2018
|  | Construct Track | 1823259 | Oct, 2017 | Aug, 2018
|  | TOTALS | 27222400.529
0

## Liberty HS
|  | FINAL BOND RECOMMENDATION - LIBERTY HIGH SCHOOL |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 548099
|  | Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc) |  | Jun, 2018 | Aug, 2019
|  | Stobes, Visual Warning Inside and Outside |  | Jun, 2018 | Aug, 2019
|  | Security Cameras |  | Jun, 2018 | Aug, 2019
|  | Improve Line of Sight From Office to Front Door |  | Oct, 2017 | Aug, 2018
|  | Card Key Access - Exterior Doors |  | Jun, 2018 | Aug, 2019
|  | Local Door Alarms for Outside Doors |  | Jun, 2018 | Aug, 2019
|  | Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Fire Doors on Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Main Door |  | Jun, 2018 | Aug, 2019
|  | Upgrade In Building Radio Communication |  | Jun, 2018 | Aug, 2019
|  | Improve In Building Public Safety Communication Capability |  | Oct, 2017 | Aug, 2018
Educational Technology
| Technology-Classroom |  | 970178.08
CRT Monitor Replacement
Classroom Projectors
Voice Amplification
Wireless Access Points
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Student Audio/Video Production Devices - Media/Learning Center
Student Achievement
| High School CTE Infrastructure Investments |  | 3500000 | Jun, 2018 | Aug, 2019
Hospitality & Tourism
Early Childhood Education
Health Sciences
Engineering
Media Production
Visual Arts
Performing Arts
Sustainable Agriculture
Environmental Design/Architecture
Diesel Mechanics
Biotechnology
| Replacement of Classroom Furniture |  | 782093.4594
Current Infrastructure Improvements
|  | Roofing | 104087.7918 | Jun, 2018 | Aug, 2019
|  | Chiller Replacement | 957211 | Jun, 2018 | Aug, 2019
|  | TOTALS | 6861669.3312
0

## Miller-Big Picture
|  | FINAL BOND RECOMMENDATION - MILLER ED WEST |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 226476
|  | Stobes, Visual Warning Inside and Outside |  | Jun, 2018 | Aug, 2019
|  | Security Cameras |  | Jun, 2018 | Aug, 2019
|  | Improve Line of Sight From Office to Front Door |  | Jun, 2018 | Aug, 2019
|  | Card Key Access - Exterior Doors |  | Jun, 2018 | Aug, 2019
|  | Alert Button at Front Desk |  | Jun, 2018 | Aug, 2019
|  | Glass Film at Main Door |  | Jun, 2018 | Aug, 2019
|  | Upgrade In Building Radio Communication |  | Jun, 2018 | Aug, 2019
| School Seismic Upgrades |  | 3838888 | Jun, 2018 | Aug, 2019
Educational Technology
| Technology-Classroom |  | 61541
Classroom Projectors
Voice Amplification
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Current Infrastructure Improvements
|  | Roofing | 625115.7835 | Jun, 2018 | Aug, 2019
|  | Upgrade HVAC | 171482 | Jun, 2018 | Aug, 2019
|  | Water Pipe Replacement | 181005 | Oct, 2017 | Aug, 2018
|  | Boiler Replacement | 737286 | Jun, 2018 | Aug, 2019
|  | Direct Digital Controls (DDC) | 284483 | Jun, 2018 | Aug, 2019
|  | TOTALS | 6126276.7835
0

## Miller-East Campus
|  | FINAL BOND RECOMMENDATION - MILLER ED EAST |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 179573
Interior Door Locks - Classrooms
|  | Security Cameras |  | Oct, 2017 | Aug, 2018
Card Key Access - Exterior Doors
Alert Button at Front Desk
Glass Film at Main Door
Upgrade In Building Radio Communication
| School Seismic Upgrades |  | 328557
Educational Technology
| Technology-Classroom |  | 65635
Classroom Projectors
Voice Amplification
Whiteboards
Document Cameras
Student Computers
Licensed Staff Computers
Classified Staff Computers
Current Infrastructure Improvements
|  | Roofing | 190708.1831
|  | Add Air Conditioning | 573212.1023
|  | TOTALS | 1337685.2854
0

## Peter Boscow
|  | FINAL BOND RECOMMENDATION - PETER BOSCOW |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 91127
Interior Door Locks - Classrooms
Interior Door Locks - Other Rooms (Offices, Conference Rooms, Closets, Etc)
Security Cameras
Improve Line of Sight From Office to Front Door
Card Key Access - Exterior Doors
| School Seismic Upgrades |  | 687534
Current Infrastructure Improvements
|  | Roofing | 615952.7498
|  | TOTALS | 1394613.7498
0

## Transportation
| FINAL BOND RECOMMENDATION - TRANSPORTATION |  | Begin | Project
Safety & Security Enhancements |  |  | Pre-Design | Complete
| Cameras on All Buses | 744188
Current Infrastructure Improvements
| Roofing | 175420.4753
| Upgrade HVAC | 270895
| Direct Digital Controls (DDC) | 135158
| Upgrade Electrical Service/Generator | 91402
| Satellite Transportation/Maintenance Facility | 16352831 | Feb, 2018 | Jul, 2020
| TOTALS | 17769894.4753
0

## Admin Center
|  | FINAL BOND RECOMMENDATION - ADMINISTRATION CENTER |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 322963
Upgrade PA System
Improve Line of Sight From Office to Front Door
Card Key Access - Exterior Doors
Glass Film at Main Door
Improve In Building Public Safety Communication Capability
|  | TOTALS | 322963
0

## Hare Field
| FINAL BOND RECOMMENDATION - HARE FIELD |  | Begin | Project
Current Infrastructure Improvements |  |  | Pre-Design | Complete
| Water Pipe Replacement | 59904
| TOTALS | 59904
0

## Facilities
|  | FINAL BOND RECOMMENDATION - FACILITIES |  | Begin | Project
Safety & Security Enhancements |  |  |  | Pre-Design | Complete
| School Safety Upgrades |  | 99167
Security Cameras
Card Key Access - Exterior Doors
Upgrade In Building Radio Communication
|  | TOTALS | 99167
0

## District Technology
| FINAL BOND RECOMMENDATION - DISTRICT TECHNOLOGY |  | Begin | Project
District Technology |  | 15932500 | Pre-Design | Complete
Internal Dark Fiber Ring
VoIP Phone System
Refresh Internal Switching Infrastructure
Full UPS Refresh
Refresh current Wireless Infrastructure
Fence-to-Fence Wireless
Server Infrastructure Refresh
Security and Routing Architecture
Upgrade Storage Infrastructure
Replace Internal Frame Connection Fiber
| TOTALS | 15932500
0