## Slide 1
B O A R D O F E D U C A T I O N
Board Meeting| August 26, 2019
Dr. H A S M I K D A N I E L l A N
Superintendent
E S T U A R D O S A N T I L L A N
Assistant Superintendent| Business Services
E D I T H C. F L O R E N C E
Director| Facilities Planning & Construction
A N T O N I O S A L C I D O
Program Director| Cumming (Program Management)
B O N D P R O G R A M U P D A T E
B O N D P R O G R A M U P D A T E
August 26, 2019
Notes: Good evening Board President Valencia, Vice President Cazares, Board Members, Dr. Danielian, Executive staff and guests.

## Slide 2
MAY 07, 2018
  AGENDA
  Measure G
    Financial Update
  Measure G Phase 1A
    Financial & Status Update
  Measure G Phase 1B
    Financial & Status Update
    La Mirada High School
    Schematic Design
B O N D P R O G R A M U P D A T E
1
August 26, 2019
B O N D P R O G R A M U P D A T E
Notes: This is a Measure G Bond Program Update.

## Slide 3
Measure G – Financial Update
B O N D P R O G R A M U P D A T E
2
August 26, 2019
Expenditures as of July 2019 $80.3M
Chart: total bond issuance $375M
| Series A - $24M | Series B - $59M | Series C - $10.25M | Series D - $60M | Unallocated $221.75
 | 24 | 59 | 10.25 | 60 | 221.75

## Slide 4
Phase 1A – Financial & Status Update
PROJECT | REVISED BUDGET | EXPENDI-TURES | BALANCE | CONSTRUCTION COMPLETION
BENTON MIDDLE SCHOOL Campus-Wide Landscape Renovation | $7,573,657 | $9,132,549 | ($1,558,892)* | 99%
CORVALLIS MIDDLE SCHOOL Campus-Wide Landscape Renovation | $6,632,575 | $8,156,784 | ($1,524,209)* | 99%
GLENN HIGH SCHOOL Synthetic Turf Sports Fields, Acc Bldg, Stadium | $25,032,646 | $23,476,872 | $1,555,773 | 98%
LA MIRADA HIGH SCHOOL Modernization of Gym and Locker Room Buildings | $21,309,789 | $5,572,926 | $15,736,863 | 27% Seismic +/-$3M
MORRISON ELEMENTARY SCHOOL Modernization of Admin & MPR | $4,140,832 | $669,762 | $3,471,069 | 25%
LOS ALISOS MIDDLE SCHOOL Modernization of MPR | $2,975,081 | $604,889 | $2,370,192 | 33%
GARDENHILL ELEMENTARY SCHOOL Modernization of Admin & MPR | $3,470,980 | $3,155,054 | $315,926 | 99%
HUTCHINSON MIDDLE SCHOOL Modernization of Admin & MPR | $3,334,466 | $2,816,889 | $517,577 | 99%
TOTAL | $74,470,025 | $55,585,726 | $20,884,299 | 
B O N D P R O G R A M U P D A T E
3
August 26, 2019
*Funded by Measure S

## Slide 5
Phase 1B – Financial and Status Update*
B O N D P R O G R A M U P D A T E
4
August 26, 2019
PROJECT | REVISED BUDGET | EXPENDI- TURES | BALANCE | PROJECT PHASE
NORWALK HIGH SCHOOL New Synthetic Sports Fields, Acc Bldgs & Stadium | $33,548,865 | $1,343,703 | $32,205,162 | Bid Review & Evaluation underway
LA MIRADA HIGH SCHOOL Modernization Synthetic Football Field, Acc Bldgs & Stadium | $19,083,924 | $3,726 | $19,080,198 | Design
DISTRICT-WIDE Safety | $3,000,000 | $0 | $3,000,000 | Procurement
MORRISON ELEMENTARY SCHOOL & LOS ALISOS MIDDLE SCHOOL Modernization of Admin & MPR | $2,000,000 | $0 | $2,000,000 | Construction
PROGRAM UNFORESEEN CONDITIONS | $2,367,211 | $454,388** | $1,912,823 | 
TOTAL | $60,000,000 | $1,801,817 | $58,198,183 | 
*Financial Update as of July 31, 2019 from Monthly Progress Report by Cumming
**Bond Issuance Series D Cost of Issuance

## Slide 6
Phase 1B – La Mirada High School Current Scope of Work
B O N D P R O G R A M U P D A T E
5
August 26, 2019
Current Scope of Work
Football Field, Accessory Buildings, Stadium
Baseball and Softball Dug-Outs
ADA Scope of Work
Design Concept
By NAC Architecture
Athletic Entry Pavilion
Unifying Elements
Central Accessible Spine
Relationship to Gym, Locker Rooms

## Slide 7
Phase 1B – La Mirada High School Current Scope of Work
B O N D P R O G R A M U P D A T E
6
August 26, 2019
Schematic Design
Current Scope of Work
New Synthetic Turf Football/Soccer Field
New 9-Lane All-Weather Certified CIF Track
Please note existing 8-Lane Track is not CIF-Certified

## Slide 8
Phase 1B – La Mirada High School Current Scope of Work
B O N D P R O G R A M U P D A T E
7
August 26, 2019
Schematic Design
Current Scope of Work
New Visitor Bleachers
New Ramp
New Ticket Booth
New Concession & Restrooms
New Field Lights, Scoreboard, Goal Post
Home Bleachers & Press Box (mod)
Notes: Phasing not recommended because it would require two separate bid packages and the same ADA scope
Will add milestones to project schedule as part of the bid documents to expedite use of the field

## Slide 9
Phase 1B – La Mirada High School Current Scope of Work
B O N D P R O G R A M U P D A T E
8
August 26, 2019
Schematic Design
Current Scope of Work
Path of Travel to Baseball Field
New Baseball Dugouts
(concrete block)
New Baseball Bullpens

## Slide 10
Phase 1B – La Mirada High School Current Scope of Work
B O N D P R O G R A M U P D A T E
9
August 26, 2019
Schematic Design
Current Scope of Work
Path of Travel to Softball Field
New Softball Dugouts
(chain link fencing)
New Baseball Bullpens

## Slide 11
Phase 1B – La Mirada High School Current Scope of Work
B O N D P R O G R A M U P D A T E
10
August 26, 2019
SCHEMATIC DESIGN | CONSTRUCTION BUDGET* | CONSTRUCTION COST ESTIMATE**
Football Field |  | 
Ticket Booth | $243,804 | $310,000
Concessions Buildings (Home and Visitor) | $1,376,939 | $1,500,000
Synthetic Turf & Track | $4,130,817 | $3,500,000
Bleachers | $5,033,456 | $2,700,000
Stadium Components (lights, scoreboard) | $1,110,502 | $1,100,000
Path of Travel (ramp) | $214,842 | $250,000
Baseball (ramp, dugouts, bullpens) | $593,206 | $1,000,000
Softball (ramp, dugouts, bullpens) | $334,508 | $250,000
General Site (path of travel, gates, ped lighting) | $387,138 | $390,000
TOTAL | $13,425,211 | $11,000,000
*Budget approved by Board on 11/29/19, **Cost Estimate from NAC Architecture

## Slide 12
Phase 1B – La Mirada High School Additional Scope of Work
B O N D P R O G R A M U P D A T E
11
August 26, 2019
SCHEMATIC DESIGN | CONSTRUCTION COSTS | NOTES
New Visitors Bleachers | No cost impact | Already Included in scope
New Home Bleachers | Increased cost of $2,700,000 | Recommendation to add to Project
New Press Box | Increased cost of $260,000 | Recommendation to add to Project
Softball Dug Outs (from chain link to concrete block) | Increased cost of $110,000 | Recommendation to add to Project
Multi-Use Building under Bleachers |  | Not recommended due to site layout and limited circulation/accessibility
 | $3,070,000 | Total Recommendation for Additional Scope of Work

## Slide 13
Phase 1B – La Mirada High School Current & Additional Scope of Work
B O N D P R O G R A M U P D A T E
12
August 26, 2019
SCHEMATIC DESIGN | CONSTRUCTION BUDGET* | CONSTRUCTION COST ESTIMATE** | DIFFERENCE
Football Field |  |  | 
Ticket Booth | $243,804 | $310,000 | 
Concessions Buildings (Home and Visitor) | $1,376,939 | $1,500,000 | 
Synthetic Turf & Track | $4,130,817 | $3,500,000 | 
Bleachers | $5,033,456 | $2,700,000 | 
Stadium Components (lights, scoreboard) | $1,110,502 | $1,100,000 | 
Path of Travel (ramp) | $214,842 | $250,000 | 
Baseball (ramp, dugouts, bullpens) | $593,206 | $1,000,000 | 
Softball (ramp, dugouts, bullpens) | $334,508 | $250,000 | 
General Site (path of travel, gates, ped lighting) | $387,138 | $390,000 | 
Additional Scope of Work |  | 3,070,000 | 
TOTAL | $13,425,211 | $14,070,000 | $644,789

## Slide 14
Phase 1B – La Mirada High School Current & Additional Scope of Work
B O N D P R O G R A M U P D A T E
13
August 26, 2019
SCHEMATIC DESIGN | APPROVED BUDGET | REVISED BUDGET | DIFFERENCE
Construction Costs | $13,425,211 | $14,070,000 | $644,789
Soft Costs | $5,658,713 | $5,930,000 | $271,287
TOTAL COSTS | $19,083,924 | $20,000,000 | $916,076

## Slide 15
Phase 1B – La Mirada High School
B O N D P R O G R A M U P D A T E
14
August 26, 2019
RECOMMENDATION
Approve Current & Additional Scope of Work
Approve New Budget
Proceed as Design-Bid-Build