## Goal 1 Timeline
Action Plan Goal # 1: East Union will work towards developing formal processes for common formative, formative or projects as appropritate for monitoring student achievement in all course.
Action Plan Step | Date to be completed | Items Needed | Who to send to | Goal Tracking
1.2 PLC/Departments will develop formative, common formative or projects to use as data/rubric points in analyzing student learning. This includes baseline measurements on progress tracking programs such as Alecks or Reading Plus. | 2024-10-31 | 4 Formative, common formative or projects with rubrics, type of data used or where base line measurements will come from | Shared HUB | 50% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2024-10-31 | WASC Focus groups: Protocol for monitoring SLOs Achievemnt and Student learner Outcomes progress | WASC Coordinator, | 100% of depts.
1.1 Developing department process for collecting data on common formative, formative or project for review. | 2024-12-31 | Protocol Processes with Procedures, Protocol form | WASC Coordinator, Staff HUB PLC Folder Clearly Labeled | 30% of depts.
1.2 PLC/Departments will develop formative, common formative or projects to use as data/rubric points in analyzing student learning. This includes baseline measurements on progress tracking programs such as Alecks or Reading Plus. | 2024-12-31 | 4 Formative, common formative or projects with rubrics, type of data used or where base line measurements will come from | Shared HUB | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2024-12-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
1.1 Developing department process for collecting data on common formative, formative or project for review. | 2025-05-31 | Protocol Processes with Procedures, Protocol form | WASC Coordinator, Staff HUB PLC Folder Clearly Labeled | 50% of depts.
1.2 PLC/Departments will develop formative, common formative or projects to use as data/rubric points in analyzing student learning. This includes baseline measurements on progress tracking programs such as Alecks or Reading Plus. | 2025-05-31 | 4 Formative, common formative or projects with rubrics, type of data used or where base line measurements will come from | WASC Coordinator, Staff HUB PLC Folder Clearly Labeled | 100% of depts.
1.1 Developing department process for collecting data on common formative, formative or project for review. | 2025-10-31 | Protocol Processes with Procedures, Protocol form | WASC Coordinator, Staff HUB PLC Folder Clearly Labeled | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2025-10-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2025-12-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2026-03-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2026-05-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
1.3 Staff will use monitoring procedures to review data on student achievement. The monitoring procedures and data will be posted to the Staff HUB. | 2026-05-31 | Completed Protocol Sheet, Corresponding Data | Shared HUB | 100% of depts.
1.3 Staff will use monitoring procedures to review data on student achievement. The monitoring procedures and data will be posted to the Staff HUB. | 2026-10-31 | Completed Protocol Sheet, Corresponding Data | Shared HUB | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2027-05-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
1.3 Staff will use monitoring procedures to review data on student achievement. The monitoring procedures and data will be posted to the Staff HUB. | 2027-05-31 | Completed Protocol Sheet, Corresponding Data | Shared HUB | 100% of depts.
1.3 Staff will use monitoring procedures to review data on student achievement. The monitoring procedures and data will be posted to the Staff HUB. | 2027-10-31 | Completed Protocol Sheet, Corresponding Data | Shared HUB | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2027-12-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2028-03-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2028-05-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
1.3 Staff will use monitoring procedures to review data on student achievement. The monitoring procedures and data will be posted to the Staff HUB. | 2028-05-31 | Completed Protocol Sheet, Corresponding Data | Shared HUB | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2028-10-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
1.3 Staff will use monitoring procedures to review data on student achievement. The monitoring procedures and data will be posted to the Staff HUB. | 2028-10-31 | Dissaggregated Data for Formative, CFA or Project Assessment Protocol sheet | Shared HUB | 50% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2028-12-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2029-03-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2029-05-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
1.3 Staff will use monitoring procedures to review data on student achievement. The monitoring procedures and data will be posted to the Staff HUB. | 2029-05-31 | Dissaggregated Data for Formative, CFA or Project Assessment Protocol sheet | Shared HUB | 100% of depts.
1.3 Staff will use monitoring procedures to review data on student achievement. The monitoring procedures and data will be posted to the Staff HUB. | 2029-10-31 | Dissaggregated Data for Formative, CFA or Project Assessment Protocol sheet | Shared HUB | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2030-03-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2030-10-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.
SLOs 1.4 WASC Focus Group will develop formal procedures for gathering data for Student Learner Objectives and Student Learner Outcomes. | 2030-12-31 | SLOs and Student Learner Outcome monitoring review | WASC Coordinator | 100% of depts.

## Goal 2 Timeline
Action Plan Goal # 2:East Union will coninue to use data and project-based rubrics in departmental settings and PLCs to deelop academic strategies to increase student learning as appropriate for each course.
Action Plan Step | Date to be completed | Items Needed | Who to send to | Goal Tracking
2.1 Departments will use their commonf formative formative or projects to develop lessons to improve achievement or progressThis lesson will be posted in staff HUB. | 2026-10-31 | 2Data and 2 Best practice lesson plan | Post In Staff HUB | 50% of depts.
2.1 Departments will use their commonf formative formative or projects to develop lessons to improve achievement or progressThis lesson will be posted in staff HUB. | 2027-05-31 | 2 Data and 2 Best practice lesson plan | Post In Staff HUB | 100% of depts.
2.1 Departments will use their commonf formative formative or projects to develop lessons to improve achievement or progressThis lesson will be posted in staff HUB. | 2027-10-31 | 4 data and 4 Best practice lesson plan | Post In Staff HUB | 50% of depts.
2.1 Departments will use their commonf formative formative or projects to develop lessons to improve achievement or progressThis lesson will be posted in staff HUB. | 2028-05-31 | 4 data and 4 Best practice lesson plan | Post In Staff HUB | 100% of depts.
2.2 Departments will use their previously developed lessons and modify them to reach English Language Learners (ELL) and Students with disbabilities. Lessons will be posted in staff HUB. | 2028-10-31 | Disaggregated data, best practice lesson, modified lesson | Post in Staff Hub | 50% of depts.
2.2 Departments will use their previously developed lessons and modify them to reach English Language Learners (ELL) and Students with disbabilities. Lessons will be posted in staff HUB. | 2029-05-31 | Disaggregated data, best practice lesson, modified lesson | Post in Staff Hub | 100% of depts.
2.2 Departments will use their previously developed lessons and modify them to reach English Language Learners (ELL) and Students with disbabilities. Lessons will be posted in staff HUB. | 2029-10-31 | Disaggregated data, best practice lesson, modified lesson | Post in Staff Hub | 100% of depts.
2.2 Departments will use their previously developed lessons and modify them to reach English Language Learners (ELL) and Students with disbabilities. Lessons will be posted in staff HUB. | 2030-05-31 | Disaggregated data, best practice lesson, modified lesson | Post in Staff Hub | 100% of depts.

## Goal 3 Timeline
Action Plan Goal # 3: East Union will continue to reach out to all stakeholders by creating increased oppurtunities for diversifying community involvement.
Action Plan Step | Date to be completed | Items Needed | Who to send to | Goal Tracking
31. Staff and School leadership will create a comprehensive calendar of events given annually. This will include leadership activities, school events and events on campus that may interfere with instructional time. | 2025-08-31 | Activities Calendar, AP Testing Calendar, Sports calenar, Booster calendar | Administration | 100% of annual events on calendar
31. Staff and School leadership will create a comprehensive calendar of events given annually. This will include leadership activities, school events and events on campus that may interfere with instructional time. | 31-Sept-2025 | A singe calendar with access for staff to view activities and events on campus. | Administration | 100% of annual events on calendar
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2025-10-31 | List of proposed Events, possible dates for oppurtunities | Leadership Coordinator, WASC Coordinator, Administration | 5 proposed alternative events that are culturally sensitive
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2025-03-31 | List of Event requests with cost and planning form | Leadership Coordinator, WASC Coordinator, Administration | 3 viable event options with cost and proposed dates
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2026-05-31 | List proposed to staff of events, survey results of top 2 events | Leadership Coordinator, WASC Coordinator, Administration | 2 events to add to the calendar for 2026-27 school year
3.3 Administration will pull and review student attendance at events and disciplinary actions to monitor or review if there is a direct correlation between event attendance and disciplinary matters. | 2025-2026 School Year | Tally or 5 star check in rosters, Event Ticket Purchases | Leadership Coordinator, WASC Coordinator, Administration, Adjunct Personnel | Pull Event attendance's per month to complete a full year review by May 2026. Compare with behavior and disciplinary numbers to find correlation or causation.
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2027-05-31 | Survey Results, List of events per month | WASC Coordinator, Administration | 50% response from each stakeholder group on survey
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2027-10-31 | Proposed List of Events, School Calendar, school budget | Leadership Coordinator, WASC Coordinator, Administration, Faculty, Students, Parents | 5 new events proposed that are diverse and culturally sensitive
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2028-03-31 | Updated Calendar with new events for following school year | Leadership Coordinator, Adminsitration | Updated calendaer of events based on attendance and stakeholder surveys
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2028-05-31 | Survey of reviews of events given during the current school year | Leadership Coordinator, WASC Coordinator, Administration, Stakeholders | 60% of each stakeholder group will respond to surveys
3.3 Administration will pull and review student attendance at events and disciplinary actions to monitor or review if there is a direct correlation between event attendance and disciplinary matters. | 2028-05-31 | Tally or 5 star check in rosters, Event Ticket Purchases | Administration | Pull Event attendance's per month to complete a full year review by May 2026. Compare with behavior and disciplinary numbers to find correlation or causation.
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2028-08-31 | Calendar for the 2028-2029 school year | Leadership Coordinator, WASC Coordinator, Administration, | 2 new events will be implemented based on stakeholder reviews for the next school year
3.3 Administration will pull and review student attendance at events and disciplinary actions to monitor or review if there is a direct correlation between event attendance and disciplinary matters. | 2026-2027 School Year | Tally or 5 star check in rosters, Event Ticket Purchases | Leadership Coordinator, WASC Coordinator, Administration, Adjunct Personnel | Pull Event attendance's per month to complete a full year review by May 2027. Compare with behavior and disciplinary numbers to find correlation or causation.
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2028-10-31 | Proposed List of Events, School Calendar, school budget | Leadership Coordinator, WASC Coordinator, Administration, Faculty, Students, Parents | 5 new events proposed that are diverse and culturally sensitive
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2029-03-31 | Updated Calendar with new events for following school year | Leadership Coordinator, Adminsitration | Updated calendaer of events based on attendance and stakeholder surveys
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2029-05-31 | Survey of reviews of events given during the current school year | Leadership Coordinator, WASC Coordinator, Administration, Stakeholders | 60% of each stakeholder group will respond to surveys
3.3 Administration will pull and review student attendance at events and disciplinary actions to monitor or review if there is a direct correlation between event attendance and disciplinary matters. | 2029-05-31 | Tally or 5 star check in rosters, Event Ticket Purchases | Administration | Pull Event attendance's per month to complete a full year review by May 2026. Compare with behavior and disciplinary numbers to find correlation or causation.
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2029-08-31 | Calendar for the 2028-2029 school year | Leadership Coordinator, WASC Coordinator, Administration, | 2 new events will be implemented based on stakeholder reviews for the next school year
3.3 Administration will pull and review student attendance at events and disciplinary actions to monitor or review if there is a direct correlation between event attendance and disciplinary matters. | 2027-2028 School Year | Tally or 5 star check in rosters, Event Ticket Purchases | Leadership Coordinator, WASC Coordinator, Administration, Adjunct Personnel | Pull Event attendance's per month to complete a full year review by May 2028. Compare with behavior and disciplinary numbers to find correlation or causation.
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2029-08-31 | Calendar for the 2029-2030 school year | Leadership Coordinator, WASC Coordinator, Administration, | 2 new events will be implemented based on stakeholder reviews for the next school year
3.3 Administration will pull and review student attendance at events and disciplinary actions to monitor or review if there is a direct correlation between event attendance and disciplinary matters. | 2028-2029 School Year | Tally or 5 star check in rosters, Event Ticket Purchases | Leadership Coordinator, WASC Coordinator, Administration, Adjunct Personnel | Pull Event attendance's per month to complete a full year review by May 2029. Compare with behavior and disciplinary numbers to find correlation or causation.
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2029-10-31 | Proposed List of Events, School Calendar, school budget | Leadership Coordinator, WASC Coordinator, Administration, Faculty, Students, Parents | 5 new events proposed that are diverse and culturally sensitive
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2030-03-31 | Updated Calendar with new events for following school year | Leadership Coordinator, Adminsitration | Updated calendaer of events based on attendance and stakeholder surveys
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2030-05-31 | Survey of reviews of events given during the current school year | Leadership Coordinator, WASC Coordinator, Administration, Stakeholders | 60% of each stakeholder group will respond to surveys
3.3 Administration will pull and review student attendance at events and disciplinary actions to monitor or review if there is a direct correlation between event attendance and disciplinary matters. | 2030-05-31 | Tally or 5 star check in rosters, Event Ticket Purchases | Administration | Pull Event attendance's per month to complete a full year review by May 2030. Compare with behavior and disciplinary numbers to find correlation or causation.
3.2 The administration and staff will work to expand after school offerings where students and parents can be involved in campus decisions. This can include offering multiple days for reviewing SLO's and open forums for suggests for campus offerings to increase the amount of diversity in programs such as guest speakers on multiple topic to peak student interest. | 2030-08-31 | Calendar for the 2030-2031 school year | Leadership Coordinator, WASC Coordinator, Administration, | 2 new events will be implemented based on stakeholder reviews for the next school year
3.3 Administration will pull and review student attendance at events and disciplinary actions to monitor or review if there is a direct correlation between event attendance and disciplinary matters. | 2029-2030 School Year | Tally or 5 star check in rosters, Event Ticket Purchases | Leadership Coordinator, WASC Coordinator, Administration, Adjunct Personnel | Pull Event attendance's per month to complete a full year review by May 2026. Compare with behavior and disciplinary numbers to find correlation or causation.

## Goal 4 Timeline
Action Plan Goal # 4: East Union will develop new Student Learner Objectives in alignment with the schools new vision statement
Action Plan Step | Date to be completed | Items Needed | Who to send to | Goal Tracking
4.1b Survey will be sent out to students with a sentence starter, they will suggest statements to incorporate | 2024-05-01 | Sentence starter, 5 Star Survey | Visions Committee Secretary, Wasc Coordinator, Principal, AP | Survey Results, Compiled results. By May 23, 2024
4.1c Vision committee will meet 1 more time to finalize vision statement. | 2024-05-01 | Survey Results, Vision Staement | Principal, Asst Principal | Final Proposed vision statement to be submitted to school site council for vote.
4.2 East Union create new WASC Focus Groups for the upcoming School Year | 2024-05-01 | Previous Wasc Focus Group List | Staff, Administration, Wasc Coordinator | WASC Coordinator will email staff of new assigned groups. Certified and Classified
4.1d Vision statement will be sent out to to all stakeholder to inform of the new vision statement for East Union | 2024-08-01 | Final Vision Statement | Parents, Students, and Teachers | Voting Poll sent out to all stakeholders
4.1 Staff and School leadership will create a new vision statement with input from all stake holders. | 2024-08-01 | Vision Statement, Student Survey., Parent Survey, Staff Survey | Principal, Asst Principal | Vision sttement is supported by majority from each stake holder group and is implemented at the beginning of Semester 2.
4.3 WASC Focus Group Meeting to Discuss development of new SLO's based off of vision statement and Behavior Expectations. L-E-A-D. (1-academic, 1- behavior) with methods of Measurement | 2024-08-01 | LEAD Expectation breakdown, SLO Expectation form | WASC Coordinator | WASC Coordinator will receive all proposed SLO's, compile into a list and resend to all staff for review
4.3LEAD color groups will meet and review ALL the proposed SLO's for the values and metrics | 2024-09-01 | Compiled Proposed SLO's, LEAD Expectation list, Survey Link | WASC Coordinator (Planet Survey Link) | Groups will discuss and vote as a group on the proposed SLO's individually. WASC Coordinator will receive survey replies
4.4 Redrafted SLO's will be sent to whole staff for review and vote for finalization | 2024-11-01 | Proposed SLOs document and survey plant link for vote | WASC Coordinator (Planet Survey Link) | All staff will vote individually on th SLO's. WASC Coordinator will receive survey results.
4.5 SLO's will be submitted to the schoool site council for review and vote. | 2024-11-01 | SLO's Document | Administration | School site council will vote on the proposed SLO's administration will relay the end decision.
4.6 SLO's will be monitored monthly to track progress. | 2024-2026 | Surveys, 5 Star, Rosters (dependent on metrics of measurements) | WASC Coordinator, Administration | Compile results into monthly powerpoints to analyze effectiveness and strengths and weaknesses.
4.7 Review of the year will be sent out to all stakeholders of Progress of SLO's | May 2025, May 2026, May 2027, May 2028 | PPT of the SLO's Monitoring throughout the year | Staff, Administration, Wasc Coordinator | PPt will be sent to all stakeholders for review