| LEA: Bridge Preparatory Charter School | ARP-ESSER |
| --- | --- |
| BEDSCODE: 353100-86-1144 |  |
| # Project Period: 3/13/20 - 9/30/24 # Project No: 5880-21-5585 Allocation: $254,396 |  |

BUDGET NARRATIVE – revised Jan. 2022

| CODE/ BUDGET CATEGORY | EXPLANATION OF EXPENDITURES IN THIS CATEGORY (as it relates to the program narrative for this title) |
| --- | --- |
| Code 15 Professional Salaries | Activity 14 – We will provide mental health services and supports for all of our students but especially those adversely impacted by the COVID-19 pandemic and in need of more individualized attention by hiring a Social Worker. Social Worker (1 year: 2021-22) 1 @ $67,000/year = 67,000 Activity 14 = $67,000 Activity 15 – We will plan and implement activities related to summer learning & enrichment and supplemental after-school programs, including providing classroom instruction or online learning if necessary, to address the impact of lost instructional time of our students through the implementation of evidence-based interventions, and ensure that we will address the needs of low income students, students with disabilities, English learners, migrant students, students experiencing homelessness, and children in foster care. Summer School Learning & Enrichment Program – Summer 2022 and Summer 2023 We will offer a Summer School Learning & Enrichment Program for 40 students in Grades K-4 for 10 days each Summer for two years – 5 hours each day. We will provide breakfast and lunch on-site for our students (see Code 45). 5 Summer School Teachers x 10 days @ $250/day = $12,500/year x 2 years = 25,000 2 Summer School Administrative Assistants x 10 days @ $100/day = $2,000/year x 2 years = 4,000 1 Summer School Supervisor x 10 days @ $350/day = $3,500/year x 2 years = 7,000 Total Summer School: 36,000 Supplemental After-School Academic Enrichment Program – 2021-22 and 2022-23 We will offer a Supplemental After-School Academic Enrichment Program for 50 students in Grades K-4 for two school years – for 80 days each year – for 1 ½ hours a day immediately following the regular school day. 5 After-School Teachers x 1 ½ hrs./day x 80 days @ $50/hr. = $30,000/year x 2 years = 60,000 1 After-School Administrative Assistant x 1 ½ hrs./day x 80 days @ $18/hr. = $2,160/year x 2 years = 4,320 1 After-School Supervisor x 1 ½ hrs./day x 80 days @ $75/hr. = $9,000/year x 2 years = 18,000 Total After-School: 82,320 Activity 15 = $118,320 Total Code 15 = $185,320 |
| Code 45 Supplies and Materials | Activity 13 – Purchasing educational technology for students who are served by the LEA that aids in regular and substantive educational interaction between students and their classroom instructors, including low-income students and students with disabilities. LED Smart Boards (Mount) 4 @ $2,900 = 11,600 LED Smart Boards (Non-Mount) 3 @ $2,500 = 7,500 Total Activity 13 = $19,100 Activity 15 – We will plan and implement activities related to summer learning & enrichment and supplemental after-school programs, including providing classroom instruction or online learning if necessary, to address the impact of lost instructional time of our students through the implementation of evidence-based interventions, and ensure that we will address the needs of low income students, students with disabilities, English learners, migrant students, students experiencing homelessness, and children in foster care. Summer School Learning & Enrichment Program – Summer 2022 and Summer 2023 Instructional Supplies & Materials to support students in Summer School Program: Examples include: Student Academic Materials: workbooks, assessment materials; Student Classroom Supplies: pens, pencils, notebooks, binders, binder sheets, folders; Staff Supplies: binders, post-its, index cards, binder sheets, folders, pens, markers, highlighters; Multisensory Student Furniture: individual student rocking chairs, individual student supply storage, portable lap desks. 40 students @ $118.75 = $4,750/year x 2 years = 9,500 Supplemental After-School Academic Enrichment Program – 2021-22 & 2022-23 Instructional Supplies & Materials to support students in After-School Program: Examples include: Student Academic Materials: workbooks, assessment materials; Student Classroom Supplies: pens, pencils, notebooks, binders, binder sheets, folders; Staff Supplies: binders, post-its, index cards, binder sheets, folders, pens, markers, highlighters; Multisensory Student Furniture: individual student rocking chairs, individual student supply storage, portable lap desks. 50 students @ $75/student = $3,750/year x 2 years = 7,500 Activity 15 = 17,000 Total Code 45 = $36,100 |
| Code 80 Employee Benefits | Activity 14: $67,000 x 28% = 18,760 Activity 15: $118,320 x 7.65% = 9,051 (only adding 8,000) 26,760 Employee Benefits 27,760 |
| Code 90 Indirect Cost | Activity 20 – Indirect Costs that are necessary to maintain the operation of and continuity of services in our LEA and to help us defray the costs of proper and efficient performance in the administering of our ARP-ESSER funded program. Indirect Cost $248,180 x 2.5046% = 6,216 |