## One Plan
We dare to empower the whole student to profoundly impact our world. 2021-22 Doherty HS Unified Improvement Plan - Accountability Chart
Student Engagement
Major Improvement Strategy | Objective | Action Steps | Date to be Completed | Person Responsible | Collaborators | Status
Implement Pre-AP shared principles (close observation and analysis, evidence based writing, higher order questioning, and academic conversations) | Increase rigor, student engagement, and integrate with the D11 graduate profile. | Deliver Pre-AP shared principles PD to Doherty staff. | 2021-08-01 | Lauren/Hillary | Lana, Stephanie, and Elaine
|  | Deliver D11 Graduate Profile PD to all Doherty Staff. | 2021-08-02 | Lauren/Hillary | Lana, Stephanie, and Elaine | In Progress
|  | Provide every classroom with Pre-AP Shared Principles poster | 2021-08-03 | Amy | Lana, Hillary, Elaine, and Lauren | Completed 9/20
|  | Provide every classroom with D11 Graduate Profile poster. | 2021-08-04 | Amy | Lana, Hillary, Elaine, and Lauren | Completed 9/20
|  | Introduce Pre-Ap Shared Principles in CCR. | 2021-09-01 | Lauren | CCR Teachers
|  | Introduce D11 Graduate Profile in CCR | 2021-09-02 |  | CCR Teachers
|  | Collaborate with staff to develop "look fors" for classroom observations and evaluations. | 2021-10-01 | Lauren/Hillary/Lana | Elaine | In Progress
|  | Evaluators utilize "look fors" during observations | 2022-04-01 | Lana, Hillary, Elaine, and Lauren | Lana, Hillary, Elaine, and Lauren
|  | Administer Pre-AP quarterly assessments with fidelity. | 2022-05-01 | Hillary | Core Pre-AP teams, Pre-AP Coordinator, Evaluators | In Progress
Strengthen teacher and administrator efficacy by re-establishing a positive and engaging culture. | Teachers and administrators will share a strong sense of responsibility for student development, school improvement, and professional growth. | Team will attend Kagan training and determine next steps for whole staff roll out. | 2021-08-01 | Lana | Hillary, Lauren, Elaine, Stephanie, and Chris F., Sarah O., Missi M., Sara M., Chris H. | In Progress
|  | Collaboratively agree on schoolwide administrator, staff and student expectations. | 2021-08-01 | Lana/Hillary | Staff | Completed 8/11
|  | Provide Kagan training to staff. | Ongoing thru school year 5 sessions planned | Lauren/Hillary | Lana, Elaine, Steph, and teachers | In Progress
|  | Evaluators determine "look fors" while doing classroom observations. | 2021-12-01 | Hillary | Lana, Elaine, Lauren, and Steph | In Progress
|  | Train 100% of Doherty Staff on MHFA. | September 2021. | Tim and Kathy R. | Tim and Kathy R. | In Progress - Have 10 Certified Staff to Train
|  | Train 10th graders on MHFA. | 2022-05-01 | Tim and Kathy R. | Tim and Kathy R. | In Progress
|  | Offer Trauma Informed Teaching training and book study for volunteers. | 2022-05-01 | Hillary/Lauren | Lana, Elaine, Steph | In Progress

## Resources
Resouces
Kagan | Kagan Website | Kagan Strategy Quick Reference
VIDEO
Teen Mental Health First Aid | Web Site
D11 Graduate Profile | Graduate Profile
Pre AP Shared Principles | Shared Principles
Trauma Informed Teaching | Resource

## Data Sets That Were Considered
Data Sets
Attendance
Failure Rate
Demographics
5 Es
Youth Truth Survey
Special Populations
Behavior Data
Permits/Transfers
Assessments