## Sheet1
LINCOLN ACADEMY BUILDING A FIRE ALARM/SPRINKER PROJECT
CONTRACTED SERVICES |  | DATE | PAYMENTS REASON |  |  | AMOUNT PAID
TAMI LYNN HOLLEY |  |  | Tami Lynn Holley
Engineering Services | 12760 | 2018-07-07 | Engineering Services to date |  |  | 9953
C/O Change of Scope | 2900 | 2018-07-07 | Additional Scope Coordination |  |  | 2900
Addl to Al Bruch Design SPRINKLERS | 11880 | 2018-07-07 | Sprinkler Design |  |  | 2700
| 27540 |  |  |  |  | 15553
Tami Lynn Holley
|  | 2019-01-24 | Fire Sprinkler Shop Drawing |  |  | 8100
|  | 2018-01-24 | TLH fire sprinkler coordination |  |  | 1080
9180
TLH Fire dba Tami Lynn Holley
|  | 2019-07-29 | Fire Alarm shop drawing review |  |  | 1000
|  | 2019-07-29 | Fire Alarm record drawomg review |  |  | 766
1766
WEIFIELD |  | 2018-08-31 | Weifield APP #1 | ORIGINAL | RETAINAGE | AMOUNT PAID
Fire Alarm | 221960 |  | Fire Alarm Drawings | 3250 | 162.5 | 3087.5
Sprinkler System | 110960 |  | Sprinkler Drawings | 3900 | 195 | 3705
Patch and Paint | 11051 |  | Bond and Permit | 14737 | 736.85 | 14000.15
Ceiling Grid | 5525 |  |  | 21887 | 1094.35 | 20792.65
349046
|  | 9/50/2018 | Weifield APP #2 | ORIGINAL | RETAINAGE | AMOUNT PAID
|  |  | Fire Alarm Parts | 1685 | 84.25 | 1600.75
|  |  | Fire Alarm Drawings | 2600 | 130 | 2470
|  |  | Sprinkler Drawings | 3900 | 195 | 3705
|  |  |  | 8185 | 409.25 | 7775.75
|  | 2018-10-31 | Weifield APP #3 | ORIGINAL | RETAINAGE | AMOUNT PAID
|  |  | Fire Alarm Parts | 1404 | 70.2 | 1333.8
|  |  | Fire Sprinkler Vendor | 2888 | 144.4 | 2743.6
|  |  |  | 4292 | 214.6 | 4077.4
|  | 2018-11-30 | Weifield APP #4 | ORIGINAL | RETAINAGE | AMOUNT PAID
|  |  | Mobilization | 12298 | 614.9 | 11683.1
|  |  | Fire Alarm Material | 9689 | 484.45 | 9204.55
|  |  |  | 21987 | 1099.35 | 20887.65
|  | 2018-12-31 | Weifield APP #5 | ORIGINAL | RETAINAGE | AMOUNT PAID
|  |  | Fire Alarm Parts | 53069 | 2653.45 | 50415.55
|  |  | Fire Alarm Shop Drawings | 650 | 32.5 | 617.5
|  |  | Fire Alarm Install | 17258 | 862.9 | 16395.1
|  |  |  | 70977 | 3548.85 | 67428.15
|  | 2019-05-31 | Weifield APP #6 | ORIGINAL | RETAINAGE | AMOUNT PAID
|  |  | Fire Sprinkler - vendor | 10607 | 530.35 | 10076.65
|  |  | Sprinkler install | 4873 | 243.65 | 4629.35
|  |  | Fire Alarm Old System Demo | 9453 | 472.65 | 8980.35
23686.35
|  | 2019-06-30 | Weifield APP #7 | ORIGINAL | RETAINAGE | AMOUNT PAID
|  |  | Fire Sprinkler - vendor | 26990 | 1349.5 | 25640.5
|  |  | Sprinkler install | 7310 | 365.5 | 6944.5
|  |  | Fire Alarm install | 23349 | 1167.45 | 22181.55
|  |  | Fire Alarm Old System Demo | 4726 | 236.3 | 4489.7
59256.25
|  | 2019-07-31 | Weifield App #8 | ORIGINAL | RETAINAGE | AMOUNT PAID
|  |  | Fire Sprinkler - vendor | 13495 | 674.75 | 12820.25
|  |  | Sprinkler install | 29238 | 1461.9 | 27776.1
|  |  | Fire Alarm Install | 45683 | 2284.15 | 43398.85
|  |  | Fire Alarm Old System Demo | 4726 | 236.3 | 4489.7
|  |  |  | 93142 | 4657.1 | 88484.9
Vanir Construction Management
Project Manager | 3072 |  | VANIR WORK FEBRUARY 2019 |  |  | 1980
Project Director | 1980 |  | VANIR WORK MARCH 2019 |  |  | 0
reimbursables | 50 |  | VANIR WORK APRIL 2019 |  |  | 210.5
| 5102 |  | VANIR WORK MAY 2019 |  |  | 256
|  |  | VANIR WORK JUNE 2019 |  |  | 384
|  |  | TOTAL PAID IN 18-19 | TOTAL PAID IN 18-19 | TOTAL PAID IN 19-20
TOTAL PROJECT BUDGET | 381688
|  |  | Total paid Tammy Holley | 24733 | 1766
|  |  | Total paid Weifield | 203904.2 | 88484.9
|  |  | Total paid Vanir | 2830.5
|  |  | Grand total paid | 231467.7 | 90250.9
|  |  | REMAING DUE ON PROJECT. | 59969.4
=