## Sheet1
LINCOLN ACADEMY BUILDING A FIRE ALARM/SPRINKER PROJECT
CONTRACTED SERVICES |  | DATE | PAYMENTS REASON |  |  | AMOUNT PAID | PROJECTED STILL DUE
TAMI LYNN HOLLEY |  |  | Tami Lynn Holley
Engineering Services | 12760 | 2018-07-07 | Engineering Services to date |  |  | 9953 | 2807
C/O Change of Scope | 2900 | 2018-07-07 | Additional Scope Coordination |  |  | 2900 | 0
Addl to Al Bruch Design sPRINKLERS | 11880 | 2018-07-07 | Sprinkler Design |  |  | 2700 | 9180
| 27540 |  |  |  |  | 15553 | 11987
WEIFIELD |  |  | Weifield | ORIGINAL | RETAINAGE | AMOUNT PAID
Fire Alarm | 221960 |  | Fire Alarm Drawings | 3250 | 162.5 | 3087.5
Sprinkler System | 110960 |  | Sprinkler Drawings | 3900 | 195 | 3705
Patch and Paint | 11051 |  | Bond and Permit | 14737 | 736.85 | 14000.15
Ceiling Grid | 5525 |  |  | 21887 | 1094.35 | 20792.65
| 349046 | [5 empty] | 328253.35 | Includes Retainage.
TOTAL PROJECT BUDGET | 376586