## Slide 1: Churchville-Chili CSD Capital Project Update Board Of Education Meeting June 25, 2024

## Slide 2: Current Capital Projects
Capital Improvement Project Phase 6-2
  MS Renovations, Turf Baseball & Softball, Tennis Courts, Buffalo Road Entry, Transportation Bus Parking Lot, MS Bus Loop
2023/2024 Capital Outlay CES Floors
  Staff Lounge, Classrooms 301, 303, 306, 307, 307A, & Office 309A

## Slide 3
Phase VI Construction Project is approximately 33% complete
Construction Contingency Budget $ 3,369,829
Change Order Total (May 2024) $ 853,311
Remaining Construction Contingency $ 2,516,518
Project Team is following approximately $180,768 in potential issues pending approval:
Overall Phase VI Project Budget
INCIDENTAL BUDGET $ 11,332,254
CAPITALIZED INTEREST/DANSY $ 3,887,503
CONSTRUCTION CONTINGENCY $ 3,369,829
PHASE VI-1 PROJECT CONTRACTS $ 4,862,980
PHASE VI-2 PROJECT CONTRACTS $ 31,628,666
Phase VI Project Budget

## Slide 4: Capital Improvement Projects Schedule Update
Capital Improvement Project Phase 6-2:
  Area D Classrooms (3524, 3522, 3520, 3518, 3516, 3514)
    Complete installation of new windowsills
    Complete flooring installation
    Complete install of new appliances (washer, dryer, stove, refrigerator)
    Complete final cleaning
  Site
    Complete softball field flat drain install
    Begin softball field concrete curb install
    Complete setting of tennis court fence posts
    Continue HS entry/exit way work

## Slide 5
Corridor 3800 Wall Tile
Corridor 3800 Wall Tile

## Slide 6
FACS Room Drywall
FACS Room Millwork, Sinks, & Hoods

## Slide 7
Area D Classroom Floor Prep
Area D Classroom Flooring

## Slide 8
HS New Entry/Exit Topsoil Removal
HS New Entry/Exit Topsoil Removal

## Slide 9
Tennis Court Stone
Tennis Court Area
Underground Electric
Tennis Court Stone Subbase
Tennis Court Grading

## Slide 10
Baseball Field Athletic Lighting Drilling
Baseball Field Athletic Lighting

## Slide 11
Baseball Field Bullpen Foundation
Baseball Field Bullpen

## Slide 12
Baseball Field Decals
Baseball Field Pitching Mound
Baseball Field Infill Grooming
Baseball Field Turf

## Slide 14: QUESTIONS