## Slide 1
HIGH SCHOOL CAMPUS PLANNING PROJECT
Schematic Design Update Presentation
28 JANUARY 2025
METHACTON
SCHOOL DISTRICT

## Slide 2
DISCUSSION
01 RECAP
02 CURRENT SITE PLAN
03 PROGRAM AND SCOPE ADJUSTMENTS
01
02
03

## Slide 3
01
02
03
04
01
RECAP
METHACTON HIGH SCHOOL
SCHEDULE & COST ESTIMATES

## Slide 4: Timeline – Current Design Schedule
MILESTONES DATES BOARD DECISION
2024 - 2025
Schematic Design (SD) 10/29/24 - 3/18/25 3/25/25
Design Development (DD) 3/26/25 - 9/16/25 9/23/25
Approve Act 34 Resolution
ACT 34 Hearing 10/21/25
Construction Documents (CD) 9/17/25 - 1/25/25 January 2026
Bidding 2/6/26 – 3/17/26
Board Approval of Bids March 2026
*Architect and Owner’s Representative will provide monthly progress reports to Board of School Directors
**Schedule is completely contingent on permitting and approval process

## Slide 5: Timeline – Construction
MILESTONES DATES
2026 - 2028
Construction May 2026 – December 2028
Building Construction May 2026 – August 2028
Students move to new building December ‘28
Demolition of existing HS January ’29 – March ‘29
Site restoration April ’29 – July ‘29
Project Complete Summer 2029
**Schedule is completely contingent on permitting and approval process

## Slide 6: Land Development Status
KEY SUBMISSIONS
2026 - 2028
Worcester Township Meeting – November 11
Sketch Plan Submission – January 7
Infiltration & Geotechnical Testing on-going
NPDES Submission to Montgomery County Conservation District – (March/April)
Traffic Impact Study – starting in February
Meeting with adjacent neighbors – January 13

## Slide 7: Zoning Considerations
WORCESTER TOWNSHIP
Public School is a use permitted by Conditional Use in AGR district
  CU may or may not be needed since public school is existing use
Zoning Relief likely needed:
  Building height – 35 ft, not exceeding 2.5 stories
  Impervious surface coverage – limit is 40%, existing is 45%, proposed is 47%
  Parking lot(s) within building setbacks – 250 feet front yard
  Steep slope disturbance
  Varsity baseball/softball field lighting; also requires Conditional Use
  Height of parking lot lighting (12’ max)
Parking, Traffic, and Speeding are all areas of concern and are viewed as opportunities for improvement. Off-site parking should be eliminated if possible with increased parking on the campus.

## Slide 9
COST ESTIMATES
HARD COSTS Low Range High Range
New H.S. Building Construction $120,250,000 $130,000,000
Utilities (Water, Sewer, Storm, Gas) $ 13,600,000 $ 13,600,000
Site Excavation and Improvements $ 12,600,000 $ 12,600,000
Athletic Facilities Improvements $ 6,612,000 $ 6,894,000
Abatement & Demolition: HS & Farina $ 3,725,000 $ 4,225,000
Offsite Road Improvements & Phasing Costs $ 1,050,000 $ 1,050,000
$157,837,000 $168,369,000
SOFT COSTS
Fees and Land Development $ 14,729,000 $ 15,525,000
Technology, Fixtures & Equipment $ 4,500,000 $ 4,500,000
Design & Construction Contingency $ 12,626,000 $ 13,470,000
Escalation at 3% Annually $ 16,416,000 $ 17,464,000
$ 48,271,000 $ 50,959,000
Total Project Budget $206,108,000 $219,328,000

## Slide 10: Other Opportunities for Input
Land Development Approval Process – Township Planning and Supervisors meetings
County Conservation District (NPDES) approvals
Teacher meetings for space design
Student input sessions
Parent / Community presentations of project progress
Web-hosted project image updates
10

## Slide 11
01
02
03
04
02
CURRENT PLANS
METHACTON HIGH SCHOOL
SITE PLANS

## Slide 13
NORTH
DEVELOPMENT AREA
NON- BUILDABLE AREA
NON- BUILDABLE AREA
NON- BUILDABLE AREA
NON- BUILDABLE AREA
NON- BUILDABLE AREA

## Slide 14
BUS DROP-OFF
PARENT DROP-OFF
OPTION 1 – SITE CIRCULATION
EXISTING
BASEBALL FIELD
EXISTING
MULTI-PURPOSE FIELD
EXISTING STADIUM
TRANSPORTATION
NEW HS BUILDING
EXISTING TENNIS COURTS
NEW
FIELDHOUSE
FIELD EVENTS
ABOVE GROUND SWM BASIN
PROPOSED REVISED SITE PLAN
STUDENT PARKING

## Slide 15
BUS DROP-OFF
STUDENT PARKING
PARENT DROP-OFF
OPTION 1 – SITE CIRCULATION
EXISTING
BASEBALL FIELD
SOFTBALL FIELD
MULTI-PURPOSE FIELD
EXISTING
MULTI-PURPOSE FIELD
EXISTING STADIUM
TRANSPORTATION
NEW HS BUILDING
EXISTING TENNIS COURTS
NEW
FIELDHOUSE
FIELD EVENTS
ABOVE GROUND SWM BASIN
ABOVE GROUND SWM BASIN
ABOVE GROUND SWM BASIN
PROPOSED REVISED SITE PLAN

## Slide 16
03
PROJECT & SCOPE ADJUSTMENTS
IPC, DAO, SCIENCE LABS, POOL
01
02
03
04

## Slide 17
PROJECT & SCOPE ADJUSTMENTS
01 INSTRUCTIONAL PLANNING CENTERS
02 DISTRICT ADMINISTRATION OFFICE
03 SHARED SCIENCE LABS
04 POOL BULKHEAD
PREP
LAB
CLASSROOM
CLASSROOM

## Slide 18
28 JANUARY 2025
QUESTIONS?