## Cover Page
TSDS KNOWN ISSUES REPORT As-Of: March 7, 2025

## New & Updated Issues
NEW ISSUES
COMPONENT | SUB-COMPONENT | ISSUE | IMPACT | WORKAROUND | REPORTED DATE | TARGET RELEASE DATE
PEIMS SUMR | Reports | The CSV option for report PDM3-120-002 Migratory Students by Grade is displaying 0 counts for every grade level. | N/A | Use the PDF option for the report. | 2024-09-30 | 2025-04-25
PEIMS SUMR | Validation Rules | Based upon guidance from the TEA Texas Tutoring program area, the domain of values will be increased for AssignedHoursAcceleratedInstruction (E3086) and CompletedHoursAcceleratedInstruction (E3087) from 00.00-60.00 to 00.00-90.00. | The API and IODS have a pending update for this change. If an LEA uses a value greater than 60.00 but less than or equal to 90.00, they will receive a Level 1 error on the AssignedHoursAcceleratedInstruction (E3086) or CompletedHoursAcceleratedInstruction (E3087) even though the data is valid. | N/A | 2025-03-06 | 2025-04-25
UPDATED ISSUES
COMPONENT | SUB-COMPONENT | ISSUE | IMPACT | WORKAROUND | REPORTED DATE | TARGET RELEASE DATE
* An asterisk indicates which column(s) was updated

## Scheduled for Release
For information on recently released TSDS updates, review the TSDSKB-543 for the Field Coordination Network Newsletters.
COMPONENT | SUB-COMPONENT | ISSUE | IMPACT | WORKAROUND | REPORTED DATE | TARGET RELEASE DATE
Class Roster | Reports | For reports CLS2-100-001 and CLS2-100-002 the below grade levels are displaying a numeric value instead of the alpha designation: - "0" displaying instead of "KG" - "-1" displaying instead of "PK" - "-2" displaying instead of "EE" Additionally, numeric grade levels are displaying as blank on the reports. |  |  | 2025-02-22 | 2025-03-14
PEIMS Summer | Reports | 2024-2025 Career and Technical (CTE) Service ID Tier data is currently not available from the program area. The following reports will not have CTE data: PDM3-130-001 Superintendent’s/Principal’s Report of Student Attendance, PDM3-130-002 Superintendent's/Principal's Report of Career & Technical Education Eligible Days, PDM3-130-005 Comparison of Current and Prior Year Attendance, and PDM3-130-008 Superintendent's/Principal's Summary Report of Student Attendance. | No CTE data will print on the reports. | N/A | 2024-10-30 | 2025-03-31
ECDS Kindergarten | Reports | For the ECD0-000-001 Early Childhood Assessment Completion campus level report "Students Enrolled by Teacher" is displaying an incorrect total if an optional StudentSectionAssociation.EndDate (E3020) is not provided. | The ECD0-000-001 Campus level report will display an incorrect total if an optional StudentSectionAssociation.EndDate (E3020) is not provided. | LEAs can use the ECD0-000-004 Early Childhood KG Data Submission report to verify their staff data for theECDS KG submission. | 2025-01-13 | 2025-04-04
PEIMS | Application | Campus collection status displays as 'Not Loaded' when Campus level promotions are performed by LEA. |  |  | 2024-09-03 | 2025-04-25
PEIMS Fall | Reports | Report PDM1-231-002 Percentage of Change from Prior Year: Student Demographics, Characteristics, & Programs: When printing report by Campus Level - Grouped by Selected Programs, the campus name should print only once for each program for all the program indicators. The campus name is repeated intermittently on the program indicators. | N/A | N/A | 2024-10-26 | TBD
PEIMS Fall | Reports | Report PDM1-231-002 Percentage of Change from Prior Year: Student Demographics, Characteristics, & Programs is including Associate Degree as part of the enrollment programs to be selected. Associate Degree is only reported for leavers so the counts will always be zero. Associate Degree should not be included on the enrollment section of this report. | Associate Degree student counts will always have zeros. LEAs can ignore these student counts. | N/A | 2024-10-26 | TBD
PEIMS Fall | Reports | Report PDM1-120-002 EB/BIL/ESL and Parental Denial Students by Program and Grade is not displaying the grade level totals for the Alternative Language Program. The report total for Alternative Language Program is displaying correctly. | The grade level totals for the Alternative Language Program are not displayed on the report. | The report total for Alternative Language Program are displayed correctly. | 2024-12-18 | TBD
PEIMS Fall | Promotions | Title I, Part A Program is being promoted for Leavers with a blank Title I Part A code. This will inflate the record counts for PDM1-230-002 Submission Summary Report and the Prepare/Finalize screen. Only the record counts are off, since there is no code value to be counted. | The record counts are including the Title I, Part A for Leavers with a blank Title I, Part A code. | N/A | 2024-12-02 | TBD
PEIMS Fall | Reports | The CSV version of PDM1-111-002 Staff Roster report is missing the Role ID and description. This is a sub header on the PDF version of the report. | N/A | N/A | 2025-01-10 | TBD
ECDS Kindergarten | Reports | For the ECD0-000-005 Early Childhood Incomplete KG Assessment report, students are being incorrectly displayed on the report who have met the assessment domain/academic subject requirements for KG assessment readiness that are listed in the ECDS Assessment Specifications document in TEDS for the BOY KG TX-KEA English or BOY KG TX-KEA Spanish assessments. | The ECD0-000-005 report will incorrectly display students on the report who have met the 'Required for KG Readiness' assessment domain/academic subjects for the BOY KG TX-KEA English or BOY KG TX-KEA Spanish assessments. | N/A | 2025-01-16 | TBD
ECDS | Reports | The ECD0-000-004 Early Childhood KG Data Submission report has the following issues when run by Student Criteria Selection parameters: -KG Students w/ BOY Assessments is displaying the incorrect Homeroom teacher for students that have changed sections. -KG Students w/ No BOY Assessments is displaying some students that have assessment data. | Users will not be able to verify the data accurately on the ECD0-000-004 report if they select the Student Criteria Selection parameters of KG Students w/ BOY Assessments or KG Students w/ No BOY Assessments. | Users should use the 'All KG Students (with or w/o BOY Assessments)' parameter value under the Student Selection Criteria to verify their data on the ECD0-000-004 report. | 2025-01-24 | TBD
PEIMS Fall | Validations | Fatal Rule 20030-0010 states BudgetFund must not be '420'. In the identifying information the UI displays 'BudgetFunction' instead of 'BudgetFund'. | The rule is firing correctly, just displaying the wrong data element name. | N/A | 2025-01-28 | TBD
UPDATED PEIMS Fall | Reports | * Report PDM1-231-002 Percentage of Change from Prior Year: Student Demographics, Characteristics, & Programs is including Associate Degree as part of the enrollment programs to be selected. Associate Degree can be reported for enrolled students and leaver students. The percent change report will only count Associate Degree for enrolled students. This could cause confusion on the counts, the Associate Degree will be removed from the enrollment section of this report. | * The Percent Change Report for Associate Degree student counts will only include the enrolled students where other reports have Associate Degree counts for enrolled students and leaver students. | N/A | 2024-10-26 | TBD
ECDS | Prekindergarten | Fatal rules 40110-0217 and 40110-0218 are firing due to a promotion logic issue where if the OrderOfPKFundingSource descriptor value is "1" but has an EndDate, the PrimaryPKFundingSource descriptor value is still being promoted. | LEAs will see inaccurate information displayed for the PrimaryPKFunding Source on the ECD0-000-006 PK Data Submission report and also be unable to complete their ECDS PK Submission. | N/A | 2025-01-24 | TBD
PEIMS EXYR | Reports Help | PDM4-404-002 Career and Technical Education Student Roster and PDM4-404-003 Student Counts by Career and Technical Indicator Code and Grade do not have reports help. |  | LEAs can utilize PEIMS Summer Report Help for PDM3-404-002 Career and Technical Education Student Roster and PDM3-404-003 Student Counts by Career and Technical Indicator Code and Grade. | 2024-10-11 | TBD 2025-2026
PEIMS FALL | VALIDATIONS | Special Warning rules 40203-0032 and 40203-0033 are triggering for campuses serving grades EE-08 in both Level 2 and Level 3 validations. | These are special warnings, the LEA may still complete the submission. | N/A | 2024-11-04 | TBD 2025-2026

## Backlog
COMPONENT | SUB-COMPONENT | ISSUE | IMPACT | WORKAROUND | REPORTED DATE | TARGET RELEASE DATE
Census Block Group Tool | Single Address Entry Option | The CBGT single address entry option is currently not accepting a '#' character associated with the address name as a valid value. | N/A | The batch entry option can be used to retrieve a Census Block Group number for student addresses that contain the '#'. | 2023-10-16 | TBD
Class Roster | Prepare/Finalize Submission | Some LEAs that are promoting Class Roster Winter data for the Staff > Staff Basic subcategory, who also have data for the Staff > Staff Association subcategory, may encounter an issue where the Staff > Staff Association record counts will display in the Staff > Staff Basic Information record counts on the Prepare/Finalize screen. | N/A | LEAs can verify their Staff Basic data counts by running the CLS2-000-005 report and the CLS2-100-007 report to verify their Staff Association records count totals related to the total TIA designation Codes. | 2024-07-01 | TBD
Class Roster | Reports | When the following reports are run for the first time a status of 'undefined' is displayed. - CLS2-100-003 Winter Staff Class Assignment Report - CLS2-100-006 Winter Submission Summary Report | Once the refresh button is clicked, the status appropriately displays 'in progress'. This issue does not impact the generation of the report. | LEAs can click the 'refresh' button to display the correct status. | 2023-05-26 | TBD
Core | Validation Request Details Page | The ‘back’ button on the Validation Request Details page for each Core data collection is not working. | N/A | LEAs can utilize the breadcrumb trail located underneath the header bar to return to the previous screen. | 2023-06-09 | TBD
Core | Status History screen | When sorting the Updated Date column in ascending or descending order, the year is not used to determine the order. Example, 12/31/19 is listed before 1/1/20 when sorting in descending order. | Cosmetic issue | N/A | 2020-05-01 | TBD
Core | Core Application | For ESC users (logged into Core as an ESC) with additional LEA-level access for one or more of their LEAs (for example, promote/validate privileges), a forbidden message may appear when they navigate from the screen containing the additional access to another LEA for which they do not have LEA-level access. | N/A | Click on the home icon to re-establish the proper access for the organization that has been selected. | 2020-01-09 | TBD
Core | Core Application | When a Core data submission is closed, the banner message on the Promote Loaded Data page does not display the correct message. | Cosmetic issue | N/A | 2019-11-17 | TBD
Core | Revisited Links | Links to previously viewed pages are being greyed out when they should be blue. | Cosmetic issue | N/A | 2017-03-31 | TBD
PEIMS | Validation Rules Count | The Validation Rules Count page is loading slowly and intermittently fails to produce the requested list. | N/A | The LEA can download the Validation Errors by Job to an XLS spreadsheet and use column filters to review and sort by Fatal, Warning, and Special Warning. | 2023-10-20 | TBD
PEIMS | Notifications | ESCs and LEAs are not always getting an email notification when the PEIMS submission has been completed. | N/A | Users should verify submission status on the Prepare/Finalize screen. | 2020-08-26 | TBD
PEIMS | Data Validation | If the Staff Responsibility validation error limit is set to 5,000 and the limit is reached on more than one rule, the validation will fail. | N/A | LEAs should set the validation error limit to 1,000. | 2018-11-15 | TBD
PEIMS | Reports | The bundle reports feature returns the message “Completed with Errors”, but it doesn’t tell you which reports failed. | N/A | N/A | 2018-06-20 | TBD
PEIMS | Retrieve Submission Data | The Retrieve Submission Data function pulls all current and prior year data elements regardless of the school year selected when it should be year specific. | N/A | N/A | 2017-12-06 | TBD
PEIMS | LEA Overview Page | Sorting on the 'Last Updated Date' column does not work. | N/A | N/A | 2017-12-04 | TBD
PEIMS | PEIMS Application | The table print outs only include the first page. | N/A | N/A | 2017-10-30 | TBD
PEIMS | View Validation Errors | The View Validation Errors page severity column (F, SW, W) does not consistently display validation error counts from the last validation event. | N/A | N/A | 2017-10-20 | TBD
PEIMS | Prepare/Finalize Submission | The Prepare/Finalize screen extension column may display an incorrect extension date. Also, when an extension has been rejected, an extension date is populating in the extension column. | N/A | N/A | 2017-07-21 | TBD
PEIMS | Prepare/Finalize Submission | The Extension Date column is currently shown in Campus Overview. It should only show for LEA Overview. | N/A | N/A | 2017-03-28 | TBD
PEIMS | Monitor Submission Retrieval | After downloading the data, an error message occurs when switching to a different collection, year, or LEA. | N/A | N/A | 2016-10-04 | TBD
PEIMS | Extension Request | The Extension Request history table should show the latest comments from an approval/rejection of an extension request. It currently maintains the LEAs original comment. | N/A | N/A | 2016-09-13 | TBD
PEIMS | SOA | Warning message reminding the user that they must contact TEA to have the status on the collection reset is not displayed when SOA is rejected after LEA/ESC Collection data is in Accepted status. | N/A | N/A | 2016-08-11 | TBD
PEIMS | Status History page | SOA status is not displayed on Status History page for campus users. | N/A | N/A | 2016-04-28 | TBD
PEIMS | Data Element Summary | LEA users can switch to campus on the Data Element Summary page, but they should receive an Access Denied page. | N/A | N/A | 2016-03-10 | TBD
PEIMS | Student Roster Search | The Student Roster Search is not retrieving the search results when only Ethnicity is selected and one of the mandatory fields is entered. | N/A | N/A | 2016-03-01 | TBD
PEIMS | PEIMS Application | When users refresh the page, the stage 2 screen displays 'Not Configured for PEIMS' instead of displaying the timeout page. | N/A | N/A | 2016-02-02 | TBD
PEIMS | PEIMS Application | When logging back into the PEIMS application, the collection does not retain the last collection visited if it is an 'Accepted' collection. | N/A | N/A | 2015-12-11 | TBD
PEIMS FALL | Reports | CTE indicator data in the Prior Year Data column of the following report is currently not displaying the correct value for students with more than one program of study. - PDM1-124-007 Graduate Roster by Graduation Type | N/A | * LEAs can utilize the prior year PEIMS Summer Submission report, PDM3-404-002, Career and Technical Education Student Roster for students that had course completion data reported in the Summer Submission. and * LEAs can utilize the prior year PEIMS Extended Year Submission report, PDM4-404-002, Career and Technical Education Student Roster if the student had course completion data reported in the Extended Year Submission. | 2023-10-30 | TBD
PEIMS FALL | Reports | There is a sort order mismatch for the following report between the PDF and CSV version of the Campus level report. The CSV version does not include the campus ID as part of the sort order. - PDM1-120-006 Students not Enrolled on Selected PEIMS Date | N/A | N/A | 2019-05-28 | TBD
PEIMS FALL | Data Validation | Org ID of Data in Error' in the Identifying info should be Campus ID instead of LEA ID for the following validation rule. - 40203-0015 | N/A | N/A | 2018-10-17 | TBD
PEIMS SUMR | Data Promotion | The PEIMS Summer Education Organization > Calendar subcategory is incorrectly promoting calendar type 16 which should only be promoted for ADSY calendars for Extended Year. | Fatal error 10200-0069 is firing for each calendar date where the calendar type is '16' in the PEIMS Summer Submission. | N/A | 2024-09-16 | TBD
PEIMS SUMR | Reports | The following report has not been updated for the flexible attendance calculations to use the adjusted eligible equivalent days instead of eligible equivalent days. - PDM3-130-005 Comparison of Current and Prior Year Attendance | LEAs with flexible attendance where eligible equivalent days does not match adjusted eligible equivalent days, will not be able to verify the total refined ADA from PDM3-130-005 by adding the total refined ADA from PDM3-130-008 Superintendent’s Summary Report of Student Attendance to the total refined ADA from PDM3-130-014 Flex Attendance – Superintendent’s Summary Report of Student Attendance. | N/A | 2023-10-02 | TBD
PEIMS SUMR | Data Validation | The following validation rule is displaying incorrect error text and identifying information. - 40110-0077 | N/A | N/A | 2019-05-16 | TBD
PEIMS SUMR | Data Validation | The Org ID that is displayed in the 'Identifying info' should be the Campus ID instead of LEA ID for the following validation rule. - 43415-0006 | N/A | N/A | 2019-03-15 | TBD
PEIMS SUMR | Data Validation | Error data is showing grade level code as NULL for the following validation rule. - 43415-0052 | N/A | N/A | 2017-10-16 | TBD
PEIMS SUMR, PEIMS EXYR | Data Validation | The following validation rule is firing for each student in error, rather than only firing once at the LEA and campus level. - 42510-0015 | N/A | N/A | 2017-12-01 | TBD
SPPI-14 | Reports | The following report is running longer than expected. - SPP0-000-002 TSDS SPPI-14 Expected Student Counts Report Reminder: This report is only available at the ESC-level. The student counts on the report should match the number of students that promote to the SPPI-14 data mart for each LEA. | The report will process but it may take a few hours to complete. | N/A | 2024-02-09 | TBD
TSDS Portal | Core Collection XML | The following Collection/Submissions are erroneously displaying school year '2024-2025' when accessing the Core Collection (XML) tab: -Class Roster/Winter -CSW -ECDS KG/ECDS PK | 2024-2025 data is only viewable through the Core Collection tab for core collections. If the user clicks on the Prepare/Finalize Screen or on Reports for the 2024-2025 school year in the 'Core Collection (XML)' Tab, no data will be available. | LEAs need to make sure that they are in the 'Core Collection' tab in order to see Prepare/Finalize counts and data on reports for the '2024-2025' school year. | 2024-09-18 | TBD
UID | Retired Enrollment Tab | When a Unique ID has been retired, the 'Retired Enrollment' tab does not have columns 'Grade Level', 'Enroll/Withdraw Date' or 'Enroll/Withdraw Type'. | N/A | N/A | ** | TBD
UID | Reports | The following report is not displaying all students with an exit event in UID who meet the criteria as a "Potential Leaver". - UID-000-002 Students Showing Withdrawn | N/A | N/A | 2024-06-21 | TBD
UID | UID Batch Search | Users with the Unique-ID Search role are unable to download search results because the download button is greyed out. | N/A | N/A | 2016-08-10 | TBD
CSW | Reports | When running CSW0-100-001 CSW Roster Report, LEAs may see an extra page showing "No Data To Report". | N/A | Running the CSW0-100-001 report in CSV format will provide a full list of each campus and all waitlist students. | 2024-10-21 | TBD 2025-2026