## Project Plan
Phase | Item | Owner(s) | Due Date | Status

## Sample
Phase | Item | Owner(s) | Due Date | Status
1. Planning | Obtain from Tyler the Top 5 Requests and Top 5 Incidents | Peyri Herrera | 2021-03-16 | Done
1. Planning | Test entry of the top requests and incidents | Peyri Herrera | 2021-03-16 | Done
1. Planning | Meet with Uyen and John V. to talk about ServiceNow | Peyri Herrera | 2021-03-16 | Done
1. Planning | Work with John V. to determine who will conduct the training meeting with Admin Assistants | Peyri Herrera | 2021-03-18 | Done
1. Planning | Meet with Terry to review Project Charter | Peyri Herrera | 2021-03-18 | Done
1. Planning | Meet with Tyler, Flora, Candace, John V. to introduce the project | Peyri Herrera | 2021-03-19 | Done
2. Prep - Materials Creation | Collect feedback from 16 Admin Assistants | Peyri Herrera, Candace Wong | 2021-03-26 | Done
2. Prep - Materials Creation | Obtain from John V. the dropdown list of incidents that SDCOE staff can choose from (Workaround: Manually type in list into job aid) | Peyri Herrera | 2021-03-29 | Done
2. Prep - Materials Creation | Determine if the “I am having trouble with” search box can be a Contains search instead of Begins With (for better usability) (UYEN) | Peyri Herrera | 2021-03-29 | Done
2. Prep - Materials Creation | Create job aid | Peyri Herrera, Candace Wong | 2021-04-12 | Done
2. Prep - Materials Creation | Create video | Peyri Herrera | 2021-04-12 | Done
2. Prep - Materials Creation | Review and sign off on materials | Peyri Herrera | 2021-04-13 | Done
2. Prep - Materials Creation | Post materials on Common Ground | Peyri Herrera, Candace Wong | 2021-04-13 | Done
2. Prep - Materials Creation | Create PPT that will be used as part of the short instructional video and ServiceNow Training Meeting | Peyri Herrera | 2021-04-13 | Done
2. Prep - Materials Creation | Provide Susana with the recorded training meeting video to post on Common Ground | Candace Wong | 2021-04-20 | Done
3. Prep - Scheduling and Communications | Inform ITS Senior Leadership of the project plan - via email and at ITS Leadership Team Meeting | Peyri Herrera | 2021-03-22 | Done
3. Prep - Scheduling and Communications | Schedule and conduct Teams meeting with CSS to inform them of the effort | Tyler Petro | 2021-03-23 | Done
3. Prep - Scheduling and Communications | Set up spreadsheet to capture baseline metrics | Peyri Herrera, Candace Wong | 2021-03-23 | Done
3. Prep - Scheduling and Communications | Draft email to Executive Assistants, Admin Assistants, and Program Secretaries | Candace Wong | 2021-03-24 | Done
3. Prep - Scheduling and Communications | Set up spreadsheet of identified admin staff for training and review with Ewa | Candace Wong | 2021-03-24 | Done
3. Prep - Scheduling and Communications | Determine date/time and schedule Teams dry run AND training meeting with Admin Assistants and Program Secretaries | Candace Wong | 2021-03-26 | Done
3. Prep - Scheduling and Communications | Meet with Tyler, Flora, and Candace to review progress/discuss next steps for project | Peyri Herrera | 2021-03-26 | Done
3. Prep - Scheduling and Communications | Review draft email to assistants to introduce project and mention training meeting | Peyri Herrera | 2021-03-29 | Done
3. Prep - Scheduling and Communications | Request from Leo that at future New Hire Orientations that ITS can play the 2-minute video and have all new hires navigate to ServiceNow and log in | Peyri Herrera | 2021-03-30 | Stuck
3. Prep - Scheduling and Communications | Send formal invite from Peyri's calendar for training meeting with assistants | Candace Wong | 2021-03-30 | Done
3. Prep - Scheduling and Communications | Work with Stacy on methods of communications | Peyri Herrera | 2021-04-06 | Done
3. Prep - Scheduling and Communications | Meet with Flora and Candace to review progress/discuss next steps for project | Peyri Herrera | 2021-04-06 | Done
3. Prep - Scheduling and Communications | Meet with Flora, Uyen, and Candace to discuss changes for ServiceNow | Peyri Herrera | 2021-04-06 | Done
3. Prep - Scheduling and Communications | Find out if we can present to Managers for 15 minutes at a future COMET meeting and ask them to share the 2-minute video at their department meeting | Flora Pourzamani | 2021-04-09 | Done
3. Prep - Scheduling and Communications | Work on draft FAQs for job aid | Candace Wong, Tyler Petro | 2021-04-12 | Done
3. Prep - Scheduling and Communications | Meet with Stacy, Tyler, Flora, and Candace to discuss the messaging for Inspire/communications for the project | Peyri Herrera | 2021-04-13 | Done
3. Prep - Scheduling and Communications | Have CSS populate spreadsheet for 4 weeks | Tyler Petro | 2021-04-16 | Done
3. Prep - Scheduling and Communications | Draft the “friendly script” that CSS and other agents will use when employees continue to not use the system to submit a ticket | Peyri Herrera, Tyler Petro | 2021-04-19 | Done
4. Execution - Education and Communications | Share job aid, instructional video, and training meeting plan with ITS Leadership and managers of PeopleSoft Support | Peyri Herrera | 2021-04-14 | Done
4. Execution - Education and Communications | Practice/dry run for training meeting - Mon, 4/19 10-11am | Tyler Petro, Peyri Herrera | 2021-04-19 | Done
4. Execution - Education and Communications | Conduct ServiceNow Training Meeting with Exec Assts, Admin Assts, Prog Secretaries - Tue, 4/20 10:00-10:45 am | Tyler Petro, Peyri Herrera | 2021-04-20 | Done
4. Execution - Education and Communications | Debrief ServiceNow Training Meeting/Dry Run for COMET Presentation - Tue, 4/20 1:50-2:30 pm | Tyler Petro, Peyri Herrera, Candace Wong | 2021-04-20 | Done
4. Execution - Education and Communications | Conduct presentation at COMET - Wed, 4/21 3:00-4:00 pm | Tyler Petro | 2021-04-21 | Done
4. Execution - Education and Communications | Meet with CSS to explain all the materials that were created and what will be covered at the training | Tyler Petro | 2021-04-22 | Done
4. Execution - Education and Communications | Send/post a variety of communications (STACY) 4/14-4/30 | Peyri Herrera, Candace Wong | 2021-04-30 | Done
5. Closure | Follow up with Stacy to confirm we are on track with the May issue of Inspire and set up post-metrics tab for side-door requests | Candace Wong | 2021-04-27 | Done
5. Closure | Take next steps with potential ITS quarterly meetups based on feedback from the training meeting | Tyler Petro | 2021-05-03 | Done
5. Closure | Create and deploy post-training meeting survey to collect feedback from attendees | Peyri Herrera, Candace Wong | 2021-05-04 | Done
5. Closure | Review post-training meeting survey data and incorporate in final report/presentation | Peyri Herrera | 2021-05-06 | Done
5. Closure | Create final presentation | Peyri Herrera, Candace Wong | 2021-05-07 | Done
5. Closure | Send celebration invite to attendees and email 16 AAs who provided feedback directly to invite them | Peyri Herrera, Candace Wong | 2021-05-14 | Done
5. Closure | Share final presentation with ITS Senior Leadership | Peyri Herrera | 2021-05-14 | Done
5. Closure | Meet with Flora, Tyler, and Candace to plan celebration | Peyri Herrera | 2021-05-18 | Done
5. Closure | Create agenda and presentation for celebration | Peyri Herrera, Candace Wong | 2021-05-25 | Done
5. Closure | Practice/dry run for celebration - Wed, 5/26 9:30-10am | Peyri Herrera, Tyler Petro, Candace Wong | 2021-05-26 | Done
5. Closure | Conduct end of project celebration - Thu, 5/27 9:30-10am | Peyri Herrera | 2021-05-27 | Done
5. Closure | Capture post-metrics for ServiceNow usage - April, May, June | Peyri Herrera | 2021-06-30 | Done
5. Closure | Capture post-metrics for side-door requests - May, June | Tyler Petro | 2021-07-02 | Done
5. Closure | Share out answers to questions from ServiceNow Training Meeting and update job guide FAQs section | Peyri Herrera, Tyler Petro, Candace Wong | 2021-08-02 | Working on it
5. Closure | Meet with Flora, Tyler, and Candace to review post-metrics | Peyri Herrera | 2021-08-03 | Done

## Tips
Tips for Creating a Project Plan in Excel
COLUMN A | COLUMN B | COLUMN C | COLUMN D | COLUMN E
Phase | Item | Owner(s) | Due Date | Status
1. Planning | Obtain from Tyler the Top 5 Requests and Top 5 Incidents | Peyri Herrera | 2021-03-16 | Done
1. Planning | Test entry of the top requests and incidents | Peyri Herrera | 2021-03-16 | Done
1. Planning | Meet with Uyen and John V. to talk about ServiceNow | Peyri Herrera | 2021-03-16 | Done
1. Planning | Work with John V. to determine who will conduct the training meeting with Admin Assistants | Peyri Herrera | 2021-03-18 | Done
1. Planning | Meet with Terry to review Project Charter | Peyri Herrera | 2021-03-18 | Done
1. Planning | Meet with Tyler, Flora, Candace, John V. to introduce the project | Peyri Herrera | 2021-03-19 | Done
2. Prep - Materials Creation | Collect feedback from 16 Admin Assistants | Peyri Herrera, Candace Wong | 2021-03-26 | Done
2. Prep - Materials Creation | Obtain from John V. the dropdown list of incidents that SDCOE staff can choose from (Workaround: Manually type in list into job aid) | Peyri Herrera | 2021-03-29 | Done
2. Prep - Materials Creation | Determine if the “I am having trouble with” search box can be a Contains search instead of Begins With (for better usability) (UYEN) | Peyri Herrera | 2021-03-29 | Done
2. Prep - Materials Creation | Create job aid | Peyri Herrera, Candace Wong | 2021-04-12 | Done
2. Prep - Materials Creation | Create video | Peyri Herrera | 2021-04-12 | Done
Number your phases so they appear ordered when you sort/filter. | Starting an item with a verb can help clarify the task. | Set up the spreadsheet as a shared doc and encourage team members to add and update their own items. | Set reasonable and realistic due dates when establishing your plan. | Limit your statuses to a few and be consistent in their use.
Use column filters to view information (filter by phase, by owner, by status, by due date). |  |  |  | The spreadsheet is set up with Conditional Formatting to automatically color code these 3 statuses.
Examples of Phases:
1. Discovery or Planning |  |  |  | Statuses:
2. Design |  |  |  | Working on it
3. Development or Build |  |  |  | Stuck
4. Testing |  |  |  | Done
5. Training |  |  |  | [Blank] = Not started
6. Pre-Go Live Activities
7. Go Live / Implementation
8. Post-Go Live
9. Closure
This list is not meant to be all inclusive and not every phase may be needed.