CAPITAL CONSTRUCTION FINANCIAL OVERVIEW

April 10, 2018

CURRENT BOND FINANCIAL STATUS

In millions

|  | 2017 -18 Activity |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Beginning balance from 2012 Bond |  |  | $117 |
|  |  | Bond issue from 2012 ballot |  |  | 62 |
|  |  | 2017 Bond Issue |  |  | 347 |
|  |  | Premium/income |  |  | 13 |
|  |  |  |  |  | 539 |
|  |  | Spending projection |  |  | (63) |
|  |  | Ending balance 6/30/18 |  |  | 476 |
|  | 2018-19 Activity |  |  |  |  |
|  |  | Income |  |  | 3 |
|  |  | Spending projection |  |  | (185) |
|  |  | Ending balance 6/30/19 |  |  | 294 |
|  |  | Remaining issuance authority |  |  | 443 |
|  |  | Total available to finish program |  |  | $737 |

•   Beginning of eight year plan

•   Not a cash problem

2012 BOND

Nearing completion - remaining projects:

Finish Grant HS

Maker Space at Roosevelt

Schools larger than original specifications

Increased capacity

More classrooms for full time classload

Roosevelt Maker Space added to project ($5 million for space)

Currently forecast to cost $0-$10 million over funds					available from 2012 authority

MIDDLE SCHOOL

IMPLEMENTATION/TRANSITION

| REVISED UNFUNDED COSTS (millions) |  |
| --- | --- |
| Tubman | $5.8 |
| Roseway Heights | 0.2 |
| Rose City Park | 1.9 |
| Holladay/Youngson | 0.7 |
| Contingency | 2.5 |
| Design/soft costs to date | 0.8 |
| Total construction | 11.9 |
| Owner costs | 1.4 |
|  | 13.3 |
| Fundable from bond Health & Safety | -1.9 |
| Total unfunded costs | $11.4 |

*Does not include any costs of transitioning ACCESS

BUILDING PROCESS STATUS

KELLOGG

- Board approved master plan at original scope.

- Later analysis showed costs were much higher

- Internal group including educational leader reduced scope to get cost down		   Some efficiencies

Smaller classrooms, no breakout rooms

Removed small fourth floor

- Must bring revised master plan back for board approval

MADISON

- Internal group met and reduced costs to "bare minimum" $172 million			   Removes all field improvements

Removes 4 classrooms, 2 labs, 4 collaboration spaces

Smaller classrooms, science labs

- Waiting for direction on budget. Will then submit master plan to Board

- Can meet Fall 21 opening date if decision made by mid-May and scope changes

not too large

LINCOLN

- Internal group met and reduced costs to $196 million

- Still working on reductions.

- Decision needed by mid-May

BENSON

- No group meeting as yet

OPTIONS

MIDDLE SCHOOL IMPLEMENTATION/TRANSITION

- Include all unfunded construction costs in bond funding.

- Charge non-bond funded items to construction excise tax

  - Barely fits – can handle about $12 million

  - Allows $3 million per year for rest of schools in addition to Health and Safety bond and $1 million General Fund transfer

  - Requires postponing/repealing dedication to capital asset renewal

- Borrow money and repay from General Fund

  - Debt service about $1 million per year on 15 year loan @4%.

  - Could declare intent to refund from next voter approval

2012 BOND

- Include all unfunded construction costs in bond funding.

- Charge non-bond funded items to construction excise tax

  - Probably won’t fit if this solution used for middle school implementation

- Borrow money and repay from General Fund or CET

  - Could declare intent to refund from next voter approval

BOND OPTIONS

- Kellogg - consider revised master plan when it is ready

- High schools

  - Set timelines for high school building master plan approval

  - Continue the local process of analyzing/removing costs based on the timelines

  - Establish district reconciliation process to ensure equity across all high schools

  - Budget options

    - Go forward with reduced costs/scope

    - Do buildings in phases, fund second phase from next voter approval

    - Raise more money - some will come from structure of next bond issue and interest earnings

    - Borrow to complete projects, refund with next voter approval