## FacilitiesSafety
Need | Action Item | Immediate (I) Mid-Term (M) Long-Term (L) | Person Responsible | Anticipated Completion | Comments | Started | Completed
Limited/inadequate academic, extracurricular and carreer and technology space for district's rapid enrollment growth. | Form a facilitie's committee to identify the district's facility needs. | M | Superintendent | 2019-05-30
Limited/inadequate academic, extracurricular and carreer and technology space for district's rapid enrollment growth. | Develop a facilities master plan | L | Superintendent | 2020-05-30
Safety Improvements at all campuses | Form a district safety committee to evaluate the safety needs of the district. | I | Assistant Superintendent | 2018-12-01
Safety Improvements at all campuses | Security camera upgrades for all district facilitiues. | M | Assistant Superintendent | 2019-05-30
Safety Improvements at all campuses | Update the district/campus hazard plan. | I | Assistant Superintendent | 2018-12-01
Safety Improvements at all campuses | Add a school resource officer (SRO) for the district. | I | Superintendent | 2018-10-01
Safety Improvements at all campuses | Improve safety training for staff and students. | M | Assistant Superintendent | 2019-05-30
Safety Improvements at all campuses | Construct a secure entry at Academy Middle School. | L | Assistant Superintendent | 2021-05-30

## BusinessCommunity Partnerships
Need | Action Item | Immediate (I) Mid-Term (M) Long-Term (L) | Person Responsible | Anticipated Completion | Comments | Started | Completed
Lack of district outreach and engagement with all stakeholders, including new housing additions in Temple, Texas. | Create representative groups from PAC/SAC committees to improve outreach. | M | Campus Principals | 2019-05-30
Lack of district outreach and engagement with all stakeholders, including new housing additions in Temple, Texas. | Increase number of school events hosted off campus (i.e. in Temple city limits, local subdivisions, parks). | M | Campus Principals | 2020-05-30
Lack of district outreach and engagement with all stakeholders, including new housing additions in Temple, Texas. | Conduct administrator and teacher "Home Visits". | I | Campus Principals | 2018-12-01
Lack of district and business partnerships. | AISD will become a member of the Temple Chamber of Commerce. | I | Superintendent | 2018-12-01
Lack of funding mechanism by which community members and businesses can support innovation in the classroom and enhance student learning opportunities through fundraising | Identify a leadership team to develop an education foundation | M | Superintendent | 2019-05-30

## Expand Curriculum Opportunities
Need | Action Item | Immediate (I) Mid-Term (M) Long-Term (L) | Person Responsible | Anticipated Completion | Comments | Started | Completed
Limited dual credit opportunities at AHS. | Partner with UTPB and TC to create ECHS | M | High School Principal | 2019-05-30
Limited endorsement pathway and elective opportunities with anticipated enrollment growth. | Continue to add pathways and course offerings based off student interest/need | L | Campus Principals | 2028-05-30
Limited elective courses at the middle school. | Add additional fine arts at the secondary level (i.e. choir, dance). | L | Campus Principals | 2028-05-30
Lack of community awareness of the GT Program. | Create Fall/Spring Symposium for the GT Program to share info and projects | I | Campus Principals | 2019-05-30
Lack of ESL certified staff at the secondary level. | Require 6-12th grade ELAR teachers to be ESL certified | M | Campus Principals | 2020-05-30
Limited special offerings at the elementary level due to enrollment growth. | Add additional special offering to partner with music/PE (i.e. art, technology) | L | Campus Principals | 2022-05-30

## Student LeadershipCharacter Dev
Need | Action Item | Immediate (I) Mid-Term (M) Long-Term (L) | Person Responsible | Anticipated Completion | Comments | Started | Completed
Lack of consistency throughout the district on teaching character development | Implement CKH with fidelity PK-12, rating our classrooms daily and requiring the district to focus on certain chosen leadership characteristics or traits. | I | Campus Principals | 2019-05-30
Limited behavioral support for Tier 2 and 3 students | Implement social skills training for students on Tier 2 and 3. | M | Campus Principals | 2020-05-30
Limited behavioral support for Tier 2 and 3 students | Investigate the addition of an LSSP, at-risk counselor or behavioral specialist. | L | Superintendent | 2021-05-30
Lack of leadership opportunities for all students PK-12 | Create inter-campus and intra-campus leadership development opportunities for all students | M | Campus Principals | 2020-05-30

## Staffing
Need | Action Item | Immediate (I) Mid-Term (M) Long-Term (L) | Person Responsible | Anticipated Completion | Comments | Started | Completed
Lack of personnel to meet the need of the growing student population and teaching staff. | Hire an Assistant Principal at the elementary school. | L | Superintendent/Elementary Principal | 2021-05-30
Lack of personnel to meet the need of the growing student population and teaching staff. | Hire an Assistant Principal at the intermediate school. | L | Superintendent/Intermediate Principal | 2021-05-30
Lack of personnel to meet the need of the growing student population and teaching staff. | Hire a second Assistant Principal at the high school. | L | Superintendent/High School Principal | 2023-05-30
Lack of personnel to meet the need of the growing student population and increase focus on CCR and graduation requirements. | Hire a second counselor at the high school. | L | Superintendent/High School Principal | 2023-05-30
Lack of personnel to meet the need of the growing student population | Hire a middle school Ag teacher. | M | Superintendent/Middle School Principal | 2023-05-30
Lack of personnel to meet the need of the growing student population | Hire a middle school elective teacher. | L | Superintendent/Middle School Principal | 2021-05-30
Lack of personnel to meet the need of the growing student population | Hire an 8th grade core teacher. | L | Superintendent/Middle School Principal | 2021-05-30
Lack of personnel to meet the need of the growing student population | Hire an intermediate school elective teacher. | L | Superintendent/IntermediatePrincipal | 2021-05-30
Lack of personnel to meet the need of the growing student population | Hire a District Testing Coordinator. | L | Superintendent | 2023-05-30
Lack of personnel to meet the need of the growing student population and the increased need of social-emotional counseling | Hire a LSSP. | M | Superintendent | 2023-05-30
Increase safety measures for the growing district population | Hire a SRO. | I | Superintendent | 2019-05-30
Lack of personnel to meet the need of the growing pathways | Hire additional CTE Teachers. | L | Superintendent/High School Principal | 2023-05-30
Lack of personnel to meet the need of the growing student population | Hire an elementary math specialist. | L | Superintendent/Elementary Principal | 2023-05-30
Lack of opportunity for teacher leadership | Continue Leadership Academy | M | Campus Principals | 2020-05-30
Lack of opportunity for teacher leadership | Conduct book studies (admin & teacher level) | M | Campus Principals | 2020-05-30
Lack of opportunity for teacher leadership | Tiered professional development | M | Campus Principals | 2020-05-30