## Detail
Strasburg School District 31J
Strasburg Story Scorecard-Detail
Driver #1: Strasburg School District31 J prepares, engages, and supports students in a challenging and personalized education, empowering each student to achieve their full potential.
Goal | Objective | Status | Outcomes | Quantitative Metric | Spring 2025 Score | 2026 Target | Progress to Goal | Notes
Make learning seamless by aligning the things students learn (curriculum), how they learn (instruction), and how me measure their progress (assessment), all supported by research. | Develop a 3-year instructional practices refinement plan. | 2025-2026 Objective | Improved curriculum alignment and coherence (Teacher Influence) | 5 Essentials: Ambitious Instruction > Academic Press (Rigor) | Neutral-49 | Strong-60 | Met Prior Target | District shared data with staff to identify current perception. Created the Strasburg Way instructional pillars. Implemented Targeted instructional rounds with building leaders in all buildings. Implemented PLCs across district.
|  |  |  | 5 Essentials: Ambitious Instruction > Quality of Discussion Between Students | Neutral-43 | Strong-60 | Met Prior Target | District shared data with staff to identify current perception. Created the Strasburg Way instructional pillars. Implemented PLCs across district.
|  |  |  | 5 Essentials - Collaborative Teachers > School Commitment | Weak-21 | Neutral-40 | Decreasing | Enhanced benefit offering to employees in September 2024. Provided off-site lunch and teambuilding in August 2024. Superintendent communication to staff on a monthly basis via Strasburg Scoop started in August 2024. Implemented districtwide PLC.
|  |  |  | 5 Essentials - Collaborative Teachers > Teacher to Teacher Trust | Very Weak-16 | Weak-25 | Decreasing | All district staff completed Emergenetics by August 2024. Implemented districtwide PLC.
|  |  |  | 5 Essentials - Collaborative Teachers > Collaborative Practices | Weak-26 | Neutral-40 | Increasing | Engaged third party to provide systemic professional learning community (PLC) structure.
|  |  |  | 5 Essentials - Collaborative Teachers > Collective Responsibility | Very Weak-10 | Weak-20 | Decreasing | Initiated K-5 vertical alignment. Started developing a collective K-12 Writing Rubric. Formalized induction program for new teachers. Monthly districtwide professional development. Each building established Building Leadership Teams. Implemented a process for open positions that includes interviews by the grade level team (not just moving people).
| Develop a 3-year instructional practices refinement plan. | 2025-2026 Objective | Improved student learning outcomes. | School Performance Framework | Accredited-56.9 | 56 | Decreasing (Improvement-54.1) | District shared data with staff to identify current achievement and growth data. Aligned all building UIPs to Strategic Plan and District Level UIP. |  | No data to update yet | 3200
| Align PK-12 Unified Improvement Plans to Community-driven strategic plan | In Progress | Increased student support, engagement and motivation (Collective Responsibility) | 5 Essentials: Ambitious Instruction > English Instruction | Strong-61 | Very Strong-80 | Met Prior Target | PLCs focused on English included as a major improvement strategy in the district UIP. K-5 literacy consultant hired by district for the 2024-2025 academic year. |  |  | 11500
|  |  |  | 5 Essentials: Ambitious Instruction > Math Instruction | Strong 60 | Very Strong-80 | Met Prior Target | PLCs focused on Math included as a major improvement strategy in the district UIP.
|  |  |  | 5 Essentials - Collaborative Teachers > Collaborative Practices | Weak-26 | Neutral-40 | Increasing | PLC included as a major improvement strategy in the district UIP.
|  |  |  | 5 Essentials: Supportive Environment > Student-Teacher Trust | Neutral - 51 | Strong-60 | Decreasing | Attendance included as a major improvement strategy in the district UIP.
| Align PK-12 Unified Improvement Plans to Community-driven strategic plan | In Progress | Enhanced engagement and ownership with families and community (Decision Making in Schools) | 5 Essentials: Involved Families > Parent Involvement in School | Weak - 29 | Neutral-40 | Neutral | Modified Parent/Teacher Conferences to include daytime hours beginning in October 2024. Intentional communication plan at building level and district level.
Tailor learning journeys to individual student needs and goals, ensuring timely graduation and college and career readiness for all. | Develop a Student Mentor Program | 2026-2027 Objective | Improved school climate and culture (Student-Peer Relationships) | 5 Essentials: Supportive Environment > Peer Support for Academic Work | Neutral - 57 | Strong-60 | Increasing | In the last 2 years district purchased K-12 social/emotional learning curriculum.
|  |  | Increased support, self-esteem and confidence (Student-Teacher Trust) | Daily Attendance Rate | 91.9% | 93% | Improving from 23-24 data (91.5%) | 2 staff members in State attendance cohort. Implementing consistent attendance practices and systems is a major improvement strategy in district UIP. Update district policies to align K-12.
|  |  |  | Chronically Absent Rate | 27.3% | 24% | Improving from 22-23 data (28.2%) | 2 staff members in State attendance cohort. Implementing consistent attendance practices and systems is a major improvement strategy in district UIP. Update district policies to align K-12.
|  |  |  | Suspensions | 87 | 87 | Progress data received in Fall 2025 | Ensuring consistency in data being reported and adherence to policy district-wide. |  | No Data yet
|  |  |  | 5 Essentials: Supportive Environment | Neutral - 47 | Strong-60 | Increasing | Elementary implemented House System as a way to support and encourage Student-Student and Student Teacher trust.
| Align PK-12 Calendar | 2025-2026 Objective | Increased efficiency and resource utilization (Family Involvement in Schools) | 5 Essentials: Involved Families | Weak - 31 | Neutral-40 | Decreasing | District implemented FMX during December 2025 which includes master schedule K-12. Athletic Director sending activity calendars out on a weekly basis. Communication plan established at Building and District level.
|  |  | Enhanced communication and collaboration across schools | Family Satisfaction Survey (Response Rate) | 5.704% | 12% | Baseline data only available at this time. | Baseline survey delivered in Spring 2025.
Driver #2: Strasburg 31J values, empowers, and inspires each staff member to achieve their full potential by creating performance and support systems.
Goal | Objective | Status | Outcomes | Data Marker | Spring 2025 Score | 2026 Target | Progress to Goal | Notes
Invest in professional development to ensure needs-based training for staff, leadership development, and coaching/mentoring. | Implement a Staff Career Program | 2025-2026 Objective | Increased career satisfaction and engagement. | Staff Satisfaction Survey |  |  |  | Stay Interviews delivered in 2025-2026 to gain baseline data prior to focus.
|  |  | Improved succession planning | Intent to Return Survey (Turnover Rate) | 25.15% | 18% | Baseline data only available at this time. | 2024-2025 Staff Turnover Report from CDE Website
| Create a Professional Development Plan | 2025-2026 Objective | Increased teacher confidence and self-efficacy (Instructional Leadership) | Staff Satisfaction Survey |  |  |  | Stay Interviews delivered in 2025-2026 to gain baseline data prior to focus. |  |  | 22931
|  |  | Improved teacher collaboration and professional learning communities (Ambitious Instruction) | 5 Essentials: Ambitious Instruction | Neutral-56 | Strong-60 | Met Prior Target | Staff Satisfaction Survey delivered in Spring 2026 to gain baseline data prior to focus. Monthly professional development days and feedback loop.
|  |  |  | 5 Essentials: Collaborative Teachers > Collaborative Practices | Weak-26 | Neutral-40 | Increasing | Engaged third party to provide systemic professional learning community (PLC) structure.
Create a culture of recognition and appreciation fostering a positive work environment. | Develop a Positive Workplace Environment Plan | In Progress | Increased employee engagement and motivation. | Staff Satisfaction Survey |  |  |  | Stay Interviews delivered in 2025-2026 to gain baseline data prior to focus. Creating an Employee Engagement Committee to capture a broader voice in future plans. |  |  | 10809
|  |  |  | 5 Essentials: Effective Leaders | Weak - 31 | Neutral-40 | Decreasing | Leadership training opportunities included in Cabinet at least monthly. Established clear communication structure (i.e., Strasburg Scoop). Leadership Summit scheduled for February 2025. Implemented mid-year Building Leadership Stop, Start, Continue Evaluation. Establish SMART goals for each Director in the district as part of the annual evaluation process.
|  |  | Enhanced Collaboration and Teamwork | 5 Essentials: Collaborative Teachers > Collective Responsibility | Very Weak - 10 | Weak-20 | Decreasing | Initiated K-5 vertical alignment. Started developing a collective K-12 Writing Rubric. Formalized induction program for new teachers. Monthly districtwide professional development. Each building established Building Leadership Teams. Implemented a process for open positions that includes interviews by the grade level team (not just moving people).
Driver #3: Strasburg 31J optimizes our collective vision by vision casting and community building.
Goal | Objective | Status | Outcomes | Data Marker | Spring 2025 Score | 2026 Target | Progress to Goal | Notes
Foster widespread understanding and ownership of our district's collective vision. | Develop and launch a communication plan. | In Progress | Increased awareness and understanding of the District's vision. | Family Satisfaction Survey-School has clearly defined purpose and mission. | 40.62% | 50% | Baseline data only available at this time. | Baseline data from Spring 2025 Family Satisfaction Survey.
|  |  | Improved internal communication and alignment. | Staff Satisfaction Survey |  |  |  | Stay Interviews delivered in 2025-2026 to gain baseline data prior to focus.
Strengthen and encourage collaborative partnerships that leverage and share resources and expertise. | Develop Partnership Plan that identifies and engages potential partners. | 2025-2026 Objective | Enhanced and expanded learning opportunities. | # of opportunities increases | 6 | 12 | Baseline data only available at this time. | BOE and Administration intentionally focused on attending community activities (i.e., Chamber of Commerce, Strasburg VIP, REAP, etc.). Identifying ways to partner with Strasburg Rec to provide services to the community such as walking club. Reporting # of events attended by Superintendent. | Community partner survey? Community resources through Adams County?
|  |  | Enhanced community engagement and support. | Family Satisfaction Survey-I support the goals of the school. | 53.54% | 60% | Baseline data only available at this time. | Baseline data from Spring 2025 Family Satisfaction Survey.
Note on H7: ====== ID#AAABXGtVguk Nancy Taylor (2024-10-24 14:31:46) Met - Green (60) Improving - Yellow Decreasing - Red
Note on F26: Nancy Taylor: =# of responses/funded pupil count
Note on H28: ====== ID#AAABXGtVguo Nancy Taylor (2024-10-24 14:31:46) Met - Green (60) Improving - Yellow Decreasing - Red
Note on F30: Nancy Taylor: 2024-2025 Turnover Report on CDE Website
Note on H38: ====== ID#AAABXGtVgu0 Nancy Taylor (2024-10-24 14:31:46) Met - Green (60) Improving - Yellow Decreasing - Red

## Summary
Strasburg School District 31J
Strasburg Story Scorecard
Summary
Driver #1: Strasburg School District31 J prepares, engages, and supports students in a challenging and personalized education, empowering each student to achieve their full potential.
Goal | Objective | Status | Outcomes | Progress to Goal
Make learning seamless by aligning the things students learn (curriculum), how they learn (instruction), and how me measure their progress (assessment), all supported by research. | Develop a 3-year instructional practices refinement plan. | 2026-2026Objective | Improved curriculum alignment and coherence (Teacher Influence) | Progress data received in April 2025
|  |  | Improved student learning outcomes. | Decreasing
| Align PK-12 Unified Improvement Plans to Community-driven strategic plan | In Progress | Increased student support, engagement and motivation (Collective Responsibility | Progress data received in April 2025
|  |  | Enhanced engagement and ownership with families and community (Decision Making in Schools) | Progress data received in April 2025
Tailor learning journeys to individual student needs and goals, ensuring timely graduation and college and career readiness for all. | Develop a Student Mentor Program | 2026-2027 Objective | Improved school climate and culture (Student-Peer Relationships) | Progress data received in April 2026
|  |  | Increased support, self-esteem and confidence (Student-Teacher Trust) | Improving
| Align PK-12 Calendar | 2025-2026 Objective | Increased efficiency and resource utilization (Family Involvement in Schools) | Progress data received in April 2026
|  |  | Enhanced communication and collaboration across schools | Progress data received in April 2027
Driver #2: Strasburg 31J values, empowers, and inspires each staff member to achieve their full potential by creating performance and support systems.
Goal | Objective | Status | Outcomes | Progress to Goal
Invest in professional development to ensure needs-based training for staff, leadership development, and coaching/mentoring. | Implement a Staff Career Program | 2025-2026 Objective | Increased career satisfaction and engagement. | Obtaining baseline data in Spring 2025
|  |  | Improved succession planning | Obtaining baseline data in Spring 2025
| Create a Professional Development Plan | 2024-2026 Objective | Increased teacher confidence and self-efficacy (Instructional Leadership) | Obtaining baseline data in Spring 2025
|  |  | Improved teacher collaboration and professional learning communities (Ambitious Instruction) | Progress data received in April 2025
Create a culture of recognition and appreciation fostering a positive work environment. | Develop a Positive Workplace Environment Plan | In Progress | Increased employee engagement and motivation. | Progress data received in April 2025
|  |  | Enhanced Collaboration and Teamwork | Progress data received in April 2025
Driver #3: Strasburg 31J optimizes our collective vision by vision casting and community building.
Goal | Objective | Status | Outcomes | Progress to Goal
Foster widespread understanding and ownership of our district's collective vision. | Develop and launch a communication plan. | In Progress | Increased awareness and understanding of the District's vision. | Obtaining baseline data in Spring 2025
|  |  | Improved internal communication and alignment. | Obtaining baseline data in Spring 2025
Strengthen and encourage collaborative partnerships that leverage and share resources and expertise. | Develop Partnership Plan that identifies and engages potential partners. | 2025-2026 Objective | Enhanced and expanded learning opportunities. | Obtaining baseline data in Spring 2025
|  |  | Enhanced community engagement and support. | Obtaining baseline data in Spring 2025
Note on E7: ====== ID#AAABXGtVgug Nancy Taylor (2024-10-24 14:31:46) Met - Green (60) Improving - Yellow Decreasing - Red
Note on E17: ====== ID#AAABXGtVgus Nancy Taylor (2024-10-24 14:31:46) Met - Green (60) Improving - Yellow Decreasing - Red
Note on E25: ====== ID#AAABXGtVguw Nancy Taylor (2024-10-24 14:31:46) Met - Green (60) Improving - Yellow Decreasing - Red