## Board Items
January 23, 2017 BOT AGENDA ITEMS - All items are Pending
M-1 | BA #1a | Re-allocation of Proposition O Bond Sale 2 funds. Original Budget $26,750,000; Reduction $(25,910,000); Udated Budget $840,000.
M-1 | BA #1b | Re-allocate the $25,910,000 reduction above to the following projects: HVAC Project $23,400,000; Castle Park HS Gym Bleachers $500,000; Southwest HS Gym Bleachers $500,000; Prop O Bond Sale 2 Contingency $1,510,000.
M-2 | CVH Full Campus Master Planning | Approve contract with Roesling Nakamura Terada Architects to provide architectural master planning, programming, budget estimating and design services for the Full Campus Master Plan at Chula Vista High School. $29,000.00.
M-2 | HTM Master Plan | Approve contract with Baker Nowicki Design Studio to provide architectural services for the Hilltop Middle School - Master Plan. $28,421.00.
M-2 | MVH Pool Replacement | Approve contract with Counsilman Hunsaker Operations to provide aquatic planning and design consultant for the Mar Vista High School (MVH) Pool Replacement Project. $14,880.00.
December 12, 2016 BOT AGENDA ITEMS - All items were APPROVED
M-1 | BA# 2 | Increase the Sweetwater High School (SUH) ADA Hygiene Restrooms Project budget by $55,000. Funding is from Prop O Bond Sale 1 contingency (Fund 22, Resource Code: 0000). The necessary ADA upgrades required at SUH, exceeded the initial cost estimates.
M-1 | BA# 3 | Acknowledge Fiscal Year (FY) 2016-17 1st quarter interest earnings of $13,716.26, for Prop O Bond Sale 1. Revenue is added to Prop O Bond Sale 1 contingency (Fund 22, Resource Code: 0000).
M-1 | BA# 4 | Acknowledge FY 2016-17 1st quarter interest earnings of $139,195.03, for Prop O Bond Sale 2. Revenue is added to Prop O Bond Sale 2 contingency (Fund 22, Resource Code: 0220).
M-2 | HTH Artificial Track & Field Improvements | Approve contract with BWE to provide surveying and civil engineering services for the Artificial Track & Field Improvements Project at Hilltop High School. $35,080.00
M-2 | HTM Modernization and Expansion of Building | Approve contract with Baker Nowicki Design Studio to provide architectural services for the modernization and expansion of Building 600. $372.475.00
November 14, 2016 BOT AGENDA ITEMS - All items were PENDING
M-2 | SUH Title IX Softball Field Modifications – geotechnical, materials testing and special inspection services | Ratify Contract with Ninyo & Moore to perform geotechnical, materials testing, and special inspection services for the Title IX Softball Field Modifications Project at Sweetwater High School. $12,274.00
M-2 | CVH Title IX Softball Team Room – DSA Inspector- of- Record Services | Ratify Amendment No.1 to the Contract with Construction Quality Assurance Group, LLC, to provide additional inspector-of-record services as required by the Division of the State Architect (DSA) for the Title IX Softball Team Room Project at Chula Vista High School. $13,527.00
M-3 | CVH Title IX Softball Team Room | Change Order No. 1, Cyber Professional Solutions Corp, CVH Title IX Bid #56-2530-RB. $5,673.08
M-3 | SUH Site Improvements | Change Order No. 1, SD Global Development Inc. dba New Vision Building & Design, Site Improvements Bid #56-2371-TC. $12,894.00