## Slide 1: 2019 Nederland ISD Bond Project
November 2023

## Slide 2: Nederland High School

## Slide 3: Nederland High School
Exterior
  Erection of CTE Building
  Install Area D Windows
  Mechanical Yard Chilled Water Piping
  Canopy columns being set.

## Slide 4: Nederland High School
HVAC piping
  Continue installing duct work in J, H, G, F, E, D, C, and B.
  Continue insulating MEP piping throughout building
  Complete piping of cassettes in area D1
Sheetrock & Paint
  Continue first coat of paint in area’s J, H, G, F, E, & C
  Continue plater ceilings in Area ‘J/G’
Start Tile in Restrooms
Start Ceiling Grid in Labs
Install Gym Scoreboards

## Slide 5: Langham Elementary School

## Slide 6: Langham Elementary School
Continue Gym addition
Complete Gate install
Install handrails over Thanksgiving

## Slide 7: Hillcrest Elementary School

## Slide 8: Hillcrest Elementary School
Café/kitchen extension
  Finish Epoxy Floors
  Wax Floors
Complete gym addition
  Epoxy & Fixtures
Landscape & Sod
Begin work in pre-k classroom over thanksgiving break

## Slide 9: Highland Park Elementary School

## Slide 10: Highland Park Elementary School
Complete concrete scope of work, final grading
Complete Roof Scope
Landscape & Sod

## Slide 11: Helena Park Elementary School

## Slide 12: Helena Park Elementary School
Complete Fencing & Gates
Entergy to remove utility pole
  Install Canopy
Landscape & Sod
Complete punch list

## Slide 13: Nederland Bulldog Stadium
Complete trim on elevator shaft
Install Restroom Signage
Complete visitors side gutters

## Slide 14: CO Wilson Middle School
Landscaping

## Slide 15: Central Middle School
Install Exterior Natatorium Door glazing
Install Wheelchair Lift