## Slide 1: 2019 Nederland ISD Bond Project
September 2023

## Slide 2: Nederland High School

## Slide 3: Nederland High School
Exterior
  CTE Building has been delivered and is currently being erected
  Continue Flatwork around main plaza area
  Install Area ‘C’ Windows, Area ‘D’ is in fabrication
  Continue trim out work on roof

## Slide 4: Nederland High School
HVAC piping
  Continue installing duct work in J, H, G, F, E, D, C, and B.
  Continue insulating MEP piping throughout building
  Complete hanging of cassettes in area D1/D2
Sheetrock & Paint
  Finish topping out sheetrock in Area ‘E’
  Continue first coat of paint in area’s J, H, G, F, E, & C
  Continue plater ceilings in Area ‘J/G’
Gas line being installed to building.
Install kitchen hoods in kitchen and culinary area.
Canopy columns being set.
Install standing seam room over high gable area of main entrance.

## Slide 5: Langham Elementary School

## Slide 6: Langham Elementary School
Begin Gym addition
Complete Fence & Gate install
Complete concrete scope of work & final grading
Landscape & Sod
Complete punch list

## Slide 7: Hillcrest Elementary School

## Slide 8: Hillcrest Elementary School
Café/kitchen extension
  Soffit install
  Cooler/Freezer
  Interior finish out
  Wall demo is complete
Complete gym addition
Complete Fence & Gates
Landscape & Sod
Complete Punch List

## Slide 9: Highland Park Elementary School

## Slide 10: Highland Park Elementary School
Continue with gym addition
Complete soffit install at café
Complete concrete scope of work, final grading
Complete Fence & Gates
Landscape & Sod
Complete punch list

## Slide 11: Helena Park Elementary School

## Slide 12: Helena Park Elementary School
Café Extension
  Complete Soffit Panel install
  Demo existing wall
  Interior finish out
Complete concrete scope of work, final grading
Complete Fencing & Gates
Landscape & Sod
Complete punch list

## Slide 13: Nederland Bulldog Stadium
Complete elevator install
Electrical complete
Complete signage install
Install Canopy coverings
Complete trim on elevator shaft

## Slide 14: CO Wilson Middle School
Front Office Complete
Laboratories Complete
Toilet Partitions Complete
Complete Trench Drain / Concrete Island
Install Fence & Gates
Remove Entergy Pole

## Slide 15: Central Middle School
Front Office Complete
  Installing New Casework
Laboratories Complete
Toilet Partitions Complete
Flatwork & Canopy outside Natatorium
Change Exterior Door for ADA.
Install Wheelchair Lift