Lake County Tech Campus Foundation – Updated Timeline (Now – July 2025)

Goal Area: Finance
Strategy: Expand Revenue Through Strategic External Partnerships

Phase 1: Completed Steps (Before January 2025)

| Action Steps | Status | Notes / Responsible Party |
| --- | --- | --- |
| Form Foundation Planning Committee | ✅ Completed | Committee members: Tech Campus Foundation and Stakeholder Relations Office, Executive Director, Business Manager |
| File nonprofit status | ✅ Completed | Legal status confirmed; Foundation recognized as a 501(c)(3) |
| Draft initial bylaws, mission, and vision | ⚙ In progress | Preliminary drafts exist; to be refined with input from Planning Committee and Board |
| Develop preliminary Director job description / title | Completed | Tech Campus Foundation and Stakeholder Relations Office; formal posting to follow bylaws approval |

Phase 2: Pre-Launch Board Activities (January – May 2025)

| Meeting Date | Action Steps | Responsible Party | Progress Monitoring / Notes |
| --- | --- | --- | --- |
| Jan 15, 2025 | Introductory Planning Committee/Board meeting with potential members; review draft bylaws, mission, vision | Tech Campus Foundation and Stakeholder Relations Office & Executive Director | Meeting minutes, % attendance recorded |
| Feb 5, 2025 | Planning Committee meeting to refine bylaws, finalize Director job description, and review fundraising strategy | Planning Committee | Minutes submitted; prepare recommendations for Board |
| Mar 12, 2025 | Planning Committee final review of bylaws, fundraising strategy, and public awareness plan | Planning Committee | Minutes submitted; prepare final materials for Board approval |
| Apr 16, 2025 | Submit final bylaws and mission/vision to Planning Committee and Executive Director | Planning Committee | Final draft approved internally; ready for Board approval in May |
| May 14, 2025 | Introducing official Foundation Board members; conducting inaugural Foundation meeting | Strategic Lead & Executive Director | Approve bylaws, confirm Board members, finalize action plan and committees, confirm Director hiring plan |

Phase 3: Foundation Launch (June – July 2025)

| Timeline | Action Steps | Responsible Party | Progress Monitoring / Notes |
| --- | --- | --- | --- |
| June 2025 | Finalize hiring of Tech Campus Foundation and Stakeholder Relations Officer (if approved by Board) | Strategic Lead & Board | Director onboarding completed |
| June – July 2025 | Launch fundraising strategy and public awareness campaign | Strategic Lead & Board | Strategy documented; plan major public launch event |
| July 1, 2025 | Official Foundation Launch | Strategic Lead & Board | All operations active; begin accepting gifts, implementing programs, scholarships, and certifications |

Phase 4: Ongoing Monitoring (FY26)

- Board Meetings: Monthly for the first year (Jan – Dec 2025), then six times per year in FY26, plus one annual 4-hour planning meeting.

- Evaluation: Adjust strategies based on progress toward revenue, student access, and equity initiatives.

- Annual Report: Present outcomes and financial report to LCTC Board of Control at the final FY26 meeting.

Indicators of Success

- Planning Committee and Board meetings held with documented minutes and attendance.

- Bylaws approved, Board established, and Tech Campus Foundation and Stakeholder Relations Office hired.

- Fundraising strategy implemented; donations secured.