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Rockdale County Superintendent Search FY26 Timeline
(March 2026 - June 2026)
February 16, 2026 
Board Initiates Search 
Board Action Needed

March 2026
Board Members Complete Qualifications Survey
Draft Criteria Development Initiated

March 2026
Submit Draft Announcement to Board

March 2026
Announcement Approval by Board

April 2026
Search Posted to GSBA Website & Launched (GSBA Application Receipt Process Begins)

April 2026
Online Community Input Survey Posted
(Optional - Board's Decision)

May 10, 2026
Applications Close
Two Week Window Needed by GSBA for Confidential Application Packet Evaluation/Reference Check, etc.

Week of May 26, 2026
Deliver Applications to the Board
Board Executive Session Needed
Board Establishes Proposed Interview Timetable
 
TBD
Interviews
May-June 2026 (Executive Sessions)

Finalist(s) Announced June 2026 (Board Meeting Required)*

* At least 14 calendar days prior to the meeting at which final action or vote is to be taken on the position of superintendent, all documents concerning as many as three persons under consideration whom the board has determined to be the best qualified for the position shall be subject to inspection and copying. The board can vote on the appointment at any time after the 14-day period.

June 2026
Appointment of Superintendent

Negotiated
Superintendent Reporting Date
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