## Slide 1
Ramona Elementary
Facilities Update
August 19, 2026 Board Meeting
Notes: Opening frame. This update begins from the August 5 Board presentation and narrows to information developed since then. [Sources] August 5 Board presentation provided by the District; user-provided meeting notes and Kristen Pifko feedback dated August 12, 2026.

## Slide 2
Ramona Elementary Facilities Update
Update Since the August 5 Presentation
Completed / in process
NAC, ABB, KPFF and Viola completed follow-up site work
Structural review focused on Buildings 400, 500 and 600
Final ABB report is expected after structural analysis
Viola is preparing ROM repair pricing
Next information needed
Final ABB report and structural recommendations
ROM pricing for the assumed campuswide repair scope
NAC guidance on DSA and code requirements
Operational feasibility of limited campus use
Notes: Talking points: Keep this as an update slide. Do not recite every detail from the investigation; explain that the focus has shifted from temporary relocation logistics to the repair/replacement decision framework. [Sources] User-provided notes from NAC meeting; NAC email re: August 7 site visit and structural review; August 5 Board presentation.

## Slide 3
Ramona Elementary Facilities Update
Current Status
The relocation decision was based on the full pattern of information, not a single isolated condition.
No immediate structural hazard has been identified
Current information does not indicate that the buildings were unsafe to enter.
The underlying issue is systemic
Water intrusion has affected building components and is expected to recur without comprehensive repair.
Continued operation would be reactive
Rain events could require inspections, remediation and additional testing.
Notes: Talking points: This slide addresses the apparent contradiction between previous occupancy statements and the relocation decision. The point is that there is not an identified immediate structural danger, but continued water intrusion would make ongoing occupancy operationally and financially unsound. [Sources] ABB draft investigation report dated July 17, 2026; Insight Environmental testing reports; user-provided notes from NAC meeting.

## Slide 4
Ramona Elementary Facilities Update
Working Repair Assumptions
NAC has advised that similar repairs should be assumed for similar campus buildings.
Planning assumption
Conditions are systemic rather than isolated
Representative testing supports campuswide repair planning
Additional testing may refine scope, not change the basic assumption
Likely cost drivers
Windows and exterior wall systems
Flashing and base-of-wall conditions
Interior remediation and reconstruction
DSA and code-related requirements
Notes: Talking points: This slide answers why the District is not simply pricing three openings or a few classrooms. NAC is advising that the defects are representative of similar assemblies across the affected buildings. Viola’s ROM should convert that assumption into a repair range. [Sources] User-provided NAC meeting notes; ABB draft investigation report dated July 17, 2026.

## Slide 5
Ramona Elementary Facilities Update
DSA Cost Framework
The ROM price will help determine whether the project is a repair path or a rehabilitation/replacement analysis.
Below 50%
Repair scope plus DSA review based on the work
Near 50%
At / over 50%
Comprehensive rehabilitation evaluation may be required
Risk zone for cost growth.
Notes: Talking points: Avoid overexplaining DSA in the visible slide. Talk through that 50% is important because it can move the project beyond targeted repair into rehabilitation evaluation and upgrades. The value shown is a planning reference and should be validated by NAC/DSA. [Sources] DSA Publications page, IR EB-4 Rehabilitation Required by Cost: 2025 CAC; DSA Valuation Threshold Update for 2026; OPSC Facility Hardship Funding guidance; user-provided Ramona square footage of 48,893 SF.

## Slide 6
Ramona Elementary Facilities Update
Decision Path and Planning
Now
Final report and ROM pending
Next Board update
Present Report and ROM Pricing
Short-term operational options
Review buildings at SW corner of campus for use.
Long-term repair vs replacement analysis
Consider options based on final report and ROM pricing.
Notes: Talking points: This slide follows Kristen’s direction: remove explanatory wording under the title; frame short-term operational options separately from the long-term repair/replacement analysis. [Sources] Kristen Pifko feedback dated August 12, 2026; user-provided notes from NAC meeting; OSD relocation planning documents.

## Slide 7
Ramona Elementary Facilities Update
Conclusion
Receive ABB final report and structural review
Receive Viola ROM repair pricing
Confirm DSA, fire/life-safety and accessibility requirements
Compare repair, rehabilitation and replacement paths
Notes: Talking points: Close by emphasizing that no final repair/reopening recommendation is being made until the report, ROM pricing and DSA implications are complete. [Sources] User-provided notes from NAC meeting; August 5 Board presentation.