## Slide 1
Overlook Avenue/McKinley Drive
Storm Drainage Improvements
Public Involvement Meeting
December 12, 2023
ROOM 504

## Slide 2
OVERLOOK AVENUE FLOODING
1985 – Overlook Avenue
July 4, 2023 – Overlook Avenue

## Slide 3
PROJECT AREA
LOCATION OF PHOTOS
PHASE 2
McKinley Dr
PHASE 1

## Slide 4
FLOOD STUDIES
Tata & Howard (2019)
  Analyzed the 450-acre watershed
  Developed peak flows
  Identified 2 phases to address issues with existing drainage system
Weston & Sampson (2020)
  Reviewed hydraulics and modifying drainage on McKinley Drive
  Developed plans and cost estimate
    Phase 1 Completed December 2021
      Construction Cost $100,000
      Install new manhole to eliminate turbulence on Overlook, completed December 2021
    Phase 2 Currently in Design and scheduled for Spring 2024 Construction
      Estimated Cost $3.0M ($2.0M in ARPA funds and $1.0M in City Clean Water Fund)
      Replace approximately 850 feet of existing 54” and 48” RCP with a 4’x8’ Box Culvert on McKinley Drive between Governor Street and Hale Lane
      Sidewalks, driveway aprons will be replaced

## Slide 5
PHASE 1 DEC. 2021
72” RCP
54” RCP
42” RCP

## Slide 6
PHASE 1 DEC. 2021
72” RCP
42” RCP
54” RCP

## Slide 7
PHASE 1 OVERLOOK AVE 12/2021

## Slide 8
EXISTING CONDITIONS
IN: 72”+24”+27” DIAMETER PIPES
OUT: 54” DIAMETER PIPE
48” RCP
54” RCP
60”
RCP
54” RCP
72” RCP
27” RCP
24” RCP
30” RCP
Project Length 850’
McKinley Drive
Governor Street
Overlook Avenue
Hale Lane
54” RCP
42” RCP
24” RCP
15” RCP

## Slide 9
PROJECT DESCRIPTION
Replace 48”/54” Diameter Concrete Pipes with 4’x8’ Concrete Box
New Sidewalks and Ramps
PROJECT LIMITS
4’ HEIGHT X 8’ WIDE CONCRETE BOX
SPECIAL STRUCTURE
SPECIAL STRUCTURE
McKinley Drive
Hale Lane
Governor Street
Overlook
Project Length 850’

## Slide 10
PROJECT CONSIDERATIONS
Coordination with CNG to relocate gas main (Completed)
Resident access during construction
Temporary rights to grade for sidewalk and driveways
Lead time on Box Culvert and Special Structures
Handling water during construction
Project restoration
Please provide contact information to make communication easier mostly for residents between 18-92 McKinley Drive

## Slide 11
Thank you
City of New Britain Public Works
Discussion & Questions