## Measure BB_Data
Combined Headers | Pha se | Category | Site | Project | Vendor | Description (Services) | Est. start date | Est. end date | School Year | BEST Req. | PO Number | Committed Amount | Total Exp. & Committed | Invoice Number | Warrant Date | Warrant Number | Completed Amount | DSA Number | Project Tracking # | Fund | Res. | Goal | Funct. | Obj. | Loc. | % Completion | Detail Description | Combined Headers 2
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Amazon Capital Services | Wall plates | 2020-07-08 | 2020-07-21 | 2020/21 | 21-507 | PO3W-210000000037 | 0 | 64.06 | 191J-YKGF-FMKK | 2020-07-21 | 000000020115026 | 64.06 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 100% | C2G 39702 HDMI and USB pass through wall plates, white, for Nelson, room #C1 | Nelson-1-21st Century classroom
Cedarlane-21st Century classroom-Reprographics | 1 | Reprographics | Cedarlane | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 106.6 | 10742434 | 2020-10-13 | 000000020134052 | 106.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 3.019% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Reprographics | 1 | Reprographics | Cedarlane | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 40.85 | 10744155 | 2020-10-13 | 000000020134052 | 40.85 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 1.157% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Reprographics | 1 | Reprographics | Cedarlane | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 20.51 | 10744848 | 2020-10-13 | 000000020134052 | 20.51 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.5809% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Reprographics | 1 | Reprographics | Cedarlane | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 |  | PO1-200000001133 | 0 | 7.03 | 10746778 | 2020-10-20 | 000000020136011 | 7.03 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.1991% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Reprographics | 1 | Reprographics | Cedarlane | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 |  | PO1-200000001133 | 0 | 41.17 | 10746782 | 2020-10-20 | 000000020136011 | 41.17 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 1.166% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Reprographics | 1 | Reprographics | Cedarlane | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 |  | PO1-200000001133 | 1469.2 | 1469.2 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane. Remaining balance in this PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Reprographics | 1 | Reprographics | Cedarlane | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2021-06-30 | 2020/21 | 2-9811 | PO1-200000001133 | -1469.2 | -1469.2 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Cedarlane. Close-out PO. | Cedarlane-1-21st Century classroom
District Office-21st Century classroom-Reprographics | 0 | Reprographics | District Office | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-05-13 | 2019-06-03 | 2018/19 |  | 19-109342 | 0 | 229.19 | 10193793 | 2019-06-03 | 25329661 | 229.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 100% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for the District office. | District Office-0-21st Century classroom
District Office-21st Century classroom-Reprographics | 0 | Reprographics | District Office | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-05-13 | 2019-06-03 | 2018/19 |  | 19-109342 | 1770.81 | 1770.81 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for the District office. Remaining balance in this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Reprographics | 0 | Reprographics | District Office | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-05-13 | 2019-06-30 | 2018/19 |  | 19-109342 | -1770.81 | -1770.81 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for the District office. Close-out PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Reprographics | 0 | Reprographics | District Office | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-06 | 2023/24 |  | PO1-230000000596 | 0 | 18.86 | 12291600 | 2023-12-06 | 000000021353989 | 18.86 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0.3772% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for the District office. | District Office-0-21st Century classroom
District Office-21st Century classroom-Reprographics | 0 | Reprographics | District Office | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-18 | 2023/24 |  | PO1-230000000596 | 0 | -18.86 | 12291600 | 2023-12-06 | 000000021353989 | -18.86 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | -0.3772% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover. Move exp to Facilities, PO1-24*188 (JVER 24*136) | District Office-0-21st Century classroom
District Office-21st Century classroom-Reprographics | 0 | Reprographics | District Office | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2027-12-09 | 2023/24 | 23-6057 | PO1-230000000596 | 598.41 | 598.41 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for the District office. | District Office-0-21st Century classroom
District Office-21st Century classroom-Reprographics | 0 | Reprographics | District Office | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-05-23 | 2027-12-09 | 2023/24 | 23-8344 | PO1-230000000663 | 10000 | 10000 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for the District office. | District Office-0-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-10 | 2022/23 |  | PO1-210000000492 | 0 | 40.96 | 11292881 | 2022-08-10 | 000000020578855 | 40.96 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.8192% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-18 | 2022/23 |  | PO1-210000000492 | 0 | 85.07 | 11284411 | 2022-08-18 | 000000020587943 | 85.07 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 1.701% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-18 | 2022/23 |  | PO1-210000000492 | 0 | 12.55 | 11297255 | 2022-08-18 | 000000020587943 | 12.55 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.251% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-22 | 2022/23 |  | PO1-210000000492 | 0 | 6.17 | 11300418 | 2022-08-22 | 000000020591609 | 6.17 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.1234% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 12.67 | 11304234 | 2022-08-31 | 000000020606674 | 12.67 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2534% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 4.46 | 11305380 | 2022-08-31 | 000000020606674 | 4.46 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.0892% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 4.44 | 11307269 | 2022-08-31 | 000000020606674 | 4.44 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.0888% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2023-03-07 | 2022/23 |  | PO1-210000000492 | 0 | 1179.62 | 11359952 | 2023-03-07 | 000000020889935 | 1179.62 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 23.59% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-03-07 | 2022/23 |  | PO1-230000000596 | 0 | 10.35 | 11359952 | 2023-03-07 | 000000020889935 | 10.35 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.207% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-06-06 | 2022/23 |  | PO1-230000000596 | 0 | 764.42 | 11360036 | 2023-06-06 | 000000021050327 | 764.42 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 15.29% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-01 | 2023/24 |  | PO1-230000000596 | 0 | 349.34 | 12247248 | 2023-12-01 | 000000021346387 | 349.34 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 6.987% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Reprographics | 2 | Reprographics | Grandview | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-01 | 2023/24 |  | PO1-230000000596 | 0 | 388.02 | 12248730 | 2023-12-01 | 000000021346387 | 388.02 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 7.76% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Grandview. | Grandview-2-21st Century classroom
La Puente HS-21st Century classroom-Reprographics | 5 | Reprographics | La Puente HS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-06 | 2023/24 |  | PO1-230000000596 | 0 | 88.79 | 12292159 | 2023-12-06 | 000000021353989 | 88.79 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 1.776% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for La Puente HS. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Reprographics | 5 | Reprographics | La Puente HS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-06 | 2023/24 |  | PO1-230000000596 | 0 | 24.67 | 12297228 | 2023-12-06 | 000000021353989 | 24.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 0.4934% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for La Puente HS. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Reprographics | 5 | Reprographics | La Puente HS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-06 | 2023/24 |  | PO1-230000000596 | 0 | 13.16 | 12298366 | 2023-12-06 | 000000021353989 | 13.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 0.2632% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for La Puente HS. | La Puente HS-5-21st Century classroom
Los Altos ES-21st Century classroom-Reprographics | 2 | Reprographics | Los Altos ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 2019/20 |  | PO1-200000000625 | 0 | 728.6 | 10597813 | 2020-04-22 | 000000020091358 | 728.6 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 36.43% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos HS-21st Century classroom-Reprographics | 5 | Reprographics | Los Altos HS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-01 | 2023/24 |  | PO1-230000000596 | 0 | 349.34 | 12247248 | 2023-12-01 | 000000021346387 | 349.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9411101 | 6.987% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Los Altos HS. | Los Altos HS-5-21st Century classroom
Los Molinos-Fire Alarm replacement-Reprographics | 4 | Reprographics | Los Molinos | Fire Alarm replacement | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-02-08 | 2020/21 |  | PO1-210000000492 | 0 | 422.21 | 10842654 | 2021-02-08 | 000000020162966 | 422.21 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201103 | 8.444% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Los Molinos | Los Molinos-4-Fire Alarm replacement
Mesa Robles-21st Century classroom-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 106.6 | 10742434 | 2020-10-13 | 000000020134052 | 106.6 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 3.019% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 40.84 | 10744155 | 2020-10-13 | 000000020134052 | 40.84 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.157% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-13 | 2020/21 |  | PO1-200000001133 | 0 | 20.51 | 10744848 | 2020-10-13 | 000000020134052 | 20.51 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.5809% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 |  | PO1-200000001133 | 0 | 7.03 | 10746778 | 2020-10-20 | 000000020136011 | 7.03 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.1991% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Reprographics | 1 | Reprographics | Mesa Robles | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-10-20 | 2020/21 |  | PO1-200000001133 | 0 | 41.16 | 10746782 | 2020-10-20 | 000000020136011 | 41.16 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.166% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-Interim Housing-Reprographics | 1 | Reprographics | Mesa Robles | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-06-17 | 2019/20 |  | PO1-200000001133 | 0 | 1661.08 | 10644576 | 2020-06-17 | 000000020106104 | 1661.08 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221102 | 47.05% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Mesa Robles. | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-Reprographics | 1 | Reprographics | Nelson | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-30 | 2019/20 |  | PO1-200000000625 | 0 | 728.6 | 10583551 | 2020-04-30 | 000000020093653 | 728.6 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 36.43% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Nelson. | Nelson-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-10 | 2022/23 |  | PO1-210000000492 | 0 | 40.96 | 11292881 | 2022-08-10 | 000000020578855 | 40.96 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.8192% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-18 | 2022/23 |  | PO1-210000000492 | 0 | 85.07 | 11284411 | 2022-08-18 | 000000020587943 | 85.07 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 1.701% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-18 | 2022/23 |  | PO1-210000000492 | 0 | 12.55 | 11297255 | 2022-08-18 | 000000020587943 | 12.55 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.251% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-22 | 2022/23 |  | PO1-210000000492 | 0 | 6.17 | 11300418 | 2022-08-22 | 000000020591609 | 6.17 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.1234% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 12.68 | 11304234 | 2022-08-31 | 000000020606674 | 12.68 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.2536% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 4.47 | 11305380 | 2022-08-31 | 000000020606674 | 4.47 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.0894% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 4.43 | 11307269 | 2022-08-31 | 000000020606674 | 4.43 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.0886% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2023-03-07 | 2022/23 |  | PO1-210000000492 | 0 | 1179.63 | 11359952 | 2023-03-07 | 000000020889935 | 1179.63 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 23.59% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-03-07 | 2022/23 |  | PO1-230000000596 | 0 | 10.34 | 11359952 | 2023-03-07 | 000000020889935 | 10.34 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.2068% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-06-06 | 2022/23 |  | PO1-230000000596 | 0 | 764.42 | 11360036 | 2023-06-06 | 000000021050327 | 764.42 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 15.29% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-21st Century classroom-Reprographics | 1 | Reprographics | Newton | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-01 | 2023/24 |  | PO1-230000000596 | 0 | 388.02 | 12248730 | 2023-12-01 | 000000021346387 | 388.02 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 7.76% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-21st Century classroom
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 2021/22 |  | PO1-210000000492 | 0 | 129.45 | 10959170 | 2021-09-08 | 000000020253617 | 129.45 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 2.589% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-Interim Housing
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 2021/22 |  | PO1-210000000492 | 0 | 28.53 | 10973023 | 2021-09-08 | 000000020253617 | 28.53 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 0.5706% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-Interim Housing
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 2021/22 |  | PO1-210000000492 | 0 | 15.58 | 10975113 | 2021-09-08 | 000000020253617 | 15.58 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 0.3116% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-Interim Housing
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2021-09-08 | 2021/22 |  | PO1-210000000492 | 0 | 13.38 | 10978975 | 2021-09-08 | 000000020253617 | 13.38 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 0.2676% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-Interim Housing
Newton-Interim Housing-Reprographics | 1 | Reprographics | Newton | Interim Housing | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-01-24 | 2021/22 |  | PO1-210000000492 | 0 | 353 | 11120655 | 2022-01-24 | 000000020395760 | 353 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 7.06% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Newton. | Newton-1-Interim Housing
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-10 | 2022/23 |  | PO1-210000000492 | 0 | 40.97 | 11292881 | 2022-08-10 | 000000020578855 | 40.97 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.8194% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-18 | 2022/23 |  | PO1-210000000492 | 0 | 85.07 | 11284411 | 2022-08-18 | 000000020587943 | 85.07 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 1.701% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-18 | 2022/23 |  | PO1-210000000492 | 0 | 12.55 | 11297255 | 2022-08-18 | 000000020587943 | 12.55 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.251% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-22 | 2022/23 |  | PO1-210000000492 | 0 | 6.16 | 11300418 | 2022-08-22 | 000000020591609 | 6.16 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.1232% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 12.67 | 11304234 | 2022-08-31 | 000000020606674 | 12.67 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.2534% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 4.47 | 11305380 | 2022-08-31 | 000000020606674 | 4.47 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.0894% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2022-08-31 | 2022/23 |  | PO1-210000000492 | 0 | 4.43 | 11307269 | 2022-08-31 | 000000020606674 | 4.43 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.0886% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-10-05 | 2023-03-07 | 2022/23 | 21-2247 | PO1-210000000492 | 0 | 1179.63 | 11359952 | 2023-03-07 | 000000020889935 | 1179.63 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 23.59% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-03-07 | 2022/23 |  | PO1-230000000596 | 0 | 10.34 | 11359952 | 2023-03-07 | 000000020889935 | 10.34 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.2068% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-06-06 | 2022/23 |  | PO1-230000000596 | 0 | 764.41 | 11360036 | 2023-06-06 | 000000021050327 | 764.41 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 15.29% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Reprographics | 2 | Reprographics | Sparks MS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-01 | 2023/24 |  | PO1-230000000596 | 0 | 349.35 | 12247248 | 2023-12-01 | 000000021346387 | 349.35 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 6.987% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Sparks MS. | Sparks MS-2-21st Century classroom
Workman ES-21st Century classroom-Reprographics | 2 | Reprographics | Workman ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 2019/20 |  | PO1-200000000625 | 0 | 13.62 | 10580310 | 2020-04-22 | 000000020091358 | 13.62 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.681% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Reprographics | 2 | Reprographics | Workman ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 2019/20 |  | PO1-200000000625 | 0 | 24.33 | 10589708 | 2020-04-22 | 000000020091358 | 24.33 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 1.216% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Reprographics | 2 | Reprographics | Workman ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-22 | 2019/20 |  | PO1-200000000625 | 0 | 40.19 | 10597813 | 2020-04-22 | 000000020091358 | 40.19 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 2.009% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Reprographics | 2 | Reprographics | Workman ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-30 | 2019/20 |  | PO1-200000000625 | 0 | 256.09 | 10583551 | 2020-04-30 | 000000020093653 | 256.09 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 12.8% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Reprographics | 2 | Reprographics | Workman ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-04-30 | 2019/20 |  | PO1-200000000625 | 0 | 19.71 | 10583837 | 2020-04-30 | 000000020093653 | 19.71 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.9855% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Reprographics | 2 | Reprographics | Workman ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2019-10-01 | 2020-05-06 | 2019/20 | 2-3971 | PO1-200000000625 | 0 | 188.86 | 10568458 | 2020-05-06 | 000000020095031 | 188.86 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 9.443% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Reprographics | 2 | Reprographics | Workman ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-05-06 | 2019/20 |  | PO1-200000001133 | 0 | 185.8 | 10568458 | 2020-05-06 | 000000020095031 | 185.8 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 5.262% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Reprographics | 2 | Reprographics | Workman ES | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2020-04-28 | 2020-08-17 | 2019/20 |  | PO1-200000001133 | 0 | 1251.62 | 10673862 | 2020-08-17 | 000000020119759 | 1251.62 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 35.45% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman ES. | Workman ES-2-21st Century classroom
Workman HS-21st Century classroom-Reprographics | 5 | Reprographics | Workman HS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-06 | 2023/24 |  | PO1-230000000596 | 0 | 88.79 | 12292159 | 2023-12-06 | 000000021353989 | 88.79 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 1.776% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman HS. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Reprographics | 5 | Reprographics | Workman HS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-06 | 2023/24 |  | PO1-230000000596 | 0 | 24.66 | 12297228 | 2023-12-06 | 000000021353989 | 24.66 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 0.4932% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman HS. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Reprographics | 5 | Reprographics | Workman HS | 21st Century classroom | ARC Document Solutions | Scanning/printing | 2023-02-24 | 2023-12-06 | 2023/24 |  | PO1-230000000596 | 0 | 13.17 | 12298366 | 2023-12-06 | 000000021353989 | 13.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 0.2634% | Scanning/printing - set-up, copy, digital processing, copying, stapling, binding, 3 hole drill, cover, and delivery for Workman HS. | Workman HS-5-21st Century classroom
Amar-21st Century classroom-Technology | 0 | Technology | Amar | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 19593.92 | 0175554-IN | 2019-10-21 | 000000020028933 | 19593.92 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9011101 | 2.469% | Ergotron Zip40 Charging carts to store laptops at Amar. Total carts: 15 | Amar-0-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15596.68 | 0173757-IN | 2019-10-08 | 000000020023867 | 15596.68 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 200 | 0173757-IN | 2019-10-08 | 000000020023867 | 200 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 380 | 0173757-IN | 2019-10-08 | 000000020023867 | 380 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173757-IN | 2019-10-08 | 000000020023867 | 465.6 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173757-IN | 2019-10-08 | 000000020023867 | 1281.2 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173757-IN | 2019-10-08 | 000000020023867 | 120 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173757-IN | 2019-10-08 | 000000020023867 | 60 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10917.68 | 0175537-IN | 2019-10-08 | 000000020023867 | 10917.68 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 0.2513% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 140 | 0175537-IN | 2019-10-08 | 000000020023867 | 140 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.003222% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 266 | 0175537-IN | 2019-10-08 | 000000020023867 | 266 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.006122% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 325.92 | 0175537-IN | 2019-10-08 | 000000020023867 | 325.92 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.007502% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 896.84 | 0175537-IN | 2019-10-08 | 000000020023867 | 896.84 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.02064% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 84 | 0175537-IN | 2019-10-08 | 000000020023867 | 84 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.001933% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 42 | 0175537-IN | 2019-10-08 | 000000020023867 | 42 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0009667% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 388.14 | 0173882-IN | 2019-10-10 | 000000020025135 | 388.14 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 0.008934% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 32.03 | 0173882-IN | 2019-10-10 | 000000020025135 | 32.03 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0007372% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 11.64 | 0173882-IN | 2019-10-10 | 000000020025135 | 11.64 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0002679% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 9.5 | 0173882-IN | 2019-10-10 | 000000020025135 | 9.5 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5 | 0173882-IN | 2019-10-10 | 000000020025135 | 5 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.0001151% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3 | 0173882-IN | 2019-10-10 | 000000020025135 | 3 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 6.905e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1.5 | 0173882-IN | 2019-10-10 | 000000020025135 | 1.5 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 3.452e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 155966.8 | 0174031-IN | 2019-10-10 | 000000020025135 | 155966.8 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 3.59% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 12812 | 0174031-IN | 2019-10-10 | 000000020025135 | 12812 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.2949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 600 | 0174031-IN | 2019-10-10 | 000000020025135 | 600 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.01381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1200 | 0174031-IN | 2019-10-10 | 000000020025135 | 1200 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.02762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2000 | 0174031-IN | 2019-10-10 | 000000020025135 | 2000 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.04603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3800 | 0174031-IN | 2019-10-10 | 000000020025135 | 3800 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.08746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 4656 | 0174031-IN | 2019-10-10 | 000000020025135 | 4656 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9021101 | 0.1072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Baldwin. Total computers: 469 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 |  | PO3W-200000000448 | 0 | 2600.65 | 0173900-IN | 2019-09-23 | 000000020017958 | 2600.65 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 2.854% | Ergotron Zip40 Charging carts to store laptops at Baldwin. Total carts: 14 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 15603.88 | 0174051-IN | 2019-09-23 | 000000020017958 | 15603.88 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 17.12% | Ergotron Zip40 Charging carts to store laptops at Baldwin. Total carts: 14 | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Technology | 3 | Technology | Baldwin | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-11-07 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 16981.39 | 0174405-IN | 2019-11-07 | 000000020035575 | 16981.39 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 2.14% | Ergotron Zip40 Charging carts to store laptops at Baldwin. Total carts: 13 | Baldwin-3-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5822.17 | 0173716-IN | 2019-10-10 | 000000020025135 | 5822.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9031101 | 0.134% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 174.6 | 0173716-IN | 2019-10-10 | 000000020025135 | 174.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.004019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 142.5 | 0173716-IN | 2019-10-10 | 000000020025135 | 142.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.00328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 480.45 | 0173716-IN | 2019-10-10 | 000000020025135 | 480.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.01106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 75 | 0173716-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 45 | 0173716-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 22.5 | 0173716-IN | 2019-10-10 | 000000020025135 | 22.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.0005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 7762.89 | 0173799-IN | 2019-10-10 | 000000020025135 | 7762.89 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9031101 | 0.1787% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173799-IN | 2019-10-10 | 000000020025135 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173799-IN | 2019-10-10 | 000000020025135 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173799-IN | 2019-10-10 | 000000020025135 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173799-IN | 2019-10-10 | 000000020025135 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173799-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173799-IN | 2019-10-10 | 000000020025135 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 50458.8 | 0174050-IN | 2019-10-10 | 000000020025135 | 50458.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9031101 | 1.161% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4163.9 | 0174050-IN | 2019-10-10 | 000000020025135 | 4163.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.09584% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 195 | 0174050-IN | 2019-10-10 | 000000020025135 | 195 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.004488% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 390 | 0174050-IN | 2019-10-10 | 000000020025135 | 390 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.008976% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 650 | 0174050-IN | 2019-10-10 | 000000020025135 | 650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.01496% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1235 | 0174050-IN | 2019-10-10 | 000000020025135 | 1235 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.02843% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1513.2 | 0174050-IN | 2019-10-10 | 000000020025135 | 1513.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9031101 | 0.03483% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Bixby. Total computers: 165 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 |  | PO3W-200000000448 | 0 | 1300.32 | 0174085-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9031101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Bixby. Total carts: 5 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 5201.29 | 0174091-IN | 2019-09-23 | 000000020017958 | 5201.29 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9031101 | 5.707% | Ergotron Zip40 Charging carts to store laptops at Bixby. Total carts: 5 | Bixby-6-21st Century classroom
Bixby-21st Century classroom-Technology | 6 | Technology | Bixby | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 11702.91 | 0175105-IN | 2019-10-08 | 000000020023867 | 11702.91 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9031101 | 1.475% | Ergotron Zip40 Charging carts to store laptops at Bixby. Total carts: 9 | Bixby-6-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 7018.51 | 0173641-IN | 2019-10-08 | 000000020023867 | 7018.51 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 0.1615% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 209.52 | 0173641-IN | 2019-10-08 | 000000020023867 | 209.52 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.004822% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 171 | 0173641-IN | 2019-10-08 | 000000020023867 | 171 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.003936% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 576.54 | 0173641-IN | 2019-10-08 | 000000020023867 | 576.54 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.01327% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 90 | 0173641-IN | 2019-10-08 | 000000020023867 | 90 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 54 | 0173641-IN | 2019-10-08 | 000000020023867 | 54 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.001243% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 27 | 0173641-IN | 2019-10-08 | 000000020023867 | 27 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.0006214% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173804-IN | 2019-10-21 | 000000020028933 | 7798.34 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173804-IN | 2019-10-21 | 000000020028933 | 190 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173804-IN | 2019-10-21 | 000000020028933 | 100 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173804-IN | 2019-10-21 | 000000020028933 | 232.8 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173804-IN | 2019-10-21 | 000000020028933 | 640.6 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173804-IN | 2019-10-21 | 000000020028933 | 60 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173804-IN | 2019-10-21 | 000000020028933 | 30 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 73694.31 | 0175624-IN | 2019-10-21 | 000000020028933 | 73694.31 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 1.696% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6053.67 | 0175624-IN | 2019-10-21 | 000000020028933 | 6053.67 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.1393% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 283.5 | 0175624-IN | 2019-10-21 | 000000020028933 | 283.5 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.006525% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 567 | 0175624-IN | 2019-10-21 | 000000020028933 | 567 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.01305% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 945 | 0175624-IN | 2019-10-21 | 000000020028933 | 945 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.02175% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1795.5 | 0175624-IN | 2019-10-21 | 000000020028933 | 1795.5 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.04133% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2199.96 | 0175624-IN | 2019-10-21 | 000000020028933 | 2199.96 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.05064% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 227 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 10137.84 | 0175604-IN | 2019-11-13 | 000000020037339 | 10137.84 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 0.3613% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 39 | 0175604-IN | 2019-11-13 | 000000020037339 | 39 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.00139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 |  | PO3W-200000000332 | 0 | 130 | 0175604-IN | 2019-11-13 | 000000020037339 | 130 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.004634% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 |  | PO3W-200000000332 | 0 | 247 | 0175604-IN | 2019-11-13 | 000000020037339 | 247 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.008804% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 |  | PO3W-200000000332 | 0 | 302.64 | 0175604-IN | 2019-11-13 | 000000020037339 | 302.64 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.01079% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 |  | PO3W-200000000332 | 0 | 832.78 | 0175604-IN | 2019-11-13 | 000000020037339 | 832.78 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.02968% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-13 | 2019/20 |  | PO3W-200000000332 | 0 | 78 | 0175604-IN | 2019-11-13 | 000000020037339 | 78 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9041101 | 0.00278% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for California. Total computers: 26 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO3W-200000000730 | 0 | 1306.26 | 0175607-IN | 2019-10-21 | 000000020028933 | 1306.26 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9041101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at California. Total carts: 16 | California-3-21st Century classroom
California-21st Century classroom-Technology | 3 | Technology | California | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 19593.92 | 0175608-IN | 2019-10-21 | 000000020028933 | 19593.92 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9041101 | 2.469% | Ergotron Zip40 Charging carts to store laptops at California. Total carts: 16 | California-3-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 17466.51 | 0173447-IN | 2019-10-10 | 000000020025135 | 17466.51 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 0.402% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 135 | 0173447-IN | 2019-10-10 | 000000020025135 | 135 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.003107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 225 | 0173447-IN | 2019-10-10 | 000000020025135 | 225 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 427.5 | 0173447-IN | 2019-10-10 | 000000020025135 | 427.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.00984% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 523.8 | 0173447-IN | 2019-10-10 | 000000020025135 | 523.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.01206% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1441.35 | 0173447-IN | 2019-10-10 | 000000020025135 | 1441.35 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.03318% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 67.5 | 0173447-IN | 2019-10-10 | 000000020025135 | 67.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.001554% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 11644.34 | 0173687-IN | 2019-10-10 | 000000020025135 | 11644.34 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 0.268% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 150 | 0173687-IN | 2019-10-10 | 000000020025135 | 150 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 285 | 0173687-IN | 2019-10-10 | 000000020025135 | 285 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.00656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 349.2 | 0173687-IN | 2019-10-10 | 000000020025135 | 349.2 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.008037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 960.9 | 0173687-IN | 2019-10-10 | 000000020025135 | 960.9 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.02212% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 90 | 0173687-IN | 2019-10-10 | 000000020025135 | 90 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 45 | 0173687-IN | 2019-10-10 | 000000020025135 | 45 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7762.89 | 0173800-IN | 2019-10-21 | 000000020028933 | 7762.89 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 0.1787% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173800-IN | 2019-10-21 | 000000020028933 | 30 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173800-IN | 2019-10-21 | 000000020028933 | 190 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173800-IN | 2019-10-21 | 000000020028933 | 100 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173800-IN | 2019-10-21 | 000000020028933 | 232.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173800-IN | 2019-10-21 | 000000020028933 | 640.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173800-IN | 2019-10-21 | 000000020028933 | 60 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 95 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 201835.22 | 0175292-IN | 2019-10-22 | 000000020029495 | 201835.22 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 7.194% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 16655.6 | 0175292-IN | 2019-10-22 | 000000020029495 | 16655.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.5937% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 780 | 0175292-IN | 2019-10-22 | 000000020029495 | 780 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.0278% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1560 | 0175292-IN | 2019-10-22 | 000000020029495 | 1560 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.0556% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2600 | 0175292-IN | 2019-10-22 | 000000020029495 | 2600 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.09267% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 4940 | 0175292-IN | 2019-10-22 | 000000020029495 | 4940 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.1761% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 6052.8 | 0175292-IN | 2019-10-22 | 000000020029495 | 6052.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9051101 | 0.2157% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Cedarlane. Total computers: 520 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173470-IN | 2019-09-23 | 000000020017958 | 1300.32 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Cedarlane. Total cart: 1 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 |  | PO3W-200000000730 | 0 | 1300.32 | 0175313-IN | 2019-10-15 | 000000020026572 | 1300.32 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 0.1639% | Ergotron Zip40 Charging carts to store laptops at Cedarlane. Total carts: 21 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 26006.47 | 0175340-IN | 2019-10-15 | 000000020026572 | 26006.47 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 3.277% | Ergotron Zip40 Charging carts to store laptops at Cedarlane. Total carts: 21 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-12-02 | 2021-03-04 | 2020/21 |  | PO3W-210000001075 | 0 | 13871.18 | 0195589-IN | 2021-03-04 | 000000020169354 | 13871.18 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 10.08% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Cedarlane. Total monitors: 25 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-12-02 | 2021-04-09 | 2020/21 | 21-3335 | PO3W-210000001075 | 0 | 40746.58 | 0196289-IN | 2021-04-09 | 000000020179111 | 40746.58 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 29.6% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Cedarlane. Total monitors: 25 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 2020/21 |  | PO3W-210000001078 | 0 | 1988.53 | 0193365-IN | 2021-01-22 | 000000020158901 | 1988.53 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 2.995% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 25 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | 24363.75 | 0193365-IN | 2021-01-22 | 000000020158901 | 24363.75 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 36.69% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 25 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-03-04 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | -2.74 | 193365C-CM | 2021-03-04 | 000000020169354 | -2.74 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | -0.004126% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 25. Credit memo from vendor | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2021-08-18 | 2022-02-08 | 2021/22 | 22-1266 | PO3W-220000000256 | 0 | 4357.42 | 0205845-IN | 2022-02-08 | 000000020409355 | 4357.42 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 65.22% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Cedarlane. Total monitors: 2 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Web camera(s) | 2021-08-18 | 2022-02-08 | 2021/22 | 22-1266 | PO3W-220000000256 | 0 | 175.21 | 0205845-IN | 2022-02-08 | 000000020409355 | 175.21 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 2.623% | Viewsonic ViewCam VB-CAM-001 for Cedarlane. Total web cams: 2 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2021-08-18 | 2022-02-08 | 2021/22 |  | PO3W-220000000256 | 0 | 86.3 | 0207936-IN | 2022-02-08 | 000000020409355 | 86.3 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 1.292% | Desktop computers (Lenovo ThinkCentre M70q), ThinkCentre Tiny Sandwich Kit II, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 2 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2021-08-18 | 2022-02-08 | 2021/22 |  | PO3W-220000000256 | 0 | 2061.76 | 0207936-IN | 2022-02-08 | 000000020409355 | 2061.76 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 30.86% | Desktop computers (Lenovo ThinkCentre M70q), ThinkCentre Tiny Sandwich Kit II, and Tiny Power Cage II for Cedarlane (4 year warranty). Total computers: 2 | Cedarlane-1-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15596.67 | 0173756-IN | 2019-10-10 | 000000020025135 | 15596.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9061101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 200 | 0173756-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173756-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 380 | 0173756-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173756-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173756-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173756-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6628.59 | 0175538-IN | 2019-10-10 | 000000020025135 | 6628.59 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9061101 | 0.1526% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 25.5 | 0175538-IN | 2019-10-10 | 000000020025135 | 25.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.0005869% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 197.88 | 0175538-IN | 2019-10-10 | 000000020025135 | 197.88 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.004555% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 161.5 | 0175538-IN | 2019-10-10 | 000000020025135 | 161.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.003717% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 85 | 0175538-IN | 2019-10-10 | 000000020025135 | 85 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.001956% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 544.51 | 0175538-IN | 2019-10-10 | 000000020025135 | 544.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.01253% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 51 | 0175538-IN | 2019-10-10 | 000000020025135 | 51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.001174% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 57 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 89680.91 | 0175097-IN | 2019-10-10 | 000000020025132 | 89680.91 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9061101 | 3.197% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7366.9 | 0175097-IN | 2019-10-10 | 000000020025132 | 7366.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.2626% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 345 | 0175097-IN | 2019-10-10 | 000000020025132 | 345 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.0123% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 690 | 0175097-IN | 2019-10-10 | 000000020025132 | 690 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.02459% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 1150 | 0175097-IN | 2019-10-10 | 000000020025132 | 1150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.04099% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 2185 | 0175097-IN | 2019-10-10 | 000000020025132 | 2185 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.07788% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 2677.2 | 0175097-IN | 2019-10-10 | 000000020025132 | 2677.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9061101 | 0.09543% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Del Valle. Total computers: 230 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO3W-200000000730 | 0 | 2612.53 | 0175076-IN | 2019-10-08 | 000000020023867 | 2612.53 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9061101 | 0.3292% | Ergotron Zip40 Charging carts to store laptops at Del Valle. Total carts: 16 | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-Technology | 7 | Technology | Del Valle | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 18287.65 | 0175099-IN | 2019-10-08 | 000000020023867 | 18287.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9061101 | 2.305% | Ergotron Zip40 Charging carts to store laptops at Del Valle. Total carts: 16 | Del Valle-7-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 16690.22 | 0174219-IN | 2019-10-10 | 000000020025135 | 16690.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 0.3842% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 64.5 | 0174219-IN | 2019-10-10 | 000000020025135 | 64.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.001485% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 215 | 0174219-IN | 2019-10-10 | 000000020025135 | 215 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.004949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 129 | 0174219-IN | 2019-10-10 | 000000020025135 | 129 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.002969% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 408.5 | 0174219-IN | 2019-10-10 | 000000020025135 | 408.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.009402% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 500.52 | 0174219-IN | 2019-10-10 | 000000020025135 | 500.52 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.01152% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1377.29 | 0174219-IN | 2019-10-10 | 000000020025135 | 1377.29 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.0317% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 43 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2020-02-07 | 2020-03-06 | 2019/20 |  | PO2W-200000004388 | 0 | 1164.44 | 0178870-IN | 2020-03-06 | 000000020078467 | 1164.44 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 43.14% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 6 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2020-02-07 | 2020-03-06 | 2019/20 |  | PO2W-200000004388 | 0 | 185.01 | 0178870-IN | 2020-03-06 | 000000020078467 | 185.01 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 6.855% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 6 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2020-02-07 | 2020-04-23 | 2019/20 | 2-7716 | PO2W-200000004388 | 0 | 1164.43 | 0181588-IN | 2020-04-23 | 000000020091968 | 1164.43 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 43.14% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 6 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2020-02-07 | 2020-04-23 | 2019/20 | 2-7716 | PO2W-200000004388 | 0 | 185.02 | 0181588-IN | 2020-04-23 | 000000020091968 | 185.02 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 6.855% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 6 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 37650.03 | 0176668-IN | 2019-11-21 | 000000020040910 | 37650.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 1.342% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 3106.91 | 0176668-IN | 2019-11-21 | 000000020040910 | 3106.91 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.1107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 |  | PO3W-200000000332 | 0 | 145.5 | 0176668-IN | 2019-11-21 | 000000020040910 | 145.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.005186% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 |  | PO3W-200000000332 | 0 | 291 | 0176668-IN | 2019-11-21 | 000000020040910 | 291 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.01037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 |  | PO3W-200000000332 | 0 | 485 | 0176668-IN | 2019-11-21 | 000000020040910 | 485 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.01729% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 |  | PO3W-200000000332 | 0 | 921.5 | 0176668-IN | 2019-11-21 | 000000020040910 | 921.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.03285% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-21 | 2019/20 |  | PO3W-200000000332 | 0 | 1129.08 | 0176668-IN | 2019-11-21 | 000000020040910 | 1129.08 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.04024% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for District-wide use. Total computers: 97 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Document camera(s) | 2023-08-15 | 2023-11-03 | 2023/24 | 24-1684 | PO3W-240000000370 | 0 | 3602.93 | 0231244-IN | 2023-11-03 | 000000021302745 | 3602.93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 15.85% | Elmo TT-12W Stem Cam Document Camera (HDMI Input, wireless connectivity) for District-wide use. Total cameras: 5 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2023-08-15 | 2023-11-03 | 2023/24 | 24-1684 | PO3W-240000000370 | 0 | 13163.81 | 0231502-IN | 2023-11-03 | 000000021302745 | 13163.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 57.91% | ViewSonicViewBoard IFP7550-E2 - 75" Diagonal class LED display-interactive-with touchscreen (multi touch), ewaste, and extended service agreement for parts & labor (7 year warranty) for District-wide use. Total monitors: 5 | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2023-08-15 | 2023-11-03 | 2023/24 | 24-1684 | PO3W-240000000370 | 0 | 5965.07 | 0231664-IN | 2023-11-03 | 000000021302745 | 5965.07 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 26.24% | Desktop computers (Lenovo ThinkCentre M70q Gen 3 i7-12700T 16GB RAM 256GB SSD), 4 year warranty for District-wide use. Total computers: 5 | District Office-0-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15596.67 | 0173446-IN | 2019-10-10 | 000000020025135 | 15596.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 200 | 0173446-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173446-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 380 | 0173446-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173446-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173446-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173446-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 15206.76 | 0175539-IN | 2019-10-10 | 000000020025135 | 15206.76 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 0.35% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 195 | 0175539-IN | 2019-10-10 | 000000020025135 | 195 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.004488% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 117 | 0175539-IN | 2019-10-10 | 000000020025135 | 117 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.002693% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 370.5 | 0175539-IN | 2019-10-10 | 000000020025135 | 370.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.008528% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 453.96 | 0175539-IN | 2019-10-10 | 000000020025135 | 453.96 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.01045% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1249.17 | 0175539-IN | 2019-10-10 | 000000020025135 | 1249.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.02875% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 58.5 | 0175539-IN | 2019-10-10 | 000000020025135 | 58.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.001346% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 17546.27 | 0173770-IN | 2019-10-21 | 000000020028933 | 17546.27 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 0.4039% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1441.35 | 0173770-IN | 2019-10-21 | 000000020028933 | 1441.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.03318% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 135 | 0173770-IN | 2019-10-21 | 000000020028933 | 135 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.003107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 67.5 | 0173770-IN | 2019-10-21 | 000000020028933 | 67.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.001554% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 225 | 0173770-IN | 2019-10-21 | 000000020028933 | 225 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 427.5 | 0173770-IN | 2019-10-21 | 000000020028933 | 427.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.00984% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 523.8 | 0173770-IN | 2019-10-21 | 000000020028933 | 523.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.01206% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 124 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 298286.51 | 0175159-IN | 2019-10-22 | 000000020029495 | 298286.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 10.63% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 24502.95 | 0175159-IN | 2019-10-22 | 000000020029495 | 24502.95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.8734% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1147.5 | 0175159-IN | 2019-10-22 | 000000020029495 | 1147.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.0409% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2295 | 0175159-IN | 2019-10-22 | 000000020029495 | 2295 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.0818% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 3825 | 0175159-IN | 2019-10-22 | 000000020029495 | 3825 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.1363% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 7267.5 | 0175159-IN | 2019-10-22 | 000000020029495 | 7267.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.259% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 8904.6 | 0175159-IN | 2019-10-22 | 000000020029495 | 8904.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9091101 | 0.3174% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Fairgrove. Total computers: 765 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1306.26 | 0173475-IN | 2019-09-23 | 000000020017958 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at Fairgrove. Total cart: 1 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 |  | PO3W-200000000730 | 0 | 43106.72 | 0175372-IN | 2019-10-11 | 000000020025716 | 43106.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | 5.432% | Ergotron Zip40 Charging carts to store laptops at Fairgrove. Total carts: 35 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 |  | PO3W-200000000730 | 0 | 2612.53 | 0175124-IN | 2019-10-15 | 000000020026572 | 2612.53 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | 0.3292% | Ergotron Zip40 Charging carts to store laptops at Fairgrove. Total carts: 35 | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Technology | 4 | Technology | Fairgrove | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | -0.1 | 0175372-IN | 2019-10-15 | 000000020026572 | -0.1 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | -1.26e-05% | Ergotron Zip40 Charging carts to store laptops at Fairgrove. Total carts: 35. To offset over payment of $0.10 on invoice #175372 | Fairgrove-4-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10479.91 | 0175540-IN | 2019-10-10 | 000000020025135 | 10479.91 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 0.2412% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 135 | 0175540-IN | 2019-10-10 | 000000020025135 | 135 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.003107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 81 | 0175540-IN | 2019-10-10 | 000000020025135 | 81 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.001864% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 256.5 | 0175540-IN | 2019-10-10 | 000000020025135 | 256.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.005904% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 314.28 | 0175540-IN | 2019-10-10 | 000000020025135 | 314.28 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.007234% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 864.81 | 0175540-IN | 2019-10-10 | 000000020025135 | 864.81 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.01991% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 40.5 | 0175540-IN | 2019-10-10 | 000000020025135 | 40.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.0009322% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 7762.89 | 0173759-IN | 2019-10-21 | 000000020028933 | 7762.89 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 0.1787% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30 | 0173759-IN | 2019-10-21 | 000000020028933 | 30 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173759-IN | 2019-10-21 | 000000020028933 | 190 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173759-IN | 2019-10-21 | 000000020028933 | 100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173759-IN | 2019-10-21 | 000000020028933 | 60 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173759-IN | 2019-10-21 | 000000020028933 | 232.8 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173759-IN | 2019-10-21 | 000000020028933 | 640.6 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 47 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 196013.05 | 0175497-IN | 2019-10-22 | 000000020029495 | 196013.05 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 6.987% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 16175.15 | 0175497-IN | 2019-10-22 | 000000020029495 | 16175.15 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.5765% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 757.5 | 0175497-IN | 2019-10-22 | 000000020029495 | 757.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.027% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1515 | 0175497-IN | 2019-10-22 | 000000020029495 | 1515 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.054% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2525 | 0175497-IN | 2019-10-22 | 000000020029495 | 2525 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.09% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 4797.5 | 0175497-IN | 2019-10-22 | 000000020029495 | 4797.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.171% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 5878.2 | 0175497-IN | 2019-10-22 | 000000020029495 | 5878.2 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9121101 | 0.2095% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grandview. Total computers: 505 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000730 | 0 | 1300.32 | 0175125-IN | 2019-10-22 | 000000020029495 | 1300.32 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 0.1639% | Ergotron Zip40 Charging carts to store laptops at Grandview. Total carts: 18 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 22105.5 | 0175546-IN | 2019-10-22 | 000000020029495 | 22105.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 2.786% | Ergotron Zip40 Charging carts to store laptops at Grandview. Total carts: 18 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 40841.02 | 0221871-IN | 2023-01-26 | 000000020824366 | 40841.02 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 24.19% | ViewSonicViewBoard IFP7550 interactive flat panel - 75" Diagonal class LED-backlit LCD, adapter, ewaste, and extended service agreement for parts & labor for Grandview. Total monitors: 19 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Web camera(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 1004.27 | 0221871-IN | 2023-01-26 | 000000020824366 | 1004.27 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 0.5948% | Viewsonic ViewCam VB-CAM-001 for Grandview. Total web cams: 19 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 21054.09 | 0221901-IN | 2023-01-26 | 000000020824366 | 21054.09 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 12.47% | Desktop computers (Lenovo ThinkCentre M70q Gen 3 i7-12700T 16GB RAM 256GB SSD), 4 year warranty for Grandview. Total computers: 19 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Mounting bracket | 2023-03-31 | 2023-05-04 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 624.15 | 0226489-IN | 2023-05-04 | 000000020993482 | 624.15 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 13.15% | Lenovo ThinkCentre tiny sandwich kit II - system mounting bracket (19) for Grandview | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Keyboard & mouse | 2023-03-31 | 2023-05-04 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 811.4 | 0226489-IN | 2023-05-04 | 000000020993482 | 811.4 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 17.09% | Lenovo essential wireless combo - keyboard & mouse set - wireless - 2.4 GHz - US (19) for Grandview | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Arey Jones Educational Solutions | Power supply | 2023-03-31 | 2023-06-26 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 332.88 | 0228571-IN | 2023-06-26 | 000000021091332 | 332.88 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 7.013% | Lenovo tiny power cage II - Power supply cage (19) for Grandview | Grandview-2-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 9315.47 | 0173712-IN | 2019-10-10 | 000000020025135 | 9315.47 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9131101 | 0.2144% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173712-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 72 | 0173712-IN | 2019-10-10 | 000000020025135 | 72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.001657% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 228 | 0173712-IN | 2019-10-10 | 000000020025135 | 228 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.005248% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 279.36 | 0173712-IN | 2019-10-10 | 000000020025135 | 279.36 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.00643% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 768.72 | 0173712-IN | 2019-10-10 | 000000020025135 | 768.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.01769% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 36 | 0173712-IN | 2019-10-10 | 000000020025135 | 36 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.0008286% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 126147.01 | 0174014-IN | 2019-10-10 | 000000020025135 | 126147.01 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9131101 | 2.903% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10409.75 | 0174014-IN | 2019-10-10 | 000000020025135 | 10409.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.2396% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 487.5 | 0174014-IN | 2019-10-10 | 000000020025135 | 487.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.01122% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 975 | 0174014-IN | 2019-10-10 | 000000020025135 | 975 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.02244% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1625 | 0174014-IN | 2019-10-10 | 000000020025135 | 1625 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.0374% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3087.5 | 0174014-IN | 2019-10-10 | 000000020025135 | 3087.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.07106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3783 | 0174014-IN | 2019-10-10 | 000000020025135 | 3783 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9131101 | 0.08707% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Grazide. Total computers: 349 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 13003.23 | 0174099-IN | 2019-09-23 | 000000020017958 | 13003.23 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9131101 | 14.27% | Ergotron Zip40 Charging carts to store laptops at Grazide. Total carts: 10 | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Technology | 3 | Technology | Grazide | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 16904.22 | 0175152-IN | 2019-10-08 | 000000020023867 | 16904.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9131101 | 2.13% | Ergotron Zip40 Charging carts to store laptops at Grazide. Total carts: 13 | Grazide-3-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5822.17 | 0173555-IN | 2019-10-10 | 000000020025135 | 5822.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 0.134% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 174.6 | 0173555-IN | 2019-10-10 | 000000020025135 | 174.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.004019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 142.5 | 0173555-IN | 2019-10-10 | 000000020025135 | 142.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.00328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 75 | 0173555-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 480.45 | 0173555-IN | 2019-10-10 | 000000020025135 | 480.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 45 | 0173555-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 22.5 | 0173555-IN | 2019-10-10 | 000000020025135 | 22.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15525.78 | 0173802-IN | 2019-10-10 | 000000020025135 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 0.3574% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 200 | 0173802-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173802-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173802-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 380 | 0173802-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173802-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173802-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5822.17 | 0173880-IN | 2019-10-10 | 000000020025135 | 5822.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 0.134% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 174.6 | 0173880-IN | 2019-10-10 | 000000020025135 | 174.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.004019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 142.5 | 0173880-IN | 2019-10-10 | 000000020025135 | 142.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.00328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 75 | 0173880-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 480.45 | 0173880-IN | 2019-10-10 | 000000020025135 | 480.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 45 | 0173880-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 22.5 | 0173880-IN | 2019-10-10 | 000000020025135 | 22.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 388.16 | 0173881-IN | 2019-10-10 | 000000020025135 | 388.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 0.008934% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 32.03 | 0173881-IN | 2019-10-10 | 000000020025135 | 32.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0007372% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 11.64 | 0173881-IN | 2019-10-10 | 000000020025135 | 11.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0002679% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 9.5 | 0173881-IN | 2019-10-10 | 000000020025135 | 9.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5 | 0173881-IN | 2019-10-10 | 000000020025135 | 5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0001151% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3 | 0173881-IN | 2019-10-10 | 000000020025135 | 3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 6.905e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1.5 | 0173881-IN | 2019-10-10 | 000000020025135 | 1.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 3.452e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 58221.7 | 0173950-IN | 2019-10-10 | 000000020025135 | 58221.7 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 1.34% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4804.5 | 0173950-IN | 2019-10-10 | 000000020025135 | 4804.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.1106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 225 | 0173950-IN | 2019-10-10 | 000000020025135 | 225 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 450 | 0173950-IN | 2019-10-10 | 000000020025135 | 450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 750 | 0173950-IN | 2019-10-10 | 000000020025135 | 750 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.01726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1425 | 0173950-IN | 2019-10-10 | 000000020025135 | 1425 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.0328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1746 | 0173950-IN | 2019-10-10 | 000000020025135 | 1746 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9161101 | 0.04019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Kwis. Total computers: 221 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 2600.65 | 0173901-IN | 2019-09-23 | 000000020017958 | 2600.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 2.854% | Ergotron Zip40 Charging carts to store laptops at Kwis. Total carts: 8 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 |  | PO3W-200000000448 | 0 | 1300.32 | 0173905-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Kwis. Total carts: 8 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 6501.61 | 0173952-IN | 2019-09-23 | 000000020017958 | 6501.61 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 7.134% | Ergotron Zip40 Charging carts to store laptops at Kwis. Total carts: 8 | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Technology | 7 | Technology | Kwis | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 9102.26 | 0175117-IN | 2019-10-08 | 000000020023867 | 9102.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 1.147% | Ergotron Zip40 Charging carts to store laptops at Kwis. Total carts: 7 | Kwis-7-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 13647.1 | 0173367-IN | 2019-10-10 | 000000020025135 | 13647.1 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9401101 | 0.3141% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 175 | 0173367-IN | 2019-10-10 | 000000020025135 | 175 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.004028% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 105 | 0173367-IN | 2019-10-10 | 000000020025135 | 105 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.002417% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 52.5 | 0173367-IN | 2019-10-10 | 000000020025135 | 52.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.001208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 332.5 | 0173367-IN | 2019-10-10 | 000000020025135 | 332.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.007653% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 407.4 | 0173367-IN | 2019-10-10 | 000000020025135 | 407.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.009377% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1121.05 | 0173367-IN | 2019-10-10 | 000000020025135 | 1121.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.0258% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 20275.68 | 0173639-IN | 2019-10-10 | 000000020025135 | 20275.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9401101 | 0.4667% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 156 | 0173639-IN | 2019-10-10 | 000000020025135 | 156 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.003591% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 78 | 0173639-IN | 2019-10-10 | 000000020025135 | 78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.001795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 260 | 0173639-IN | 2019-10-10 | 000000020025135 | 260 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.005984% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 494 | 0173639-IN | 2019-10-10 | 000000020025135 | 494 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.01137% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 605.28 | 0173639-IN | 2019-10-10 | 000000020025135 | 605.28 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.01393% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1665.56 | 0173639-IN | 2019-10-10 | 000000020025135 | 1665.56 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.03834% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 366521.98 | 0174537-IN | 2019-10-10 | 000000020025135 | 366521.98 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9401101 | 8.436% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 30108.2 | 0174537-IN | 2019-10-10 | 000000020025135 | 30108.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.693% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1410 | 0174537-IN | 2019-10-10 | 000000020025135 | 1410 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.03245% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2820 | 0174537-IN | 2019-10-10 | 000000020025135 | 2820 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.06491% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 4700 | 0174537-IN | 2019-10-10 | 000000020025135 | 4700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.1082% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 8930 | 0174537-IN | 2019-10-10 | 000000020025135 | 8930 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.2055% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 10941.6 | 0174537-IN | 2019-10-10 | 000000020025135 | 10941.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9401101 | 0.2518% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for La Puente HS. Total computers: 1027 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1306.26 | 0173476-IN | 2019-09-23 | 000000020017958 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9401101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at La Puente HS. Total cart: 1 | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Technology | 5 | Technology | La Puente HS | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 39187.83 | 0174704-IN | 2019-10-08 | 000000020023867 | 39187.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9401101 | 4.938% | Ergotron Zip40 Charging carts to store laptops at La Puente HS. Total carts: 30 | La Puente HS-5-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 11697.51 | 0173445-IN | 2019-10-10 | 000000020025135 | 11697.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 0.2692% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 150 | 0173445-IN | 2019-10-10 | 000000020025135 | 150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 90 | 0173445-IN | 2019-10-10 | 000000020025135 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 45 | 0173445-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 285 | 0173445-IN | 2019-10-10 | 000000020025135 | 285 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.00656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 349.2 | 0173445-IN | 2019-10-10 | 000000020025135 | 349.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.008037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 960.9 | 0173445-IN | 2019-10-10 | 000000020025135 | 960.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.02212% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 11697.51 | 0173633-IN | 2019-10-10 | 000000020025135 | 11697.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 0.2692% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 150 | 0173633-IN | 2019-10-10 | 000000020025135 | 150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 90 | 0173633-IN | 2019-10-10 | 000000020025135 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 45 | 0173633-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 285 | 0173633-IN | 2019-10-10 | 000000020025135 | 285 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.00656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 349.2 | 0173633-IN | 2019-10-10 | 000000020025135 | 349.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.008037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 960.9 | 0173633-IN | 2019-10-10 | 000000020025135 | 960.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.02212% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173801-IN | 2019-10-10 | 000000020025135 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173801-IN | 2019-10-10 | 000000020025135 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173801-IN | 2019-10-10 | 000000020025135 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173801-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173801-IN | 2019-10-10 | 000000020025135 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173801-IN | 2019-10-10 | 000000020025135 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173801-IN | 2019-10-10 | 000000020025135 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 150118.05 | 0173980-IN | 2019-10-10 | 000000020025135 | 150118.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 3.455% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 12331.55 | 0173980-IN | 2019-10-10 | 000000020025135 | 12331.55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.2838% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 577.5 | 0173980-IN | 2019-10-10 | 000000020025135 | 577.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.01329% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1155 | 0173980-IN | 2019-10-10 | 000000020025135 | 1155 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.02658% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1925 | 0173980-IN | 2019-10-10 | 000000020025135 | 1925 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.04431% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3657.5 | 0173980-IN | 2019-10-10 | 000000020025135 | 3657.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.08418% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 4481.4 | 0173980-IN | 2019-10-10 | 000000020025135 | 4481.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9171101 | 0.1031% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Lassalette. Total computers: 465 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 |  | PO3W-200000000448 | 0 | 1306.26 | 0173471-IN | 2019-09-23 | 000000020017958 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at Lassalette. Total carts: 16 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 |  | PO3W-200000000448 | 0 | 1306.26 | 0174062-IN | 2019-09-23 | 000000020017958 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at Lassalette. Total carts: 16 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 18287.67 | 0174093-IN | 2019-09-23 | 000000020017958 | 18287.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 20.07% | Ergotron Zip40 Charging carts to store laptops at Lassalette. Total carts: 16 | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-Technology | 6 | Technology | Lassalette | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-11-07 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 11756.35 | 0174403-IN | 2019-11-07 | 000000020035575 | 11756.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 1.482% | Ergotron Zip40 Charging carts to store laptops at Lassalette. Total carts: 9 | Lassalette-6-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 8539.18 | 0173645-IN | 2019-10-10 | 000000020025135 | 8539.18 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9191101 | 0.1965% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 704.66 | 0173645-IN | 2019-10-10 | 000000020025135 | 704.66 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.01622% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 209 | 0173645-IN | 2019-10-10 | 000000020025135 | 209 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.00481% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 110 | 0173645-IN | 2019-10-10 | 000000020025135 | 110 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.002532% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 66 | 0173645-IN | 2019-10-10 | 000000020025135 | 66 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.001519% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 33 | 0173645-IN | 2019-10-10 | 000000020025135 | 33 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.0007595% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 256.08 | 0173645-IN | 2019-10-10 | 000000020025135 | 256.08 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.005894% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 22 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 114502.67 | 0175570-IN | 2019-10-22 | 000000020029495 | 114502.67 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9191101 | 4.081% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 9448.85 | 0175570-IN | 2019-10-22 | 000000020029495 | 9448.85 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.3368% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 442.5 | 0175570-IN | 2019-10-22 | 000000020029495 | 442.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.01577% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 885 | 0175570-IN | 2019-10-22 | 000000020029495 | 885 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.03154% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1475 | 0175570-IN | 2019-10-22 | 000000020029495 | 1475 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.05257% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2802.5 | 0175570-IN | 2019-10-22 | 000000020029495 | 2802.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.09989% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 3433.8 | 0175570-IN | 2019-10-22 | 000000020029495 | 3433.8 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9191101 | 0.1224% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos ES. Total computers: 295 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 27306.79 | 0175609-IN | 2019-10-22 | 000000020029495 | 27306.79 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 3.441% | Ergotron Zip40 Charging carts to store laptops at Los Altos ES. Total carts: 21 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 120 | 0189682-IN | 2020-10-01 | 000000020131103 | 120 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 0.09629% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Los Altos ES. Total monitors: 20 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 43574.21 | 0189682-IN | 2020-10-01 | 000000020131103 | 43574.21 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 34.96% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Los Altos ES. Total monitors: 20 | Los Altos ES-2-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15525.78 | 0173444-IN | 2019-10-10 | 000000020025135 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9411101 | 0.3574% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 200 | 0173444-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173444-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173444-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 380 | 0173444-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173444-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173444-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 28334.56 | 0173701-IN | 2019-10-10 | 000000020025135 | 28334.56 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9411101 | 0.6522% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 109.5 | 0173701-IN | 2019-10-10 | 000000020025135 | 109.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.00252% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 219 | 0173701-IN | 2019-10-10 | 000000020025135 | 219 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.005041% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 365 | 0173701-IN | 2019-10-10 | 000000020025135 | 365 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.008401% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 693.5 | 0173701-IN | 2019-10-10 | 000000020025135 | 693.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.01596% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 849.72 | 0173701-IN | 2019-10-10 | 000000020025135 | 849.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.01956% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2338.19 | 0173701-IN | 2019-10-10 | 000000020025135 | 2338.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.05382% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 388.14 | 0173889-IN | 2019-10-10 | 000000020025135 | 388.14 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9411101 | 0.008934% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 32.03 | 0173889-IN | 2019-10-10 | 000000020025135 | 32.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.0007372% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 11.64 | 0173889-IN | 2019-10-10 | 000000020025135 | 11.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.0002679% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 9.5 | 0173889-IN | 2019-10-10 | 000000020025135 | 9.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.0002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5 | 0173889-IN | 2019-10-10 | 000000020025135 | 5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.0001151% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3 | 0173889-IN | 2019-10-10 | 000000020025135 | 3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 6.905e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1.5 | 0173889-IN | 2019-10-10 | 000000020025135 | 1.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 3.452e-05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 580276.25 | 0174379-IN | 2019-10-10 | 000000020025136 | 580276.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9411101 | 13.36% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 47884.85 | 0174379-IN | 2019-10-10 | 000000020025136 | 47884.85 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 1.102% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2242.5 | 0174379-IN | 2019-10-10 | 000000020025136 | 2242.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.05161% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 4485 | 0174379-IN | 2019-10-10 | 000000020025136 | 4485 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.1032% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 7475 | 0174379-IN | 2019-10-10 | 000000020025136 | 7475 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.172% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 14202.5 | 0174379-IN | 2019-10-10 | 000000020025136 | 14202.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.3269% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 17401.8 | 0174379-IN | 2019-10-10 | 000000020025136 | 17401.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9411101 | 0.4005% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Altos HS. Total computers: 1609 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173472-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9411101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Los Altos HS. Total cart: 1 | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-Technology | 5 | Technology | Los Altos HS | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-11-07 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 55913.91 | 0174574-IN | 2019-11-07 | 000000020035575 | 55913.91 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9411101 | 7.046% | Ergotron Zip40 Charging carts to store laptops at Los Altos HS. Total carts: 43 | Los Altos HS-5-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 8927.33 | 0173684-IN | 2019-10-10 | 000000020025135 | 8927.33 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9201101 | 0.2055% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 736.69 | 0173684-IN | 2019-10-10 | 000000020025135 | 736.69 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.01696% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 115 | 0173684-IN | 2019-10-10 | 000000020025135 | 115 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.002647% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 69 | 0173684-IN | 2019-10-10 | 000000020025135 | 69 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.001588% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 34.5 | 0173684-IN | 2019-10-10 | 000000020025135 | 34.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.0007941% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 218.5 | 0173684-IN | 2019-10-10 | 000000020025135 | 218.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.005029% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 267.72 | 0173684-IN | 2019-10-10 | 000000020025135 | 267.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.006162% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 23 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 95095.44 | 0175473-IN | 2019-10-22 | 000000020029495 | 95095.44 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9201101 | 3.39% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7847.35 | 0175473-IN | 2019-10-22 | 000000020029495 | 7847.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.2797% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 367.5 | 0175473-IN | 2019-10-22 | 000000020029495 | 367.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.0131% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 735 | 0175473-IN | 2019-10-22 | 000000020029495 | 735 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.0262% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1225 | 0175473-IN | 2019-10-22 | 000000020029495 | 1225 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.04366% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2327.5 | 0175473-IN | 2019-10-22 | 000000020029495 | 2327.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.08296% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2851.8 | 0175473-IN | 2019-10-22 | 000000020029495 | 2851.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9201101 | 0.1016% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Molinos. Total computers: 245 | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Technology | 4 | Technology | Los Molinos | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 28607.12 | 0175494-IN | 2019-10-22 | 000000020029495 | 28607.12 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9201101 | 3.605% | Ergotron Zip40 Charging carts to store laptops at Los Molinos. Total carts: 22 | Los Molinos-4-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4269.59 | 0173646-IN | 2019-10-10 | 000000020025135 | 4269.59 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9211101 | 0.09827% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 16.5 | 0173646-IN | 2019-10-10 | 000000020025135 | 16.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.0003798% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 128.04 | 0173646-IN | 2019-10-10 | 000000020025135 | 128.04 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.002947% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 104.5 | 0173646-IN | 2019-10-10 | 000000020025135 | 104.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.002405% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 55 | 0173646-IN | 2019-10-10 | 000000020025135 | 55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.001266% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 33 | 0173646-IN | 2019-10-10 | 000000020025135 | 33 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.0007595% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 352.33 | 0173646-IN | 2019-10-10 | 000000020025135 | 352.33 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.008109% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 11 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 50458.8 | 0175393-IN | 2019-10-22 | 000000020029495 | 50458.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9211101 | 1.799% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 4163.9 | 0175393-IN | 2019-10-22 | 000000020029495 | 4163.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.1484% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 195 | 0175393-IN | 2019-10-22 | 000000020029495 | 195 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.006951% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 390 | 0175393-IN | 2019-10-22 | 000000020029495 | 390 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.0139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 650 | 0175393-IN | 2019-10-22 | 000000020029495 | 650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.02317% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1235 | 0175393-IN | 2019-10-22 | 000000020029495 | 1235 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.04402% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1513.2 | 0175393-IN | 2019-10-22 | 000000020029495 | 1513.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9211101 | 0.05394% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Los Robles. Total computers: 130 | Los Robles-9-21st Century classroom
Los Robles-21st Century classroom-Technology | 9 | Technology | Los Robles | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 13003.22 | 0175400-IN | 2019-10-15 | 000000020026572 | 13003.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9211101 | 1.639% | Ergotron Zip40 Charging carts to store laptops at Los Robles. Total carts: 10 | Los Robles-9-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 17854.66 | 0173717-IN | 2019-10-10 | 000000020025135 | 17854.66 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9221101 | 0.411% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1473.38 | 0173717-IN | 2019-10-10 | 000000020025135 | 1473.38 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.03391% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 138 | 0173717-IN | 2019-10-10 | 000000020025135 | 138 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.003176% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 69 | 0173717-IN | 2019-10-10 | 000000020025135 | 69 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.001588% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 230 | 0173717-IN | 2019-10-10 | 000000020025135 | 230 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.005294% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 437 | 0173717-IN | 2019-10-10 | 000000020025135 | 437 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.01006% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 535.44 | 0173717-IN | 2019-10-10 | 000000020025135 | 535.44 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.01232% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 46 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 357093.08 | 0175413-IN | 2019-10-22 | 000000020029495 | 357093.08 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9221101 | 12.73% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 29467.6 | 0175413-IN | 2019-10-22 | 000000020029495 | 29467.6 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 1.05% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1380 | 0175413-IN | 2019-10-22 | 000000020029495 | 1380 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.04919% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2760 | 0175413-IN | 2019-10-22 | 000000020029495 | 2760 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.09838% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 4600 | 0175413-IN | 2019-10-22 | 000000020029495 | 4600 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.164% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 8740 | 0175413-IN | 2019-10-22 | 000000020029495 | 8740 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.3115% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 10708.8 | 0175413-IN | 2019-10-22 | 000000020029495 | 10708.8 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9221101 | 0.3817% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Mesa Robles. Total computers: 920 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 48111.97 | 0175412-IN | 2019-10-22 | 000000020029495 | 48111.97 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 6.063% | Ergotron Zip40 Charging carts to store laptops at Mesa Robles. Total carts: 37 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-12-02 | 2021-03-04 | 2020/21 |  | PO3W-210000001075 | 0 | 21084.19 | 0195589-IN | 2021-03-04 | 000000020169354 | 21084.19 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 15.32% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Mesa Robles. Total monitors: 38 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-12-02 | 2021-04-09 | 2020/21 | 21-3335 | PO3W-210000001075 | 0 | 61934.82 | 0196289-IN | 2021-04-09 | 000000020179111 | 61934.82 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 45% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Mesa Robles. Total monitors: 38 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | 3022.54 | 0193365-IN | 2021-01-22 | 000000020158901 | 3022.54 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 4.552% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Mesa Robles (4 year warranty). Total computers: 38 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-01-22 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | 37032.9 | 0193365-IN | 2021-01-22 | 000000020158901 | 37032.9 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 55.77% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Mesa Robles (4 year warranty). Total computers: 38 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2020-12-03 | 2021-03-04 | 2020/21 | 21-3355 | PO3W-210000001078 | 0 | -4.16 | 193365C-CM | 2021-03-04 | 000000020169354 | -4.16 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | -0.006265% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Mesa Robles (4 year warranty). Total computers: 38. Credit memo from vendor | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2021-06-14 | 2022-02-04 | 2021/22 | 21-6817 | PO3W-210000003053 | 0 | 10923.55 | 0205447-IN | 2022-02-04 | 000000020406994 | 10923.55 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 100% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Mesa Robles. Total monitors: 5 | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173629-IN | 2019-10-10 | 000000020025135 | 7798.34 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173629-IN | 2019-10-10 | 000000020025135 | 190 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173629-IN | 2019-10-10 | 000000020025135 | 100 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173629-IN | 2019-10-10 | 000000020025135 | 60 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173629-IN | 2019-10-10 | 000000020025135 | 30 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173629-IN | 2019-10-10 | 000000020025135 | 232.8 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173629-IN | 2019-10-10 | 000000020025135 | 640.6 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15596.67 | 0173777-IN | 2019-10-21 | 000000020028933 | 15596.67 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173777-IN | 2019-10-21 | 000000020028933 | 1281.2 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 200 | 0173777-IN | 2019-10-21 | 000000020028933 | 200 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173777-IN | 2019-10-21 | 000000020028933 | 120 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173777-IN | 2019-10-21 | 000000020028933 | 60 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 380 | 0173777-IN | 2019-10-21 | 000000020028933 | 380 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173777-IN | 2019-10-21 | 000000020028933 | 465.6 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 60 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 85781.75 | 0175468-IN | 2019-10-22 | 000000020029495 | 85781.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 3.058% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7046.6 | 0175468-IN | 2019-10-22 | 000000020029495 | 7046.6 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.2512% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 330 | 0175468-IN | 2019-10-22 | 000000020029495 | 330 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.01176% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 660 | 0175468-IN | 2019-10-22 | 000000020029495 | 660 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.02352% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1100 | 0175468-IN | 2019-10-22 | 000000020029495 | 1100 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.03921% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2090 | 0175468-IN | 2019-10-22 | 000000020029495 | 2090 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.0745% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2560.8 | 0175468-IN | 2019-10-22 | 000000020029495 | 2560.8 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9231101 | 0.09128% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Nelson. Total computers: 220 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000730 | 0 | 2612.53 | 0175485-IN | 2019-10-22 | 000000020029495 | 2612.53 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 0.3292% | Ergotron Zip40 Charging carts to store laptops at Nelson. Total carts: 18 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 20900.17 | 0175493-IN | 2019-10-22 | 000000020029495 | 20900.17 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 2.634% | Ergotron Zip40 Charging carts to store laptops at Nelson. Total carts: 18 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-06-05 | 2020-07-01 | 2019/20 | 2-10688 | PO3W-200000003014 | 0 | 2184.71 | 186220-IN | 2020-07-01 | 000000020109906 | 2184.71 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 100% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor - sample for Nelson room #C1. Total monitor: 1 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-09-16 | 2020/21 |  | PO3W-210000000003 | 0 | 60 | 0187656-IN | 2020-09-16 | 000000020127001 | 60 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 0.04814% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Nelson. Total monitors: 25 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-09-16 | 2020/21 |  | PO3W-210000000003 | 0 | 21886.59 | 0187656-IN | 2020-09-16 | 000000020127001 | 21886.59 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 17.56% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Nelson. Total monitors: 25 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 90 | 0189682-IN | 2020-10-01 | 000000020131103 | 90 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 0.07221% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Nelson. Total monitors: 25 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 32680.66 | 0189682-IN | 2020-10-01 | 000000020131103 | 32680.66 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 26.22% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Nelson. Total monitors: 25 | Nelson-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 13585.07 | 0173449-IN | 2019-10-10 | 000000020025135 | 13585.07 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9241101 | 0.3127% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 175 | 0173449-IN | 2019-10-10 | 000000020025135 | 175 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.004028% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 105 | 0173449-IN | 2019-10-10 | 000000020025135 | 105 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.002417% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 52.5 | 0173449-IN | 2019-10-10 | 000000020025135 | 52.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.001208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 332.5 | 0173449-IN | 2019-10-10 | 000000020025135 | 332.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.007653% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 407.4 | 0173449-IN | 2019-10-10 | 000000020025135 | 407.4 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.009377% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1121.05 | 0173449-IN | 2019-10-10 | 000000020025135 | 1121.05 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.0258% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10091.76 | 0173660-IN | 2019-10-10 | 000000020025135 | 10091.76 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9241101 | 0.2323% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 832.78 | 0173660-IN | 2019-10-10 | 000000020025135 | 832.78 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.01917% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 130 | 0173660-IN | 2019-10-10 | 000000020025135 | 130 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.002992% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 78 | 0173660-IN | 2019-10-10 | 000000020025135 | 78 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.001795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 39 | 0173660-IN | 2019-10-10 | 000000020025135 | 39 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.0008976% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 247 | 0173660-IN | 2019-10-10 | 000000020025135 | 247 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.005685% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 302.64 | 0173660-IN | 2019-10-10 | 000000020025135 | 302.64 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.006966% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 61 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 242590.4 | 0175374-IN | 2019-10-22 | 000000020029495 | 242590.4 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9241101 | 8.647% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 20018.75 | 0175374-IN | 2019-10-22 | 000000020029495 | 20018.75 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.7135% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 937.5 | 0175374-IN | 2019-10-22 | 000000020029495 | 937.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.03342% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1875 | 0175374-IN | 2019-10-22 | 000000020029495 | 1875 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.06683% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 3125 | 0175374-IN | 2019-10-22 | 000000020029495 | 3125 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.1114% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 5937.5 | 0175374-IN | 2019-10-22 | 000000020029495 | 5937.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.2116% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 7275 | 0175374-IN | 2019-10-22 | 000000020029495 | 7275 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9241101 | 0.2593% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Newton. Total computers: 625 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 |  | PO3W-200000000448 | 0 | 1300.32 | 0173474-IN | 2019-09-23 | 000000020017958 | 1300.32 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Newton. Total cart: 1 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-15 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 20805.18 | 0175378-IN | 2019-10-15 | 000000020026572 | 20805.18 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 2.622% | Ergotron Zip40 Charging carts to store laptops at Newton. Total carts: 16 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 42990.55 | 0221871-IN | 2023-01-26 | 000000020824366 | 42990.55 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 25.46% | ViewSonicViewBoard IFP7550 interactive flat panel - 75" Diagonal class LED-backlit LCD, adapter, ewaste, and extended service agreement for parts & labor for Newton. Total monitors: 20 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Web camera(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 1057.11 | 0221871-IN | 2023-01-26 | 000000020824366 | 1057.11 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 0.6261% | Viewsonic ViewCam VB-CAM-001 for Newton. Total web cams: 20 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 22162.19 | 0221901-IN | 2023-01-26 | 000000020824366 | 22162.19 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 13.13% | Desktop computers (Lenovo ThinkCentre M70q Gen 3 i7-12700T 16GB RAM 256GB SSD), 4 year warranty for Newton. Total computers: 20 | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Mounting bracket | 2023-03-31 | 2023-05-04 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 657 | 0226489-IN | 2023-05-04 | 000000020993482 | 657 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 13.84% | Lenovo ThinkCentre tiny sandwich kit II - system mounting bracket (20) for Newton | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Keyboard & mouse | 2023-03-31 | 2023-05-04 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 854.1 | 0226489-IN | 2023-05-04 | 000000020993482 | 854.1 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 17.99% | Lenovo essential wireless combo - keyboard & mouse set - wireless - 2.4 GHz - US (20) for Newton | Newton-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Arey Jones Educational Solutions | Power supply | 2023-03-31 | 2023-06-26 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 350.4 | 0228571-IN | 2023-06-26 | 000000021091332 | 350.4 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 7.382% | Lenovo tiny power cage II - Power supply cage (20) for Newton | Newton-1-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 13585.07 | 0173448-IN | 2019-10-10 | 000000020025135 | 13585.07 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9251101 | 0.3127% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 175 | 0173448-IN | 2019-10-10 | 000000020025135 | 175 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.004028% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 105 | 0173448-IN | 2019-10-10 | 000000020025135 | 105 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.002417% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 52.5 | 0173448-IN | 2019-10-10 | 000000020025135 | 52.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.001208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 332.5 | 0173448-IN | 2019-10-10 | 000000020025135 | 332.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.007653% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 407.4 | 0173448-IN | 2019-10-10 | 000000020025135 | 407.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.009377% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1121.05 | 0173448-IN | 2019-10-10 | 000000020025135 | 1121.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.0258% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 6986.6 | 0173634-IN | 2019-10-10 | 000000020025135 | 6986.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9251101 | 0.1608% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 209.52 | 0173634-IN | 2019-10-10 | 000000020025135 | 209.52 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.004822% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 171 | 0173634-IN | 2019-10-10 | 000000020025135 | 171 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.003936% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 90 | 0173634-IN | 2019-10-10 | 000000020025135 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 54 | 0173634-IN | 2019-10-10 | 000000020025135 | 54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.001243% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 27 | 0173634-IN | 2019-10-10 | 000000020025135 | 27 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.0006214% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 576.54 | 0173634-IN | 2019-10-10 | 000000020025135 | 576.54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.01327% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 130028.46 | 0174900-IN | 2019-10-10 | 000000020025136 | 130028.46 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9251101 | 2.993% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10730.05 | 0174900-IN | 2019-10-10 | 000000020025136 | 10730.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.247% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 502.5 | 0174900-IN | 2019-10-10 | 000000020025136 | 502.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.01157% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1005 | 0174900-IN | 2019-10-10 | 000000020025136 | 1005 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.02313% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1675 | 0174900-IN | 2019-10-10 | 000000020025136 | 1675 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.03855% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3182.5 | 0174900-IN | 2019-10-10 | 000000020025136 | 3182.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.07325% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3899.4 | 0174900-IN | 2019-10-10 | 000000020025136 | 3899.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.08975% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 388 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 15525.78 | 0175595-IN | 2019-10-22 | 000000020029495 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9251101 | 0.5534% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 60 | 0175595-IN | 2019-10-22 | 000000020029495 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.002139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 120 | 0175595-IN | 2019-10-22 | 000000020029495 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.004277% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 200 | 0175595-IN | 2019-10-22 | 000000020029495 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.007129% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 380 | 0175595-IN | 2019-10-22 | 000000020029495 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.01354% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 465.6 | 0175595-IN | 2019-10-22 | 000000020029495 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.0166% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1281.2 | 0175595-IN | 2019-10-22 | 000000020029495 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9251101 | 0.04567% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Orange Grove. Total computers: 40 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 |  | PO3W-200000000448 | 0 | 1300.32 | 0173479-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9251101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Orange Grove. Total carts: 2 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0175549-IN | 2019-10-22 | 000000020029495 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9251101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Orange Grove. Total carts: 2 | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Technology | 3 | Technology | Orange Grove | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 13003.23 | 0175002-IN | 2019-10-08 | 000000020023867 | 13003.23 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9251101 | 1.639% | Ergotron Zip40 Charging carts to store laptops at Orange Grove. Total carts: 10 | Orange Grove-3-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5822.17 | 0173644-IN | 2019-10-10 | 000000020025135 | 5822.17 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9261101 | 0.134% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 174.6 | 0173644-IN | 2019-10-10 | 000000020025135 | 174.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.004019% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 142.5 | 0173644-IN | 2019-10-10 | 000000020025135 | 142.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.00328% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 75 | 0173644-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 45 | 0173644-IN | 2019-10-10 | 000000020025135 | 45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 22.5 | 0173644-IN | 2019-10-10 | 000000020025135 | 22.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.0005179% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 480.45 | 0173644-IN | 2019-10-10 | 000000020025135 | 480.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.01106% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 7762.89 | 0173803-IN | 2019-10-10 | 000000020025135 | 7762.89 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9261101 | 0.1787% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173803-IN | 2019-10-10 | 000000020025135 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173803-IN | 2019-10-10 | 000000020025135 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173803-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173803-IN | 2019-10-10 | 000000020025135 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173803-IN | 2019-10-10 | 000000020025135 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173803-IN | 2019-10-10 | 000000020025135 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 67925.32 | 0174011-IN | 2019-10-10 | 000000020025135 | 67925.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9261101 | 1.563% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 5605.25 | 0174011-IN | 2019-10-10 | 000000020025135 | 5605.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.129% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 262.5 | 0174011-IN | 2019-10-10 | 000000020025135 | 262.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.006042% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 525 | 0174011-IN | 2019-10-10 | 000000020025135 | 525 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.01208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 875 | 0174011-IN | 2019-10-10 | 000000020025135 | 875 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.02014% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1662.5 | 0174011-IN | 2019-10-10 | 000000020025135 | 1662.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.03827% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2037 | 0174011-IN | 2019-10-10 | 000000020025135 | 2037 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9261101 | 0.04688% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm. Total computers: 210 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 |  | PO3W-200000000448 | 0 | 1300.32 | 0174081-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9261101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Palm. Total carts: 7 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 7801.94 | 0174092-IN | 2019-09-23 | 000000020017958 | 7801.94 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9261101 | 8.561% | Ergotron Zip40 Charging carts to store laptops at Palm. Total carts: 7 | Palm-6-21st Century classroom
Palm-21st Century classroom-Technology | 6 | Technology | Palm | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 9102.26 | 0175150-IN | 2019-10-08 | 000000020023867 | 9102.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9261101 | 1.147% | Ergotron Zip40 Charging carts to store laptops at Palm. Total carts: 7 | Palm-6-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 1164.44 | 0173685-IN | 2019-10-10 | 000000020025135 | 1164.44 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 8031101 | 0.0268% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 4.5 | 0173685-IN | 2019-10-10 | 000000020025135 | 4.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.0001036% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 96.09 | 0173685-IN | 2019-10-10 | 000000020025135 | 96.09 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.002212% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 34.92 | 0173685-IN | 2019-10-10 | 000000020025135 | 34.92 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.0008037% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 28.5 | 0173685-IN | 2019-10-10 | 000000020025135 | 28.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.000656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15 | 0173685-IN | 2019-10-10 | 000000020025135 | 15 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.0003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 9 | 0173685-IN | 2019-10-10 | 000000020025135 | 9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.0002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 3 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7762.89 | 0175575-IN | 2019-10-22 | 000000020029495 | 7762.89 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 8031101 | 0.2767% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 30 | 0175575-IN | 2019-10-22 | 000000020029495 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.001069% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 190 | 0175575-IN | 2019-10-22 | 000000020029495 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.006772% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 232.8 | 0175575-IN | 2019-10-22 | 000000020029495 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.008298% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 640.6 | 0175575-IN | 2019-10-22 | 000000020029495 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.02283% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 100 | 0175575-IN | 2019-10-22 | 000000020029495 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.003564% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20 | Palm Canyon-0-21st Century classroom
Palm Canyon-21st Century classroom-Technology | 0 | Technology | Palm Canyon | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 60 | 0175575-IN | 2019-10-22 | 000000020029495 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8031101 | 0.002139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Palm Canyon. Total computers: 20 | Palm Canyon-0-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 6628.58 | 0173677-IN | 2019-10-10 | 000000020025135 | 6628.58 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9281101 | 0.1526% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 197.88 | 0173677-IN | 2019-10-10 | 000000020025135 | 197.88 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.004555% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 161.5 | 0173677-IN | 2019-10-10 | 000000020025135 | 161.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.003717% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 85 | 0173677-IN | 2019-10-10 | 000000020025135 | 85 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.001956% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 51 | 0173677-IN | 2019-10-10 | 000000020025135 | 51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.001174% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 25.5 | 0173677-IN | 2019-10-10 | 000000020025135 | 25.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.0005869% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 544.51 | 0173677-IN | 2019-10-10 | 000000020025135 | 544.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.01253% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 130622.2 | 0174861-IN | 2019-10-10 | 000000020025135 | 130622.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9281101 | 3.006% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 10730.05 | 0174861-IN | 2019-10-10 | 000000020025135 | 10730.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.247% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 502.5 | 0174861-IN | 2019-10-10 | 000000020025135 | 502.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.01157% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1005 | 0174861-IN | 2019-10-10 | 000000020025135 | 1005 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.02313% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1675 | 0174861-IN | 2019-10-10 | 000000020025135 | 1675 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.03855% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3182.5 | 0174861-IN | 2019-10-10 | 000000020025135 | 3182.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.07325% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3899.4 | 0174861-IN | 2019-10-10 | 000000020025135 | 3899.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9281101 | 0.08975% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sierra Vista. Total computers: 352 | Sierra Vista-8-21st Century classroom
Sierra Vista-21st Century classroom-Technology | 8 | Technology | Sierra Vista | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 11756.35 | 0174873-IN | 2019-10-08 | 000000020023867 | 11756.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9281101 | 1.482% | Ergotron Zip40 Charging carts to store laptops at Sierra Vista. Total carts: 9 | Sierra Vista-8-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7408.42 | 0173642-IN | 2019-10-08 | 000000020023867 | 7408.42 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9291101 | 0.1705% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 608.57 | 0173642-IN | 2019-10-08 | 000000020023867 | 608.57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.01401% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 180.5 | 0173642-IN | 2019-10-08 | 000000020023867 | 180.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.004155% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 95 | 0173642-IN | 2019-10-08 | 000000020023867 | 95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 57 | 0173642-IN | 2019-10-08 | 000000020023867 | 57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.001312% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 28.5 | 0173642-IN | 2019-10-08 | 000000020023867 | 28.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.000656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 221.16 | 0173642-IN | 2019-10-08 | 000000020023867 | 221.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.00509% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173778-IN | 2019-10-21 | 000000020028933 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9291101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173778-IN | 2019-10-21 | 000000020028933 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173778-IN | 2019-10-21 | 000000020028933 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173778-IN | 2019-10-21 | 000000020028933 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173778-IN | 2019-10-21 | 000000020028933 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173778-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173778-IN | 2019-10-21 | 000000020028933 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 39 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 113075.93 | 0175197-IN | 2019-10-22 | 000000020029495 | 113075.93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9291101 | 4.03% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 9288.7 | 0175197-IN | 2019-10-22 | 000000020029495 | 9288.7 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.3311% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 435 | 0175197-IN | 2019-10-22 | 000000020029495 | 435 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.0155% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 870 | 0175197-IN | 2019-10-22 | 000000020029495 | 870 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.03101% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1450 | 0175197-IN | 2019-10-22 | 000000020029495 | 1450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.05168% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2755 | 0175197-IN | 2019-10-22 | 000000020029495 | 2755 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.0982% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 3375.6 | 0175197-IN | 2019-10-22 | 000000020029495 | 3375.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9291101 | 0.1203% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks ES. Total computers: 290 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 |  | PO3W-200000000730 | 0 | 22206.44 | 0175271-IN | 2019-10-11 | 000000020025716 | 22206.44 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9291101 | 2.798% | Ergotron Zip40 Charging carts to store laptops at Sparks ES. Total carts: 18 | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Technology | 7 | Technology | Sparks ES | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175272-IN | 2019-10-11 | 000000020025716 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9291101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Sparks ES. Total carts: 18 | Sparks ES-7-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173640-IN | 2019-10-08 | 000000020023867 | 7798.34 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9301101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173640-IN | 2019-10-08 | 000000020023867 | 640.6 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173640-IN | 2019-10-08 | 000000020023867 | 190 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173640-IN | 2019-10-08 | 000000020023867 | 100 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173640-IN | 2019-10-08 | 000000020023867 | 60 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173640-IN | 2019-10-08 | 000000020023867 | 30 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173640-IN | 2019-10-08 | 000000020023867 | 232.8 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 220303.11 | 0174877-IN | 2019-10-10 | 000000020025135 | 220303.11 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9301101 | 5.071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 18096.95 | 0174877-IN | 2019-10-10 | 000000020025135 | 18096.95 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.4165% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 847.5 | 0174877-IN | 2019-10-10 | 000000020025135 | 847.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.01951% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1695 | 0174877-IN | 2019-10-10 | 000000020025135 | 1695 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.03901% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2825 | 0174877-IN | 2019-10-10 | 000000020025135 | 2825 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.06502% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5367.5 | 0174877-IN | 2019-10-10 | 000000020025135 | 5367.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.1235% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 6576.6 | 0174877-IN | 2019-10-10 | 000000020025135 | 6576.6 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9301101 | 0.1514% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sparks MS. Total computers: 20 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-04 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 18287.65 | 0174911-IN | 2019-10-04 | 000000020022961 | 18287.65 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 2.305% | Ergotron Zip40 Charging carts to store laptops at Sparks MS. Total carts: 14 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 25794.32 | 0221871-IN | 2023-01-26 | 000000020824366 | 25794.32 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 15.28% | ViewSonicViewBoard IFP7550 interactive flat panel - 75" Diagonal class LED-backlit LCD, adapter, ewaste, and extended service agreement for parts & labor for Sparks MS. Total monitors: 12 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Web camera(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 634.26 | 0221871-IN | 2023-01-26 | 000000020824366 | 634.26 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 0.3757% | Viewsonic ViewCam VB-CAM-001 for Sparks MS. Total web cams: 12 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Desktop computer(s) | 2022-11-18 | 2023-01-26 | 2022/23 | 23-4055 | PO3W-230000001319 | 0 | 13297.32 | 0221901-IN | 2023-01-26 | 000000020824366 | 13297.32 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 7.876% | Desktop computers (Lenovo ThinkCentre M70q Gen 3 i7-12700T 16GB RAM 256GB SSD), 4 year warranty for Sparks MS. Total computers: 12 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Mounting bracket | 2023-03-31 | 2023-05-04 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 394.2 | 0226489-IN | 2023-05-04 | 000000020993482 | 394.2 | 03-121296 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9301101 | 8.304% | Lenovo ThinkCentre tiny sandwich kit II - system mounting bracket (12) for Sparks MS | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Keyboard & mouse | 2023-03-31 | 2023-05-04 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 512.46 | 0226489-IN | 2023-05-04 | 000000020993482 | 512.46 | 03-121296 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9301101 | 10.8% | Lenovo essential wireless combo - keyboard & mouse set - wireless - 2.4 GHz - US (12) for Sparks MS | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Arey Jones Educational Solutions | Power supply | 2023-03-31 | 2023-06-26 | 2022/23 | 23-7403 | PO3W-230000002778 | 0 | 210.24 | 0228571-IN | 2023-06-26 | 000000021091332 | 210.24 | 03-121296 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9301101 | 4.429% | Lenovo tiny power cage II - Power supply cage (12) for Sparks MS | Sparks MS-2-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 2328.86 | 0173715-IN | 2019-10-10 | 000000020025135 | 2328.86 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 8021101 | 0.0536% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 9 | 0173715-IN | 2019-10-10 | 000000020025135 | 9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.0002071% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 192.18 | 0173715-IN | 2019-10-10 | 000000020025135 | 192.18 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.004423% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 69.84 | 0173715-IN | 2019-10-10 | 000000020025135 | 69.84 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.001607% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 57 | 0173715-IN | 2019-10-10 | 000000020025135 | 57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.001312% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173715-IN | 2019-10-10 | 000000020025135 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 18 | 0173715-IN | 2019-10-10 | 000000020025135 | 18 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.0004143% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 6 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 15525.78 | 0175429-IN | 2019-10-22 | 000000020029495 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 8021101 | 0.5534% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 60 | 0175429-IN | 2019-10-22 | 000000020029495 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.002139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 120 | 0175429-IN | 2019-10-22 | 000000020029495 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.004277% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 200 | 0175429-IN | 2019-10-22 | 000000020029495 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.007129% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 380 | 0175429-IN | 2019-10-22 | 000000020029495 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.01354% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 465.6 | 0175429-IN | 2019-10-22 | 000000020029495 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.0166% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40 | Stimson-4-21st Century classroom
Stimson-21st Century classroom-Technology | 4 | Technology | Stimson | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1281.2 | 0175429-IN | 2019-10-22 | 000000020029495 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 8021101 | 0.04567% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Stimson. Total computers: 40 | Stimson-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 5068.92 | 0173628-IN | 2019-10-10 | 000000020025135 | 5068.92 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9311101 | 0.1167% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 151.32 | 0173628-IN | 2019-10-10 | 000000020025135 | 151.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.003483% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 123.5 | 0173628-IN | 2019-10-10 | 000000020025135 | 123.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.002843% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 65 | 0173628-IN | 2019-10-10 | 000000020025135 | 65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.001496% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 39 | 0173628-IN | 2019-10-10 | 000000020025135 | 39 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.0008976% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 19.5 | 0173628-IN | 2019-10-10 | 000000020025135 | 19.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.0004488% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 416.39 | 0173628-IN | 2019-10-10 | 000000020025135 | 416.39 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.009584% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173780-IN | 2019-11-12 | 000000020036764 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9311101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173780-IN | 2019-11-12 | 000000020036764 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173780-IN | 2019-11-12 | 000000020036764 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173780-IN | 2019-11-12 | 000000020036764 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173780-IN | 2019-11-12 | 000000020036764 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173780-IN | 2019-11-12 | 000000020036764 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-11-12 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173780-IN | 2019-11-12 | 000000020036764 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 33 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-12-06 | 2019/20 | 2-5090 | PO2W-200000002766 | 0 | 1306.26 | 0175960-IN | 2019-12-06 | 000000020045865 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9311101 | 100% | Ergotron Zip40 Charging carts to store laptops at Sunset. Total cart: 1 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 70185.04 | 0175621-IN | 2019-10-22 | 000000020029495 | 70185.04 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9311101 | 2.502% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5765.4 | 0175621-IN | 2019-10-22 | 000000020029495 | 5765.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.2055% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 270 | 0175621-IN | 2019-10-22 | 000000020029495 | 270 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.009624% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 540 | 0175621-IN | 2019-10-22 | 000000020029495 | 540 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.01925% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 900 | 0175621-IN | 2019-10-22 | 000000020029495 | 900 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.03208% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1710 | 0175621-IN | 2019-10-22 | 000000020029495 | 1710 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.06095% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2095.2 | 0175621-IN | 2019-10-22 | 000000020029495 | 2095.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9311101 | 0.07468% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Sunset. Total computers: 180 | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Technology | 4 | Technology | Sunset | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-22 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 10450.09 | 0175658-IN | 2019-10-22 | 000000020029495 | 10450.09 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9311101 | 1.317% | Ergotron Zip40 Charging carts to store laptops at Sunset. Total carts: 8 | Sunset-4-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6238.67 | 0173635-IN | 2019-10-08 | 000000020023867 | 6238.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 0.1436% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 512.48 | 0173635-IN | 2019-10-08 | 000000020023867 | 512.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.0118% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 186.24 | 0173635-IN | 2019-10-08 | 000000020023867 | 186.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.004287% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 152 | 0173635-IN | 2019-10-08 | 000000020023867 | 152 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.003499% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 80 | 0173635-IN | 2019-10-08 | 000000020023867 | 80 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.001841% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 48 | 0173635-IN | 2019-10-08 | 000000020023867 | 48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.001105% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 24 | 0173635-IN | 2019-10-08 | 000000020023867 | 24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.0005524% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173776-IN | 2019-10-21 | 000000020028933 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173776-IN | 2019-10-21 | 000000020028933 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173776-IN | 2019-10-21 | 000000020028933 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173776-IN | 2019-10-21 | 000000020028933 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173776-IN | 2019-10-21 | 000000020028933 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173776-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173776-IN | 2019-10-21 | 000000020028933 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 36 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 58487.55 | 0175196-IN | 2019-10-22 | 000000020029495 | 58487.55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 2.085% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 225 | 0175196-IN | 2019-10-22 | 000000020029495 | 225 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.00802% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 450 | 0175196-IN | 2019-10-22 | 000000020029495 | 450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.01604% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 750 | 0175196-IN | 2019-10-22 | 000000020029495 | 750 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.02673% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1425 | 0175196-IN | 2019-10-22 | 000000020029495 | 1425 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.05079% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1746 | 0175196-IN | 2019-10-22 | 000000020029495 | 1746 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.06223% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 4804.5 | 0175196-IN | 2019-10-22 | 000000020029495 | 4804.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.1712% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 7798.34 | 0175594-IN | 2019-10-22 | 000000020029495 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 0.278% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 30 | 0175594-IN | 2019-10-22 | 000000020029495 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.001069% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 100 | 0175594-IN | 2019-10-22 | 000000020029495 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.003564% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 190 | 0175594-IN | 2019-10-22 | 000000020029495 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.006772% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 232.8 | 0175594-IN | 2019-10-22 | 000000020029495 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.008298% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 640.6 | 0175594-IN | 2019-10-22 | 000000020029495 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.02283% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 60 | 0175594-IN | 2019-10-22 | 000000020029495 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9331101 | 0.002139% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Temple. Total computers: 170 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 |  | PO3W-200000000730 | 0 | 16981.39 | 0175274-IN | 2019-10-11 | 000000020025716 | 16981.39 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9331101 | 2.14% | Ergotron Zip40 Charging carts to store laptops at Temple. Total carts: 14 | Temple-8-21st Century classroom
Temple-21st Century classroom-Technology | 8 | Technology | Temple | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175278-IN | 2019-10-11 | 000000020025716 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9331101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Temple. Total carts: 14 | Temple-8-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15596.68 | 0173466-IN | 2019-10-08 | 000000020023867 | 15596.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 0.359% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173466-IN | 2019-10-08 | 000000020023867 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 200 | 0173466-IN | 2019-10-08 | 000000020023867 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173466-IN | 2019-10-08 | 000000020023867 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173466-IN | 2019-10-08 | 000000020023867 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 380 | 0173466-IN | 2019-10-08 | 000000020023867 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173466-IN | 2019-10-08 | 000000020023867 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 12087.43 | 0173675-IN | 2019-10-08 | 000000020023867 | 12087.43 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 0.2782% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 992.93 | 0173675-IN | 2019-10-08 | 000000020023867 | 992.93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.02285% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 155 | 0173675-IN | 2019-10-08 | 000000020023867 | 155 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.003568% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 93 | 0173675-IN | 2019-10-08 | 000000020023867 | 93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.002141% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 46.5 | 0173675-IN | 2019-10-08 | 000000020023867 | 46.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.00107% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 294.5 | 0173675-IN | 2019-10-08 | 000000020023867 | 294.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.006778% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 360.84 | 0173675-IN | 2019-10-08 | 000000020023867 | 360.84 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.008305% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173760-IN | 2019-10-21 | 000000020028933 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173760-IN | 2019-10-21 | 000000020028933 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173760-IN | 2019-10-21 | 000000020028933 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173760-IN | 2019-10-21 | 000000020028933 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173760-IN | 2019-10-21 | 000000020028933 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173760-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173760-IN | 2019-10-21 | 000000020028933 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 91 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 159865.97 | 0175193-IN | 2019-10-22 | 000000020029495 | 159865.97 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 5.698% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 13132.3 | 0175193-IN | 2019-10-22 | 000000020029495 | 13132.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.4681% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 615 | 0175193-IN | 2019-10-22 | 000000020029495 | 615 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.02192% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1230 | 0175193-IN | 2019-10-22 | 000000020029495 | 1230 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.04384% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 2050 | 0175193-IN | 2019-10-22 | 000000020029495 | 2050 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.07307% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 3895 | 0175193-IN | 2019-10-22 | 000000020029495 | 3895 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.1388% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 4772.4 | 0175193-IN | 2019-10-22 | 000000020029495 | 4772.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9341101 | 0.1701% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valinda. Total computers: 410 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1300.32 | 0173478-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Valinda. Total cart: 1 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 |  | PO3W-200000000730 | 0 | 1306.26 | 0175126-IN | 2019-10-11 | 000000020025716 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Valinda. Total carts: 26 | Valinda-6-21st Century classroom
Valinda-21st Century classroom-Technology | 6 | Technology | Valinda | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-11 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 32656.53 | 0175203-IN | 2019-10-11 | 000000020025716 | 32656.53 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 4.115% | Ergotron Zip40 Charging carts to store laptops at Valinda. Total carts: 26 | Valinda-6-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 6210.31 | 0173686-IN | 2019-10-10 | 000000020025135 | 6210.31 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9441101 | 0.1429% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 512.48 | 0173686-IN | 2019-10-10 | 000000020025135 | 512.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.0118% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 186.24 | 0173686-IN | 2019-10-10 | 000000020025135 | 186.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.004287% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 152 | 0173686-IN | 2019-10-10 | 000000020025135 | 152 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.003499% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 80 | 0173686-IN | 2019-10-10 | 000000020025135 | 80 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.001841% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 48 | 0173686-IN | 2019-10-10 | 000000020025135 | 48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.001105% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 24 | 0173686-IN | 2019-10-10 | 000000020025135 | 24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.0005524% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 16 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 62103.14 | 0175627-IN | 2019-10-22 | 000000020029495 | 62103.14 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9441101 | 2.214% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5124.8 | 0175627-IN | 2019-10-22 | 000000020029495 | 5124.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.1827% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 240 | 0175627-IN | 2019-10-22 | 000000020029495 | 240 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.008554% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 480 | 0175627-IN | 2019-10-22 | 000000020029495 | 480 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.01711% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 800 | 0175627-IN | 2019-10-22 | 000000020029495 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.02851% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1520 | 0175627-IN | 2019-10-22 | 000000020029495 | 1520 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.05418% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-22 | 2019/20 |  | PO3W-200000000332 | 0 | 1862.4 | 0175627-IN | 2019-10-22 | 000000020029495 | 1862.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9441101 | 0.06638% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Valley. Total computers: 1609 | Valley-8-21st Century classroom
Valley-21st Century classroom-Technology | 8 | Technology | Valley | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-21 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 7801.94 | 0175663-IN | 2019-10-21 | 000000020028933 | 7801.94 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9441101 | 0.9832% | Ergotron Zip40 Charging carts to store laptops at Valley. Total carts: 6 | Valley-8-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 9703.62 | 0173714-IN | 2019-10-10 | 000000020025135 | 9703.62 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9351101 | 0.2233% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 125 | 0173714-IN | 2019-10-10 | 000000020025135 | 125 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.002877% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 75 | 0173714-IN | 2019-10-10 | 000000020025135 | 75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 37.5 | 0173714-IN | 2019-10-10 | 000000020025135 | 37.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.0008631% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 237.5 | 0173714-IN | 2019-10-10 | 000000020025135 | 237.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.005466% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 291 | 0173714-IN | 2019-10-10 | 000000020025135 | 291 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.006698% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 800.75 | 0173714-IN | 2019-10-10 | 000000020025135 | 800.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.01843% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 89273.27 | 0174906-IN | 2019-10-10 | 000000020025136 | 89273.27 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9351101 | 2.055% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7366.9 | 0174906-IN | 2019-10-10 | 000000020025136 | 7366.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.1696% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 345 | 0174906-IN | 2019-10-10 | 000000020025136 | 345 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.007941% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 690 | 0174906-IN | 2019-10-10 | 000000020025136 | 690 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.01588% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1150 | 0174906-IN | 2019-10-10 | 000000020025136 | 1150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.02647% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2185 | 0174906-IN | 2019-10-10 | 000000020025136 | 2185 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.05029% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2677.2 | 0174906-IN | 2019-10-10 | 000000020025136 | 2677.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9351101 | 0.06162% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery at Wedgeworth. Total computers: 255 | Wedgeworth-0-21st Century classroom
Wedgeworth-21st Century classroom-Technology | 0 | Technology | Wedgeworth | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 31207.76 | 0175048-IN | 2019-10-08 | 000000020023867 | 31207.76 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9351101 | 3.933% | Ergotron Zip40 Charging carts to store laptops at Wedgeworth. Total carts: 24 | Wedgeworth-0-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 22124.25 | 0173713-IN | 2019-10-10 | 000000020025135 | 22124.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9421101 | 0.5092% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 171 | 0173713-IN | 2019-10-10 | 000000020025135 | 171 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.003936% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 85.5 | 0173713-IN | 2019-10-10 | 000000020025135 | 85.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.001968% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 285 | 0173713-IN | 2019-10-10 | 000000020025135 | 285 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.00656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 541.5 | 0173713-IN | 2019-10-10 | 000000020025135 | 541.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.01246% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 663.48 | 0173713-IN | 2019-10-10 | 000000020025135 | 663.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.01527% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1825.71 | 0173713-IN | 2019-10-10 | 000000020025135 | 1825.71 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.04202% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 506528.77 | 0174691-IN | 2019-10-10 | 000000020025135 | 506528.77 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9421101 | 11.66% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1957.5 | 0174691-IN | 2019-10-10 | 000000020025135 | 1957.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.04506% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3915 | 0174691-IN | 2019-10-10 | 000000020025135 | 3915 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.09011% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 6525 | 0174691-IN | 2019-10-10 | 000000020025135 | 6525 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.1502% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 12397.5 | 0174691-IN | 2019-10-10 | 000000020025135 | 12397.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.2853% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15190.2 | 0174691-IN | 2019-10-10 | 000000020025135 | 15190.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.3496% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 41799.15 | 0174691-IN | 2019-10-10 | 000000020025135 | 41799.15 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.9621% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 3881.45 | 0173890-IN | 2019-10-21 | 000000020028933 | 3881.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9421101 | 0.08934% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 320.3 | 0173890-IN | 2019-10-21 | 000000020028933 | 320.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.007372% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 116.4 | 0173890-IN | 2019-10-21 | 000000020028933 | 116.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.002679% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 95 | 0173890-IN | 2019-10-21 | 000000020028933 | 95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 50 | 0173890-IN | 2019-10-21 | 000000020028933 | 50 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.001151% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173890-IN | 2019-10-21 | 000000020028933 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-21 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15 | 0173890-IN | 2019-10-21 | 000000020028933 | 15 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9421101 | 0.0003452% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wilson HS. Total computers: 1372 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Technology | 5 | Technology | Wilson HS | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 53313.26 | 0174830-IN | 2019-10-08 | 000000020023867 | 53313.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9421101 | 6.719% | Ergotron Zip40 Charging carts to store laptops at Wilson HS. Total carts: 41 | Wilson HS-5-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 6238.67 | 0173676-IN | 2019-10-08 | 000000020023867 | 6238.67 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9371101 | 0.1436% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 186.24 | 0173676-IN | 2019-10-08 | 000000020023867 | 186.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.004287% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 152 | 0173676-IN | 2019-10-08 | 000000020023867 | 152 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.003499% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 80 | 0173676-IN | 2019-10-08 | 000000020023867 | 80 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.001841% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 48 | 0173676-IN | 2019-10-08 | 000000020023867 | 48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.001105% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 24 | 0173676-IN | 2019-10-08 | 000000020023867 | 24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.0005524% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 512.48 | 0173676-IN | 2019-10-08 | 000000020023867 | 512.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.0118% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173772-IN | 2019-10-08 | 000000020023867 | 7798.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9371101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173772-IN | 2019-10-08 | 000000020023867 | 640.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173772-IN | 2019-10-08 | 000000020023867 | 190 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173772-IN | 2019-10-08 | 000000020023867 | 100 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173772-IN | 2019-10-08 | 000000020023867 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173772-IN | 2019-10-08 | 000000020023867 | 30 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173772-IN | 2019-10-08 | 000000020023867 | 232.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 16 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 64336.31 | 0175131-IN | 2019-10-10 | 000000020025132 | 64336.31 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9371101 | 2.293% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 495 | 0175131-IN | 2019-10-10 | 000000020025132 | 495 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.01764% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 247.5 | 0175131-IN | 2019-10-10 | 000000020025132 | 247.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.008822% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 825 | 0175131-IN | 2019-10-10 | 000000020025132 | 825 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.02941% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 1567.5 | 0175131-IN | 2019-10-10 | 000000020025132 | 1567.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.05587% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 1920.6 | 0175131-IN | 2019-10-10 | 000000020025132 | 1920.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.06846% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 5284.95 | 0175131-IN | 2019-10-10 | 000000020025132 | 5284.95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9371101 | 0.1884% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Wing Lane. Total computers: 165 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-04 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 1306.26 | 0175122-IN | 2019-10-04 | 000000020022961 | 1306.26 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9371101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Wing Lane. Total carts: 15 | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-Technology | 9 | Technology | Wing Lane | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-04 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 18287.65 | 0175143-IN | 2019-10-04 | 000000020022961 | 18287.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9371101 | 2.305% | Ergotron Zip40 Charging carts to store laptops at Wing Lane. Total carts: 15 | Wing Lane-9-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 9747.93 | 0173465-IN | 2019-10-10 | 000000020025135 | 9747.93 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 0.2244% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 125 | 0173465-IN | 2019-10-10 | 000000020025135 | 125 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.002877% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 75 | 0173465-IN | 2019-10-10 | 000000020025135 | 75 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.001726% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 37.5 | 0173465-IN | 2019-10-10 | 000000020025135 | 37.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.0008631% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 237.5 | 0173465-IN | 2019-10-10 | 000000020025135 | 237.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.005466% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 291 | 0173465-IN | 2019-10-10 | 000000020025135 | 291 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.006698% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 800.75 | 0173465-IN | 2019-10-10 | 000000020025135 | 800.75 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.01843% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 7408.42 | 0173631-IN | 2019-10-10 | 000000020025135 | 7408.42 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 0.1705% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 180.5 | 0173631-IN | 2019-10-10 | 000000020025135 | 180.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.004155% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 95 | 0173631-IN | 2019-10-10 | 000000020025135 | 95 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.002187% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 57 | 0173631-IN | 2019-10-10 | 000000020025135 | 57 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.001312% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 28.5 | 0173631-IN | 2019-10-10 | 000000020025135 | 28.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.000656% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 221.16 | 0173631-IN | 2019-10-10 | 000000020025135 | 221.16 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.00509% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 608.57 | 0173631-IN | 2019-10-10 | 000000020025135 | 608.57 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.01401% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 7798.34 | 0173774-IN | 2019-10-10 | 000000020025135 | 7798.34 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 0.1795% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 640.6 | 0173774-IN | 2019-10-10 | 000000020025135 | 640.6 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.01474% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 190 | 0173774-IN | 2019-10-10 | 000000020025135 | 190 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.004373% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 100 | 0173774-IN | 2019-10-10 | 000000020025135 | 100 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.002302% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173774-IN | 2019-10-10 | 000000020025135 | 60 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 30 | 0173774-IN | 2019-10-10 | 000000020025135 | 30 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.0006905% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 232.8 | 0173774-IN | 2019-10-10 | 000000020025135 | 232.8 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.005358% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 64 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 62386.72 | 0175132-IN | 2019-10-10 | 000000020025132 | 62386.72 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 2.224% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-1409 | PO3W-200000000332 | 0 | 5124.8 | 0175132-IN | 2019-10-10 | 000000020025132 | 5124.8 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.1827% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 240 | 0175132-IN | 2019-10-10 | 000000020025132 | 240 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.008554% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 480 | 0175132-IN | 2019-10-10 | 000000020025132 | 480 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.01711% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 800 | 0175132-IN | 2019-10-10 | 000000020025132 | 800 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.02851% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 1520 | 0175132-IN | 2019-10-10 | 000000020025132 | 1520 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.05418% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO3W-200000000332 | 0 | 1862.4 | 0175132-IN | 2019-10-10 | 000000020025132 | 1862.4 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9381101 | 0.06638% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman ES. Total computers: 160 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-1980 | PO3W-200000000448 | 0 | 1306.26 | 0173477-IN | 2019-09-23 | 000000020017958 | 1306.26 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 1.433% | Ergotron Zip40 Charging carts to store laptops at Workman ES. Total cart: 1 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 |  | PO3W-200000000730 | 0 | 1306.26 | 0175123-IN | 2019-10-08 | 000000020023867 | 1306.26 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 0.1646% | Ergotron Zip40 Charging carts to store laptops at Workman ES. Total carts: 17 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-10-08 | 2019/20 | 2-2605 | PO3W-200000000730 | 0 | 20900.18 | 0175133-IN | 2019-10-08 | 000000020023867 | 20900.18 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 2.634% | Ergotron Zip40 Charging carts to store laptops at Workman ES. Total carts: 17 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 72 | 0189682-IN | 2020-10-01 | 000000020131103 | 72 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 0.05777% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Workman ES. Total monitors: 12 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2020-07-01 | 2020-10-01 | 2020/21 | 21-129 | PO3W-210000000003 | 0 | 26144.53 | 0189682-IN | 2020-10-01 | 000000020131103 | 26144.53 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 20.98% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Workman ES. Total monitors: 12 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Arey Jones Educational Solutions | ViewSonic monitor(s) | 2021-06-14 | 2022-02-11 | 2021/22 | 21-6818 | PO3W-210000003054 | 0 | 15362.62 | 0205446-IN | 2022-02-11 | 000000020412893 | 15362.62 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 100% | ViewSonicViewBoard IFP7550 Bundle 7 yr warranty, monitor, 75" class LED display with touchscreen, ewaste, and extended service agreement for parts & labor for Workman ES. Total monitors: 7 | Workman ES-2-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 15525.78 | 0173366-IN | 2019-10-10 | 000000020025135 | 15525.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9431101 | 0.3574% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 200 | 0173366-IN | 2019-10-10 | 000000020025135 | 200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.004603% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 120 | 0173366-IN | 2019-10-10 | 000000020025135 | 120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.002762% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 60 | 0173366-IN | 2019-10-10 | 000000020025135 | 60 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.001381% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 380 | 0173366-IN | 2019-10-10 | 000000020025135 | 380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.008746% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 465.6 | 0173366-IN | 2019-10-10 | 000000020025135 | 465.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.01072% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1281.2 | 0173366-IN | 2019-10-10 | 000000020025135 | 1281.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.02949% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 19795.37 | 0173630-IN | 2019-10-10 | 000000020025135 | 19795.37 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9431101 | 0.4556% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 153 | 0173630-IN | 2019-10-10 | 000000020025135 | 153 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.003522% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 76.5 | 0173630-IN | 2019-10-10 | 000000020025135 | 76.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.001761% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 255 | 0173630-IN | 2019-10-10 | 000000020025135 | 255 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.005869% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 484.5 | 0173630-IN | 2019-10-10 | 000000020025135 | 484.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.01115% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 593.64 | 0173630-IN | 2019-10-10 | 000000020025135 | 593.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.01366% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1633.53 | 0173630-IN | 2019-10-10 | 000000020025135 | 1633.53 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.0376% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-512 | PO2W-200000000689, 19-109955 | 0 | 359033.8 | 0174233-IN | 2019-10-10 | 000000020025135 | 359033.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9431101 | 8.264% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 | 2-514 | PO2W-200000000689, 19-109955 | 0 | 29627.75 | 0174233-IN | 2019-10-10 | 000000020025136 | 29627.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.6819% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 1387.5 | 0174233-IN | 2019-10-10 | 000000020025136 | 1387.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.03194% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 2775 | 0174233-IN | 2019-10-10 | 000000020025136 | 2775 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.06387% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 4625 | 0174233-IN | 2019-10-10 | 000000020025136 | 4625 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.1065% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 8787.5 | 0174233-IN | 2019-10-10 | 000000020025136 | 8787.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.2023% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Laptops | 2019-07-01 | 2019-10-10 | 2019/20 |  | PO2W-200000000689, 19-109955 | 0 | 10767 | 0174233-IN | 2019-10-10 | 000000020025136 | 10767 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9431101 | 0.2478% | Lenovo 300e Laptops, electronic waste, 3 yr sealed battery replacement, 4.5 year warranty, integration services, imaging, asset tag & reporting, cart wiring, and delivery for Workman HS. Total computers: 1016 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-09-23 | 2019/20 | 2-515 | PO3W-200000000448 | 0 | 1300.32 | 0173473-IN | 2019-09-23 | 000000020017958 | 1300.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9431101 | 1.427% | Ergotron Zip40 Charging carts to store laptops at Workman HS. Total cart: 1 | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Technology | 5 | Technology | Workman HS | 21st Century classroom | Arey Jones Educational Solutions | Charging carts | 2019-07-01 | 2019-11-07 | 2019/20 | 2-516 | PO3W-200000000730 | 0 | 40310.03 | 0174342-IN | 2019-11-07 | 000000020035575 | 40310.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9431101 | 5.08% | Ergotron Zip40 Charging carts to store laptops at Workman HS. Total carts: 31 | Workman HS-5-21st Century classroom
District Office-21st Century classroom-Move Management | 0 | Move Management | District Office | 21st Century classroom | ATC LLC | Moving of container(s) | 2024-01-17 | 2028-12-09 | 2023/24 | 24-5047 |  | 4950 | 4950 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9851100 | 0% | Moving of container(s) for the District Office | District Office-0-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Avia Communications, Inc. | Printing & posting of POS/Os | 2017-07-11 | 2017-07-11 | 2017/18 |  | N/A - Cost of Issuance | 0 | 1350.74 |  |  |  | 1350.74 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9900000 | 100% | Printing & posting of POS/Os, 18-KT005 | District Office-0-Cost of Issuance
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | AWP Marketing and Printing Services LLC | Decal | 2022-01-06 | 2022-01-24 | 2021/22 | 22-3836 | PO2W-220000001278 | 0 | 455.52 | 318278 | 2022-01-24 | 000000020395761 | 455.52 |  |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9851100 | 100% | 8 Decal for sign (46" x 30") for the District Office | District Office-0-21st Century classroom
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | AWP Marketing and Printing Services LLC | Decal | 2024-01-18 | 2025-12-09 | 2023/24 | 24-5071 |  | 501.51 | 501.51 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9851100 | 0% | 8 Decal for sign (46" x 30") for the District Office | District Office-0-21st Century classroom
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2022-04-04 | 2021/22 |  | PO2W-220000001857 | 0 | 159 | 19409789 | 2022-04-04 | 000000020461018 | 159 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 100% | Fire monitoring of 4 portables at Los Altos ES. Starting from Jan. 2022 at $26.50/month. Bay Alarm purchased Mijac Alarm. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2023-07-13 | 2022/23 |  | PO2W-220000001857 | 0 | 79.5 | 19712541 | 2023-07-13 | 000000021124107 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Jan. 2022 at $26.50/month. Bay Alarm purchased Mijac Alarm. This expenditure is not supposed to be part of the bond's projects. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2023-07-13 | 2022/23 |  | PO2W-220000001857 | 0 | 79.5 | 19969540 | 2023-07-13 | 000000021124107 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Jan. 2022 at $26.50/month. Bay Alarm purchased Mijac Alarm. This expenditure is not supposed to be part of the bond's projects. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2023-07-13 | 2022/23 |  | PO2W-220000001857 | 0 | 79.5 | 20216664 | 2023-07-13 | 000000021124107 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Jan. 2022 at $26.50/month. Bay Alarm purchased Mijac Alarm. This expenditure is not supposed to be part of the bond's projects. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2023-07-13 | 2022/23 |  | PO2W-220000001857 | 0 | 79.5 | 20429705 | 2023-07-13 | 000000021124107 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Jan. 2022 at $26.50/month. Bay Alarm purchased Mijac Alarm. This expenditure is not supposed to be part of the bond's projects. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2023-07-17 | 2022/23 |  | PO2W-220000001857 | 0 | -318 |  |  |  | -318 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Jan. 2022 at $26.50/month. Bay Alarm purchased Mijac Alarm. The 2022/23 expenditure is not supposed to be part of the bond's projects. Moved exp. to NCS, JVA 24*84. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2023-07-18 | 2022/23 |  | PO2W-220000001857 | 2623.5 | 2623.5 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Jan. 2022 at $26.50/month. Bay Alarm purchased Mijac Alarm. Remaining balance in this PO. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Bay Alarm Company | Alarm for portables | 2022-03-23 | 2023-07-19 | 2022/23 | 22-5814 | PO2W-220000001857 | -2623.5 | -2623.5 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Jan. 2022 at $26.50/month. Bay Alarm purchased Mijac Alarm. Close-out PO | Los Altos ES-2-Interim Housing
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | California Municipal Statistics, Inc. | Demographic data | 2017-07-11 | 2017-07-11 | 2017/18 |  | N/A - Cost of Issuance | 0 | 1700 |  |  |  | 1700 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Demographic data, 18-KT005 | District Office-0-Cost of Issuance
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Camcor Inc. | Document camera(s) | 2020-12-02 | 2021-04-14 | 2020/21 | 21-3339 | PO3W-210000001076 | 0 | 15519.98 | 2508704 | 2021-04-14 | 000000020180213 | 15519.98 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 39.68% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Cedarlane. Total cameras: 25 | Cedarlane-1-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Camcor Inc. | Document camera(s) bundles | 2022-05-18 | 2022-06-03 | 2021/22 | 22-6711 | PO3W-220000003018 | 0 | 1347.66 | 2529948 | 2022-06-03 | 000000020516587 | 1347.66 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 100% | Elmo 1386-72 MO-2 + Elmo Cast Bundle for District-wide. Total cameras & wireless receivers: 2 each | District Office-0-21st Century classroom
Grandview-21st Century classroom-Technology | 2 | Technology | Grandview | 21st Century classroom | Camcor Inc. | Document camera(s) | 2022-11-17 | 2023-01-09 | 2022/23 | 23-4030 | PO3W-230000001318 | 0 | 12031.09 | 2539612 | 2023-01-09 | 000000020794053 | 12031.09 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 38% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Grandview. Total cameras: 19 | Grandview-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Camcor Inc. | Document camera(s) | 2020-07-01 | 2020-07-16 | 2020/21 | 21-309 | PO3W-210000000006 | 0 | 11954.12 | 2494523 | 2020-07-16 | 000000020114150 | 11954.12 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 35.09% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Los Altos ES. Total cameras: 20 | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Camcor Inc. | Document camera(s) | 2020-12-02 | 2021-04-14 | 2020/21 | 21-3339 | PO3W-210000001076 | 0 | 23590.37 | 2508704 | 2021-04-14 | 000000020180213 | 23590.37 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 60.32% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Mesa Robles. Total cameras: 38 | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Camcor Inc. | Document camera(s) | 2020-07-01 | 2020-07-16 | 2020/21 | 21-309 | PO3W-210000000006 | 0 | 14942.64 | 2494523 | 2020-07-16 | 000000020114150 | 14942.64 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 43.86% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Nelson. Total cameras: 25 | Nelson-1-21st Century classroom
Newton-21st Century classroom-Technology | 1 | Technology | Newton | 21st Century classroom | Camcor Inc. | Document camera(s) | 2022-11-17 | 2023-01-09 | 2022/23 | 23-4030 | PO3W-230000001318 | 0 | 12347.7 | 2539612 | 2023-01-09 | 000000020794053 | 12347.7 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 39% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Newton. Total cameras: 20 | Newton-1-21st Century classroom
Sparks MS-21st Century classroom-Technology | 2 | Technology | Sparks MS | 21st Century classroom | Camcor Inc. | Document camera(s) | 2022-11-17 | 2023-01-09 | 2022/23 | 23-4030 | PO3W-230000001318 | 0 | 7281.97 | 2539612 | 2023-01-09 | 000000020794053 | 7281.97 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 23% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Sparks MS. Total cameras: 12 | Sparks MS-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Camcor Inc. | Document camera(s) | 2020-07-01 | 2020-07-16 | 2020/21 | 21-309 | PO3W-210000000006 | 0 | 7172.46 | 2494523 | 2020-07-16 | 000000020114150 | 7172.46 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 21.05% | Elmo TT-12W Stem Cam Document Camera (HDMI Input & Output) for Workman ES. Total cameras: 12 | Workman ES-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Caston Inc. | Contractor | 2023-09-12 | 2024-01-22 | 2023/24 |  | PO2W-240000001253 | 0 | 5000 | 01777 | 2024-01-22 | 000000021420044 | 5000 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9121101 | 26.64% | Provide labor and materials to clean the interior break walls with Simply Green in 19 rooms at Grandview | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Caston Inc. | Contractor | 2023-09-12 | 2024-12-09 | 2023/24 | 24-2511 | PO2W-240000001253 | 13770.85 | 13770.85 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9121101 | 0% | Provide labor and materials to clean the interior break walls with Simply Green in 19 rooms at Grandview | Grandview-2-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 67.45 | 5725548 | 2021-03-05 | 000000020169721 | 67.45 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 1.76% | C2G HDMI and USB pass through wall plates for Cedarlane. Total items: 25 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 318.86 | 8312741 | 2021-03-05 | 000000020169721 | 318.86 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 8.32% | C2G HDMI and USB pass through wall plates for Cedarlane. Total items: 25 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 380.19 | 8316064 | 2021-03-05 | 000000020169721 | 380.19 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 9.92% | C2G HDMI and USB pass through wall plates for Cedarlane. Total items: 25 | Cedarlane-1-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 13475.07 | TGH9705 | 2019-10-04 | 000000020022968 | 13475.07 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 3.657% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 11454.58 | TGH9705 | 2019-10-04 | 000000020022968 | 11454.58 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 3.108% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 8316 | TGJ0727 | 2019-10-04 | 000000020022968 | 8316 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 2.257% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 13611.22 | TGJ0727 | 2019-10-04 | 000000020022968 | 13611.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 3.694% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 16.2 | TGQ7072 | 2019-10-04 | 000000020022968 | 16.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.004396% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 16.2 | TGQ7072 | 2019-10-04 | 000000020022968 | 16.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.004396% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 16.2 | TGQ7072 | 2019-10-04 | 000000020022968 | 16.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.004396% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 23.4 | TGQ7072 | 2019-10-04 | 000000020022968 | 23.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.00635% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 91.8 | TGQ7072 | 2019-10-04 | 000000020022968 | 91.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.02491% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 6.3 | TGQ7072 | 2019-10-04 | 000000020022968 | 6.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.00171% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-04 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 9432.55 | TPH9179 | 2019-10-04 | 000000020022968 | 9432.55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 2.56% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 67375.35 | TGG6297 | 2019-10-08 | 000000020023870 | 67375.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 18.28% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 6132 | TGG6297 | 2019-10-08 | 000000020023870 | 6132 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 1.664% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 194041.01 | TLW3515 | 2019-10-08 | 000000020023870 | 194041.01 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 52.65% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 63 | TLW3515 | 2019-10-08 | 000000020023870 | 63 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 0.0171% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 6716.35 | TLW3515 | 2019-10-08 | 000000020023870 | 6716.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4340 | 9851100 | 1.823% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | CDW-G Government Inc. | Wireless network equipment | 2019-07-01 | 2019-10-08 | 2019/20 | 2-1437 | PO2W-200000000348 | 0 | 37730.2 | TMH3476 | 2019-10-08 | 000000020023870 | 37730.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 10.24% | HPE Aruba AP-325-wireless access point, mounting kits, licenses, software supports, and next day exchange service for District-wide use | District Office-0-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 56.66 | 5725548 | 2021-03-05 | 000000020169721 | 56.66 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 1.478% | C2G HDMI and USB pass through wall plates for Los Altos ES. Total items: 21 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 267.85 | 8312741 | 2021-03-05 | 000000020169721 | 267.85 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 6.989% | C2G HDMI and USB pass through wall plates for Los Altos ES. Total items: 21 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 319.35 | 8316064 | 2021-03-05 | 000000020169721 | 319.35 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 8.333% | C2G HDMI and USB pass through wall plates for Los Altos ES. Total items: 21 | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 107.92 | 5725548 | 2021-03-05 | 000000020169721 | 107.92 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 2.816% | C2G HDMI and USB pass through wall plates for Mesa Robles. Total items: 40 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 510.18 | 8312741 | 2021-03-05 | 000000020169721 | 510.18 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 13.31% | C2G HDMI and USB pass through wall plates for Mesa Robles. Total items: 40 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 608.3 | 8316064 | 2021-03-05 | 000000020169721 | 608.3 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 15.87% | C2G HDMI and USB pass through wall plates for Mesa Robles. Total items: 40 | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | CDW-G Government Inc. | Document camera(s) | 2020-07-01 | 2020-08-21 | 2020/21 | 21-122 | PO3W-210000000002 | 0 | 706.28 | ZCT7823 | 2020-08-21 | 000000020120955 | 706.28 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 100% | Elmo TT-12W Stem Cam Document Camera - a sample for Nelson room #C1 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 53.96 | 5725548 | 2021-03-05 | 000000020169721 | 53.96 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 1.408% | C2G HDMI and USB pass through wall plates for Nelson. Total items: 20 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 255.09 | 8312741 | 2021-03-05 | 000000020169721 | 255.09 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 6.656% | C2G HDMI and USB pass through wall plates for Nelson. Total items: 20 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 304.15 | 8316064 | 2021-03-05 | 000000020169721 | 304.15 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 7.936% | C2G HDMI and USB pass through wall plates for Nelson. Total items: 20 | Nelson-1-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 51.27 | 5725548 | 2021-03-05 | 000000020169721 | 51.27 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 1.338% | C2G HDMI and USB pass through wall plates for Workman ES. Total items: 19 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 |  | PO3W-210000001145 | 0 | 242.34 | 8312741 | 2021-03-05 | 000000020169721 | 242.34 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 6.323% | C2G HDMI and USB pass through wall plates for Workman ES. Total items: 19 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | CDW-G Government Inc. | Wall plates | 2020-12-09 | 2021-03-05 | 2020/21 | 21-3477 | PO3W-210000001145 | 0 | 288.93 | 8316064 | 2021-03-05 | 000000020169721 | 288.93 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 7.539% | C2G HDMI and USB pass through wall plates for Workman ES. Total items: 19 | Workman ES-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2022-12-16 | 2022/23 |  | PO2W-230000001268 | 0 | 196317.5 | Pay app #1 | 2022-12-16 | 000000020772552 | 196317.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 7.165% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-01-23 | 2022/23 |  | PO2W-230000001268 | 0 | 160692.5 | Pay app #2 | 2023-01-23 | 000000020817401 | 160692.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 5.865% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-03-07 | 2022/23 |  | PO2W-230000001268 | 0 | 104737.5 | Pay app #3 | 2023-03-07 | 000000020889950 | 104737.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 3.823% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-04-10 | 2022/23 |  | PO2W-230000001268 | 0 | 124550.48 | Pay app #4 | 2023-04-10 | 000000020949731 | 124550.48 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 4.546% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-04-21 | 2022/23 |  | PO2W-230000001268 | 0 | 324235 | Pay app #5 | 2023-04-21 | 000000020971349 | 324235 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 11.83% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-01 | 2022/23 |  | PO2W-230000001268 | 0 | -124550.48 | Pay app #4 | 2023-04-10 | 000000020949731 | -124550.48 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | -4.546% | Classroom improvements for Grandview 21st Century. Bid option #2. Warrant was lost in the mail. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-04 | 2022/23 |  | PO2W-230000001268 | 0 | 124550.48 | Pay app #4 | 2023-05-04 | 000000020993488 | 124550.48 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 4.546% | Classroom improvements for Grandview 21st Century. Bid option #2. Replaced warrant #20949731 that was lost in the mail | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-18 | 2022/23 |  | PO2W-230000001268 | 0 | 218903.75 | Pay app #6 | 2023-05-18 | 000000021019977 | 218903.75 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 7.989% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-06-27 | 2022/23 |  | PO2W-230000001268 | 0 | 155990 | Pay app #7 | 2023-06-27 | 000000021094596 | 155990 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 5.693% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-08-04 | 2022/23 |  | PO2W-230000001268 | 0 | 142890.01 | Pay app #8 | 2023-08-04 | 000000021154020 | 142890.01 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 5.215% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-08-22 | 2023/24 |  | PO2W-230000001268 | 0 | 746961.26 | Pay app #9 | 2023-08-22 | 000000021175345 | 746961.26 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 27.26% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-11-06 | 2023/24 |  | PO2W-230000001268 | 0 | 21517.5 | Pay app #10 | 2023-11-06 | 000000021304956 | 21517.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 0.7853% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2024-01-19 | 2023/24 |  | PO2W-230000001268 | 0 | 218690.54 | Pay app #11 | 2024-01-19 | 000000021417631 | 218690.54 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 7.981% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Contractor | 2 | Contractor | Grandview | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2027-12-09 | 2023/24 | 23-2750 | PO2W-230000001268 | 324513.96 | 324513.96 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9121101 | 0% | Classroom improvements for Grandview 21st Century. Bid option #2 | Grandview-2-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2020-11-30 | 2020/21 |  | PO2W-210000000935 | 0 | 194607.5 | Pay app #1 | 2020-11-30 | 000000020145581 | 194607.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 6.284% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-01-07 | 2020/21 |  | PO2W-210000000935 | 0 | 171275.5 | Pay app #2 | 2021-01-07 | 000000020154782 | 171275.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 5.53% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-02-11 | 2020/21 |  | PO2W-210000000935 | 0 | 216182 | Pay app #3 | 2021-02-11 | 000000020164229 | 216182 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 6.98% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-02-11 | 2020/21 |  | PO2W-210000000935 | 0 | 331075 | Pay app #4 | 2021-02-11 | 000000020164229 | 331075 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 10.69% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-03-16 | 2020/21 |  | PO2W-210000000935 | 0 | 299915 | Pay app #5 | 2021-03-16 | 000000020172574 | 299915 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 9.684% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-04-06 | 2020/21 |  | PO2W-210000000935 | 0 | 476649.8 | Pay app #6 | 2021-04-06 | 000000020177857 | 476649.8 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 15.39% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-05-17 | 2020/21 |  | PO2W-210000000935 | 0 | 481460 | Pay app #7 | 2021-05-17 | 000000020189638 | 481460 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 15.55% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-06-17 | 2020/21 |  | PO2W-210000000935 | 0 | 492670 | Pay app #8 | 2021-06-17 | 000000020198970 | 492670 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 15.91% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-07-08 | 2020/21 |  | PO2W-210000000935 | 0 | 134615 | Pay app #9 | 2021-07-08 | 000000020206245 | 134615 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 4.347% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2021-09-09 | 2021/22 |  | PO2W-210000000935 | 0 | 143700.2 | Pay app #10 | 2021-09-09 | 000000020255185 | 143700.2 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 4.64% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2022-01-05 | 2021/22 |  | PO2W-210000000935 | 0 | 130557.95 | Pay app #11 | 2022-01-05 | 000000020376882 | 130557.95 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 4.216% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2020-10-16 | 2022-08-05 | 2021/22 | 21-2506 | PO2W-210000000935 | 0 | 24292.05 | Pay app #12 | 2022-08-05 | 000000020574607 | 24292.05 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221101 | 0.7844% | 21st Century classroom modification at Mesa Robles. Base bid #1. The total project costs with the change order (PO2W-22*1552) is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2021-12-16 | 2022-08-05 | 2021/22 | 22-3690 | PO2W-220000001552, PO2W-210000000935 | 0 | 137429.42 | Pay app #12 | 2022-08-05 | 000000020574607 | 137429.42 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221101 | 100% | Change order for the 21st Century classroom at Mesa Robles. This is for the additional cost to change CAT 6 cables to CAT 6A, Frame, install plywood, and install new tackable wall on top section of windows, Demo of 2 portable bldgs, Relocate & rewire 4 thermostats, Bead blast classrm E4 floor for second time, Remove wire mold & tracing out existing circuits, Re-feed existing receptacle in library, Add pathways, wiring, programming & relays to interface the TOP CAT & fire alarm systems, Provide & install shut off valve for bldg H. Addendum to PO2W-21*935. The total project costs with this change order is $3,234,429.42 | Mesa Robles-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2022-12-12 | 2022/23 |  | PO2W-230000001269 | 0 | 120966.35 | Pay app #1 | 2022-12-12 | 000000020762675 | 120966.35 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 5.719% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-01-23 | 2022/23 |  | PO2W-230000001269 | 0 | 32917.5 | Pay app #2 | 2023-01-23 | 000000020817402 | 32917.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 1.556% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-03-07 | 2022/23 |  | PO2W-230000001269 | 0 | 62937.5 | Pay app #3 | 2023-03-07 | 000000020889950 | 62937.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 2.976% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-04-10 | 2022/23 |  | PO2W-230000001269 | 0 | 152276.97 | Pay app #4 | 2023-04-10 | 000000020949731 | 152276.97 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 7.2% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-04-21 | 2022/23 |  | PO2W-230000001269 | 0 | 67640.01 | Pay app #5 | 2023-04-21 | 000000020971349 | 67640.01 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 3.198% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-01 | 2022/23 |  | PO2W-230000001269 | 0 | -152276.97 | Pay app #4 | 2023-04-10 | 000000020949731 | -152276.97 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | -7.2% | Classroom improvements for Newton 21st Century. Bid option #2. Warrant was lost in the mail. | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-04 | 2022/23 |  | PO2W-230000001269 | 0 | 152276.97 | Pay app #4 | 2023-05-04 | 000000020993488 | 152276.97 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 7.2% | Classroom improvements for Newton 21st Century. Bid option #2. Replaced warrant #20949731 that was lost in the mail | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-18 | 2022/23 |  | PO2W-230000001269 | 0 | 218222.61 | Pay app #6 | 2023-05-18 | 000000021019977 | 218222.61 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 10.32% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-06-27 | 2022/23 |  | PO2W-230000001269 | 0 | 142063.96 | Pay app #7 | 2023-06-27 | 000000021094596 | 142063.96 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 6.717% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-08-04 | 2022/23 |  | PO2W-230000001269 | 0 | 397329.43 | Pay app #8 | 2023-08-04 | 000000021154020 | 397329.43 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 18.79% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-08-22 | 2023/24 |  | PO2W-230000001269 | 0 | 407181.88 | Pay app #9 | 2023-08-22 | 000000021175345 | 407181.88 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 19.25% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-11-06 | 2023/24 |  | PO2W-230000001269 | 0 | 23476.88 | Pay app #10 | 2023-11-06 | 000000021304956 | 23476.88 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 1.11% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2024-01-19 | 2023/24 |  | PO2W-230000001269 | 0 | 276738.47 | Pay app #11 | 2024-01-19 | 000000021417631 | 276738.47 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 13.08% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2027-12-09 | 2023/24 | 23-2751 | PO2W-230000001269 | 213248.44 | 213248.44 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241101 | 0% | Classroom improvements for Newton 21st Century. Bid option #2 | Newton-1-21st Century classroom
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-03-11 | 2021/22 |  | PO2W-220000001166 | 0 | 117420 | Pay app #1 | 2022-03-11 | 000000020441844 | 117420 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 29.65% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-05-04 | 2021/22 |  | PO2W-220000001166 | 0 | 73435 | Pay app #2 | 2022-05-04 | 000000020484150 | 73435 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 18.55% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-05-06 | 2021/22 |  | PO2W-220000001166 | 0 | 86260 | Pay app #3 | 2022-05-06 | 000000020487442 | 86260 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 21.79% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-08-19 | 2022/23 |  | PO2W-220000001166 | 0 | 87591.8 | Pay app #4 | 2022-08-19 | 000000020590138 | 87591.8 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 22.12% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-12-07 | 2022/23 |  | PO2W-220000001166 | 0 | 11453.39 | Pay app #5 | 2022-12-07 | 000000020755466 | 11453.39 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 2.893% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-12-12 | 2022/23 |  | PO2W-220000001166 | 0 | 19797.9 | Pay app #6 | 2022-12-12 | 000000020762676 | 19797.9 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 5% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-12-12 | 2022/23 |  | PO2W-220000001166 | 2541.91 | 2541.91 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 0% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30. Credit from change order. Remaining balance in this PO. | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Chalmers Construction Services, Inc. | Contractor | 2021-12-08 | 2022-12-13 | 2022/23 | 22-3543 | PO2W-220000001166 | -2541.91 | -2541.91 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 0% | Provide labor and materials to complete Newton Interim Housing project per Bid #2020-21.30. Close-out PO. | Newton-1-Interim Housing
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2022-12-16 | 2022/23 |  | PO2W-230000001271 | 0 | 169622.5 | Pay app #1 | 2022-12-16 | 000000020772553 | 169622.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 9.833% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-01-23 | 2022/23 |  | PO2W-230000001271 | 0 | 67070 | Pay app #2 | 2023-01-23 | 000000020817403 | 67070 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 3.888% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-03-07 | 2022/23 |  | PO2W-230000001271 | 0 | 51395 | Pay app #3 | 2023-03-07 | 000000020889950 | 51395 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 2.979% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-04-10 | 2022/23 |  | PO2W-230000001271 | 0 | 109369.54 | Pay app #4 | 2023-04-10 | 000000020949731 | 109369.54 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 6.34% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-04-21 | 2022/23 |  | PO2W-230000001271 | 0 | 325517.41 | Pay app #5 | 2023-04-21 | 000000020971349 | 325517.41 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 18.87% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-01 | 2022/23 |  | PO2W-230000001271 | 0 | -109369.54 | Pay app #4 | 2023-04-10 | 000000020949731 | -109369.54 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | -6.34% | Classroom improvements for Sparks MS 21st Century. Bid option #2. Warrant was lost in the mail. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-04 | 2022/23 |  | PO2W-230000001271 | 0 | 109369.54 | Pay app #4 | 2023-05-04 | 000000020993488 | 109369.54 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 6.34% | Classroom improvements for Sparks MS 21st Century. Bid option #2. Replaced warrant #20949731 that was lost in the mail | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-05-18 | 2022/23 |  | PO2W-230000001271 | 0 | 88373.66 | Pay app #6 | 2023-05-18 | 000000021019977 | 88373.66 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 5.123% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-06-27 | 2022/23 |  | PO2W-230000001271 | 0 | 153140 | Pay app #7 | 2023-06-27 | 000000021094596 | 153140 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 8.878% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-08-04 | 2022/23 |  | PO2W-230000001271 | 0 | 417040.26 | Pay app #8 | 2023-08-04 | 000000021154020 | 417040.26 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 24.18% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-08-22 | 2023/24 |  | PO2W-230000001271 | 0 | 151049.91 | Pay app #9 | 2023-08-22 | 000000021175345 | 151049.91 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 8.757% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2023-11-06 | 2023/24 |  | PO2W-230000001271 | 0 | 14962.5 | Pay app #10 | 2023-11-06 | 000000021304956 | 14962.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 0.8674% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2024-01-19 | 2023/24 |  | PO2W-230000001271 | 0 | 36255.04 | Pay app #11 | 2024-01-19 | 000000021417631 | 36255.04 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 2.102% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Contractor | 2 | Contractor | Sparks MS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2022-09-23 | 2027-12-09 | 2023/24 | 23-2752 | PO2W-230000001271 | 141204.18 | 141204.18 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9301101 | 0% | Classroom improvements for Sparks MS 21st Century. Bid option #2 | Sparks MS-2-21st Century classroom
Workman HS-21st Century classroom-Contractor | 5 | Contractor | Workman HS | 21st Century classroom | Chalmers Construction Services, Inc. | Contractor | 2024-01-09 | 2028-06-01 | 2023/24 | 24-4844 |  | 2080000 | 2080000 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9431101 | 0% | Classroom improvements for Workman HS. Bid #2023-24.05 Measure BB Bond Base Bid #2 | Workman HS-5-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Chatfield-Clarke | Tack boards | 2020-09-23 | 2020-11-03 | 2020/21 | 21-2077 | PO2W-210000000770 | 0 | 413.91 | 136701 | 2020-11-03 | 000000020139548 | 413.91 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 100% | Tack boards for Workman ES. Total tack boards: 5 | Workman ES-2-21st Century classroom
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-02-05 | 2020/21 |  | PO2W-210000001098 | 0 | 5342.5 | 20-31311-30-01 | 2021-02-05 | 000000020162565 | 5342.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 51.78% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-02-05 | 2020/21 |  | PO2W-210000001098 | 0 | 1360 | 20-31311-30-02 | 2021-02-05 | 000000020162565 | 1360 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 13.18% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-04-19 | 2020/21 |  | PO2W-210000001098 | 0 | 1650 | 20-31311-30-04 | 2021-04-19 | 000000020181372 | 1650 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 15.99% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-05-26 | 2020/21 |  | PO2W-210000001098 | 0 | 1732.5 | 20-31311-30-03 | 2021-05-26 | 000000020192519 | 1732.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 16.79% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2021-09-15 | 2021/22 |  | PO2W-210000001098 | 0 | 232.5 | 20-31311-30-05 | 2021-09-15 | 000000020259582 | 232.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 2.253% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2023-06-30 | 2022/23 |  | PO2W-210000001098 | 6602.5 | 6602.5 |  |  |  | 0 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 0% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane. Remaining balance in this PO | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Cedarlane | Interim Housing | Converse Consultants | Geotechnical | 2020-11-06 | 2023-07-11 | 2022/23 | 21-2936 | PO2W-210000001098 | -6602.5 | -6602.5 |  |  |  | 0 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9051102 | 0% | Geotechnical observation and testing and materials testing and inspection services at Cedarlane. Close-out PO. | Cedarlane-1-Interim Housing
Grandview-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Grandview | 21st Century classroom | Converse Consultants | Geotechnical | 2022-11-02 | 2023-05-10 | 2022/23 |  | PO2W-230000001453 | 0 | 1760 | 22-31309-61-0000001 | 2023-05-10 | 000000021004830 | 1760 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9121101 | 31.68% | Provide material inspection & testing services for the campus modernization project at Grandview | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Grandview | 21st Century classroom | Converse Consultants | Geotechnical | 2022-11-02 | 2025-12-09 | 2023/24 | 23-3940 | PO2W-230000001453 | 320 | 320 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9121101 | 0% | Provide material inspection & testing services for the campus modernization project at Grandview | Grandview-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2020-08-17 | 2020/21 |  | PO2W-200000005542 | 0 | 779.5 | 20-31197-30-0000001 | 2020-08-17 | 000000020119768 | 779.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 6.297% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2020-12-04 | 2020/21 |  | PO2W-200000005542 | 0 | 342.5 | 20-31197-30-0000002 | 2020-12-04 | 000000020147422 | 342.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 2.767% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2021-02-05 | 2020/21 |  | PO2W-200000005542 | 0 | 1153.5 | 20-31197-30-0000003 | 2021-02-05 | 000000020162565 | 1153.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 9.318% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2021-03-24 | 2020/21 |  | PO2W-200000005542 | 0 | 1722.5 | 20-31197-30-0000004 | 2021-03-24 | 000000020174717 | 1722.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 13.91% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2021-03-24 | 2020/21 |  | PO2W-200000005542 | 0 | 2565 | 20-31197-30-0000005 | 2021-03-24 | 000000020174717 | 2565 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 20.72% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2021-03-24 | 2020/21 |  | PO2W-200000005542 | 0 | 4936 | 20-31197-30-0000006 | 2021-03-24 | 000000020174717 | 4936 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 39.87% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2021-04-19 | 2020/21 |  | PO2W-200000005542 | 0 | 880 | 20-31197-30-0000007 | 2021-04-19 | 000000020181372 | 880 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 7.109% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2023-06-30 | 2022/23 |  | PO2W-200000005542 | 11301 | 11301 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 0% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel. Remaining balance in this PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2023-07-11 | 2022/23 | 2-10672 | PO2W-200000005542 | -11301 | -11301 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191101 | 0% | Geotechnical observation and materials testing and special inspection services at Los Altos ES. The project consists of alteration and upgrades to several existing classroom buildings including buildings A to F and portable classroom buildings G1 to G3, and other site works at Los Altos ES. Scope of services include reviewing, inspecting, and preparing reports for soils, concrete, and reinforcing steel. Close-out PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | 21st Century classroom | Converse Consultants | Masonry inspection | 2020-10-28 | 2021-09-09 | 2021/22 | 21-2786 | PO2W-210000001034 | 0 | 2537.5 | 20-31197-61-0000001 | 2021-09-09 | 000000020255186 | 2537.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 30.48% | Masonry inspection of brick veneer repair for Los Altos ES 21st Century classroom modification program | Los Altos ES-2-21st Century classroom
Los Altos ES-Interim Housing-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | Interim Housing | Converse Consultants | Geotechnical | 2019-07-01 | 2019-12-11 | 2019/20 |  | PO2W-200000000203 | 0 | 5280.5 | 19-31241-30-0000001 | 2019-12-11 | 000000020047618 | 5280.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191102 | 100% | Geotechnical observation and testing, special inspection and material testing services for 4 portables at Los Altos ES. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | Interim Housing | Converse Consultants | Geotechnical | 2019-07-01 | 2023-06-30 | 2022/23 |  | PO2W-200000000203 | 9249.5 | 9249.5 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191102 | 0% | Geotechnical observation and testing, special inspection and material testing services for 4 portables at Los Altos ES. Remaining balance in this PO. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-DSA Special Inspection | 2 | DSA Special Inspection | Los Altos ES | Interim Housing | Converse Consultants | Geotechnical | 2019-07-01 | 2023-07-11 | 2022/23 | 2-739 | PO2W-200000000203 | -9249.5 | -9249.5 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9191102 | 0% | Geotechnical observation and testing, special inspection and material testing services for 4 portables at Los Altos ES. Close-out PO. | Los Altos ES-2-Interim Housing
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2020-06-22 | 2019/20 |  | PO2W-200000004115 | 0 | 3705 | 20-31125-30-01 | 2020-06-22 | 000000020107232 | 3705 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 32.7% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2020-06-22 | 2019/20 |  | PO2W-200000004115 | 0 | 4077.5 | 20-31125-30-02 | 2020-06-22 | 000000020107232 | 4077.5 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 35.99% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2020-10-13 | 2020/21 |  | PO2W-200000004115 | 0 | 1050.5 | 20-31125-30-03 | 2020-10-13 | 000000020134066 | 1050.5 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 9.271% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2021-04-19 | 2020/21 |  | PO2W-200000004115 | 0 | 1052.5 | 20-31125-30-04 | 2021-04-19 | 000000020181372 | 1052.5 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 9.289% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2021-09-09 | 2021/22 |  | PO2W-200000004115 | 0 | 1445 | 20-31125-30-05 | 2021-09-09 | 000000020255186 | 1445 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 12.75% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2023-06-30 | 2022/23 |  | PO2W-200000004115 | 2209.5 | 2209.5 |  |  |  | 0 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 0% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles. Remaining balance in this PO. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Mesa Robles | Interim Housing | Converse Consultants | Geotechnical | 2020-02-13 | 2023-07-11 | 2022/23 | 2-7894 | PO2W-200000004115 | -2209.5 | -2209.5 |  |  |  | 0 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9221102 | 0% | Geotechnical observation and materials testing services. Perform soils testing, special inspection and material testing services. The project consists of design and construction of interim housing and portable replacements at Mesa Robles. Close-out PO. | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-DSA Special Inspection | 1 | DSA Special Inspection | Nelson | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2021-02-05 | 2020/21 |  | PO2W-200000005543 | 0 | 1117.5 | 20-31198-60-0000001 | 2021-02-05 | 000000020162565 | 1117.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9231101 | 100% | Provide materials testing and special inspection services at Nelson The project consists of alteration and upgrades to several existing classroom buildings including buildings A, B, C, D, & K and portable classroom buidings D5, D6, and E1 through E4, and other site works. Scope of services include reviewing, testing, and prepare reports for concrete and reinforcing steel. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Special Inspection | 1 | DSA Special Inspection | Nelson | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2023-06-30 | 2022/23 |  | PO2W-200000005543 | 19732.5 | 19732.5 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9231101 | 0% | Provide materials testing and special inspection services at Nelson The project consists of alteration and upgrades to several existing classroom buildings including buildings A, B, C, D, & K and portable classroom buidings D5, D6, and E1 through E4, and other site works. Scope of services include reviewing, testing, and prepare reports for concrete and reinforcing steel. Remaining balance in this PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Special Inspection | 1 | DSA Special Inspection | Nelson | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2023-07-11 | 2022/23 | 2-10673 | PO2W-200000005543 | -19732.5 | -19732.5 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9231101 | 0% | Provide materials testing and special inspection services at Nelson The project consists of alteration and upgrades to several existing classroom buildings including buildings A, B, C, D, & K and portable classroom buidings D5, D6, and E1 through E4, and other site works. Scope of services include reviewing, testing, and prepare reports for concrete and reinforcing steel. Close-out PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Special Inspection | 1 | DSA Special Inspection | Nelson | 21st Century classroom | Converse Consultants | Masonry inspection | 2020-10-28 | 2021-10-01 | 2021/22 | 21-2786 | PO2W-210000001034 | 0 | 5787.5 | 20-31198-61-0000001 | 2021-10-01 | 000000020283669 | 5787.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 69.52% | Masonry inspection of brick veneer repair for Nelson 21st Century classroom modification program | Nelson-1-21st Century classroom
Newton-21st Century classroom-DSA Special Inspection | 1 | DSA Special Inspection | Newton | 21st Century classroom | Converse Consultants | Geotechnical | 2022-11-02 | 2023-04-13 | 2022/23 |  | PO2W-230000001453 | 0 | 540 | 22-31309-62-0000001 | 2023-04-13 | 000000020956682 | 540 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9241101 | 9.721% | Provide material inspection & testing services for the campus modernization project at Newton | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Special Inspection | 1 | DSA Special Inspection | Newton | 21st Century classroom | Converse Consultants | Geotechnical | 2022-11-02 | 2025-12-09 | 2023/24 | 23-3940 | PO2W-230000001453 | 855 | 855 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9241101 | 0% | Provide material inspection & testing services for the campus modernization project at Newton | Newton-1-21st Century classroom
Newton-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Newton | Interim Housing | Converse Consultants | Geotechnical | 2022-07-01 | 2022-08-01 | 2021/22 | 22-7244 | PO2W-230000000005 | 0 | 750 | 19-31282-60-0000002 | 2022-08-01 | 000000020567761 | 750 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9241102 | 100% | Geotechnical observation and testing and materials testing and inspection services at Newton. The proposal was for $1,395.00 - 210.00 (paid by Facilities, warrant #20119769) = $1,185.00 (Remaining balance). This PO didn't roll over into the new year. Paid this invoice through GAX. See PO2W-23*1454 for the remainder of the payment for Newton IH project. | Newton-1-Interim Housing
Newton-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Newton | Interim Housing | Converse Consultants | Geotechnical | 2022-07-01 | 2023-06-30 | 2022/23 |  | PO2W-230000001454, PO2W-230000000005 | 435 | 435 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9241102 | 0% | Geotechnical observation and testing and materials testing and inspection services at Newton. The proposal was for $1,395.00 - 210.00 (paid by Facilities, PO2W-20*2359, warrant #20119769) = $1,185.00 - 750.00 (PO2W-23*5, warrant #20567761) = $435.00 (Remaining balance). Remaining balance in this PO. | Newton-1-Interim Housing
Newton-Interim Housing-DSA Special Inspection | 1 | DSA Special Inspection | Newton | Interim Housing | Converse Consultants | Geotechnical | 2022-07-01 | 2023-07-11 | 2022/23 | 23-3942 | PO2W-230000001454, PO2W-230000000005 | -435 | -435 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9241102 | 0% | Geotechnical observation and testing and materials testing and inspection services at Newton. The proposal was for $1,395.00 - 210.00 (paid by Facilities, PO2W-20*2359, warrant #20119769) = $1,185.00 - 750.00 (PO2W-23*5, warrant #20567761) = $435.00 (Remaining balance). Close-out PO. | Newton-1-Interim Housing
Sparks MS-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Sparks MS | 21st Century classroom | Converse Consultants | Geotechnical | 2022-11-02 | 2023-04-13 | 2022/23 |  | PO2W-230000001453 | 0 | 2061.5 | 22-31309-60-0000001 | 2023-04-13 | 000000020956682 | 2061.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9301101 | 37.11% | Provide material inspection & testing services for the campus modernization project at Sparks MS | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Sparks MS | 21st Century classroom | Converse Consultants | Geotechnical | 2022-11-02 | 2025-12-09 | 2023/24 | 23-3940 | PO2W-230000001453 | 18.5 | 18.5 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9301101 | 0% | Provide material inspection & testing services for the campus modernization project at Sparks MS | Sparks MS-2-21st Century classroom
Workman ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Workman ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2021-02-05 | 2020/21 |  | PO2W-200000005544 | 0 | 507.5 | 20-31196-60-0000001 | 2021-02-05 | 000000020162565 | 507.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9381101 | 100% | Provide materials testing and special inspection services at Workman ES. The project consists of alteration to 3 classroom buildings 1, 2, and 3 and 10 classroom buildings AP2 to AP11, and other site works. Scope of services include reviewing, inspecting, testing, and prepare reports for concrete and reinforcing steel. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Workman ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2023-06-30 | 2022/23 |  | PO2W-200000005544 | 16092.5 | 16092.5 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9381101 | 0% | Provide materials testing and special inspection services at Workman ES. The project consists of alteration to 3 classroom buildings 1, 2, and 3 and 10 classroom buildings AP2 to AP11, and other site works. Scope of services include reviewing, inspecting, testing, and prepare reports for concrete and reinforcing steel. Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Special Inspection | 2 | DSA Special Inspection | Workman ES | 21st Century classroom | Converse Consultants | Geotechnical | 2020-06-05 | 2023-07-11 | 2022/23 | 2-10674 | PO2W-200000005544 | -16092.5 | -16092.5 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6284 | 9381101 | 0% | Provide materials testing and special inspection services at Workman ES. The project consists of alteration to 3 classroom buildings 1, 2, and 3 and 10 classroom buildings AP2 to AP11, and other site works. Scope of services include reviewing, inspecting, testing, and prepare reports for concrete and reinforcing steel. Close-out PO. | Workman ES-2-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 |  | PO2W-210000001657 | 0 | 3799.65 | 31135 | 2021-03-24 | 000000020174718 | 3799.65 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 4.958% | Furniture for Cedarlane students grade 1-3 (Room F-2, F-3, G-3, & H-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 |  | PO2W-210000001657 | 0 | 9983.73 | 31135 | 2021-03-24 | 000000020174718 | 9983.73 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 13.03% | Furniture for Cedarlane students grade 1-3 (Room F-2, F-3, G-3, & H-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-08-16 | 2021/22 | 21-4030 | PO2W-210000001657 | 0 | 52203.03 | 32071 | 2021-08-16 | 000000020230714 | 52203.03 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 68.12% | Furniture for Cedarlane students grade 1-3 (Room F-2, F-3, G-3, & H-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-08-16 | 2021/22 | 21-4030 | PO2W-210000001657 | 0 | 10649.97 | 32071 | 2021-08-16 | 000000020230714 | 10649.97 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 13.9% | Furniture for Cedarlane students grade 1-3 (Room F-2, F-3, G-3, & H-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 | 21-4032 | PO2W-210000001659 | 0 | 27615.9 | 31136 | 2021-03-24 | 000000020174718 | 27615.9 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 72.8% | Furniture for Cedarlane students grade 4-8 (Room F-1 & G-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 |  | PO2W-210000001659 | 0 | 4991.86 | 31136 | 2021-03-24 | 000000020174718 | 4991.86 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 13.16% | Furniture for Cedarlane students grade 4-8 (Room F-1 & G-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-04-19 | 2020/21 | 21-4032 | PO2W-210000001659 | 0 | 5324.99 | 31181 | 2021-04-19 | 000000020181375 | 5324.99 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 14.04% | Furniture for Cedarlane students grade 4-8 (Room F-1 & G-1). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 | 21-6167 | PO2W-210000002168 | 0 | 160829.48 | 32191 | 2021-08-16 | 000000020230714 | 160829.48 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 72.12% | Furniture for Cedarlane students grade 4-8 (Room A-1 through A-4, B-1, B-3, C-1 through C-4, D-1, & Band). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 | 21-6167 | PO2W-210000002168 | 0 | 62180.33 | 32191 | 2021-08-16 | 000000020230714 | 62180.33 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 27.88% | Furniture for Cedarlane students grade 4-8 (Room A-1 through A-4, B-1, B-3, C-1 through C-4, D-1, & Band). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6362 | PO2W-210000002280 | 0 | 42470.95 | 32074 | 2021-08-16 | 000000020230714 | 42470.95 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 73.21% | Furniture for Cedarlane students grade 4-8 (Room E-1, E-2, & E-4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 |  | PO2W-210000002280 | 0 | 11816.6 | 32074 | 2021-08-16 | 000000020230714 | 11816.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 20.37% | Furniture for Cedarlane students grade 4-8 (Room E-1, E-2, & E-4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-09-30 | 2021/22 | 21-6362 | PO2W-210000002280 | 0 | 3728.48 | 32478 | 2021-09-30 | 000000020276414 | 3728.48 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 6.427% | Furniture for Cedarlane students grade 4-8 (Room E-1, E-2, & E-4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6363 | PO2W-210000002281 | 0 | 28313.96 | 32073 | 2021-08-16 | 000000020230714 | 28313.96 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 73.21% | Furniture for Cedarlane students grade 1-3 (Room E-3 & H-3) . Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6363 | PO2W-210000002281 | 0 | 10363.39 | 32073 | 2021-08-16 | 000000020230714 | 10363.39 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 26.79% | Furniture for Cedarlane students grade 1-3 (Room E-3 & H-3) . Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-01-14 | 2022-05-20 | 2021/22 | 22-3983 | PO2W-220000001344 | 0 | 28827.85 | 34699 | 2022-05-20 | 000000020498793 | 28827.85 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 100% | Mid-tower mobile storage with shelves & 2 locking doors for Cedarlane. Total towers: 24 | Cedarlane-1-21st Century classroom
Cedarlane-Interim Housing-FF & E | 1 | FF & E | Cedarlane | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-12-18 | 2020/21 |  | PO2W-200000004768 | 0 | 20580.53 | 30699 | 2020-12-18 | 000000020151932 | 20580.53 | 03-120587 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051102 | 3.336% | Furniture for Cedarlane - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-FF & E | 1 | FF & E | Cedarlane | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 11760.3 | 30789 | 2021-05-07 | 000000020187154 | 11760.3 | 03-120587 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051102 | 1.906% | Furniture for Cedarlane - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-FF & E | 1 | FF & E | Cedarlane | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 2940.07 | 31584 | 2021-05-25 | 000000020192063 | 2940.07 | 03-120587 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051102 | 0.4766% | Furniture for Cedarlane - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Cedarlane-1-Interim Housing
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-06-17 | 2019/20 |  | PO2W-200000004768 | 0 | 55307.63 | 29473 | 2020-06-17 | 000000020106116 | 55307.63 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 8.965% | Furniture for 36 classrooms - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. | District Office-0-21st Century classroom
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-06-17 | 2019/20 |  | PO2W-200000004768 | 0 | 21087.13 | 29473 | 2020-06-17 | 000000020106116 | 21087.13 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 3.418% | Furniture for 36 classrooms - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. | District Office-0-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-05-19 | 2022/23 |  | PO3W-230000000771 | 0 | 120332.09 | 38036 | 2023-05-19 | 000000021022625 | 120332.09 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 34.52% | Furniture for Grandview students (18 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-05-19 | 2022/23 |  | PO3W-230000000771 | 0 | 31610.47 | 38036 | 2023-05-19 | 000000021022625 | 31610.47 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 9.068% | Furniture for Grandview students (18 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-08-22 | 2023/24 |  | PO3W-230000000771 | 0 | 70834.72 | 39191 | 2023-08-22 | 000000021175349 | 70834.72 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 20.32% | Furniture for Grandview students (18 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-08-22 | 2023/24 |  | PO3W-230000000771 | 0 | 19846.75 | 39191 | 2023-08-22 | 000000021175349 | 19846.75 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 5.693% | Furniture for Grandview students (18 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2024-01-04 | 2023/24 | 23-2839 | PO3W-230000000771 | 0 | 86206.84 | 39267 | 2024-01-04 | 000000021391057 | 86206.84 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 24.73% | Furniture for Grandview students (18 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2024-01-04 | 2023/24 | 23-2839 | PO3W-230000000771 | 0 | 19756.54 | 39267 | 2024-01-04 | 000000021391057 | 19756.54 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 5.668% | Furniture for Grandview students (18 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Grandview-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 45198.42 | 30789 | 2021-05-07 | 000000020187154 | 45198.42 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 7.326% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 25304.56 | 30789 | 2021-05-07 | 000000020187154 | 25304.56 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 4.102% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 40063.8 | 30790 | 2021-05-07 | 000000020187155 | 40063.8 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 6.494% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 22953.74 | 30790 | 2021-05-07 | 000000020187155 | 22953.74 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 3.721% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 | 2-9304 | PO2W-200000004768 | 0 | 615.5 | 30860 | 2021-05-07 | 000000020187156 | 615.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 0.09977% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. Per Jessica Morley @ Cumming, all furniture received. Vendor did not send us invoice for line item #9 & 13. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 22251.5 | 30860 | 2021-05-07 | 000000020187156 | 22251.5 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 3.607% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 192.72 | 31584 | 2021-05-25 | 000000020192063 | 192.72 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 0.03124% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-31 | 2020/21 |  | PO2W-200000004768 | 742.42 | 742.42 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 0% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. Per Jessica Morley @ Cumming, all furniture were received. Vendor did not send us invoice for line item #9 & 13. Remaining balance in this PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-06-01 | 2020/21 | 2-9304 | PO2W-200000004768 | -742.42 | -742.42 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 0% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. Per Jessica Morley @ Cumming, all furniture received. Vendor did not send us invoice for line item #9 & 13. Close-out PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-11-06 | 2021-02-09 | 2020/21 | 21-2938 | PO2W-210000001121 | 0 | 126666.16 | 30874 | 2021-02-09 | 000000020163346 | 126666.16 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 74.83% | Furniture for Los Altos ES. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-11-06 | 2021-02-09 | 2020/21 | 21-2938 | PO2W-210000001121 | 0 | 42608.94 | 30874 | 2021-02-09 | 000000020163346 | 42608.94 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 25.17% | Furniture for Los Altos ES. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-09-07 | 2021-11-16 | 2021/22 | 22-1683 | PO2W-220000000413 | 0 | 983.31 | 32994 | 2021-11-16 | 000000020337015 | 983.31 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 100% | Furniture for Los Altos ES. Student chairs. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-09-07 | 2022-04-20 | 2021/22 | 22-3984 | PO2W-220000001345 | 0 | 19218.56 | 34218 | 2022-04-20 | 000000020473558 | 19218.56 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 100% | Mid-tower mobile storage with shelves & 2 locking doors for Los Altos ES. Total towers: 16 | Los Altos ES-2-21st Century classroom
Los Altos ES-Interim Housing-FF & E | 2 | FF & E | Los Altos ES | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 2450.06 | 30860 | 2021-05-07 | 000000020187156 | 2450.06 | 03-119857 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191102 | 0.3971% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-FF & E | 2 | FF & E | Los Altos ES | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 8036.2 | 31584 | 2021-05-25 | 000000020192063 | 8036.2 | 03-119857 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191102 | 1.303% | Furniture for Los Altos ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Los Altos ES-2-Interim Housing
Los Molinos-21st Century classroom-FF & E | 4 | FF & E | Los Molinos | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2019-10-22 | 2020-04-15 | 2019/20 | 2-4685 | PO3W-200000001600 | 0 | 12545.73 | 29073 | 2020-04-15 | 000000020089465 | 12545.73 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9201101 | 59.26% | Furniture for Los Molinos' room #6. Stackable desks, student chairs, tables, mobile tables, stools, cubbies, desks, and rugs | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-FF & E | 4 | FF & E | Los Molinos | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2019-10-22 | 2020-04-15 | 2019/20 | 2-4685 | PO3W-200000001600 | 0 | 8623.69 | 29073 | 2020-04-15 | 000000020089465 | 8623.69 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9201101 | 40.74% | Furniture for Los Molinos' room #6. Stackable desks, student chairs, tables, mobile tables, stools, cubbies, desks, and rugs | Los Molinos-4-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 233.02 | 30860 | 2021-05-07 | 000000020187156 | 233.02 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 0.03777% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-03-23 | 2020/21 |  | PO2W-210000001658 | 0 | 15400.08 | 31134 | 2021-03-23 | 000000020174427 | 15400.08 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 20.09% | Furniture for Mesa Robles students grade 1-3 (Room E-1 through E4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-03-23 | 2020/21 |  | PO2W-210000001658 | 0 | 9983.73 | 31134 | 2021-03-23 | 000000020174427 | 9983.73 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 13.03% | Furniture for Mesa Robles students grade 1-3 (Room E-1 through E4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-08-16 | 2021/22 | 21-4031 | PO2W-210000001658 | 0 | 40602.59 | 32079 | 2021-08-16 | 000000020230714 | 40602.59 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 52.98% | Furniture for Mesa Robles students grade 1-3 (Room E-1 through E4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-08-16 | 2021/22 | 21-4031 | PO2W-210000001658 | 0 | 10649.98 | 32079 | 2021-08-16 | 000000020230714 | 10649.98 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 13.9% | Furniture for Mesa Robles students grade 1-3 (Room E-1 through E4). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 | 21-4036 | PO2W-210000001660 | 0 | 82847.7 | 31137 | 2021-03-24 | 000000020174718 | 82847.7 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 72.8% | Furniture for Mesa Robles students grade 4-8 (Room K-30 through K-33, & C-1, & C-2). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-03-24 | 2020/21 |  | PO2W-210000001660 | 0 | 14975.59 | 31137 | 2021-03-24 | 000000020174718 | 14975.59 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 13.16% | Furniture for Mesa Robles students grade 4-8 (Room K-30 through K-33, & C-1, & C-2). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-01-28 | 2021-04-19 | 2020/21 | 21-4036 | PO2W-210000001660 | 0 | 15974.96 | 31182 | 2021-04-19 | 000000020181375 | 15974.96 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 14.04% | Furniture for Mesa Robles students grade 4-8 (Room K-30 through K-33, & C-1, & C-2). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 | 21-6171 | PO2W-210000002169 | 0 | 113255.85 | 32252 | 2021-08-16 | 000000020230714 | 113255.85 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 73.21% | Furniture for Mesa Robles students grade 4-8 (Room D-12 through D-15, G-5, G-6, G-11, & G-12). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 |  | PO2W-210000002169 | 0 | 14687.37 | 32252 | 2021-08-16 | 000000020230714 | 14687.37 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 9.494% | Furniture for Mesa Robles students grade 4-8 (Room D-12 through D-15, G-5, G-6, G-11, & G-12). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-04-29 | 2021-08-16 | 2021/22 |  | PO2W-210000002169 | 0 | 20610.09 | 32275 | 2021-08-16 | 000000020230714 | 20610.09 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 13.32% | Furniture for Mesa Robles students grade 4-8 (Room D-12 through D-15, G-5, G-6, G-11, & G-12). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-04-29 | 2021-09-30 | 2021/22 | 21-6171 | PO2W-210000002169 | 0 | 6156.09 | 32477 | 2021-09-30 | 000000020276414 | 6156.09 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 3.979% | Furniture for Mesa Robles students grade 4-8 (Room D-12 through D-15, G-5, G-6, G-11, & G-12). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6364 | PO2W-210000002282 | 0 | 56627.92 | 32253 | 2021-08-16 | 000000020230714 | 56627.92 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 73.21% | Furniture for Mesa Robles students grade 1-3. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6364 | PO2W-210000002282 | 0 | 20726.78 | 32253 | 2021-08-16 | 000000020230714 | 20726.78 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 26.79% | Furniture for Mesa Robles students grade 1-3. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6365 | PO2W-210000002283 | 0 | 169883.76 | 32255 | 2021-08-16 | 000000020230714 | 169883.76 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 73.21% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-05-10 | 2021-08-16 | 2021/22 | 21-6365 | PO2W-210000002283 | 0 | 62180.33 | 32255 | 2021-08-16 | 000000020230714 | 62180.33 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 26.79% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-09-07 | 2022-01-24 | 2021/22 | 22-1681 | PO2W-220000000464 | 0 | 29690.92 | 33532 | 2022-01-24 | 000000020395770 | 29690.92 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 72.65% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-09-07 | 2022-01-24 | 2021/22 | 22-1681 | PO2W-220000000464 | 0 | 11175.25 | 33532 | 2022-01-24 | 000000020395770 | 11175.25 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 27.35% | Furniture for Mesa Robles students grade 4-8. Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-01-14 | 2022-05-20 | 2021/22 | 22-3985 | PO2W-220000001346 | 0 | 44442.93 | 34700 | 2022-05-20 | 000000020498793 | 44442.93 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 100% | Mid-tower mobile storage with shelves & 2 locking doors for Mesa Robles. Total towers: 37 | Mesa Robles-1-21st Century classroom
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-09-28 | 2020/21 |  | PO2W-200000004768 | 0 | 56280.59 | 30164 | 2020-09-28 | 000000020130222 | 56280.59 | 03-120417 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221102 | 9.123% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-09-28 | 2020/21 |  | PO2W-200000004768 | 0 | 16869.7 | 30164 | 2020-09-28 | 000000020130222 | 16869.7 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221102 | 2.734% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 11760.3 | 30790 | 2021-05-07 | 000000020187155 | 11760.3 | 03-120417 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221102 | 1.906% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 1225.03 | 30860 | 2021-05-07 | 000000020187156 | 1225.03 | 03-120417 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221102 | 0.1986% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-FF & E | 1 | FF & E | Mesa Robles | Interim Housing | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 715.92 | 31584 | 2021-05-25 | 000000020192063 | 715.92 | 03-120417 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221102 | 0.116% | Furniture for Mesa Robles - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-08-24 | 2020/21 |  | PO2W-200000004768 | 0 | 72270.22 | 29896 | 2020-08-24 | 000000020121270 | 72270.22 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 11.71% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-08-24 | 2020/21 |  | PO2W-200000004768 | 0 | 37326.95 | 29896 | 2020-08-24 | 000000020121270 | 37326.95 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 6.05% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 1854.45 | 30790 | 2021-05-07 | 000000020187155 | 1854.45 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 0.3006% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 23671.93 | 30860 | 2021-05-07 | 000000020187156 | 23671.93 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 3.837% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 3468.41 | 30860 | 2021-05-07 | 000000020187156 | 3468.41 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 0.5622% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 192.72 | 31584 | 2021-05-25 | 000000020192063 | 192.72 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 0.03124% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-06-01 | 2020/21 |  | PO2W-200000004768 | 0 | 8499.94 | 31626 | 2021-06-01 | 000000020193670 | 8499.94 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 1.378% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-06-02 | 2020/21 |  | PO2W-200000004768 | 3443.01 | 3443.01 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 0% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. Per Jessica Morley @ Cumming, all furniture were received. Vendor did not send us an invoice for line item #9 & 13 listed on the PO. Remaining balance in this PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-06-03 | 2020/21 | 2-9304 | PO2W-200000004768 | -3443.01 | -3443.01 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 0% | Furniture for Nelson - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves. Close-out PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-11-06 | 2021-02-09 | 2020/21 | 21-2945 | PO2W-210000001122 | 0 | 97706.07 | 30925 | 2021-02-09 | 000000020163346 | 97706.07 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 74.24% | Furniture for Nelson. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-11-06 | 2021-02-09 | 2020/21 | 21-2945 | PO2W-210000001122 | 0 | 33893.46 | 30925 | 2021-02-09 | 000000020163346 | 33893.46 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 25.76% | Furniture for Nelson. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-01-14 | 2022-05-20 | 2021/22 | 22-3986 | PO2W-220000001347 | 0 | 19306.32 | 34698 | 2022-05-20 | 000000020498793 | 19306.32 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 100% | Mid-tower mobile storage with shelves & 2 locking doors for Nelson. Total towers: 16 | Nelson-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-03-21 | 2022/23 |  | PO3W-230000000772 | 0 | 15805.23 | 36973 | 2023-03-21 | 000000020914273 | 15805.23 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 4.263% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-03-21 | 2022/23 |  | PO3W-230000000772 | 0 | 60166.05 | 36973 | 2023-03-21 | 000000020914273 | 60166.05 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 16.23% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-08-04 | 2022/23 |  | PO3W-230000000772 | 0 | 11853.92 | 38287 | 2023-08-04 | 000000021154022 | 11853.92 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 3.197% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-08-04 | 2022/23 |  | PO3W-230000000772 | 0 | 45124.54 | 38287 | 2023-08-04 | 000000021154022 | 45124.54 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 12.17% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-09-20 | 2023/24 |  | PO3W-230000000772 | 0 | 259.84 | 39154 | 2023-09-20 | 000000021222302 | 259.84 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 0.07008% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-09-20 | 2023/24 |  | PO3W-230000000772 | 0 | 15805.23 | 39207 | 2023-09-20 | 000000021222302 | 15805.23 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 4.263% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-09-20 | 2023/24 |  | PO3W-230000000772 | 0 | 59906.2 | 39207 | 2023-09-20 | 000000021222302 | 59906.2 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 16.16% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-10-02 | 2023/24 |  | PO3W-230000000772 | 0 | 36118.25 | 39154 | 2023-10-02 | 000000021240011 | 36118.25 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 9.742% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-10-02 | 2023/24 |  | PO3W-230000000772 | 0 | 259.84 | 39503 | 2023-10-02 | 000000021240011 | 259.84 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 0.07008% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-12-06 | 2023/24 |  | PO3W-230000000772 | 0 | 15805.24 | 39154 | 2023-12-06 | 000000021354005 | 15805.24 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 4.263% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-12-06 | 2023/24 |  | PO3W-230000000772 | 0 | 23787.95 | 39154 | 2023-12-06 | 000000021354005 | 23787.95 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 6.416% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-12-19 | 2023/24 |  | PO3W-230000000772 | 0 | 15805.23 | 40313 | 2023-12-19 | 000000021377372 | 15805.23 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 4.263% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-12-19 | 2023/24 |  | PO3W-230000000772 | 0 | 51071.52 | 40313 | 2023-12-19 | 000000021377372 | 51071.52 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 13.77% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2024-01-04 | 2023/24 | 23-2840 | PO3W-230000000772 | 0 | 3951.3 | 40386 | 2024-01-04 | 000000021391057 | 3951.3 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 1.066% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2024-01-04 | 2023/24 | 23-2840 | PO3W-230000000772 | 0 | 15041.52 | 40386 | 2024-01-04 | 000000021391057 | 15041.52 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 4.057% | Furniture for Newton students (20 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Newton-1-21st Century classroom
Sparks MS-21st Century classroom-FF & E | 2 | FF & E | Sparks MS | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-05-18 | 2022/23 |  | PO3W-230000000773 | 0 | 138560.75 | 38037 | 2023-05-18 | 000000021019978 | 138560.75 | 03-121296 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9301101 | 52.2% | Furniture for Sparks MS students (13 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-FF & E | 2 | FF & E | Sparks MS | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-05-18 | 2022/23 |  | PO3W-230000000773 | 0 | 31754.8 | 38037 | 2023-05-18 | 000000021019978 | 31754.8 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 11.96% | Furniture for Sparks MS students (13 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-FF & E | 2 | FF & E | Sparks MS | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-08-21 | 2022/23 | 23-2841 | PO3W-230000000773 | 0 | 75254.52 | 39051 | 2023-08-21 | 000000021173824 | 75254.52 | 03-121296 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9301101 | 28.35% | Furniture for Sparks MS students (13 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-FF & E | 2 | FF & E | Sparks MS | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-09-27 | 2023-08-21 | 2022/23 | 23-2841 | PO3W-230000000773 | 0 | 19846.75 | 39051 | 2023-08-21 | 000000021173824 | 19846.75 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 7.478% | Furniture for Sparks MS students (13 classrooms). Student chairs, mid towers shelves, mega cases shelves, mobile teacher's desks, etc | Sparks MS-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-12-18 | 2020/21 |  | PO2W-200000004768 | 0 | 47603.64 | 30699 | 2020-12-18 | 000000020151932 | 47603.64 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 7.716% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2020-12-18 | 2020/21 |  | PO2W-200000004768 | 0 | 33109.53 | 30699 | 2020-12-18 | 000000020151932 | 33109.53 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 5.367% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 980.03 | 30789 | 2021-05-07 | 000000020187154 | 980.03 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 0.1589% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-07 | 2020/21 |  | PO2W-200000004768 | 0 | 19857.71 | 30860 | 2021-05-07 | 000000020187156 | 19857.71 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 3.219% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-03-17 | 2021-05-25 | 2020/21 |  | PO2W-200000004768 | 0 | 2266.65 | 31584 | 2021-05-25 | 000000020192063 | 2266.65 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 0.3674% | Furniture for Workman ES - large seats, filing cabinets with locks, stools, mobile desks, student desks, book boxes for above desks, locking casters, mobile teacher desks, and cascade mini-case with shelves | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-11-06 | 2021-04-19 | 2020/21 | 21-2946 | PO2W-210000001123 | 0 | 87940.71 | 30959 | 2021-04-19 | 000000020181375 | 87940.71 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 77.58% | Furniture for Workman ES. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2020-11-06 | 2021-04-19 | 2020/21 | 21-2946 | PO2W-210000001123 | 0 | 25420.1 | 30959 | 2021-04-19 | 000000020181375 | 25420.1 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 22.42% | Furniture for Workman ES. Student chairs, mid towers shelves, mega cases shelves, filing cabinets, desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2021-02-05 | 2021-05-25 | 2020/21 | 21-4243 | PO2W-210000001743 | 0 | 5321.7 | 31593 | 2021-05-25 | 000000020192063 | 5321.7 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 100% | Additional furniture for Workman ES - student chairs, total: 45 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Culver Newlin, Inc. | Furniture | 2022-01-14 | 2022-03-23 | 2021/22 | 22-3988 | PO2W-220000001348 | 0 | 16893.03 | 34201 | 2022-03-23 | 000000020450077 | 16893.03 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 100% | Mid-tower mobile storage with shelves & 2 locking doors for Workman ES. Total towers: 14 | Workman ES-2-21st Century classroom
Baldwin-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 960 | 100653 | 2021-09-08 | 000000020253624 | 960 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 2.469% | Construction management services for Baldwin - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 1760 | 101514 | 2021-09-29 | 000000020275054 | 1760 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 4.527% | Construction management services for Baldwin - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-10 | 2023/24 |  | PO1-220000000334 | 292142 | 292142 |  |  |  | 0 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 0% | Construction management services for Baldwin - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-11 | 2023/24 | 22-1057 | PO1-220000000334 | -292142 | -292142 |  |  |  | 0 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 0% | Construction management services for Baldwin - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS). Close-out PO. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Baldwin | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862, PO1-220000000334 | 0 | 5650 | 102578 | 2021-11-08 | 000000020325325 | 5650 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9021101 | 11.52% | Construction management services for Baldwin - phase 3 & 4. This PO is only to pay invoice #102578 (Prof. service from 09/01-09/30/21), dated 09/30/21. This payment is supposed to be paid from PO1-22*334. The Board freezed payments to vendors and only allowed this invoice to be paid. Reduced PO1-22*334 by this invoice amount. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Baldwin-3-21st Century classroom
California-21st Century classroom-CM/PM Management | 3 | CM/PM Management | California | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 800 | 100653 | 2021-09-08 | 000000020253624 | 800 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 2.058% | Construction management services for California - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | California-3-21st Century classroom
California-21st Century classroom-CM/PM Management | 3 | CM/PM Management | California | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 7360 | 101514 | 2021-09-29 | 000000020275054 | 7360 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 18.93% | Construction management services for California - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | California-3-21st Century classroom
California-21st Century classroom-CM/PM Management | 3 | CM/PM Management | California | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-10 | 2023/24 |  | PO1-220000000334 | 170210 | 170210 |  |  |  | 0 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 0% | Construction management services for California - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | California-3-21st Century classroom
California-21st Century classroom-CM/PM Management | 3 | CM/PM Management | California | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-11 | 2023/24 | 22-1057 | PO1-220000000334 | -170210 | -170210 |  |  |  | 0 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 0% | Construction management services for California - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS). Close-out PO. | California-3-21st Century classroom
California-21st Century classroom-CM/PM Management | 3 | CM/PM Management | California | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862, PO1-220000000334 | 0 | 9450 | 102578 | 2021-11-08 | 000000020325325 | 9450 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041101 | 19.27% | Construction management services for California - phase 3 & 4. This PO is only to pay invoice #102578 (Prof. service from 09/01-09/30/21), dated 09/30/21. This payment is supposed to be paid from PO1-22*334. The Board freezed payments to vendors and only allowed this invoice to be paid. Reduced PO1-22*334 by this invoice amount. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | California-3-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 9648.75 | 80804 | 2020-01-09 | 000000020055612 | 9648.75 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6712% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3193.75 | 80796 | 2020-01-14 | 000000020057268 | 3193.75 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.2222% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8378.75 | 81699 | 2020-01-14 | 000000020057268 | 8378.75 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.5828% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 10365 | 82273 | 2020-04-01 | 000000020085960 | 10365 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.721% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 7852.5 | 83068 | 2020-04-01 | 000000020085960 | 7852.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.5462% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 10562.5 | 84567 | 2020-04-15 | 000000020089466 | 10562.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.7347% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 10410 | 85320 | 2020-05-28 | 000000020100719 | 10410 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.7241% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 6977.5 | 86240 | 2020-06-17 | 000000020106117 | 6977.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.4853% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 14165 | 86864 | 2020-07-27 | 000000020116270 | 14165 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.9853% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 10209.09 | 88480 | 2020-08-17 | 000000020119773 | 10209.09 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.7101% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 9643.06 | 89359 | 2020-10-13 | 000000020134067 | 9643.06 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6708% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 9136.35 | 90460 | 2020-10-20 | 000000020136025 | 9136.35 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6355% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 10180.08 | 91321 | 2020-12-18 | 000000020151933 | 10180.08 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.7081% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 8801.11 | 91964 | 2020-12-18 | 000000020151933 | 8801.11 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6122% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 9411.62 | 92821 | 2021-02-08 | 000000020162981 | 9411.62 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.6547% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 6923.17 | 94011 | 2021-04-05 | 000000020177572 | 6923.17 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.4816% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 5862.68 | 94918 | 2021-04-16 | 000000020181024 | 5862.68 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.4078% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 6261.09 | 95700 | 2021-05-25 | 000000020192064 | 6261.09 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.4355% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 3630.82 | 96936 | 2021-05-25 | 000000020192064 | 3630.82 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0.2526% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-30 | 2021/22 |  | PO1-200000000640 | 0 | 25487.18 | 101444 | 2021-09-30 | 000000020276415 | 25487.18 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 1.773% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-30 | 2021/22 |  | PO1-200000000640 | 22 | 22 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Remaining balance in this PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Cedarlane | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-20 | 2021/22 | 2-4694 | PO1-200000000640 | -22 | -22 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051101 | 0% | Construction management services for Cedarlane - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Close-out PO. | Cedarlane-1-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000761 | 0 | 3840 | 81350 | 2020-01-14 | 000000020057268 | 3840 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0.8534% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000761 | 0 | 14560 | 82274 | 2020-04-01 | 000000020085958 | 14560 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 3.236% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000761 | 0 | 12640 | 83069 | 2020-04-01 | 000000020085958 | 12640 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.809% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000761 | 0 | 11535 | 84568 | 2020-04-15 | 000000020089466 | 11535 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.563% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000761 | 0 | 12325 | 85325 | 2020-05-28 | 000000020100719 | 12325 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.739% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000761 | 0 | 11885 | 86424 | 2020-06-17 | 000000020106117 | 11885 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.641% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000761 | 0 | 22090 | 86866 | 2020-07-27 | 000000020116270 | 22090 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 4.909% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000761 | 0 | 18080 | 88481 | 2020-08-17 | 000000020119773 | 18080 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 4.018% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000761 | 0 | 19265 | 89360 | 2020-10-13 | 000000020134067 | 19265 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 4.281% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000761 | 0 | 14080 | 90127 | 2020-10-20 | 000000020136025 | 14080 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 3.129% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-17 | 2020/21 |  | PO1-200000000761 | 0 | 23495 | 90702 | 2020-12-17 | 000000020151520 | 23495 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 5.221% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-17 | 2020/21 |  | PO1-200000000761 | 0 | 23450 | 91823 | 2020-12-17 | 000000020151520 | 23450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 5.211% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000761 | 0 | 27150 | 92822 | 2021-02-08 | 000000020162981 | 27150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 6.034% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000761 | 0 | 34605 | 94013 | 2021-04-05 | 000000020177572 | 34605 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 7.69% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000761 | 0 | 38455 | 94920 | 2021-04-16 | 000000020181024 | 38455 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 8.546% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-07 | 2020/21 |  | PO1-200000000761 | 0 | 46550 | 95725 | 2021-05-07 | 000000020187158 | 46550 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 10.34% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000761 | 0 | 41875 | 96938 | 2021-05-25 | 000000020192064 | 41875 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 9.306% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000761 | 0 | 37625 | 98319 | 2021-06-22 | 000000020200048 | 37625 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 8.361% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-08 | 2021/22 |  | PO1-200000000761 | 0 | 11520 | 100272 | 2021-09-08 | 000000020253624 | 11520 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.56% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000761 | 0 | 24960 | 98429 | 2021-09-09 | 000000020255187 | 24960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 5.547% | Construction management services for the District's bond projects as needed | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-10 | 2021/22 |  | PO1-200000000761 | 15 | 15 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Construction management services for the District's bond projects as needed. Remaining balance in this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-27 | 2021/22 | 2-4696 | PO1-200000000761 | -15 | -15 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Construction management services for the District's bond projects as needed. Close-out PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-02-28 | 2021/22 |  | PO1-220000000675, PO1-200000000761 | 0 | 25600 | 107249 | 2022-02-28 | 000000020430482 | 25600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 8.535% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-03-15 | 2021/22 |  | PO1-220000000675, PO1-200000000761 | 0 | 25320 | 108242 | 2022-03-15 | 000000020443751 | 25320 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 8.442% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-04-20 | 2021/22 |  | PO1-220000000675, PO1-200000000761 | 0 | 33410 | 109492 | 2022-04-20 | 000000020473559 | 33410 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 11.14% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-05-10 | 2021/22 |  | PO1-220000000675, PO1-200000000761 | 0 | 33005 | 110806 | 2022-05-10 | 000000020489703 | 33005 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 11% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-06-16 | 2021/22 |  | PO1-220000000675, PO1-200000000761 | 0 | 37325 | 111888 | 2022-06-16 | 000000020527704 | 37325 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 12.44% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-07-15 | 2021/22 |  | PO1-220000000675, PO1-200000000761 | 0 | 38000 | 112789 | 2022-07-15 | 000000020553439 | 38000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 12.67% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-08-26 | 2022/23 |  | PO1-220000000675, PO1-200000000761 | 0 | 35270 | 114508 | 2022-08-26 | 000000020601010 | 35270 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 11.76% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-10-04 | 2022/23 |  | PO1-220000000675, PO1-200000000761 | 0 | 32080 | 115420 | 2022-10-04 | 000000020653691 | 32080 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 10.7% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-10-13 | 2022/23 |  | PO1-220000000675, PO1-200000000761 | 0 | 32320 | 116895 | 2022-10-13 | 000000020673474 | 32320 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 10.78% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2022-11-21 | 2022/23 |  | PO1-220000000675, PO1-200000000761 | 0 | 7125 | 118103 | 2022-11-21 | 000000020734021 | 7125 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 2.376% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2023-01-12 | 2022/23 |  | PO1-220000000675, PO1-200000000761 | 0 | 480 | 1195330 | 2023-01-12 | 000000020803337 | 480 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0.16% | Construction management services for the District's bond projects as needed. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2023-04-24 | 2022/23 |  | PO1-220000000675, PO1-200000000761 | 65 | 65 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Construction management services for the District's bond projects as needed. Remaining balance in this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-02-09 | 2023-04-25 | 2022/23 | 22-4584 | PO1-220000000675, PO1-200000000761 | -65 | -65 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Construction management services for the District's bond projects as needed. Close-out PO | District Office-0-21st Century classroom
District Office-21st Century classroom-CM/PM Management | 0 | CM/PM Management | District Office | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-10-11 | 2028-07-11 | 2023/24 | 24-3290 | PO2W-240000000890, PO2W-220000000862, PO1-220000000334 | 1790290 | 1790290 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9851100 | 0% | Construction management services for the District Office - phase B (All sites, except for the 4 high schools). Addendum to PO1-22*334 & PO2W-22*862. | District Office-0-21st Century classroom
Fairgrove-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 1440 | 100653 | 2021-09-08 | 000000020253624 | 1440 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 3.704% | Construction management services for Fairgrove - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 5120 | 101514 | 2021-09-29 | 000000020275054 | 5120 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 13.17% | Construction management services for Fairgrove - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-10 | 2023/24 |  | PO1-220000000334 | 400194 | 400194 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 0% | Construction management services for Fairgrove - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-11 | 2023/24 | 22-1057 | PO1-220000000334 | -400194 | -400194 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 0% | Construction management services for Fairgrove - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS). Close-out PO. | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Fairgrove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862, PO1-220000000334 | 0 | 6450 | 102578 | 2021-11-08 | 000000020325325 | 6450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9091101 | 13.16% | Construction management services for Fairgrove - phase 3 & 4. This PO is only to pay invoice #102578 (Prof. service from 09/01-09/30/21), dated 09/30/21. This payment is supposed to be paid from PO1-22*334. The Board freezed payments to vendors and only allowed this invoice to be paid. Reduced PO1-22*334 by this invoice amount. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Fairgrove-4-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 7143.75 | 80804 | 2020-01-09 | 000000020055612 | 7143.75 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.4969% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3193.75 | 80796 | 2020-01-14 | 000000020057268 | 3193.75 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2222% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8131.25 | 81699 | 2020-01-14 | 000000020057268 | 8131.25 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5656% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8685 | 82273 | 2020-04-01 | 000000020085960 | 8685 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.6041% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 7692.5 | 83068 | 2020-04-01 | 000000020085960 | 7692.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5351% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 7442.5 | 84567 | 2020-04-15 | 000000020089466 | 7442.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5177% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9460 | 85320 | 2020-05-28 | 000000020100719 | 9460 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.658% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 7020 | 86240 | 2020-06-17 | 000000020106117 | 7020 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.4883% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 3765 | 86864 | 2020-07-27 | 000000020116270 | 3765 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2619% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 12733.4 | 88480 | 2020-08-17 | 000000020119773 | 12733.4 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.8857% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 12027.42 | 89359 | 2020-10-13 | 000000020134067 | 12027.42 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.8366% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 11395.42 | 90460 | 2020-10-20 | 000000020136025 | 11395.42 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.7927% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 12697.22 | 91321 | 2020-12-18 | 000000020151933 | 12697.22 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.8832% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 10977.3 | 91964 | 2020-12-18 | 000000020151933 | 10977.3 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.7636% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 11738.76 | 92821 | 2021-02-08 | 000000020162981 | 11738.76 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.8165% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 8635.01 | 94011 | 2021-04-05 | 000000020177572 | 8635.01 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.6006% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 7312.3 | 94918 | 2021-04-16 | 000000020181024 | 7312.3 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5086% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 7809.22 | 95700 | 2021-05-25 | 000000020192064 | 7809.22 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5432% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 4528.58 | 96936 | 2021-05-25 | 000000020192064 | 4528.58 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.315% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 9920 | 97857R1 | 2021-06-22 | 000000020200048 | 9920 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.69% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-08 | 2021/22 |  | PO1-200000000640 | 0 | 4160 | 100426 | 2021-09-08 | 000000020253624 | 4160 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2894% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000640 | 0 | 6240 | 98430 | 2021-09-09 | 000000020255187 | 6240 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.434% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-03-15 | 2021/22 |  | PO1-200000000640 | 0 | 4086.62 | 108239 | 2022-03-15 | 000000020443751 | 4086.62 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.2843% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-20 | 2021/22 |  | PO1-200000000640 | 0 | 7395 | 109812 | 2022-04-20 | 000000020473559 | 7395 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0.5144% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-21 | 2021/22 |  | PO1-200000000640 | 15 | 15 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Remaining balance in this PO. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-22 | 2021/22 | 2-4694 | PO1-200000000640 | -15 | -15 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9121101 | 0% | Construction management services for Grandview - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Close-out PO. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-04-21 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 1160 | 109813 | 2022-04-21 | 000000020474726 | 1160 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 0.1696% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-05-11 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 4930 | 110803 | 2022-05-11 | 000000020490794 | 4930 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 0.7208% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-05-20 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 44765 | 109867 | 2022-05-20 | 000000020498794 | 44765 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 6.545% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-11-28 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 9920 | 118100 | 2022-11-28 | 000000020738339 | 9920 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 1.45% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-01-17 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 12160 | 119529 | 2023-01-17 | 000000020807849 | 12160 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 1.778% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-01-18 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 14160 | 120458 | 2023-01-18 | 000000020810620 | 14160 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 2.07% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-03-07 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 24320 | 121878 | 2023-03-07 | 000000020889955 | 24320 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 3.556% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-03-22 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 11960 | 123129 | 2023-03-22 | 000000020916530 | 11960 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 1.749% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-05-10 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 28080 | 124386 | 2023-05-10 | 000000021004831 | 28080 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 4.105% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-06-12 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 23680 | 125813 | 2023-06-12 | 000000021061433 | 23680 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 3.462% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-06-28 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 26640 | 127728 | 2023-06-28 | 000000021097278 | 26640 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 3.895% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-07-17 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 14720 | 129343 | 2023-07-17 | 000000021128981 | 14720 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 2.152% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-07-18 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 31270 | 31270 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 0% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. Remaining balance in this PO, unfortunately; BEST finalized this amount. See XREQ 24*866 for the remaining balance of Grandview | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-07-19 | 2022/23 | 22-6151 | PO1-220000000753, PO1-200000000640 | -31270 | -31270 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 0% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-20*640. See XREQ 24*866 for the remaining balance of Grandview. Close-out this line item of the PO. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2023-09-21 | 2023/24 |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 0 | 6370 | 131161 | 2023-09-21 | 000000021224765 | 6370 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 10.74% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-22*753. This line item #1 (Grandview) was inadvertenly finalized in BEST. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2023-09-21 | 2023/24 |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 0 | 8360 | 132686 | 2023-09-21 | 000000021224765 | 8360 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 14.09% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-22*753. This line item #1 (Grandview) was inadvertenly finalized in BEST. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2024-01-22 | 2023/24 |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 0 | 7200 | 136008 | 2024-01-22 | 000000021420047 | 7200 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 12.14% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-22*753. This line item #1 (Grandview) was inadvertenly finalized in BEST. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2024-01-22 | 2023/24 |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 0 | 9300 | 137635 | 2024-01-22 | 000000021420047 | 9300 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 15.68% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-22*753. This line item #1 (Grandview) was inadvertenly finalized in BEST. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Grandview | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2025-07-11 | 2023/24 | 24-866 | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 40 | 40 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 0% | Amendment to construction management services for Grandview - phase 1 & 2. Addendum to PO1-22*753. This line item #1 (Grandview) was inadvertenly finalized in BEST. | Grandview-2-21st Century classroom
Grazide-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 800 | 100653 | 2021-09-08 | 000000020253624 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 2.058% | Construction management services for Grazide - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Grazide-3-21st Century classroom
Grazide-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 3960 | 101514 | 2021-09-29 | 000000020275054 | 3960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 10.19% | Construction management services for Grazide - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Grazide-3-21st Century classroom
Grazide-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-10 | 2023/24 |  | PO1-220000000334 | 196192 | 196192 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 0% | Construction management services for Grazide - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Grazide-3-21st Century classroom
Grazide-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-11 | 2023/24 | 22-1057 | PO1-220000000334 | -196192 | -196192 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 0% | Construction management services for Grazide - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS). Close-out PO. | Grazide-3-21st Century classroom
Grazide-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Grazide | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862, PO1-220000000334 | 0 | 5650 | 102578 | 2021-11-08 | 000000020325325 | 5650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9131101 | 11.52% | Construction management services for Grazide - phase 3 & 4. This PO is only to pay invoice #102578 (Prof. service from 09/01-09/30/21), dated 09/30/21. This payment is supposed to be paid from PO1-22*334. The Board freezed payments to vendors and only allowed this invoice to be paid. Reduced PO1-22*334 by this invoice amount. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Grazide-3-21st Century classroom
La Puente HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | La Puente HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-07-13 | 2022/23 |  | PO2W-230000003838 | 0 | 21920 | 129348 | 2023-07-13 | 000000021124116 | 21920 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 100% | Construction management services for La Puente HS. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | La Puente HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-07-14 | 2022/23 |  | PO2W-230000003838 | 149480 | 149480 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 0% | Construction management services for La Puente HS. Remaining balance in this PO. Po did not roll-over into 2023/24 school year. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | La Puente HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-08-03 | 2022/23 | 23-8210 | PO2W-230000003838 | -149480 | -149480 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 0% | Construction management services for La Puente HS. Close-out PO. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | La Puente HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2023-09-21 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 28670 | 130959 | 2023-09-21 | 000000021224765 | 28670 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 4.32% | Construction management services for La Puente HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | La Puente HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2023-09-21 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 16660 | 132694 | 2023-09-21 | 000000021224765 | 16660 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 2.51% | Construction management services for La Puente HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | La Puente HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2023-11-17 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 12760 | 134283 | 2023-11-17 | 000000021328304 | 12760 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 1.923% | Construction management services for La Puente HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | La Puente HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2024-01-19 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 19840 | 136011 | 2024-01-19 | 000000021417635 | 19840 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 2.989% | Construction management services for La Puente HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | La Puente HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2027-12-09 | 2023/24 | 24-1466 | PO2W-240000000481, PO2W-230000003838 | 71550 | 71550 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9401101 | 0% | Construction management services for La Puente HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | La Puente HS-5-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 8571.25 | 80804 | 2020-01-09 | 000000020055612 | 8571.25 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.5962% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3268.75 | 80796 | 2020-01-14 | 000000020057268 | 3268.75 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2274% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 9428.75 | 81699 | 2020-01-14 | 000000020057268 | 9428.75 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.6559% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8525 | 82273 | 2020-04-01 | 000000020085960 | 8525 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.593% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8872.5 | 83068 | 2020-04-01 | 000000020085960 | 8872.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.6172% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 12647.5 | 84567 | 2020-04-15 | 000000020089466 | 12647.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.8797% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9337.5 | 85320 | 2020-05-28 | 000000020100719 | 9337.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.6495% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 9947.5 | 86240 | 2020-06-17 | 000000020106117 | 9947.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.6919% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 13287.5 | 86864 | 2020-07-27 | 000000020116270 | 13287.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.9243% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 5953.78 | 88480 | 2020-08-17 | 000000020119773 | 5953.78 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.4141% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 5623.68 | 89359 | 2020-10-13 | 000000020134067 | 5623.68 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.3912% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 5328.17 | 90460 | 2020-10-20 | 000000020136025 | 5328.17 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.3706% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 5936.86 | 91321 | 2020-12-18 | 000000020151933 | 5936.86 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.413% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 5132.67 | 91964 | 2020-12-18 | 000000020151933 | 5132.67 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.357% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 5488.71 | 92821 | 2021-02-08 | 000000020162981 | 5488.71 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.3818% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 4037.49 | 94011 | 2021-04-05 | 000000020177572 | 4037.49 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2808% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 3419.03 | 94918 | 2021-04-16 | 000000020181024 | 3419.03 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2378% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 3651.37 | 95700 | 2021-05-25 | 000000020192064 | 3651.37 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.254% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 2117.43 | 96936 | 2021-05-25 | 000000020192064 | 2117.43 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.1473% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-30 | 2021/22 |  | PO1-200000000640 | 0 | 11952.82 | 101444 | 2021-09-30 | 000000020276415 | 11952.82 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.8314% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-10-18 | 2021/22 |  | PO1-200000000640 | 0 | 2897.99 | 102576 | 2021-10-18 | 000000020301535 | 2897.99 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0.2016% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-19 | 2021/22 |  | PO1-200000000640 | 25.75 | 25.75 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Remaining balance in this PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Los Altos ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-20 | 2021/22 | 2-4694 | PO1-200000000640 | -25.75 | -25.75 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 0% | Construction management services for Los Altos ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Close-out PO. | Los Altos ES-2-21st Century classroom
Los Altos HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Los Altos HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-07-11 | 2022/23 |  | PO2W-230000003838 | 171400 | 171400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9411101 | 0% | Construction management services for Los Altos HS. Remaining balance in this PO. Po did not roll-over into 2023/24 school year. | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Los Altos HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-08-03 | 2022/23 | 23-8210 | PO2W-230000003838 | -171400 | -171400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9411101 | 0% | Construction management services for Los Altos HS. Close-out PO. | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Los Altos HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2024-01-18 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 14210 | 137829 | 2024-01-18 | 000000021415279 | 14210 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9411101 | 2.141% | Construction management services for Los Altos HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Los Altos HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2024-01-19 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 2240 | 136011 | 2024-01-19 | 000000021417635 | 2240 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9411101 | 0.3375% | Construction management services for Los Altos HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Los Altos HS-5-21st Century classroom
Los Altos HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Los Altos HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2027-12-09 | 2023/24 | 24-1466 | PO2W-240000000481, PO2W-230000003838 | 154950 | 154950 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9411101 | 0% | Construction management services for Los Altos HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Los Altos HS-5-21st Century classroom
Los Molinos-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 960 | 100653 | 2021-09-08 | 000000020253624 | 960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 2.469% | Construction management services for Los Molinos - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 4280 | 101514 | 2021-09-29 | 000000020275054 | 4280 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 11.01% | Construction management services for Los Molinos - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-10 | 2023/24 |  | PO1-220000000334 | 270840 | 270840 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 0% | Construction management services for Los Molinos - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-11 | 2023/24 | 22-1057 | PO1-220000000334 | -270840 | -270840 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 0% | Construction management services for Los Molinos - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS). Close-out PO. | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Los Molinos | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862, PO1-220000000334 | 0 | 5650 | 102578 | 2021-11-08 | 000000020325325 | 5650 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9201101 | 11.52% | Construction management services for Los Molinos - phase 3 & 4. This PO is only to pay invoice #102578 (Prof. service from 09/01-09/30/21), dated 09/30/21. This payment is supposed to be paid from PO1-22*334. The Board freezed payments to vendors and only allowed this invoice to be paid. Reduced PO1-22*334 by this invoice amount. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Los Molinos-4-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 9691.25 | 80804 | 2020-01-09 | 000000020055612 | 9691.25 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.6741% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3193.75 | 80796 | 2020-01-14 | 000000020057268 | 3193.75 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.2222% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8433.75 | 81699 | 2020-01-14 | 000000020057268 | 8433.75 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.5866% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 12485 | 82273 | 2020-04-01 | 000000020085960 | 12485 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.8684% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 7932.5 | 83068 | 2020-04-01 | 000000020085960 | 7932.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.5518% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 8200 | 84567 | 2020-04-15 | 000000020089466 | 8200 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.5704% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 12690 | 85320 | 2020-05-28 | 000000020100719 | 12690 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.8827% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 13470 | 86240 | 2020-06-17 | 000000020106117 | 13470 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.937% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 15197.5 | 86864 | 2020-07-27 | 000000020116270 | 15197.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.057% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 16815.75 | 88480 | 2020-08-17 | 000000020119773 | 16815.75 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.17% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 15883.43 | 89359 | 2020-10-13 | 000000020134067 | 15883.43 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.105% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 15048.8 | 90460 | 2020-10-20 | 000000020136025 | 15048.8 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.047% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 16767.97 | 91321 | 2020-12-18 | 000000020151933 | 16767.97 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.166% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 14496.63 | 91964 | 2020-12-18 | 000000020151933 | 14496.63 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.008% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 15502.22 | 92821 | 2021-02-08 | 000000020162981 | 15502.22 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.078% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 11403.41 | 94011 | 2021-04-05 | 000000020177572 | 11403.41 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.7932% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 9656.64 | 94918 | 2021-04-16 | 000000020181024 | 9656.64 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.6717% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 10312.87 | 95700 | 2021-05-25 | 000000020192064 | 10312.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.7174% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 5980.44 | 96936 | 2021-05-25 | 000000020192064 | 5980.44 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.416% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 3520 | 97857R1 | 2021-06-22 | 000000020200048 | 3520 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.2448% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000640 | 0 | 160 | 98430 | 2021-09-09 | 000000020255187 | 160 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.01113% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-10-18 | 2021/22 |  | PO1-200000000640 | 0 | 3182.01 | 102576 | 2021-10-18 | 000000020301535 | 3182.01 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.2213% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-12-13 | 2021/22 |  | PO1-200000000640 | 0 | 1280 | 104806 | 2021-12-13 | 000000020358822 | 1280 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.08904% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-01-24 | 2021/22 |  | PO1-200000000640 | 0 | 13920 | 105896 | 2022-01-24 | 000000020395771 | 13920 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0.9683% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-02-11 | 2021/22 |  | PO1-200000000640 | 0 | 19869.83 | 106727 | 2022-02-11 | 000000020412897 | 19869.83 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 1.382% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-19 | 2021/22 |  | PO1-200000000640 | 85.25 | 85.25 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Mesa Robles | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-20 | 2021/22 | 2-4694 | PO1-200000000640 | -85.25 | -85.25 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221101 | 0% | Construction management services for Mesa Robles - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Close-out PO. | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 8556.25 | 80804 | 2020-01-09 | 000000020055612 | 8556.25 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.5952% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3268.75 | 80796 | 2020-01-14 | 000000020057268 | 3268.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.2274% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 9568.75 | 81699 | 2020-01-14 | 000000020057268 | 9568.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.6656% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 9765 | 82273 | 2020-04-01 | 000000020085960 | 9765 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.6792% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 10195 | 83068 | 2020-04-01 | 000000020085960 | 10195 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.7092% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 13455 | 84567 | 2020-04-15 | 000000020089466 | 13455 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.9359% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9450 | 85320 | 2020-05-28 | 000000020100719 | 9450 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.6573% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 10027.5 | 86240 | 2020-06-17 | 000000020106117 | 10027.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.6975% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 10887.5 | 86864 | 2020-07-27 | 000000020116270 | 10887.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.7573% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 6349.45 | 88480 | 2020-08-17 | 000000020119773 | 6349.45 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.4417% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 5997.42 | 89359 | 2020-10-13 | 000000020134067 | 5997.42 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.4172% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 5682.27 | 90460 | 2020-10-20 | 000000020136025 | 5682.27 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.3953% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 6331.41 | 91321 | 2020-12-18 | 000000020151933 | 6331.41 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.4404% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 5473.78 | 91964 | 2020-12-18 | 000000020151933 | 5473.78 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.3808% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 5853.48 | 92821 | 2021-02-08 | 000000020162981 | 5853.48 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.4072% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 4305.81 | 94011 | 2021-04-05 | 000000020177572 | 4305.81 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.2995% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 3646.24 | 94918 | 2021-04-16 | 000000020181024 | 3646.24 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.2536% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 3894.03 | 95700 | 2021-05-25 | 000000020192064 | 3894.03 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.2709% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 2258.15 | 96936 | 2021-05-25 | 000000020192064 | 2258.15 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.1571% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-02-11 | 2021/22 |  | PO1-200000000640 | 0 | 2315.17 | 106727 | 2022-02-11 | 000000020412897 | 2315.17 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.161% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-03-15 | 2021/22 |  | PO1-200000000640 | 0 | 13530.29 | 108239 | 2022-03-15 | 000000020443751 | 13530.29 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0.9412% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-19 | 2021/22 |  | PO1-200000000640 | 19.75 | 19.75 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Remaining balance in this PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Nelson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-20 | 2021/22 | 2-4694 | PO1-200000000640 | -19.75 | -19.75 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 0% | Construction management services for Nelson - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Close-out PO. | Nelson-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 7376.25 | 80804 | 2020-01-09 | 000000020055612 | 7376.25 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5131% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3231.25 | 80796 | 2020-01-14 | 000000020057268 | 3231.25 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.2248% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8163.75 | 81699 | 2020-01-14 | 000000020057268 | 8163.75 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5679% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 9405 | 82273 | 2020-04-01 | 000000020085960 | 9405 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6542% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8072.5 | 83068 | 2020-04-01 | 000000020085960 | 8072.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5615% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 7480 | 84567 | 2020-04-15 | 000000020089466 | 7480 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5203% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9737.5 | 85320 | 2020-05-28 | 000000020100719 | 9737.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6773% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 8587.5 | 86240 | 2020-06-17 | 000000020106117 | 8587.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5973% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 6685 | 86864 | 2020-07-27 | 000000020116270 | 6685 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.465% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 10803.44 | 88480 | 2020-08-17 | 000000020119773 | 10803.44 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.7515% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 10204.46 | 89359 | 2020-10-13 | 000000020134067 | 10204.46 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.7098% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 9668.25 | 90460 | 2020-10-20 | 000000020136025 | 9668.25 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6725% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 10772.74 | 91321 | 2020-12-18 | 000000020151933 | 10772.74 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.7493% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 9313.5 | 91964 | 2020-12-18 | 000000020151933 | 9313.5 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6478% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 9959.55 | 92821 | 2021-02-08 | 000000020162981 | 9959.55 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6928% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 7326.23 | 94011 | 2021-04-05 | 000000020177572 | 7326.23 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.5096% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 6204 | 94918 | 2021-04-16 | 000000020181024 | 6204 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.4315% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 6625.6 | 95700 | 2021-05-25 | 000000020192064 | 6625.6 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.4609% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 3842.19 | 96936 | 2021-05-25 | 000000020192064 | 3842.19 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.2673% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 5920 | 97857R1 | 2021-06-22 | 000000020200048 | 5920 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.4118% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-08 | 2021/22 |  | PO1-200000000640 | 0 | 21440 | 100426 | 2021-09-08 | 000000020253624 | 21440 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 1.491% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000640 | 0 | 9760 | 98430 | 2021-09-09 | 000000020255187 | 9760 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0.6789% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-10 | 2021/22 |  | PO1-200000000640 | -10125.71 | -10125.71 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. JVER 22*421: Exp trf to Workman ES. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-15 | 2021/22 |  | PO1-200000000640 | 10142.46 | 0 |  |  |  | -10142.46 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | -0.7055% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. JVER 22*421: Exp trf to Workman ES. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-20 | 2021/22 | 2-4694 | PO1-200000000640 | -16.75 | -16.75 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241101 | 0% | Construction management services for Newton - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. JVER 22*421: Exp trf to Workman ES. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-04-21 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 3335 | 109813 | 2022-04-21 | 000000020474726 | 3335 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 0.4876% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-05-11 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 4495 | 110803 | 2022-05-11 | 000000020490794 | 4495 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 0.6572% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-05-20 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 26330 | 109876 | 2022-05-20 | 000000020498794 | 26330 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 3.85% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-06-17 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 24000 | 111886 | 2022-06-17 | 000000020529345 | 24000 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 3.509% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-07-18 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 26400 | 112769 | 2022-07-18 | 000000020554415 | 26400 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 3.86% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-08-18 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 20400 | 114381 | 2022-08-18 | 000000020587950 | 20400 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 2.983% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-10-06 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 25200 | 115412 | 2022-10-06 | 000000020661315 | 25200 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 3.684% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-11-28 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 29360 | 118100 | 2022-11-28 | 000000020738339 | 29360 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 4.293% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-12-06 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 24000 | 116892 | 2022-12-06 | 000000020752786 | 24000 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 3.509% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-01-17 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 24000 | 119529 | 2023-01-17 | 000000020807849 | 24000 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 3.509% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-01-18 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 14000 | 120458 | 2023-01-18 | 000000020810620 | 14000 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 2.047% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-03-07 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 3100 | 121878 | 2023-03-07 | 000000020889955 | 3100 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 0.4532% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-03-22 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 23120 | 123129 | 2023-03-22 | 000000020916530 | 23120 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 3.38% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Newton-21st Century classroom-CM/PM Management | 1 | CM/PM Management | Newton | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2025-07-11 | 2023/24 | 22-6151 | PO1-220000000753, PO1-200000000640 | 25 | 25 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 0% | Amendment to construction management services for Newton - phase 1 & 2. Addendun to PO1-20*640. | Newton-1-21st Century classroom
Orange Grove-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 800 | 100653 | 2021-09-08 | 000000020253624 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 2.058% | Construction management services for Orange Grove - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 2960 | 101514 | 2021-09-29 | 000000020275054 | 2960 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 7.613% | Construction management services for Orange Grove - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-10 | 2023/24 |  | PO1-220000000334 | 197337 | 197337 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 0% | Construction management services for Orange Grove - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-11 | 2023/24 | 22-1057 | PO1-220000000334 | -197337 | -197337 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 0% | Construction management services for Orange Grove - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS). Close-out PO. | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-CM/PM Management | 3 | CM/PM Management | Orange Grove | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862, PO1-220000000334 | 0 | 5505 | 102578 | 2021-11-08 | 000000020325325 | 5505 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9251101 | 11.23% | Construction management services for Orange Grove - phase 3 & 4. This PO is only to pay invoice #102578 (Prof. service from 09/01-09/30/21), dated 09/30/21. This payment is supposed to be paid from PO1-22*334. The Board freezed payments to vendors and only allowed this invoice to be paid. Reduced PO1-22*334 by this invoice amount. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Orange Grove-3-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 8306.25 | 80804 | 2020-01-09 | 000000020055612 | 8306.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5778% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3231.25 | 80796 | 2020-01-14 | 000000020057268 | 3231.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.2248% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 7703.75 | 81699 | 2020-01-14 | 000000020057268 | 7703.75 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5359% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8765 | 82273 | 2020-04-01 | 000000020085960 | 8765 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.6097% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 7457.5 | 83068 | 2020-04-01 | 000000020085960 | 7457.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5187% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 7320 | 84567 | 2020-04-15 | 000000020089466 | 7320 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5092% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9337.5 | 85320 | 2020-05-28 | 000000020100719 | 9337.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.6495% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 6822.5 | 86240 | 2020-06-17 | 000000020106117 | 6822.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.4746% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 3765 | 86864 | 2020-07-27 | 000000020116270 | 3765 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.2619% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 8001.67 | 88480 | 2020-08-17 | 000000020119773 | 8001.67 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5566% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 7558.04 | 89359 | 2020-10-13 | 000000020134067 | 7558.04 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5257% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 7160.88 | 90460 | 2020-10-20 | 000000020136025 | 7160.88 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.4981% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 7978.94 | 91321 | 2020-12-18 | 000000020151933 | 7978.94 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.555% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 6898.14 | 91964 | 2020-12-18 | 000000020151933 | 6898.14 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.4798% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 7376.64 | 92821 | 2021-02-08 | 000000020162981 | 7376.64 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5131% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 5426.24 | 94011 | 2021-04-05 | 000000020177572 | 5426.24 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.3774% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 4595.05 | 94918 | 2021-04-16 | 000000020181024 | 4595.05 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.3196% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 4907.32 | 95700 | 2021-05-25 | 000000020192064 | 4907.32 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.3413% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 2845.76 | 96936 | 2021-05-25 | 000000020192064 | 2845.76 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.1979% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 5760 | 97857R1 | 2021-06-22 | 000000020200048 | 5760 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.4007% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-08 | 2021/22 |  | PO1-200000000640 | 0 | 1600 | 100426 | 2021-09-08 | 000000020253624 | 1600 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.1113% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-09-09 | 2020/21 |  | PO1-200000000640 | 0 | 8160 | 98430 | 2021-09-09 | 000000020255187 | 8160 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.5676% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-20 | 2021/22 |  | PO1-200000000640 | 0 | 4470.07 | 109812 | 2022-04-20 | 000000020473559 | 4470.07 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0.3109% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-21 | 2021/22 |  | PO1-200000000640 | 3.5 | 3.5 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Remaining balance in this PO. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-22 | 2021/22 | 2-4694 | PO1-200000000640 | -3.5 | -3.5 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9301101 | 0% | Construction management services for Sparks MS - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Close-out PO. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-04-21 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 2646.25 | 109813 | 2022-04-21 | 000000020474726 | 2646.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 0.3869% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-05-11 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 4640 | 110803 | 2022-05-11 | 000000020490794 | 4640 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 0.6784% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-05-20 | 2021/22 |  | PO1-220000000753, PO1-200000000640 | 0 | 47640 | 109866 | 2022-05-20 | 000000020498794 | 47640 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 6.965% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2022-11-28 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 10080 | 118100 | 2022-11-28 | 000000020738339 | 10080 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 1.474% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-01-17 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 13280 | 119529 | 2023-01-17 | 000000020807849 | 13280 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 1.942% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-01-18 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 14320 | 120458 | 2023-01-18 | 000000020810620 | 14320 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 2.094% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-03-07 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 23140 | 121878 | 2023-03-07 | 000000020889955 | 23140 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 3.383% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-03-22 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 12040 | 123129 | 2023-03-22 | 000000020916530 | 12040 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 1.76% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-05-10 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 27680 | 124386 | 2023-05-10 | 000000021004831 | 27680 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 4.047% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-06-12 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 23360 | 125813 | 2023-06-12 | 000000021061433 | 23360 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 3.415% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-06-28 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 26640 | 127728 | 2023-06-28 | 000000021097278 | 26640 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 3.895% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-07-17 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 0 | 14240 | 129343 | 2023-07-17 | 000000021128981 | 14240 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 2.082% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-07-18 | 2022/23 |  | PO1-220000000753, PO1-200000000640 | 28058.75 | 28058.75 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 0% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. Remaining balance in this PO, unfortunately; BEST finalized this amount. See XREQ 24*866 for the remaining balance of Sparks MS | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2022-04-05 | 2023-07-19 | 2022/23 | 22-6151 | PO1-220000000753, PO1-200000000640 | -28058.75 | -28058.75 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 0% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-20*640. See XREQ 24*866 for the remaining balance of Sparks MS. Close-out this line item of the PO. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2023-09-21 | 2023/24 |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 0 | 8400 | 131161 | 2023-09-21 | 000000021224765 | 8400 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 14.16% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-22*753. This line item #3 (Sparks MS) was inadvertenly finalized in BEST. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2023-09-21 | 2023/24 |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 0 | 7160 | 132686 | 2023-09-21 | 000000021224765 | 7160 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 12.07% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-22*753. This line item #3 (Sparks MS) was inadvertenly finalized in BEST. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2024-01-22 | 2023/24 |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 0 | 2400 | 136008 | 2024-01-22 | 000000021420047 | 2400 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 4.045% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-22*753. This line item #3 (Sparks MS) was inadvertenly finalized in BEST. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2024-01-22 | 2023/24 |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 0 | 10050 | 137635 | 2024-01-22 | 000000021420047 | 10050 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 16.94% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-22*753. This line item #3 (Sparks MS) was inadvertenly finalized in BEST. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Sparks MS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-07-13 | 2025-07-11 | 2023/24 | 24-866 | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 48.75 | 48.75 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 0% | Amendment to construction management services for Sparks MS - phase 1 & 2. Addendum to PO1-22*753. This line item #3 (Sparks MS) was inadvertenly finalized in BEST. | Sparks MS-2-21st Century classroom
Stimson-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 480 | 100653 | 2021-09-08 | 000000020253624 | 480 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 1.235% | Construction management services for Stimson - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Stimson-4-21st Century classroom
Stimson-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 4800 | 101514 | 2021-09-29 | 000000020275054 | 4800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 12.35% | Construction management services for Stimson - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Stimson-4-21st Century classroom
Stimson-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-10 | 2023/24 |  | PO1-220000000334 | 64678 | 64678 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 0% | Construction management services for Stimson - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Stimson-4-21st Century classroom
Stimson-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-11 | 2023/24 | 22-1057 | PO1-220000000334 | -64678 | -64678 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 0% | Construction management services for Stimson - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS). Close-out PO. | Stimson-4-21st Century classroom
Stimson-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Stimson | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862, PO1-220000000334 | 0 | 5170 | 102578 | 2021-11-08 | 000000020325325 | 5170 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 8021101 | 10.54% | Construction management services for Stimson - phase 3 & 4. This PO is only to pay invoice #102578 (Prof. service from 09/01-09/30/21), dated 09/30/21. This payment is supposed to be paid from PO1-22*334. The Board freezed payments to vendors and only allowed this invoice to be paid. Reduced PO1-22*334 by this invoice amount. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Stimson-4-21st Century classroom
Sunset-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-08 | 2021/22 |  | PO1-220000000334 | 0 | 800 | 100653 | 2021-09-08 | 000000020253624 | 800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 2.058% | Construction management services for Sunset - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Sunset-4-21st Century classroom
Sunset-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2021-09-29 | 2021/22 |  | PO1-220000000334 | 0 | 1600 | 101514 | 2021-09-29 | 000000020275054 | 1600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 4.115% | Construction management services for Sunset - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Sunset-4-21st Century classroom
Sunset-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-10 | 2023/24 |  | PO1-220000000334 | 198697 | 198697 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 0% | Construction management services for Sunset - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Sunset-4-21st Century classroom
Sunset-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-07-01 | 2023-10-11 | 2023/24 | 22-1057 | PO1-220000000334 | -198697 | -198697 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 0% | Construction management services for Sunset - phase 3 & 4. This PO includes allowances of $40,000.00. See PO2W-22*862 for payment on invoice #102578. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS). Close-out PO. | Sunset-4-21st Century classroom
Sunset-21st Century classroom-CM/PM Management | 4 | CM/PM Management | Sunset | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2021-11-02 | 2021-11-08 | 2021/22 | 22-2878 | PO2W-220000000862, PO1-220000000334 | 0 | 5505 | 102578 | 2021-11-08 | 000000020325325 | 5505 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9311101 | 11.23% | Construction management services for Sunset - phase 3 & 4. This PO is only to pay invoice #102578 (Prof. service from 09/01-09/30/21), dated 09/30/21. This payment is supposed to be paid from PO1-22*334. The Board freezed payments to vendors and only allowed this invoice to be paid. Reduced PO1-22*334 by this invoice amount. Also see PO2W-24*890 for changing the scope of work to include management services for all schools (exclude 4 HS) | Sunset-4-21st Century classroom
Wilson HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Wilson HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-07-11 | 2022/23 |  | PO2W-230000003838 | 171400 | 171400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9421101 | 0% | Construction management services for Wilson HS. Remaining balance in this PO. Po did not roll-over into 2023/24 school year. | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Wilson HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-08-03 | 2022/23 | 23-8210 | PO2W-230000003838 | -171400 | -171400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9421101 | 0% | Construction management services for Wilson HS. Close-out PO. | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Wilson HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2024-01-18 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 10005 | 137829 | 2024-01-18 | 000000021415279 | 10005 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9421101 | 1.508% | Construction management services for Wilson HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Wilson HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2024-01-19 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 4640 | 136011 | 2024-01-19 | 000000021417635 | 4640 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9421101 | 0.6991% | Construction management services for Wilson HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Wilson HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2027-12-09 | 2023/24 | 24-1466 | PO2W-240000000481, PO2W-230000003838 | 156755 | 156755 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9421101 | 0% | Construction management services for Wilson HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Wilson HS-5-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-09 | 2019/20 |  | PO1-200000000640 | 0 | 9866.25 | 80804 | 2020-01-09 | 000000020055612 | 9866.25 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.6863% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 3268.75 | 80796 | 2020-01-14 | 000000020057268 | 3268.75 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.2274% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-01-14 | 2019/20 |  | PO1-200000000640 | 0 | 8071.25 | 81699 | 2020-01-14 | 000000020057268 | 8071.25 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5614% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8365 | 82273 | 2020-04-01 | 000000020085960 | 8365 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5819% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-01 | 2019/20 |  | PO1-200000000640 | 0 | 8765 | 83068 | 2020-04-01 | 000000020085960 | 8765 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.6097% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-04-15 | 2019/20 |  | PO1-200000000640 | 0 | 12972.5 | 84567 | 2020-04-15 | 000000020089466 | 12972.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.9024% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-05-28 | 2019/20 |  | PO1-200000000640 | 0 | 9657.5 | 85320 | 2020-05-28 | 000000020100719 | 9657.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.6718% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-06-17 | 2019/20 |  | PO1-200000000640 | 0 | 9947.5 | 86240 | 2020-06-17 | 000000020106117 | 9947.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.6919% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-07-27 | 2019/20 |  | PO1-200000000640 | 0 | 12327.5 | 86864 | 2020-07-27 | 000000020116270 | 12327.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.8575% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-08-17 | 2020/21 |  | PO1-200000000640 | 0 | 8313.42 | 88480 | 2020-08-17 | 000000020119773 | 8313.42 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5783% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-13 | 2020/21 |  | PO1-200000000640 | 0 | 7852.49 | 89359 | 2020-10-13 | 000000020134067 | 7852.49 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5462% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-10-20 | 2020/21 |  | PO1-200000000640 | 0 | 7439.86 | 90460 | 2020-10-20 | 000000020136025 | 7439.86 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5175% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 8289.78 | 91321 | 2020-12-18 | 000000020151933 | 8289.78 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5766% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2020-12-18 | 2020/21 |  | PO1-200000000640 | 0 | 7166.87 | 91964 | 2020-12-18 | 000000020151933 | 7166.87 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.4985% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-02-08 | 2020/21 |  | PO1-200000000640 | 0 | 7664.02 | 92821 | 2021-02-08 | 000000020162981 | 7664.02 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.5331% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-05 | 2020/21 |  | PO1-200000000640 | 0 | 5637.64 | 94011 | 2021-04-05 | 000000020177572 | 5637.64 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.3921% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-04-16 | 2020/21 |  | PO1-200000000640 | 0 | 4774.06 | 94918 | 2021-04-16 | 000000020181024 | 4774.06 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.3321% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 5098.5 | 95700 | 2021-05-25 | 000000020192064 | 5098.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.3546% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-05-25 | 2020/21 |  | PO1-200000000640 | 0 | 2956.63 | 96936 | 2021-05-25 | 000000020192064 | 2956.63 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.2057% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2021-06-22 | 2020/21 |  | PO1-200000000640 | 0 | 480 | 97857R1 | 2021-06-22 | 000000020200048 | 480 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.03339% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-03-15 | 2021/22 |  | PO1-200000000640 | 0 | 5583.09 | 108239 | 2022-03-15 | 000000020443751 | 5583.09 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.3884% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-20 | 2021/22 |  | PO1-200000000640 | 0 | 4483.68 | 109812 | 2022-04-20 | 000000020473559 | 4483.68 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.3119% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-21 | 2021/22 |  | PO1-200000000640 | 0 | 10125.71 |  |  |  | 10125.71 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.7043% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. JVER 22*421: Exp trf from Newton. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-21 | 2021/22 |  | PO1-200000000640 | 0 | 16.75 |  |  |  | 16.75 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0.001165% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. JVER 22*421: Exp trf from Newton. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-21 | 2021/22 |  | PO1-200000000640 | 83.25 | 83.25 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-CM/PM Management | 2 | CM/PM Management | Workman ES | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2019-10-10 | 2022-04-21 | 2021/22 | 2-4694 | PO1-200000000640 | -83.25 | -83.25 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 0% | Construction management services for Workman ES - phase 1 & 2. This PO includes allowances of $100,000.00. See PO1-22*753 for additional payments to Cumming for the following sites: Grandview, Newton, and Sparks MS. Close-out PO. | Workman ES-2-21st Century classroom
Workman HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Workman HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-07-11 | 2022/23 |  | PO2W-230000003838 | 171400 | 171400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 0% | Construction management services for Workman HS. Remaining balance in this PO. Po did not roll-over into 2023/24 school year. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Workman HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-05-17 | 2023-08-03 | 2022/23 | 23-8210 | PO2W-230000003838 | -171400 | -171400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 0% | Construction management services for Workman HS. Close-out PO. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Workman HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2023-09-21 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 27780 | 132694 | 2023-09-21 | 000000021224765 | 27780 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 4.186% | Construction management services for Workman HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Workman HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2023-11-17 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 61520 | 134283 | 2023-11-17 | 000000021328304 | 61520 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 9.27% | Construction management services for Workman HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Workman HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2024-01-18 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 3480 | 137829 | 2024-01-18 | 000000021415279 | 3480 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 0.5243% | Construction management services for Workman HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Workman HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2024-01-19 | 2023/24 |  | PO2W-240000000481, PO2W-230000003838 | 0 | 11600 | 136011 | 2024-01-19 | 000000021417635 | 11600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 1.748% | Construction management services for Workman HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-CM/PM Management | 5 | CM/PM Management | Workman HS | 21st Century classroom | Cumming Construction Management, Inc. | Construction mgmt services | 2023-08-04 | 2027-12-09 | 2023/24 | 24-1466 | PO2W-240000000481, PO2W-230000003838 | 67020 | 67020 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9431101 | 0% | Construction management services for Workman HS. Addendum to PO2W-23*3838 that did not roll-over into 2023/24 school year. | Workman HS-5-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | David M. Bertino Manufacturing, Inc. | Furniture | 2021-11-09 | 2022-01-11 | 2021/22 | 22-3033 | PO2W-220000000940 | 0 | 3858.78 | J21117-2519 | 2022-01-11 | 000000020381073 | 3858.78 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 100% | Custom made rolling instrument storage cabinets for Cedarlane. Total cabinets: 2 | Cedarlane-1-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | David M. Bertino Manufacturing, Inc. | Furniture | 2022-11-09 | 2023-08-10 | 2022/23 | 23-3880 | PO3W-230000001317 | 0 | 7480 | J23039-199 | 2023-08-10 | 000000021161313 | 7480 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 31.53% | Custom made rolling instrument storage cabinets for Grandview. Delivery fee: $500.00. Total cabinets: 3 | Grandview-2-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | David M. Bertino Manufacturing, Inc. | Furniture | 2022-11-09 | 2023-08-10 | 2022/23 | 23-3880 | PO3W-230000001317 | 0 | 7446 | J23039-199 | 2023-08-10 | 000000021161313 | 7446 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 31.38% | Custom made rolling instrument storage cabinets for Newton. Delivery fee: $500.00. Total cabinets: 3 | Newton-1-21st Century classroom
Sparks MS-21st Century classroom-FF & E | 2 | FF & E | Sparks MS | 21st Century classroom | David M. Bertino Manufacturing, Inc. | Furniture | 2022-11-09 | 2023-08-10 | 2022/23 | 23-3880 | PO3W-230000001317 | 0 | 8800 | J23039-199 | 2023-08-10 | 000000021161313 | 8800 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 37.09% | Custom made rolling instrument storage cabinets & a sheet music cabinet for Sparks MS. Delivery fee: $500.00. Total cabinets: 4 | Sparks MS-2-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Dell Marketing Lp | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 9695.45 | 10513843591 | 2021-08-27 | 000000020245275 | 9695.45 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 13.33% | PowerSwitch N2200-ON OS6 for Cedarlane. Total power switch: 2 | Cedarlane-1-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Dell Marketing Lp | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 9695.44 | 10513843591 | 2021-08-27 | 000000020245275 | 9695.44 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 13.33% | PowerSwitch N2200-ON OS6 for Los Altos ES. Total power switch: 2 | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Dell Marketing Lp | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 33934.03 | 10513843591 | 2021-08-27 | 000000020245275 | 33934.03 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 46.67% | PowerSwitch N2200-ON OS6 for Mesa Robles. Total power switch: 7 | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Dell Marketing Lp | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 9695.44 | 10513843591 | 2021-08-27 | 000000020245275 | 9695.44 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 13.33% | PowerSwitch N2200-ON OS6 for Nelson. Total power switch: 2 | Nelson-1-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Dell Marketing Lp | Networking power switches | 2021-05-12 | 2021-08-27 | 2021/22 | 21-6393 | PO3W-210000002719 | 0 | 9695.44 | 10513843591 | 2021-08-27 | 000000020245275 | 9695.44 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 13.33% | PowerSwitch N2200-ON OS6 for Workman ES. Total power switch: 2 | Workman ES-2-21st Century classroom
California-Fire Alarm replacement-DSA Fees | 3 | DSA Fees | California | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-08-25 | 2021-09-09 | 2021/22 | 22-1428 | PO2W-220000000367 | 0 | 1290 | 12742 | 2021-09-09 | 000000020255188 | 1290 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9041103 | 100% | Plan/field review fee for fire alarm at California. Alterations to California ES (FA system): Units A, B, D-F (A#15158, 03-106032), Unit C (A#15158,03-106023, 03-118115), Unit G (A#16973, 03-106023), & Relocatable Bldgs E1-E5 (A#03-111921) | California-3-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-DSA Fees | 1 | DSA Fees | Cedarlane | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-01-20 | 2020/21 | 21-3658 | PO2W-210000001557 | 0 | 1290 | 12367 | 2021-01-20 | 000000020157905 | 1290 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9051103 | 60% | Plan/field review fee for fire alarm at Cedarlane. Alterations to 11 Bldgs - FA: CR Bldg A-C, CR/Library Bldg D, CR Bldg E-H, Locker Bldg K, Admin Bldg M, & Multi-purpose Bldg P (A#20545) | Cedarlane-1-Fire Alarm replacement
Cedarlane-Interim Housing-DSA Fees | 1 | DSA Fees | Cedarlane | Interim Housing | Department of General Services (DGS) | DSA fees | 2022-08-08 | 2022-08-19 | 2022/23 | 23-1343 | PO2W-230000000336 | 0 | 11662.54 | 14275 | 2022-08-19 | 000000020590141 | 11662.54 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9051102 | 100% | Plan/field review fee for interim Housing at Cedarlane. Relocation of 4-Classrm bldgs (Relocatable): 1 (24' x 40') from A#02-104123, 1 (24' x 40') from A#04-104262, 1 (24' x 40') from A#04-104624, 1 (24' x 40') from A#65965, Foundation PC per A#04-116149 & Ramp PC per A#04-118089 | Cedarlane-1-Interim Housing
Grandview-Fire Alarm replacement-DSA Fees | 2 | DSA Fees | Grandview | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-07-21 | 2021-08-04 | 2021/22 | 22-742 | PO2W-220000000119 | 0 | 1451.25 | 12682 | 2021-08-04 | 000000020223410 | 1451.25 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9121103 | 45.76% | Plan/field review fee for fire alarm at Grandview. Alterations to 1-Campus wide (A-18215, A-25271, A03-106060, A03-106061) - FA System | Grandview-2-Fire Alarm replacement
Los Altos ES-21st Century classroom-DSA Fees | 2 | DSA Fees | Los Altos ES | 21st Century classroom | Department of General Services (DGS) | DSA fees | 2021-12-15 | 2022-01-06 | 2021/22 | 22-3685 | PO2W-220000001228 | 0 | 15210.87 | 12901 | 2022-01-06 | 000000020378116 | 15210.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191101 | 100% | Plan/field review fee for 21st Century at Los Altos ES. Alterations to 3-Classrm Upgrades Bldgs A-C (A03-106050, A-19204), 2-Classrm upgrades E&F (A03-100753, A-19909), 1-Classrm upgrade relo bldgs G1 (A03-100753), 1-Classrm upgrade relo bldg G2 (A03-118191), 1-Classrm upgrade relo bldg G3 (A03-117281) | Los Altos ES-2-21st Century classroom
Mesa Robles-Fire Alarm replacement-DSA Fees | 1 | DSA Fees | Mesa Robles | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-07-21 | 2021-08-04 | 2021/22 | 22-742 | PO2W-220000000119 | 0 | 1720 | 12681 | 2021-08-04 | 000000020223411 | 1720 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9221103 | 54.24% | Plan/field review fee for fire alarm at Mesa Robles. Alterations to 1-campus wide (A-18215, A-25271, A03-106060, A03-106061) - FA System | Mesa Robles-1-Fire Alarm replacement
Nelson-21st Century classroom-DSA Fees | 1 | DSA Fees | Nelson | 21st Century classroom | Department of General Services (DGS) | DSA fees | 2022-01-13 | 2022-01-28 | 2021/22 | 22-3947 | PO2W-220000001343 | 0 | 14670.45 | 12946 | 2022-01-28 | 000000020401402 | 14670.45 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9231101 | 100% | Plan/field review fee for 21st Century at Nelson. Alterations to 5-Classrm upgrade Bldg A-D, & K (A03-100749, A-17643), 1-Classrm bldgs (Relocatable) D6 (A03-109891), 1-Classrm bldgs (Relocatable) E1 (A-109891), 1-P.O.T./Campus walkway upgrades | Nelson-1-21st Century classroom
Newton-Fire Alarm replacement-DSA Fees | 1 | DSA Fees | Newton | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-03-20 | 2020/21 | 21-4441 | PO2W-210000001789 | 0 | 645 | 12429 | 2021-03-20 | 000000020172261 | 645 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9241103 | 100% | Plan/field review fee for fire alarm at Newton. Alterations to 1-campus wide FA upgrade | Newton-1-Fire Alarm replacement
Newton-Interim Housing-DSA Fees | 1 | DSA Fees | Newton | Interim Housing | Department of General Services (DGS) | DSA fees | 2023-04-26 | 2023-07-13 | 2022/23 | 23-7733 | PO2W-230000003701 | 0 | 7947.1 | 14567 | 2023-07-13 | 000000021124125 | 7947.1 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9241102 | 100% | Plan/field review fee for interim housing at Newton. Alterations to 1-Classroom bldg (03-106062), Relocation of 4-24'X40' Relocatable C.R. Bldg (A02-102873, A04-106102 & (2) A04-103044) with foundation PC04-113193 - Temporary 36 month approval. This PO (PO2W-23*3651) was created with DSA as the vendor on 05/16/23. DSA and DGS is the same organization and they will cash our checks regardless of the either vendor's name, but the new purchasing supervisor did not know about it. She changed the vendor name to DGS, 6 days later, as it should be, by this time, the payment deadline was only 4 days away. So, the DIstrict used US Bank credit card to pay this fee on 05/24/23. On 07/13/23, we reimbursed HLPUSD revolving fund account that paid the District's credit card. | Newton-1-Interim Housing
Sparks MS-Fire Alarm replacement-DSA Fees | 2 | DSA Fees | Sparks MS | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-01-06 | 2021-01-20 | 2020/21 | 21-3659 | PO2W-210000001557 | 0 | 860 | 12304 | 2021-01-20 | 000000020157906 | 860 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9301103 | 40% | Plan/field review fee for fire alarm at Sparks MS. Alterations to 1-Campus wide (A-17742, A03-106011) FA System | Sparks MS-2-Fire Alarm replacement
Valley-Fire Alarm replacement-DSA Fees | 8 | DSA Fees | Valley | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-07-13 | 2021-08-02 | 2021/22 |  | PO2W-220000000054 | 0 | 698.75 | 12664 | 2021-08-02 | 000000020221968 | 698.75 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9441103 | 100% | Plan/field review fee for fire alarm at Valley. Alterations to 1-Valley Alternative Sch (FA System): CR Bldg A (A#25561, 03-106020, 03-117538), Multi-purpose bldg B (A#25561, 03-106020, 03-100754), Admin bldg D (A#53743, 03-106020), Relocatable CR bldgs 2 & 5 (A#03-112718), & Relocatable CR Bldgs 3 & 4 (A#03-113573) | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-DSA Fees | 8 | DSA Fees | Valley | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-07-13 | 2021-08-08 | 2021/22 |  | PO2W-220000000054 | 0 | -698.75 | 12664 | 2021-08-02 | 000000020221968 | -698.75 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9441103 | -100% | Plan/field review fee for fire alarm at Valley. Alterations to 1-Valley Alternative Sch (FA System): CR Bldg A (A#25561, 03-106020, 03-117538), Multi-purpose bldg B (A#25561, 03-106020, 03-100754), Admin bldg D (A#53743, 03-106020), Relocatable CR bldgs 2 & 5 (A#03-112718), & Relocatable CR Bldgs 3 & 4 (A#03-113573). We issued warrant #20221968 dated 08/02/21 for this project; unfortunately, this warrant was inadvertently cashed by tBP. | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-DSA Fees | 8 | DSA Fees | Valley | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-07-13 | 2021-08-09 | 2021/22 |  | PO2W-220000000054 | 0 | 698.75 | 12664 | 2021-08-09 | 37503 | 698.75 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9441103 | 100% | Plan/field review fee for fire alarm at Valley. Alterations to 1-Valley Alternative Sch (FA System): CR Bldg A (A#25561, 03-106020, 03-117538), Multi-purpose bldg B (A#25561, 03-106020, 03-100754), Admin bldg D (A#53743, 03-106020), Relocatable CR bldgs 2 & 5 (A#03-112718), & Relocatable CR Bldgs 3 & 4 (A#03-113573). We issued warrant #20221968 dated 08/02/21 for this project; unfortunately, this warrant was inadvertently cashed by tBP. tBP issued check #37503 to replaced our warrant that they cashed. | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-DSA Fees | 8 | DSA Fees | Valley | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-07-13 | 2022-02-22 | 2021/22 |  | PO2W-220000000054 | 0 | -698.75 | 12664 | 2022-02-22 | 000000020424483 | -698.75 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9441103 | -100% | Plan/field review fee for fire alarm at Valley. Alterations to 1-Valley Alternative Sch (FA System): CR Bldg A (A#25561, 03-106020, 03-117538), Multi-purpose bldg B (A#25561, 03-106020, 03-100754), Admin bldg D (A#53743, 03-106020), Relocatable CR bldgs 2 & 5 (A#03-112718), & Relocatable CR Bldgs 3 & 4 (A#03-113573). We issued warrant #20221968 dated 08/02/21 for this project; unfortunately, this warrant was inadvertently cashed by tBP. tBP issued check #37503 to replaced our warrant that they cashed. On 01/31/22, the trial balance showed warrant #20221968 was stale dated. We investigated and found that tBP reversed their deposit of our warrant #20221968. On 02/22/22, we reimbursed tBP with warrant #20424483 which was lost in the mail. | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-DSA Fees | 8 | DSA Fees | Valley | Fire Alarm replacement | Department of General Services (DGS) | DSA fees | 2021-07-13 | 2022-05-06 | 2021/22 | 22-527 | PO2W-220000000054 | 0 | 698.75 | 12664 | 2022-05-06 | 000000020487475 | 698.75 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9441103 | 100% | Plan/field review fee for fire alarm at Valley. Alterations to 1-Valley Alternative Sch (FA System): CR Bldg A (A#25561, 03-106020, 03-117538), Multi-purpose bldg B (A#25561, 03-106020, 03-100754), Admin bldg D (A#53743, 03-106020), Relocatable CR bldgs 2 & 5 (A#03-112718), & Relocatable CR Bldgs 3 & 4 (A#03-113573). We issued warrant #20221968 dated 08/02/21 for this project; unfortunately, this check was inadvertently cashed by tBP. tBP issued ck #37503 to replaced our warrant that they cashed. On 01/31/22, the trial balance showed warrant #20221968 was stale dated. We investigated and found that tBP reversed their deposit of our warrant #20221968. On 02/22/22, we reimbursed tBP with warrant #20424483 which was lost in the mail. We reissue warrant #20487475 to reimburse tBP. | Valley-8-Fire Alarm replacement
Baldwin-21st Century classroom-DSA Fees | 3 | DSA Fees | Baldwin | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2024-01-09 | 2024-01-22 | 2023/24 | 24-4826 | PO2W-240000001909 | 0 | 37740 | Per email | 2024-01-22 | 000000021420049 | 37740 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9021101 | 100% | DSA plan check review fee for Baldwin 21st Century | Baldwin-3-21st Century classroom
Baldwin-Drinking Fountain replacement-DSA Fees | 3 | DSA Fees | Baldwin | Drinking Fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7621 | PO1-200000000954 | 0 | 1050 | Per email | 2020-02-13 | 000000020070039 | 1050 | 03-120655 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9021104 | 100% | Plan check review fee for drinking fountain at Baldwin | Baldwin-3-Drinking Fountain replacement
Baldwin-Fire Alarm replacement-DSA Fees | 3 | DSA Fees | Baldwin | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3175 | PO2W-200000001057 | 0 | 1020 | Per email | 2019-09-13 | 000000020015013 | 1020 | 03-120157 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9021103 | 100% | Plan check review fee for drinking fountain at Baldwin | Baldwin-3-Fire Alarm replacement
Bixby-Drinking Fountain replacement-DSA Fees | 6 | DSA Fees | Bixby | Drinking Fountain replacement | Division of the State Architect (DSA) | DSA fees | 2021-04-27 | 2021-05-05 | 2020/21 | 21-6130 | PO2W-210000002164 | 0 | 1050 | Per email | 2021-05-05 | 000000020186220 | 1050 | 03-121642 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9031104 | 50% | Plan check review fee for drinking fountain at Bixby | Bixby-6-Drinking Fountain replacement
Bixby-Fire Alarm replacement-DSA Fees | 6 | DSA Fees | Bixby | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6932 | PO1-200000000849 | 0 | 870 | Per email | 2020-02-13 | 000000020070034 | 870 | 03-120620 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9031103 | 100% | Plan check review fee for fire alarm at Bixby | Bixby-6-Fire Alarm replacement
California-21st Century classroom-DSA Fees | 3 | DSA Fees | California | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2024-01-09 | 2024-01-22 | 2023/24 | 24-4827 | PO2W-240000001910 | 0 | 26400 | Per email | 2024-01-22 | 000000021420049 | 26400 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9041101 | 100% | DSA plan check review fee for California 21st Century | California-3-21st Century classroom
California-Drinking Fountain replacement-DSA Fees | 3 | DSA Fees | California | Drinking Fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7620 | PO1-200000000953 | 0 | 1050 | Per email | 2020-02-13 | 000000020070038 | 1050 | 03-120656 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9041104 | 100% | Plan check review fee for drinking fountain at California | California-3-Drinking Fountain replacement
California-Fire Alarm replacement-DSA Fees | 3 | DSA Fees | California | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3172 | PO2W-200000001054 | 0 | 780 | Per email | 2019-09-13 | 000000020015009 | 780 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9041103 | 100% | Plan check review fee for fire alarm at California | California-3-Fire Alarm replacement
Cedarlane-21st Century classroom-DSA Fees | 1 | DSA Fees | Cedarlane | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2020-04-13 | 2020-04-24 | 2019/20 | 2-9602 | PO2W-200000004897 | 0 | 22159 | Per email | 2020-04-24 | 000000020092204 | 22159 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9051101 | 100% | Plan check review fee for 21st Century at Cedarlane. Application & fees for approval of plans & specifications | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Fees | 1 | DSA Fees | Cedarlane | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2022-08-02 | 2022-08-10 | 2022/23 | 23-1197 | PO2W-230000000247 | 0 | 18962.47 | 14253 | 2022-08-10 | 000000020578872 | 18962.47 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9051101 | 100% | Plan/field review fee for 21st Century at Cedarlane. Alterations to 9-Classrm bldgs A-H & P (A-20545, A03-105980, A03-119421) Non-structural work | Cedarlane-1-21st Century classroom
Cedarlane-Interim Housing-DSA Fees | 1 | DSA Fees | Cedarlane | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2020-01-28 | 2020-01-31 | 2019/20 | 2-7309 | PO2W-200000003716 | 0 | 3052.5 | Per email | 2020-01-31 | 000000020064667 | 3052.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9051102 | 100% | Plan/field review fee for interim Housing at Cedarlane. Application & fees for approval of plans & specifications | Cedarlane-1-Interim Housing
Del Valle-Fire Alarm replacement-DSA Fees | 7 | DSA Fees | Del Valle | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 870 | Per email | 2021-03-30 | 000000020176203 | 870 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9061103 | 12.26% | Plan check review fee for fire alarm at Del Valle | Del Valle-7-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-DSA Fees | 4 | DSA Fees | Fairgrove | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3174 | PO2W-200000001056 | 0 | 1230 | Per email | 2019-09-13 | 000000020015010 | 1230 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9091103 | 100% | Plan check review fee for fire alarm at Fairgrove | Fairgrove-4-Fire Alarm replacement
Grandview-21st Century classroom-DSA Fees | 2 | DSA Fees | Grandview | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 2020/21 | 21-3752 | PO2W-210000001571 | 0 | 35235.88 | Per email | 2021-01-20 | 000000020157908 | 35235.88 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9121101 | 61.28% | Plan check review fee for 21st Century at Grandview | Grandview-2-21st Century classroom
Grazide-Fire Alarm replacement-DSA Fees | 3 | DSA Fees | Grazide | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6933 | PO1-200000000850 | 0 | 960 | Per email | 2020-02-13 | 000000020070035 | 960 | 03-120624 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9131103 | 100% | Plan check review fee for fire alarm at Grazide | Grazide-3-Fire Alarm replacement
Kwis-Fire Alarm replacement-DSA Fees | 7 | DSA Fees | Kwis | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 891 | Per email | 2021-03-30 | 000000020176202 | 891 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9161103 | 12.56% | Plan check review fee for fire alarm at Kwis | Kwis-7-Fire Alarm replacement
Lassalette-Fire Alarm replacement-DSA Fees | 6 | DSA Fees | Lassalette | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 |  | PO1-200000000853 | 0 | 945 | Per email | 2020-02-13 | 000000020070037 | 945 | 03-120621 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9171103 | 100% | Plan check review fee for fire alarm at Lassalette. This warrant was voided on 04/30/20 per Carolyn Loughrey @ tBP. | Lassalette-6-Fire Alarm replacement
Lassalette-Fire Alarm replacement-DSA Fees | 6 | DSA Fees | Lassalette | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-04-30 | 2019/20 | 2-6934 | PO1-200000000853 | 0 | -945 | Per email | 2020-02-13 | 000000020070037 | -945 | 03-120621 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9171103 | -100% | Plan check review fee for Lassalette fire alarm. We voided this warrant. Per Carolyn Loughrey @ tBP - email dated 06/08/20, somehow she had 2 warrants with this amount and Lassalette was already paid for. She further said no replacement warrant is needed for this site. Close-out PO. | Lassalette-6-Fire Alarm replacement
Los Altos ES-21st Century classroom-DSA Fees | 2 | DSA Fees | Los Altos ES | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2019-06-11 | 2019-06-19 | 2018/19 |  | 19-109963 | 0 | 14918.24 | Per email | 2019-06-19 | 25365032 | 14918.24 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191101 | 100% | Plan check review fee for 21st Century at Los Altos ES | Los Altos ES-2-21st Century classroom
Los Altos ES-Drinking Fountain replacement-DSA Fees | 2 | DSA Fees | Los Altos ES | Drinking Fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7622 | PO1-200000000955 | 0 | 1050 | Per email | 2020-02-13 | 000000020070040 | 1050 | 03-120657 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191104 | 100% | Plan check review fee for drinking fountain at Los Altos ES | Los Altos ES-2-Drinking Fountain replacement
Los Altos ES-Interim Housing-DSA Fees | 2 | DSA Fees | Los Altos ES | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2019-03-18 | 2019-03-21 | 2018/19 |  | 19-107318 | 0 | 3481.54 | Per email | 2019-03-21 | 25172246 | 3481.54 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191102 | 100% | Plan check review fee for interim housing at Los Altos ES | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-DSA Fees | 2 | DSA Fees | Los Altos ES | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2020-03-06 | 2020-03-11 | 2019/20 | 2-8781 | PO2W-200000004548 | 0 | 2687.5 | 11816 | 2020-03-11 | 000000020080278 | 2687.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9191102 | 100% | Plan check review fee for interim housing at Los Altos ES (Relocation of 4 modular classrooms). | Los Altos ES-2-Interim Housing
Los Altos HS-Fire Alarm replacement-DSA Fees | 5 | DSA Fees | Los Altos HS | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3167 | PO2W-200000001053 | 0 | 5500 | Per email | 2019-09-13 | 000000020015011 | 5500 | 03-120155 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9411103 | 100% | Plan check review fee for fire alarm at Los Altos HS | Los Altos HS-5-Fire Alarm replacement
Los Molinos-Drinking Fountain replacement-DSA Fees | 4 | DSA Fees | Los Molinos | Drinking Fountain replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-05-05 | 2020/21 | 21-6130 | PO2W-210000002164 | 0 | 1050 | Per email | 2021-05-05 | 000000020186221 | 1050 | 03-121641 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9201104 | 50% | Plan check review fee for drinking fountain at Los Molinos | Los Molinos-4-Drinking Fountain replacement
Los Molinos-Fire Alarm replacement-DSA Fees | 4 | DSA Fees | Los Molinos | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3176 | PO2W-200000001058 | 0 | 870 | Per email | 2019-09-13 | 000000020015014 | 870 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9201103 | 100% | Plan check review fee for fire alarm at Los Molinos | Los Molinos-4-Fire Alarm replacement
Los Robles-Fire Alarm replacement-DSA Fees | 9 | DSA Fees | Los Robles | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 900 | Per email | 2021-03-30 | 000000020176204 | 900 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9211103 | 12.68% | Plan check review fee for fire alarm at Los Robles | Los Robles-9-Fire Alarm replacement
Mesa Robles-21st Century classroom-DSA Fees | 1 | DSA Fees | Mesa Robles | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2020-04-13 | 2020-04-24 | 2019/20 | 2-9603 | PO1-200000001113 | 0 | 28009 | Per email | 2020-04-24 | 000000020092203 | 28009 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9221101 | 100% | Plan check review fee for 21st Century at Mesa Robles. Application & fees for approval of plans & specifications | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Fees | 1 | DSA Fees | Mesa Robles | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2022-09-22 | 2022-10-19 | 2022/23 | 23-2683 | PO2W-230000001043 | 0 | 12075.87 | 14324 | 2022-10-19 | 000000020681642 | 12075.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9221101 | 100% | Plan/field review fee for 21st Century at Mesa Robles . Alterations to 1-campus wide classrooms, all work non-structural | Mesa Robles-1-21st Century classroom
Mesa Robles-Drinking Fountain replacement-DSA Fees | 1 | DSA Fees | Mesa Robles | Drinking Fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7623 | PO1-200000000956 | 0 | 1050 | Per email | 2020-02-13 | 000000020070041 | 1050 | 03-120658 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9211104 | 100% | Plan check review fee for drinking fountain at Mesa Robles . This check was originally issued for Los Robles' (loc 9211104) drinking fountain project, but since this project was cancelled by District, per Carolyn Loughrey, tBP applied this payment to Mesa Robles. | Mesa Robles-1-Drinking Fountain replacement
Mesa Robles-Interim Housing-DSA Fees | 1 | DSA Fees | Mesa Robles | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2019-10-22 | 2019-10-28 | 2019/20 | 2-4764 | PO2W-200000001911 | 0 | 7425 | Per email | 2019-10-28 | 000000020031416 | 7425 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9221102 | 100% | Plan check review fee for interim housing at Mesa Robles | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-DSA Fees | 1 | DSA Fees | Nelson | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2019-06-11 | 2019-06-19 | 2018/19 |  | 19-109964 | 0 | 15540.64 | Per email | 2019-06-19 | 25365030 | 15540.64 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9231101 | 100% | Plan check review fee for 21st Century at Nelson | Nelson-1-21st Century classroom
Nelson-Drinking Fountain replacement-DSA Fees | 1 | DSA Fees | Nelson | Drinking Fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7624 | PO1-200000000957 | 0 | 1050 | Per email | 2020-02-13 | 000000020070042 | 1050 | 03-120659 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9231104 | 100% | Plan check review fee for drinking fountain at Nelson | Nelson-1-Drinking Fountain replacement
Newton-21st Century classroom-DSA Fees | 1 | DSA Fees | Newton | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 2020/21 | 21-3753 | PO2W-210000001572 | 0 | 28270.82 | Per email | 2021-01-20 | 000000020157907 | 28270.82 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9241101 | 100% | Plan check review fee for 21st Century at Newton | Newton-1-21st Century classroom
Newton-Interim Housing-DSA Fees | 1 | DSA Fees | Newton | Interim Housing | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-01-28 | 2019/20 | 2-6939 | PO1-200000000863 | 0 | 4175.44 | Per email | 2020-01-28 | 000000020062969 | 4175.44 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9241102 | 100% | Plan check review fee forinterim housing at Newton. Initial registration for project submittal | Newton-1-Interim Housing
Orange Grove-Fire Alarm replacement-DSA Fees | 3 | DSA Fees | Orange Grove | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 1080 | Per email | 2021-03-30 | 000000020176205 | 1080 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9251103 | 15.22% | Plan check review fee for fire alarm at Orange Grove | Orange Grove-3-Fire Alarm replacement
Palm-Drinking Fountain replacement-DSA Fees | 6 | DSA Fees | Palm | Drinking Fountain replacement | Division of the State Architect (DSA) | DSA fees | 2020-02-04 | 2020-02-13 | 2019/20 | 2-7625 | PO1-200000000958 | 0 | 1050 | Per email | 2020-02-13 | 000000020070043 | 1050 | 03-120660 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9261104 | 100% | Plan check review fee for drinking fountain at Palm | Palm-6-Drinking Fountain replacement
Palm-Fire Alarm replacement-DSA Fees | 6 | DSA Fees | Palm | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 870 | Per email | 2021-03-30 | 000000020176206 | 870 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9261103 | 12.26% | Plan check review fee for fire alarm at Palm | Palm-6-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-DSA Fees | 8 | DSA Fees | Sierra Vista | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 1050 | Per email | 2021-03-30 | 000000020176207 | 1050 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9281103 | 14.8% | Plan check review fee for fire alarm at Sierra Vista | Sierra Vista-8-Fire Alarm replacement
Sparks ES-Fire Alarm replacement-DSA Fees | 7 | DSA Fees | Sparks ES | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6935 | PO1-200000000848 | 0 | 930 | Per email | 2020-02-13 | 000000020070033 | 930 | 03-120623 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9291103 | 100% | Plan check review fee for fire alarm at Sparks ES | Sparks ES-7-Fire Alarm replacement
Sparks MS-21st Century classroom-DSA Fees | 2 | DSA Fees | Sparks MS | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2021-01-12 | 2021-01-20 | 2020/21 | 21-3754 | PO2W-210000001571 | 0 | 22264.25 | Per email | 2021-01-20 | 000000020157909 | 22264.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9301101 | 38.72% | Plan check review fee for 21st Century at Sparks MS | Sparks MS-2-21st Century classroom
Stimson-Fire Alarm replacement-DSA Fees | 4 | DSA Fees | Stimson | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6937 | PO1-200000000851 | 0 | 375 | Per email | 2020-02-13 | 000000020070044 | 375 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 8021103 | 100% | Plan check review fee for fire alarm at Stimson | Stimson-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-DSA Fees | 4 | DSA Fees | Sunset | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 564 | Per email | 2021-03-30 | 000000020176208 | 564 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9311103 | 7.949% | Plan check review fee for fire alarm at Sunset | Sunset-4-Fire Alarm replacement
Valinda-Fire Alarm replacement-DSA Fees | 6 | DSA Fees | Valinda | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2020-01-15 | 2020-02-13 | 2019/20 | 2-6938 | PO1-200000000852 | 0 | 1125 | Per email | 2020-02-13 | 000000020070036 | 1125 | 03-120622 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9341103 | 100% | Plan check review fee for fire alarm at Valinda | Valinda-6-Fire Alarm replacement
Valley-Fire Alarm replacement-DSA Fees | 8 | DSA Fees | Valley | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2019-09-09 | 2019-09-13 | 2019/20 | 2-3173 | PO2W-200000001055 | 0 | 630 | Per email | 2019-09-13 | 000000020015012 | 630 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9441103 | 100% | Plan/field review fee for fire alarm at Valley | Valley-8-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-DSA Fees | 9 | DSA Fees | Wing Lane | Fire Alarm replacement | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-03-30 | 2020/21 | 21-5370 | PO2W-210000001958 | 0 | 870 | Per email | 2021-03-30 | 000000020176209 | 870 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9371103 | 12.26% | Plan check review fee for fire alarm at Wing Lane | Wing Lane-9-Fire Alarm replacement
Workman ES-21st Century classroom-DSA Fees | 2 | DSA Fees | Workman ES | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2019-04-16 | 2019-04-18 | 2018/19 |  | 19-108465 | 0 | 9500 | Per email | 2019-04-18 | 25237048 | 9500 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9381101 | 100% | Plan check review fee for 21st Century at Workman ES | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Fees | 2 | DSA Fees | Workman ES | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2021-03-17 | 2021-05-05 | 2020/21 | 21-6131 | PO2W-210000002165 | 0 | 800 | Per email | 2021-05-05 | 000000020186222 | 800 | 03-121545 | 73445-382 | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9381101 | 100% | Plan check review fee for 21st Century at Workman ES. Hardware replacement project (doors & locks). | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Fees | 2 | DSA Fees | Workman ES | 21st Century classroom | Division of the State Architect (DSA) | DSA fees | 2022-01-19 | 2022-01-28 | 2021/22 | 22-4020 | PO2W-220000001377 | 0 | 12085.87 | 12959 | 2022-01-28 | 000000020401405 | 12085.87 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9381101 | 100% | Plan check review fee for 21st Century at Workman ES. Alterations to 3 classrm bldg 1-3 (A#03-119612) & 10 classrm bldgs (Relocatable AP2-AP11) (A#03-119612) | Workman ES-2-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Dr. Alfonso Jimenez | Conference | 2023-08-02 | 2023-09-19 | 2023/24 | 24-1262 | PO2W-240000000439 | 0 | 58.65 | Conf reimb 07/09 -07/10/23 | 2023-09-19 | 000000021219857 | 58.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5220 | 9851100 | 100% | Travel reimbursement to attend bond rating workshop conducted by RBC Capital in San Francisco on July 9-10, 2023 (JVA 24*369) | District Office-0-Cost of Issuance
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 2019/20 | 2-7592 | PO2W-200000004016 | 0 | 949.34 | EPS6017-2020 | 2020-04-22 | 000000020091373 | 949.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 50.33% | Covered vinyl tack boards (46" x 96") as sample for the District-wide use. Each panel will be wrapped on 4 sides, no trim. Total tack boards for this PO: 8 | District Office-0-21st Century classroom
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 2019/20 |  | PO2W-200000004016 | 0 | 264.04 | EPS6017-2020 | 2020-04-22 | 000000020091373 | 264.04 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 14% | Covered vinyl tack boards (46" x 96") as sample for the District-wide use. Each panel will be wrapped on 4 sides, no trim. Total tack boards for this PO: 8 | District Office-0-21st Century classroom
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 2019/20 |  | PO2W-200000004016 | 0 | 336.49 | EPS6017-2020 | 2020-04-22 | 000000020091373 | 336.49 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 17.84% | Covered vinyl tack boards (46" x 96") as sample for the District-wide use. Each panel will be wrapped on 4 sides, no trim. Total tack boards for this PO: 8 | District Office-0-21st Century classroom
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Education Products & Services | Tack boards | 2020-02-04 | 2020-04-22 | 2019/20 |  | PO2W-200000004016 | 0 | 336.49 | EPS6017-2020 | 2020-04-22 | 000000020091373 | 336.49 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 17.84% | Covered vinyl tack boards (46" x 96") as sample for the District-wide use. Each panel will be wrapped on 4 sides, no trim. Total tack boards for this PO: 8 | District Office-0-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Education Products & Services | White board(s) | 2019-09-16 | 2019-09-25 | 2019/20 | 2-923 | PO2W-200000000102 | 0 | 1464.78 | EPS6083-2019 | 2019-09-25 | 000000020019023 | 1464.78 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 100% | Da-Lite IDEA Panoramic white board 16 x 10 format with panoramic screen surface for Grandview's room #61. | Grandview-2-21st Century classroom
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | Education Products & Services | Contractor | 2019-10-14 | 2020-02-12 | 2019/20 | 2-4518 | PO2W-200000002196 | 0 | 1894.88 | EPS6097-2019 | 2020-02-12 | 000000020069435 | 1894.88 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 100% | Installation of 7 new horizontal 1" blinds in 4 portable classrooms at Los Altos ES. | Los Altos ES-2-Interim Housing
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Education Products & Services | Sliding white boards | 2020-01-15 | 2020-04-23 | 2019/20 | 2-6913 | PO2W-200000003506 | 0 | 5465.85 | EPS6013-2020 | 2020-04-23 | 000000020091979 | 5465.85 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Provide labor and materials to install four (4) 44" x 60" Top mounted sliding white board to include track as sample for Nelson room #C1. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Education Products & Services | White board(s) | 2020-01-31 | 2020-04-23 | 2019/20 | 2-7521 | PO2W-200000003738 | 0 | 1253.77 | EPS6021-2020 | 2020-04-23 | 000000020091979 | 1253.77 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Provide labor and materials to install two (2) 48" x 96" porcelain white boards with 1" map rail and blade style marker tray. 1/2" aluminum trim on 3 sides, mitered corners as sample for Nelson room #C1. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Education Products & Services | Sink cabinet | 2020-01-31 | 2020-04-23 | 2019/20 | 2-7493 | PO2W-200000003740 | 0 | 3449.99 | EPS6022-2020 | 2020-04-23 | 000000020091979 | 3449.99 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Provide labor and material to install sink cabinet which include backsplash & countertop as a sample for Nelson room #C1. Cabinetwill be 48" wide x 24" deep x 34" high with a 7" front facia under the countertop in front of sink. | Nelson-1-21st Century classroom
Valinda-21st Century classroom-FF & E | 6 | FF & E | Valinda | 21st Century classroom | Education Products & Services | White board(s) | 2019-09-16 | 2019-10-01 | 2019/20 | 2-3418 | PO3W-200000000563 | 0 | 1464.78 | EPS6062-2019 | 2019-10-01 | 000000020021433 | 1464.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 100% | Da-Lite IDEA Panoramic white board 16 x 10 format with panoramic screen surface for Valinda - room #14. | Valinda-6-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2017-07-11 | 2017-12-19 | 2017/18 |  | 18-104648 | 0 | 1064 | 54830-3 | 2017-12-19 | 24246702 | 1064 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 100% | Legal services for the bond projects. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2017-07-11 | 2017-12-20 | 2017/18 |  | 18-104648 | 48936 | 48936 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Remaining balance in this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2017-07-11 | 2018-06-30 | 2017/18 |  | 18-104648 | -48936 | -48936 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Close-out PO | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2018-07-11 | 2019-04-09 | 2018/19 |  | 19-100300 | 0 | 2375 | 62570-4 | 2019-04-09 | 25217951 | 2375 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 100% | Legal services for the bond projects. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2018-07-11 | 2019-04-10 | 2018/19 |  | 19-100300 | 7625 | 7625 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Remaining balance in this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2018-07-11 | 2019-06-30 | 2018/19 |  | 19-100300 | -7625 | -7625 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Close-out PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-01-03 | 2019/20 |  | PO1-200000000812 | 0 | 7283.51 | 179385-5 | 2020-01-03 | 000000020053868 | 7283.51 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 36.42% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-01-08 | 2019/20 |  | PO1-200000000812 | 0 | 2112.68 | 178377-4 | 2020-01-08 | 000000020055186 | 2112.68 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 10.56% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-01-13 | 2019/20 |  | PO1-200000000812 | 0 | 10128 | 179785-4 | 2020-01-13 | 000000020056662 | 10128 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 50.64% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-03-03 | 2019/20 |  | PO1-200000000812 | 0 | 31.62 | 181255-3 | 2020-03-03 | 000000020076553 | 31.62 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0.1581% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-12-30 | 2020-04-29 | 2019/20 | 2-6047 | PO1-200000000812 | 0 | 444.19 | 180616-2 | 2020-04-29 | 000000020093273 | 444.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 2.221% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2020-04-29 | 2019/20 |  | PO1-200000001126 | 0 | 6906.81 | 180616-2 | 2020-04-29 | 000000020093273 | 6906.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 100% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2020-06-30 | 2019/20 |  | PO1-200000001126 | 0 | 13093.19 |  |  |  | 13093.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 65.47% | Legal services for the bond projects. Accrued remaining balance of this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2020-07-01 | 2020/21 |  | PO1-200000001126 | 0 | -13093.19 |  |  |  | -13093.19 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | -65.47% | Legal services for the bond projects. Reversed accrual from prior year | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2020-07-02 | 2020/21 |  | PO1-200000001126 | 13093.19 | 13093.19 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Remaining balance in this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-03-10 | 2021-06-30 | 2020/21 | 2-9052 | PO1-200000001126 | -13093.19 | -13093.19 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Close-out PO | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2021-12-14 | 2021/22 |  | PO1-210000000260 | 0 | 1417.5 | 196338-1 | 2021-12-14 | 000000020360176 | 1417.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 9.401% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2021-12-23 | 2021/22 |  | PO1-210000000260 | 0 | 1799.5 | 197570-1 | 2021-12-23 | 000000020374043 | 1799.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 11.94% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2022-01-24 | 2021/22 |  | PO1-210000000260 | 0 | 5735 | 195670-4 | 2022-01-24 | 000000020395774 | 5735 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 38.04% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2022-01-28 | 2021/22 |  | PO1-210000000260 | 0 | 3513 | 197728-4 | 2022-01-28 | 000000020401406 | 3513 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 23.3% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2022-03-02 | 2021/22 |  | PO1-210000000260 | 0 | 2612.5 | 198458-2 | 2022-03-02 | 000000020432785 | 2612.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 17.33% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2023-07-19 | 2022/23 |  | PO1-210000000260 | 34922.5 | 34922.5 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Remaining balance in this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2020-07-31 | 2023-07-20 | 2022/23 | 21-192 | PO1-210000000260 | -34922.5 | -34922.5 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Close-out PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-07-11 | 2019-08-21 | 2019/20 |  | PO2W-200000000134 | 0 | 90 | 64515-4 | 2019-08-21 | 000000020006819 | 90 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0.9% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-07-11 | 2019-08-28 | 2019/20 |  | PO2W-200000000134 | 0 | 3235 | 64302-2 | 2019-08-28 | 000000020008961 | 3235 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 32.35% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-07-11 | 2019-09-18 | 2019/20 |  | PO2W-200000000134 | 0 | 1387.5 | 176791-5 | 2019-09-18 | 000000020016440 | 1387.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 13.88% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Fagen Friedman & Fulfrost LLP | Attorney fees | 2019-07-11 | 2020-01-03 | 2019/20 | 2-99 | PO2W-200000000134 | 0 | 5287.5 | 179385-5 | 2020-01-03 | 000000020053868 | 5287.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 52.88% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Fitch Ratings, Inc. | Rating Agency Fee | 2017-08-03 | 2017-08-03 | 2017/18 |  | N/A - Cost of Issuance | 0 | 45000 |  |  |  | 45000 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Rating Agency Fee, 18-KT005 | District Office-0-Cost of Issuance
California-21st Century classroom-Contractor | 3 | Contractor | California | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 12744.48 | Pay app #4 | 2020-12-08 | 000000020148205 | 12744.48 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041101 | 2.831% | Prep & install Mohawk LVT, walk off mat & base at California for room #5 & 12 | California-3-21st Century classroom
Del Valle-21st Century classroom-Contractor | 7 | Contractor | Del Valle | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 6372.24 | Pay app #3 | 2020-12-08 | 000000020148205 | 6372.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061101 | 1.415% | Prep & install Mohawk LVT, walk off mat & base at Del Valle for room #12 | Del Valle-7-21st Century classroom
District Office-21st Century classroom-Contractor | 0 | Contractor | District Office | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-05-07 | 2019/20 |  | PO2W-200000004391 | 0 | 259042.4 | Pay app #1 | 2020-05-07 | 000000020095892 | 259042.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9851100 | 57.54% | Supply 38,400 SF Mohawk LVT and bond for District-wide use (30 classrooms) | District Office-0-21st Century classroom
Los Altos HS-21st Century classroom-Contractor | 5 | Contractor | Los Altos HS | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-03-24 | 2020/21 |  | PO2W-200000004391 | 0 | 19116.72 | Pay app #5 | 2021-03-24 | 000000020174719 | 19116.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9411101 | 4.246% | Prep & install Mohawk LVT, walk off mat & base at Los Altos HS for room #J10, J11, & J14 | Los Altos HS-5-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-01-15 | 2020-04-23 | 2019/20 | 2-6914 | PO2W-200000003507 | 0 | 11175 | 12652 | 2020-04-23 | 000000020091981 | 11175 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Prepare and install new LVT. Supply and install 4" rubber topset base and 4 yards of First Step Up II for Nelson room #C1. | Nelson-1-21st Century classroom
Orange Grove-21st Century classroom-Contractor | 3 | Contractor | Orange Grove | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2022-05-11 | 2021/22 | 2-8416 | PO2W-200000004391 | 0 | 19116.72 | Pay app #8 | 2022-05-11 | 000000020490801 | 19116.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9251101 | 4.246% | Prep & install Mohawk LVT, walk off mat & base at Orange Grove Admin | Orange Grove-3-21st Century classroom
Palm-21st Century classroom-Contractor | 6 | Contractor | Palm | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-08-28 | 2020/21 |  | PO2W-200000004391 | 0 | 2006.79 | Pay app #2 | 2020-08-28 | 000000020122640 | 2006.79 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261101 | 0.4457% | Demo 4,266 sy carpet, prepare concrete. Supply & install 252 yd First step Up II & bond at Palm for room #13 | Palm-6-21st Century classroom
Palm-21st Century classroom-Contractor | 6 | Contractor | Palm | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 4365.45 | Pay app #3 | 2020-12-08 | 000000020148205 | 4365.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261101 | 0.9696% | Prep & install Mohawk LVT, walk off mat & base at Palm for room #13 | Palm-6-21st Century classroom
Sparks ES-21st Century classroom-Contractor | 7 | Contractor | Sparks ES | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 19116.72 | Pay app #3 | 2020-12-08 | 000000020148205 | 19116.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291101 | 4.246% | Prep & install Mohawk LVT, walk off mat & base at Sparks ES for room #5, 9, & 14 | Sparks ES-7-21st Century classroom
Valley-21st Century classroom-Contractor | 8 | Contractor | Valley | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-09-09 | 2021/22 |  | PO2W-200000004391 | 0 | 19116.72 | Pay app #7 | 2021-09-09 | 000000020255193 | 19116.72 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9441101 | 4.246% | Prep & install Mohawk LVT, walk off mat & base at Valley for room #5, 6, & 7 | Valley-8-21st Century classroom
Wedgeworth-21st Century classroom-Contractor | 0 | Contractor | Wedgeworth | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-04-06 | 2020/21 |  | PO2W-200000004391 | 0 | 12744.48 | Pay app #6 | 2021-04-06 | 000000020177862 | 12744.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9351101 | 2.831% | Prep & install Mohawk LVT, walk off mat & base at Wedgeworth for room #5 & 6 | Wedgeworth-0-21st Century classroom
Wilson HS-21st Century classroom-Contractor | 5 | Contractor | Wilson HS | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2020-12-08 | 2020/21 |  | PO2W-200000004391 | 0 | 12744.48 | Pay app #4 | 2020-12-08 | 000000020148205 | 12744.48 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9421101 | 2.831% | Prep & install Mohawk LVT, walk off mat & base at Wilson HS for room #B-6A & D-2 | Wilson HS-5-21st Century classroom
Wilson HS-21st Century classroom-Contractor | 5 | Contractor | Wilson HS | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-04-06 | 2020/21 |  | PO2W-200000004391 | 0 | 6372.24 | Pay app #6 | 2021-04-06 | 000000020177862 | 6372.24 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9421101 | 1.415% | Prep & install Mohawk LVT, walk off mat & base at Wilson HS for room #T1 | Wilson HS-5-21st Century classroom
Workman HS-21st Century classroom-Contractor | 5 | Contractor | Workman HS | 21st Century classroom | Floor Tech America (FTA) | Contractor | 2020-02-26 | 2021-04-06 | 2020/21 |  | PO2W-200000004391 | 0 | 57350.16 | Pay app #6 | 2021-04-06 | 000000020177862 | 57350.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9431101 | 12.74% | Prep & install Mohawk LVT, walk off mat & base at Workman HS for room #A9-A12, A18, E25-E27, & F1 | Workman HS-5-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | GDL Best Contractors, Inc. | Contractor | 2020-09-11 | 2021-03-26 | 2020/21 | 21-1847 | PO2W-210000000586 | 0 | 7950 | 6232 | 2021-03-26 | 000000020175473 | 7950 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191101 | 36.64% | Concrete work for wing A & B, per site walk with Richard Walsh at Los Altos ES | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | GDL Best Contractors, Inc. | Contractor | 2020-09-11 | 2021-03-26 | 2020/21 | 21-1847 | PO2W-210000000586 | 0 | 13746 | 6233 | 2021-03-26 | 000000020175473 | 13746 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191101 | 63.36% | Concrete work for wing E & F, per site walk with Richard Walsh at Los Altos ES | Los Altos ES-2-21st Century classroom
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2019-07-01 | 2019-11-06 | 2019/20 |  | PO2W-200000000121 | 0 | 183825 | Pay app #1 | 2019-11-06 | 000000020035020 | 183825 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 83.37% | 4 portable units at Los Altos ES - demolition,remove and dump grass, relocate existing irrigation, install base, asphalt, electrical service, fire alarm, condensation drains, drywell, metal guards at each HVAC, signage. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2019-07-01 | 2020-06-16 | 2019/20 |  | PO2W-200000000121 | 0 | 25650 | Pay app #2 | 2020-06-16 | 000000020105600 | 25650 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 11.63% | 4 portable units at Los Altos ES - demolition,remove and dump grass, relocate existing irrigation, install base, asphalt, electrical service, fire alarm, condensation drains, drywell, metal guards at each HVAC, signage. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2019-07-01 | 2020-06-16 | 2019/20 | 2-724 | PO2W-200000000121 | 0 | 11025 | Pay app #3 | 2020-06-16 | 000000020105600 | 11025 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 5% | 4 portable units at Los Altos ES - demolition,remove and dump grass, relocate existing irrigation, install base, asphalt, electrical service, fire alarm, condensation drains, drywell, metal guards at each HVAC, signage. | Los Altos ES-2-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2020-03-03 | 2020-07-28 | 2019/20 |  | PO2W-200000004670 | 0 | 382506.49 | Pay app #1 | 2020-07-28 | 000000020116619 | 382506.49 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 50.6% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. The total project costs with this change order (PO2W-22*897) is $773,385.54 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2020-03-03 | 2020-09-08 | 2019/20 |  | PO2W-200000004670 | 0 | 20131.92 | Pay app #2 | 2020-09-08 | 000000020124730 | 20131.92 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 2.663% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. The total project costs with this change order (PO2W-22*897) is $773,385.54 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2020-03-03 | 2020-09-08 | 2020/21 |  | PO2W-200000004670 | 0 | 282815.48 | Pay app #2 | 2020-09-08 | 000000020124730 | 282815.48 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 37.41% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. The total project costs with this change order (PO2W-22*897) is $773,385.54 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2020-03-03 | 2021-05-21 | 2020/21 |  | PO2W-200000004670 | 0 | 51574.48 | Pay app #3 | 2021-05-21 | 000000020191175 | 51574.48 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 6.822% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. The total project costs with this change order (PO2W-22*897) is $773,385.54 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2020-03-03 | 2022-01-28 | 2021/22 | 2-8610 | PO2W-200000004670 | 0 | 18937.04 | Pay app #4 | 2022-01-28 | 000000020401407 | 18937.04 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9221102 | 2.505% | 10 portable replacement - Scope of work consists of saw-cut & demo existing asphalt, remove and dump grass, relocate existing irrigation, shooting elevations, installation & compaction of new class II base, grading for class II base asphalt installation to prepare for the new interim housing at Mesa Robles. The total project costs with this change order (PO2W-22*897) is $773,385.54 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2021-11-02 | 2022-02-01 | 2021/22 | 22-2885 | PO2W-220000000897 | 0 | 17420.13 | Pay app #4 | 2022-02-01 | 000000020403713 | 17420.13 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221102 | 100% | Change order to 10 portable replacement to the new interim housing at Mesa Robles - Short circuit coordination, install fuses, sawcut and remove asphalt against building, relocate and re-install markerboards, & remove existing locks and install new sets for 10 doors. Addendum to PO2W-20*4670. The total project costs with this change order is $773,385.54 | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | GDL Best Contractors, Inc. | Contractor | 2020-02-03 | 2020-06-18 | 2019/20 | 2-7580 | PO2W-200000004356 | 0 | 14900 | 6071 | 2020-06-18 | 000000020106497 | 14900 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 100% | Prep existing doors & install new door hardware, provide & install tack board sheets, provide & install sink, faucet, & bubbler and plumbing, prime & paint existing window frames & door, provide & install TV bracket for Nelson room #C1. | Nelson-1-21st Century classroom
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | GDL Best Contractors, Inc. | Contractor | 2022-07-01 | 2022-08-26 | 2022/23 | 23-289 | PO2W-230000000447 | 0 | 2645 | 6619 | 2022-08-26 | 000000020601013 | 2645 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9241102 | 100% | Frame with 2 x 6 and T1-11 plywood siding at 3 portable openings, approx. 5' x 10'. Prep, prime, and paint to match existing portable color at Newton | Newton-1-Interim Housing
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Global Industrial | Scissor lift | 2021-05-18 | 2021-06-03 | 2020/21 | 21-6450 | PO3W-210000002747 | 0 | 1665.5 | 117699325 | 2021-06-03 | 000000020194623 | 1665.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 100% | A Pneumatic-Hydraullic Mobile Scissor Lift Table AIR-800-D. 800 lb. capacity for District-wide use | District Office-0-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Graybar Electric | Door hardware | 2021-06-16 | 2021-08-30 | 2021/22 |  | PO3W-210000003051 | 0 | 376.36 | 9322335589 | 2021-08-30 | 000000020246134 | 376.36 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 17.34% | Mounting brackets, faceplates, & mini com stereo for Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Graybar Electric | Door hardware | 2021-06-16 | 2021-09-23 | 2021/22 |  | PO3W-210000003051 | 0 | 358.62 | 9323008978 | 2021-09-23 | 000000020271037 | 358.62 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 16.53% | Mounting brackets, faceplates, & mini com stereo for Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Graybar Electric | Door hardware | 2021-06-16 | 2022-03-15 | 2021/22 | 21-6866 | PO3W-210000003051 | 0 | 101.99 | 9325677028 | 2022-03-15 | 000000020443754 | 101.99 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 4.7% | Mounting brackets, faceplates, & mini com stereo for Cedarlane | Cedarlane-1-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Graybar Electric | Door hardware | 2020-12-14 | 2021-02-08 | 2020/21 | 21-3550 | PO3W-210000001162 | 0 | 246.82 | 9319230223 | 2021-02-08 | 000000020162991 | 246.82 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 33.33% | Mounting brackets & blank face plates for Los Altos ES | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Graybar Electric | Door hardware | 2021-06-16 | 2021-08-30 | 2021/22 |  | PO3W-210000003051 | 0 | 599.39 | 9322335589 | 2021-08-30 | 000000020246134 | 599.39 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 27.62% | Mounting brackets, faceplates, & mini com stereo for Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Graybar Electric | Door hardware | 2021-06-16 | 2021-09-23 | 2021/22 |  | PO3W-210000003051 | 0 | 571.14 | 9323008978 | 2021-09-23 | 000000020271037 | 571.14 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 26.32% | Mounting brackets, faceplates, & mini com stereo for Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Graybar Electric | Door hardware | 2021-06-16 | 2022-03-15 | 2021/22 | 21-6866 | PO3W-210000003051 | 0 | 162.45 | 9325677028 | 2022-03-15 | 000000020443754 | 162.45 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 7.486% | Mounting brackets, faceplates, & mini com stereo for Mesa Robles | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Graybar Electric | Door hardware | 2020-12-14 | 2021-02-08 | 2020/21 | 21-3550 | PO3W-210000001162 | 0 | 246.82 | 9319230223 | 2021-02-08 | 000000020162991 | 246.82 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 33.33% | Mounting brackets & blank face plates for Nelson | Nelson-1-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Graybar Electric | Door hardware | 2020-12-14 | 2021-02-08 | 2020/21 | 21-3550 | PO3W-210000001162 | 0 | 246.8 | 9319230223 | 2021-02-08 | 000000020162991 | 246.8 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 33.33% | Mounting brackets & blank face plates for Workman ES | Workman ES-2-21st Century classroom
District Office-Design guidelines-Design | 0 | Design | District Office | Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2018-09-17 | 2018/19 |  | PO2W-200000001205, 19-100491, 18-109571 | 0 | 16080 | 966301 | 2018-09-17 | 24789789 | 16080 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9851100 | 67% | Architect - Create design guidelines to serve as a set of guiding principles for District's 21st Century classroom projects. | District Office-0-Design guidelines
District Office-Design guidelines-Design | 0 | Design | District Office | Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2018-10-19 | 2018/19 |  | PO2W-200000001205, 19-100491, 18-109571 | 0 | 6720 | 966422 | 2018-10-19 | 24871020 | 6720 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9851100 | 28% | Architect - Create design guidelines to serve as a set of guiding principles for District's 21st Century classroom projects. | District Office-0-Design guidelines
District Office-Design guidelines-Design | 0 | Design | District Office | Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2021-06-02 | 2020/21 | 2-514 | PO2W-200000001205, 19-100491, 18-109571 | 0 | 1200 | 969692 | 2021-06-02 | 000000020194098 | 1200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9851100 | 5% | Architect - Create design guidelines to serve as a set of guiding principles for District's 21st Century classroom projects. | District Office-0-Design guidelines
District Office-Design guidelines-Design | 0 | Design | District Office | Design guidelines | Harley Ellis Devereaux (HED) | Architect | 2018-07-01 | 2026-06-01 | 2023/24 | 2-516 | PO2W-200000001206, 19-103806 | 5500 | 5500 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9851100 | 0% | Architect - Additional services to create design guidelines to serve as a set of guiding principles for District's 21st Century classroom projects. | District Office-0-Design guidelines
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2018-07-24 | 2017/18 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2800 | 965679 | 2018-07-24 | 24699522 | 2800 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.564% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2019-02-19 | 2018/19 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 10110 | 967398R | 2019-02-19 | 25105194 | 10110 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 5.648% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. Allowances for site survey (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $27,331.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2019-09-16 | 2018/19 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 15400 | 968553R | 2019-09-16 | 000000020015463 | 15400 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 8.603% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2019-09-17 | 2018/19 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 265.07 |  |  |  | 265.07 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00. Accrued invoice in the amount of $265.07 (for allowances). | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2020-02-13 | 2019/20 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 19600 | 970824 | 2020-02-13 | 000000020070049 | 19600 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 10.95% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2020-03-10 | 2019/20 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | -265.07 |  |  |  | -265.07 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00. The invoice for allowances was cancelled by HED. Reversed accrual from prior year. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2020-06-04 | 2019/20 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 23100 | 971442 | 2020-06-04 | 000000020102538 | 23100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 12.91% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2020-12-08 | 2020/21 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 17221 | 971453R | 2020-12-08 | 000000020148211 | 17221 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 9.621% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. Allowances for civil engineering for all path of travel issues (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $27,331.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2021-05-07 | 2020/21 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 11550 | 971724R | 2021-05-07 | 000000020187161 | 11550 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 6.453% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2021-05-07 | 2020/21 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 11550 | 972095R | 2021-05-07 | 000000020187161 | 11550 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 6.453% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2021-06-23 | 2020/21 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 3500 | 975780 | 2021-06-23 | 000000020200446 | 3500 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.955% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2021-12-20 | 2021/22 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 1050 | 976674 | 2021-12-20 | 000000020370745 | 1050 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.5866% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2022-07-18 | 2021/22 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 350 | 977969 | 2022-07-18 | 000000020554417 | 350 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.1955% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2022-07-18 | 2021/22 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 1050 | 979948 | 2022-07-18 | 000000020554417 | 1050 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.5866% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2022-07-18 | 2021/22 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 350 |  |  |  | 350 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.1955% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00. Accrued invoice that we received. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2022-08-18 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | -350 |  |  |  | -350 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | -0.1955% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00. The invoice was cancelled by HED. Reversed accrual from prior year. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2022-10-06 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 350 | 980196 | 2022-10-06 | 000000020661323 | 350 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.1955% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2022-10-06 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 140 | 980805 | 2022-10-06 | 000000020661323 | 140 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.07821% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2022-10-28 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 210 | 981114R | 2022-10-28 | 000000020698109 | 210 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.1173% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2022-11-25 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 350 | 981950 | 2022-11-25 | 000000020738352 | 350 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0.1955% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-01-10 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2450 | 982360 | 2023-01-10 | 000000020796322 | 2450 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.369% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-01-25 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2450 | 982713 | 2023-01-25 | 000000020822004 | 2450 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.369% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-03-07 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2100 | 983097 | 2023-03-07 | 000000020889963 | 2100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.173% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-05-18 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2100 | 983453 | 2023-05-18 | 000000021019982 | 2100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.173% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-05-18 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2800 | 983930 | 2023-05-18 | 000000021019982 | 2800 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.564% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-07-14 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2100 | 984278 | 2023-07-14 | 000000021126788 | 2100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.173% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-07-19 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2450 | 984603 | 2023-07-19 | 000000021132853 | 2450 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.369% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-08-28 | 2022/23 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2800 | 985087 | 2023-08-28 | 000000021185719 | 2800 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.564% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-10-02 | 2023/24 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 3500 | 985476 | 2023-10-02 | 000000021240035 | 3500 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.955% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-12-05 | 2023/24 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2100 | 986329 | 2023-12-05 | 000000021351312 | 2100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.173% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2023-12-18 | 2023/24 |  | PO2W-200000001207, 19-100507, 18-109551 | 0 | 2800 | 985948 | 2023-12-18 | 000000021374459 | 2800 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 1.564% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-06-13 | 2026-06-01 | 2023/24 | 2-517 | PO2W-200000001207, 19-100507, 18-109551 | 33019 | 33019 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121101 | 0% | Architect - To modernize and upgrade Grandview to create classrooms for the 21st Century project. Include allowances of $39,000.00. The total architect costs with the change orders (PO2W-21*359 & 23*1310) is $294,300.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2020-08-07 | 2020-12-08 | 2020/21 | 21-1214 | PO2W-210000000359 | 0 | 81300 | 972626 | 2020-12-08 | 000000020148209 | 81300 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 100% | Architect - Modifications to Architect services for Grandview 21st Century, per District's request. Change order #1. To pay for: Mod 3 - Restroom, Mod 5 - Mock-up room 61, Mod 6 - Contract deviations, & Mod 7 - New Standards. Addendum to PO2W-20*1207. The total architect costs with the change orders (this PO & PO2W-23*1310) is $294,300.00. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-03 | 2022/23 |  | PO2W-230000001310 | 0 | 3400 | 981575 | 2022-11-03 | 000000020706421 | 3400 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 4.25% | Architect - Modifications to Architect services for Grandview 21st Century (Mod 8 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1207. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*359) is $294,300.00. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-03 | 2022/23 |  | PO2W-230000001310 | 0 | 27200 | 981114A | 2022-11-03 | 000000020706421 | 27200 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 34% | Architect - Modifications to Architect services for Grandview 21st Century (Mod 8 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1207. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*359) is $294,300.00. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-28 | 2022/23 |  | PO2W-230000001310 | 0 | 1700 | 981950A | 2022-11-28 | 000000020738352 | 1700 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 2.125% | Architect - Modifications to Architect services for Grandview 21st Century (Mod 8 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1207. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*359) is $294,300.00. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-01-10 | 2022/23 |  | PO2W-230000001310 | 0 | 1020 | 982360A | 2023-01-10 | 000000020796322 | 1020 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 1.275% | Architect - Modifications to Architect services for Grandview 21st Century (Mod 8 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1207. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*359) is $294,300.00. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-01-25 | 2022/23 |  | PO2W-230000001310 | 0 | 170 | 982713A | 2023-01-25 | 000000020822004 | 170 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 0.2125% | Architect - Modifications to Architect services for Grandview 21st Century (Mod 8 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1207. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*359) is $294,300.00. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Design | 2 | Design | Grandview | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-05-23 | 2022/23 | 23-2644 | PO2W-230000001310 | 0 | 510 | 983930A | 2023-05-23 | 000000021027448 | 510 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9121101 | 0.6375% | Architect - Modifications to Architect services for Grandview 21st Century (Mod 8 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1207. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*359) is $294,300.00. | Grandview-2-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 2018/19 |  | PO2W-200000001210, 19-101980 | 0 | 2312.3 | 966481 | 2018-10-19 | 24871020 | 2312.3 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.705% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-09-16 | 2018/19 |  | PO2W-200000001210, 19-101980 | 0 | 12717.65 | 968552R | 2019-09-16 | 000000020015463 | 12717.65 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 9.378% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-02-13 | 2019/20 |  | PO2W-200000001210, 19-101980 | 0 | 16186.1 | 970829 | 2020-02-13 | 000000020070049 | 16186.1 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 11.94% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-06-04 | 2019/20 |  | PO2W-200000001210, 19-101980 | 0 | 19076.48 | 971445 | 2020-06-04 | 000000020102538 | 19076.48 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 14.07% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-09-10 | 2020/21 |  | PO2W-200000001210, 19-101980 | 0 | 11738 | 971454R | 2020-09-10 | 000000020125582 | 11738 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 8.655% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. Allowances for civil engineering for path of travel (Mod 1 dated 02/11/19). The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001210, 19-101980 | 0 | 9538.23 | 971723R | 2021-05-07 | 000000020187161 | 9538.23 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 7.033% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001210, 19-101980 | 0 | 9538.24 | 972096R | 2021-05-07 | 000000020187161 | 9538.24 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 7.033% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-06-23 | 2020/21 |  | PO2W-200000001210, 19-101980 | 0 | 2890.38 | 975779 | 2021-06-23 | 000000020200446 | 2890.38 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 2.131% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-12-20 | 2021/22 |  | PO2W-200000001210, 19-101980 | 0 | 867.11 | 96675 | 2021-12-20 | 000000020370745 | 867.11 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0.6394% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-07-18 | 2021/22 |  | PO2W-200000001210, 19-101980 | 0 | 289.03 | 977970 | 2022-07-18 | 000000020554417 | 289.03 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0.2131% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-07-18 | 2021/22 |  | PO2W-200000001210, 19-101980 | 0 | 867.11 | 979949 | 2022-07-18 | 000000020554417 | 867.11 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0.6394% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-07-18 | 2021/22 |  | PO2W-200000001210, 19-101980 | 0 | 289.04 | 980197 | 2022-07-18 | 000000020554417 | 289.04 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0.2131% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-10-06 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 115.61 | 980807 | 2022-10-06 | 000000020661323 | 115.61 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0.08525% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-10-28 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 173.42 | 981115R | 2022-10-28 | 000000020698109 | 173.42 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0.1279% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-01-10 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 2312.3 | 982361 | 2023-01-10 | 000000020796322 | 2312.3 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.705% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-01-25 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 2023.28 | 982712 | 2023-01-25 | 000000020822004 | 2023.28 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.492% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-03-07 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 1734.21 | 983100 | 2023-03-07 | 000000020889963 | 1734.21 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.279% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-05-18 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 2023.27 | 983412 | 2023-05-18 | 000000021019982 | 2023.27 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.492% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-05-18 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 2023.27 | 983931 | 2023-05-18 | 000000021019982 | 2023.27 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.492% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-07-14 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 1734.22 | 984279 | 2023-07-14 | 000000021126788 | 1734.22 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.279% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-07-19 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 2023.26 | 984604 | 2023-07-19 | 000000021132853 | 2023.26 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.492% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-08-28 | 2022/23 |  | PO2W-200000001210, 19-101980 | 0 | 2312.3 | 985095 | 2023-08-28 | 000000021185719 | 2312.3 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.705% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-10-02 | 2023/24 |  | PO2W-200000001210, 19-101980 | 0 | 2890.38 | 985479 | 2023-10-02 | 000000021240035 | 2890.38 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 2.131% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-11-21 | 2023/24 |  | PO2W-200000001210, 19-101980 | 0 | 2312.3 | 985951 | 2023-11-21 | 000000021333526 | 2312.3 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.705% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-12-05 | 2023/24 |  | PO2W-200000001210, 19-101980 | 0 | 1734.22 | 986331 | 2023-12-05 | 000000021351312 | 1734.22 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 1.279% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2026-06-01 | 2023/24 | 2-521 | PO2W-200000001210, 19-101980 | 25893.29 | 25893.29 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241101 | 0% | Architect - To modernize and upgrade Newton to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*360 & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2020-08-07 | 2020-09-10 | 2020/21 | 21-1215 | PO2W-210000000360 | 0 | 85965 | 972646 | 2020-09-10 | 000000020125582 | 85965 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 100% | Architect - Modifications to Architect services for Newton 21st Century, per District's request. To pay for : Mod 2 - CADD as builts, Mod 3 - Restrooms, Mod 4 - Contract deviations, & Mod 5 - New Standards. Addendum to PO2W-20*1210. Change order #1. The total architect costs with the change orders (this PO & 23*1310) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-03 | 2022/23 |  | PO2W-230000001310 | 0 | 2300 | 981575 | 2022-11-03 | 000000020706421 | 2300 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 2.875% | Architect - Modifications to Architect services for Newton 21st Century (Mod 6 R1 - modifications to the original scope & structural engineering). Addendum to PO2W-20*1210. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*360) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-03 | 2022/23 |  | PO2W-230000001310 | 0 | 18400 | 981114A | 2022-11-03 | 000000020706421 | 18400 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 23% | Architect - Modifications to Architect services for Newton 21st Century (Mod 6 R1 - modifications to the original scope & structural engineering). Addendum to PO2W-20*1210. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*360) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-28 | 2022/23 |  | PO2W-230000001310 | 0 | 1150 | 981950A | 2022-11-28 | 000000020738352 | 1150 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 1.438% | Architect - Modifications to Architect services for Newton 21st Century (Mod 6 R1 - modifications to the original scope & structural engineering). Addendum to PO2W-20*1210. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*360) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-01-10 | 2022/23 |  | PO2W-230000001310 | 0 | 690 | 982360A | 2023-01-10 | 000000020796322 | 690 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 0.8625% | Architect - Modifications to Architect services for Newton 21st Century (Mod 6 R1 - modifications to the original scope & structural engineering). Addendum to PO2W-20*1210. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*360) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-01-25 | 2022/23 |  | PO2W-230000001310 | 0 | 115 | 982713A | 2023-01-25 | 000000020822004 | 115 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 0.1437% | Architect - Modifications to Architect services for Newton 21st Century (Mod 6 R1 - modifications to the original scope & structural engineering). Addendum to PO2W-20*1210. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*360) is $244,580.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Design | 1 | Design | Newton | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-05-23 | 2022/23 | 23-2644 | PO2W-230000001310 | 0 | 345 | 983930A | 2023-05-23 | 000000021027448 | 345 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241101 | 0.4313% | Architect - Modifications to Architect services for Newton 21st Century (Mod 6 R1 - modifications to the original scope & structural engineering). Addendum to PO2W-20*1210. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*360) is $244,580.00 | Newton-1-21st Century classroom
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2021-12-15 | 2026-12-09 | 2023/24 | 22-3670 | PO1-220000000605 | 1725 | 1725 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 0% | Architect - Modifications to Architect services for Newton Interim Housing parking lot. Additional design service fee for the civil engineering to conduct topographic survey for redesigning the existing ADA parking stalls/accessible ramp (Mod 5 dated 12/06/21). Addendum to PO2W-20*1208. Change order #3. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 2018/19 |  | PO2W-200000001208, 19-101983 | 0 | 1006.76 | 966483 | 2018-10-19 | 24871020 | 1006.76 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 1.431% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-02-28 | 2018/19 |  | PO2W-200000001208, 19-101983 | 0 | 11511.5 | 967630 | 2019-02-28 | 25125651 | 11511.5 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 16.37% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. Allowances for site survey (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $24,520.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-09-16 | 2018/19 |  | PO2W-200000001208, 19-101983 | 0 | 12584.52 | 968554R | 2019-09-16 | 000000020015463 | 12584.52 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 17.89% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-09-17 | 2018/19 |  | PO2W-200000001208, 19-101983 | 0 | 24.36 |  |  |  | 24.36 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 0% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08. Accrued invoice in the amount of $24.36 (for allowances). | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-03-10 | 2019/20 |  | PO2W-200000001208, 19-101983 | 0 | -24.36 |  |  |  | -24.36 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 0% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08. The invoice for allowances was cancelled by HED. Reversed accrual from prior year. | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-04-02 | 2019/20 |  | PO2W-200000001208, 19-101983 | 0 | 16611.57 | 970837 | 2020-04-02 | 000000020086379 | 16611.57 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 23.62% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001208, 19-101983 | 0 | 8488.5 | 971456 | 2021-05-07 | 000000020187161 | 8488.5 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 12.07% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. Allowances for site survey (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $24,520.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-06-02 | 2020/21 |  | PO2W-200000001208, 19-101983 | 0 | 1258.45 | 972926 | 2021-06-02 | 000000020194098 | 1258.45 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 1.789% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-12-20 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 1258.45 | 976673 | 2021-12-20 | 000000020370745 | 1258.45 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 1.789% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-03-11 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 5033.81 | 978312 | 2022-03-11 | 000000020441852 | 5033.81 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 7.157% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-03-11 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 2516.9 | 978476 | 2022-03-11 | 000000020441852 | 2516.9 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 3.578% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-03-24 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 3146.13 | 978836 | 2022-03-24 | 000000020451058 | 3146.13 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 4.473% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-05-04 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 880.92 | 979189 | 2022-05-04 | 000000020484155 | 880.92 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 1.252% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-07-19 | 2021/22 |  | PO2W-200000001208, 19-101983 | 0 | 377.53 | 980200 | 2022-07-19 | 000000020555834 | 377.53 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 0.5367% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-10-06 | 2022/23 |  | PO2W-200000001208, 19-101983 | 0 | 377.54 | 980808 | 2022-10-06 | 000000020661323 | 377.54 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 0.5368% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-01-25 | 2022/23 |  | PO2W-200000001208, 19-101983 | 0 | 755.07 | 982714 | 2023-01-25 | 000000020822004 | 755.07 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 1.073% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-05-18 | 2022/23 |  | PO2W-200000001208, 19-101983 | 0 | 4027.05 | 983423 | 2023-05-18 | 000000021019982 | 4027.05 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 5.725% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-05-19 | 2022/23 | 2-518 | PO2W-200000001208, 19-101983 | 4.6612e-12 | 503.38 | 983892 | 2023-05-19 | 000000021022640 | 503.38 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241102 | 0.7157% | Architect - To provide interim housing at Newton during renovation of existing classrooms. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*374, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2020-08-10 | 2021-05-07 | 2020/21 | 21-1247 | PO2W-210000000374 | 0 | 4520 | 971456R | 2021-05-07 | 000000020187161 | 4520 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 100% | Architect - Modifications to Architect services for Newton Interim Housing, per District's request (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $24,520.00. Addendum to PO2W-20*1208. Change order #1. The total architect costs with the change orders (this PO, 21*1831, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Newton-Interim Housing-Design | 1 | Design | Newton | Interim Housing | Harley Ellis Devereaux (HED) | Architect | 2021-02-24 | 2021-05-07 | 2020/21 | 21-4651 | PO2W-210000001831 | 0 | 5000 | 972466R | 2021-05-07 | 000000020187161 | 5000 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 100% | Architect - Modifications to Architect services for Newton Interim Housing, to change fire alarm system to a non-voice evacuation type system (Mod 4 dated 06/01/20, revision 2). Addendum to PO2W-20*1208. Change order #2. The total architect costs with the change orders (this PO, PO2W-21*374, & PO1-22*605) is $81,583.08 | Newton-1-Interim Housing
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2018-10-19 | 2018/19 |  | PO2W-200000001211, 19-101981 | 0 | 1757.34 | 966482 | 2018-10-19 | 24871020 | 1757.34 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.629% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2019-02-27 | 2018/19 |  | PO2W-200000001211, 19-101981 | 0 | 11610.5 | 967629 | 2019-02-27 | 25120799 | 11610.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 10.76% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. Allowances for site survey (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $22,616.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-02-13 | 2019/20 |  | PO2W-200000001211, 19-101981 | 0 | 21966.75 | 970833 | 2020-02-13 | 000000020070049 | 21966.75 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 20.36% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-02-14 | 2018/19 |  | PO2W-200000001211, 19-101981 | 0 | 53.76 |  |  |  | 53.76 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00. Accrued invoice in the amount of $53.76 (for allowances). | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-03-10 | 2019/20 |  | PO2W-200000001211, 19-101981 | 0 | -53.76 |  |  |  | -53.76 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00. The invoice for allowances was cancelled by HED. Reversed accrual from prior year. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-06-18 | 2019/20 |  | PO2W-200000001211, 19-101981 | 0 | 14498.06 | 971446 | 2020-06-18 | 000000020106504 | 14498.06 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 13.44% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2020-12-08 | 2020/21 |  | PO2W-200000001211, 19-101981 | 0 | 8389.5 | 971455R | 2020-12-08 | 000000020148212 | 8389.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 7.778% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. Allowances for civil engineering for all path of travel (Part of mod 1 - site survey & Mod 2 - civil engineering). Total charged for mod 1 & 2 is $22,616.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001211, 19-101981 | 0 | 7249.02 | 971722R | 2021-05-07 | 000000020187161 | 7249.02 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 6.72% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-05-07 | 2020/21 |  | PO2W-200000001211, 19-101981 | 0 | 7249.03 | 972097R | 2021-05-07 | 000000020187161 | 7249.03 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 6.72% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-06-23 | 2020/21 |  | PO2W-200000001211, 19-101981 | 0 | 2196.68 | 975781 | 2021-06-23 | 000000020200446 | 2196.68 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 2.036% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2021-12-20 | 2021/22 |  | PO2W-200000001211, 19-101981 | 0 | 659 | 976676 | 2021-12-20 | 000000020370745 | 659 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0.6109% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-07-18 | 2021/22 |  | PO2W-200000001211, 19-101981 | 0 | 219.67 | 977968 | 2022-07-18 | 000000020554417 | 219.67 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0.2036% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-07-18 | 2021/22 |  | PO2W-200000001211, 19-101981 | 0 | 659 | 979950 | 2022-07-18 | 000000020554417 | 659 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0.6109% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-07-18 | 2021/22 |  | PO2W-200000001211, 19-101981 | 0 | 219.67 | 980198 | 2022-07-18 | 000000020554417 | 219.67 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0.2036% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2022-11-03 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 219.66 | 981116 | 2022-11-03 | 000000020706421 | 219.66 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0.2036% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-01-10 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 1757.34 | 982362 | 2023-01-10 | 000000020796322 | 1757.34 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.629% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-01-25 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 1537.68 | 982711 | 2023-01-25 | 000000020822004 | 1537.68 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.426% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-03-07 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 1318 | 983102 | 2023-03-07 | 000000020889963 | 1318 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.222% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-05-18 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 1537.67 | 983418 | 2023-05-18 | 000000021019982 | 1537.67 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.426% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-05-18 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 1537.68 | 983932 | 2023-05-18 | 000000021019982 | 1537.68 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.426% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-07-14 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 1318 | 984282 | 2023-07-14 | 000000021126788 | 1318 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.222% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-07-19 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 1537.67 | 984606 | 2023-07-19 | 000000021132853 | 1537.67 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.426% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-08-28 | 2022/23 |  | PO2W-200000001211, 19-101981 | 0 | 1757.34 | 985101 | 2023-08-28 | 000000021185719 | 1757.34 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.629% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-10-02 | 2023/24 |  | PO2W-200000001211, 19-101981 | 0 | 2196.68 | 985480 | 2023-10-02 | 000000021240035 | 2196.68 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 2.036% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-11-21 | 2023/24 |  | PO2W-200000001211, 19-101981 | 0 | 1757.34 | 985952 | 2023-11-21 | 000000021333526 | 1757.34 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 1.629% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2023-12-05 | 2023/24 |  | PO2W-200000001211, 19-101981 | 0 | 8567.03 | 986332 | 2023-12-05 | 000000021351312 | 8567.03 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 7.942% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2018-09-01 | 2026-06-01 | 2023/24 | 2-522 | PO2W-200000001211, 19-101981 | 6150.69 | 6150.69 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301101 | 0% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2020-08-07 | 2020-12-08 | 2020/21 | 21-1216 | PO2W-210000000403 | 0 | 64990 | 972635 | 2020-12-08 | 000000020148210 | 64990 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 96.13% | Architect - Modifications to Architect services for Sparks MS 21st Century, per District's request (Part of mod 1 - Site survey & mod 2 - civil engineering). Total charged for mod 1 & 2 is $22,616.00 & available allowance amount is : $20,000.00. Addendum to PO2W-20*1211. Change order #1. The total architect costs with the change orders (this PO & PO2W-23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2020-08-07 | 2020-12-08 | 2020/21 |  | PO2W-210000000403 | 0 | 2616 | 971455R | 2020-12-08 | 000000020148212 | 2616 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 3.869% | Architect - To modernize and upgrade Sparks MS to create classrooms for the 21st Century project. Include allowances of $20,000.00. The total architect costs with the change orders (PO2W-21*403 & 23*1310) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-03 | 2022/23 |  | PO2W-230000001310 | 0 | 2300 | 981575 | 2022-11-03 | 000000020706421 | 2300 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 2.875% | Architect - Modifications to Architect services for Sparks MS 21st Century (Mod 6 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1211. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*403) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-03 | 2022/23 |  | PO2W-230000001310 | 0 | 18400 | 981114A | 2022-11-03 | 000000020706421 | 18400 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 23% | Architect - Modifications to Architect services for Sparks MS 21st Century (Mod 6 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1211. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*403) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2022-11-28 | 2022/23 |  | PO2W-230000001310 | 0 | 1150 | 981950A | 2022-11-28 | 000000020738352 | 1150 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 1.438% | Architect - Modifications to Architect services for Sparks MS 21st Century (Mod 6 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1211. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*403) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-01-10 | 2022/23 |  | PO2W-230000001310 | 0 | 690 | 982360A | 2023-01-10 | 000000020796322 | 690 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 0.8625% | Architect - Modifications to Architect services for Sparks MS 21st Century (Mod 6 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1211. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*403) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-01-25 | 2022/23 |  | PO2W-230000001310 | 0 | 115 | 982713A | 2023-01-25 | 000000020822004 | 115 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 0.1437% | Architect - Modifications to Architect services for Sparks MS 21st Century (Mod 6 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1211. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*403) is $198,473.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Design | 2 | Design | Sparks MS | 21st Century classroom | Harley Ellis Devereaux (HED) | Architect | 2022-09-21 | 2023-05-23 | 2022/23 | 23-2644 | PO2W-230000001310 | 0 | 345 | 983930A | 2023-05-23 | 000000021027448 | 345 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9301101 | 0.4313% | Architect - Modifications to Architect services for Sparks MS 21st Century (Mod 6 R1 - modifications to the original scope, structural & civil engineering). Addendum to PO2W-20*1211. Change order #2. The total architect costs with the change orders (this PO & PO2W-21*403) is $198,473.00 | Sparks MS-2-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Haul-Away Rubbish Service Co. | Rental/Moving of container(s) | 2021-02-11 | 2021-02-22 | 2020/21 |  | PO1-210000000609 | 0 | 125.17 | 0CX00268 | 2021-02-22 | 000000020166211 | 125.17 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 100% | Rental of 1 container for Mesa Robles. Monthly rental is $65.17 for the first month to include taxes, delivery and pick-up fees. After the intial month, the monthly rental rate is $85.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Haul-Away Rubbish Service Co. | Rental/Moving of container(s) | 2021-02-11 | 2021-02-23 | 2020/21 |  | PO1-210000000609 | 1116.9 | 1116.9 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0% | Rental of 1 container for Mesa Robles. Monthly rental is $65.17 for the first month to include taxes, delivery and pick-up fees. After the intial month, the monthly rental rate is $85.00/month through December 2021. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Haul-Away Rubbish Service Co. | Rental/Moving of container(s) | 2021-02-11 | 2021-06-30 | 2020/21 | 21-4313 | PO1-210000000609 | -1116.9 | -1116.9 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0% | Rental of 1 container for Mesa Robles. Monthly rental is $65.17 for the first month to include taxes, delivery and pick-up fees. After the intial month, the monthly rental rate is $85.00/month through December 2021. Close-out PO. | Mesa Robles-1-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Hawkins Delafield & Wood LLP | Bond Counsel and Disclosure Counsel Fees | 2017-07-11 | 2017-07-11 | 2017/18 |  | N/A - Cost of Issuance | 0 | 115000 |  |  |  | 115000 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Bond Counsel and Disclosure Counsel Fees, 18-KT005 | District Office-0-Cost of Issuance
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 32910709-008 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 32910709-009 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 32910709-010 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 32910709-011 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 32910709-012 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 32910709-013 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 32910709-014 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 32910709-015 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 186.04 | 33904390-001 | 2023-12-18 | 000000021374459 | 186.04 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 4% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 33904390-002 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 33904390-003 | 2023-12-18 | 000000021374459 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-18 | 2023/24 |  | PO2W-240000001651 | 0 | -350 | 90000201-010 | 2023-12-18 | 000000021374459 | -350 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | -7.525% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. Credit memo from vendor. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2023-12-19 | 2023/24 |  | PO2W-240000001651 | 0 | 166.24 | 33904390-004 | 2023-12-19 | 000000021377398 | 166.24 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.574% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Herc Rentals Inc. | Rental/Moving of container(s) | 2023-10-26 | 2025-12-09 | 2023/24 | 24-3613 | PO2W-240000001651 | 2986.32 | 2986.32 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 0% | Rental of 1 - 20' dry container at Grandview. The monthly rental rate is $150.00/month. | Grandview-2-21st Century classroom
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Home Depot | Hardware to install access point for classrooms | 2020-05-18 | 2020-06-17 | 2019/20 | 2-10194 | PO1-200000001148 | 0 | 198.23 | 8010077 | 2020-06-17 | 000000020106127 | 198.23 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9851100 | 100% | Hardware to install access point for classrooms-Shelf brackets, screws, and drill bits for District-wide use | District Office-0-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 163.5 | 35255 | 2021-10-21 | 000000020304825 | 163.5 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9051101 | 5.3% | Walked and reviewed site for the wireless door contacts installation at Cedarlane. Repair damage caused by bond work. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 2169.1 | 35275 | 2021-10-21 | 000000020304825 | 2169.1 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9051101 | 70.32% | Troubleshot intercom system, was unable to hear bell system at Cedarlane. Repair damage caused by bond work. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5992 | PO3W-210000002406 | 0 | 2660.68 | 34985 | 2021-06-07 | 000000020195370 | 2660.68 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 31.87% | Equipment to repair & replace security system at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5992 | PO3W-210000002406 | 0 | 558.94 | 34985 | 2021-06-07 | 000000020195370 | 558.94 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 6.694% | Equipment to repair & replace security system at Cedarlane | Cedarlane-1-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 130.8 | 35256 | 2021-10-21 | 000000020304825 | 130.8 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9191101 | 4.24% | Walked and reviewed site for the wireless door contacts installation at Los Altos ES. Repair damage caused by bond work. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5994 | PO3W-210000002406 | 0 | 1971.64 | 34985 | 2021-06-07 | 000000020195370 | 1971.64 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 23.61% | Equipment to repair & replace security system at Los Altos ES | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5994 | PO3W-210000002406 | 0 | 558.94 | 34985 | 2021-06-07 | 000000020195370 | 558.94 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 6.694% | Equipment to repair & replace security system at Los Altos ES | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 479.6 | 35253 | 2021-10-21 | 000000020304825 | 479.6 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9221101 | 15.55% | Walked and reviewed site for the wireless door contacts installation at Mesa Robles. Repair damage caused by bond work. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2021-04-22 | 2021-06-07 | 2020/21 | 21-6038 | PO3W-210000002442 | 0 | 2867.39 | 34986 | 2021-06-07 | 000000020195370 | 2867.39 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 83.69% | Equipment to repair & replace security system at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2021-04-22 | 2021-06-07 | 2020/21 | 21-6038 | PO3W-210000002442 | 0 | 558.94 | 34986 | 2021-06-07 | 000000020195370 | 558.94 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 16.31% | Equipment to repair & replace security system at Mesa Robles | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | ICS Service Co. | Contractor | 2021-10-06 | 2021-10-21 | 2021/22 | 22-2317 | PO2W-220000000706 | 0 | 141.7 | 35254 | 2021-10-21 | 000000020304825 | 141.7 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 5800 | 9231101 | 4.594% | Walked and reviewed site for the wireless door contacts installation at Nelson. Repair damage caused by bond work. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5995 | PO3W-210000002406 | 0 | 2040.54 | 34985 | 2021-06-07 | 000000020195370 | 2040.54 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 24.44% | Equipment to repair & replace security system at Nelson | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2021-04-20 | 2021-06-07 | 2020/21 | 21-5995 | PO3W-210000002406 | 0 | 558.94 | 34985 | 2021-06-07 | 000000020195370 | 558.94 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 6.694% | Equipment to repair & replace security system at Nelson | Nelson-1-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2020-11-30 | 2021-04-16 | 2020/21 |  | PO2W-210000001354 | 0 | 507.43 | 34750 | 2021-04-16 | 000000020181028 | 507.43 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 24.52% | Equipment to repair & replace security system at Workman ES | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2020-11-30 | 2021-04-16 | 2020/21 | 21-3242 | PO2W-210000001354 | 0 | 603.66 | 34750 | 2021-04-16 | 000000020181028 | 603.66 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 29.18% | Equipment to repair & replace security system at Workman ES | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | ICS Service Co. | Equipment to repair & replace security system | 2020-11-30 | 2022-06-03 | 2021/22 | 21-3242 | PO2W-210000001354 | 0 | 957.98 | 35917 | 2022-06-03 | 000000020516592 | 957.98 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 46.3% | Equipment to repair & replace security system at Workman ES | Workman ES-2-21st Century classroom
Baldwin-21st Century classroom-Contractor | 3 | Contractor | Baldwin | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 2020/21 | 21-4688 | PO2W-210000001838 | 0 | 50000 | 2021-022D | 2021-04-23 | 000000020182905 | 50000 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021101 | 38.46% | Demo of ceiling tiles in 20 classrooms at Baldwin | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Contractor | 3 | Contractor | Baldwin | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-06-14 | 2021-09-09 | 2021/22 | 21-6790 | PO2W-210000002615 | 0 | 6500 | 2021-088D | 2021-09-09 | 000000020255195 | 6500 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021101 | 38.24% | Demo of ceiling tiles in 2 classrooms at Baldwin for room #TK-KA & TK-KB | Baldwin-3-21st Century classroom
Bixby-21st Century classroom-Contractor | 6 | Contractor | Bixby | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-05-11 | 2021-06-28 | 2020/21 | 21-6371 | PO2W-210000002308 | 0 | 52500 | 2021-061A | 2021-06-28 | 000000020201777 | 52500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9031101 | 100% | Demo of ceiling tiles in 21 classrooms at Bixby | Bixby-6-21st Century classroom
California-21st Century classroom-Contractor | 3 | Contractor | California | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2021-04-23 | 2020/21 | 21-1882 | PO2W-210000000658 | 0 | 40000 | 2020-089A | 2021-04-23 | 000000020182905 | 40000 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041101 | 100% | Demo of ceiling tiles in 16 classrooms at California | California-3-21st Century classroom
Del Valle-21st Century classroom-Contractor | 7 | Contractor | Del Valle | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2020-11-30 | 2020/21 | 21-1830 | PO2W-210000000725 | 0 | 42500 | 2020-086AD | 2020-11-30 | 000000020145591 | 42500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061101 | 100% | Demo of ceiling tiles in 17 classrooms at Del Valle | Del Valle-7-21st Century classroom
Grazide-21st Century classroom-Contractor | 3 | Contractor | Grazide | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2021-03-24 | 2020/21 | 21-3656 | PO2W-210000001556 | 0 | 37500 | 2021-006D | 2021-03-24 | 000000020174720 | 37500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131101 | 38.46% | Demo of ceiling tiles in 15 classrooms at Grazide | Grazide-3-21st Century classroom
Kwis-21st Century classroom-Contractor | 7 | Contractor | Kwis | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-04-06 | 2021-05-26 | 2020/21 | 21-5873 | PO2W-210000002060 | 0 | 42500 | 2021-044D | 2021-05-26 | 000000020192522 | 42500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161101 | 51.52% | Demo of ceiling tiles in 17 classrooms at Kwis | Kwis-7-21st Century classroom
Kwis-21st Century classroom-Contractor | 7 | Contractor | Kwis | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-06-14 | 2021-09-09 | 2021/22 | 21-6790 | PO2W-210000002615 | 0 | 6500 | 2021-088D | 2021-09-09 | 000000020255195 | 6500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161101 | 38.24% | Demo of ceiling tiles in 2 classrooms at Kwis for room #4 & 7 | Kwis-7-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-06-05 | 2020-08-18 | 2019/20 | 2-10679 | PO2W-200000005820 | 0 | 18000 | 2019-032A-8 | 2020-08-18 | 000000020120080 | 18000 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 100% | Asbestos abatement of floor tile at Los Altos ES classroom B3, C1, and work room between C1 & C2. Demolish and haul off casework. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-07-06 | 2020-10-13 | 2020/21 | 21-397 | PO2W-210000000146 | 0 | 32000 | 2019-032A-10 | 2020-10-13 | 000000020134080 | 32000 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 100% | Asbestos abatement of Los Altos ES floor tile in classroom E2, E3, E4, & F4. Demolish and haul off casework. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 2020/21 | 21-2378 | PO2W-210000000884 | 0 | 45000 | 2020-096D | 2020-11-20 | 000000020144493 | 45000 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 38.3% | Demo of ceiling tiles in 18 classrooms at Los Altos ES | Los Altos ES-2-21st Century classroom
Los Molinos-21st Century classroom-Contractor | 4 | Contractor | Los Molinos | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2021-03-24 | 2020/21 | 21-3656 | PO2W-210000001556 | 0 | 37500 | 2021-006D | 2021-03-24 | 000000020174720 | 37500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201101 | 38.46% | Demo of ceiling tiles in 15 classrooms at Los Molinos | Los Molinos-4-21st Century classroom
Los Robles-21st Century classroom-Contractor | 9 | Contractor | Los Robles | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-04-06 | 2021-05-26 | 2020/21 | 21-5873 | PO2W-210000002060 | 0 | 40000 | 2021-044D | 2021-05-26 | 000000020192522 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9211101 | 48.48% | Demo of ceiling tiles in 16 classrooms at Los Robles | Los Robles-9-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Contractor | 2020-01-31 | 2020-04-02 | 2019/20 | 2-7494 | PO2W-200000003741 | 0 | 12975 | 2019-032A | 2020-04-02 | 000000020086380 | 12975 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 100% | Interior demolition and haul of flooring, ceiling, casework, tack board, and electrical data for Nelson room #C1. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-07-06 | 2020-10-13 | 2020/21 | 21-398 | PO2W-210000000145 | 0 | 27860 | 2019-032A-11 | 2020-10-13 | 000000020134080 | 27860 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 100% | Asbestos abatement of Nelson floor tile in classroom A1, B1, B3, & mastic under cabinets in classroom B2 & B4. Demolish and haul off casework. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 2020/21 | 21-2378 | PO2W-210000000884 | 0 | 45000 | 2020-097D | 2020-11-20 | 000000020144493 | 45000 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 38.3% | Demo of ceiling tiles in 18 classrooms at Nelson | Nelson-1-21st Century classroom
Palm-21st Century classroom-Contractor | 6 | Contractor | Palm | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 2020/21 | 21-4688 | PO2W-210000001838 | 0 | 40000 | 2021-022D | 2021-04-23 | 000000020182905 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261101 | 30.77% | Demo of ceiling tiles in 16 classrooms at Palm | Palm-6-21st Century classroom
Sparks ES-21st Century classroom-Contractor | 7 | Contractor | Sparks ES | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-09-10 | 2020-10-13 | 2020/21 | 21-1828 | PO2W-210000000726 | 0 | 40000 | 2020-085AD | 2020-10-13 | 000000020134080 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291101 | 100% | Demo of ceiling tiles in 17 classrooms at Sparks ES | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-Contractor | 7 | Contractor | Sparks ES | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-06-14 | 2021-09-09 | 2021/22 | 21-6790 | PO2W-210000002615 | 0 | 4000 | 2021-088D | 2021-09-09 | 000000020255195 | 4000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291101 | 23.53% | Demo of ceiling tiles in 1 classroom at Sparks ES for room #19 | Sparks ES-7-21st Century classroom
Sunset-21st Century classroom-Contractor | 4 | Contractor | Sunset | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-01-06 | 2021-03-24 | 2020/21 | 21-3656 | PO2W-210000001556 | 0 | 22500 | 2021-006D | 2021-03-24 | 000000020174720 | 22500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311101 | 23.08% | Demo of ceiling tiles in 9 classrooms at Sunset | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Contractor | 4 | Contractor | Sunset | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-07-16 | 2021-09-09 | 2021/22 | 22-321 | PO2W-220000000024 | 0 | 19000 | 2021-097D | 2021-09-09 | 000000020255195 | 19000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311101 | 100% | Demo of ceiling tiles in 7 classrooms at Sunset | Sunset-4-21st Century classroom
Wing Lane-21st Century classroom-Contractor | 9 | Contractor | Wing Lane | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2021-02-25 | 2021-04-23 | 2020/21 | 21-4688 | PO2W-210000001838 | 0 | 40000 | 2021-022D | 2021-04-23 | 000000020182905 | 40000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9371101 | 30.77% | Demo of ceiling tiles in 16 classrooms at Wing Lane | Wing Lane-9-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement & demolition | 2020-07-06 | 2020-08-18 | 2019/20 | 21-399 | PO2W-210000000144 | 0 | 32000 | 2019-032A-7 | 2020-08-18 | 000000020120080 | 32000 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 100% | Asbestos abatement of Workman ES floor tile in classroom #5,6,7, & 12. Demolish and haul off casework. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement | 2020-09-18 | 2021-03-24 | 2020/21 | 21-2008 | PO2W-210000000675 | 0 | 4250 | 2020-093A | 2021-03-24 | 000000020174720 | 4250 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 100% | Asbestos abatement of flooring at Workman ES for the staff bathroom | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | Integrated Demolition & Remediation, Inc. (IDR) | Demo ceiling tiles | 2020-10-09 | 2020-11-20 | 2020/21 | 21-2378 | PO2W-210000000884 | 0 | 27500 | 2020-093A-2 | 2020-11-20 | 000000020144493 | 27500 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 23.4% | Demo of ceiling tiles in 11 classrooms at Workman ES | Workman ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Integrated Pest Control Management | Termite service | 2020-08-07 | 2020-08-24 | 2020/21 | 21-1217 | PO2W-210000000362 | 0 | 785 | 25029 | 2020-08-24 | 000000020121275 | 785 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5570 | 9191101 | 100% | Termite service at room #A-4 for the interior open studs at Los Altos ES. | Los Altos ES-2-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | LACOE | Remaining funds-dep. into District's debt service fund & close acct. | 2017-12-14 | 2017-12-14 | 2017/18 |  | N/A - Cost of Issuance | 0 | 11211.58 |  |  |  | 11211.58 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Remaining funds - deposited into District's debt service fund & close account, 18-KT005 | District Office-0-Cost of Issuance
Amar-21st Century classroom-FF & E | 0 | FF & E | Amar | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5002 | PO3W-200000001592 | 0 | 43947.28 | 3205801119 | 2020-02-03 | 000000020065149 | 43947.28 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9011101 | 62.45% | Furniture for Amar - Chairs, mobile tchr desks, media towers, storage units, book nooks, toddler changing tables, etc | Amar-0-21st Century classroom
Amar-21st Century classroom-FF & E | 0 | FF & E | Amar | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5002 | PO3W-200000001592 | 0 | 26429.02 | 3205801119 | 2020-02-03 | 000000020065149 | 26429.02 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9011101 | 37.55% | Furniture for Amar - Chairs, mobile tchr desks, media towers, storage units, book nooks, toddler changing tables, etc | Amar-0-21st Century classroom
Amar-21st Century classroom-FF & E | 0 | FF & E | Amar | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5018 | PO3W-200000001595 | 0 | 7509.33 | 3207401219 | 2020-02-03 | 000000020065148 | 7509.33 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9011101 | 100% | Furniture for Amar - Desks, media towers, storage units, combo kitchens, etc. The original PO was for $245,447.23 - $237,937.90 (moved to fund 12.0, per Annie Bui) = $7,509.33 (remaining balance charged to bond). | Amar-0-21st Century classroom
Amar-21st Century classroom-FF & E | 0 | FF & E | Amar | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-01-31 | 2019/20 | 2-5020 | PO3W-200000001597 | 0 | 12081.12 | 3469331119 | 2020-01-31 | 000000020064674 | 12081.12 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9011101 | 81.66% | Furniture for Amar - Chairs, mobile tchr desk, media tower, storage units, etc | Amar-0-21st Century classroom
Amar-21st Century classroom-FF & E | 0 | FF & E | Amar | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-01-31 | 2019/20 | 2-5020 | PO3W-200000001597 | 0 | 2713.22 | 3469331119 | 2020-01-31 | 000000020064674 | 2713.22 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9011101 | 18.34% | Furniture for Amar - Chairs, mobile tchr desk, media tower, storage units, etc | Amar-0-21st Century classroom
Baldwin-21st Century classroom-FF & E | 3 | FF & E | Baldwin | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2019-12-19 | 2019/20 | 2-5017 | PO3W-200000001593 | 0 | 17081.11 | 3205971119 | 2019-12-19 | 000000020051312 | 17081.11 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 73.67% | Furniture for Baldwin - Chairs, mobile tchr desks, media towers, storage units, combo kitchens, etc. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-FF & E | 3 | FF & E | Baldwin | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2019-12-19 | 2019/20 | 2-5017 | PO3W-200000001593 | 0 | 6105.79 | 3205971119 | 2019-12-19 | 000000020051312 | 6105.79 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 26.33% | Furniture for Baldwin - Chairs, mobile tchr desks, media towers, storage units, combo kitchens, etc. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-FF & E | 3 | FF & E | Baldwin | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9021101 | 3.16% | Furniture for Baldwin - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-FF & E | 3 | FF & E | Baldwin | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9021101 | 1.655% | Furniture for Baldwin - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Baldwin-3-21st Century classroom
Bixby-21st Century classroom-FF & E | 6 | FF & E | Bixby | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9031101 | 3.16% | Furniture for Bixby - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Bixby-6-21st Century classroom
Bixby-21st Century classroom-FF & E | 6 | FF & E | Bixby | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9031101 | 1.655% | Furniture for Bixby - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Bixby-6-21st Century classroom
California-21st Century classroom-FF & E | 3 | FF & E | California | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9041101 | 3.16% | Furniture for California - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | California-3-21st Century classroom
California-21st Century classroom-FF & E | 3 | FF & E | California | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9041101 | 1.655% | Furniture for California - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | California-3-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-16 | 2020/21 | 21-3578 | PO2W-210000001495 | 0 | 18390.28 | 2322450221 | 2021-04-16 | 000000020181030 | 18390.28 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 46.37% | Furniture for Cedarlane - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-16 | 2020/21 | 21-3578 | PO2W-210000001495 | 0 | 21273.58 | 2322450221 | 2021-04-16 | 000000020181030 | 21273.58 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 53.63% | Furniture for Cedarlane - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9051101 | 3.16% | Furniture for Cedarlane - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 1.655% | Furniture for Cedarlane - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Cedarlane-1-21st Century classroom
Del Valle-21st Century classroom-FF & E | 7 | FF & E | Del Valle | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 27193.65 | 3207761219 | 2020-02-03 | 000000020065147 | 27193.65 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9061101 | 6.319% | Furniture for Del Valle - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Del Valle-7-21st Century classroom
Del Valle-21st Century classroom-FF & E | 7 | FF & E | Del Valle | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 14247.57 | 3207761219 | 2020-02-03 | 000000020065147 | 14247.57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9061101 | 3.311% | Furniture for Del Valle - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Del Valle-7-21st Century classroom
Fairgrove-21st Century classroom-FF & E | 4 | FF & E | Fairgrove | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 27193.64 | 3207761219 | 2020-02-03 | 000000020065147 | 27193.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9091101 | 6.319% | Furniture for Fairgrove - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-FF & E | 4 | FF & E | Fairgrove | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 14247.57 | 3207761219 | 2020-02-03 | 000000020065147 | 14247.57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9091101 | 3.311% | Furniture for Fairgrove - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Fairgrove-4-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2023-07-03 | 2024-12-09 | 2023/24 | 24-609 | PO2W-240000000105 | 0 | 9546.12 | 843410071823 | 2023-10-11 | 000000021258021 | 9546.12 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 35.59% | Furniture for Grandview - Tables, chairs, stools, mobile storage centers, mobile tchrs desks, etc. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2023-07-03 | 2024-12-09 | 2023/24 | 24-609 | PO2W-240000000105 | 0 | 17274.85 | 843410071823 | 2023-10-11 | 000000021258021 | 17274.85 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 64.41% | Furniture for Grandview - Tables, chairs, stools, mobile storage centers, mobile tchrs desks, etc. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 3.16% | Furniture for Grandview - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 1.655% | Furniture for Grandview - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2022-09-29 | 2023-07-10 | 2022/23 | 23-2901 | PO3W-230000000930 | 0 | 10350.68 | 631280051923 | 2023-07-10 | 000000021114930 | 10350.68 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 38.37% | Furniture for Grandview - Chairs, storage units, media tower, etc | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2022-09-29 | 2023-07-10 | 2022/23 | 23-2901 | PO3W-230000000930 | 0 | 16626.94 | 631280051923 | 2023-07-10 | 000000021114930 | 16626.94 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 61.63% | Furniture for Grandview - Chairs, storage units, media tower, etc | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2022-10-21 | 2023-05-01 | 2022/23 |  | PO3W-230000001205 | 0 | 8979.44 | 810721031323 | 2023-05-01 | 000000020985676 | 8979.44 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 16% | Furniture for Grandview room #21-24, 33, 34, 41, 43, 51-54, 61-64, & band room. Mobile media towers: 17 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2022-10-21 | 2023-06-05 | 2022/23 | 23-3483 | PO3W-230000001205 | 0 | 10101.87 | 673191051923 | 2023-06-05 | 000000021047675 | 10101.87 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9121101 | 18% | Furniture for Grandview room #21-24, 33, 34, 41, 43, 51-54, 61-64, & band room. Mobile media towers: 17 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2023-08-02 | 2023-10-30 | 2023/24 | 24-1390 | PO3W-240000000842 | 0 | 842.5 | 382347101023 | 2023-10-30 | 000000021293520 | 842.5 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 100% | Furniture for Grandview - Flex-Space premium Wobble chairs. | Grandview-2-21st Century classroom
Kwis-21st Century classroom-FF & E | 7 | FF & E | Kwis | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 23990.6 | 3207761219 | 2020-02-03 | 000000020065147 | 23990.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9161101 | 5.575% | Furniture for Kwis - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Kwis-7-21st Century classroom
Kwis-21st Century classroom-FF & E | 7 | FF & E | Kwis | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 14247.57 | 3207761219 | 2020-02-03 | 000000020065147 | 14247.57 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9161101 | 3.311% | Furniture for Kwis - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Kwis-7-21st Century classroom
Lassalette-21st Century classroom-FF & E | 6 | FF & E | Lassalette | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9171101 | 3.16% | Furniture for Lassalette - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Lassalette-6-21st Century classroom
Lassalette-21st Century classroom-FF & E | 6 | FF & E | Lassalette | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9171101 | 1.655% | Furniture for Lassalette - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Lassalette-6-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-02-17 | 2020/21 | 21-2985 | PO2W-210000001120 | 0 | 27585.39 | 2979771220 | 2021-02-17 | 000000020165087 | 27585.39 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 46.37% | Furniture for Los Altos ES. - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-02-17 | 2020/21 | 21-2985 | PO2W-210000001120 | 0 | 31910.4 | 2979771220 | 2021-02-17 | 000000020165087 | 31910.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 53.63% | Furniture for Los Altos ES. - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc. | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-05 | 2020/21 | 21-3579 | PO2W-210000001496 | 0 | 36780.56 | 2324500221 | 2021-04-05 | 000000020177583 | 36780.56 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 46.37% | Furniture for Mesa Robles - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-FF & E | 1 | FF & E | Mesa Robles | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-12-16 | 2021-04-05 | 2020/21 | 21-3579 | PO2W-210000001496 | 0 | 42547.14 | 2324500221 | 2021-04-05 | 000000020177583 | 42547.14 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 53.63% | Furniture for Mesa Robles - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc. | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2020-08-12 | 2020/21 | 2-9319 | PO2W-200000004769 | 0 | 9237.16 | 3539770720 | 2020-08-12 | 000000020118972 | 9237.16 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 41.6% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2020-08-12 | 2020/21 | 2-9319 | PO2W-200000004769 | 0 | 10685.34 | 3539770720 | 2020-08-12 | 000000020118972 | 10685.34 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 58.4% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2021-03-23 | 2020/21 | 2-9327 | PO2W-200000004771 | 0 | 8762.52 | 3584031220 | 2021-03-23 | 000000020174431 | 8762.52 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 43.98% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2021-03-23 | 2020/21 | 2-9327 | PO2W-200000004771 | 0 | 11159.98 | 3584031220 | 2021-03-23 | 000000020174431 | 11159.98 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 56.02% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2020-08-12 | 2020/21 | 2-9328 | PO2W-200000004776 | 0 | 9237.16 | 3585880720 | 2020-08-12 | 000000020118972 | 9237.16 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 41.6% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-03-17 | 2020-08-12 | 2020/21 | 2-9328 | PO2W-200000004776 | 0 | 10685.34 | 3585880720 | 2020-08-12 | 000000020118972 | 10685.34 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 58.4% | Furniture - sample for Nelson's kindergarteen classrooms - Flex-space mobile rectangular tables, ergo chairs, wobble chairs, carpets, storage units, comfy curved seats, bean bag seats, mobile book bin & tray storage centers, book and storage bins, storage centers, mobile student desks, adjustable stools, mobile locking media, mobile teacher desks, and all purpose 3-shelf storage units | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 27193.61 | 3207761219 | 2020-02-03 | 000000020065147 | 27193.61 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 6.319% | Furniture for Nelson - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-FF & E | 1 | FF & E | Nelson | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 14247.61 | 3207761219 | 2020-02-03 | 000000020065147 | 14247.61 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 3.311% | Furniture for Nelson - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Nelson-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2022-10-21 | 2023-05-01 | 2022/23 |  | PO3W-230000001205 | 0 | 4489.72 | 810753031323 | 2023-05-01 | 000000020985676 | 4489.72 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 8% | Furniture for Newton room #D-1-D-4, C-1-C-4, C-6-C-8, B-4, B-6-B8, A-1-A-4, & band room. Mobile media towers: 20 | Newton-1-21st Century classroom
Newton-21st Century classroom-FF & E | 1 | FF & E | Newton | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2022-10-21 | 2023-06-05 | 2022/23 | 23-3483 | PO3W-230000001205 | 0 | 17958.88 | 517262051623 | 2023-06-05 | 000000021047675 | 17958.88 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9241101 | 32% | Furniture for Newton room #D-1-D-4, C-1-C-4, C-6-C-8, B-4, B-6-B8, A-1-A-4, & band room. Mobile media towers: 20 | Newton-1-21st Century classroom
Palm-21st Century classroom-FF & E | 6 | FF & E | Palm | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 11995.3 | 3207761219 | 2020-02-03 | 000000020065147 | 11995.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9261101 | 2.787% | Furniture for Palm - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Palm-6-21st Century classroom
Palm-21st Century classroom-FF & E | 6 | FF & E | Palm | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9261101 | 1.655% | Furniture for Palm - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Palm-6-21st Century classroom
Sparks ES-21st Century classroom-FF & E | 7 | FF & E | Sparks ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9291101 | 3.16% | Furniture for Sparks ES - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Sparks ES-7-21st Century classroom
Sparks ES-21st Century classroom-FF & E | 7 | FF & E | Sparks ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9291101 | 1.655% | Furniture for Sparks ES - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Sparks ES-7-21st Century classroom
Sparks MS-21st Century classroom-FF & E | 2 | FF & E | Sparks MS | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2022-10-21 | 2023-05-01 | 2022/23 |  | PO3W-230000001205 | 0 | 8979.44 | 810654031323 | 2023-05-01 | 000000020985676 | 8979.44 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 16% | Furniture for Sparks MS room #9-20 & band room. Mobile media towers: 13 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-FF & E | 2 | FF & E | Sparks MS | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2022-10-21 | 2023-06-05 | 2022/23 | 23-3483 | PO3W-230000001205 | 0 | 5612.15 | 673167051823 | 2023-06-05 | 000000021047675 | 5612.15 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9301101 | 10% | Furniture for Sparks MS room #9-20 & band room. Mobile media towers: 13 | Sparks MS-2-21st Century classroom
Sunset-21st Century classroom-FF & E | 4 | FF & E | Sunset | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9311101 | 3.16% | Furniture for Sunset - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Sunset-4-21st Century classroom
Sunset-21st Century classroom-FF & E | 4 | FF & E | Sunset | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9311101 | 1.655% | Furniture for Sunset - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Sunset-4-21st Century classroom
Temple-21st Century classroom-FF & E | 8 | FF & E | Temple | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9331101 | 3.16% | Furniture for Temple - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Temple-8-21st Century classroom
Temple-21st Century classroom-FF & E | 8 | FF & E | Temple | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9331101 | 1.655% | Furniture for Temple - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Temple-8-21st Century classroom
Valinda-21st Century classroom-FF & E | 6 | FF & E | Valinda | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9341101 | 3.16% | Furniture for Valinda - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Valinda-6-21st Century classroom
Valinda-21st Century classroom-FF & E | 6 | FF & E | Valinda | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9341101 | 1.655% | Furniture for Valinda - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Valinda-6-21st Century classroom
Wing Lane-21st Century classroom-FF & E | 9 | FF & E | Wing Lane | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9371101 | 3.16% | Furniture for Wing Lane - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Wing Lane-9-21st Century classroom
Wing Lane-21st Century classroom-FF & E | 9 | FF & E | Wing Lane | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9371101 | 1.655% | Furniture for Wing Lane - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Wing Lane-9-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9237.13 | 2902451120 | 2021-03-24 | 000000020174722 | 9237.13 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.273% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 10685.36 | 2902451120 | 2021-03-24 | 000000020174722 | 10685.36 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 10.73% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9826.74 | 2979801120 | 2021-03-24 | 000000020174722 | 9826.74 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.865% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 11367.4 | 2979801120 | 2021-03-24 | 000000020174722 | 11367.4 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 11.41% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9826.74 | 2979811120 | 2021-03-24 | 000000020174722 | 9826.74 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.865% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 11367.4 | 2979811120 | 2021-03-24 | 000000020174722 | 11367.4 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 11.41% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9826.74 | 2979821120 | 2021-03-24 | 000000020174722 | 9826.74 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.865% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 11367.4 | 2979821120 | 2021-03-24 | 000000020174722 | 11367.4 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 11.41% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 9826.32 | 2979831120 | 2021-03-24 | 000000020174722 | 9826.32 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 9.865% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-03-24 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | 11367.82 | 2979831120 | 2021-03-24 | 000000020174722 | 11367.82 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 11.41% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2020-11-10 | 2021-04-16 | 2020/21 | 21-2982 | PO2W-210000001119 | 0 | -5086.56 | 5292870421 | 2021-04-16 | 000000020181030 | -5086.56 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | -5.106% | Furniture for Workman ES - Tables, chairs, stools, mobile storage centers, media towers, mobile tchrs desks, etc. Credit memo from vendor. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 13596.83 | 3207761219 | 2020-02-03 | 000000020065147 | 13596.83 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9381101 | 3.16% | Furniture for Workman ES - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-FF & E | 2 | FF & E | Workman ES | 21st Century classroom | Lakeshore Learning Materials | Furniture | 2019-11-01 | 2020-02-03 | 2019/20 | 2-5019 | PO3W-200000001596 | 0 | 7123.78 | 3207761219 | 2020-02-03 | 000000020065147 | 7123.78 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 1.655% | Furniture for Workman ES - Chairs, mobile tchr desks, media towers, storage units, reading nooks, kitchens, etc. | Workman ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 1401.61 | 6454842481 | 2020-07-27 | 000000020116281 | 1401.61 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 2.492% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Los Altos ES (4 year warranty). Total computers: 20 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-05 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 19688.1 | 6454893288 | 2020-08-05 | 000000020117729 | 19688.1 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 32.76% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Los Altos ES (4 year warranty). Total computers: 20 | Los Altos ES-2-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 1752 | 6454832194 | 2020-07-27 | 000000020116281 | 1752 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 2.804% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Nelson (4 year warranty). Total computers: 25 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-05 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 24610.13 | 6454893288 | 2020-08-05 | 000000020117729 | 24610.13 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 40.94% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Nelson (4 year warranty). Total computers: 25 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-20 | 2019/20 | 21-131 | PO3W-210000000005 | 0 | 55.85 | 6454678562 | 2020-08-20 | 000000020120647 | 55.85 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9231101 | 5.369% | Desktop computer (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Nelson (4 year warranty) - room #C1 - sample. Total computer: 1 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-20 | 2019/20 | 21-131 | PO3W-210000000005 | 0 | 984.41 | 6454728085 | 2020-08-20 | 000000020120647 | 984.41 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 94.63% | Desktop computer (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Nelson (4 year warranty) - room #C1 - sample. Total computer: 1 | Nelson-1-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-07-27 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 840.96 | 6454842481 | 2020-07-27 | 000000020116281 | 840.96 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 1.35% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Workman ES (4 year warranty). Total computers: 12 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Lenovo Education | Desktop computer(s) | 2020-07-01 | 2020-08-05 | 2020/21 | 21-130 | PO3W-210000000004 | 0 | 11812.86 | 6454893288 | 2020-08-05 | 000000020117729 | 11812.86 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 19.65% | Desktop computers (Lenovo ThinkCentre M720q), ThinkCentre Tiny Sandwich Kit II, Wireless combo keyboard & mouse, and Tiny Power Cage II for Workman ES (4 year warranty). Total computers: 12 | Workman ES-2-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2020-12-03 | 2021-04-13 | 2020/21 | 21-3356 | PO3W-210000001079 | 0 | 5475 | 133637 | 2021-04-13 | 000000020179759 | 5475 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 11.95% | Voice amplification system - Topcat, mounting kit & sensor clip for Cedarlane. Total system: 25 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2020-12-03 | 2021-04-13 | 2020/21 | 21-3356 | PO3W-210000001079 | 0 | 40350.82 | 133637 | 2021-04-13 | 000000020179759 | 40350.82 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9051101 | 88.05% | Voice amplification system - Topcat, mounting kit & sensor clip for Cedarlane. Total system: 25 | Cedarlane-1-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 4292.4 | 128357 | 2020-07-23 | 000000020115778 | 4292.4 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 3.814% | Voice amplification system - Topcat, mounting kit & sensor clip for Los Altos ES. Total system: 20 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 35193.3 | 128357 | 2020-07-23 | 000000020115778 | 35193.3 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9191101 | 31.27% | Voice amplification system - Topcat, mounting kit & sensor clip for Los Altos ES. Total system: 20 | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2021-05-19 | 2021-09-02 | 2021/22 | 21-6461 | PO3W-210000002832 | 0 | 9198 | 135992 | 2021-09-02 | 000000020250616 | 9198 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 11.95% | Voice amplification system - Topcat, mounting kit & sensor clip for Mesa Robles. Total system: 42 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2021-05-19 | 2021-09-02 | 2021/22 | 21-6461 | PO3W-210000002832 | 0 | 67789.31 | 135992 | 2021-09-02 | 000000020250616 | 67789.31 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9221101 | 88.05% | Voice amplification system - Topcat, mounting kit & sensor clip for Mesa Robles. Total system: 42 | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 5365.5 | 128357 | 2020-07-23 | 000000020115778 | 5365.5 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 4.768% | Voice amplification system - Topcat, mounting kit & sensor clip for Nelson. Total system: 25 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 43991.63 | 128357 | 2020-07-23 | 000000020115778 | 43991.63 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9231101 | 39.09% | Voice amplification system - Topcat, mounting kit & sensor clip for Nelson. Total system: 25 | Nelson-1-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 2575.44 | 128357 | 2020-07-23 | 000000020115778 | 2575.44 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 2.289% | Voice amplification system - Topcat, mounting kit & sensor clip for Workman ES. Total system: 12 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | Lightspeed Technologies, Inc. | Voice amplification system | 2020-07-07 | 2020-07-23 | 2020/21 | 21-409 | PO3W-210000000029 | 0 | 21115.98 | 128357 | 2020-07-23 | 000000020115778 | 21115.98 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9381101 | 18.76% | Voice amplification system - Topcat, mounting kit & sensor clip for Workman ES. Total system: 12 | Workman ES-2-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Manoj Roychowdhury | Mileage | 2023-07-09 | 2023-09-19 | 2023/24 | 24-1117 | PO2W-240000000437 | 0 | 23.32 | Conf reimb 07/09 -07/10/23 | 2023-09-19 | 000000021219872 | 23.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5220 | 9851100 | 100% | Mileage reimbursement to attend bond rating workshop conducted by RBC Capital in San Francisco on July 9-10, 2023 | District Office-0-Cost of Issuance
Cedarlane-21st Century classroom-Move Management | 1 | Move Management | Cedarlane | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 3328.8 | RI90797 | 2021-02-22 | 000000020166212 | 3328.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9051101 | 16.07% | Rental of 2 - 40' dry containers with lock box for 6 months for Cedarlane. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move Management | 1 | Move Management | Cedarlane | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 394.2 | RI95473 | 2021-09-09 | 000000020255202 | 394.2 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9051101 | 1.903% | Rental of 2 - 40' dry containers with lock box for 6 months for Cedarlane. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move Management | 1 | Move Management | Cedarlane | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-10 | 2021/22 |  | PO1-210000000608 | 1248.3 | 1248.3 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9051101 | 0% | Rental of 2 - 40' dry containers with lock box for 6 months for Cedarlane. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Remaining balance in this PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move Management | 1 | Move Management | Cedarlane | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2022-03-07 | 2021/22 | 21-4281 | PO1-210000000608 | -1248.3 | -1248.3 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9051101 | 0% | Rental of 2 - 40' dry containers with lock box for 6 months for Cedarlane. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO. | Cedarlane-1-21st Century classroom
District Office-21st Century classroom-Move Management | 0 | Move Management | District Office | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2024-01-08 | 2028-12-09 | 2023/24 | 24-4809 | PO1-240000000624 | 7000 | 7000 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9851100 | 0% | Rental or moving of container(s) for the District Office | District Office-0-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2022-12-20 | 2022/23 |  | PO2W-230000001433 | 0 | 907.5 | RI108025 | 2022-12-20 | 000000020777166 | 907.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 8.346% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-01-18 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI108902 | 2023-01-18 | 000000020810631 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-01-25 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI109679 | 2023-01-25 | 000000020822006 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-03-23 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI111044 | 2023-03-23 | 000000020919005 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-03-30 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI110383 | 2023-03-30 | 000000020934425 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-05-18 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI111722 | 2023-05-18 | 000000021019990 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-18 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI112429 | 2023-07-18 | 000000021130762 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-18 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI113063 | 2023-07-18 | 000000021130762 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-08-28 | 2023/24 |  | PO2W-230000001433 | 0 | 247.5 | RI113655 | 2023-08-28 | 000000021185728 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-10-02 | 2023/24 |  | PO2W-230000001433 | 0 | 247.5 | RI114235 | 2023-10-02 | 000000021240072 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-10-02 | 2023/24 |  | PO2W-230000001433 | 0 | 247.5 | RI114769 | 2023-10-02 | 000000021240072 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-12-06 | 2023/24 | 23-3594 | PO2W-230000001433 | 0 | 247.5 | RI115333 | 2023-12-06 | 000000021354009 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2023-10-06 | 2024-01-22 | 2023/24 |  | PO2W-240000001552 | 0 | 247.5 | RI116096 | 2024-01-22 | 000000021420055 | 247.5 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 3.333% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Move Management | 2 | Move Management | Grandview | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2023-10-06 | 2024-06-01 | 2023/24 | 24-3201 | PO2W-240000001552 | 2227.5 | 2227.5 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9121101 | 0% | Rental of 1 - 40' dry container with lock box for 1 year at Grandview. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Grandview-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI89941 | 2021-02-22 | 000000020166212 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.88 | RI90464 | 2021-02-22 | 000000020166212 | 136.88 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6609% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI90780 | 2021-02-22 | 000000020166212 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI90909 | 2021-02-22 | 000000020166212 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.86 | RI91366 | 2021-02-22 | 000000020166212 | 136.86 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI91626 | 2021-03-24 | 000000020174723 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 273.75 | RI91692 | 2021-03-24 | 000000020174723 | 273.75 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92159 | 2021-03-24 | 000000020174723 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92428 | 2021-03-24 | 000000020174723 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 273.75 | RI92503 | 2021-03-24 | 000000020174723 | 273.75 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92908 | 2021-05-26 | 000000020192523 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93188 | 2021-05-26 | 000000020192523 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI93275 | 2021-05-26 | 000000020192523 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93714 | 2021-05-26 | 000000020192523 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93942 | 2021-06-23 | 000000020200450 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI94010 | 2021-06-23 | 000000020200450 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94485 | 2021-06-23 | 000000020200450 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94728 | 2021-06-23 | 000000020200450 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI94798 | 2021-06-23 | 000000020200450 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-30 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI95214 | 2021-06-30 | 000000020202687 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI95450 | 2021-09-09 | 000000020255202 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 273.76 | RI95527 | 2021-09-09 | 000000020255202 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI95922 | 2021-09-09 | 000000020255202 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI96157 | 2021-09-09 | 000000020255202 | 136.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 273.76 | RI96227 | 2021-09-09 | 000000020255202 | 273.76 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 1.322% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-10 | 2021/22 |  | PO1-210000000608 | 3695.64 | 3695.64 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Remaining balance in this PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2022-03-07 | 2021/22 | 21-4282 | PO1-210000000608 | -3695.64 | -3695.64 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 0% | Rental of 5 - 40' dry containers with lock box for 6 months for Los Altos ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-06 | 2020-06-24 | 2019/20 |  | PO2W-200000005018 | 0 | 1357.8 | RI85306 | 2020-06-24 | 000000020108003 | 1357.8 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 40.79% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-06 | 2020-06-24 | 2020/21 | 2-10090 | PO2W-200000005018 | 0 | 1971 | RI85306 | 2020-06-24 | 000000020108003 | 1971 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 59.21% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-06-03 | 2020-08-18 | 2019/20 |  | PO2W-200000005483 | 0 | 678.9 | RI85947 | 2020-08-18 | 000000020120082 | 678.9 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 40.79% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-06-03 | 2020-08-18 | 2020/21 | 2-10620 | PO2W-200000005483 | 0 | 985.5 | RI85947 | 2020-08-18 | 000000020120082 | 985.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 59.21% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-07-06 | 2020-08-17 | 2020/21 | 21-400 | PO2W-210000000059 | 0 | 1664.4 | RI85718 | 2020-08-17 | 000000020119789 | 1664.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 100% | Rental of 1 - 40' dry container with lock box for 6 months (06/15-12/14/20) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Move Management | 2 | Move Management | Los Altos ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-07-06 | 2020-10-13 | 2020/21 | 21-1040 | PO2W-210000000340 | 0 | 1664.4 | RI87097 | 2020-10-13 | 000000020134091 | 1664.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9191101 | 100% | Rental of 1 - 40' dry container with lock box for 6 months (08/01-01/31/21) for Los Altos ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.86 | R90910 | 2021-02-22 | 000000020166212 | 136.86 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.88 | RI89942 | 2021-02-22 | 000000020166212 | 136.88 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6609% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 678.9 | RI90939 | 2021-02-22 | 000000020166212 | 678.9 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 3.278% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI91693 | 2021-03-24 | 000000020174723 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI91740 | 2021-03-24 | 000000020174723 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92504 | 2021-03-24 | 000000020174723 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI92539 | 2021-03-24 | 000000020174723 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93276 | 2021-05-26 | 000000020192523 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI93311 | 2021-05-26 | 000000020192523 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI94055 | 2021-05-26 | 000000020192523 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94011 | 2021-06-23 | 000000020200450 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 591.3 | RI94776 | 2021-06-23 | 000000020200450 | 591.3 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 2.855% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94799 | 2021-06-23 | 000000020200450 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 197.1 | RI94835 | 2021-06-23 | 000000020200450 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 591.3 | RI95508 | 2021-09-09 | 000000020255202 | 591.3 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 2.855% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI95528 | 2021-09-09 | 000000020255202 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 197.1 | RI95559 | 2021-09-09 | 000000020255202 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 591.3 | RI96203 | 2021-09-09 | 000000020255202 | 591.3 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 2.855% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI96228 | 2021-09-09 | 000000020255202 | 136.87 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.6608% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 197.1 | RI96259 | 2021-09-09 | 000000020255202 | 197.1 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0.9516% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-10 | 2021/22 |  | PO1-210000000608 | 2485.7 | 2485.7 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2022-03-07 | 2021/22 | 21-4283 | PO1-210000000608 | -2485.7 | -2485.7 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 0% | Rental of 5 - 40' dry containers with lock box for 6 months for Mesa Robles. Monthly rental is $180.00 for the first 6 month to include taxes, delivery and pick-up fees. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-06 | 2020-06-24 | 2019/20 |  | PO2W-200000005019 | 0 | 678.9 | RI85305 | 2020-06-24 | 000000020108003 | 678.9 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 40.79% | Rental of 1 - 40' dry container with lock box for 6 months (05/15-11/14/20) for Mesa Robles. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-06 | 2020-06-24 | 2020/21 | 2-10091 | PO2W-200000005019 | 0 | 985.5 | RI85305 | 2020-06-24 | 000000020108003 | 985.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 59.21% | Rental of 1 - 40' dry container with lock box for 6 months (05/15-11/14/20) for Mesa Robles. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move Management | 1 | Move Management | Mesa Robles | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-10-22 | 2021-02-05 | 2020/21 | 21-2653 | PO2W-210000000975 | 0 | 4993.2 | RI89503, RI89853, RI89908 | 2021-02-05 | 000000020162568 | 4993.2 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 100% | Rental of 3 - 40' dry containers with lock box for 6 months (11/01/20-04/30/21) for Mesa Robles. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Mesa Robles-1-21st Century classroom
Mesa Robles-Interim Housing-Move Management | 1 | Move Management | Mesa Robles | Interim Housing | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-27 | 2020-06-23 | 2019/20 | 2-10376 | PO2W-200000005377 | 0 | 500 | RI85308 | 2020-06-23 | 000000020107623 | 500 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221102 | 100% | Moved 2 of the District's existing containers from one location to another location in the campus at Mesa Robles. | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI89940 | 2021-02-22 | 000000020166212 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.88 | RI90465 | 2021-02-22 | 000000020166212 | 136.88 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6609% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI90908 | 2021-02-22 | 000000020166212 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 136.86 | RI91367 | 2021-02-22 | 000000020166212 | 136.86 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 273.75 | RI91691 | 2021-03-24 | 000000020174723 | 273.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92160 | 2021-03-24 | 000000020174723 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 273.75 | RI92502 | 2021-03-24 | 000000020174723 | 273.75 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI92909 | 2021-05-26 | 000000020192523 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI93274 | 2021-05-26 | 000000020192523 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI93715 | 2021-05-26 | 000000020192523 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI94009 | 2021-06-23 | 000000020200450 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI94486 | 2021-06-23 | 000000020200450 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 273.76 | RI94797 | 2021-06-23 | 000000020200450 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-30 | 2020/21 |  | PO1-210000000608 | 0 | 136.87 | RI95215 | 2021-06-30 | 000000020202687 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 273.76 | RI95526 | 2021-09-09 | 000000020255202 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 136.87 | RI95923 | 2021-09-09 | 000000020255202 | 136.87 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0.6608% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 273.76 | RI96226 | 2021-09-09 | 000000020255202 | 273.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 1.322% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-10 | 2021/22 |  | PO1-210000000608 | 2737.47 | 2737.47 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Remaining balance in this PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2022-03-07 | 2021/22 | 21-4284 | PO1-210000000608 | -2737.47 | -2737.47 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0% | Rental of 4 - 40' dry containers with lock box for 6 months for Nelson. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-06 | 2020-06-24 | 2019/20 |  | PO2W-200000005020 | 0 | 1357.8 | RI85307 | 2020-06-24 | 000000020108003 | 1357.8 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 40.79% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-06 | 2020-06-24 | 2020/21 | 2-10092 | PO2W-200000005020 | 0 | 1971 | RI85307 | 2020-06-24 | 000000020108003 | 1971 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 59.21% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-06-03 | 2020-08-18 | 2019/20 |  | PO2W-200000005484 | 0 | 678.9 | RI85719 | 2020-08-18 | 000000020120082 | 678.9 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 40.79% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-06-03 | 2020-08-18 | 2020/21 | 2-10621 | PO2W-200000005484 | 0 | 985.5 | RI85719 | 2020-08-18 | 000000020120082 | 985.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 59.21% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-10-09 | 2022-03-06 | 2021/22 |  | PO2W-210000000883 | 1664.4 | 1664.4 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0% | Rental of 1 - 40' dry container with lock box for 6 months (10/15/20-04/14/21) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees. Remaining balance in this PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Move Management | 1 | Move Management | Nelson | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-10-09 | 2022-03-07 | 2021/22 | 21-2375 | PO2W-210000000883 | -1664.4 | -1664.4 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 0% | Rental of 1 - 40' dry container with lock box for 6 months (10/15/20-04/14/21) for Nelson. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees. Close-out PO. | Nelson-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-01-17 | 2022/23 |  | PO2W-230000001433 | 0 | 903.37 | RI107954 | 2023-01-17 | 000000020807860 | 903.37 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 8.308% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-01-17 | 2022/23 |  | PO2W-230000001433 | 0 | 246.37 | RI108807 | 2023-01-17 | 000000020807860 | 246.37 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-01-25 | 2022/23 |  | PO2W-230000001433 | 0 | 246.37 | RI109606 | 2023-01-25 | 000000020822006 | 246.37 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-03-23 | 2022/23 |  | PO2W-230000001433 | 0 | 246.37 | RI110983 | 2023-03-23 | 000000020919005 | 246.37 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-03-30 | 2022/23 |  | PO2W-230000001433 | 0 | 246.38 | RI110322 | 2023-03-30 | 000000020934425 | 246.38 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-05-23 | 2022/23 |  | PO2W-230000001433 | 0 | 246.38 | RI111655 | 2023-05-23 | 000000021027467 | 246.38 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-19 | 2022/23 |  | PO2W-230000001433 | 0 | 32.85 | RI113599 | 2023-07-19 | 000000021132856 | 32.85 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 0.3021% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-19 | 2022/23 |  | PO2W-230000001433 | 0 | 213.52 | RI113599 | 2023-07-19 | 000000021132856 | 213.52 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 1.964% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00. | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-21 | 2022/23 |  | PO2W-230000001433 | 0 | 246.37 | RI112369 | 2023-07-21 | 000000021137159 | 246.37 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-21 | 2022/23 |  | PO2W-230000001433 | 0 | 246.37 | RI113007 | 2023-07-21 | 000000021137159 | 246.37 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-26 | 2022/23 |  | PO2W-230000001433 | 213.52 | 0 |  |  |  | -213.52 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | -1.964% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00. Prepaid month of July. | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-26 | 2022/23 |  | PO2W-230000001433 | -213.52 | -213.52 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 0% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00. | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-27 | 2023/24 |  | PO2W-230000001433 | 0 | 213.52 |  |  |  | 213.52 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 1.964% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00. Reversed prepaid expense from prior year. | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-10-03 | 2023/24 |  | PO2W-230000001433 | 0 | 246.38 | RI114185 | 2023-10-03 | 000000021242333 | 246.38 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-10-03 | 2023/24 |  | PO2W-230000001433 | 0 | 246.38 | RI114716 | 2023-10-03 | 000000021242333 | 246.38 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2024-01-08 | 2023/24 |  | PO2W-230000001433 | 0 | 246.38 | RI115268 | 2024-01-08 | 000000021395119 | 246.38 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 2.266% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2024-01-09 | 2023/24 |  | PO2W-230000001433 | 16.51 | 16.51 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 0% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2024-01-16 | 2023/24 | 23-3594 | PO2W-230000001433 | -16.51 | -16.51 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 0% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00. Close-out PO. | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2023-10-06 | 2024-01-22 | 2023/24 |  | PO2W-240000001552 | 0 | 246.37 | RI116012 | 2024-01-22 | 000000021420055 | 246.37 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 3.318% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Newton-21st Century classroom-Move Management | 1 | Move Management | Newton | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2023-10-06 | 2024-06-01 | 2023/24 | 24-3201 | PO2W-240000001552 | 2228.63 | 2228.63 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241101 | 0% | Rental of 1 - 40' dry container with lock box for 1 year at Newton. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Newton-1-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2022-12-20 | 2022/23 |  | PO2W-230000001433 | 0 | 907.5 | RI107905 | 2022-12-20 | 000000020777166 | 907.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 8.346% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-01-17 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI108790 | 2023-01-17 | 000000020807860 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-01-25 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI109592 | 2023-01-25 | 000000020822006 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-03-07 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI110302 | 2023-03-07 | 000000020889979 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-03-23 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI110964 | 2023-03-23 | 000000020919005 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-05-18 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI111640 | 2023-05-18 | 000000021019990 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-06-05 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI112350 | 2023-06-05 | 000000021047678 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-18 | 2022/23 |  | PO2W-230000001433 | 0 | 247.5 | RI112999 | 2023-07-18 | 000000021130762 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-19 | 2022/23 |  | PO2W-230000001433 | 0 | 41.25 | RI113587 | 2023-07-19 | 000000021132856 | 41.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 0.3794% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-19 | 2022/23 |  | PO2W-230000001433 | 0 | 206.25 | RI113587 | 2023-07-19 | 000000021132856 | 206.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 1.897% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-26 | 2022/23 |  | PO2W-230000001433 | 206.25 | 0 |  |  |  | -206.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | -1.897% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00. Prepaid month of July. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-26 | 2022/23 |  | PO2W-230000001433 | -206.25 | -206.25 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 0% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-07-27 | 2023/24 |  | PO2W-230000001433 | 0 | 206.25 |  |  |  | 206.25 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 1.897% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00. Reversed prepaid expense from prior year. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-10-02 | 2023/24 |  | PO2W-230000001433 | 0 | 247.5 | RI114174 | 2023-10-02 | 000000021240072 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-10-02 | 2023/24 |  | PO2W-230000001433 | 0 | 247.5 | RI114709 | 2023-10-02 | 000000021240072 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2022-10-27 | 2023-12-06 | 2023/24 | 23-3594 | PO2W-230000001433 | 0 | 247.5 | RI115252 | 2023-12-06 | 000000021354009 | 247.5 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 2.276% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Move Management | 2 | Move Management | Sparks MS | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2023-10-06 | 2024-06-01 | 2023/24 | 24-3201 | PO2W-240000001552 | 2475 | 2475 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9301101 | 0% | Rental of 1 - 40' dry container with lock box for 1 year at Sparks MS. The monthly rental rate is $225.00/month. The total cost of the container's delivery and pick-up charges is $600.00 | Sparks MS-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI89943 | 2021-02-22 | 000000020166212 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI90466 | 2021-02-22 | 000000020166212 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI90911 | 2021-02-22 | 000000020166212 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-02-22 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI91368 | 2021-02-22 | 000000020166212 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI91694 | 2021-03-24 | 000000020174723 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI92161 | 2021-03-24 | 000000020174723 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-03-24 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI92505 | 2021-03-24 | 000000020174723 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI92910 | 2021-05-26 | 000000020192523 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI93277 | 2021-05-26 | 000000020192523 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-05-26 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI93716 | 2021-05-26 | 000000020192523 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI94012 | 2021-06-23 | 000000020200450 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI94487 | 2021-06-23 | 000000020200450 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 275.01 | RI94800 | 2021-06-23 | 000000020200450 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-23 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI94935 | 2021-06-23 | 000000020200450 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-06-30 | 2020/21 |  | PO1-210000000608 | 0 | 137.5 | RI95216 | 2021-06-30 | 000000020202687 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 275.01 | RI95529 | 2021-09-09 | 000000020255202 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 137.5 | RI95924 | 2021-09-09 | 000000020255202 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0.6639% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-09 | 2021/22 |  | PO1-210000000608 | 0 | 275.01 | RI96229 | 2021-09-09 | 000000020255202 | 275.01 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 1.328% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2021-09-10 | 2021/22 |  | PO1-210000000608 | 1488.66 | 1488.66 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-02-10 | 2022-03-07 | 2021/22 | 21-4285 | PO1-210000000608 | -1488.66 | -1488.66 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0% | Rental of 3 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-06 | 2020-06-24 | 2019/20 |  | PO2W-200000005021 | 0 | 1373 | RI85304 | 2020-06-24 | 000000020108003 | 1373 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 41.06% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Workman ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-05-06 | 2020-07-01 | 2020/21 | 2-10093 | PO2W-200000005021 | 0 | 1971 | RI85304 | 2020-07-01 | 000000020108003 | 1971 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 58.94% | Rental of 2 - 40' dry containers with lock box for 6 months (05/15-11/14/20) for Workman ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-06-03 | 2020-08-18 | 2019/20 |  | PO2W-200000005485 | 0 | 682 | RI85720 | 2020-08-18 | 000000020120082 | 682 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 40.79% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Workman ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2020-06-03 | 2020-08-18 | 2020/21 | 2-10622 | PO2W-200000005485 | 0 | 990 | RI85720 | 2020-08-18 | 000000020120082 | 990 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 59.21% | Rental of 1 - 40' dry container with lock box for 6 months (06/01-11/30/20) for Workman ES. Monthly rental is $180.00 ($1,080.00/6 mo) to include taxes, delivery and pick-up fees | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-03-12 | 2021-03-30 | 2020/21 |  | PO2W-210000001957 | 0 | 137.5 | RI92642 | 2021-03-30 | 000000020176212 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-03-12 | 2021-05-26 | 2020/21 |  | PO2W-210000001957 | 0 | 137.5 | RI93429 | 2021-05-26 | 000000020192523 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-03-12 | 2021-05-26 | 2020/21 |  | PO2W-210000001957 | 0 | 137.5 | RI94169 | 2021-05-26 | 000000020192523 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-03-12 | 2021-09-09 | 2021/22 |  | PO2W-210000001957 | 0 | 137.5 | RI95656 | 2021-09-09 | 000000020255202 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-03-12 | 2021-09-09 | 2021/22 |  | PO2W-210000001957 | 0 | 137.5 | RI96355 | 2021-09-09 | 000000020255202 | 137.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 20% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-03-12 | 2021-09-10 | 2021/22 |  | PO2W-210000001957 | 2359.5 | 2359.5 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Move Management | 2 | Move Management | Workman ES | 21st Century classroom | Martin Container, Inc. | Rental/Moving of container(s) | 2021-03-12 | 2022-03-07 | 2021/22 | 21-5282 | PO2W-210000001957 | -2359.5 | -2359.5 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9381101 | 0% | Rental of 1 - 40' dry containers with lock box for 6 months for Workman ES. After the intial 6 months, the monthly rental rate is $125.00/month through December 2021. Close-out PO. | Workman ES-2-21st Century classroom
Amar-21st Century classroom-Environ Consultant | 0 | Environ Consultant | Amar | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10236 | PO2W-200000005314 | 0 | 2600 | MCSI-4532 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9011101 | 100% | Asbestos & lead-based paint survey of Amar's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Amar-0-21st Century classroom
Baldwin-21st Century classroom-Environ Consultant | 3 | Environ Consultant | Baldwin | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10237 | PO2W-200000005315 | 0 | 2600 | MCSI-4533 | 2020-08-17 | 000000020119790 | 2600 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9021101 | 100% | Asbestos & lead-based paint survey of Baldwin's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Baldwin-3-21st Century classroom
Bixby-21st Century classroom-Environ Consultant | 6 | Environ Consultant | Bixby | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10238 | PO2W-200000005316 | 0 | 2600 | MCSI-4534 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9031101 | 100% | Asbestos & lead-based paint survey of Bixby's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Bixby-6-21st Century classroom
California-21st Century classroom-Environ Consultant | 3 | Environ Consultant | California | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10239 | PO2W-200000005317 | 0 | 2600 | MCSI-4535 | 2020-08-17 | 000000020119790 | 2600 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9041101 | 100% | Asbestos & lead-based paint survey of California's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | California-3-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-29 | 2020-10-13 | 2020/21 | 2-10466 | PO2W-200000005389 | 0 | 2800 | MCSI-4529 | 2020-10-13 | 000000020134092 | 2800 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 100% | Asbestos & lead-based paint survey of Cedarlane's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-10-27 | 2021-02-04 | 2020/21 |  | PO2W-210000000995 | 0 | 6950 | MCSI-4651 | 2021-02-04 | 000000020162190 | 6950 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 100% | Oversight asbestos abatement at Cedarlane for room #F1-F3, G1-G4, & H1 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-10-27 | 2023-05-09 | 2022/23 |  | PO2W-210000000995 | 4850 | 4850 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #F1-F3, G1-G4, & H1. Remaining balance in this PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-10-27 | 2023-05-10 | 2022/23 | 21-2726 | PO2W-210000000995 | -4850 | -4850 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #F1-F3, G1-G4, & H1. Close-out PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-01-27 | 2021-03-22 | 2020/21 |  | PO2W-210000001656 | 0 | 6950 | MCSI-4686 | 2021-03-22 | 000000020174069 | 6950 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 61.23% | Oversight asbestos abatement at Cedarlane for room #E1, E2, E3 & H3 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-01-27 | 2023-05-09 | 2022/23 |  | PO2W-210000001656 | 500 | 500 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #E1, E2, E3 & H3. Remaining balance in this PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-01-27 | 2023-05-10 | 2022/23 | 21-4009 | PO2W-210000001656 | -500 | -500 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #E1, E2, E3 & H3. Close-out PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-03-19 | 2021-04-16 | 2020/21 |  | PO2W-210000001982 | 0 | 4750 | MCSI-4712 | 2021-04-16 | 000000020181032 | 4750 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 100% | Oversight asbestos abatement at Cedarlane for room #C1-C3. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-03-19 | 2023-05-09 | 2022/23 |  | PO2W-210000001982 | 2200 | 2200 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #C1-C3. Remaining balance in this PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-03-19 | 2023-05-10 | 2022/23 | 21-5452 | PO2W-210000001982 | -2200 | -2200 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #C1-C3. Close-out PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-05-06 | 2021-05-25 | 2020/21 |  | PO2W-210000002278 | 0 | 3050 | MCSI-4735 | 2021-05-25 | 000000020192073 | 3050 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 58.1% | Oversight asbestos abatement at Cedarlane for room #A2, A3, & B1. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-05-06 | 2021-09-08 | 2021/22 |  | PO2W-210000002278 | 0 | 2200 | MCSI-4872 | 2021-09-08 | 000000020253629 | 2200 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 41.9% | Oversight asbestos abatement at Cedarlane for room #A2, A3, & B1. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-05-06 | 2023-05-09 | 2022/23 |  | PO2W-210000002278 | 2300 | 2300 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #A2, A3, & B1. Remaining balance in this PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-05-06 | 2023-05-10 | 2022/23 | 21-6338 | PO2W-210000002278 | -2300 | -2300 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for room #A2, A3, & B1. Close-out PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-06-07 | 2021-06-22 | 2020/21 | 21-6713 | PO2W-210000002602 | 0 | 425 | MCSI-4746 | 2021-06-22 | 000000020200055 | 425 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 33.33% | Oversight asbestos abatement at Cedarlane (asbestos cement pipe) | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-08-10 | 2021-09-30 | 2021/22 |  | PO2W-220000000246 | 0 | 2200 | MCSI-4873 | 2021-09-30 | 000000020276431 | 2200 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 100% | Oversight asbestos abatement at Cedarlane for flooring in room #B3 & D1 under the cabinets and side rooms off band room | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-08-10 | 2023-05-09 | 2022/23 |  | PO2W-220000000246 | 400 | 400 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for flooring in room #B3 & D1 under the cabinets and side rooms off band room. Remaining balance in this PO | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Cedarlane | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-08-10 | 2023-05-10 | 2022/23 | 22-976 | PO2W-220000000246 | -400 | -400 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051101 | 0% | Oversight asbestos abatement at Cedarlane for flooring in room #B3 & D1 under the cabinets and side rooms off band room. Close-out PO | Cedarlane-1-21st Century classroom
Cedarlane-Fire Alarm replacement-Environ Consultant | 1 | Environ Consultant | Cedarlane | Fire Alarm replacement | Masek Consulting Services, Inc. | Asbestos survey | 2020-04-13 | 2020-04-29 | 2019/20 | 2-9606 | PO2W-200000004872 | 0 | 800 | MCSI-4507 | 2020-04-29 | 000000020093275 | 800 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9051103 | 100% | Limited asbestos survey of Cedarlane's permanent buildings. Testing for fire alarm project. | Cedarlane-1-Fire Alarm replacement
Del Valle-21st Century classroom-Environ Consultant | 7 | Environ Consultant | Del Valle | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10240 | PO2W-200000005318 | 0 | 2600 | MCSI-4536 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9061101 | 100% | Asbestos & lead-based paint survey of Del Valle's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Del Valle-7-21st Century classroom
Dibble-21st Century classroom-Environ Consultant | 0 | Environ Consultant | Dibble | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 2020/21 | 21-1573 | PO1-210000000427 | 0 | 2700 | MCSI-4625 | 2020-10-20 | 000000020136035 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 7451101 | 6.553% | Asbestos & lead-based paint survey of Dibble's permanent buildings. | Dibble-0-21st Century classroom
Fairgrove-21st Century classroom-Environ Consultant | 4 | Environ Consultant | Fairgrove | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1575 | PO1-210000000427 | 0 | 2700 | MCSI-4606 | 2020-10-13 | 000000020134092 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9091101 | 6.553% | Asbestos & lead-based paint survey of Fairgrove's permanent buildings. | Fairgrove-4-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2019/20 | 2-10467 | PO2W-200000005390 | 0 | 2900 | MCSI-4521 | 2020-06-19 | 000000020106917 | 2900 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 100% | Asbestos & lead-based paint survey of Grandview's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2022-11-14 | 2022/23 |  | PO2W-230000001411 | 0 | 7100 | MCSI-5008 | 2022-11-14 | 000000020720870 | 7100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 73.58% | Oversight asbestos abatement at Grandview for room #51-54, & 61-64. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2023-07-14 | 2022/23 |  | PO2W-230000001411 | 0 | 2550 | MCSI-5103 | 2023-07-14 | 000000021126791 | 2550 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 26.42% | Oversight asbestos abatement at Grandview for room #K1 & K2 which was not covered on PO2W-23*4063 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2023-07-15 | 2022/23 |  | PO2W-230000001411 | 550 | 550 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 0% | Oversight asbestos abatement at Grandview for room #K1 & K2 which was not covered on PO2W-23*4063. Remaining balance in this PO. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2023-07-16 | 2022/23 | 23-3425 | PO2W-230000001411 | -550 | -550 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 0% | Oversight asbestos abatement at Grandview for room #K1 & K2 which was not covered on PO2W-23*4063. Close-out PO. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-05-18 | 2023-07-14 | 2022/23 |  | PO2W-230000004063 | 0 | 7100 | MCSI-5103 | 2023-07-14 | 000000021126791 | 7100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 100% | Oversight asbestos abatement at Grandview for room #31-44. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-05-18 | 2023-07-15 | 2022/23 |  | PO2W-230000004063 | 550 | 550 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 0% | Oversight asbestos abatement at Grandview for room #31-44. Remaining balance in this PO. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-05-18 | 2023-07-16 | 2022/23 | 23-8020 | PO2W-230000004063 | -550 | -550 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 0% | Oversight asbestos abatement at Grandview for room #31-44. Close-out PO. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-08-24 | 2023-10-24 | 2023/24 | 24-2016 | PO2W-240000000516 | 0 | 3550 | MCSI-5134 | 2023-10-24 | 000000021283467 | 3550 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 100% | Oversight asbestos abatement for the additional work at Grandview, room #21. Addendum to PO2W-24*757 | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-07-26 | 2023-10-24 | 2023/24 |  | PO2W-240000000757 | 0 | 3550 | MCSI-5133 | 2023-10-24 | 000000021283467 | 3550 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 78.02% | Oversight asbestos abatement at Grandview for room #21-24. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Grandview | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-07-26 | 2026-12-09 | 2023/24 | 24-1222 | PO2W-240000000757 | 1000 | 1000 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121101 | 0% | Oversight asbestos abatement at Grandview for room #21-24. | Grandview-2-21st Century classroom
Grandview-Fire Alarm replacement-Environ Consultant | 2 | Environ Consultant | Grandview | Fire Alarm replacement | Masek Consulting Services, Inc. | Asbestos survey | 2020-04-13 | 2020-04-29 | 2019/20 | 2-9607 | PO2W-200000004873 | 0 | 850 | MCSI-4508 | 2020-04-29 | 000000020093275 | 850 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9121103 | 100% | Limited asbestos survey of Grandview's permanent buildings. | Grandview-2-Fire Alarm replacement
Grazide-21st Century classroom-Environ Consultant | 3 | Environ Consultant | Grazide | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10241 | PO2W-200000005319 | 0 | 2550 | MCSI-4537 | 2020-08-17 | 000000020119790 | 2550 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9131101 | 100% | Asbestos & lead-based paint survey of Grazide's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Grazide-3-21st Century classroom
Kwis-21st Century classroom-Environ Consultant | 7 | Environ Consultant | Kwis | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10242 | PO2W-200000005320 | 0 | 2600 | MCSI-4538 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9161101 | 100% | Asbestos & lead-based paint survey of Kwis' permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Kwis-7-21st Century classroom
La Puente HS-21st Century classroom-Environ Consultant | 5 | Environ Consultant | La Puente HS | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2021-03-23 | 2020/21 | 21-1580 | PO1-210000000427 | 0 | 6900 | MCSI-4666 | 2021-03-23 | 000000020174432 | 6900 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9401101 | 16.75% | Asbestos & lead-based paint survey of La Puente HS permanent buildings. | La Puente HS-5-21st Century classroom
La Puente HS-21st Century classroom-Environ Consultant | 5 | Environ Consultant | La Puente HS | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2024-01-12 | 2027-06-01 | 2023/24 | 24-4953 |  | 32500 | 32500 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9401101 | 0% | Oversight asbestos abatement at La Puente HS for room #7, 101-104, 106, 111, 113-116, 17, 17A, & 30A | La Puente HS-5-21st Century classroom
Lassalette-21st Century classroom-Environ Consultant | 6 | Environ Consultant | Lassalette | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1576 | PO1-210000000427 | 0 | 2800 | MCSI-4609 | 2020-10-13 | 000000020134092 | 2800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9171101 | 6.796% | Asbestos & lead-based paint survey of Lassalette's permanent buildings. | Lassalette-6-21st Century classroom
Los Altos ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2019/20 | 2-9624 | PO2W-200000004874 | 0 | 2800 | MCSI-4517 | 2020-06-03 | 000000020102133 | 2800 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 100% | Asbestos & lead-based paint survey of Los Altos ES permanent buildings. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2020-08-17 | 2019/20 |  | PO2W-210000000060 | 0 | 3475 | MCSI-4560 | 2020-08-17 | 000000020119790 | 3475 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 44.69% | Floor tile & mastic abatement oversight and clearance at Los Altos ES for room #C1, work room between C1 & C2, B3 in phase I and E2, E3, E4, & F4 in phase 2. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2020-08-17 | 2020/21 |  | PO2W-210000000060 | 0 | 4300 | MCSI-4581 | 2020-08-17 | 000000020119790 | 4300 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 55.31% | Floor tile & mastic abatement oversight and clearance at Los Altos ES for room #C1, work room between C1 & C2, B3 in phase I and E2, E3, E4, & F4 in phase 2. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2023-05-09 | 2022/23 |  | PO2W-210000000060 | 6125 | 6125 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 0% | Floor tile & mastic abatement oversight and clearance at Los Altos ES for room #C1, work room between C1 & C2, B3 in phase I and E2, E3, E4, & F4 in phase 2. Remaining balance in this PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Los Altos ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2023-05-10 | 2022/23 | 21-401 | PO2W-210000000060 | -6125 | -6125 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9191101 | 0% | Floor tile & mastic abatement oversight and clearance at Los Altos ES for room #C1, work room between C1 & C2, B3 in phase I and E2, E3, E4, & F4 in phase 2. Close-out PO. | Los Altos ES-2-21st Century classroom
Los Altos HS-21st Century classroom-Environ Consultant | 5 | Environ Consultant | Los Altos HS | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2021-01-19 | 2020/21 | 21-1581 | PO1-210000000427 | 0 | 4350 | MCSI-4658 | 2021-01-19 | 000000020157533 | 4350 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9411101 | 10.56% | Asbestos & lead-based paint survey of Los Altos HS permanent buildings. | Los Altos HS-5-21st Century classroom
Los Molinos-21st Century classroom-Environ Consultant | 4 | Environ Consultant | Los Molinos | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10243 | PO2W-200000005321 | 0 | 2600 | MCSI-4539 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9201101 | 100% | Asbestos & lead-based paint survey of Los Molinos' permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Los Molinos-4-21st Century classroom
Los Robles-21st Century classroom-Environ Consultant | 9 | Environ Consultant | Los Robles | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10244 | PO2W-200000005322 | 0 | 2800 | MCSI-4540 | 2020-08-17 | 000000020119790 | 2800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9211101 | 100% | Asbestos & lead-based paint survey of Los Robles' permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Los Robles-9-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2019/20 | 2-10468 | PO2W-200000005391 | 0 | 2950 | MCSI-4530 | 2020-06-19 | 000000020106917 | 2950 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 100% | Asbestos & lead-based paint survey of Mesa Robles' permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-10-22 | 2021-02-04 | 2020/21 |  | PO2W-210000000976 | 0 | 4400 | MCSI-4644 | 2021-02-04 | 000000020162190 | 4400 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 100% | Oversight asbestos abatement at Mesa Robles for room #2 & 4 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-10-22 | 2023-05-09 | 2022/23 |  | PO2W-210000000976 | 1600 | 1600 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #2 & 4. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-10-22 | 2023-05-10 | 2022/23 | 21-2654 | PO2W-210000000976 | -1600 | -1600 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #2 & 4. Close-out PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-10-23 | 2021-02-04 | 2020/21 | 21-2682 | PO2W-210000000986 | 0 | 1480 | MCSI-4640 | 2021-02-04 | 000000020162190 | 1480 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 100% | Asbestos & lead-based paint survey of Mesa Robles permanent portable building #25 & 26. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-01-27 | 2021-03-22 | 2020/21 |  | PO2W-210000001656 | 0 | 4400 | MCSI-4683 | 2021-03-22 | 000000020174069 | 4400 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 38.77% | Oversight asbestos abatement at Mesa Robles for room #D12-D15 & G11 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-01-27 | 2023-05-09 | 2022/23 |  | PO2W-210000001656 | 4900 | 4900 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #D12-D15 & G11. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-01-27 | 2023-05-10 | 2022/23 | 21-4009 | PO2W-210000001656 | -4900 | -4900 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #D12-D15 & G11. Close-out PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-03-18 | 2021-04-16 | 2020/21 |  | PO2W-210000001978 | 0 | 7910 | MCSI-4709 | 2021-04-16 | 000000020181032 | 7910 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 100% | Oversight asbestos abatement at Mesa Robles for room #B21 & G8-G10. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-03-18 | 2023-05-09 | 2022/23 |  | PO2W-210000001978 | 1440 | 1440 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #B21 & G8-G10. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-03-18 | 2023-05-10 | 2022/23 | 21-5398 | PO2W-210000001978 | -1440 | -1440 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 0% | Oversight asbestos abatement at Mesa Robles for room #B21 & G8-G10. Close-out PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Mesa Robles | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2021-06-07 | 2021-06-22 | 2020/21 | 21-6713 | PO2W-210000002602 | 0 | 850 | MCSI-4724 | 2021-06-22 | 000000020200055 | 850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221101 | 66.67% | Oversight asbestos abatement for Mesa Robles' flooring at room #16 & 17 areas under the cabinets | Mesa Robles-1-21st Century classroom
Mesa Robles-Interim Housing-Environ Consultant | 1 | Environ Consultant | Mesa Robles | Interim Housing | Masek Consulting Services, Inc. | Pre-demo asbestos & lead-based paint | 2020-01-31 | 2020-06-03 | 2019/20 | 2-7522 | PO2W-200000003739 | 0 | 1280 | MCSI-4490 | 2020-06-03 | 000000020102133 | 1280 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9221102 | 100% | Pre-demolition asbestos & lead-based paint survey of Mesa Robles' old portable building #27 and 28. | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Nelson | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2019/20 | 2-9625 | PO2W-200000004875 | 0 | 2530 | MCSI-4513 | 2020-06-03 | 000000020102133 | 2530 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9231101 | 100% | Asbestos & lead-based paint survey of Nelson's permanent buildings (exclude Admin & multi-purpose bldg) and old portable buildings. Walk through, collect samples, testing of samples, and prepare report. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Nelson | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2020-10-13 | 2020/21 |  | PO2W-210000000061 | 0 | 3975 | MCSI-4591 | 2020-10-13 | 000000020134092 | 3975 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9231101 | 100% | Floor tile & mastic abatement abatement oversight and clearance at Nelson for room #A1, B1, B3, and under the cabinets in B2 & B4. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Nelson | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2023-05-09 | 2022/23 |  | PO2W-210000000061 | 4125 | 4125 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9231101 | 0% | Floor tile & mastic abatement abatement oversight and clearance at Nelson for room #A1, B1, B3, and under the cabinets in B2 & B4. Remaining balance in this PO | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Nelson | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2023-05-10 | 2022/23 | 21-402 | PO2W-210000000061 | -4125 | -4125 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9231101 | 0% | Floor tile & mastic abatement abatement oversight and clearance at Nelson for room #A1, B1, B3, and under the cabinets in B2 & B4. Close-out PO. | Nelson-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-29 | 2020-10-13 | 2020/21 | 2-10469 | PO2W-200000005392 | 0 | 2950 | MCSI-4528 | 2020-10-13 | 000000020134092 | 2950 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 100% | Asbestos & lead-based paint survey of Newton's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2022-11-14 | 2022/23 |  | PO2W-230000001412 | 0 | 5550 | MCSI-5009 | 2022-11-14 | 000000020720870 | 5550 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 100% | Oversight asbestos abatement at Newton for room #D1-D4. | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2023-05-09 | 2022/23 |  | PO2W-230000001412 | 1000 | 1000 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 0% | Oversight asbestos abatement at Newton for room #D1-D4. Remaining balance in this PO | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2023-05-10 | 2022/23 | 23-3426 | PO2W-230000001412 | -1000 | -1000 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 0% | Oversight asbestos abatement at Newton for room #D1-D4. Close-out PO | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-03-13 | 2023-05-16 | 2022/23 |  | PO2W-230000003345 | 0 | 2000 | MCSI-5075 | 2023-05-16 | 000000021014795 | 2000 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 40% | Oversight asbestos abatement at Newton for room #C5-C8. | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-03-13 | 2023-06-29 | 2022/23 |  | PO2W-230000003345 | 0 | 2000 | MCSI-5104A | 2023-06-29 | 000000021099938 | 2000 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 40% | Oversight asbestos abatement at Newton for room #C5-C8. | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-03-13 | 2027-06-01 | 2023/24 | 23-6738 | PO2W-230000003345 | 1000 | 1000 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 0% | Oversight asbestos abatement at Newton for room #C5-C8. | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-06-15 | 2023-09-15 | 2023/24 |  | PO2W-230000004340 | 0 | 2550 | MCSI-5104B | 2023-09-15 | 000000021215375 | 2550 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 56.04% | Oversight asbestos abatement at Newton for the Band room. | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-06-15 | 2024-06-01 | 2023/24 | 23-8674 | PO2W-230000004340 | 2000 | 2000 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 0% | Oversight asbestos abatement at Newton for the Band room. | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-07-26 | 2023-10-16 | 2023/24 |  | PO2W-240000000758 | 0 | 3000 | MCSI-5132 | 2023-10-16 | 000000021268264 | 3000 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 26.79% | Oversight asbestos abatement at Newton for room #D1, D2, E1, & E2 (4 classrooms in the E wing). These rooms were formerly Home Economic/shop rooms. Per Rima @ Masek, room #D1 and D2 are not the same rooms as listed in PO2W-23-1412. | Newton-1-21st Century classroom
Newton-21st Century classroom-Environ Consultant | 1 | Environ Consultant | Newton | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-07-26 | 2026-12-09 | 2023/24 | 24-1223 | PO2W-240000000758 | 8200 | 8200 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9241101 | 0% | Oversight asbestos abatement at Newton for room #D1, D2, E1, & E2 (4 classrooms in the E wing). These rooms were formerly Home Economic/shop rooms. Per Rima @ Masek, room #D1 and D2 are not the same rooms as listed in PO2W-23-1412. | Newton-1-21st Century classroom
Orange Grove-21st Century classroom-Environ Consultant | 3 | Environ Consultant | Orange Grove | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1577 | PO1-210000000427 | 0 | 2800 | MCSI-4612 | 2020-10-13 | 000000020134092 | 2800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9251101 | 6.796% | Asbestos & lead-based paint survey of Orange Grove's permanent buildings. | Orange Grove-3-21st Century classroom
Palm-21st Century classroom-Environ Consultant | 6 | Environ Consultant | Palm | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10245 | PO2W-200000005323 | 0 | 2500 | MCSI-4541 | 2020-08-17 | 000000020119790 | 2500 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9261101 | 100% | Asbestos & lead-based paint survey of Palm's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Palm-6-21st Century classroom
Sierra Vista-21st Century classroom-Environ Consultant | 8 | Environ Consultant | Sierra Vista | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1578 | PO1-210000000427 | 0 | 3000 | MCSI-4613 | 2020-10-13 | 000000020134092 | 3000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9281101 | 7.282% | Asbestos & lead-based paint survey of Sierra Vista's permanent buildings. | Sierra Vista-8-21st Century classroom
Sparks ES-21st Century classroom-Environ Consultant | 7 | Environ Consultant | Sparks ES | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10246 | PO2W-200000005324 | 0 | 2670 | MCSI-4542 | 2020-08-17 | 000000020119790 | 2670 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9291101 | 100% | Asbestos & lead-based paint survey of Spark ES permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Sparks ES-7-21st Century classroom
Sparks MS-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Sparks MS | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-29 | 2020-06-19 | 2019/20 | 2-10470 | PO2W-200000005393 | 0 | 2950 | MCSI-4546 | 2020-06-19 | 000000020106917 | 2950 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9301101 | 100% | Asbestos & lead-based paint survey of Spark MS permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Sparks MS | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2022-12-05 | 2022/23 |  | PO2W-230000001413 | 0 | 2000 | MCSI-5007 | 2022-12-05 | 000000020750486 | 2000 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9301101 | 43.96% | Oversight asbestos abatement at Sparks MS for room #9-12, & 13-16. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Sparks MS | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2023-07-20 | 2022/23 |  | PO2W-230000001413 | 0 | 2550 | MCSI-5099 | 2023-07-20 | 000000021134877 | 2550 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9301101 | 56.04% | Oversight asbestos abatement at Sparks MS for the additional work at room #19. See PO2W-23*4062 which had been created for room #17-20. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Sparks MS | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2023-07-21 | 2022/23 |  | PO2W-230000001413 | 450 | 450 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9301101 | 0% | Oversight asbestos abatement at Sparks MS for the additional work at room #19. Addendum to PO2W-23*4062 which had been created for room #17-20. Remaining balance in this PO. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Sparks MS | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2022-10-19 | 2023-07-22 | 2022/23 | 23-3427 | PO2W-230000001413 | -450 | -450 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9301101 | 0% | Oversight asbestos abatement at Sparks MS for the additional work at room #19. Addendum to PO2W-23*4062 which had been created for room #17-20. Close-out PO | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Sparks MS | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2023-04-21 | 2023-07-14 | 2022/23 | 23-7673 | PO2W-230000004062 | 0 | 3000 | MCSI-5099 | 2023-07-14 | 000000021126791 | 3000 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9301101 | 100% | Oversight asbestos abatement at Sparks MS for room #17-20 | Sparks MS-2-21st Century classroom
Sunset-21st Century classroom-Environ Consultant | 4 | Environ Consultant | Sunset | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10247 | PO2W-200000005325 | 0 | 2700 | MCSI-4543 | 2020-08-17 | 000000020119790 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9311101 | 100% | Asbestos & lead-based paint survey of Sunset's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Sunset-4-21st Century classroom
Temple-21st Century classroom-Environ Consultant | 8 | Environ Consultant | Temple | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10248 | PO2W-200000005326 | 0 | 2600 | MCSI-4544 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9331101 | 100% | Asbestos & lead-based paint survey of Temple's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Temple-8-21st Century classroom
Valinda-21st Century classroom-Environ Consultant | 6 | Environ Consultant | Valinda | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1579 | PO1-210000000427 | 0 | 3000 | MCSI-4605 | 2020-10-13 | 000000020134092 | 3000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9341101 | 7.282% | Asbestos & lead-based paint survey of Valinda's permanent buildings. | Valinda-6-21st Century classroom
Valley-21st Century classroom-Environ Consultant | 8 | Environ Consultant | Valley | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-13 | 2020/21 | 21-1584 | PO1-210000000427 | 0 | 2700 | MCSI-4621 | 2020-10-13 | 000000020134092 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9441101 | 6.553% | Asbestos & lead-based paint survey of Valley's permanent buildings. | Valley-8-21st Century classroom
Willow-21st Century classroom-Environ Consultant | 0 | Environ Consultant | Willow | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 2020/21 | 21-1574 | PO1-210000000427 | 0 | 2700 | MCSI-4623 | 2020-10-20 | 000000020136035 | 2700 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 7461101 | 6.553% | Asbestos & lead-based paint survey of Willow's permanent buildings. | Willow-0-21st Century classroom
Wilson HS-21st Century classroom-Environ Consultant | 5 | Environ Consultant | Wilson HS | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2020-10-20 | 2020/21 | 21-1582 | PO1-210000000427 | 0 | 3400 | MCSI-4627 | 2020-10-20 | 000000020136035 | 3400 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9421101 | 8.252% | Asbestos & lead-based paint survey of Wilson HS permanent buildings. | Wilson HS-5-21st Century classroom
Wing Lane-21st Century classroom-Environ Consultant | 9 | Environ Consultant | Wing Lane | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-05-20 | 2020-08-17 | 2020/21 | 2-10249 | PO2W-200000005327 | 0 | 2600 | MCSI-4545 | 2020-08-17 | 000000020119790 | 2600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9371101 | 100% | Asbestos & lead-based paint survey of Wing Lane's permanent buildings. Walk through, collect samples, testing of samples, and prepare report. | Wing Lane-9-21st Century classroom
Workman ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-04-15 | 2020-06-03 | 2019/20 | 2-9626 | PO2W-200000004876 | 0 | 2500 | MCSI-4512 | 2020-06-03 | 000000020102133 | 2500 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 100% | Asbestos & lead-based paint survey of Workman ES permanent buildings and old portable buildings. Walk through, collect samples, testing of samples, and prepare report. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-06-03 | 2020-06-26 | 2019/20 | 2-10645 | PO2W-200000005541 | 0 | 1200 | MCSI-4519 | 2020-06-26 | 000000020108764 | 1200 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 100% | Asbestos & lead-based paint survey of Workman ES classrooms #P13 through P17, pre-demolition | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2020-08-17 | 2019/20 |  | PO2W-210000000062 | 0 | 6775 | MCSI-4561 | 2020-08-17 | 000000020119790 | 6775 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 100% | Floor tile & mastic abatement oversight at Workman ES for room #5, 6, 7, and 12 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2023-05-09 | 2022/23 |  | PO2W-210000000062 | 4300 | 4300 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 0% | Floor tile & mastic abatement oversight at Workman ES for room #5, 6, 7, and 12. Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-07-06 | 2023-05-10 | 2022/23 | 21-403 | PO2W-210000000062 | -4300 | -4300 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 0% | Floor tile & mastic abatement oversight at Workman ES for room #5, 6, 7, and 12. Close-out PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-09-11 | 2020-11-19 | 2020/21 |  | PO2W-210000000585 | 0 | 825 | MCSI-4639 | 2020-11-19 | 000000020143747 | 825 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 100% | Oversight asbestos abatement of a small area next to staff restrooms at Workman ES | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-09-11 | 2023-05-09 | 2022/23 |  | PO2W-210000000585 | 100 | 100 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 0% | Oversight asbestos abatement of a small area next to staff restrooms at Workman ES. Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Environ Consultant | 2 | Environ Consultant | Workman ES | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2020-09-11 | 2023-05-10 | 2022/23 | 21-1846 | PO2W-210000000585 | -100 | -100 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9381101 | 0% | Oversight asbestos abatement of a small area next to staff restrooms at Workman ES. Close-out PO. | Workman ES-2-21st Century classroom
Workman HS-21st Century classroom-Environ Consultant | 5 | Environ Consultant | Workman HS | 21st Century classroom | Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | 2020-08-26 | 2021-01-19 | 2020/21 | 21-1583 | PO1-210000000427 | 0 | 4150 | MCSI-4657 | 2021-01-19 | 000000020157533 | 4150 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9431101 | 10.07% | Asbestos & lead-based paint survey of Workman HS permanent buildings. | Workman HS-5-21st Century classroom
Workman HS-21st Century classroom-Environ Consultant | 5 | Environ Consultant | Workman HS | 21st Century classroom | Masek Consulting Services, Inc. | Oversight asbestos abatement | 2024-01-12 | 2027-06-01 | 2023/24 | 24-4954 |  | 3500 | 3500 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5850 | 9431101 | 0% | Oversight asbestos abatement at Workman HS for room #E21 | Workman HS-5-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-01-22 | 2020/21 |  | PO2W-210000000983 | 0 | 588686.5 | Pay app #1 | 2021-01-22 | 000000020158915 | 588686.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 15.43% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-01-22 | 2020/21 |  | PO2W-210000000983 | 0 | 318682.25 | Pay app #2 | 2021-01-22 | 000000020158915 | 318682.25 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 8.353% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-03-17 | 2020/21 |  | PO2W-210000000983 | 0 | 137481.65 | Pay app #3 | 2021-03-17 | 000000020172903 | 137481.65 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 3.604% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-04-07 | 2020/21 |  | PO2W-210000000983 | 0 | 346238.1 | Pay app #4 | 2021-04-07 | 000000020178357 | 346238.1 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 9.076% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-05-21 | 2020/21 |  | PO2W-210000000983 | 0 | 264523.27 | Pay app #5 | 2021-05-21 | 000000020191176 | 264523.27 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 6.934% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-05-21 | 2020/21 |  | PO2W-210000000983 | 0 | 60733.5 | Pay app #6 | 2021-05-21 | 000000020191176 | 60733.5 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 1.592% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-06-18 | 2020/21 |  | PO2W-210000000983 | 0 | 161808.95 | Pay app #7 | 2021-06-18 | 000000020199433 | 161808.95 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 4.241% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-07-12 | 2020/21 |  | PO2W-210000000983 | 0 | 470243.82 | Pay app #8 | 2021-07-12 | 000000020207269 | 470243.82 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 12.33% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-08-17 | 2021/22 |  | PO2W-210000000983 | 0 | 277494.35 | Pay app #9 | 2021-08-17 | 000000020231509 | 277494.35 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 7.274% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-11-23 | 2021/22 |  | PO2W-210000000983 | 0 | 143188.64 | Pay app #10 | 2021-11-23 | 000000020343098 | 143188.64 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 3.753% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-12-20 | 2021/22 |  | PO2W-210000000983 | 0 | 71418.97 | Pay app #11 | 2021-12-20 | 000000020370752 | 71418.97 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 1.872% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2022-07-05 | 2021/22 |  | PO2W-210000000983 | 0 | 99528.2 | Pay app #12 | 2022-07-05 | 000000020542150 | 99528.2 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 2.609% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31. We withheld the stop notice amount of $100,740.64 from the Digital Networks Group, Inc.; therefore, the payment to Masters is: $200,268.84 - 100,740.64 = $99,528.20 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2022-07-06 | 2021/22 |  | PO2W-210000000983 | 0 | 49971.8 |  |  |  | 49971.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 1.31% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31. Accrued stop payment amount. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2022-08-18 | 2022/23 |  | PO2W-210000000983 | 0 | -49971.8 |  |  |  | -49971.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | -1.31% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31. Reversed accrual from prior year. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-10-23 | 2022-10-27 | 2022/23 | 21-2507 | PO2W-210000000983 | 0 | 49971.8 | Pay app #13 | 2022-10-27 | 000000020696076 | 49971.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051101 | 1.31% | Classroom improvements for Cedarlane 21st Century. Bid option #1. Includes $170,000.00 of allowances. The total project costs with the change order (PO2W-22*2554) is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2022-04-13 | 2022-07-06 | 2021/22 |  | PO2W-220000002554 | 0 | 50768.84 |  |  |  | 50768.84 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9051101 | 24.08% | Change order for Cedarlane 21st Century classroom improvements. Addendum to PO2W-21*983. The total project costs with this change order is $3,200,809.31. Accrued stop payment amount. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2022-04-13 | 2022-08-18 | 2022/23 |  | PO2W-220000002554 | 0 | -50768.84 |  |  |  | -50768.84 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9051101 | -24.08% | Change order for Cedarlane 21st Century classroom improvements. Addendum to PO2W-21*983. The total project costs with this change order is $3,200,809.31. Reversed accrual from prior year. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2022-04-13 | 2022-10-28 | 2022/23 |  | PO2W-220000002554 | 0 | 84883.51 | Pay app #13 | 2022-10-28 | 000000020698113 | 84883.51 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9051101 | 40.27% | Change order for Cedarlane 21st Century classroom improvements. Addendum to PO2W-21*983. The total project costs with this change order is $3,200,809.31 | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Contractor | 1 | Contractor | Cedarlane | 21st Century classroom | Masters Contracting Corp. | Contractor | 2022-04-13 | 2023-04-27 | 2022/23 | 22-5085 | PO2W-220000002554 | 0 | 125925.8 | Stop payment release | 2023-04-27 | 000000020981115 | 125925.8 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9051101 | 59.73% | Change order for Cedarlane 21st Century classroom improvements. Addendum to PO2W-21*983. The total project costs with this change order is $3,200,809.31. Stop payment released amount: $49,971.80 + 50,768.84 + (100,740.64 x 0.25) -= $125,925.80 | Cedarlane-1-21st Century classroom
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-01-22 | 2020/21 |  | PO2W-210000000983 | 0 | 184120.83 | Pay app #1 | 2021-01-22 | 000000020158915 | 184120.83 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 4.826% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project costs with the change order (PO2W-22*2312) is 895,740.41 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-01-22 | 2020/21 |  | PO2W-210000000983 | 0 | 259777.5 | Pay app #2 | 2021-01-22 | 000000020158915 | 259777.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 6.809% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project costs with the change order (PO2W-22*2312) is 895,740.41 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-03-23 | 2020/21 |  | PO2W-210000000983 | 0 | 13195.5 | Pay app #3 | 2021-03-23 | 000000020174433 | 13195.5 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 0.3459% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project costs with the change order (PO2W-22*2312) is 895,740.41 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-04-07 | 2020/21 |  | PO2W-210000000983 | 0 | 247627 | Pay app #4 | 2021-04-07 | 000000020178357 | 247627 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 6.491% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project costs with the change order (PO2W-22*2312) is 895,740.41 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-05-21 | 2020/21 |  | PO2W-210000000983 | 0 | 64002.29 | Pay app #5 | 2021-05-21 | 000000020191176 | 64002.29 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 1.678% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project costs with the change order (PO2W-22*2312) is 895,740.41 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2020-10-23 | 2021-12-20 | 2021/22 |  | PO2W-210000000983 | 0 | 15026.88 | Pay app #6 | 2021-12-20 | 000000020370752 | 15026.88 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 0.3939% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project costs with the change order (PO2W-22*2312) is 895,740.41 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2020-10-23 | 2022-05-23 | 2021/22 |  | PO2W-210000000983 | 0 | 41250 | Pay app #7 | 2022-05-23 | 000000020505849 | 41250 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9051102 | 1.081% | Classroom modifications for Cedarlane Interim Housing. Bid option #1. The total project costs with the change order (PO2W-22*2312) is 895,740.41 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2022-03-25 | 2022-05-23 | 2021/22 |  | PO2W-220000002312 | 0 | 25953.39 | Pay app #7 | 2022-05-23 | 000000020505849 | 25953.39 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9051102 | 36.69% | Change order for classroom modifications at Cedarlane Interim Housing. Addendum to PO2W-21*983. The total project costs with this change order is $895,740.41 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Masters Contracting Corp. | Contractor | 2022-03-25 | 2022-10-27 | 2022/23 | 22-5138 | PO2W-220000002312 | 0 | 44787.02 | Pay app #8 | 2022-10-27 | 000000020696077 | 44787.02 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9051102 | 63.31% | Change order for classroom modifications at Cedarlane Interim Housing. Addendum to PO2W-21*983. The total project costs with this change order is $895,740.41 | Cedarlane-1-Interim Housing
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-07-31 | 2020/21 |  | PO2W-200000005828 | 0 | 680168.65 | Pay app #1 | 2020-07-31 | 000000020117168 | 680168.65 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 30.62% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-08-18 | 2020/21 |  | PO2W-200000005828 | 0 | 63129.4 | Pay app #2 | 2020-08-18 | 000000020120083 | 63129.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 2.842% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-09-28 | 2020/21 |  | PO2W-200000005828 | 0 | 306478.32 | Pay app #3 | 2020-09-28 | 000000020130229 | 306478.32 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 13.8% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-11-09 | 2020/21 |  | PO2W-200000005828 | 0 | 589220.4 | Pay app #4 | 2020-11-09 | 000000020141125 | 589220.4 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 26.53% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-12-18 | 2020/21 |  | PO2W-200000005828 | 0 | 187365.65 | Pay app #5 | 2020-12-18 | 000000020151937 | 187365.65 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 8.436% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2021-01-15 | 2020/21 |  | PO2W-200000005828 | 0 | 79831.6 | Pay app #6 | 2021-01-15 | 000000020157265 | 79831.6 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 3.594% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2021-03-16 | 2020/21 |  | PO2W-200000005828 | 0 | 153632.87 | Pay app #7 | 2021-03-16 | 000000020172578 | 153632.87 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 6.917% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2021-05-21 | 2020/21 |  | PO2W-200000005828 | 0 | 46286.31 | Pay app #8 | 2021-05-21 | 000000020191176 | 46286.31 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 2.084% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2022-05-06 | 2021/22 |  | PO2W-200000005828 | 0 | 3836.8 | Pay app #9 | 2022-05-06 | 000000020487457 | 3836.8 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 0.1728% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2022-09-15 | 2022/23 | 2-10667 | PO2W-200000005828 | 0 | 111050 | Pay app #10 | 2022-09-15 | 000000020626858 | 111050 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191101 | 5% | 21st Century classroom modifications at Los Altos ES. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. Include bid alternate 1 to furnish all labor & equipment to construct cast in place concrete accesible ramp in lieu of furnishing & installing prefabicated metal deck accessible ramp. Total project cost with the change order (PO2W-22*2619) is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Contractor | 2 | Contractor | Los Altos ES | 21st Century classroom | Masters Contracting Corp. | Contractor | 2022-06-14 | 2022-09-15 | 2022/23 | 22-5053 | PO2W-220000002619 | 0 | 32583.58 | Pay app #10 | 2022-09-15 | 000000020626858 | 32583.58 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9191101 | 100% | Change order for the 21st Century classroom at Los Altos ES. Addendum to PO2W20*5828. The total project cost with this change order is $2,253,583.58 | Los Altos ES-2-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-07-31 | 2019/20 |  | PO2W-200000005829 | 0 | 496863.78 | Pay app #1 | 2020-07-31 | 000000020117168 | 496863.78 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 22.69% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-08-18 | 2019/20 |  | PO2W-200000005829 | 0 | 26150.72 | Pay app #2 | 2020-08-18 | 000000020120083 | 26150.72 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 1.194% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-08-18 | 2020/21 |  | PO2W-200000005829 | 0 | 565926.8 | Pay app #2 | 2020-08-18 | 000000020120083 | 565926.8 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 25.84% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-09-28 | 2020/21 |  | PO2W-200000005829 | 0 | 301087.74 | Pay app #3 | 2020-09-28 | 000000020130229 | 301087.74 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 13.75% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2020-11-09 | 2020/21 |  | PO2W-200000005829 | 0 | 282947.52 | Pay app #4 | 2020-11-09 | 000000020141125 | 282947.52 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 12.92% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2021-01-15 | 2020/21 |  | PO2W-200000005829 | 0 | 177129.4 | Pay app #5 | 2021-01-15 | 000000020157265 | 177129.4 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 8.088% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2021-01-20 | 2020/21 |  | PO2W-200000005829 | 0 | 71383.63 | Pay app #6 | 2021-01-20 | 000000020157917 | 71383.63 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 3.26% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2021-03-16 | 2020/21 |  | PO2W-200000005829 | 0 | 107716.68 | Pay app #7 | 2021-03-16 | 000000020172578 | 107716.68 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 4.919% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2021-05-21 | 2020/21 |  | PO2W-200000005829 | 0 | 37289.79 | Pay app #8 | 2021-05-21 | 000000020191176 | 37289.79 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 1.703% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2022-05-23 | 2021/22 | 2-10671 | PO2W-200000005829 | 0 | 109500 | Pay app #10 | 2022-05-23 | 000000020505849 | 109500 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 5% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2020-06-04 | 2022-05-23 | 2021/22 |  | PO2W-200000005829 | 0 | 14003.94 | Pay app #9 | 2022-05-23 | 000000020505849 | 14003.94 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231101 | 0.6394% | 21st Century classroom modifications at Nelson. The cost includes all scope items as defined within the drawings, specifications, phasing plans and schedules. The change order of $1,400.00 (PO2W-22*2620) was cancelled. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2022-06-14 | 2023-07-05 | 2022/23 |  | PO2W-220000002620 | 1400 | 1400 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9231101 | 0% | Change order for the 21st Century classroom at Nelson. Addendum to PO2W20*5829. Remaining balance in this PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Masters Contracting Corp. | Contractor | 2022-06-14 | 2023-07-06 | 2022/23 | 22-5140 | PO2W-220000002620 | -1400 | -1400 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9231101 | 0% | Change order for the 21st Century classroom at Nelson. Addendum to PO2W20*5829. Close-out PO. | Nelson-1-21st Century classroom
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2019-11-05 | 2019/20 |  | PO1-200000000617 | 0 | 79.5 | 446143 | 2019-11-05 | 000000020034486 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2020-01-14 | 2019/20 |  | PO1-200000000617 | 0 | 79.5 | 449936 | 2020-01-14 | 000000020057282 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2020-04-07 | 2019/20 |  | PO1-200000000617 | 0 | 79.5 | 454218 | 2020-04-07 | 000000020087144 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2020-08-17 | 2020/21 |  | PO1-200000000617 | 0 | 79.5 | 458282 | 2020-08-17 | 000000020119792 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2020-10-13 | 2020/21 |  | PO1-200000000617 | 0 | 79.5 | 462413 | 2020-10-13 | 000000020134095 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-01-15 | 2020/21 |  | PO1-200000000617 | 0 | 79.5 | 466515 | 2021-01-15 | 000000020157266 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-04-16 | 2020/21 |  | PO1-200000000617 | 0 | 79.5 | 470595 | 2021-04-16 | 000000020181033 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-11-30 | 2021/22 |  | PO1-200000000617 | 0 | 79.5 | 474504 | 2021-11-30 | 000000020345298 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-11-30 | 2021/22 |  | PO1-200000000617 | 0 | 79.5 | 478578 | 2021-11-30 | 000000020345298 | 79.5 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 11.11% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2021-12-09 | 2021/22 |  | PO1-200000000617 | 2782.5 | 2782.5 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. Remaining balance in this PO. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Alarm | 2 | Alarm | Los Altos ES | Interim Housing | Mijac Alarm | Alarm for portables | 2019-10-01 | 2022-03-23 | 2021/22 | 2-4011 | PO1-200000000617 | -2782.5 | -2782.5 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191102 | 0% | Fire monitoring of 4 portables at Los Altos ES. Starting from Oct 1, 2019 through Dec. 31, 2021 at $26.50/month. Bay Alarm purchased Mijac. Close-out PO. | Los Altos ES-2-Interim Housing
Cedarlane-Interim Housing-Modular Buildings | 1 | Modular Buildings | Cedarlane | Interim Housing | Mobile Modular Management Corp. | Portable classrooms | 2019-03-20 | 2020-02-18 | 2019/20 | 2-2078 | PO2W-200000003188, PO2W-200000001048, 19-107585 | 0 | 218488.74 | R20530140 | 2020-02-18 | 000000020070593 | 218488.74 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9051102 | 100% | Purchase of 4 Portable classrooms - 24' x 40' DSA, install closure panels, new carpets, HVAC, T-8 lights lines, and delivery to Cedarlane. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Modular Buildings | 1 | Modular Buildings | Cedarlane | Interim Housing | Mobile Modular Management Corp. | Portable classrooms | 2019-03-20 | 2021-02-05 | 2020/21 | 2-2078 | PO2W-200000003189, PO2W-200000001048, 19-107585 | 0 | 21300 | R20554228 | 2021-02-05 | 000000020162569 | 21300 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9051102 | 100% | For 4 portable classrooms - Block & level building, installation, and relocation of these classrooms at Cedarlane | Cedarlane-1-Interim Housing
Los Altos ES-Interim Housing-Modular Buildings | 2 | Modular Buildings | Los Altos ES | Interim Housing | Mobile Modular Management Corp. | Portable classrooms | 2019-03-20 | 2020-01-16 | 2019/20 | 2-2084 | PO2W-200000001050, 19-107587 | 0 | 236959.74 | R20521588-1KR | 2020-01-16 | 000000020058725 | 236959.74 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9191102 | 100% | Purchase of 4 Portable classrooms - 24' x 40' DSA, install closure panels, new carpets, HVAC, T-8 lights lines, and delivery to Los Altos ES. | Los Altos ES-2-Interim Housing
Mesa Robles-Interim Housing-Modular Buildings | 1 | Modular Buildings | Mesa Robles | Interim Housing | Mobile Modular Management Corp. | Portable classrooms | 2019-03-20 | 2020-02-18 | 2019/20 | 2-2086 | PO2W-200000003190, PO2W-200000001052, 19-107584 | 0 | 436977.48 | R20530141 | 2020-02-18 | 000000020070593 | 436977.48 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9221102 | 100% | Purchase of 8 Portable classrooms - 24' x 40' DSA, install closure panels, new carpets, HVAC, T-8 lights lines, and delivery to Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Modular Buildings | 1 | Modular Buildings | Mesa Robles | Interim Housing | Mobile Modular Management Corp. | Portable classrooms | 2019-03-20 | 2020-08-18 | 2020/21 | 2-2086 | PO2W-200000003191, PO2W-200000001052, 19-107584 | 0 | 42600 | R20546442 | 2020-08-18 | 000000020120084 | 42600 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9221102 | 100% | For 8 portable classrooms - Block & level building, installation, and relocation of these classrooms at Mesa Robles | Mesa Robles-1-Interim Housing
Newton-Interim Housing-Modular Buildings | 1 | Modular Buildings | Newton | Interim Housing | Mobile Modular Management Corp. | Portable classrooms | 2019-03-20 | 2020-02-18 | 2019/20 | 2-2085 | PO2W-200000003192, PO2W-200000001051, 19-107586 | 0 | 218488.74 | R20530142 | 2020-02-18 | 000000020070593 | 218488.74 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9241102 | 100% | Purchase of 4 Portable classrooms - 24' x 40' DSA, install closure panels, new carpets, HVAC, T-8 lights lines, and delivery to Newton. | Newton-1-Interim Housing
Newton-Interim Housing-Modular Buildings | 1 | Modular Buildings | Newton | Interim Housing | Mobile Modular Management Corp. | Portable classrooms | 2019-03-20 | 2022-03-16 | 2021/22 | 2-2085 | PO2W-200000003193, PO2W-200000001051, 19-107586 | 0 | 21300 | R20587497 | 2022-03-16 | 000000020444816 | 21300 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6200 | 9241102 | 100% | For 4 portable classrooms - Block & level building, installation, and relocation of these classrooms at Newton | Newton-1-Interim Housing
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Montague DeRose and Associates, LLC | Municipal Advisory services | 2017-07-12 | 2017-07-12 | 2017/18 |  | N/A - Cost of Issuance | 0 | 42740 |  |  |  | 42740 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Municipal Advisory services, 18-KT005 | District Office-0-Cost of Issuance
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Moody's Investors Service, Inc. | Rating Agency Fee | 2017-07-31 | 2017-07-31 | 2017/18 |  | N/A - Cost of Issuance | 0 | 37000 |  |  |  | 37000 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Rating Agency Fee, 18-KT005 | District Office-0-Cost of Issuance
District Office-21st Century classroom-Technology | 0 | Technology | District Office | 21st Century classroom | Network Integration Company Partners, Inc. (NIC Partners) | Loudspeakers & horns | 2023-07-20 | 2023-10-13 | 2023/24 | 24-707 | PO2W-240000000158 | 0 | 261019.31 | N56016 | 2023-10-13 | 000000021266172 | 261019.31 |  |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9851100 | 100% | Atlas loudspeakers with mount slanted enclosures (200 each) and Atlas horns with mount straight enclosures (50 each) for District-wide use. Moved exp from NCS, JVER 24*95 | District Office-0-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-02-26 | 2018/19 |  | 19-100488 | 0 | 7100 | 001 | 2019-02-26 | 25118280 | 7100 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 100% | Architect - Allowances for civil engineering in 21st Century classroom projects at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-02-27 | 2018/19 |  | 19-100488 | 24900 | 24900 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0% | Architect - Allowances for civil engineering in 21st Century classroom projects at Mesa Robles. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-06-05 | 2018/19 |  | 19-100488 | -24900 | -24900 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0% | Architect - Allowances for civil engineering in 21st Century classroom projects at Mesa Robles. Close-out PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-06-28 | 2017/18 |  | 19-100492, 18-109572 | 0 | 4007.97 | 001 | 2018-06-28 | 24653404 | 4007.97 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 50% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles 21st Century. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-07-17 | 2017/18 |  | 19-100492, 18-109572 | 0 | 4007.97 | 002 | 2018-07-17 | 24688289 | 4007.97 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 50% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles 21st Century. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-07-18 | 2017/18 |  | 19-100492, 18-109572 | 192382.83 | 192382.83 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles 21st Century. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2019-06-05 | 2017/18 |  | 19-100492, 18-109572 | -192382.83 | -192382.83 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles 21st Century. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. Close-out PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-10-28 | 2019/20 | 2-4236 | PO2W-200000001909 | 0 | 411.5 | 001 | 2019-10-28 | 000000020031417 | 411.5 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 100% | Architect - Reimbursement for digital scanning (ARC services) for Mesa Robles 21st Century (Allowances) | Mesa Robles-1-21st Century classroom
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-06-28 | 2017/18 |  | 19-100493, 18-109556 | 0 | 1286.49 | 001 | 2018-06-28 | 24653404 | 1286.49 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 50% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles Interim Housing. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-07-17 | 2017/18 |  | 19-100493, 18-109556 | 0 | 1286.49 | 002 | 2018-07-17 | 24688289 | 1286.49 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 50% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles Interim Housing. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2018-07-18 | 2017/18 |  | 19-100493, 18-109556 | 61751.42 | 61751.42 |  |  |  | 0 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 0% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles Interim Housing. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. Remaining balance in this PO. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-06-13 | 2019-06-05 | 2017/18 |  | 19-100493, 18-109556 | -61751.42 | -61751.42 |  |  |  | 0 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 0% | Architect - Architectural design work required to create and prepare the contract set of drawings for submittal to DSA for Mesa Robles Interim Housing. Inclusive are fees for conceptual design, schematic design. Design development, construction documents, bidding and negotiation, and construction administration. Close-out PO. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-10-28 | 2019/20 |  | PO2W-200000001924 | 0 | 2894.95 | 003 | 2019-10-28 | 000000020031418 | 2894.95 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 74.33% | Architect - Payment for schematic design & design development for Mesa Robles Interim Housing (Allowances) | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | Office p.S. Architecture + Urbanism + Design | Architect | 2018-07-01 | 2019-10-28 | 2019/20 | 2-4246 | PO2W-200000001924 | 0 | 1000 | Per email | 2019-10-28 | 000000020031418 | 1000 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 25.67% | Architect - Reimbursement for fire hydrant services at Mesa Robles (Allowances) | Mesa Robles-1-Interim Housing
Amar-Drinking Fountain replacement-Contractor | 0 | Contractor | Amar | Drinking Fountain replacement | Optima | Contractor | 2019-08-20 | 2020-02-20 | 2019/20 | 2-4812 | PO2W-200000002201 | 0 | 8200 | 5000189 | 2020-02-20 | 000000020071939 | 8200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9011104 | 100% | Provide & install 1 new drinking fountain at Amar. | Amar-0-Drinking Fountain replacement
Los Altos HS-Drinking Fountain replacement-Contractor | 5 | Contractor | Los Altos HS | Drinking Fountain replacement | Optima | Contractor | 2019-08-20 | 2020-02-10 | 2019/20 | 2-4817 | PO2W-200000002204 | 0 | 6600 | 5000187 | 2020-02-10 | 000000020068412 | 6600 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9411104 | 100% | Provide & install 1 new drinking fountain at Los Altos HS. | Los Altos HS-5-Drinking Fountain replacement
Mesa Robles-Drinking Fountain replacement-Contractor | 1 | Contractor | Mesa Robles | Drinking Fountain replacement | Optima | Contractor | 2019-08-20 | 2020-02-10 | 2019/20 | 2-4816 | PO2W-200000002203 | 0 | 11000 | 5000191 | 2020-02-10 | 000000020068412 | 11000 | 03-120658 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221104 | 100% | Provide & install 1 new drinking fountain at Mesa Robles. | Mesa Robles-1-Drinking Fountain replacement
Sunset-Drinking Fountain replacement-Contractor | 4 | Contractor | Sunset | Drinking Fountain replacement | Optima | Contractor | 2019-12-18 | 2021-04-23 | 2020/21 | 2-6493 | PO1-200000000833 | 0 | 18000 | Pay app #1 | 2021-04-23 | 000000020182911 | 18000 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9311104 | 100% | Provide & install dual wall mount drinking fountain (hi & lo) at Sunset. | Sunset-4-Drinking Fountain replacement
Wedgeworth-Drinking Fountain replacement-Contractor | 0 | Contractor | Wedgeworth | Drinking Fountain replacement | Optima | Contractor | 2019-12-18 | 2021-04-07 | 2020/21 |  | PO1-200000000834 | 0 | 3502.75 | Pay app #1 | 2021-04-07 | 000000020178359 | 3502.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9351104 | 100% | Provide & install dual wall mount drinking fountain (hi & lo) at Wedgeworth. | Wedgeworth-0-Drinking Fountain replacement
Wedgeworth-Drinking Fountain replacement-Contractor | 0 | Contractor | Wedgeworth | Drinking Fountain replacement | Optima | Contractor | 2019-12-18 | 2023-03-02 | 2022/23 |  | PO1-200000000834 | 2997.25 | 2997.25 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9351104 | 0% | Provide & install dual wall mount drinking fountain (hi & lo) at Wedgeworth. Remaining balance in this PO | Wedgeworth-0-Drinking Fountain replacement
Wedgeworth-Drinking Fountain replacement-Contractor | 0 | Contractor | Wedgeworth | Drinking Fountain replacement | Optima | Contractor | 2019-12-18 | 2023-03-03 | 2022/23 | 2-6495 | PO1-200000000834 | -2997.25 | -2997.25 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9351104 | 0% | Provide & install dual wall mount drinking fountain (hi & lo) at Wedgeworth. Close-out PO | Wedgeworth-0-Drinking Fountain replacement
Wing Lane-Drinking Fountain replacement-Contractor | 9 | Contractor | Wing Lane | Drinking Fountain replacement | Optima | Contractor | 2019-08-20 | 2020-02-20 | 2019/20 | 2-4814 | PO2W-200000002202 | 0 | 6800 | 5000190 | 2020-02-20 | 000000020071939 | 6800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9371104 | 100% | Provide & install 1 new drinking fountain at Wing Lane. | Wing Lane-9-Drinking Fountain replacement
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-03-04 | 2019/20 |  | PO1-200000001027 | 0 | 4647.5 | 89592 | 2020-03-04 | 000000020077144 | 4647.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 53.22% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-04-07 | 2019/20 |  | PO1-200000001027 | 0 | 2286.63 | 89866 | 2020-04-07 | 000000020087145 | 2286.63 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 26.18% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-04-22 | 2019/20 |  | PO1-200000001027 | 0 | 1799 | 90267 | 2020-04-22 | 000000020091403 | 1799 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 20.6% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-06-30 | 2019/20 |  | PO1-200000001027 | 0 | 1266.87 |  |  |  | 1266.87 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 14.51% | Legal services for the bond projects. Accrued remaining balance of this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-07-01 | 2020/21 |  | PO1-200000001027 | 0 | -1266.87 |  |  |  | -1266.87 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | -14.51% | Legal services for the bond projects. Reversed accrual from prior year | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2020-07-02 | 2020/21 |  | PO1-200000001027 | 1266.87 | 1266.87 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Remaining balance in this PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-02-26 | 2021-06-30 | 2020/21 | 2-8365 | PO1-200000001027 | -1266.87 | -1266.87 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects. Close-out PO. | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2022-10-04 | 2022/23 |  | PO1-230000000406 | 0 | 795 | 97802 | 2022-10-04 | 000000020653700 | 795 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0.318% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2022-11-28 | 2022/23 |  | PO1-230000000406 | 0 | 6180.49 | 98960 | 2022-11-28 | 000000020738363 | 6180.49 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 2.472% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2023-01-04 | 2022/23 |  | PO1-230000000406 | 0 | 2652.5 | 99130 | 2023-01-04 | 000000020787893 | 2652.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 1.061% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2023-01-23 | 2022/23 |  | PO1-230000000406 | 0 | 4818.49 | 99398 | 2023-01-23 | 000000020817419 | 4818.49 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 1.927% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2023-01-26 | 2022/23 |  | PO1-230000000406 | 0 | 2462.79 | 99700 | 2023-01-26 | 000000020865642 | 2462.79 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0.9851% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2023-03-17 | 2022/23 |  | PO1-230000000406 | 0 | 8898.5 | 100159 | 2023-03-17 | 000000020909871 | 8898.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 3.559% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2023-06-05 | 2022/23 |  | PO1-230000000406 | 0 | 4865.41 | 100851 | 2023-06-05 | 000000021047690 | 4865.41 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 1.946% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2023-06-22 | 2022/23 |  | PO1-230000000406 | 0 | 6380 | 101256 | 2023-06-22 | 000000021085432 | 6380 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 2.552% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2024-01-25 | 2023/24 |  | PO1-230000000406 | 0 | 809.03 | 103340 | 2024-01-25 | 000000021429805 | 809.03 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0.3236% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2022-07-01 | 2026-12-09 | 2023/24 | 23-643 | PO1-230000000406 | 212137.79 | 212137.79 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2023-07-12 | 2024-06-30 | 2023/24 | 24-664 | PO1-240000000018 | 50000 | 50000 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 0% | Legal services for the bond projects | District Office-0-21st Century classroom
District Office-21st Century classroom-Legal services | 0 | Legal services | District Office | 21st Century classroom | Orbach Huff Suarez + Henderson, LLP | Attorney fees | 2020-01-29 | 2020-02-27 | 2019/20 | 2-7525 | PO2W-200000004282 | 0 | 3492.5 | 89468 | 2020-02-27 | 000000020074745 | 3492.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5822 | 9851100 | 100% | Legal services for the bond projects | District Office-0-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2018-10-12 | 2017/18 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2672 | 514189 | 2018-10-12 | 24854124 | 2672 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.74% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2019-04-22 | 2018/19 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2672 | 516548 | 2019-04-22 | 25242024 | 2672 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.74% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2019-10-10 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 21376 | 518434 | 2019-10-10 | 000000020025176 | 21376 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 13.92% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2020-04-17 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 7481.6 | 522495 | 2020-04-17 | 000000020090429 | 7481.6 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 4.871% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2020-06-22 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 45958.4 | 523906 | 2020-06-22 | 000000020107236 | 45958.4 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 29.92% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2020-08-18 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 524035 | 2020-08-18 | 000000020120086 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2020-08-18 | 2019/20 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 19100 | 524035 | 2020-08-18 | 000000020120086 | 19100 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 12.43% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Allowances for topographic survey, fire water plan, coutyard grading, & revised site plan. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2020-10-13 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 524655 | 2020-10-13 | 000000020134100 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2020-10-13 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 668 | 525158 | 2020-10-13 | 000000020134100 | 668 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 0.4349% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2020-10-21 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2672 | 525717 | 2020-10-21 | 000000020136453 | 2672 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.74% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2021-02-05 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 526191 | 2021-02-05 | 000000020162570 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2021-02-05 | 2020/21 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 526648 | 2021-02-05 | 000000020162570 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 | 527231 | 2022-01-25 | 000000020397386 | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2004 | 528248 | 2022-01-25 | 000000020397386 | 2004 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.305% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2338 | 528686 | 2022-01-25 | 000000020397386 | 2338 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.522% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1336 | 529088 | 2022-01-25 | 000000020397386 | 1336 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 0.8698% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-01-25 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 4008 | 530146 | 2022-01-25 | 000000020397386 | 4008 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 2.609% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 3340 | 527739 | 2022-01-26 | 000000020398558 | 3340 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 2.174% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 2338 | 529656 | 2022-01-26 | 000000020398558 | 2338 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.522% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-06-30 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 8016 |  |  |  | 8016 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 5.219% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Accrued invoice #530837. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-06-30 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 |  |  |  | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Accrued invoice #531270. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-06-30 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1670 |  |  |  | 1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Accrued invoice #531946. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-06-30 | 2021/22 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 1002 |  |  |  | 1002 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 0.6523% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Accrued invoice #532300. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-08-18 | 2022/23 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | -8016 |  |  |  | -8016 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | -5.219% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Reversed accrual from prior year. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-08-18 | 2022/23 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | -1670 |  |  |  | -1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | -1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Reversed accrual from prior year. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-08-18 | 2022/23 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | -1670 |  |  |  | -1670 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | -1.087% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Reversed accrual from prior year. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-08-18 | 2022/23 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | -1002 |  |  |  | -1002 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | -0.6523% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Reversed accrual from prior year. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2022-12-12 | 2022/23 |  | PO2W-200000000856, 19-100508, 18-109907 | 0 | 473.59 | 527736 | 2022-12-12 | 000000020762694 | 473.59 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 0.3083% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. Allowances for reprographics. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Design | 1 | Design | Cedarlane | 21st Century classroom | PBK Architects | Architect | 2018-06-26 | 2026-06-01 | 2023/24 | 2-525 | PO2W-200000000856, 19-100508, 18-109907 | 26812.41 | 26812.41 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051101 | 0% | Architect - Provide architectural & engineering services for Cedarlane 21st Century Modernization project. Scope of work consists of technology & interior upgrades to all classrooms in each bldg. Sitework will be limited to ADA access & path of travel requirements to each classroom. Include allowances of $20,000.00. | Cedarlane-1-21st Century classroom
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2018-10-12 | 2017/18 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 1146.66 | 513128 | 2018-10-12 | 24854124 | 1146.66 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 1.483% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2019-02-27 | 2018/19 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 8313.29 | 515588 | 2019-02-27 | 25120812 | 8313.29 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 10.75% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2019-05-23 | 2018/19 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 15479.91 | 516551 | 2019-05-23 | 25313243 | 15479.91 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 20.02% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2019-09-20 | 2018/19 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 8500 | 517420 | 2019-09-20 | 000000020017558 | 8500 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 10.99% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. Allowances for topographic survey. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2019-10-01 | 2019/20 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 9459.94 | 516992 | 2019-10-01 | 000000020021440 | 9459.94 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 12.23% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2020-08-18 | 2019/20 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 2579.99 | 524036 | 2020-08-18 | 000000020120086 | 2579.99 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 3.336% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2020-08-18 | 2019/20 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 9100 | 524036 | 2020-08-18 | 000000020120086 | 9100 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 11.77% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. Allowances for civil engineering. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2021-02-05 | 2020/21 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 143.33 | 525686 | 2021-02-05 | 000000020162570 | 143.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2021-02-05 | 2020/21 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 143.33 | 526210 | 2021-02-05 | 000000020162570 | 143.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 8033.3 | 526678 | 2022-01-26 | 000000020398558 | 8033.3 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 10.39% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. Payment includes allowances of $2,300.00 for civil engineering. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 3583.31 | 527232 | 2022-01-26 | 000000020398558 | 3583.31 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 4.634% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 1433.33 | 527747 | 2022-01-26 | 000000020398558 | 1433.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 1.853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 859.99 | 528250 | 2022-01-26 | 000000020398558 | 859.99 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 1.112% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 2006.66 | 528688 | 2022-01-26 | 000000020398558 | 2006.66 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 2.595% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 430 | 529657 | 2022-01-26 | 000000020398558 | 430 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.556% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 143.33 | 530147 | 2022-01-26 | 000000020398558 | 143.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-01-26 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 143.33 | 531271 | 2022-01-26 | 000000020398558 | 143.33 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1853% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-06-30 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 1146.66 |  |  |  | 1146.66 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 1.483% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01. Accrued invoice #531947. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-06-30 | 2021/22 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 1719.99 |  |  |  | 1719.99 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 2.224% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01. Accrued invoice #532301. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-08-18 | 2022/23 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | -1146.66 |  |  |  | -1146.66 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | -1.483% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01. Reversed accrual from prior year. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-08-18 | 2022/23 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | -1719.99 |  |  |  | -1719.99 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | -2.224% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01. Reversed accrual from prior year. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2022-12-12 | 2022/23 |  | PO2W-200000001212, 19-100509, 18-109906 | 0 | 100 | 527745 | 2022-12-12 | 000000020762694 | 100 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0.1293% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. Allowances for reprographics. Total reprographic charges for inv #527745 is $1,564.01. Paid $100.00 on this PO and the remaining balance of $1,464.01 on PO2W-23*2021. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2018-06-26 | 2026-06-01 | 2023/24 | 2-524 | PO2W-200000001212, 19-100509, 18-109906 | 5733.3 | 5733.3 |  |  |  | 0 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051102 | 0% | Architect - Provide architectural & engineering services for Cedarlane Interim Housing project. Scope of work consists of constructing 7 portable classroom bldgs and 1 restroom bldg. Sitework will be limited to ADA access and path of travel reqs. to the new portables. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-23-2021) is $78,797.01 | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Design | 1 | Design | Cedarlane | Interim Housing | PBK Architects | Architect | 2022-12-05 | 2023-01-17 | 2022/23 | 23-4280 | PO2W-230000002021 | 0 | 1464.01 | 527745 | 2023-01-17 | 000000020807866 | 1464.01 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9051102 | 100% | Architect - Additional reprographics allowances for Cedarlane Interim Housing. Addendum to PO2W-20*1212. Change order #1. Total reprographic charges for inv #527745 is $1,564.01. Paid $1,464.01 on this PO and the remaining balance of $100.00 on PO2W-20*1212. The total architect costs with this change order (PO2W-23*2021) is $78,797.01. | Cedarlane-1-Interim Housing
Fairgrove-21st Century classroom-Design | 4 | Design | Fairgrove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2022-06-30 | 2021/22 |  | PO1-210000000684 | 0 | 3667.5 |  |  |  | 3667.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091101 | 0.9% | Architect - Provide architectural/engineering services for the Fairgrove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Fairgrove. Accrued invoice #531949. | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Design | 4 | Design | Fairgrove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2022-06-30 | 2021/22 |  | PO1-210000000684 | 0 | 16300 |  |  |  | 16300 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091101 | 4% | Architect - Provide architectural/engineering services for the Fairgrove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Fairgrove. Accrued invoice #530840. | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Design | 4 | Design | Fairgrove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2022-08-18 | 2022/23 |  | PO1-210000000684 | 0 | -3667.5 |  |  |  | -3667.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091101 | -0.9% | Architect - Provide architectural/engineering services for the Fairgrove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Fairgrove. Reversed accrual from prior year. | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Design | 4 | Design | Fairgrove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2022-08-18 | 2022/23 |  | PO1-210000000684 | 0 | -16300 |  |  |  | -16300 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091101 | -4% | Architect - Provide architectural/engineering services for the Fairgrove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Fairgrove. Reversed accrual from prior year. | Fairgrove-4-21st Century classroom
Fairgrove-21st Century classroom-Design | 4 | Design | Fairgrove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2028-06-01 | 2023/24 | 21-6230 | PO1-210000000684 | 407500 | 407500 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091101 | 0% | Architect - Provide architectural/engineering services for the Fairgrove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Fairgrove. | Fairgrove-4-21st Century classroom
Fairgrove-Interim Housing-Design | 4 | Design | Fairgrove | Interim Housing | PBK Architects | Architect | 2021-05-03 | 2028-06-01 | 2023/24 |  | PO1-210000000686 | 95400 | 95400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091102 | 0% | Architect - Provide architectural/engineering services for the Fairgrove Interim Housing project. Sitework will be limited to ADA access & path of travel requirements to the new portables. | Fairgrove-4-Interim Housing
Fairgrove-Interim Housing-Design | 4 | Design | Fairgrove | Interim Housing | PBK Architects | Architect | 2021-05-03 | 2028-06-01 | 2023/24 | 21-6233 | PO1-210000000686 | -95400 | -95400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091102 | 0% | Architect - Provide architectural/engineering services for the Fairgrove Interim Housing project. Sitework will be limited to ADA access & path of travel requirements to the new portables. Close-out PO. | Fairgrove-4-Interim Housing
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2020-04-02 | 2019/20 |  | PO2W-200000000098 | 0 | 17328 | 521305 | 2020-04-02 | 000000020086381 | 17328 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 6.987% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2020-04-02 | 2019/20 |  | PO2W-200000000098 | 0 | 12312 | 521639 | 2020-04-02 | 000000020086381 | 12312 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 4.965% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2020-04-02 | 2019/20 |  | PO2W-200000000098 | 0 | 15960 | 522150 | 2020-04-02 | 000000020086381 | 15960 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 6.435% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2020-04-17 | 2019/20 |  | PO2W-200000000098 | 0 | 12768 | 522494 | 2020-04-17 | 000000020090429 | 12768 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 5.148% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2020-06-18 | 2019/20 |  | PO2W-200000000098 | 0 | 78432 | 523681 | 2020-06-18 | 000000020106518 | 78432 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 31.63% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2020-08-18 | 2019/20 |  | PO2W-200000000098 | 0 | 2850 | 524037 | 2020-08-18 | 000000020120086 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2020-10-13 | 2020/21 |  | PO2W-200000000098 | 0 | 2850 | 524656 | 2020-10-13 | 000000020134100 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2020-10-13 | 2020/21 |  | PO2W-200000000098 | 0 | 1140 | 525159 | 2020-10-13 | 000000020134100 | 1140 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0.4597% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2021-02-05 | 2020/21 |  | PO2W-200000000098 | 0 | 4560 | 525689 | 2021-02-05 | 000000020162570 | 4560 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.839% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 5700 | 526682 | 2022-01-25 | 000000020397386 | 5700 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 2.298% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 2850 | 527749 | 2022-01-25 | 000000020397386 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 3420 | 528252 | 2022-01-25 | 000000020397386 | 3420 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.379% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 5130 | 528689 | 2022-01-25 | 000000020397386 | 5130 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 2.069% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 2280 | 529090 | 2022-01-25 | 000000020397386 | 2280 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0.9194% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 3990 | 529658 | 2022-01-25 | 000000020397386 | 3990 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.609% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 7980 | 530149 | 2022-01-25 | 000000020397386 | 7980 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 3.218% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 14250 | 530839 | 2022-01-25 | 000000020397386 | 14250 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 5.746% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 2850 | 531274 | 2022-01-25 | 000000020397386 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 2850 | 531948 | 2022-01-25 | 000000020397386 | 2850 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.149% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 4560 | 532302 | 2022-01-25 | 000000020397386 | 4560 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.839% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-01-25 | 2021/22 |  | PO2W-200000000098 | 0 | 5700 | 527233R | 2022-01-25 | 000000020397386 | 5700 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 2.298% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-07-05 | 2021/22 |  | PO2W-200000000098 | 0 | 14600 | 526278 | 2022-07-05 | 000000020542151 | 14600 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 5.887% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00. Allowances for topographic survey and ADA compliances. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-07-05 | 2021/22 |  | PO2W-200000000098 | 0 | 11400 | 534699 | 2022-07-05 | 000000020542151 | 11400 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 4.597% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-07-05 | 2021/22 |  | PO2W-200000000098 | 0 | 3420 | 192930027 | 2022-07-05 | 000000020542151 | 3420 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 1.379% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-07-05 | 2021/22 |  | PO2W-200000000098 | 0 | 1140 | 192930028 | 2022-07-05 | 000000020542151 | 1140 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0.4597% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-11-14 | 2022/23 |  | PO2W-200000000098 | 0 | 2280 | 192930029 | 2022-11-14 | 000000020720871 | 2280 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0.9194% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2022-12-14 | 2022/23 |  | PO2W-200000000098 | 0 | 780.44 | 20767577 | 2022-12-14 | 000000020767577 | 780.44 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0.3147% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00. Allowances for reprographics. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Design | 1 | Design | Mesa Robles | 21st Century classroom | PBK Architects | Architect | 2019-07-01 | 2026-06-01 | 2023/24 | 2-887 | PO2W-200000000098 | 4619.56 | 4619.56 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221101 | 0% | Architect - Provide architectural & engineering services to consists of technology and interior upgrades to all classrooms in each building at Mesa Robles. Sitework will be limited to ADA access and path of travel requirements to each classroom. Include allowances of $20,000.00 | Mesa Robles-1-21st Century classroom
Orange Grove-21st Century classroom-Design | 3 | Design | Orange Grove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2022-06-30 | 2021/22 |  | PO1-210000000685 | 0 | 8880 |  |  |  | 8880 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251101 | 4% | Architect - Provide architectural/engineering services for the Orange Grove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Orange Grove. Accrued invoice #530841. | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Design | 3 | Design | Orange Grove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2022-06-30 | 2021/22 |  | PO1-210000000685 | 0 | 1998 |  |  |  | 1998 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251101 | 0.9% | Architect - Provide architectural/engineering services for the Orange Grove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Orange Grove. Accrued invoice #531950. | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Design | 3 | Design | Orange Grove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2022-08-18 | 2022/23 |  | PO1-210000000685 | 0 | -8880 |  |  |  | -8880 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251101 | -4% | Architect - Provide architectural/engineering services for the Orange Grove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Orange Grove. Reversed accrual from prior year. | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Design | 3 | Design | Orange Grove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2022-08-18 | 2022/23 |  | PO1-210000000685 | 0 | -1998 |  |  |  | -1998 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251101 | -0.9% | Architect - Provide architectural/engineering services for the Orange Grove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Orange Grove. Reversed accrual from prior year. | Orange Grove-3-21st Century classroom
Orange Grove-21st Century classroom-Design | 3 | Design | Orange Grove | 21st Century classroom | PBK Architects | Architect | 2021-05-03 | 2028-06-01 | 2023/24 | 21-6231 | PO1-210000000685 | 222000 | 222000 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251101 | 0% | Architect - Provide architectural/engineering services for the Orange Grove 21st Century modernization project. The scope of work generally consists of technology & interior upgrades to all classrooms in each building on Orange Grove. | Orange Grove-3-21st Century classroom
Orange Grove-Interim Housing-Design | 3 | Design | Orange Grove | Interim Housing | PBK Architects | Architect | 2021-05-03 | 2028-06-01 | 2023/24 |  | PO1-210000000687 | 95400 | 95400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251102 | 0% | Architect - Provide architectural/engineering services for the Orange Grove Interim Housing project. Sitework will be limited to ADA access & path of travel requirements to the new portables. | Orange Grove-3-Interim Housing
Orange Grove-Interim Housing-Design | 3 | Design | Orange Grove | Interim Housing | PBK Architects | Architect | 2021-05-03 | 2028-06-01 | 2023/24 | 21-6235 | PO1-210000000687 | -95400 | -95400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251102 | 0% | Architect - Provide architectural/engineering services for the Orange Grove Interim Housing project. Sitework will be limited to ADA access & path of travel requirements to the new portables. Close-out PO. | Orange Grove-3-Interim Housing
Cedarlane-21st Century classroom-Technology | 1 | Technology | Cedarlane | 21st Century classroom | PI Manufacturing Corp. | Computer cables | 2020-12-03 | 2021-02-10 | 2020/21 | 21-3361 | PO3W-210000001096 | 0 | 1351.5 | 956470 | 2021-02-10 | 000000020163835 | 1351.5 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Computer cables for Cedarlane | Cedarlane-1-21st Century classroom
Los Altos ES-21st Century classroom-Technology | 2 | Technology | Los Altos ES | 21st Century classroom | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 2020/21 | 21-3258 | PO2W-210000001349 | 0 | 1086.6 | 956466 | 2021-02-10 | 000000020163835 | 1086.6 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 100% | Computer cables for Los Altos ES | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | PI Manufacturing Corp. | Computer cables | 2020-12-03 | 2021-02-17 | 2020/21 |  | PO3W-210000001095 | 0 | 1710.17 | 956469 | 2021-02-17 | 000000020165094 | 1710.17 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 79.65% | Computer cables for Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Technology | 1 | Technology | Mesa Robles | 21st Century classroom | PI Manufacturing Corp. | Computer cables | 2020-12-03 | 2021-06-24 | 2020/21 | 21-3360 | PO3W-210000001095 | 0 | 436.91 | 962688 | 2021-06-24 | 000000020200891 | 436.91 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 20.35% | Computer cables for Mesa Robles | Mesa Robles-1-21st Century classroom
Nelson-21st Century classroom-Technology | 1 | Technology | Nelson | 21st Century classroom | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 2020/21 | 21-3264 | PO2W-210000001350 | 0 | 1023.66 | 956468 | 2021-02-10 | 000000020163835 | 1023.66 | 03-119946 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9231101 | 100% | Computer cables for Nelson | Nelson-1-21st Century classroom
Workman ES-21st Century classroom-Technology | 2 | Technology | Workman ES | 21st Century classroom | PI Manufacturing Corp. | Computer cables | 2020-11-30 | 2021-02-10 | 2020/21 | 21-3265 | PO2W-210000001351 | 0 | 1086.6 | 956471 | 2021-02-10 | 000000020163835 | 1086.6 | 03-119881 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9381101 | 100% | Computer cables for Workman ES | Workman ES-2-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Rbc Capital Markets, LLC | Hotel reimb. during rating agency presentations in San Francisco | 2017-07-11 | 2017-07-11 | 2017/18 |  | N/A - Cost of Issuance | 0 | 647.68 |  |  |  | 647.68 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Hotel reimb. during rating agency presentations in San Francisco, 18-KT005 | District Office-0-Cost of Issuance
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Rbc Capital Markets, LLC | Reimb. Continuing Disclosure Report (DAC) | 2017-08-04 | 2017-08-04 | 2017/18 |  | N/A - Cost of Issuance | 0 | 550 |  |  |  | 550 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Reimb. Continuing Disclosure Report (DAC), 18-KT005 | District Office-0-Cost of Issuance
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | S&P Global Ratings | Rating Agency Fee | 2017-08-03 | 2017-08-03 | 2017/18 |  | N/A - Cost of Issuance | 0 | 35000 |  |  |  | 35000 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Rating Agency Fee, 18-KT005 | District Office-0-Cost of Issuance
La Puente HS-21st Century classroom-Advertisement | 5 | Advertisement | La Puente HS | 21st Century classroom | San Gabriel Tribune | Newspaper Advertisement | 2024-02-01 | 2024-06-30 | 2023/24 | 24-5368 |  | 417.06 | 417.06 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9401101 | 0% | Advertising for Bid 2023-24.05 High School Refresh for La Puente HS & Workman HS. Publication dates: 11/01/23 & 11/06/23. | La Puente HS-5-21st Century classroom
Workman HS-21st Century classroom-Advertisement | 5 | Advertisement | Workman HS | 21st Century classroom | San Gabriel Tribune | Newspaper Advertisement | 2024-02-01 | 2024-06-30 | 2023/24 | 24-5368 |  | 417.06 | 417.06 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9431101 | 0% | Advertising for Bid 2023-24.05 High School Refresh for La Puente HS & Workman HS. Publication dates: 11/01/23 & 11/06/23. | Workman HS-5-21st Century classroom
Cedarlane-21st Century classroom-Advertisement | 1 | Advertisement | Cedarlane | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 2020/21 | 21-2253 | PO2W-210000000882 | 0 | 301.67 | 11412572 | 2020-10-19 | 000000020135642 | 301.67 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9051101 | 33.33% | Advertising for Bid 2020-21.01 HLPUSD Bid Bundle #2: 21st Century Classroom Improvements for Cedarlane, Mesa Robles, & Cedarlane Interim Housing. Publication dates: 09/22/20 & 09/28/20 | Cedarlane-1-21st Century classroom
Cedarlane-Interim Housing-Advertisement | 1 | Advertisement | Cedarlane | Interim Housing | San Gabriel Valley Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 2020/21 | 21-2253 | PO2W-210000000882 | 0 | 301.66 | 11412572 | 2020-10-19 | 000000020135642 | 301.66 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9051102 | 33.33% | Advertising for Bid 2020-21.01 HLPUSD Bid Bundle #2: 21st Century Classroom Improvements for Cedarlane, Mesa Robles, & Cedarlane Interim Housing. Publication dates: 09/22/20 & 09/28/20 | Cedarlane-1-Interim Housing
District Office-21st Century classroom-Advertisement | 0 | Advertisement | District Office | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2020-08-11 | 2020-10-22 | 2020/21 | 21-1254 | PO2W-210000000381 | 0 | 632 | 11403899 | 2020-10-22 | 000000020136840 | 632 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9851100 | 100% | Advertising seeking prequalification for contractors interested in bidding upcoming District's 21st Century modernization projects. Publication dates: 08/13/20 & 08/18/20 | District Office-0-21st Century classroom
District Office-21st Century classroom-Advertisement | 0 | Advertisement | District Office | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2022-03-15 | 2022-04-25 | 2021/22 | 22-5575 | PO2W-220000001958 | 0 | 611.25 | 0011522489 | 2022-04-25 | 000000020476690 | 611.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9851100 | 100% | Advertising seeking prequalification for contractors interested in bidding upcoming 21st Century modernization projects. Publication dates: 03/09/22 & 03/16/22 | District Office-0-21st Century classroom
Grandview-21st Century classroom-Advertisement | 2 | Advertisement | Grandview | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2022-07-19 | 2022-08-17 | 2022/23 | 23-844 | PO1-230000000194 | 0 | 324.48 | 0011549236 | 2022-08-17 | 000000020586484 | 324.48 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9121101 | 33.33% | Advertising for Bid 2022-23.01 HLPUSD Bid Bundle #3: 21st Century Classroom Improvements for Grandview. Publication dates: 07/20/22 & 07/27/22 | Grandview-2-21st Century classroom
Los Altos HS-21st Century classroom-Advertisement | 5 | Advertisement | Los Altos HS | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2023-12-15 | 2024-06-30 | 2023/24 | 24-4603 |  | 292.31 | 292.31 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9411101 | 0% | Advertising for Bid 2023-24.08 High School Refresh #2 for Stimson, Los Altos HS, & Wilson HS. Publication dates: 12/15/23 & 12/22/23 | Los Altos HS-5-21st Century classroom
Mesa Robles-21st Century classroom-Advertisement | 1 | Advertisement | Mesa Robles | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2020-10-05 | 2020-10-19 | 2020/21 | 21-2253 | PO2W-210000000882 | 0 | 301.67 | 11412572 | 2020-10-19 | 000000020135642 | 301.67 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9221101 | 33.33% | Advertising for Bid 2020-21.01 HLPUSD Bid Bundle #2: 21st Century Classroom Improvements for Cedarlane, Mesa Robles, & Cedarlane Interim Housing. Publication dates: 09/22/20 & 09/28/20 | Mesa Robles-1-21st Century classroom
Newton-21st Century classroom-Advertisement | 1 | Advertisement | Newton | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2022-07-19 | 2022-08-17 | 2022/23 | 23-844 | PO1-230000000194 | 0 | 324.48 | 11549236 | 2022-08-17 | 000000020586484 | 324.48 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9241101 | 33.33% | Advertising for Bid 2022-23.01 HLPUSD Bid Bundle #3: 21st Century Classroom Improvements for Grandview. Publication dates: 07/20/22 & 07/27/22 | Newton-1-21st Century classroom
Newton-Interim Housing-Advertisement | 1 | Advertisement | Newton | Interim Housing | San Gabriel Valley Tribune | Newspaper Advertisement | 2021-07-09 | 2021-07-30 | 2021/22 | 22-450 | PO2W-220000000052 | 0 | 1088 | 11469359 | 2021-07-30 | 000000020221431 | 1088 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9241102 | 100% | Advertising for Bid 2020-21.30 Newton Middle School Interim Housing. Publication dates: 06/15/21 & 06/21/21. | Newton-1-Interim Housing
Sparks MS-21st Century classroom-Advertisement | 2 | Advertisement | Sparks MS | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2022-07-19 | 2022-08-17 | 2022/23 | 23-844 | PO1-230000000194 | 0 | 324.48 | 11549236 | 2022-08-17 | 000000020586484 | 324.48 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9301101 | 33.33% | Advertising for Bid 2022-23.01 HLPUSD Bid Bundle #3: 21st Century Classroom Improvements for Grandview. Publication dates: 07/20/22 & 07/27/22 | Sparks MS-2-21st Century classroom
Stimson-21st Century classroom-Advertisement | 4 | Advertisement | Stimson | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2023-12-15 | 2024-06-30 | 2023/24 | 24-4603 |  | 292.31 | 292.31 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 8021101 | 0% | Advertising for Bid 2023-24.08 High School Refresh #2 for Stimson, Los Altos HS, & Wilson HS. Publication dates: 12/15/23 & 12/22/23 | Stimson-4-21st Century classroom
Wilson HS-21st Century classroom-Advertisement | 5 | Advertisement | Wilson HS | 21st Century classroom | San Gabriel Valley Tribune | Newspaper Advertisement | 2023-12-15 | 2024-06-30 | 2023/24 | 24-4603 |  | 292.31 | 292.31 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5830 | 9421101 | 0% | Advertising for Bid 2023-24.08 High School Refresh #2 for Stimson, Los Altos HS, & Wilson HS. Publication dates: 12/15/23 & 12/22/23 | Wilson HS-5-21st Century classroom
Amar-Ceiling replacement-Contractor | 0 | Contractor | Amar | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 17165.07 | Pay app #1 | 2019-12-17 | 000000020049998 | 17165.07 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9011105 | 0.3753% | Ceiling replacement for Amar. | Amar-0-Ceiling replacement
Amar-Ceiling replacement-Contractor | 0 | Contractor | Amar | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-03-07 | 2022/23 |  | PO1-200000000729 | 0 | 85825.38 | Pay app #7 | 2023-03-07 | 000000020889990 | 85825.38 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9011105 | 1.877% | Ceiling replacement for Amar. | Amar-0-Ceiling replacement
Amar-Ceiling replacement-Contractor | 0 | Contractor | Amar | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-18 | 2023/24 |  | PO1-200000000729 | 0 | 68660.3 | Pay app #8 | 2023-12-18 | 000000021374472 | 68660.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9011105 | 1.501% | Ceiling replacement for Amar. | Amar-0-Ceiling replacement
Amar-Ceiling replacement-Contractor | 0 | Contractor | Amar | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-4981 | PO1-200000000729 | 0 | 9034.25 | Retention | 2023-12-19 | 000000021377453 | 9034.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9011105 | 0.1975% | Ceiling replacement for Amar. | Amar-0-Ceiling replacement
Baldwin-Ceiling replacement-Contractor | 3 | Contractor | Baldwin | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 29986.18 | Pay app #1 | 2019-12-17 | 000000020049998 | 29986.18 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021105 | 0.6557% | Ceiling replacement for Baldwin. | Baldwin-3-Ceiling replacement
Baldwin-Ceiling replacement-Contractor | 3 | Contractor | Baldwin | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 89958.54 | Pay app #2 | 2020-10-21 | 000000020136454 | 89958.54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021105 | 1.967% | Ceiling replacement for Baldwin. | Baldwin-3-Ceiling replacement
Baldwin-Ceiling replacement-Contractor | 3 | Contractor | Baldwin | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 179917.08 | Pay app #5 | 2021-06-17 | 000000020198995 | 179917.08 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021105 | 3.934% | Ceiling replacement for Baldwin. | Baldwin-3-Ceiling replacement
Baldwin-Ceiling replacement-Contractor | 3 | Contractor | Baldwin | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5057 | PO1-200000000729 | 0 | 15782.2 | Retention | 2023-12-19 | 000000021377453 | 15782.2 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9021105 | 0.3451% | Ceiling replacement for Baldwin. | Baldwin-3-Ceiling replacement
Bixby-Ceiling replacement-Contractor | 6 | Contractor | Bixby | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 28196.47 | Pay app #1 | 2019-12-17 | 000000020049998 | 28196.47 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9031105 | 0.6165% | Ceiling replacement for Bixby. | Bixby-6-Ceiling replacement
Bixby-Ceiling replacement-Contractor | 6 | Contractor | Bixby | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-09-09 | 2021/22 |  | PO1-200000000729 | 0 | 253768.28 | Pay app #6 | 2021-09-09 | 000000020255213 | 253768.28 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9031105 | 5.549% | Ceiling replacement for Bixby. | Bixby-6-Ceiling replacement
Bixby-Ceiling replacement-Contractor | 6 | Contractor | Bixby | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5058 | PO1-200000000729 | 0 | 14840.25 | Retention | 2023-12-19 | 000000021377453 | 14840.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9031105 | 0.3245% | Ceiling replacement for Bixby. | Bixby-6-Ceiling replacement
California-Ceiling replacement-Contractor | 3 | Contractor | California | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 22513.29 | Pay app #1 | 2019-12-17 | 000000020049998 | 22513.29 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041105 | 0.4923% | Ceiling replacement for California. | California-3-Ceiling replacement
California-Ceiling replacement-Contractor | 3 | Contractor | California | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 202619.61 | Pay app #3 | 2021-01-08 | 000000020155354 | 202619.61 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041105 | 4.43% | Ceiling replacement for California. | California-3-Ceiling replacement
California-Ceiling replacement-Contractor | 3 | Contractor | California | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5059 | PO1-200000000729 | 0 | 11849.1 | Retention | 2023-12-19 | 000000021377453 | 11849.1 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9041105 | 0.2591% | Ceiling replacement for California. | California-3-Ceiling replacement
Del Valle-Ceiling replacement-Contractor | 7 | Contractor | Del Valle | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 31652.38 | Pay app #1 | 2019-12-17 | 000000020049998 | 31652.38 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061105 | 0.6921% | Ceiling replacement for Del Valle. | Del Valle-7-Ceiling replacement
Del Valle-Ceiling replacement-Contractor | 7 | Contractor | Del Valle | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 94957.16 | Pay app #2 | 2020-10-21 | 000000020136454 | 94957.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061105 | 2.076% | Ceiling replacement for Del Valle. | Del Valle-7-Ceiling replacement
Del Valle-Ceiling replacement-Contractor | 7 | Contractor | Del Valle | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 189914.31 | Pay app #3 | 2021-01-08 | 000000020155354 | 189914.31 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061105 | 4.153% | Ceiling replacement for Del Valle. | Del Valle-7-Ceiling replacement
Del Valle-Ceiling replacement-Contractor | 7 | Contractor | Del Valle | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5060 | PO1-200000000729 | 0 | 16659.15 | Retention | 2023-12-19 | 000000021377453 | 16659.15 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9061105 | 0.3643% | Ceiling replacement for Del Valle. | Del Valle-7-Ceiling replacement
Grazide-Ceiling replacement-Contractor | 3 | Contractor | Grazide | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 26751.81 | Pay app #1 | 2019-12-17 | 000000020049998 | 26751.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131105 | 0.5849% | Ceiling replacement for Grazide. | Grazide-3-Ceiling replacement
Grazide-Ceiling replacement-Contractor | 3 | Contractor | Grazide | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 80255.43 | Pay app #2 | 2020-10-21 | 000000020136454 | 80255.43 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131105 | 1.755% | Ceiling replacement for Grazide. | Grazide-3-Ceiling replacement
Grazide-Ceiling replacement-Contractor | 3 | Contractor | Grazide | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-04-27 | 2020/21 |  | PO1-200000000729 | 0 | 160510.86 | Pay app #3 | 2021-04-27 | 000000020183628 | 160510.86 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131105 | 3.51% | Ceiling replacement for Grazide. | Grazide-3-Ceiling replacement
Grazide-Ceiling replacement-Contractor | 3 | Contractor | Grazide | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5061 | PO1-200000000729 | 0 | 14079.9 | Retention | 2023-12-19 | 000000021377453 | 14079.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9131105 | 0.3079% | Ceiling replacement for Grazide. | Grazide-3-Ceiling replacement
Kwis-Ceiling replacement-Contractor | 7 | Contractor | Kwis | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 25747.66 | Pay app #1 | 2019-12-17 | 000000020049998 | 25747.66 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161105 | 0.563% | Ceiling replacement for Kwis. | Kwis-7-Ceiling replacement
Kwis-Ceiling replacement-Contractor | 7 | Contractor | Kwis | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 231728.94 | Pay app #5 | 2021-06-17 | 000000020198995 | 231728.94 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161105 | 5.067% | Ceiling replacement for Kwis. | Kwis-7-Ceiling replacement
Kwis-Ceiling replacement-Contractor | 7 | Contractor | Kwis | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5062 | PO1-200000000729 | 0 | 13551.4 | Retention | 2023-12-19 | 000000021377453 | 13551.4 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9161105 | 0.2963% | Ceiling replacement for Kwis. | Kwis-7-Ceiling replacement
Los Altos ES-Ceiling replacement-Contractor | 2 | Contractor | Los Altos ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 22069.45 | Pay app #1 | 2019-12-17 | 000000020049998 | 22069.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191105 | 0.4826% | Ceiling replacement for Los Altos ES. | Los Altos ES-2-Ceiling replacement
Los Altos ES-Ceiling replacement-Contractor | 2 | Contractor | Los Altos ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 198625.05 | Pay app #3 | 2021-01-08 | 000000020155354 | 198625.05 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191105 | 4.343% | Ceiling replacement for Los Altos ES. | Los Altos ES-2-Ceiling replacement
Los Altos ES-Ceiling replacement-Contractor | 2 | Contractor | Los Altos ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5063 | PO1-200000000729 | 0 | 11615.5 | Retention | 2023-12-19 | 000000021377453 | 11615.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9191105 | 0.254% | Ceiling replacement for Los Altos ES. | Los Altos ES-2-Ceiling replacement
Los Molinos-Ceiling replacement-Contractor | 4 | Contractor | Los Molinos | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 34108.32 | Pay app #1 | 2019-12-17 | 000000020049998 | 34108.32 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201105 | 0.7458% | Ceiling replacement for Los Molinos. | Los Molinos-4-Ceiling replacement
Los Molinos-Ceiling replacement-Contractor | 4 | Contractor | Los Molinos | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 102324.98 | Pay app #2 | 2020-10-21 | 000000020136454 | 102324.98 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201105 | 2.237% | Ceiling replacement for Los Molinos. | Los Molinos-4-Ceiling replacement
Los Molinos-Ceiling replacement-Contractor | 4 | Contractor | Los Molinos | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-04-27 | 2020/21 |  | PO1-200000000729 | 0 | 204649.95 | Pay app #3 | 2021-04-27 | 000000020183628 | 204649.95 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201105 | 4.475% | Ceiling replacement for Los Molinos. | Los Molinos-4-Ceiling replacement
Los Molinos-Ceiling replacement-Contractor | 4 | Contractor | Los Molinos | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5064 | PO1-200000000729 | 0 | 17951.75 | Retention | 2023-12-19 | 000000021377453 | 17951.75 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9201105 | 0.3925% | Ceiling replacement for Los Molinos. | Los Molinos-4-Ceiling replacement
Los Robles-Ceiling replacement-Contractor | 9 | Contractor | Los Robles | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 20840.81 | Pay app #1 | 2019-12-17 | 000000020049998 | 20840.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9211105 | 0.4557% | Ceiling replacement for Los Robles. | Los Robles-9-Ceiling replacement
Los Robles-Ceiling replacement-Contractor | 9 | Contractor | Los Robles | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 187567.34 | Pay app #5 | 2021-06-17 | 000000020198995 | 187567.34 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9211105 | 4.101% | Ceiling replacement for Los Robles. | Los Robles-9-Ceiling replacement
Los Robles-Ceiling replacement-Contractor | 9 | Contractor | Los Robles | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5065 | PO1-200000000729 | 0 | 10968.85 | Retention | 2023-12-19 | 000000021377453 | 10968.85 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9211105 | 0.2398% | Ceiling replacement for Los Robles. | Los Robles-9-Ceiling replacement
Nelson-Ceiling replacement-Contractor | 1 | Contractor | Nelson | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 29425.87 | Pay app #1 | 2019-12-17 | 000000020049998 | 29425.87 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231105 | 0.6434% | Ceiling replacement for Nelson. | Nelson-1-Ceiling replacement
Nelson-Ceiling replacement-Contractor | 1 | Contractor | Nelson | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 264832.83 | Pay app #3 | 2021-01-08 | 000000020155354 | 264832.83 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231105 | 5.791% | Ceiling replacement for Nelson. | Nelson-1-Ceiling replacement
Nelson-Ceiling replacement-Contractor | 1 | Contractor | Nelson | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5066 | PO1-200000000729 | 0 | 15487.3 | Retention | 2023-12-19 | 000000021377453 | 15487.3 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9231105 | 0.3386% | Ceiling replacement for Nelson. | Nelson-1-Ceiling replacement
Palm-Ceiling replacement-Contractor | 6 | Contractor | Palm | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 22069.45 | Pay app #1 | 2019-12-17 | 000000020049998 | 22069.45 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261105 | 0.4826% | Ceiling replacement for Palm. | Palm-6-Ceiling replacement
Palm-Ceiling replacement-Contractor | 6 | Contractor | Palm | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 66208.35 | Pay app #2 | 2020-10-21 | 000000020136454 | 66208.35 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261105 | 1.448% | Ceiling replacement for Palm. | Palm-6-Ceiling replacement
Palm-Ceiling replacement-Contractor | 6 | Contractor | Palm | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 132416.7 | Pay app #5 | 2021-06-17 | 000000020198995 | 132416.7 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261105 | 2.895% | Ceiling replacement for Palm. | Palm-6-Ceiling replacement
Palm-Ceiling replacement-Contractor | 6 | Contractor | Palm | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5067 | PO1-200000000729 | 0 | 11615.5 | Retention | 2023-12-19 | 000000021377453 | 11615.5 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9261105 | 0.254% | Ceiling replacement for Palm. | Palm-6-Ceiling replacement
Sparks ES-Ceiling replacement-Contractor | 7 | Contractor | Sparks ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 24521.59 | Pay app #1 | 2019-12-17 | 000000020049998 | 24521.59 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291105 | 0.5362% | Ceiling replacement for Sparks ES. | Sparks ES-7-Ceiling replacement
Sparks ES-Ceiling replacement-Contractor | 7 | Contractor | Sparks ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 73564.77 | Pay app #2 | 2020-10-21 | 000000020136454 | 73564.77 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291105 | 1.609% | Ceiling replacement for Sparks ES. | Sparks ES-7-Ceiling replacement
Sparks ES-Ceiling replacement-Contractor | 7 | Contractor | Sparks ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 147129.54 | Pay app #3 | 2021-01-08 | 000000020155354 | 147129.54 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291105 | 3.217% | Ceiling replacement for Sparks ES. | Sparks ES-7-Ceiling replacement
Sparks ES-Ceiling replacement-Contractor | 7 | Contractor | Sparks ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5068 | PO1-200000000729 | 0 | 12906.1 | Retention | 2023-12-19 | 000000021377453 | 12906.1 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9291105 | 0.2822% | Ceiling replacement for Sparks ES. | Sparks ES-7-Ceiling replacement
Sunset-Ceiling replacement-Contractor | 4 | Contractor | Sunset | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 23073.6 | Pay app #1 | 2019-12-17 | 000000020049998 | 23073.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311105 | 0.5045% | Ceiling replacement for Sunset. | Sunset-4-Ceiling replacement
Sunset-Ceiling replacement-Contractor | 4 | Contractor | Sunset | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 69220.8 | Pay app #2 | 2020-10-21 | 000000020136454 | 69220.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311105 | 1.514% | Ceiling replacement for Sunset. | Sunset-4-Ceiling replacement
Sunset-Ceiling replacement-Contractor | 4 | Contractor | Sunset | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-06-17 | 2020/21 |  | PO1-200000000729 | 0 | 138441.6 | Pay app #5 | 2021-06-17 | 000000020198995 | 138441.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311105 | 3.027% | Ceiling replacement for Sunset. | Sunset-4-Ceiling replacement
Sunset-Ceiling replacement-Contractor | 4 | Contractor | Sunset | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5069 | PO1-200000000729 | 0 | 12144 | Retention | 2023-12-19 | 000000021377453 | 12144 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9311105 | 0.2655% | Ceiling replacement for Sunset. | Sunset-4-Ceiling replacement
Temple-Ceiling replacement-Contractor | 8 | Contractor | Temple | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 24518.64 | Pay app #1 | 2019-12-17 | 000000020049998 | 24518.64 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9331105 | 0.5361% | Ceiling replacement for Temple. | Temple-8-Ceiling replacement
Temple-Ceiling replacement-Contractor | 8 | Contractor | Temple | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-04-27 | 2020/21 |  | PO1-200000000729 | 0 | 220667.81 | Pay app #3 | 2021-04-27 | 000000020183628 | 220667.81 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9331105 | 4.825% | Ceiling replacement for Temple. | Temple-8-Ceiling replacement
Temple-Ceiling replacement-Contractor | 8 | Contractor | Temple | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5070 | PO1-200000000729 | 0 | 12904.55 | Retention | 2023-12-19 | 000000021377453 | 12904.55 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9331105 | 0.2822% | Ceiling replacement for Temple. | Temple-8-Ceiling replacement
Wing Lane-Ceiling replacement-Contractor | 9 | Contractor | Wing Lane | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 28760.11 | Pay app #1 | 2019-12-17 | 000000020049998 | 28760.11 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9371105 | 0.6289% | Ceiling replacement for Wing Lane. | Wing Lane-9-Ceiling replacement
Wing Lane-Ceiling replacement-Contractor | 9 | Contractor | Wing Lane | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-04-27 | 2020/21 |  | PO1-200000000729 | 0 | 258840.99 | Pay app #3 | 2021-04-27 | 000000020183628 | 258840.99 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9371105 | 5.66% | Ceiling replacement for Wing Lane. | Wing Lane-9-Ceiling replacement
Wing Lane-Ceiling replacement-Contractor | 9 | Contractor | Wing Lane | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5071 | PO1-200000000729 | 0 | 15136.9 | Retention | 2023-12-19 | 000000021377453 | 15136.9 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9371105 | 0.331% | Ceiling replacement for Wing Lane. | Wing Lane-9-Ceiling replacement
Workman ES-Ceiling replacement-Contractor | 2 | Contractor | Workman ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2019-12-17 | 2019/20 |  | PO1-200000000729 | 0 | 23073.6 | Pay app #1 | 2019-12-17 | 000000020049998 | 23073.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381105 | 0.5045% | Ceiling replacement for Workman ES. | Workman ES-2-Ceiling replacement
Workman ES-Ceiling replacement-Contractor | 2 | Contractor | Workman ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2020-10-21 | 2020/21 |  | PO1-200000000729 | 0 | 69220.8 | Pay app #2 | 2020-10-21 | 000000020136454 | 69220.8 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381105 | 1.514% | Ceiling replacement for Workman ES. | Workman ES-2-Ceiling replacement
Workman ES-Ceiling replacement-Contractor | 2 | Contractor | Workman ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2021-01-08 | 2020/21 |  | PO1-200000000729 | 0 | 138441.6 | Pay app #3 | 2021-01-08 | 000000020155354 | 138441.6 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381105 | 3.027% | Ceiling replacement for Workman ES. | Workman ES-2-Ceiling replacement
Workman ES-Ceiling replacement-Contractor | 2 | Contractor | Workman ES | Ceiling replacement | Schneider Electric Buildings Americas, Inc. | Contractor | 2019-07-01 | 2023-12-19 | 2023/24 | 2-5072 | PO1-200000000729 | 0 | 12144 | Retention | 2023-12-19 | 000000021377453 | 12144 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381105 | 0.2655% | Ceiling replacement for Workman ES. | Workman ES-2-Ceiling replacement
Newton-Interim Housing-Utilities | 1 | Utilities | Newton | Interim Housing | Southern California Edison Co (SCE) | Temporary power | 2022-01-10 | 2022-01-24 | 2021/22 | 22-3884 | PO2W-220000001329 | 0 | 1072 | 454421 | 2022-01-24 | 000000020395794 | 1072 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6233 | 9241102 | 100% | Temporary power for Newton Interim Housing | Newton-1-Interim Housing
Baldwin-21st Century classroom-Design | 3 | Design | Baldwin | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002222 | 0 | 29733.8 | T8701 | 2021-09-09 | 000000020255214 | 29733.8 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 6.824% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Design | 3 | Design | Baldwin | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002222 | 0 | 26941.05 | 3294 | 2021-10-19 | 000000020302604 | 26941.05 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 6.183% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Design | 3 | Design | Baldwin | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002222 | 0 | 6874.45 | 3338 | 2021-10-19 | 000000020302604 | 6874.45 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 1.578% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Design | 3 | Design | Baldwin | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-24 | 2023/24 |  | PO2W-210000002222 | 0 | 59450 | 4474 | 2024-01-24 | 000000021424535 | 59450 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 13.64% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $98,590.00 for resumption of service. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Design | 3 | Design | Baldwin | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-24 | 2023/24 |  | PO2W-210000002222 | 0 | 35033.85 | 4628 | 2024-01-24 | 000000021424535 | 35033.85 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 8.041% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $98,590.00 for resumption of service. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Design | 3 | Design | Baldwin | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-25 | 2023/24 |  | PO2W-210000002222 | 0 | 39140 | 4553 | 2024-01-25 | 000000021427417 | 39140 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 8.983% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $98,590.00 for resumption of service. | Baldwin-3-21st Century classroom
Baldwin-21st Century classroom-Design | 3 | Design | Baldwin | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2027-07-11 | 2023/24 | 21-6236 | PO2W-210000002222 | 238521.85 | 238521.85 |  |  |  | 0 | 03-123988 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Baldwin. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $98,590.00 for resumption of service. | Baldwin-3-21st Century classroom
Baldwin-Interim Housing-Design | 3 | Design | Baldwin | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-11-30 | 2023/24 |  | PO2W-210000002227 | 79400 | 79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021102 | 0% | Architect - Prepare design documents for Baldwin Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Remaing balance in this PO | Baldwin-3-Interim Housing
Baldwin-Interim Housing-Design | 3 | Design | Baldwin | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-09 | 2023/24 | 21-6242 | PO2W-210000002227 | -79400 | -79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021102 | 0% | Architect - Prepare design documents for Baldwin Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Close-out PO | Baldwin-3-Interim Housing
California-21st Century classroom-Design | 3 | Design | California | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002223 | 0 | 24160.2 | T8702 | 2021-09-09 | 000000020255214 | 24160.2 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 7.146% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | California-3-21st Century classroom
California-21st Century classroom-Design | 3 | Design | California | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-10-01 | 2021/22 |  | PO2W-210000002223 | 0 | 18877.95 | T8722 | 2021-10-01 | 000000020283685 | 18877.95 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 5.583% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | California-3-21st Century classroom
California-21st Century classroom-Design | 3 | Design | California | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002223 | 0 | 19695.11 | 3339 | 2021-10-19 | 000000020302604 | 19695.11 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 5.825% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | California-3-21st Century classroom
California-21st Century classroom-Design | 3 | Design | California | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-24 | 2023/24 |  | PO2W-210000002223 | 0 | 53450 | 4473 | 2024-01-24 | 000000021424535 | 53450 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 15.81% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $92,590.00 for resumption of service. | California-3-21st Century classroom
California-21st Century classroom-Design | 3 | Design | California | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-24 | 2023/24 |  | PO2W-210000002223 | 0 | 9670.59 | 4629 | 2024-01-24 | 000000021424535 | 9670.59 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 2.86% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $92,590.00 for resumption of service. | California-3-21st Century classroom
California-21st Century classroom-Design | 3 | Design | California | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-29 | 2023/24 |  | PO2W-210000002223 | 0 | 39140 | 4554 | 2024-01-29 | 000000021432157 | 39140 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 11.58% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $92,590.00 for resumption of service. | California-3-21st Century classroom
California-21st Century classroom-Design | 3 | Design | California | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2027-07-11 | 2023/24 | 21-6238 | PO2W-210000002223 | 173121.15 | 173121.15 |  |  |  | 0 | 03-123989 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at California. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $92,590.00 for resumption of service. | California-3-21st Century classroom
California-Interim Housing-Design | 3 | Design | California | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002228 | 0 | 3096 | T8706 | 2021-09-09 | 000000020255214 | 3096 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041102 | 66.63% | Architect - Prepare design documents for California Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00 | California-3-Interim Housing
California-Interim Housing-Design | 3 | Design | California | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002228 | 0 | 1550.25 | 3340 | 2021-10-19 | 000000020302604 | 1550.25 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041102 | 33.37% | Architect - Prepare design documents for California Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00 | California-3-Interim Housing
California-Interim Housing-Design | 3 | Design | California | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-08 | 2023/24 |  | PO2W-210000002228 | 92753.75 | 92753.75 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041102 | 0% | Architect - Prepare design documents for California Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Remaining balance in this PO. | California-3-Interim Housing
California-Interim Housing-Design | 3 | Design | California | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-09 | 2023/24 | 21-6243 | PO2W-210000002228 | -92753.75 | -92753.75 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041102 | 0% | Architect - Prepare design documents for California Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Close-out PO. | California-3-Interim Housing
Grazide-21st Century classroom-Design | 3 | Design | Grazide | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002224 | 0 | 24121.52 | T8703 | 2021-09-09 | 000000020255214 | 24121.52 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131101 | 7.299% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Grazide. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Design | 3 | Design | Grazide | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002224 | 0 | 8978.93 | 3298 | 2021-10-19 | 000000020302604 | 8978.93 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131101 | 2.717% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Grazide. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Design | 3 | Design | Grazide | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-24 | 2023/24 |  | PO2W-210000002224 | 0 | 53450 | 4555 | 2024-01-24 | 000000021424535 | 53450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131101 | 16.17% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Grazide. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $85,910.00 for resumption of service. | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Design | 3 | Design | Grazide | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-29 | 2023/24 |  | PO2W-210000002224 | 0 | 32460 | 4630 | 2024-01-29 | 000000021432157 | 32460 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131101 | 9.822% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Grazide. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $85,910.00 for resumption of service. | Grazide-3-21st Century classroom
Grazide-21st Century classroom-Design | 3 | Design | Grazide | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2027-07-11 | 2023/24 | 21-6239 | PO2W-210000002224 | 211457.55 | 211457.55 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Grazide. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $85,910.00 for resumption of service. | Grazide-3-21st Century classroom
Grazide-Interim Housing-Design | 3 | Design | Grazide | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-11-30 | 2023/24 |  | PO2W-210000002229 | 79400 | 79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131102 | 0% | Architect - Prepare design documents for Grazide Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Remaining balance in this PO | Grazide-3-Interim Housing
Grazide-Interim Housing-Design | 3 | Design | Grazide | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-09 | 2023/24 | 21-6244 | PO2W-210000002229 | -79400 | -79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131102 | 0% | Architect - Prepare design documents for Grazide Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Close-out PO | Grazide-3-Interim Housing
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2018-10-11 | 2018/19 |  | PO2W-200000000858, 19-100485 | 0 | 3514.68 | T8158R | 2018-10-11 | 24850693 | 3514.68 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 3.791% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-01-28 | 2018/19 |  | PO2W-200000000858, 19-100485 | 0 | 3712 | R8227 | 2019-01-28 | 25052439 | 3712 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 4.004% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-09-05 | 2018/19 |  | PO2W-200000000858, 19-100485 | 0 | 20209.46 | T8309 | 2019-09-05 | 000000020011699 | 20209.46 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 21.8% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-09-13 | 2019/20 |  | PO2W-200000000858, 19-100485 | 0 | 28996.18 | T8352 | 2019-09-13 | 000000020015027 | 28996.18 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 31.27% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2020-06-04 | 2019/20 |  | PO2W-200000000858, 19-100485 | 0 | 8786.73 | T8518 | 2020-06-04 | 000000020102555 | 8786.73 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 9.477% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2021-02-05 | 2020/21 |  | PO2W-200000000858, 19-100485 | 0 | 18708.97 | T8573 | 2021-02-05 | 000000020162578 | 18708.97 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 20.18% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2021-04-19 | 2020/21 |  | PO2W-200000000858, 19-100485 | 0 | 4393.35 | T8635 | 2021-04-19 | 000000020181402 | 4393.35 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 4.739% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2021-12-20 | 2021/22 |  | PO2W-200000000858, 19-100485 | 0 | 4393.35 | 3378 | 2021-12-20 | 000000020370769 | 4393.35 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 4.739% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2021-12-20 | 2021/22 |  | PO2W-200000000858, 19-100485 | 15152.46 | 15152.46 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 0% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72. Remaining balance in this PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2022-02-07 | 2021/22 | 2-531 | PO2W-200000000858, 19-100485 | -15152.46 | -15152.46 |  |  |  | 0 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191101 | 0% | Architect - Prepare design documents for Los Altos ES 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5064) is $105,694.72. Close-out PO. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-Design | 2 | Design | Los Altos ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2020-05-11 | 2020-10-21 | 2020/21 | 2-10121 | PO2W-200000005064 | 0 | 12980 | T8578 | 2020-10-21 | 000000020136458 | 12980 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9191101 | 100% | Architect - These are additional changes requested by District since summer of 2019 for Los Altos ES. Changes to include replacing concrete walkway at classrooms in lieu of replacement of landing at door, revising new counter at new sink in classrooms, revising the electrical drawing, etc. Addendum to PO2W-20*858. The total architect costs with this change order is $105,694.72 | Los Altos ES-2-21st Century classroom
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2018-11-20 | 2018/19 |  | PO2W-200000000857, 19-100486 | 0 | 1515.6 | T8221 | 2018-11-20 | 24940853 | 1515.6 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 3.723% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-02-06 | 2018/19 |  | PO2W-200000000857, 19-100486 | 0 | 3410.12 | T8241 | 2019-02-06 | 25078803 | 3410.12 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 8.377% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-03-28 | 2018/19 |  | PO2W-200000000857, 19-100486 | 0 | 4774.16 | T8272 | 2019-03-28 | 25196520 | 4774.16 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 11.73% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-09-05 | 2018/19 |  | PO2W-200000000857, 19-100486 | 0 | 14928.74 | T8310 | 2019-09-05 | 000000020011699 | 14928.74 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 36.67% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-11-15 | 2019/20 |  | PO2W-200000000857, 19-100486 | 0 | 2816 | T8391 | 2019-11-15 | 000000020038501 | 2816 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 6.918% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. Allowances for topographic survey. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-12-11 | 2019/20 |  | PO2W-200000000857, 19-100486 | 0 | 9472.55 | T8429 | 2019-12-11 | 000000020047665 | 9472.55 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 23.27% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2020-06-04 | 2019/20 |  | PO2W-200000000857, 19-100486 | 0 | 3789.01 | T8519 | 2020-06-04 | 000000020102555 | 3789.01 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 9.308% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2023-12-09 | 2023/24 |  | PO2W-200000000857, 19-100486 | 17184 | 17184 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 0% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. Remaining balance in this PO. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Design | 2 | Design | Los Altos ES | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2023-12-09 | 2023/24 | 2-529 | PO2W-200000000857, 19-100486 | -17184 | -17184 |  |  |  | 0 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191102 | 0% | Architect - Prepare design documents for interim facilities related to Los Altos ES 21st Century classroom modernization project. Include work design for 5 portable classrooms and 1 portable restroom building. Include allowances of $20,000.00. Close-out PO. | Los Altos ES-2-Interim Housing
Los Molinos-21st Century classroom-Design | 4 | Design | Los Molinos | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002225 | 0 | 25060.16 | T8704 | 2021-09-09 | 000000020255214 | 25060.16 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201101 | 6.982% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Los Molinos. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Design | 4 | Design | Los Molinos | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002225 | 0 | 8326.87 | 3297 | 2021-10-19 | 000000020302604 | 8326.87 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201101 | 2.32% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Los Molinos. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Design | 4 | Design | Los Molinos | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-24 | 2023/24 |  | PO2W-210000002225 | 0 | 58450 | 4556 | 2024-01-24 | 000000021424535 | 58450 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201101 | 16.28% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Los Molinos. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $90,910.00 for resumption of service. | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Design | 4 | Design | Los Molinos | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2024-01-29 | 2023/24 |  | PO2W-210000002225 | 0 | 32460 | 4631 | 2024-01-29 | 000000021432157 | 32460 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201101 | 9.043% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Los Molinos. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $90,910.00 for resumption of service. | Los Molinos-4-21st Century classroom
Los Molinos-21st Century classroom-Design | 4 | Design | Los Molinos | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2027-07-11 | 2023/24 | 21-6240 | PO2W-210000002225 | 234636.97 | 234636.97 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Los Molinos. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Increase PO by $90,910.00 for resumption of service. | Los Molinos-4-21st Century classroom
Los Molinos-Interim Housing-Design | 4 | Design | Los Molinos | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-11-30 | 2023/24 |  | PO2W-210000002230 | 79400 | 79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201102 | 0% | Architect - Prepare design documents for Los Molinos Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Remaining balance in this PO | Los Molinos-4-Interim Housing
Los Molinos-Interim Housing-Design | 4 | Design | Los Molinos | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-09 | 2023/24 | 21-6245 | PO2W-210000002230 | -79400 | -79400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201102 | 0% | Architect - Prepare design documents for Los Molinos Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Close-out PO | Los Molinos-4-Interim Housing
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2018-10-11 | 2018/19 |  | PO2W-200000000859, 19-100470 | 0 | 3699.66 | T8157R | 2018-10-11 | 24850693 | 3699.66 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 3.753% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-01-28 | 2018/19 |  | PO2W-200000000859, 19-100470 | 0 | 4962 | R8235 | 2019-01-28 | 25052439 | 4962 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 5.033% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-09-05 | 2018/19 |  | PO2W-200000000859, 19-100470 | 0 | 21272.98 | T8308 | 2019-09-05 | 000000020011699 | 21272.98 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 21.58% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2019-09-11 | 2019/20 |  | PO2W-200000000859, 19-100470 | 0 | 30522.1 | T8351 | 2019-09-11 | 000000020013866 | 30522.1 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 30.96% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2020-06-04 | 2019/20 |  | PO2W-200000000859, 19-100470 | 0 | 9249.12 | T8517 | 2020-06-04 | 000000020102555 | 9249.12 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 9.382% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2020-10-21 | 2020/21 |  | PO2W-200000000859, 19-100470 | 0 | 19633.76 | T8572 | 2020-10-21 | 000000020136458 | 19633.76 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 19.91% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2021-04-19 | 2020/21 |  | PO2W-200000000859, 19-100470 | 0 | 4624.55 | T8634 | 2021-04-19 | 000000020181402 | 4624.55 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 4.691% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2021-12-20 | 2021/22 |  | PO2W-200000000859, 19-100470 | 0 | 4624.55 | 3377 | 2021-12-20 | 000000020370769 | 4624.55 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 4.691% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72 | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2021-12-21 | 2021/22 |  | PO2W-200000000859, 19-100470 | 13902.48 | 13902.48 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 0% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72. Remaining balance in this PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2018-07-17 | 2022-02-07 | 2021/22 | 2-532 | PO2W-200000000859, 19-100470 | -13902.48 | -13902.48 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231101 | 0% | Architect - Prepare design documents for Nelson 21st Century classroom modernization project. Include allowances of $20,000.00. The total architect costs with the change order (PO2W-20*5063) is $109,894.72. Close-out PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Design | 1 | Design | Nelson | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2020-05-11 | 2020-10-21 | 2020/21 | 2-10122 | PO2W-200000005063 | 0 | 11306 | T8577 | 2020-10-21 | 000000020136458 | 11306 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9231101 | 100% | Architect - These are additional changes requested by District since summer of 2019 for Nelson. Changes to include replacing concrete walkway at classrooms in lieu of replacement of landing at door, revising new counter at new sink in classrooms, revising the electrical drawing, etc. Addendum to PO2W-20*859. The total architect costs with this change order is $109,894.72 | Nelson-1-21st Century classroom
Sunset-21st Century classroom-Design | 4 | Design | Sunset | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-09-09 | 2021/22 |  | PO2W-210000002226 | 0 | 23712 | T8705 | 2021-09-09 | 000000020255214 | 23712 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311101 | 80.25% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Sunset. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Design | 4 | Design | Sunset | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2021-10-19 | 2021/22 |  | PO2W-210000002226 | 0 | 5833.89 | 3299 | 2021-10-19 | 000000020302604 | 5833.89 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311101 | 19.75% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Sunset. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Design | 4 | Design | Sunset | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-08 | 2023/24 |  | PO2W-210000002226 | 157014.11 | 157014.11 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Sunset. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Remaining balance inthis PO. | Sunset-4-21st Century classroom
Sunset-21st Century classroom-Design | 4 | Design | Sunset | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-09 | 2023/24 | 21-6241 | PO2W-210000002226 | -157014.11 | -157014.11 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311101 | 0% | Architect - Provide architectural & engineering services for phase 3 & 4 of the 21st Century project at Sunset. Scope of work includes basic topographic survey & full survey of the entire site. Include allowances of $20,000.00. Close-out PO. | Sunset-4-21st Century classroom
Sunset-Interim Housing-Design | 4 | Design | Sunset | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-08 | 2023/24 |  | PO2W-210000002231 | 97400 | 97400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311102 | 0% | Architect - Prepare design documents for Sunset Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Remaining balance in this PO. | Sunset-4-Interim Housing
Sunset-Interim Housing-Design | 4 | Design | Sunset | Interim Housing | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-05-03 | 2023-12-09 | 2023/24 | 21-6246 | PO2W-210000002231 | -97400 | -97400 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311102 | 0% | Architect - Prepare design documents for Sunset Interim Housing project. Scope of work includes design services of ADA path of travel to both areas of interim housing, power data, & stand alone fire alarm system. Include allowances of $20,000.00. Close-out PO. | Sunset-4-Interim Housing
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-04-08 | 2021-08-31 | 2021/22 |  | PO2W-210000002075 | 0 | 8116.8 | T8665R | 2021-08-31 | 000000020248528 | 8116.8 | 03-121545 | 73445-382 | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 100% | Architect - Prepare design documents for Workman ES 21st Century Hardware replacement project (doors & locks). | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-04-08 | 2023-12-08 | 2023/24 |  | PO2W-210000002075 | 5411.2 | 5411.2 |  |  |  | 0 | 03-121545 | 73445-382 | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 0% | Architect - Prepare design documents for Workman ES 21st Century Hardware replacement project (doors & locks). Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | 2021-04-08 | 2023-12-09 | 2023/24 | 21-5882 | PO2W-210000002075 | -5411.2 | -5411.2 |  |  |  | 0 | 03-121545 | 73445-382 | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 0% | Architect - Prepare design documents for Workman ES 21st Century Hardware replacement project (doors & locks). Close-out PO. | Workman ES-2-21st Century classroom
California-Interim Housing-Contractor | 3 | Contractor | California | Interim Housing | Suburban Water Systems | Fire flow testing | 2021-09-15 | 2021-09-27 | 2021/22 |  | PO2W-220000000489 | 0 | 212 | Per email | 2021-09-27 | 000000020272930 | 212 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041102 | 100% | Fee for fire flow testing performed or witnessed using Utility personnel for California. This fee applies to tests performed on distribution systems in the entire territory served by the Utility. | California-3-Interim Housing
California-Interim Housing-Contractor | 3 | Contractor | California | Interim Housing | Suburban Water Systems | Fire flow testing | 2021-09-15 | 2022-03-26 | 2021/22 | 22-1909 | PO2W-220000000489 | 0 | -212 | Per email | 2021-09-27 | 000000020272930 | -212 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9041102 | -100% | Fee for fire flow testing performed or witnessed using Utility personnel for California. This fee applies to tests performed on distribution systems in the entire territory served by the Utility. This warrant was stale dated. The project was on hold - email per Jeffrey Bissiri dated 03/30/22 (JVA22*1009). | California-3-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Suburban Water Systems | Fire flow testing | 2019-04-16 | 2019-04-17 | 2018/19 |  | 19-108466 | 0 | 212 | Per email | 2019-04-17 | 25234519 | 212 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051102 | 100% | Fee for fire flow testing performed or witnessed using Utility personnel for Cedarlane. This fee applies to tests performed on distribution systems in the entire territory served by the Utility. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-Contractor | 1 | Contractor | Cedarlane | Interim Housing | Suburban Water Systems | Deposit to construct (1) 6" public fire hydrant | 2019-11-25 | 2019-12-10 | 2019/20 | 2-5824 | PO2W-200000002737 | 0 | 3000 | Per email | 2019-12-10 | 000000020047106 | 3000 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9051102 | 100% | Deposit - Preliminary estimate to construct (1) 6" public fire hydrant at Cedarlane. | Cedarlane-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Suburban Water Systems | Fire flow testing | 2019-01-09 | 2019-01-11 | 2018/19 |  | 19-105188 | 0 | 636 | Per email | 2019-01-11 | 25024227 | 636 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221102 | 100% | Fee for 3 fire flow testing performed or witnessed using Utility personnel at Mesa Robles. This fee applies to tests performed on distribution systems in the entire territory served by the Utility. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Suburban Water Systems | Deposit for engineering costs to construct (1) 6" public fire hydrant | 2019-03-08 | 2019-03-12 | 2018/19 |  | 19-106996 | 0 | 2000 | Per email | 2019-03-12 | 25148637 | 2000 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221102 | 100% | Deposit - Preliminary estimate to construct (1) 6" public fire hydrant at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Suburban Water Systems | Remaining balance to construct (1) 6" public fire hydrant | 2020-01-08 | 2020-01-16 | 2019/20 | 2-6708 | PO2W-200000003306 | 0 | 39498.69 | Per email | 2020-01-16 | 000000020058736 | 39498.69 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9221102 | 100% | Remaining balance required to construct (1) 6" public fire hydrant for Mesa Robles. The winning bid amount has been adjusted to include estimates for engineering inspection, general administration, contingency, and tax gross-up costs. | Mesa Robles-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Suburban Water Systems | Fire flow testing | 2020-01-14 | 2020-01-23 | 2019/20 | 2-6872 | PO2W-200000003382 | 0 | 212 | Per email | 2020-01-23 | 000000020061285 | 212 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9241102 | 100% | Fee for fire flow testing performed or witnessed using Utility personnel at Newton. This fee applies to tests performed on distribution systems in the entire territory served by the Utility. | Newton-1-Interim Housing
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2018-06-28 | 2017/18 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 2363.68 | 54895 | 2018-06-28 | 24653416 | 2363.68 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 2% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2019-04-03 | 2018/19 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 4581.84 | 55730 Revised | 2019-04-03 | 25206760 | 4581.84 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 3.877% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2019-09-05 | 2018/19 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 23782.32 | 55870 | 2019-09-05 | 000000020011695 | 23782.32 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 20.12% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2019-09-05 | 2018/19 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 30432.38 | 55871 | 2019-09-05 | 000000020011695 | 30432.38 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 25.75% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2019-10-25 | 2019/20 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 1950.04 | 20031048 | 2019-10-25 | 000000020031048 | 1950.04 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 1.65% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2019-10-25 | 2019/20 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 3900.07 | 20031048 | 2019-10-25 | 000000020031048 | 3900.07 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 3.3% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2020-05-26 | 2019/20 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 9809.27 | 56735R | 2020-05-26 | 000000020099838 | 9809.27 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 8.3% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2020-08-18 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 5909.2 | 56975 | 2020-08-18 | 000000020120097 | 5909.2 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 5% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2021-02-05 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 14773 | 57291 | 2021-02-05 | 000000020162573 | 14773 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 12.5% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2021-02-05 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 4431.9 | 57389 | 2021-02-05 | 000000020162573 | 4431.9 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 3.75% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2022-03-24 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 2954.6 | 57466R | 2022-03-24 | 000000020451068 | 2954.6 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 2.5% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2022-03-24 | 2020/21 |  | PO2W-200000001213, 19-100506, 18-109555 | 0 | 9750.18 | 57966R | 2022-03-24 | 000000020451068 | 9750.18 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 8.25% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2022-05-04 | 2021/22 | 2-526 | PO2W-200000001213, 19-100506, 18-109555 | 0 | 3545.52 | 58793 | 2022-05-04 | 000000020484174 | 3545.52 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 3% | Architect - Scope of work consists of modernization interior of classrooms, replace sink/faucets, new monitors/projectors, update technology systems, provide additional power as required, and update accessible path of travel at Workman ES. The total architect costs including allowances (PO2W-20*1214) is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2019-02-08 | 2018/19 |  | PO2W-200000001214, 19-101982 | 0 | 3450 | 55509 | 2019-02-08 | 25085117 | 3450 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 65.03% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES. Addendum to PO2W-20*1213. The total architect costs including this allowances is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2019-02-08 | 2018/19 |  | PO2W-200000001214, 19-101982 | 0 | 1450 | 55510 | 2019-02-08 | 25085117 | 1450 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 27.33% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES. Addendum to PO2W-20*1213. The total architect costs including this allowances is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2020-06-03 | 2019/20 |  | PO2W-200000001214, 19-101982 | 0 | 404.95 | 56736R | 2020-06-03 | 000000020102139 | 404.95 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 7.633% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES. Addendum to PO2W-20*1213. The total architect costs including this allowances is $123,488.95 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2021-06-30 | 2021/22 |  | PO2W-200000001214, 19-101982 | 14695.05 | 14695.05 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 0% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES. Addendum to PO2W-20*1213. The total architect costs including this allowances is $123,488.95. Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Design | 2 | Design | Workman ES | 21st Century classroom | SVA Architects, Inc. | Architect | 2018-06-01 | 2022-04-28 | 2021/22 | 2-527 | PO2W-200000001214, 19-101982 | -14695.05 | -14695.05 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381101 | 0% | Architect - Allowances to be used for civil engineering and related services in 21st Century classroom projects at Workman ES. Addendum to PO2W-20*1213. The total architect costs including this allowances is $123,488.95. Close-out PO | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Fees | 2 | DSA Fees | Workman ES | 21st Century classroom | SVA Architects, Inc. | DSA fees | 2020-02-27 | 2020-04-02 | 2019/20 | 2-8457 | PO2W-200000004424 | 0 | 2250 | 56405 | 2020-04-02 | 000000020086382 | 2250 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6230 | 9381101 | 100% | Plan check review fee for 21st Century at Workman ES | Workman ES-2-21st Century classroom
Baldwin-Fire Alarm replacement-Design | 3 | Design | Baldwin | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2023-03-02 | 2022/23 |  | PO2W-210000000680 | 12125 | 12125 |  |  |  | 0 | 03-120157 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Baldwin. Facilities paid PO2W-20*3585 & 19-109869 in the amount of $36,375.00. The original architect contract for Baldwin FA is $48,500.00. Remaining balance in this PO | Baldwin-3-Fire Alarm replacement
Baldwin-Fire Alarm replacement-Design | 3 | Design | Baldwin | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2023-03-03 | 2022/23 | 21-1992 | PO2W-210000000680 | -12125 | -12125 |  |  |  | 0 | 03-120157 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9021103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Baldwin. Facilities paid PO2W-20*3585 & 19-109869 in the amount of $36,375.00. The total architect contract for Baldwin FA is $48,500.00. Close-out PO | Baldwin-3-Fire Alarm replacement
Bixby-Fire Alarm replacement-Design | 6 | Design | Bixby | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-02 | 2022/23 |  | PO1-200000000846 | 12125 | 12125 |  |  |  | 0 | 03-120620 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9031103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Bixby. Facilities paid PO2W-20*4417 in the amount of $36,375.00. The total architect contract for Bixby FA is $48,500.00. Remaining balance in this PO | Bixby-6-Fire Alarm replacement
Bixby-Fire Alarm replacement-Design | 6 | Design | Bixby | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-03 | 2022/23 | 2-6863 | PO1-200000000846 | -12125 | -12125 |  |  |  | 0 | 03-120620 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9031103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Bixby. Facilities paid PO2W-20*4417 in the amount of $36,375.00. The total architect contract for Bixby FA is $48,500.00. Close-out PO. | Bixby-6-Fire Alarm replacement
California-Fire Alarm replacement-Design | 3 | Design | California | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28169 | 2021-02-05 | 000000020162584 | 2425 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The original architect contract for California FA is $48,500.00 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Design | 3 | Design | California | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28227 | 2021-02-05 | 000000020162584 | 2425 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The original architect contract for California FA is $48,500.00 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Design | 3 | Design | California | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28469 | 2021-03-24 | 000000020174735 | 2425 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The original architect contract for California FA is $48,500.00 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Design | 3 | Design | California | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28606 | 2021-05-26 | 000000020192536 | 2425 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The original architect contract for California FA is $48,500.00 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Design | 3 | Design | California | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1455 | 28733 | 2021-09-09 | 000000020255226 | 1455 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 1.155% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The original architect contract for California FA is $48,500.00 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Design | 3 | Design | California | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-01-19 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 970 | 29053 | 2022-01-19 | 000000020391276 | 970 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9041103 | 0.7697% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for California. Facilities paid PO1-20*891 & 19-109871 in the amount of $36,375.00. The original architect contract for California FA is $48,500.00 | California-3-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Design | 1 | Design | Cedarlane | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28044 | 2020-10-14 | 000000020134523 | 2375 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Cedarlane. Facilities paid PO2W-20*5349 & 19-104043 in the amount of $42,750.00. The original architect contract for Cedarlane FA is $47,500.00 | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Design | 1 | Design | Cedarlane | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28165 | 2021-02-05 | 000000020162584 | 1425 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051103 | 1.131% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Cedarlane. Facilities paid PO2W-20*5349 & 19-104043 in the amount of $42,750.00. The original architect contract for Cedarlane FA is $47,500.00 | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Design | 1 | Design | Cedarlane | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 | 21-1992 | PO2W-210000000680 | 0 | 950 | 28461 | 2021-03-24 | 000000020174735 | 950 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9051103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Cedarlane. Facilities paid PO2W-20*5349 & 19-104043 in the amount of $42,750.00. The original architect contract for Cedarlane FA is $47,500.00 | Cedarlane-1-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28228 | 2021-02-05 | 000000020162584 | 7275 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. | Del Valle-7-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28289 | 2021-02-09 | 000000020163360 | 7275 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. | Del Valle-7-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28385 | 2021-03-24 | 000000020174735 | 7275 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. | Del Valle-7-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28514 | 2021-05-26 | 000000020192536 | 2425 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. | Del Valle-7-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28608 | 2021-05-26 | 000000020192536 | 9700 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 3.316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. | Del Valle-7-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28684 | 2021-06-23 | 000000020200466 | 1455 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0.4974% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. | Del Valle-7-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28833 | 2021-09-09 | 000000020255227 | 970 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0.3316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. | Del Valle-7-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-02 | 2022/23 |  | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. Remaining balance in this PO | Del Valle-7-Fire Alarm replacement
Del Valle-Fire Alarm replacement-Design | 7 | Design | Del Valle | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-03 | 2022/23 | 21-2535 | PO2W-210000000984 | -12125 | -12125 |  |  |  | 0 | 03-121431 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9061103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Del Valle. Close-out PO | Del Valle-7-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Design | 4 | Design | Fairgrove | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28383 | 2021-03-24 | 000000020174735 | 2425 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The original architect contract for Fairgrove FA is $48,500.00 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Design | 4 | Design | Fairgrove | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28470 | 2021-03-24 | 000000020174735 | 2425 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The original architect contract for Fairgrove FA is $48,500.00 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Design | 4 | Design | Fairgrove | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28520 | 2021-05-26 | 000000020192536 | 2425 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The original architect contract for Fairgrove FA is $48,500.00 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Design | 4 | Design | Fairgrove | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28614 | 2021-05-26 | 000000020192536 | 2425 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The original architect contract for Fairgrove FA is $48,500.00 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Design | 4 | Design | Fairgrove | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1455 | 28735 | 2021-09-09 | 000000020255226 | 1455 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 1.155% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The original architect contract for Fairgrove FA is $48,500.00 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Design | 4 | Design | Fairgrove | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-06-23 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 970 | 29413 | 2022-06-23 | 000000020533756 | 970 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9091103 | 0.7697% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Fairgrove. Facilities paid PO1-20*892 & 19-109872 in the amount of $36,375.00. The original architect contract for Fairgrove FA is $48,500.00 | Fairgrove-4-Fire Alarm replacement
Grandview-Fire Alarm replacement-Design | 2 | Design | Grandview | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28044 | 2020-10-14 | 000000020134523 | 2375 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The original architect contract for Grandview FA is $47,500.00 | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Design | 2 | Design | Grandview | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28116 | 2021-01-07 | 000000020154828 | 2375 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The original architect contract for Grandview FA is $47,500.00 | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Design | 2 | Design | Grandview | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28378 | 2021-03-24 | 000000020174735 | 2375 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The original architect contract for Grandview FA is $47,500.00 | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Design | 2 | Design | Grandview | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28463 | 2021-03-24 | 000000020174735 | 2375 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The original architect contract for Grandview FA is $47,500.00 | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Design | 2 | Design | Grandview | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28729 | 2021-09-09 | 000000020255226 | 1425 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 1.131% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The original architect contract for Grandview FA is $47,500.00 | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Design | 2 | Design | Grandview | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-11-17 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 28994 | 2021-11-17 | 000000020338267 | 950 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9121103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grandview. Facilities paid PO1-20*893 & 19-104049 in the amount of $35,625.00. The original architect contract for Grandview FA is $47,500.00 | Grandview-2-Fire Alarm replacement
Grazide-Fire Alarm replacement-Design | 3 | Design | Grazide | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-02 | 2022/23 |  | PO1-200000000846 | 12125 | 12125 |  |  |  | 0 | 03-120624 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grazide. Facilities paid PO2W-20*4418 in the amount of $36,375.00. The total architect contract for Grazide FA is $48,500.00. Remaining balance in this PO | Grazide-3-Fire Alarm replacement
Grazide-Fire Alarm replacement-Design | 3 | Design | Grazide | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-03 | 2022/23 | 2-6865 | PO1-200000000846 | -12125 | -12125 |  |  |  | 0 | 03-120624 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9131103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Grazide. Facilities paid PO2W-20*4418 in the amount of $36,375.00. The total architect contract for Grazide FA is $48,500.00. Close-out PO. | Grazide-3-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28229 | 2021-02-05 | 000000020162584 | 7275 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. | Kwis-7-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28290 | 2021-02-09 | 000000020163360 | 7275 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. | Kwis-7-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28386 | 2021-03-24 | 000000020174735 | 7275 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. | Kwis-7-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28515 | 2021-05-26 | 000000020192536 | 2425 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. | Kwis-7-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28609 | 2021-05-26 | 000000020192536 | 9700 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 3.316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. | Kwis-7-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28685 | 2021-06-23 | 000000020200466 | 1455 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0.4974% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. | Kwis-7-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28834 | 2021-09-09 | 000000020255227 | 970 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0.3316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. | Kwis-7-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-02 | 2022/23 |  | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. Remaining balance in this PO | Kwis-7-Fire Alarm replacement
Kwis-Fire Alarm replacement-Design | 7 | Design | Kwis | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-03 | 2022/23 | 21-2535 | PO2W-210000000984 | -12125 | -12125 |  |  |  | 0 | 03-121430 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9161103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Kwis. Close-out PO | Kwis-7-Fire Alarm replacement
La Puente HS-Fire Alarm replacement-Design | 5 | Design | La Puente HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2023-03-02 | 2022/23 |  | PO2W-210000000680 | 14700 | 14700 |  |  |  | 0 | 03-119978 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9401103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for La Puente HS. Facilities paid PO1-20*905 & 19-109188 in the amount of $44,100.00. The original architect contract for La Puente HS FA is $58,800.00. Remaining balance in this PO | La Puente HS-5-Fire Alarm replacement
La Puente HS-Fire Alarm replacement-Design | 5 | Design | La Puente HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2023-03-03 | 2022/23 | 21-1992 | PO2W-210000000680 | -14700 | -14700 |  |  |  | 0 | 03-119978 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9401103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for La Puente HS. Facilities paid PO1-20*905 & 19-109188 in the amount of $44,100.00. The original architect contract for La Puente HS FA is $58,800.00. Close-out PO | La Puente HS-5-Fire Alarm replacement
Lassalette-Fire Alarm replacement-Design | 6 | Design | Lassalette | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-02 | 2022/23 |  | PO1-200000000846 | 12375 | 12375 |  |  |  | 0 | 03-120621 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9171103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Lassalette. Facilities paid PO2W-20*4419 in the amount of $37,125.00. The total architect contract for Lassalette FA is $49,500.00. Remaining balance in this PO | Lassalette-6-Fire Alarm replacement
Lassalette-Fire Alarm replacement-Design | 6 | Design | Lassalette | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-03 | 2022/23 | 2-6866 | PO1-200000000846 | -12375 | -12375 |  |  |  | 0 | 03-120621 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9171103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Lassalette. Facilities paid PO2W-20*4419 in the amount of $37,125.00. The total architect contract for Lassalette FA is $49,500.00. Close-out PO. | Lassalette-6-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Design | 2 | Design | Los Altos ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 4750 | 28381 | 2021-03-24 | 000000020174735 | 4750 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 3.769% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The original architect contract for Los Altos ES FA is $47,500.00 | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Design | 2 | Design | Los Altos ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28466 | 2021-03-24 | 000000020174735 | 2375 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The original architect contract for Los Altos ES FA is $47,500.00 | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Design | 2 | Design | Los Altos ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28605 | 2021-05-26 | 000000020192536 | 2375 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The original architect contract for Los Altos ES FA is $47,500.00 | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Design | 2 | Design | Los Altos ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28732 | 2021-09-09 | 000000020255226 | 1425 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 1.131% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The original architect contract for Los Altos ES FA is $47,500.00 | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Design | 2 | Design | Los Altos ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-01-19 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 29052 | 2022-01-19 | 000000020391276 | 950 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9191103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos ES. Facilities paid PO1-20*895 & 19-104050 in the amount of $35,625.00. The original architect contract for Los Altos ES FA is $47,500.00 | Los Altos ES-2-Fire Alarm replacement
Los Altos HS-Fire Alarm replacement-Design | 5 | Design | Los Altos HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2023-03-02 | 2022/23 |  | PO2W-210000000680 | 13950 | 13950 |  |  |  | 0 | 03-120155 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9411103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos HS. Facilities paid PO1-20*907 & 19-109186 in the amount of $41,850.00. The original architect contract for Los Altos HS FA is $55,800.00. Remaining balance in this PO | Los Altos HS-5-Fire Alarm replacement
Los Altos HS-Fire Alarm replacement-Design | 5 | Design | Los Altos HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2023-03-03 | 2022/23 | 21-1992 | PO2W-210000000680 | -13950 | -13950 |  |  |  | 0 | 03-120155 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9411103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Altos HS. Facilities paid PO1-20*907 & 19-109186 in the amount of $41,850.00. The original architect contract for Los Altos HS FA is $55,800.00. Close-out PO | Los Altos HS-5-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Design | 4 | Design | Los Molinos | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28384 | 2021-03-24 | 000000020174735 | 2425 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Molinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The original architect contract for Los Molinos FA is $48,500.00 | Los Molinos-4-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Design | 4 | Design | Los Molinos | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2425 | 28471 | 2021-03-24 | 000000020174735 | 2425 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 1.924% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Molinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The original architect contract for Los Molinos FA is $48,500.00 | Los Molinos-4-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Design | 4 | Design | Los Molinos | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 4850 | 28607 | 2021-05-26 | 000000020192536 | 4850 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 3.848% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Molinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The original architect contract for Los Molinos FA is $48,500.00 | Los Molinos-4-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Design | 4 | Design | Los Molinos | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1455 | 28734 | 2021-09-09 | 000000020255226 | 1455 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 1.155% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Molinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The original architect contract for Los Molinos FA is $48,500.00 | Los Molinos-4-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Design | 4 | Design | Los Molinos | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-06-23 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 970 | 29414 | 2022-06-23 | 000000020533756 | 970 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9201103 | 0.7697% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Molinos. Facilities paid PO1-20*896 & 19-109874 in the amount of $36,375.00. The original architect contract for Los Molinos FA is $48,500.00 | Los Molinos-4-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28230 | 2021-02-05 | 000000020162584 | 7275 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. | Los Robles-9-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28291 | 2021-02-09 | 000000020163360 | 7275 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. | Los Robles-9-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28387 | 2021-03-24 | 000000020174735 | 7275 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. | Los Robles-9-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28516 | 2021-05-26 | 000000020192536 | 2425 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. | Los Robles-9-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28610 | 2021-05-26 | 000000020192536 | 9700 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 3.316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. | Los Robles-9-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28686 | 2021-06-23 | 000000020200466 | 1455 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0.4974% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. | Los Robles-9-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28835 | 2021-09-09 | 000000020255227 | 970 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0.3316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. | Los Robles-9-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-02 | 2022/23 |  | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. Remaining balance in this PO | Los Robles-9-Fire Alarm replacement
Los Robles-Fire Alarm replacement-Design | 9 | Design | Los Robles | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-03 | 2022/23 | 21-2535 | PO2W-210000000984 | -12125 | -12125 |  |  |  | 0 | 03-121429 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9211103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Los Robles. Close-out PO | Los Robles-9-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Design | 1 | Design | Mesa Robles | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28121 | 2021-01-07 | 000000020154828 | 2375 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The original architect contract for Mesa Robles FA is $47,500.00 | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Design | 1 | Design | Mesa Robles | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28226 | 2021-02-05 | 000000020162584 | 2375 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The original architect contract for Mesa Robles FA is $47,500.00 | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Design | 1 | Design | Mesa Robles | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28379 | 2021-03-24 | 000000020174735 | 2375 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The original architect contract for Mesa Robles FA is $47,500.00 | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Design | 1 | Design | Mesa Robles | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28464 | 2021-03-24 | 000000020174735 | 2375 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The original architect contract for Mesa Robles FA is $47,500.00 | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Design | 1 | Design | Mesa Robles | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28730 | 2021-09-09 | 000000020255226 | 1425 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 1.131% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The original architect contract for Mesa Robles FA is $47,500.00 | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Design | 1 | Design | Mesa Robles | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-12-10 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 28931 | 2021-12-10 | 000000020346458 | 950 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Mesa Robles. Facilities paid PO1-20*897 & 19-104051 in the amount of $35,625.00. The original architect contract for Mesa Robles FA is $47,500.00 | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2019-08-22 | 2018/19 |  | PO2W-200000000855, 19-109962 | 0 | 26100 | 27120 | 2019-08-22 | 000000020007292 | 26100 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 30% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2019-09-23 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 30450 | 27161 | 2019-09-23 | 000000020018005 | 30450 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 35% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-01-15 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 8700 | 27447 | 2020-01-15 | 000000020057976 | 8700 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 10% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-05-26 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 4350 | 27763 | 2020-05-26 | 000000020099864 | 4350 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 5% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-06-19 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 4350 | 27834 | 2020-06-19 | 000000020106941 | 4350 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 5% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-08-18 | 2019/20 |  | PO2W-200000000855, 19-109962 | 0 | 2610 | 27928 | 2020-08-18 | 000000020120112 | 2610 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 3% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-10-14 | 2020/21 |  | PO2W-200000000855, 19-109962 | 0 | 1740 | 27977 | 2020-10-14 | 000000020134523 | 1740 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 2% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2020-10-14 | 2020/21 |  | PO2W-200000000855, 19-109962 | 0 | 4350 | 28050 | 2020-10-14 | 000000020134523 | 4350 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 5% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2021-02-05 | 2020/21 |  | PO2W-200000000855, 19-109962 | 0 | 2610 | 28235 | 2021-02-05 | 000000020162584 | 2610 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 3% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Design | 1 | Design | Mesa Robles | Interim Housing | tBP Architecture | Architect | 2019-06-11 | 2021-10-01 | 2021/22 | 2-523 | PO2W-200000000855, 19-109962 | 0 | 1740 | 28879 | 2021-10-01 | 000000020283689 | 1740 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9221102 | 2% | Architect - Provide architectural & engineering services to place 8 portable classrooms (24' x 40") on raised foundations at Mesa Robles. | Mesa Robles-1-Interim Housing
Nelson-Fire Alarm replacement-Design | 1 | Design | Nelson | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 4750 | 28380 | 2021-03-24 | 000000020174735 | 4750 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 3.769% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The original architect contract for Nelson FA is $47,500.00 | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Design | 1 | Design | Nelson | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28465 | 2021-03-24 | 000000020174735 | 2375 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The original architect contract for Nelson FA is $47,500.00 | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Design | 1 | Design | Nelson | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28604 | 2021-05-26 | 000000020192536 | 2375 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The original architect contract for Nelson FA is $47,500.00 | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Design | 1 | Design | Nelson | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28731 | 2021-09-09 | 000000020255226 | 1425 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 1.131% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The original architect contract for Nelson FA is $47,500.00 | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Design | 1 | Design | Nelson | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-02-23 | 2021/22 |  | PO2W-210000000680 | 0 | 950 | 29184 | 2022-02-23 | 000000020425550 | 950 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The original architect contract for Nelson FA is $47,500.00 | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Design | 1 | Design | Nelson | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-04-04 | 2021/22 |  | PO2W-210000000680 | 0 | -950 | 29184 | 2022-02-23 | 000000020425550 | -950 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | -0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The original architect contract for Nelson FA is $47,500.00. Warrant was lost in the mail | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Design | 1 | Design | Nelson | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-04-06 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 29184 | 2022-04-06 | 000000020463387 | 950 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9231103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Nelson. Facilities paid PO1-20*898 & 19-104052 in the amount of $35,625.00. The total architect contract for Nelson FA is $47,500.00. Replaced warrant #2042550 which was lost in the mail. | Nelson-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Design | 1 | Design | Newton | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2020-09-18 | 2020/21 |  | PO1-200000000899, 19-104053, JVER21-187 | 0 | 7125 | 27975 | 2020-09-18 | 20122659 | 7125 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241103 | 100% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Newton. Facilities paid PO1-20*899 & 19-104053 in the amount of $45,125.00. The total architect contract for Newton FA is $47,500.00. $47,500.00 - (38,000.00 + 7,125.00) (Facil pymts) = $2,375.00 (PO2W-21*680 for Newton) | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Design | 1 | Design | Newton | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28167 | 2021-02-05 | 000000020162584 | 1425 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241103 | 1.131% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Newton. Facilities paid PO1-20*899 & 19-104053 in the amount of $45,125.00. The original architect contract for Newton FA is $47,500.00. $47,500.00 - (38,000.00 + 7,125.00) (Facil pymts) = $2,375.00 (PO2W-21*680) | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Design | 1 | Design | Newton | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-05-26 | 2020/21 | 21-1992 | PO2W-210000000680 | 0 | 950 | 28513 | 2021-05-26 | 000000020192536 | 950 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9241103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Newton. Facilities paid PO1-20*899 & 19-104053 in the amount of $45,125.00. The original architect contract for Newton FA is $47,500.00. $47,500.00 - (38,000.00 + 7,125.00) (Facil pymts) = $2,375.00 (PO2W-21*680) | Newton-1-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7425 | 28231 | 2021-02-05 | 000000020162584 | 7425 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 2.538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 4920 | 28292 | 2021-02-09 | 000000020163360 | 4920 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 1.682% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-22 | 2020/21 |  | PO2W-210000000984 | 0 | 30 | 28292 | 2021-02-22 | 000000020166218 | 30 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0.01026% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4950 | 28388 | 2021-03-24 | 000000020174735 | 4950 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 1.692% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4950 | 28472 | 2021-03-24 | 000000020174735 | 4950 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 1.692% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2475 | 28521 | 2021-05-26 | 000000020192536 | 2475 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0.8462% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9900 | 28615 | 2021-05-26 | 000000020192536 | 9900 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 3.385% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1485 | 28688 | 2021-06-23 | 000000020200466 | 1485 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0.5077% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 990 | 28836 | 2021-09-09 | 000000020255227 | 990 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0.3385% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-02 | 2022/23 |  | PO2W-210000000984 | 12375 | 12375 |  |  |  | 0 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. Remaining balance in this PO | Orange Grove-3-Fire Alarm replacement
Orange Grove-Fire Alarm replacement-Design | 3 | Design | Orange Grove | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-03 | 2022/23 | 21-2535 | PO2W-210000000984 | -12375 | -12375 |  |  |  | 0 | 03-121428 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9251103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Orange Grove. Close-out PO | Orange Grove-3-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28232 | 2021-02-05 | 000000020162584 | 7275 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28293 | 2021-02-09 | 000000020163360 | 7275 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4850 | 28389 | 2021-03-24 | 000000020174735 | 4850 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 1.658% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28473 | 2021-03-24 | 000000020174735 | 2425 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28522 | 2021-05-26 | 000000020192536 | 2425 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28616 | 2021-05-26 | 000000020192536 | 9700 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 3.316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28689 | 2021-06-23 | 000000020200466 | 1455 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0.4974% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28837 | 2021-09-09 | 000000020255227 | 970 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0.3316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-02 | 2022/23 |  | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. Remaining balance in this PO | Palm-6-Fire Alarm replacement
Palm-Fire Alarm replacement-Design | 6 | Design | Palm | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-03 | 2022/23 | 21-2535 | PO2W-210000000984 | -12125 | -12125 |  |  |  | 0 | 03-121427 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9261103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Palm. Close-out PO | Palm-6-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-Design | 8 | Design | Sierra Vista | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 14850 | 28390 | 2021-03-24 | 000000020174735 | 14850 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 5.077% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista. | Sierra Vista-8-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-Design | 8 | Design | Sierra Vista | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4950 | 28474 | 2021-03-24 | 000000020174735 | 4950 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 1.692% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista. | Sierra Vista-8-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-Design | 8 | Design | Sierra Vista | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 4950 | 28523 | 2021-05-26 | 000000020192536 | 4950 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 1.692% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista. | Sierra Vista-8-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-Design | 8 | Design | Sierra Vista | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9900 | 28617 | 2021-05-26 | 000000020192536 | 9900 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 3.385% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista. | Sierra Vista-8-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-Design | 8 | Design | Sierra Vista | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1485 | 28690 | 2021-06-23 | 000000020200466 | 1485 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 0.5077% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista. | Sierra Vista-8-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-Design | 8 | Design | Sierra Vista | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 990 | 28838 | 2021-09-09 | 000000020255227 | 990 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 0.3385% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista. | Sierra Vista-8-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-Design | 8 | Design | Sierra Vista | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-02 | 2022/23 |  | PO2W-210000000984 | 12375 | 12375 |  |  |  | 0 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista. Remaining balance in this PO | Sierra Vista-8-Fire Alarm replacement
Sierra Vista-Fire Alarm replacement-Design | 8 | Design | Sierra Vista | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-03 | 2022/23 | 21-2535 | PO2W-210000000984 | -12375 | -12375 |  |  |  | 0 | 03-121426 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9281103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sierra Vista. Close-out PO | Sierra Vista-8-Fire Alarm replacement
Sparks ES-Fire Alarm replacement-Design | 7 | Design | Sparks ES | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-02 | 2022/23 |  | PO1-200000000846 | 12125 | 12125 |  |  |  | 0 | 03-120623 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9291103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks ES. Facilities paid PO2W-20*4420 in the amount of $36,375.00. The total architect contract for Spark ES FA is $48,500.00. Remaining balance in this PO | Sparks ES-7-Fire Alarm replacement
Sparks ES-Fire Alarm replacement-Design | 7 | Design | Sparks ES | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-03 | 2022/23 | 2-6867 | PO1-200000000846 | -12125 | -12125 |  |  |  | 0 | 03-120623 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9291103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks ES. Facilities paid PO2W-20*4420 in the amount of $36,375.00. The total architect contract for Spark ES FA is $48,500.00. Close-out PO. | Sparks ES-7-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Design | 2 | Design | Sparks MS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2020/21 |  | PO2W-210000000680 | 0 | 2475 | 28044 | 2020-10-14 | 000000020134523 | 2475 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301103 | 1.964% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks MS. Facilities paid PO1-20*901 & 19-104054 in the amount of $44,550.00. The original architect contract for Spark MS FA is $49,500.00 | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Design | 2 | Design | Sparks MS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 1485 | 28166 | 2021-02-05 | 000000020162584 | 1485 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301103 | 1.178% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks MS. Facilities paid PO1-20*901 & 19-104054 in the amount of $44,550.00. The original architect contract for Spark MS FA is $49,500.00 | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Design | 2 | Design | Sparks MS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 | 21-1992 | PO2W-210000000680 | 0 | 990 | 28462 | 2021-03-24 | 000000020174735 | 990 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9301103 | 0.7856% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sparks MS. Facilities paid PO1-20*901 & 19-104054 in the amount of $44,550.00. The original architect contract for Spark MS FA is $49,500.00 | Sparks MS-2-Fire Alarm replacement
Stimson-Fire Alarm replacement-Design | 4 | Design | Stimson | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2020-05-26 | 2019/20 |  | PO1-200000000846 | 0 | 9875 | 27770 | 2020-05-26 | 000000020099863 | 9875 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 33.33% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson. | Stimson-4-Fire Alarm replacement
Stimson-Fire Alarm replacement-Design | 4 | Design | Stimson | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2020-06-19 | 2019/20 |  | PO1-200000000846 | 0 | 9875 | 27839 | 2020-06-19 | 000000020106941 | 9875 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 33.33% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson. | Stimson-4-Fire Alarm replacement
Stimson-Fire Alarm replacement-Design | 4 | Design | Stimson | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2020-10-14 | 2020/21 |  | PO1-200000000846 | 0 | 7900 | 27976 | 2020-10-14 | 000000020134523 | 7900 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 26.67% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson. | Stimson-4-Fire Alarm replacement
Stimson-Fire Alarm replacement-Design | 4 | Design | Stimson | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2021-05-26 | 2020/21 |  | PO1-200000000846 | 0 | 1975 | 28601 | 2021-05-26 | 000000020192536 | 1975 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 6.667% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson. | Stimson-4-Fire Alarm replacement
Stimson-Fire Alarm replacement-Design | 4 | Design | Stimson | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-02 | 2022/23 |  | PO1-200000000846 | 9875 | 9875 |  |  |  | 0 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson. Remaining balance in this PO | Stimson-4-Fire Alarm replacement
Stimson-Fire Alarm replacement-Design | 4 | Design | Stimson | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-03 | 2022/23 | 2-6868 | PO1-200000000846 | -9875 | -9875 |  |  |  | 0 | 03-120829 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 8021103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Stimson. Close-out PO. | Stimson-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28233 | 2021-02-05 | 000000020162584 | 2425 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28294 | 2021-02-09 | 000000020163360 | 9700 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 3.316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 4850 | 28391 | 2021-03-24 | 000000020174735 | 4850 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 1.658% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28475 | 2021-03-24 | 000000020174735 | 2425 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 4850 | 28524 | 2021-05-26 | 000000020192536 | 4850 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 1.658% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28618 | 2021-05-26 | 000000020192536 | 9700 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 3.316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28691 | 2021-06-23 | 000000020200466 | 1455 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0.4974% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28839 | 2021-09-09 | 000000020255227 | 970 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0.3316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-02 | 2022/23 |  | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. Remaining balance in this PO | Sunset-4-Fire Alarm replacement
Sunset-Fire Alarm replacement-Design | 4 | Design | Sunset | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-03 | 2022/23 | 21-2535 | PO2W-210000000984 | -12125 | -12125 |  |  |  | 0 | 03-121425 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9311103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Sunset. Close-out PO | Sunset-4-Fire Alarm replacement
Valinda-Fire Alarm replacement-Design | 6 | Design | Valinda | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-02 | 2022/23 |  | PO1-200000000846 | 12375 | 12375 |  |  |  | 0 | 03-120622 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9341103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valinda. Facilities paid PO2W-20*4421 in the amount of $37,125.00. The total architect contract for Valinda FA is $49,500.00. Remaining balance in this PO | Valinda-6-Fire Alarm replacement
Valinda-Fire Alarm replacement-Design | 6 | Design | Valinda | Fire Alarm replacement | tBP Architecture | Architect | 2020-01-14 | 2023-03-03 | 2022/23 | 2-6869 | PO1-200000000846 | -12375 | -12375 |  |  |  | 0 | 03-120622 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9341103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valinda. Facilities paid PO2W-20*4421 in the amount of $37,125.00. The total architect contract for Valinda FA is $49,500.00. Close-out PO. | Valinda-6-Fire Alarm replacement
Valley-Fire Alarm replacement-Design | 8 | Design | Valley | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2020-10-14 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28044 | 2020-10-14 | 000000020134523 | 2275 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 1.805% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The original architect contract for Valley FA is $45,500.00 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Design | 8 | Design | Valley | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28118 | 2021-01-07 | 000000020154828 | 2275 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 1.805% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The original architect contract for Valley FA is $45,500.00 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Design | 8 | Design | Valley | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28162 | 2021-02-05 | 000000020162584 | 2275 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 1.805% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The original architect contract for Valley FA is $45,500.00 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Design | 8 | Design | Valley | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-09 | 2020/21 |  | PO2W-210000000680 | 0 | 3640 | 28274 | 2021-02-09 | 000000020163360 | 3640 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 2.888% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The original architect contract for Valley FA is $45,500.00 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Design | 8 | Design | Valley | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-10-28 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 910 | 28874 | 2021-10-28 | 000000020313182 | 910 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9441103 | 0.7221% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Valley. Facilities paid PO1-20*909 & 19-109879 in the amount of $34,125.00. The original architect contract for Valley FA is $45,500.00 | Valley-8-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Design | 5 | Design | Wilson HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28122 | 2021-01-07 | 000000020154828 | 2275 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 1.805% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The original architect contract for Wilson HS FA is $45,500.00 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Design | 5 | Design | Wilson HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-02-05 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28164 | 2021-02-05 | 000000020162584 | 2275 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 1.805% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The original architect contract for Wilson HS FA is $45,500.00 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Design | 5 | Design | Wilson HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2275 | 28468 | 2021-03-24 | 000000020174735 | 2275 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 1.805% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The original architect contract for Wilson HS FA is $45,500.00 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Design | 5 | Design | Wilson HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2023-03-02 | 2022/23 |  | PO2W-210000000680 | 4550 | 4550 |  |  |  | 0 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The original architect contract for Wilson HS FA is $45,500.00. Remaining balance in this PO | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Design | 5 | Design | Wilson HS | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2023-03-03 | 2022/23 | 21-1992 | PO2W-210000000680 | -4550 | -4550 |  |  |  | 0 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9421103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wilson HS. Facilities paid PO1-20*908 & 19-104058 in the amount of $34,125.00. The original architect contract for Wilson HS FA is $45,500.00. Close-out PO | Wilson HS-5-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-05 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28234 | 2021-02-05 | 000000020162584 | 7275 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-02-09 | 2020/21 |  | PO2W-210000000984 | 0 | 7275 | 28295 | 2021-02-09 | 000000020163360 | 7275 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 2.487% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28392 | 2021-03-24 | 000000020174735 | 2425 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-03-24 | 2020/21 |  | PO2W-210000000984 | 0 | 2425 | 28476 | 2021-03-24 | 000000020174735 | 2425 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0.8291% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 4850 | 28525 | 2021-05-26 | 000000020192536 | 4850 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 1.658% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-05-26 | 2020/21 |  | PO2W-210000000984 | 0 | 9700 | 28619 | 2021-05-26 | 000000020192536 | 9700 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 3.316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-06-23 | 2020/21 |  | PO2W-210000000984 | 0 | 1455 | 28692 | 2021-06-23 | 000000020200466 | 1455 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0.4974% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2021-09-09 | 2021/22 |  | PO2W-210000000984 | 0 | 970 | 28840 | 2021-09-09 | 000000020255227 | 970 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0.3316% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-02 | 2022/23 |  | PO2W-210000000984 | 12125 | 12125 |  |  |  | 0 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. Remaining balance in this PO | Wing Lane-9-Fire Alarm replacement
Wing Lane-Fire Alarm replacement-Design | 9 | Design | Wing Lane | Fire Alarm replacement | tBP Architecture | Architect | 2020-10-20 | 2023-03-03 | 2022/23 | 21-2535 | PO2W-210000000984 | -12125 | -12125 |  |  |  | 0 | 03-121424 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9371103 | 0% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Wing Lane. Close-out PO | Wing Lane-9-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Design | 2 | Design | Workman ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-01-07 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28123 | 2021-01-07 | 000000020154828 | 2375 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The original architect contract for Workman ES FA is $47,500.00 | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Design | 2 | Design | Workman ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 4750 | 28382 | 2021-03-24 | 000000020174735 | 4750 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 3.769% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The original architect contract for Workman ES FA is $47,500.00 | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Design | 2 | Design | Workman ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-03-24 | 2020/21 |  | PO2W-210000000680 | 0 | 2375 | 28467 | 2021-03-24 | 000000020174735 | 2375 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 1.885% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The original architect contract for Workman ES FA is $47,500.00 | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Design | 2 | Design | Workman ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2021-09-09 | 2020/21 |  | PO2W-210000000680 | 0 | 1425 | 28727 | 2021-09-09 | 000000020255226 | 1425 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 1.131% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The original architect contract for Workman ES FA is $47,500.00 | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Design | 2 | Design | Workman ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-02-23 | 2021/22 |  | PO2W-210000000680 | 0 | 950 | 29185 | 2022-02-23 | 000000020425550 | 950 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The original architect contract for Workman ES FA is $47,500.00 | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Design | 2 | Design | Workman ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-04-04 | 2021/22 |  | PO2W-210000000680 | 0 | -950 | 29185 | 2022-02-23 | 000000020425550 | -950 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | -0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The original architect contract for Workman ES FA is $47,500.00. Warrant was lost in the mail. | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Design | 2 | Design | Workman ES | Fire Alarm replacement | tBP Architecture | Architect | 2018-07-01 | 2022-04-06 | 2021/22 | 21-1992 | PO2W-210000000680 | 0 | 950 | 29185 | 2022-04-06 | 000000020463387 | 950 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6210 | 9381103 | 0.7538% | Architect - Provide architectural & engineering services to upgrade the existing fire detection and alarm systems for Workman ES. Facilities paid PO1-20*904 & 19-109193 in the amount of $35,625.00. The original architect contract for Workman ES FA is $47,500.00. Replaced warrant #2042550 which was lost in the mail. | Workman ES-2-Fire Alarm replacement
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 1792 |  |  |  | 1792 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9051101 | 29.28% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 289.23 |  |  |  | 289.23 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9051101 | 4.726% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 24.9 |  |  |  | 24.9 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9051101 | 0.4068% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 0.86 |  |  |  | 0.86 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9051101 | 0.01405% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 17.91 |  |  |  | 17.91 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9051101 | 0.2926% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 17.91 |  |  |  | 17.91 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9051101 | 0.2926% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -1792 |  |  |  | -1792 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9051101 | -29.28% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -289.23 |  |  |  | -289.23 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9051101 | -4.726% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -24.9 |  |  |  | -24.9 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9051101 | -0.4068% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -0.86 |  |  |  | -0.86 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9051101 | -0.01405% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -17.91 |  |  |  | -17.91 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9051101 | -0.2926% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -17.91 |  |  |  | -17.91 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9051101 | -0.2926% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-01-04 | 2020/21 |  | Payroll register: C1F-C | 0 | 672 |  |  |  | 672 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9051101 | 83.61% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-01-04 | 2020/21 |  | Payroll register: C1F-C | 0 | 108.58 |  |  |  | 108.58 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9051101 | 13.51% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-01-04 | 2020/21 |  | Payroll register: C1F-C | 0 | 9.35 |  |  |  | 9.35 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9051101 | 1.163% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-01-04 | 2020/21 |  | Payroll register: C1F-C | 0 | 0.32 |  |  |  | 0.32 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9051101 | 0.03982% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-01-04 | 2020/21 |  | Payroll register: C1F-C | 0 | 6.72 |  |  |  | 6.72 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9051101 | 0.8361% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-01-04 | 2020/21 |  | Payroll register: C1F-C | 0 | 6.72 |  |  |  | 6.72 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9051101 | 0.8361% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1F-C | 0 | -672 |  |  |  | -672 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9051101 | -83.61% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1F-C | 0 | -108.58 |  |  |  | -108.58 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9051101 | -13.51% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1F-C | 0 | -9.35 |  |  |  | -9.35 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9051101 | -1.163% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1F-C | 0 | -0.32 |  |  |  | -0.32 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9051101 | -0.03982% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1F-C | 0 | -6.72 |  |  |  | -6.72 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9051101 | -0.8361% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1F-C | 0 | -6.72 |  |  |  | -6.72 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9051101 | -0.8361% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 1536 |  |  |  | 1536 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9051101 | 47.51% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 248 |  |  |  | 248 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9051101 | 7.671% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 20.78 |  |  |  | 20.78 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9051101 | 0.6427% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 0.71 |  |  |  | 0.71 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9051101 | 0.02196% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 15.36 |  |  |  | 15.36 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9051101 | 0.4751% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 15.36 |  |  |  | 15.36 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9051101 | 0.4751% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -1536 |  |  |  | -1536 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9051101 | -47.51% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -248 |  |  |  | -248 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9051101 | -7.671% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -20.78 |  |  |  | -20.78 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9051101 | -0.6427% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -0.71 |  |  |  | -0.71 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9051101 | -0.02196% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -15.36 |  |  |  | -15.36 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9051101 | -0.4751% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -15.36 |  |  |  | -15.36 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9051101 | -0.4751% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 256 |  |  |  | 256 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9051101 | 27.88% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 41.31 |  |  |  | 41.31 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9051101 | 4.5% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 3.51 |  |  |  | 3.51 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9051101 | 0.3823% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 0.12 |  |  |  | 0.12 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9051101 | 0.01307% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 2.56 |  |  |  | 2.56 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9051101 | 0.2788% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 2.56 |  |  |  | 2.56 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9051101 | 0.2788% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -256 |  |  |  | -256 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9051101 | -27.88% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -41.31 |  |  |  | -41.31 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9051101 | -4.5% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -3.51 |  |  |  | -3.51 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9051101 | -0.3823% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -0.12 |  |  |  | -0.12 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9051101 | -0.01307% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -2.56 |  |  |  | -2.56 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9051101 | -0.2788% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -2.56 |  |  |  | -2.56 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9051101 | -0.2788% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Cedarlane | Cedarlane-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 3328 |  |  |  | 3328 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | 54.38% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 537.38 |  |  |  | 537.38 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | 8.78% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 45.36 |  |  |  | 45.36 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | 0.7411% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 1.57 |  |  |  | 1.57 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | 0.02565% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 33.28 |  |  |  | 33.28 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | 0.5438% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2020-12-01 | 2020/21 |  | Payroll register: C1E-C | 0 | 31.84 |  |  |  | 31.84 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | 0.5202% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -3328 |  |  |  | -3328 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | -54.38% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -537.38 |  |  |  | -537.38 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | -8.78% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -45.36 |  |  |  | -45.36 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | -0.7411% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -1.57 |  |  |  | -1.57 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | -0.02565% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -33.28 |  |  |  | -33.28 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | -0.5438% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1E-C | 0 | -31.84 |  |  |  | -31.84 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | -0.5202% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 1168 |  |  |  | 1168 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | 36.13% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 188.62 |  |  |  | 188.62 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | 5.834% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 16.34 |  |  |  | 16.34 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | 0.5054% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 0.56 |  |  |  | 0.56 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | 0.01732% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 11.67 |  |  |  | 11.67 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | 0.361% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-03-01 | 2020/21 |  | Payroll register: C1H-C | 0 | 11.67 |  |  |  | 11.67 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | 0.361% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -1168 |  |  |  | -1168 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | -36.13% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -188.62 |  |  |  | -188.62 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | -5.834% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -16.34 |  |  |  | -16.34 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | -0.5054% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -0.56 |  |  |  | -0.56 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | -0.01732% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -11.67 |  |  |  | -11.67 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | -0.361% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1H-C | 0 | -11.67 |  |  |  | -11.67 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | -0.361% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 512 |  |  |  | 512 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | 55.77% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 82.72 |  |  |  | 82.72 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | 9.01% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 6.83 |  |  |  | 6.83 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | 0.7439% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 0.24 |  |  |  | 0.24 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | 0.02614% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 5.12 |  |  |  | 5.12 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | 0.5577% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-04-01 | 2020/21 |  | Payroll register: C1I-C | 0 | 5.12 |  |  |  | 5.12 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | 0.5577% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -512 |  |  |  | -512 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | -55.77% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -82.72 |  |  |  | -82.72 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | -9.01% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -6.83 |  |  |  | -6.83 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | -0.7439% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -0.24 |  |  |  | -0.24 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | -0.02614% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -5.12 |  |  |  | -5.12 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | -0.5577% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1I-C | 0 | -5.12 |  |  |  | -5.12 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | -0.5577% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-05-03 | 2020/21 |  | Payroll register: C1J-C | 0 | 1856 |  |  |  | 1856 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | 83.62% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-05-03 | 2020/21 |  | Payroll register: C1J-C | 0 | 299.65 |  |  |  | 299.65 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | 13.5% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-05-03 | 2020/21 |  | Payroll register: C1J-C | 0 | 25.87 |  |  |  | 25.87 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | 1.166% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-05-03 | 2020/21 |  | Payroll register: C1J-C | 0 | 0.88 |  |  |  | 0.88 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | 0.03965% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-05-03 | 2020/21 |  | Payroll register: C1J-C | 0 | 18.55 |  |  |  | 18.55 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | 0.8358% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-05-03 | 2020/21 |  | Payroll register: C1J-C | 0 | 18.55 |  |  |  | 18.55 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | 0.8358% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1J-C | 0 | -1856 |  |  |  | -1856 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | -83.62% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1J-C | 0 | -299.65 |  |  |  | -299.65 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | -13.5% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1J-C | 0 | -25.87 |  |  |  | -25.87 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | -1.166% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1J-C | 0 | -0.88 |  |  |  | -0.88 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | -0.03965% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1J-C | 0 | -18.55 |  |  |  | -18.55 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | -0.8358% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1J-C | 0 | -18.55 |  |  |  | -18.55 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | -0.8358% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-06-01 | 2020/21 |  | Payroll register: C1K-C | 0 | 256 |  |  |  | 256 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | 83.64% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-06-01 | 2020/21 |  | Payroll register: C1K-C | 0 | 41.3 |  |  |  | 41.3 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | 13.49% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-06-01 | 2020/21 |  | Payroll register: C1K-C | 0 | 3.54 |  |  |  | 3.54 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | 1.157% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-06-01 | 2020/21 |  | Payroll register: C1K-C | 0 | 0.12 |  |  |  | 0.12 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | 0.03921% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-06-01 | 2020/21 |  | Payroll register: C1K-C | 0 | 2.56 |  |  |  | 2.56 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | 0.8364% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-06-01 | 2020/21 |  | Payroll register: C1K-C | 0 | 2.56 |  |  |  | 2.56 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | 0.8364% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1K-C | 0 | -256 |  |  |  | -256 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | -83.64% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1K-C | 0 | -41.3 |  |  |  | -41.3 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | -13.49% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1K-C | 0 | -3.54 |  |  |  | -3.54 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | -1.157% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1K-C | 0 | -0.12 |  |  |  | -0.12 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | -0.03921% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1K-C | 0 | -2.56 |  |  |  | -2.56 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | -0.8364% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: C1K-C | 0 | -2.56 |  |  |  | -2.56 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | -0.8364% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-07-02 | 2020/21 |  | Payroll register: V2B-C | 0 | 768 |  |  |  | 768 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | 83.26% | Teachers' salary. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-07-02 | 2020/21 |  | Payroll register: V2B-C | 0 | 124.03 |  |  |  | 124.03 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | 13.45% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-07-02 | 2020/21 |  | Payroll register: V2B-C | 0 | 11.13 |  |  |  | 11.13 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | 1.207% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-07-02 | 2020/21 |  | Payroll register: V2B-C | 0 | 3.84 |  |  |  | 3.84 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | 0.4163% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-07-02 | 2020/21 |  | Payroll register: V2B-C | 0 | 7.68 |  |  |  | 7.68 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | 0.8326% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2021-07-02 | 2020/21 |  | Payroll register: V2B-C | 0 | 7.68 |  |  |  | 7.68 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | 0.8326% | Teachers' benefit. These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: V2B-C | 0 | -768 |  |  |  | -768 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 2900 | 9221101 | -83.26% | Moved teachers' salary to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: V2B-C | 0 | -124.03 |  |  |  | -124.03 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3112 | 9221101 | -13.45% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: V2B-C | 0 | -11.13 |  |  |  | -11.13 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3332 | 9221101 | -1.207% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: V2B-C | 0 | -3.84 |  |  |  | -3.84 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3512 | 9221101 | -0.4163% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: V2B-C | 0 | -7.68 |  |  |  | -7.68 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3612 | 9221101 | -0.8326% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Teachers | Pack classrooms | 2020-10-16 | 2022-01-19 | 2021/22 |  | Payroll register: V2B-C | 0 | -7.68 |  |  |  | -7.68 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 3712 | 9221101 | -0.8326% | Moved teachers' benefit to fund 01.0 (JVER 22*293). These are teachers who packed their classrooms for the 21 st Century project at Mesa Robles | Mesa Robles-1-21st Century classroom
Amar-Drinking Fountain replacement-DSA Inspection | 0 | DSA Inspection | Amar | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-02 | 2022/23 |  | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9011104 | 0% | General inspection for the project as defined in Title 24 at Amar. Replacement of 2-exterior drinking fountains. Remaining balance in this PO | Amar-0-Drinking Fountain replacement
Amar-Drinking Fountain replacement-DSA Inspection | 0 | DSA Inspection | Amar | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-03 | 2022/23 | 2-6599 | PO2W-200000003303 | -1200 | -1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9011104 | 0% | General inspection for the project as defined in Title 24 at Amar. Replacement of 2-exterior drinking fountains. Close-out PO | Amar-0-Drinking Fountain replacement
California-Fire Alarm replacement-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm replacement | Team Inspections | General inspection | 2020-10-22 | 2021-02-05 | 2020/21 |  | PO2W-210000000977 | 0 | 3060 | 202011-08:CFA | 2021-02-05 | 000000020162579 | 3060 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 24.98% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system. | California-3-Fire Alarm replacement
California-Fire Alarm replacement-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm replacement | Team Inspections | General inspection | 2020-10-22 | 2021-02-09 | 2020/21 |  | PO2W-210000000977 | 0 | 3060 | 202012-13:CFA | 2021-02-09 | 000000020163358 | 3060 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 24.98% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system. | California-3-Fire Alarm replacement
California-Fire Alarm replacement-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm replacement | Team Inspections | General inspection | 2020-10-22 | 2021-02-09 | 2020/21 |  | PO2W-210000000977 | 0 | 3060 | 202101-14:CFA | 2021-02-09 | 000000020163358 | 3060 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 24.98% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system. | California-3-Fire Alarm replacement
California-Fire Alarm replacement-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm replacement | Team Inspections | General inspection | 2020-10-22 | 2021-09-15 | 2020/21 |  | PO2W-210000000977 | 0 | 2570 | 20210630-12:CFA | 2021-09-15 | 000000020259610 | 2570 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 20.98% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system. | California-3-Fire Alarm replacement
California-Fire Alarm replacement-DSA Inspection | 3 | DSA Inspection | California | Fire Alarm replacement | Team Inspections | General inspection | 2020-10-22 | 2022-05-20 | 2021/22 | 21-2655 | PO2W-210000000977 | 0 | 500 | 202205-08:CFA | 2022-05-20 | 000000020498819 | 500 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9041103 | 4.082% | General inspection for the project as defined in Title 24 at California. Alterations to fire alarm system. | California-3-Fire Alarm replacement
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202102-04:CMSM | 2021-03-24 | 000000020174730 | 2880 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.039% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 5760 | 202103-06:CMSM | 2021-03-24 | 000000020174730 | 5760 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 4.077% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 5184 | 202012-10:CMSM | 2021-04-19 | 000000020181403 | 5184 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 3.67% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 3168 | 202101-07:CMSM | 2021-04-19 | 000000020181403 | 3168 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.243% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-04-20 | 2020/21 |  | PO2W-210000001035 | 0 | 6624 | 202104-05:CMSM | 2021-04-20 | 000000020181749 | 6624 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 4.689% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-06-09 | 2020/21 |  | PO2W-210000001035 | 0 | 6336 | 202105-04:CMSM | 2021-06-09 | 000000020196442 | 6336 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 4.485% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-06-23 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202106-04:CMSM | 2021-06-23 | 000000020200462 | 2880 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.039% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-09-09 | 2020/21 |  | PO2W-210000001035 | 0 | 3168 | 202107-04:CMSM | 2021-09-09 | 000000020255215 | 3168 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.243% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-09-22 | 2021/22 |  | PO2W-210000001035 | 0 | 11520 | 202108-03:CMSM | 2021-09-22 | 000000020269793 | 11520 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 8.155% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-10-22 | 2021/22 |  | PO2W-210000001035 | 0 | 6480 | 202110-03:CMSM | 2021-10-22 | 000000020305831 | 6480 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 4.587% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-12-01 | 2021/22 |  | PO2W-210000001035 | 0 | 5760 | 202111-03:CMSM | 2021-12-01 | 000000020346455 | 5760 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 4.077% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-12-20 | 2021/22 |  | PO2W-210000001035 | 0 | 6048 | 202112-03:CMSM | 2021-12-20 | 000000020370771 | 6048 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 4.281% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2022-01-12 | 2021/22 |  | PO2W-210000001035 | 0 | 3024 | 202108-09:CMSM | 2022-01-12 | 000000020382224 | 3024 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 2.141% | General inspection for the project as defined in Title 24 at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2022-07-01 | 2022/23 |  | PO2W-210000001035 | 24768 | 24768 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 0% | General inspection for the project as defined in Title 24 at Cedarlane. Remaining balance in this PO. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Cedarlane | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2023-06-30 | 2022/23 | 21-2812 | PO2W-210000001035 | -24768 | -24768 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051101 | 0% | General inspection for the project as defined in Title 24 at Cedarlane. Close-out PO. | Cedarlane-1-21st Century classroom
Cedarlane-Drinking Fountain replacement-DSA Inspection | 1 | DSA Inspection | Cedarlane | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2022-05-20 | 2021/22 | 2-6600 | PO2W-200000003303 | 0 | 1200 | 202205-12:WFA | 2022-05-20 | 000000020498819 | 1200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051104 | 50% | General inspection for the project as defined in Title 24 at Cedarlane. Replacement of 3-exterior drinking fountains | Cedarlane-1-Drinking Fountain replacement
Cedarlane-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Cedarlane | Fire Alarm replacement | Team Inspections | General inspection | 2020-02-07 | 2020-05-26 | 2019/20 |  | PO2W-200000004017 | 0 | 6185 | 202005-01:CFA | 2020-05-26 | 000000020099846 | 6185 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051103 | 74.97% | General inspection for the project as defined in Title 24 at Cedarlane. Alterations to 11 buildings' fire alarm: CR bldg A, B, C, D (Library), E, F, G, H, K (Locker bldg), M (Admin), P (MPR). | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Cedarlane | Fire Alarm replacement | Team Inspections | General inspection | 2020-02-07 | 2020-10-14 | 2020/21 | 2-7749 | PO2W-200000004017 | 0 | 2065 | 202009-08:CFA | 2020-10-14 | 000000020134520 | 2065 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051103 | 25.03% | General inspection for the project as defined in Title 24 at Cedarlane. Alterations to 11 buildings' fire alarm: CR bldg A, B, C, D (Library), E, F, G, H, K (Locker bldg), M (Admin), P (MPR). | Cedarlane-1-Fire Alarm replacement
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202102-03:CMSIH | 2021-03-24 | 000000020174730 | 2880 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 2.039% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202103-05:CMSIH | 2021-03-24 | 000000020174730 | 2880 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 2.039% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 2736 | 202012-09:CMSIH | 2021-04-19 | 000000020181403 | 2736 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 1.937% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 3168 | 202101-06:CMSIH | 2021-04-19 | 000000020181403 | 3168 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 2.243% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing. | Cedarlane-1-Interim Housing
Cedarlane-Interim Housing-DSA Inspection | 1 | DSA Inspection | Cedarlane | Interim Housing | Team Inspections | General inspection | 2020-10-29 | 2021-04-20 | 2020/21 | 21-2812 | PO2W-210000001035 | 0 | 3024 | 202104-04:CMSIH | 2021-04-20 | 000000020181749 | 3024 | 03-120587 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9051102 | 2.141% | General inspection for the project as defined in Title 24 for Cedarlane Interim Housing. | Cedarlane-1-Interim Housing
Fairgrove-Drinking Fountain replacement-DSA Inspection | 4 | DSA Inspection | Fairgrove | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-02 | 2022/23 |  | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9091104 | 0% | General inspection for the project as defined in Title 24 at Fairgrove. Replacement of 3-exterior drinking fountains. Remaining balance in this PO | Fairgrove-4-Drinking Fountain replacement
Fairgrove-Drinking Fountain replacement-DSA Inspection | 4 | DSA Inspection | Fairgrove | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-03 | 2022/23 | 2-6601 | PO2W-200000003303 | -1200 | -1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9091104 | 0% | General inspection for the project as defined in Title 24 at Fairgrove. Replacement of 3-exterior drinking fountains. Close-out PO | Fairgrove-4-Drinking Fountain replacement
Fairgrove-Fire Alarm replacement-DSA Inspection | 4 | DSA Inspection | Fairgrove | Fire Alarm replacement | Team Inspections | General inspection | 2021-01-14 | 2021-10-19 | 2021/22 | 21-3784 | PO2W-210000001585 | 0 | 14350 | 202110-04:FFA | 2021-10-19 | 000000020302605 | 14350 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9091103 | 50% | General inspection for the project as defined in Title 24 at Fairgrove. Alterations to fire alarm system | Fairgrove-4-Fire Alarm replacement
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-01-11 | 2022/23 |  | PO2W-230000001740 | 0 | 4505 | 202212-03:GA | 2023-01-11 | 000000020798746 | 4505 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 2.196% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-01-25 | 2022/23 |  | PO2W-230000001740 | 0 | 4080 | 202301-03:GA | 2023-01-25 | 000000020822011 | 4080 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 1.988% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-03-07 | 2022/23 |  | PO2W-230000001740 | 0 | 3570 | 202302-03:GA | 2023-03-07 | 000000020889993 | 3570 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 1.74% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-03-30 | 2022/23 |  | PO2W-230000001740 | 0 | 3230 | 202303-03:GA | 2023-03-30 | 000000020934441 | 3230 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 1.574% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-05-18 | 2022/23 |  | PO2W-230000001740 | 0 | 3910 | 202304-03:GA | 2023-05-18 | 000000021019993 | 3910 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 1.906% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-05-18 | 2022/23 |  | PO2W-230000001740 | 0 | 3400 | 202305-02:GA | 2023-05-18 | 000000021019993 | 3400 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 1.657% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-07-18 | 2022/23 |  | PO2W-230000001740 | 0 | 3740 | 202306-02:GA | 2023-07-18 | 000000021130769 | 3740 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 1.823% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-07-19 | 2022/23 |  | PO2W-230000001740 | 0 | 3740 | 202307-02:GA | 2023-07-19 | 000000021132858 | 3740 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 1.823% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-10-02 | 2023/24 |  | PO2W-230000001740 | 0 | 5100 | 202308-02:GA | 2023-10-02 | 000000021240115 | 5100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 2.486% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-12-08 | 2023/24 |  | PO2W-230000001740 | 0 | 7055 | 202309-02:GA | 2023-12-08 | 000000021359563 | 7055 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 3.438% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-12-08 | 2023/24 |  | PO2W-230000001740 | 0 | 5100 | 202310-02:GA | 2023-12-08 | 000000021359563 | 5100 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 2.486% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2024-01-24 | 2023/24 |  | PO2W-230000001740 | 0 | 5610 | 202311-02:GA | 2024-01-24 | 000000021424537 | 5610 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 2.734% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2024-01-24 | 2023/24 |  | PO2W-230000001740 | 0 | 2125 | 202312-02:GA | 2024-01-24 | 000000021424537 | 2125 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 1.036% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2024-01-24 | 2023/24 |  | PO2W-230000001740 | 0 | 1530 | 202401-02:GA | 2024-01-24 | 000000021424537 | 1530 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 0.7457% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Grandview | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2027-06-01 | 2023/24 | 23-4218 | PO2W-230000001740 | 595 | 595 |  |  |  | 0 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121101 | 0% | General inspection for the project as defined in Title 24 at Grandview. Alterations to CR-C1 through CR-C7, CR-K, MPR, & site work. | Grandview-2-21st Century classroom
Grandview-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2020-05-26 | 2019/20 |  | PO2W-200000002809 | 0 | 2345 | 202005-03:GFA | 2020-05-26 | 000000020099846 | 2345 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 25.01% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2020-06-19 | 2019/20 |  | PO2W-200000002809 | 0 | 2345 | 202006-02:GFA | 2020-06-19 | 000000020106934 | 2345 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 25.01% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2020-10-14 | 2020/21 |  | PO2W-200000002809 | 0 | 2345 | 202009-09:GFA | 2020-10-14 | 000000020134520 | 2345 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 25.01% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2021-09-13 | 2020/21 |  | PO2W-200000002809 | 0 | 1840 | 20210630-06: GFA | 2021-09-13 | 000000020257046 | 1840 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 19.63% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Grandview | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2022-05-20 | 2021/22 | 2-5882 | PO2W-200000002809 | 0 | 500 | 202205-09:GFA | 2022-05-20 | 000000020498819 | 500 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9121103 | 5.333% | General inspection for the project as defined in Title 24 at Grandview. Alterations to 1 campus wide fire alarm system | Grandview-2-Fire Alarm replacement
Kwis-Drinking Fountain replacement-DSA Inspection | 7 | DSA Inspection | Kwis | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-02 | 2022/23 |  | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9161104 | 0% | General inspection for the project as defined in Title 24 at Kwis. Replacement of 3-exterior drinking fountains. Remaining balance in this PO | Kwis-7-Drinking Fountain replacement
Kwis-Drinking Fountain replacement-DSA Inspection | 7 | DSA Inspection | Kwis | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-03 | 2022/23 | 2-6602 | PO2W-200000003303 | -1200 | -1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9161104 | 0% | General inspection for the project as defined in Title 24 at Kwis. Replacement of 3-exterior drinking fountains. Close-out PO | Kwis-7-Drinking Fountain replacement
La Puente HS-Drinking Fountain replacement-DSA Inspection | 5 | DSA Inspection | La Puente HS | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-02 | 2022/23 |  | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9401104 | 0% | General inspection for the project as defined in Title 24 at La Puente HS. Replacement of 3-exterior drinking fountains. Remaining balance in this PO | La Puente HS-5-Drinking Fountain replacement
La Puente HS-Drinking Fountain replacement-DSA Inspection | 5 | DSA Inspection | La Puente HS | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-03 | 2022/23 | 2-6603 | PO2W-200000003303 | -1200 | -1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9401104 | 0% | General inspection for the project as defined in Title 24 at La Puente HS. Replacement of 3-exterior drinking fountains. Close-out PO | La Puente HS-5-Drinking Fountain replacement
Lassalette-Drinking Fountain replacement-DSA Inspection | 6 | DSA Inspection | Lassalette | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-02 | 2022/23 |  | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9171104 | 0% | General inspection for the project as defined in Title 24 at Lassalette. Replacement of 2-exterior drinking fountains. Remaining balance in this PO | Lassalette-6-Drinking Fountain replacement
Lassalette-Drinking Fountain replacement-DSA Inspection | 6 | DSA Inspection | Lassalette | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-03 | 2022/23 | 2-6604 | PO2W-200000003303 | -1200 | -1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9171104 | 0% | General inspection for the project as defined in Title 24 at Lassalette. Replacement of 2-exterior drinking fountains. Close-out PO | Lassalette-6-Drinking Fountain replacement
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 2019/20 |  | PO2W-200000004960 | 0 | 4410 | 20200630-07:NEM | 2020-06-19 | 000000020106934 | 4410 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 12.7% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-08-19 | 2020/21 |  | PO2W-200000004960 | 0 | 6440 | 202008-04:LAM | 2020-08-19 | 000000020120364 | 6440 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 18.55% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-10-14 | 2020/21 |  | PO2W-200000004960 | 0 | 5880 | 202009-04:LAM | 2020-10-14 | 000000020134520 | 5880 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 16.94% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-10-21 | 2020/21 |  | PO2W-200000004960 | 0 | 5880 | 202010-04:LAM | 2020-10-21 | 000000020136459 | 5880 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 16.94% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-02-05 | 2020/21 |  | PO2W-200000004960 | 0 | 3080 | 202011-04:LAM | 2021-02-05 | 000000020162579 | 3080 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 8.871% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-03-24 | 2020/21 |  | PO2W-200000004960 | 0 | 1610 | 202102-02:LAM | 2021-03-24 | 000000020174730 | 1610 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 4.637% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-03-24 | 2020/21 |  | PO2W-200000004960 | 0 | 420 | 202103-03:LAM | 2021-03-24 | 000000020174730 | 420 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 1.21% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004960 | 0 | 2520 | 202012-04:LAM | 2021-04-19 | 000000020181403 | 2520 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 7.258% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Los Altos ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 | 2-9867 | PO2W-200000004960 | 0 | 4480 | 202101-04:LAM | 2021-04-19 | 000000020181403 | 4480 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191101 | 12.9% | General inspection for the project as defined in Title 24 at Los Altos ES. | Los Altos ES-2-21st Century classroom
Los Altos ES-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Fire Alarm replacement | Team Inspections | General inspection | 2020-12-15 | 2021-02-09 | 2020/21 |  | PO2W-210000001492 | 0 | 3060 | 202101-12:LAFA | 2021-02-09 | 000000020163358 | 3060 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191103 | 12.49% | General inspection for the project as defined in Title 24 at Los Altos ES. Alterations to fire alarm system | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Fire Alarm replacement | Team Inspections | General inspection | 2020-12-15 | 2021-04-19 | 2020/21 |  | PO2W-210000001492 | 0 | 6120 | 202102-10:LAFA | 2021-04-19 | 000000020181403 | 6120 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191103 | 24.98% | General inspection for the project as defined in Title 24 at Los Altos ES. Alterations to fire alarm system | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Fire Alarm replacement | Team Inspections | General inspection | 2020-12-15 | 2021-09-09 | 2021/22 | 21-3568 | PO2W-210000001492 | 0 | 500 | 202108-06:LAFA | 2021-09-09 | 000000020255216 | 500 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191103 | 2.041% | General inspection for the project as defined in Title 24 at Los Altos ES. Alterations to fire alarm system | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Fire Alarm replacement | Team Inspections | General inspection | 2020-12-15 | 2021-09-13 | 2020/21 |  | PO2W-210000001492 | 0 | 2570 | 20210630-09: LAFA | 2021-09-13 | 000000020257046 | 2570 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191103 | 10.49% | General inspection for the project as defined in Title 24 at Los Altos ES. Alterations to fire alarm system | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Interim Housing-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Interim Housing | Team Inspections | General inspection | 2019-07-01 | 2019-12-11 | 2019/20 |  | PO2W-200000000103 | 0 | 9900 | 201911-01:LAR | 2019-12-11 | 000000020047668 | 9900 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191102 | 75% | General inspection for the project as defined in Title 24 at Los Altos ES. Relocation of 4 modular classrooms | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-DSA Inspection | 2 | DSA Inspection | Los Altos ES | Interim Housing | Team Inspections | General inspection | 2019-07-01 | 2020-01-15 | 2019/20 | 2-737 | PO2W-200000000103 | 0 | 3300 | 201912-05:LAR | 2020-01-15 | 000000020057959 | 3300 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9191102 | 25% | General inspection for the project as defined in Title 24 at Los Altos ES. Relocation of 4 modular classrooms | Los Altos ES-2-Interim Housing
Los Molinos-Fire Alarm replacement-DSA Inspection | 4 | DSA Inspection | Los Molinos | Fire Alarm replacement | Team Inspections | General inspection | 2021-01-14 | 2021-10-19 | 2021/22 | 21-3784 | PO2W-210000001585 | 0 | 14350 | 202110-05:LMFA | 2021-10-19 | 000000020302605 | 14350 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9201103 | 50% | General inspection for the project as defined in Title 24 at Los Molinos. Alterations to fire alarm system | Los Molinos-4-Fire Alarm replacement
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 5760 | 202102-05:MRMSM | 2021-03-24 | 000000020174730 | 5760 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 4.077% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-03-24 | 2020/21 |  | PO2W-210000001035 | 0 | 2880 | 202103-07:MRMSM | 2021-03-24 | 000000020174730 | 2880 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 2.039% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 5328 | 202012-11:MRMSM | 2021-04-19 | 000000020181403 | 5328 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 3.772% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-04-19 | 2020/21 |  | PO2W-210000001035 | 0 | 6336 | 202101-08:MRMSM | 2021-04-19 | 000000020181403 | 6336 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 4.485% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-04-20 | 2020/21 |  | PO2W-210000001035 | 0 | 3600 | 202104-06:MRMSM | 2021-04-20 | 000000020181749 | 3600 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 2.548% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-05-26 | 2020/21 |  | PO2W-210000001035 | 0 | 6336 | 202105-05:MRMSM | 2021-05-26 | 000000020192532 | 6336 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 4.485% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-06-23 | 2020/21 |  | PO2W-210000001035 | 0 | 8640 | 202106-03:MRMSM | 2021-06-23 | 000000020200462 | 8640 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 6.116% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-09-09 | 2020/21 |  | PO2W-210000001035 | 0 | 9504 | 202107-03:MRMSM | 2021-09-09 | 000000020255215 | 9504 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 6.728% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-09-09 | 2021/22 |  | PO2W-210000001035 | 0 | 9072 | 202108-04:MRMSM | 2021-09-09 | 000000020255216 | 9072 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 6.422% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2021-09-22 | 2021/22 |  | PO2W-210000001035 | 0 | 288 | 202109-04:MRMSM | 2021-09-22 | 000000020269793 | 288 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 0.2039% | General inspection for the project as defined in Title 24 at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2022-07-01 | 2022/23 |  | PO2W-210000001035 | 35856 | 35856 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 0% | General inspection for the project as defined in Title 24 at Mesa Robles. Remaining balance in this PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Mesa Robles | 21st Century classroom | Team Inspections | General inspection | 2020-10-29 | 2023-06-30 | 2022/23 | 21-2812 | PO2W-210000001035 | -35856 | -35856 |  |  |  | 0 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221101 | 0% | General inspection for the project as defined in Title 24 at Mesa Robles. Close-out PO. | Mesa Robles-1-21st Century classroom
Mesa Robles-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Fire Alarm replacement | Team Inspections | General inspection | 2020-05-13 | 2020-08-19 | 2020/21 |  | PO2W-200000005057 | 0 | 2065 | 202008-10:WHSFA | 2020-08-19 | 000000020120364 | 2065 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221103 | 25.03% | General inspection for the project as defined in Title 24 at Mesa Robles. Alterations to 1 campus wide fire alarm system | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Fire Alarm replacement | Team Inspections | General inspection | 2020-05-13 | 2020-10-14 | 2020/21 |  | PO2W-200000005057 | 0 | 2065 | 202009-10:WHSFA | 2020-10-14 | 000000020134520 | 2065 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221103 | 25.03% | General inspection for the project as defined in Title 24 at Mesa Robles. Alterations to 1 campus wide fire alarm system | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Fire Alarm replacement | Team Inspections | General inspection | 2020-05-13 | 2020-10-21 | 2020/21 |  | PO2W-200000005057 | 0 | 2065 | 202010-08:WHSFA | 2020-10-21 | 000000020136459 | 2065 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221103 | 25.03% | General inspection for the project as defined in Title 24 at Mesa Robles. Alterations to 1 campus wide fire alarm system | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Fire Alarm replacement | Team Inspections | General inspection | 2020-05-13 | 2021-09-13 | 2020/21 | 2-10147 | PO2W-200000005057 | 0 | 2055 | 20210630-07: WHSFA | 2021-09-13 | 000000020257046 | 2055 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221103 | 24.91% | General inspection for the project as defined in Title 24 at Mesa Robles. Alterations to 1 campus wide fire alarm system | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Interim Housing-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Interim Housing | Team Inspections | General inspection | 2020-02-13 | 2020-06-19 | 2019/20 |  | PO2W-200000004113 | 0 | 19870 | 202006-06:MRR | 2020-06-19 | 000000020106934 | 19870 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221102 | 50% | General inspection for the project as defined in Title 24 at Mesa Robles. Relocation of 9 classroom buildings. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Interim Housing | Team Inspections | General inspection | 2020-02-13 | 2020-08-19 | 2020/21 |  | PO2W-200000004113 | 0 | 9935 | 202008-09:MRR | 2020-08-19 | 000000020120364 | 9935 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221102 | 25% | General inspection for the project as defined in Title 24 at Mesa Robles. Relocation of 9 classroom buildings. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Interim Housing | Team Inspections | General inspection | 2020-02-13 | 2020-10-14 | 2020/21 |  | PO2W-200000004113 | 0 | 5960 | 202009-12:MRR | 2020-10-14 | 000000020134520 | 5960 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221102 | 15% | General inspection for the project as defined in Title 24 at Mesa Robles. Relocation of 9 classroom buildings. | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-DSA Inspection | 1 | DSA Inspection | Mesa Robles | Interim Housing | Team Inspections | General inspection | 2020-02-13 | 2021-04-20 | 2020/21 | 2-7889 | PO2W-200000004113 | 0 | 3975 | 202104-07:MRR | 2021-04-20 | 000000020181749 | 3975 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9221102 | 10% | General inspection for the project as defined in Title 24 at Mesa Robles. Relocation of 9 classroom buildings. | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 2019/20 |  | PO2W-200000004961 | 0 | 4410 | 20200630-06:NEM | 2020-06-19 | 000000020106934 | 4410 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 13.52% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-08-19 | 2020/21 |  | PO2W-200000004961 | 0 | 3360 | 202008-03:NEM | 2020-08-19 | 000000020120364 | 3360 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 10.3% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-10-14 | 2020/21 |  | PO2W-200000004961 | 0 | 2940 | 202009-03:NEM | 2020-10-14 | 000000020134520 | 2940 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 9.013% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-10-21 | 2020/21 |  | PO2W-200000004961 | 0 | 2940 | 202010-03:NEM | 2020-10-21 | 000000020136459 | 2940 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 9.013% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-02-05 | 2020/21 |  | PO2W-200000004961 | 0 | 6160 | 202011-03:NEM | 2021-02-05 | 000000020162579 | 6160 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 18.88% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-03-24 | 2020/21 |  | PO2W-200000004961 | 0 | 1890 | 202102-01:NEM | 2021-03-24 | 000000020174730 | 1890 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 5.794% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-03-24 | 2020/21 |  | PO2W-200000004961 | 0 | 2380 | 202103-04:NEM | 2021-03-24 | 000000020174730 | 2380 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 7.296% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004961 | 0 | 2520 | 202012-03:NEM | 2021-04-19 | 000000020181403 | 2520 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 7.725% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004961 | 0 | 2800 | 202101-03:NEM | 2021-04-19 | 000000020181403 | 2800 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 8.584% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-04-20 | 2020/21 |  | PO2W-200000004961 | 0 | 3220 | 202104-03:NEM | 2021-04-20 | 000000020181749 | 3220 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 9.871% | General inspection for the project as defined in Title 24 at Nelson. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2022-07-11 | 2022/23 |  | PO2W-200000004961 | 2100 | 2100 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 0% | General inspection for the project as defined in Title 24 at Nelson. Remaining balance in this PO. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Nelson | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2023-06-30 | 2022/23 | 2-9868 | PO2W-200000004961 | -2100 | -2100 |  |  |  | 0 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231101 | 0% | General inspection for the project as defined in Title 24 at Nelson. Close-out PO. | Nelson-1-21st Century classroom
Nelson-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Nelson | Fire Alarm replacement | Team Inspections | General inspection | 2020-12-15 | 2021-02-09 | 2020/21 |  | PO2W-210000001492 | 0 | 9180 | 202101-11:NFA | 2021-02-09 | 000000020163358 | 9180 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231103 | 37.47% | General inspection for the project as defined in Title 24 at Nelson. Alterations to fire alarm system | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Nelson | Fire Alarm replacement | Team Inspections | General inspection | 2020-12-15 | 2021-09-09 | 2021/22 | 21-3568 | PO2W-210000001492 | 0 | 500 | 202108-05:NFA | 2021-09-09 | 000000020255216 | 500 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231103 | 2.041% | General inspection for the project as defined in Title 24 at Nelson. Alterations to fire alarm system | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Nelson | Fire Alarm replacement | Team Inspections | General inspection | 2020-12-15 | 2021-09-13 | 2020/21 |  | PO2W-210000001492 | 0 | 2570 | 20210630-08: NFA | 2021-09-13 | 000000020257046 | 2570 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9231103 | 10.49% | General inspection for the project as defined in Title 24 at Nelson. Alterations to fire alarm system | Nelson-1-Fire Alarm replacement
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-01-11 | 2022/23 |  | PO2W-230000001740 | 0 | 7140 | 202212-04:NA | 2023-01-11 | 000000020798746 | 7140 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.48% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-01-25 | 2022/23 |  | PO2W-230000001740 | 0 | 7140 | 202301-04:NA | 2023-01-25 | 000000020822011 | 7140 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.48% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-03-07 | 2022/23 |  | PO2W-230000001740 | 0 | 7140 | 202302-04:NA | 2023-03-07 | 000000020889993 | 7140 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.48% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-03-30 | 2022/23 |  | PO2W-230000001740 | 0 | 6460 | 202303-04:NA | 2023-03-30 | 000000020934441 | 6460 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.148% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-05-18 | 2022/23 |  | PO2W-230000001740 | 0 | 7820 | 202304-04:NA | 2023-05-18 | 000000021019993 | 7820 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.811% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-05-18 | 2022/23 |  | PO2W-230000001740 | 0 | 6800 | 202305-03:NA | 2023-05-18 | 000000021019993 | 6800 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.314% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-07-18 | 2022/23 |  | PO2W-230000001740 | 0 | 7480 | 202306-03:NA | 2023-07-18 | 000000021130769 | 7480 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.645% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-07-19 | 2022/23 |  | PO2W-230000001740 | 0 | 7480 | 202307-03:NA | 2023-07-19 | 000000021132858 | 7480 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.645% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-10-02 | 2023/24 |  | PO2W-230000001740 | 0 | 6800 | 202308-03:NA | 2023-10-02 | 000000021240115 | 6800 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.314% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-12-08 | 2023/24 |  | PO2W-230000001740 | 0 | 7820 | 202309-03:NA | 2023-12-08 | 000000021359563 | 7820 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.811% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-12-08 | 2023/24 |  | PO2W-230000001740 | 0 | 6800 | 202310-03:NA | 2023-12-08 | 000000021359563 | 6800 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.314% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2024-01-24 | 2023/24 |  | PO2W-230000001740 | 0 | 7480 | 202311-03:NA | 2024-01-24 | 000000021424537 | 7480 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.645% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2024-01-24 | 2023/24 |  | PO2W-230000001740 | 0 | 6460 | 202312-03:NA | 2024-01-24 | 000000021424537 | 6460 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 3.148% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2024-01-24 | 2023/24 |  | PO2W-230000001740 | 0 | 3060 | 202401-03:NA | 2024-01-24 | 000000021424537 | 3060 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 1.491% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-21st Century classroom-DSA Inspection | 1 | DSA Inspection | Newton | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2027-06-01 | 2023/24 | 23-4218 | PO2W-230000001740 | 19890 | 19890 |  |  |  | 0 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241101 | 0% | General inspection for the project as defined in Title 24 at Newton. Alterations to admin, MPR, CR-A through CR-E, CR-G, & site work. | Newton-1-21st Century classroom
Newton-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Newton | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2020-05-26 | 2019/20 |  | PO2W-200000002811 | 0 | 6090 | 202005-05:NFA | 2020-05-26 | 000000020099846 | 6090 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241103 | 74.95% | General inspection for the project as defined in Title 24 at Newton. Alterations to 1 campus wide fire alarm upgrade | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-DSA Inspection | 1 | DSA Inspection | Newton | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2020-06-19 | 2019/20 | 2-5883 | PO2W-200000002811 | 0 | 2035 | 202006-04:NFA | 2020-06-19 | 000000020106934 | 2035 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241103 | 25.05% | General inspection for the project as defined in Title 24 at Newton. Alterations to 1 campus wide fire alarm upgrade | Newton-1-Fire Alarm replacement
Newton-Interim Housing-DSA Inspection | 1 | DSA Inspection | Newton | Interim Housing | Team Inspections | General inspection | 2020-07-01 | 2022-05-20 | 2021/22 |  | PO2W-210000000015 | 0 | 12000 | 202205-04:NR | 2022-05-20 | 000000020498819 | 12000 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241102 | 75% | General inspection for the project as defined in Title 24 at Newton. Alterations to (1) CR Buildings & relocation of (4) 24' x 40' relocatable CR buildings | Newton-1-Interim Housing
Newton-Interim Housing-DSA Inspection | 1 | DSA Inspection | Newton | Interim Housing | Team Inspections | General inspection | 2020-07-01 | 2022-07-08 | 2021/22 | 21-307 | PO2W-210000000015 | 0 | 4000 | 202207-04:NR | 2022-07-08 | 000000020546408 | 4000 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9241102 | 25% | General inspection for the project as defined in Title 24 at Newton. Alterations to (1) CR Buildings & relocation of (4) 24' x 40' relocatable CR buildings | Newton-1-Interim Housing
Sparks ES-Drinking Fountain replacement-DSA Inspection | 7 | DSA Inspection | Sparks ES | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-02 | 2022/23 |  | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9291104 | 0% | General inspection for the project as defined in Title 24 at Sparks ES. Replacement of 2-exterior drinking fountains. Remaining balance in this PO | Sparks ES-7-Drinking Fountain replacement
Sparks ES-Drinking Fountain replacement-DSA Inspection | 7 | DSA Inspection | Sparks ES | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-03 | 2022/23 | 2-6605 | PO2W-200000003303 | -1200 | -1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9291104 | 0% | General inspection for the project as defined in Title 24 at Sparks ES. Replacement of 2-exterior drinking fountains. Close-out PO | Sparks ES-7-Drinking Fountain replacement
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2023-10-16 | 2024-01-24 | 2023/24 |  | PO1-240000000569 | 0 | 1700 | 202310-04:SA | 2024-01-24 | 000000021424537 | 1700 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 16.13% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. Addendum to PO2W-23*1740 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2023-10-16 | 2024-01-24 | 2023/24 |  | PO1-240000000569 | 0 | 1870 | 202311-04:SA | 2024-01-24 | 000000021424537 | 1870 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 17.74% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. Addendum to PO2W-23*1740 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2023-10-16 | 2024-01-24 | 2023/24 |  | PO1-240000000569 | 0 | 1615 | 202312-04:SA | 2024-01-24 | 000000021424537 | 1615 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 15.32% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. Addendum to PO2W-23*1740 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2023-10-16 | 2024-01-25 | 2023/24 |  | PO1-240000000569 | 0 | 1530 | 202401-04:SA | 2024-01-25 | 000000021427418 | 1530 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 14.52% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. Addendum to PO2W-23*1740 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2023-10-16 | 2027-12-09 | 2023/24 | 24-3376 | PO1-240000000569 | 3825 | 3825 |  |  |  | 0 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 0% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. Addendum to PO2W-23*1740 | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-01-11 | 2022/23 |  | PO2W-230000001740 | 0 | 4335 | 202212-05:SA | 2023-01-11 | 000000020798746 | 4335 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 2.113% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-01-25 | 2022/23 |  | PO2W-230000001740 | 0 | 3740 | 202301-05:SA | 2023-01-25 | 000000020822011 | 3740 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 1.823% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-03-07 | 2022/23 |  | PO2W-230000001740 | 0 | 3570 | 202302-05:SA | 2023-03-07 | 000000020889993 | 3570 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 1.74% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-03-30 | 2022/23 |  | PO2W-230000001740 | 0 | 3230 | 202303-05:SA | 2023-03-30 | 000000020934441 | 3230 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 1.574% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-05-18 | 2022/23 |  | PO2W-230000001740 | 0 | 3910 | 202304-05:SA | 2023-05-18 | 000000021019993 | 3910 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 1.906% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-05-18 | 2022/23 |  | PO2W-230000001740 | 0 | 3400 | 202305-04:SA | 2023-05-18 | 000000021019993 | 3400 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 1.657% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-07-18 | 2022/23 |  | PO2W-230000001740 | 0 | 3740 | 202306-04:SA | 2023-07-18 | 000000021130769 | 3740 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 1.823% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-07-19 | 2022/23 |  | PO2W-230000001740 | 0 | 3740 | 202307-04:SA | 2023-07-19 | 000000021132858 | 3740 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 1.823% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-10-02 | 2023/24 |  | PO2W-230000001740 | 0 | 1700 | 202308-04:SA | 2023-10-02 | 000000021240115 | 1700 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 0.8285% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Sparks MS | 21st Century classroom | Team Inspections | General inspection | 2022-12-01 | 2023-12-08 | 2023/24 | 23-4218 | PO2W-230000001740 | 0 | 765 | 202309-04:SA | 2023-12-08 | 000000021359563 | 765 | 03-121296 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301101 | 0.3728% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to admin, MPR, CR-A, CR-C through CR-F, & site work. | Sparks MS-2-21st Century classroom
Sparks MS-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Sparks MS | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2020-02-20 | 2019/20 |  | PO2W-200000002812 | 0 | 1720 | 202002-02:SFA | 2020-02-20 | 000000020071954 | 1720 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301103 | 25.02% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to 1 campus wide fire alarm system | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Sparks MS | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2020-04-17 | 2019/20 |  | PO2W-200000002812 | 0 | 3440 | 202003-02:SFA | 2020-04-17 | 000000020090431 | 3440 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301103 | 50.04% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to 1 campus wide fire alarm system | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Sparks MS | Fire Alarm replacement | Team Inspections | General inspection | 2019-11-26 | 2020-06-19 | 2019/20 | 2-5884 | PO2W-200000002812 | 0 | 1715 | 202006-03:SFA | 2020-06-19 | 000000020106934 | 1715 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9301103 | 24.95% | General inspection for the project as defined in Title 24 at Sparks MS. Alterations to 1 campus wide fire alarm system | Sparks MS-2-Fire Alarm replacement
Valley-Fire Alarm replacement-DSA Inspection | 8 | DSA Inspection | Valley | Fire Alarm replacement | Team Inspections | General inspection | 2020-08-19 | 2020-10-14 | 2020/21 |  | PO2W-210000000455 | 0 | 3675 | 202009-11:VAFA | 2020-10-14 | 000000020134520 | 3675 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9441103 | 50% | General inspection for the project as defined in Title 24 at Valley. Alterations to fire alarm system - buildings A, B, D, 2, 3, 4, & 5 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-DSA Inspection | 8 | DSA Inspection | Valley | Fire Alarm replacement | Team Inspections | General inspection | 2020-08-19 | 2021-02-09 | 2020/21 | 21-1419 | PO2W-210000000455 | 0 | 3675 | 202012-12:VAFA | 2021-02-09 | 000000020163358 | 3675 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9441103 | 50% | General inspection for the project as defined in Title 24 at Valley. Alterations to fire alarm system - buildings A, B, D, 2, 3, 4, & 5 | Valley-8-Fire Alarm replacement
Wedgeworth-Drinking Fountain replacement-DSA Inspection | 0 | DSA Inspection | Wedgeworth | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-02 | 2022/23 |  | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9351104 | 0% | General inspection for the project as defined in Title 24 at Wedgeworth. Construction of 1 bottle filler at existing drinking fountain & 2 drinking fountain guardrails. Remaining balance in this PO | Wedgeworth-0-Drinking Fountain replacement
Wedgeworth-Drinking Fountain replacement-DSA Inspection | 0 | DSA Inspection | Wedgeworth | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-03 | 2022/23 | 2-6607 | PO2W-200000003303 | -1200 | -1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9351104 | 0% | General inspection for the project as defined in Title 24 at Wedgeworth. Construction of 1 bottle filler at existing drinking fountain & 2 drinking fountain guardrails. Close-out PO | Wedgeworth-0-Drinking Fountain replacement
Wilson HS-Drinking Fountain replacement-DSA Inspection | 5 | DSA Inspection | Wilson HS | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-02 | 2022/23 |  | PO2W-200000003303 | 1200 | 1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421104 | 0% | General inspection for the project as defined in Title 24 at Wilson HS. Replacement of 3-exterior drinking fountains. Remaining balance in this PO | Wilson HS-5-Drinking Fountain replacement
Wilson HS-Drinking Fountain replacement-DSA Inspection | 5 | DSA Inspection | Wilson HS | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2023-03-03 | 2022/23 | 2-6608 | PO2W-200000003303 | -1200 | -1200 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421104 | 0% | General inspection for the project as defined in Title 24 at Wilson HS. Replacement of 3-exterior drinking fountains. Close-out PO | Wilson HS-5-Drinking Fountain replacement
Wilson HS-Fire Alarm replacement-DSA Inspection | 5 | DSA Inspection | Wilson HS | Fire Alarm replacement | Team Inspections | General inspection | 2020-05-13 | 2020-06-19 | 2019/20 |  | PO2W-200000005058 | 0 | 4125 | 202006-05:WHSFA | 2020-06-19 | 000000020106934 | 4125 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421103 | 25% | General inspection for the project as defined in Title 24 at Wilson HS. Alterations to 13 fire alarm upgrade buildings A, E, F, K, P, S, B, C (C1, C2, C3), D, G, H, N, T | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-DSA Inspection | 5 | DSA Inspection | Wilson HS | Fire Alarm replacement | Team Inspections | General inspection | 2020-05-13 | 2020-08-19 | 2020/21 |  | PO2W-200000005058 | 0 | 8250 | 202008-08:WHSFA | 2020-08-19 | 000000020120364 | 8250 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421103 | 50% | General inspection for the project as defined in Title 24 at Wilson HS. Alterations to 13 fire alarm upgrade buildings A, E, F, K, P, S, B, C (C1, C2, C3), D, G, H, N, T | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-DSA Inspection | 5 | DSA Inspection | Wilson HS | Fire Alarm replacement | Team Inspections | General inspection | 2020-05-13 | 2021-09-13 | 2020/21 |  | PO2W-200000005058 | 0 | 3625 | 20210630-10: WHSFA | 2021-09-13 | 000000020257046 | 3625 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421103 | 21.97% | General inspection for the project as defined in Title 24 at Wilson HS. Alterations to 13 fire alarm upgrade buildings A, E, F, K, P, S, B, C (C1, C2, C3), D, G, H, N, T | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-DSA Inspection | 5 | DSA Inspection | Wilson HS | Fire Alarm replacement | Team Inspections | General inspection | 2020-05-13 | 2022-05-20 | 2021/22 | 2-10148 | PO2W-200000005058 | 0 | 500 | 202205-10:WHSFA | 2022-05-20 | 000000020498819 | 500 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9421103 | 3.03% | General inspection for the project as defined in Title 24 at Wilson HS. Alterations to 13 fire alarm upgrade buildings A, E, F, K, P, S, B, C (C1, C2, C3), D, G, H, N, T | Wilson HS-5-Fire Alarm replacement
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-06-19 | 2019/20 |  | PO2W-200000004962 | 0 | 2940 | 20200630-05:WEM | 2020-06-19 | 000000020106934 | 2940 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 11.54% | General inspection for the project as defined in Title 24 at Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-08-19 | 2020/21 |  | PO2W-200000004962 | 0 | 3080 | 202008-05:WEM | 2020-08-19 | 000000020120364 | 3080 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 12.09% | General inspection for the project as defined in Title 24 at Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-10-14 | 2020/21 |  | PO2W-200000004962 | 0 | 3500 | 202009-05:WEM | 2020-10-14 | 000000020134520 | 3500 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 13.74% | General inspection for the project as defined in Title 24 at Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2020-10-21 | 2020/21 |  | PO2W-200000004962 | 0 | 2940 | 202010-05:WEM | 2020-10-21 | 000000020136459 | 2940 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 11.54% | General inspection for the project as defined in Title 24 at Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-02-05 | 2020/21 |  | PO2W-200000004962 | 0 | 3080 | 202011-05:WEM | 2021-02-05 | 000000020162579 | 3080 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 12.09% | General inspection for the project as defined in Title 24 at Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004962 | 0 | 5040 | 202012-05:WEM | 2021-04-19 | 000000020181403 | 5040 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 19.78% | General inspection for the project as defined in Title 24 at Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2021-04-19 | 2020/21 |  | PO2W-200000004962 | 0 | 4900 | 202101-05:WEM | 2021-04-19 | 000000020181403 | 4900 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 19.23% | General inspection for the project as defined in Title 24 at Workman ES. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2022-07-11 | 2022/23 |  | PO2W-200000004962 | 9240 | 9240 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 0% | General inspection for the project as defined in Title 24 at Workman ES. Remaining balance in this PO. | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-DSA Inspection | 2 | DSA Inspection | Workman ES | 21st Century classroom | Team Inspections | General inspection | 2020-04-29 | 2023-06-30 | 2022/23 | 2-9869 | PO2W-200000004962 | -9240 | -9240 |  |  |  | 0 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381101 | 0% | General inspection for the project as defined in Title 24 at Workman ES. Close-out PO. | Workman ES-2-21st Century classroom
Workman ES-Drinking Fountain replacement-DSA Inspection | 2 | DSA Inspection | Workman ES | Drinking Fountain replacement | Team Inspections | General inspection | 2020-01-06 | 2021-03-24 | 2020/21 | 2-6609 | PO2W-200000003303 | 0 | 1200 | 202103-10:WDF | 2021-03-24 | 000000020174730 | 1200 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381104 | 50% | General inspection for the project as defined in Title 24 at Workman ES. Replacement of 2-exterior drinking fountains | Workman ES-2-Drinking Fountain replacement
Workman ES-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Workman ES | Fire Alarm replacement | Team Inspections | General inspection | 2021-01-13 | 2021-02-09 | 2020/21 |  | PO2W-210000001574 | 0 | 6120 | 202101-13:WFA | 2021-02-09 | 000000020163358 | 6120 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381103 | 49.96% | General inspection for the project as defined in Title 24 at Workman ES. Alterations to fire alarm system | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Workman ES | Fire Alarm replacement | Team Inspections | General inspection | 2021-01-13 | 2021-04-19 | 2020/21 |  | PO2W-210000001574 | 0 | 3060 | 202102-11:WFA | 2021-04-19 | 000000020181403 | 3060 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381103 | 24.98% | General inspection for the project as defined in Title 24 at Workman ES. Alterations to fire alarm system | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Workman ES | Fire Alarm replacement | Team Inspections | General inspection | 2021-01-13 | 2021-09-13 | 2020/21 |  | PO2W-210000001574 | 0 | 2570 | 20210630-11: WFA | 2021-09-13 | 000000020257046 | 2570 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381103 | 20.98% | General inspection for the project as defined in Title 24 at Workman ES. Alterations to fire alarm system | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-DSA Inspection | 2 | DSA Inspection | Workman ES | Fire Alarm replacement | Team Inspections | General inspection | 2021-01-13 | 2022-05-20 | 2021/22 | 21-3772 | PO2W-210000001574 | 0 | 500 | 202205-11:WFA | 2022-05-20 | 000000020498819 | 500 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6281 | 9381103 | 4.082% | General inspection for the project as defined in Title 24 at Workman ES. Alterations to fire alarm system | Workman ES-2-Fire Alarm replacement
California-Fire Alarm replacement-Contractor | 3 | Contractor | California | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2020-12-18 | 2020/21 |  | PO2W-200000004928 | 0 | 100034.1 | Pay app #1 | 2020-12-18 | 000000020151942 | 100034.1 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 44.15% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 was created using Facilities' account string (PO2W-22*912). The total project costs with this change order is $250,564.93 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Contractor | 3 | Contractor | California | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-02-02 | 2020/21 |  | PO2W-200000004928 | 0 | 95444.14 | Pay app #2 | 2021-02-02 | 000000020161539 | 95444.14 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 42.13% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 was created using Facilities' account string (PO2W-22*912). The total project costs with this change order is $250,564.93 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Contractor | 3 | Contractor | California | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-06-02 | 2020/21 |  | PO2W-200000004928 | 0 | 10570.21 | Pay app #3 | 2021-06-02 | 000000020194112 | 10570.21 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 4.665% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 was created using Facilities' account string (PO2W-22*912). The total project costs with this change order is $250,564.93 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Contractor | 3 | Contractor | California | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-06-02 | 2020/21 |  | PO2W-200000004928 | 0 | 8055.98 | Pay app #4 | 2021-06-02 | 000000020194112 | 8055.98 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 3.556% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 was created using Facilities' account string (PO2W-22*912). The total project costs with this change order is $250,564.93 | California-3-Fire Alarm replacement
California-Fire Alarm replacement-Contractor | 3 | Contractor | California | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2022-05-20 | 2021/22 | 2-9608 | PO2W-200000004928 | 0 | 12468.66 | Pay app #6 | 2022-05-20 | 000000020498818 | 12468.66 | 03-120180 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9041103 | 5.503% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at California. Change order of $23,991.84 was created using Facilities' account string (PO2W-22*912). The total project costs with this change order is $250,564.93 | California-3-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1202.7 | Pay app #1 | 2020-03-10 | 000000020079637 | 1202.7 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 0.09398% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $108,487.74 | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-04-08 | 2019/20 |  | PO1-200000000662 | 0 | 22141.65 | Pay app #2 | 2020-04-08 | 000000020087746 | 22141.65 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 1.73% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $108,487.74 | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 38354.72 | Pay app #4 | 2020-05-29 | 000000020101116 | 38354.72 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 2.997% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $108,487.74 | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-06-30 | 2019/20 |  | PO1-200000000662 | 0 | 0.01 |  |  |  | 0.01 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 7.814e-07% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $108,487.74. Accrued $0.01 more than the amount of the invoice. | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-06-30 | 2020/21 |  | PO1-200000000662 | 0 | -0.01 |  |  |  | -0.01 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | -7.814e-07% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). Reversed accrual from prior year | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 24329.03 | Pay app #5 | 2020-07-30 | 000000020117024 | 24329.03 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 1.901% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $108,487.74 | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 14196.89 | Pay app #6 | 2020-07-30 | 000000020117024 | 14196.89 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 1.109% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $108,487.74 | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-12-18 | 2020/21 |  | PO1-200000000662 | 0 | 855 | Pay app #10 | 2020-12-18 | 000000020151942 | 855 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 0.06681% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $108,487.74 | Cedarlane-1-Fire Alarm replacement
Cedarlane-Fire Alarm replacement-Contractor | 1 | Contractor | Cedarlane | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4499 | PO1-200000000662 | 0 | 5320 | Pay app #18 | 2022-06-02 | 000000020514306 | 5320 | 03-119421 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9051103 | 0.4157% | Fire alarm and low voltage service for Cedarlane. Change order of $2,087.75 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $108,487.74 | Cedarlane-1-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Contractor | 4 | Contractor | Fairgrove | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-03-18 | 2020/21 |  | PO2W-200000004930 | 0 | 301327.64 | Pay app #1 | 2021-03-18 | 000000020173348 | 301327.64 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 79.56% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project costs with change order is $395,460.03 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Contractor | 4 | Contractor | Fairgrove | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-05-21 | 2020/21 |  | PO2W-200000004930 | 0 | 31047.52 | Pay app #2 | 2021-05-21 | 000000020191188 | 31047.52 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 8.198% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project costs with change order is $395,460.03 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Contractor | 4 | Contractor | Fairgrove | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-05-21 | 2020/21 |  | PO2W-200000004930 | 0 | 21777.19 | Pay app #3 | 2021-05-21 | 000000020191188 | 21777.19 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 5.75% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project costs with change order is $395,460.03 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Contractor | 4 | Contractor | Fairgrove | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-11-05 | 2021/22 |  | PO2W-200000004930 | 0 | 21534.68 | Pay app #4 | 2021-11-05 | 000000020324297 | 21534.68 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 5.686% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project costs with change order is $395,460.03 | Fairgrove-4-Fire Alarm replacement
Fairgrove-Fire Alarm replacement-Contractor | 4 | Contractor | Fairgrove | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2022-05-20 | 2021/22 | 2-9609 | PO2W-200000004930 | 0 | 3048.76 | Pay app #5 | 2022-05-20 | 000000020498818 | 3048.76 | 03-120181 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9091103 | 0.805% | Installation of a new fire alarm devices on the existing fire alarm control panel at Fairgrove. Change order of $16,724.24 is created using Facilities' account string (PO2W-22*913). The total project costs with change order is $395,460.03 | Fairgrove-4-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1578.9 | Pay app #1 | 2020-03-10 | 000000020079637 | 1578.9 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.1234% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 47652.48 | Pay app #4 | 2020-05-29 | 000000020101116 | 47652.48 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 3.724% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 35854.85 | Pay app #5 | 2020-07-30 | 000000020117024 | 35854.85 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 2.802% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 12251.63 | Pay app #6 | 2020-07-30 | 000000020117024 | 12251.63 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.9574% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-08-28 | 2020/21 |  | PO1-200000000662 | 0 | 28361.78 | Pay app #7 | 2020-08-28 | 000000020122656 | 28361.78 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 2.216% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 6786.8 | Pay app #12 | 2021-05-21 | 000000020191188 | 6786.8 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.5303% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 1365.7 | Pay app #14 | 2021-05-21 | 000000020191188 | 1365.7 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.1067% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 855 | Pay app #15 | 2021-05-21 | 000000020191188 | 855 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.06681% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 3650.96 | Pay app #16 | 2021-11-22 | 000000020341778 | 3650.96 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.2853% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-05-23 | 2021/22 |  | PO1-200000000662 | 0 | 950 | Pay app #17 | 2022-05-23 | 000000020505866 | 950 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.07423% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
Grandview-Fire Alarm replacement-Contractor | 2 | Contractor | Grandview | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4502 | PO1-200000000662 | 0 | 7332.01 | Pay app #18 | 2022-06-02 | 000000020514306 | 7332.01 | 03-119498 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9121103 | 0.5729% | Fire alarm and low voltage service for Grandview | Grandview-2-Fire Alarm replacement
La Puente HS-Fire Alarm replacement-Contractor | 5 | Contractor | La Puente HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 | 2-4501 | PO1-200000000662 | 0 | 2717.95 | Pay app #1 | 2020-03-10 | 000000020079637 | 2717.95 | 03-119978 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9401103 | 0.2124% | Fire alarm and low voltage service for La Puente HS | La Puente HS-5-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 943.35 | Pay app #1 | 2020-03-10 | 000000020079637 | 943.35 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.07372% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-12-18 | 2020/21 |  | PO1-200000000662 | 0 | 16828.3 | Pay app #10 | 2020-12-18 | 000000020151942 | 16828.3 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 1.315% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 39719.92 | Pay app #11 | 2021-05-21 | 000000020191188 | 39719.92 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 3.104% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 610.38 | Pay app #12 | 2021-05-21 | 000000020191188 | 610.38 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.0477% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 10073.04 | Pay app #13 | 2021-05-21 | 000000020191188 | 10073.04 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.7871% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 6352.51 | Pay app #14 | 2021-05-21 | 000000020191188 | 6352.51 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.4964% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 1710 | Pay app #15 | 2021-05-21 | 000000020191188 | 1710 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.1336% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 24679.6 | Pay app #16 | 2021-11-22 | 000000020341778 | 24679.6 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 1.929% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-05-23 | 2021/22 |  | PO1-200000000662 | 0 | 950 | Pay app #17 | 2022-05-23 | 000000020505866 | 950 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.07423% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Contractor | Los Altos ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4506 | PO1-200000000662 | 0 | 5361.43 | Pay app #18 | 2022-06-02 | 000000020514306 | 5361.43 | 03-119606 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191103 | 0.419% | Fire alarm and low voltage service for Los Altos ES | Los Altos ES-2-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Contractor | 4 | Contractor | Los Molinos | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-03-18 | 2020/21 |  | PO2W-200000004929 | 0 | 102643.66 | Pay app #1 | 2021-03-18 | 000000020173348 | 102643.66 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9201103 | 54.33% | Installation of a new fire alarm devices on the existing fire alarm control panel at Los Molinos. Change order of $34,440.93 was created using Facilities' account string (PO2W-22*914). The total project costs with this change order is $223,355.69 | Los Molinos-4-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Contractor | 4 | Contractor | Los Molinos | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-05-21 | 2020/21 |  | PO2W-200000004929 | 0 | 49407.6 | Pay app #2 | 2021-05-21 | 000000020191188 | 49407.6 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9201103 | 26.15% | Installation of a new fire alarm devices on the existing fire alarm control panel at Los Molinos. Change order of $34,440.93 was created using Facilities' account string (PO2W-22*914). The total project costs with this change order is $223,355.69 | Los Molinos-4-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Contractor | 4 | Contractor | Los Molinos | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-05-21 | 2020/21 |  | PO2W-200000004929 | 0 | 26150.38 | Pay app #3 | 2021-05-21 | 000000020191188 | 26150.38 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9201103 | 13.84% | Installation of a new fire alarm devices on the existing fire alarm control panel at Los Molinos. Change order of $34,440.93 was created using Facilities' account string (PO2W-22*914). The total project costs with this change order is $223,355.69 | Los Molinos-4-Fire Alarm replacement
Los Molinos-Fire Alarm replacement-Contractor | 4 | Contractor | Los Molinos | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2022-05-20 | 2021/22 | 2-9610 | PO2W-200000004929 | 0 | 10713.12 | Pay app #5 | 2022-05-20 | 000000020498818 | 10713.12 | 03-120183 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9201103 | 5.671% | Installation of a new fire alarm devices on the existing fire alarm control panel at Los Molinos. Change order of $34,440.93 was created using Facilities' account string (PO2W-22*914). The total project costs with this change order is $223,355.69 | Los Molinos-4-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1402.2 | Pay app #1 | 2020-03-10 | 000000020079637 | 1402.2 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.1096% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 5885.73 | Pay app #6 | 2020-07-30 | 000000020117024 | 5885.73 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.4599% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-08-28 | 2020/21 |  | PO1-200000000662 | 0 | 51687.41 | Pay app #7 | 2020-08-28 | 000000020122656 | 51687.41 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 4.039% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-10-13 | 2020/21 |  | PO1-200000000662 | 0 | 36702.12 | Pay app #8 | 2020-10-13 | 000000020134117 | 36702.12 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 2.868% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-11-04 | 2020/21 |  | PO1-200000000662 | 0 | 16603.41 | Pay app #9 | 2020-11-04 | 000000020139892 | 16603.41 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 1.297% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-12-18 | 2020/21 |  | PO1-200000000662 | 0 | 1402.96 | Pay app #10 | 2020-12-18 | 000000020151942 | 1402.96 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.1096% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 350.74 | Pay app #12 | 2021-05-21 | 000000020191188 | 350.74 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.02741% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 9897.1 | Pay app #14 | 2021-05-21 | 000000020191188 | 9897.1 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.7734% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 855 | Pay app #15 | 2021-05-21 | 000000020191188 | 855 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.06681% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 14270.46 | Pay app #16 | 2021-11-22 | 000000020341778 | 14270.46 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 1.115% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-05-23 | 2021/22 |  | PO1-200000000662 | 0 | 950 | Pay app #17 | 2022-05-23 | 000000020505866 | 950 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.07423% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Contractor | Mesa Robles | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4508 | PO1-200000000662 | 0 | 6786.48 | Pay app #18 | 2022-06-02 | 000000020514306 | 6786.48 | 03-119508 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 0.5303% | Fire alarm and low voltage service for Mesa Robles | Mesa Robles-1-Fire Alarm replacement
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2020-07-30 | 2019/20 |  | PO2W-200000004671 | 0 | 61268.26 | Pay app #1 | 2020-07-30 | 000000020117024 | 61268.26 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221103 | 22.44% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed account string for project type (from Fire Alarm replacement to Interim Housing project), per Richard Walsh on 03/08/21. Loc 9221103 is used to pay the pay app #1. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2020-08-28 | 2020/21 |  | PO2W-200000004671 | 0 | 165673.54 | Pay app #2 | 2020-08-28 | 000000020122656 | 165673.54 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 60.68% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2020-11-09 | 2020/21 |  | PO2W-200000004671 | 0 | 12873.64 | Pay app #3 | 2020-11-09 | 000000020141151 | 12873.64 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 4.715% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2020-12-18 | 2020/21 |  | PO2W-200000004671 | 0 | 3965.31 | Pay app #4 | 2020-12-18 | 000000020151942 | 3965.31 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 1.452% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2021-03-12 | 2020/21 |  | PO2W-200000004671 | 0 | 7229.21 | Pay app #5 | 2021-03-12 | 000000020171773 | 7229.21 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 2.648% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2021-05-21 | 2020/21 |  | PO2W-200000004671 | 0 | 11526.54 | Pay app #6 | 2021-05-21 | 000000020191188 | 11526.54 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 4.222% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2021-05-21 | 2020/21 |  | PO2W-200000004671 | 0 | 7566.56 | Pay app #7 | 2021-05-21 | 000000020191188 | 7566.56 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 2.771% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2022-11-28 | 2022/23 |  | PO2W-200000004671 | 0 | 475 | Pay app #8 | 2022-11-28 | 000000020738374 | 475 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 0.174% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2020-03-03 | 2022-12-06 | 2022/23 | 2-8611 | PO2W-200000004671 | 0 | 2457.25 | Pay app #9 | 2022-12-06 | 000000020752802 | 2457.25 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 0.9% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices, new IP PA clock/speakers & WP speakers with Cat 6 cabling back to new IDF cabinets (3 total), new data drops, new motion detectors and door contacts at Mesa Robles. Changed to Interim Housing project from Fire Alarm, per Richard Walsh 03/08/21. The total project costs with the change orders (PO2W-21*1738 & 21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2021-02-04 | 2022-12-06 | 2022/23 | 21-4190 | PO2W-210000001738 | 0 | 4174.01 | Pay app #9 | 2022-12-06 | 000000020752802 | 4174.01 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221102 | 100% | Change order for additional installation of telephone cable and data drops at Mesa Robles. Addendum to PO2W-20*4671. Change order #1. The total project costs with the change orders (this PO & PO2W-21*1875) is $284,819.01 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Telenet VOIP, Inc. | Contractor | 2021-03-08 | 2022-12-06 | 2022/23 | 21-5000 | PO2W-210000001875 | 0 | 7609.69 | Pay app #9 | 2022-12-06 | 000000020752802 | 7609.69 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221102 | 100% | Change order for additional installation of telephone cable and data drops at Mesa Robles. Addendum to PO2W-20*4671. Change order #2. The total project costs with the change orders (this PO & PO2W-21*1738) is $284,819.01 | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Telenet VOIP, Inc. | Contractor | 2020-02-06 | 2020-03-19 | 2019/20 |  | PO2W-200000004053 | 0 | 13950.28 | Pay app #1 | 2020-03-19 | 000000020082827 | 13950.28 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 42.75% | Low voltage/classroom raceway for Nelson, room #C1. Remove/reinstall 1 existing smoke detector and 1 existing horn strobe. Installation of required 5400 raceway & fittings. Installation of #12 solid wire from outlets to new installed circuit breaker in existing electrical distribution panel. Install Cat 6 cable for 8 data drops and Cat 6A for 4 WAP data drops with 3" of service loop. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Telenet VOIP, Inc. | Contractor | 2020-02-06 | 2020-04-23 | 2019/20 |  | PO2W-200000004053 | 0 | 6200.12 | Pay app #2 | 2020-04-23 | 000000020091991 | 6200.12 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 19% | Low voltage/classroom raceway for Nelson, room #C1. Remove/reinstall 1 existing smoke detector and 1 existing horn strobe. Installation of required 5400 raceway & fittings. Installation of #12 solid wire from outlets to new installed circuit breaker in existing electrical distribution panel. Install Cat 6 cable for 8 data drops and Cat 6A for 4 WAP data drops with 3" of service loop. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Telenet VOIP, Inc. | Contractor | 2020-02-06 | 2020-05-29 | 2019/20 |  | PO2W-200000004053 | 0 | 10850.22 | Pay app #3 | 2020-05-29 | 000000020101116 | 10850.22 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 33.25% | Low voltage/classroom raceway for Nelson, room #C1. Remove/reinstall 1 existing smoke detector and 1 existing horn strobe. Installation of required 5400 raceway & fittings. Installation of #12 solid wire from outlets to new installed circuit breaker in existing electrical distribution panel. Install Cat 6 cable for 8 data drops and Cat 6A for 4 WAP data drops with 3" of service loop. | Nelson-1-21st Century classroom
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Telenet VOIP, Inc. | Contractor | 2020-02-06 | 2021-01-07 | 2020/21 | 2-7677 | PO2W-200000004053 | 0 | 1631.61 | Pay app #4 | 2021-01-07 | 000000020154817 | 1631.61 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231101 | 5% | Low voltage/classroom raceway for Nelson, room #C1. Remove/reinstall 1 existing smoke detector and 1 existing horn strobe. Installation of required 5400 raceway & fittings. Installation of #12 solid wire from outlets to new installed circuit breaker in existing electrical distribution panel. Install Cat 6 cable for 8 data drops and Cat 6A for 4 WAP data drops with 3" of service loop. | Nelson-1-21st Century classroom
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1017.45 | Pay app #1 | 2020-03-10 | 000000020079637 | 1017.45 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.07951% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-12-18 | 2020/21 |  | PO1-200000000662 | 0 | 8907.87 | Pay app #10 | 2020-12-18 | 000000020151942 | 8907.87 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.6961% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 47854.83 | Pay app #11 | 2021-05-21 | 000000020191188 | 47854.83 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 3.739% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 5867.44 | Pay app #12 | 2021-05-21 | 000000020191188 | 5867.44 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.4585% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 9127.55 | Pay app #13 | 2021-05-21 | 000000020191188 | 9127.55 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.7132% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 7359.72 | Pay app #14 | 2021-05-21 | 000000020191188 | 7359.72 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.5751% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 2263.16 | Pay app #15 | 2021-05-21 | 000000020191188 | 2263.16 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.1768% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 29445.32 | Pay app #16 | 2021-11-22 | 000000020341778 | 29445.32 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 2.301% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-05-23 | 2021/22 |  | PO1-200000000662 | 0 | 1619.99 | Pay app #17 | 2022-05-23 | 000000020505866 | 1619.99 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.1266% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Nelson-Fire Alarm replacement-Contractor | 1 | Contractor | Nelson | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4509 | PO1-200000000662 | 0 | 5971.75 | Pay app #18 | 2022-06-02 | 000000020514306 | 5971.75 | 03-119551 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9231103 | 0.4666% | Fire alarm and low voltage service for Nelson | Nelson-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Contractor | 1 | Contractor | Newton | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 3359.2 | Pay app #1 | 2020-03-10 | 000000020079637 | 3359.2 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.2625% | Fire alarm and low voltage service for Newton | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Contractor | 1 | Contractor | Newton | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-04-08 | 2019/20 |  | PO1-200000000662 | 0 | 21443.4 | Pay app #2 | 2020-04-08 | 000000020087746 | 21443.4 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 1.676% | Fire alarm and low voltage service for Newton | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Contractor | 1 | Contractor | Newton | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-04-24 | 2019/20 |  | PO1-200000000662 | 0 | 17273.14 | Pay app #3 | 2020-04-24 | 000000020092209 | 17273.14 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 1.35% | Fire alarm and low voltage service for Newton | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Contractor | 1 | Contractor | Newton | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 21295.68 | Pay app #4 | 2020-05-29 | 000000020101116 | 21295.68 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 1.664% | Fire alarm and low voltage service for Newton | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Contractor | 1 | Contractor | Newton | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 3504.98 | Pay app #5 | 2020-07-30 | 000000020117024 | 3504.98 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.2739% | Fire alarm and low voltage service for Newton | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Contractor | 1 | Contractor | Newton | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 10458.36 | Pay app #6 | 2020-07-30 | 000000020117024 | 10458.36 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.8172% | Fire alarm and low voltage service for Newton | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Contractor | 1 | Contractor | Newton | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-08-28 | 2020/21 |  | PO1-200000000662 | 0 | 1211.25 | Pay app #7 | 2020-08-28 | 000000020122656 | 1211.25 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.09465% | Fire alarm and low voltage service for Newton | Newton-1-Fire Alarm replacement
Newton-Fire Alarm replacement-Contractor | 1 | Contractor | Newton | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4510 | PO1-200000000662 | 0 | 4134 | Pay app #18 | 2022-06-02 | 000000020514306 | 4134 | 03-119556 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9241103 | 0.323% | Fire alarm and low voltage service for Newton | Newton-1-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Contractor | 2 | Contractor | Sparks MS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 35460.79 | Pay app #1 | 2020-03-10 | 000000020079637 | 35460.79 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 2.771% | Fire alarm and low voltage service for Sparks MS | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Contractor | 2 | Contractor | Sparks MS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-04-08 | 2019/20 |  | PO1-200000000662 | 0 | 48832.8 | Pay app #2 | 2020-04-08 | 000000020087746 | 48832.8 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 3.816% | Fire alarm and low voltage service for Sparks MS | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Contractor | 2 | Contractor | Sparks MS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-04-24 | 2019/20 |  | PO1-200000000662 | 0 | 47231.15 | Pay app #3 | 2020-04-24 | 000000020092209 | 47231.15 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 3.691% | Fire alarm and low voltage service for Sparks MS | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Contractor | 2 | Contractor | Sparks MS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 3640.69 | Pay app #4 | 2020-05-29 | 000000020101116 | 3640.69 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 0.2845% | Fire alarm and low voltage service for Sparks MS | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Contractor | 2 | Contractor | Sparks MS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 9234.57 | Pay app #5 | 2020-07-30 | 000000020117024 | 9234.57 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 0.7216% | Fire alarm and low voltage service for Sparks MS | Sparks MS-2-Fire Alarm replacement
Sparks MS-Fire Alarm replacement-Contractor | 2 | Contractor | Sparks MS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4511 | PO1-200000000662 | 0 | 7600 | Pay app #18 | 2022-06-02 | 000000020514306 | 7600 | 03-119501 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9301103 | 0.5939% | Fire alarm and low voltage service for Sparks MS | Sparks MS-2-Fire Alarm replacement
Valley-Fire Alarm replacement-Contractor | 8 | Contractor | Valley | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2020-10-13 | 2020/21 |  | PO2W-200000004931 | 0 | 184497.98 | Pay app #1 | 2020-10-13 | 000000020134117 | 184497.98 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9441103 | 84.96% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at Valley. The total project costs with the change order (PO2W-21*2213) is $231,990.92 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Contractor | 8 | Contractor | Valley | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2020-11-04 | 2020/21 |  | PO2W-200000004931 | 0 | 14431.45 | Pay app #2 | 2020-11-04 | 000000020139892 | 14431.45 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9441103 | 6.646% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at Valley. The total project costs with the change order (PO2W-21*2213) is $231,990.92 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Contractor | 8 | Contractor | Valley | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2020-12-18 | 2020/21 |  | PO2W-200000004931 | 0 | 12210.58 | Pay app #3 | 2020-12-18 | 000000020151942 | 12210.58 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9441103 | 5.623% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at Valley. The total project costs with the change order (PO2W-21*2213) is $231,990.92 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Contractor | 8 | Contractor | Valley | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2020-04-13 | 2021-05-07 | 2020/21 | 2-9611 | PO2W-200000004931 | 0 | 6009.39 | Pay app #4 | 2021-05-07 | 000000020187165 | 6009.39 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9441103 | 2.767% | Installation of a new fire alarm control panel interfaced with the existing fire alarm control panel and new fire alarm devices at Valley. The total project costs with the change order (PO2W-21*2213) is $231,990.92 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Contractor | 8 | Contractor | Valley | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2021-05-03 | 2021-05-07 | 2020/21 |  | PO2W-210000002213 | 0 | 819.47 | Pay app #4 | 2021-05-07 | 000000020187165 | 819.47 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9441103 | 5.521% | Change order to add and replace new heat detectors, install 1 new wall mounted speaker and new smoke detector at Valley. Addendum to PO2W-20*4931. The total project costs with this change order is $231,990.92 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Contractor | 8 | Contractor | Valley | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2021-05-03 | 2021-05-12 | 2020/21 |  | PO2W-210000002213 | 0 | 1947.5 | Pay app #5 | 2021-05-12 | 000000020188449 | 1947.5 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9441103 | 13.12% | Change order to add and replace new heat detectors, install 1 new wall mounted speaker and new smoke detector at Valley. Addendum to PO2W-20*4931. The total project costs with this change order is $231,990.92 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Contractor | 8 | Contractor | Valley | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2021-05-03 | 2022-05-23 | 2021/22 |  | PO2W-210000002213 | 0 | 475 | Pay app #6 | 2022-05-23 | 000000020505866 | 475 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9441103 | 3.2% | Change order to add and replace new heat detectors, install 1 new wall mounted speaker and new smoke detector at Valley. Addendum to PO2W-20*4931. The total project costs with this change order is $231,990.92 | Valley-8-Fire Alarm replacement
Valley-Fire Alarm replacement-Contractor | 8 | Contractor | Valley | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2021-05-03 | 2022-05-23 | 2021/22 | 21-6251 | PO2W-210000002213 | 0 | 11599.55 | Pay app #7 | 2022-05-23 | 000000020505866 | 11599.55 | 03-120156 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9441103 | 78.16% | Change order to add and replace new heat detectors, install 1 new wall mounted speaker and new smoke detector at Valley. Addendum to PO2W-20*4931. The total project costs with this change order is $231,990.92 | Valley-8-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 2997.25 | Pay app #1 | 2020-03-10 | 000000020079637 | 2997.25 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.2342% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-05-29 | 2019/20 |  | PO1-200000000662 | 0 | 1723.3 | Pay app #4 | 2020-05-29 | 000000020101116 | 1723.3 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.1347% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 82411.36 | Pay app #5 | 2020-07-30 | 000000020117024 | 82411.36 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 6.44% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-07-30 | 2019/20 |  | PO1-200000000662 | 0 | 79907.49 | Pay app #6 | 2020-07-30 | 000000020117024 | 79907.49 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 6.244% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-08-28 | 2020/21 |  | PO1-200000000662 | 0 | 25191.82 | Pay app #7 | 2020-08-28 | 000000020122656 | 25191.82 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 1.969% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-10-13 | 2020/21 |  | PO1-200000000662 | 0 | 25638.05 | Pay app #8 | 2020-10-13 | 000000020134117 | 25638.05 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 2.003% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-11-04 | 2020/21 |  | PO1-200000000662 | 0 | 12068.33 | Pay app #9 | 2020-11-04 | 000000020139892 | 12068.33 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.943% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 4520.48 | Pay app #13 | 2021-05-21 | 000000020191188 | 4520.48 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.3532% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 565.06 | Pay app #14 | 2021-05-21 | 000000020191188 | 565.06 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.04415% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 25768.03 | Pay app #16 | 2021-11-22 | 000000020341778 | 25768.03 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 2.014% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-05-23 | 2021/22 |  | PO1-200000000662 | 0 | 6612.8 | Pay app #17 | 2022-05-23 | 000000020505866 | 6612.8 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 0.5167% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Wilson HS-Fire Alarm replacement-Contractor | 5 | Contractor | Wilson HS | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4505 | PO1-200000000662 | 0 | 14656.21 | Pay app #18 | 2022-06-02 | 000000020514306 | 14656.21 | 03-119611 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9421103 | 1.145% | Fire alarm and low voltage service for Wilson HS. Change order of $12,590.25 was created using Facilities' account string (PO2W-22*915). The total project costs with this change order is $294,650.43 | Wilson HS-5-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Contractor | 2 | Contractor | Workman ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2020-03-10 | 2019/20 |  | PO1-200000000662 | 0 | 1131.45 | Pay app #1 | 2020-03-10 | 000000020079637 | 1131.45 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0.08841% | Fire alarm and low voltage service for Workman ES | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Contractor | 2 | Contractor | Workman ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 62754.38 | Pay app #12 | 2021-05-21 | 000000020191188 | 62754.38 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 4.904% | Fire alarm and low voltage service for Workman ES | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Contractor | 2 | Contractor | Workman ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 13328.69 | Pay app #13 | 2021-05-21 | 000000020191188 | 13328.69 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 1.042% | Fire alarm and low voltage service for Workman ES | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Contractor | 2 | Contractor | Workman ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 2235.78 | Pay app #14 | 2021-05-21 | 000000020191188 | 2235.78 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0.1747% | Fire alarm and low voltage service for Workman ES | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Contractor | 2 | Contractor | Workman ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-05-21 | 2020/21 |  | PO1-200000000662 | 0 | 6656.75 | Pay app #15 | 2021-05-21 | 000000020191188 | 6656.75 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0.5202% | Fire alarm and low voltage service for Workman ES | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Contractor | 2 | Contractor | Workman ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2021-11-22 | 2021/22 |  | PO1-200000000662 | 0 | 39885.71 | Pay app #16 | 2021-11-22 | 000000020341778 | 39885.71 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 3.117% | Fire alarm and low voltage service for Workman ES | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Contractor | 2 | Contractor | Workman ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-05-23 | 2021/22 |  | PO1-200000000662 | 0 | 950 | Pay app #17 | 2022-05-23 | 000000020505866 | 950 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0.07423% | Fire alarm and low voltage service for Workman ES | Workman ES-2-Fire Alarm replacement
Workman ES-Fire Alarm replacement-Contractor | 2 | Contractor | Workman ES | Fire Alarm replacement | Telenet VOIP, Inc. | Contractor | 2019-09-26 | 2022-06-02 | 2021/22 | 2-4512 | PO1-200000000662 | 0 | 6824.25 | Pay app #18 | 2022-06-02 | 000000020514306 | 6824.25 | 03-119612 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9381103 | 0.5333% | Fire alarm and low voltage service for Workman ES | Workman ES-2-Fire Alarm replacement
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2019-07-29 | 2021-02-05 | 2020/21 |  | PO2W-200000000234 | 0 | 8497 | 71498 | 2021-02-05 | 000000020162580 | 8497 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 71.87% | Rental of power pole for Newton Interim Housing - Provide temporary power to portable classrooms and include 6 month of rents at Newton. After 6 months, rental is $150.00/month. The total project costs with the change order (PO2W-22-1932) is $21,287.00. For the monthly rental fees (after 6 months), see PO2W-23*1681 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2019-07-29 | 2022-05-04 | 2021/22 | 2-1102 | PO2W-200000000234 | 0 | 3325 | 76536 | 2022-05-04 | 000000020484178 | 3325 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 28.13% | Rental of power pole for Newton Interim Housing - Provide temporary power to portable classrooms and include 6 month of rents at Newton. After 6 months, rental is $150.00/month. The total project costs with the change order (PO2W-22-1932) is $21,287.00. For the monthly rental fees (after 6 months), see PO2W-23*1681 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-03-30 | 2022-05-04 | 2021/22 |  | PO2W-220000001932 | 0 | 1340 | 76536 | 2022-05-04 | 000000020484178 | 1340 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 17.48% | Change order for meter panel relocation & additional equipment. Provide temporary power to portable classrooms at Newton. Addendum to PO2W-20*234. The total project costs with this change order is $21,287.00. For the monthly rental fees (after 6 months), see PO2W-23*1681 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-03-30 | 2022-06-17 | 2021/22 | 22-6075 | PO2W-220000001932 | 0 | 6325 | 76644 | 2022-06-17 | 000000020529406 | 6325 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9241102 | 82.52% | Change order for meter panel relocation & additional equipment. Provide temporary power to portable classrooms at Newton. Addendum to PO2W-20*234. The total project costs with this change order is $21,287.00. For the monthly rental fees (after 6 months), see PO2W-23*1681 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2022-12-20 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 78300 | 2022-12-20 | 000000020777181 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-01-11 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 78585 | 2023-01-11 | 000000020798747 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-01-12 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 78835 | 2023-01-12 | 000000020803372 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-03-07 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 79090 | 2023-03-07 | 000000020889994 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-05-18 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 79336 | 2023-05-18 | 000000021019994 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-05-18 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 79610 | 2023-05-18 | 000000021019994 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-05-18 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 79872 | 2023-05-18 | 000000021019994 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-07-18 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 80131 | 2023-07-18 | 000000021130770 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-07-18 | 2022/23 |  | PO2W-230000001681 | 0 | 150 | 80379 | 2023-07-18 | 000000021130770 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-08-28 | 2023/24 |  | PO2W-230000001681 | 0 | 150 | 80645 | 2023-08-28 | 000000021185738 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2023-10-02 | 2023/24 |  | PO2W-230000001681 | 0 | 150 | 80931 | 2023-10-02 | 000000021240116 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2024-01-16 | 2023/24 | 23-4091 | PO2W-230000001681 | 1050 | 1050 |  |  |  | 0 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 0% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2024-01-19 | 2023/24 |  | PO2W-230000001681 | 0 | 150 | 81186 | 2024-01-19 | 000000021417653 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2024-01-19 | 2023/24 |  | PO2W-230000001681 | 0 | 150 | 81446 | 2024-01-19 | 000000021417653 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2024-01-19 | 2023/24 |  | PO2W-230000001681 | 0 | 150 | 81690 | 2024-01-19 | 000000021417653 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Temp Power Sytems | Rental of power pole | 2022-11-21 | 2024-01-19 | 2023/24 |  | PO2W-230000001681 | 0 | 150 | 81913 | 2024-01-19 | 000000021417653 | 150 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 4.545% | Rental of power pole for Newton Interim Housing - Monthly charges of $150.00 to provide temporary power to portable classrooms for 12 months (Oct. 1, 2022 - Sept. 30, 2023). Addendum to PO2W-20*234 and PO2W-22*1932. The total project costs with the change order (PO2W-22-1932) and these monthly fees are $21,287.00 | Newton-1-Interim Housing
La Puente HS-21st Century classroom-Contractor | 5 | Contractor | La Puente HS | 21st Century classroom | The Nazerian Group | Contractor | 2024-01-09 | 2028-06-01 | 2023/24 | 24-4846 |  | 2444123 | 2444123 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9401101 | 0% | Classroom improvements for La Puente HS. Bid #2023-24.05 Measure BB Bond Base Bid #1 | La Puente HS-5-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | The Nazerian Group | Contractor | 2020-06-05 | 2020-10-13 | 2020/21 |  | PO2W-200000005821 | 0 | 369049.35 | Pay app #1 | 2020-10-13 | 000000020134121 | 369049.35 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 24.7% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project costs with the change orders (PO2W-22*2621 & PO2W-23*1683) is $1,534,027.27 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | The Nazerian Group | Contractor | 2020-06-05 | 2020-10-13 | 2020/21 |  | PO2W-200000005821 | 0 | 76902.5 | Pay app #2 | 2020-10-13 | 000000020134121 | 76902.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 5.147% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project costs with the change orders (PO2W-22*2621 & PO2W-23*1683) is $1,534,027.27 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | The Nazerian Group | Contractor | 2020-06-05 | 2021-02-05 | 2020/21 |  | PO2W-200000005821 | 0 | 766840 | Pay app #3 | 2021-02-05 | 000000020162581 | 766840 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 51.32% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project costs with the change orders (PO2W-22*2621 & PO2W-23*1683) is $1,534,027.27 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | The Nazerian Group | Contractor | 2020-06-05 | 2021-04-06 | 2020/21 |  | PO2W-200000005821 | 0 | 95237.5 | Pay app #4 | 2021-04-06 | 000000020177879 | 95237.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 6.374% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project costs with the change orders (PO2W-22*2621 & PO2W-23*1683) is $1,534,027.27 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | The Nazerian Group | Contractor | 2020-06-05 | 2022-11-30 | 2022/23 |  | PO2W-200000005821 | 0 | 149296.56 | Pay app #5 | 2022-11-30 | 000000020743473 | 149296.56 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 9.992% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project costs with the change orders (PO2W-22*2621 & PO2W-23*1683) is $1,534,027.27 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | The Nazerian Group | Contractor | 2020-06-05 | 2022-12-12 | 2022/23 | 2-10690 | PO2W-200000005821 | 0 | 36797.09 | Pay app #6 | 2022-12-12 | 000000020762706 | 36797.09 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6250 | 9381101 | 2.463% | 21st Classroom modifications at Workman ES. Bid bundle #1. The total project costs with the change orders (PO2W-22*2621 & PO2W-23*1683) is $1,534,027.27 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | The Nazerian Group | Contractor | 2022-03-07 | 2022-12-12 | 2022/23 | 22-5141 | PO2W-220000002621 | 0 | 39293.51 | Pay app #6 | 2022-12-12 | 000000020762706 | 39293.51 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9381101 | 100% | Change order #1 for the 21st Classroom modifications at Workman ES. Bid bundle #1. Additional costs for Mohawk flooring & plywood backing. Addendum to PO2W-20*5821. The total project costs with the change orders (this PO & PO2W-23*1683) is $1,534,027.27 | Workman ES-2-21st Century classroom
Workman ES-21st Century classroom-Contractor | 2 | Contractor | Workman ES | 21st Century classroom | The Nazerian Group | Contractor | 2022-11-21 | 2022-12-12 | 2022/23 | 23-4094 | PO2W-230000001683 | 0 | 610.76 | Pay app #6 | 2022-12-12 | 000000020762706 | 610.76 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9381101 | 100% | Change order #2 for the 21st Classroom modifications at Workman ES. Bid bundle #1. Additional ceiling wiremold replacement. Addendum to PO2W-20*5821. The total project costs with the change orders (this PO & PO2W-22*2621) is $1,534,027.27 | Workman ES-2-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | U.S. Bank National Association | Trust fees | 2017-07-12 | 2017-07-12 | 2017/18 |  | N/A - Cost of Issuance | 0 | 550 |  |  |  | 550 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Trust fees, 18-KT005 | District Office-0-Cost of Issuance
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Uline | Carts | 2020-12-01 | 2020-12-08 | 2020/21 | 21-3309 | PO3W-210000001074 | 0 | 791.69 | 127489647 | 2020-12-08 | 000000020148246 | 791.69 |  |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9851100 | 100% | Drywall cart - 23"x50" & Adjustable panel truck - 30"x60" for District-wide use. Total carts: 2. | District Office-0-21st Century classroom
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Uline | Hydraulic stacker | 2021-05-27 | 2021-06-04 | 2020/21 | 21-6552 | PO3W-210000002899 | 0 | 1834.13 | 134374802 | 2021-06-04 | 000000020195024 | 1834.13 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 100% | A hydraulic stacker for District-wide use | District Office-0-21st Century classroom
District Office-21st Century classroom-FF & E | 0 | FF & E | District Office | 21st Century classroom | Uline | Hydraulic stacker | 2021-06-08 | 2021-06-15 | 2020/21 | 21-6760 | PO3W-210000002998 | 0 | 1834.13 | 134874288 | 2021-06-15 | 000000020198046 | 1834.13 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 4400 | 9851100 | 100% | A hydraulic stacker for District-wide use | District Office-0-21st Century classroom
Grandview-21st Century classroom-FF & E | 2 | FF & E | Grandview | 21st Century classroom | Uline | Furniture | 2019-07-01 | 2019-07-30 | 2019/20 | 2-1363 | PO3W-200000000288 | 0 | 8041.68 | 110598716 | 2019-07-30 | 000000020001919 | 8041.68 | 03-121294 |  | 21.0 | 00036.0 | 91001 | 85000 | 4300 | 9121101 | 100% | Furniture - Tables, casters, and shop stools for Grandview's room #61 | Grandview-2-21st Century classroom
La Puente HS-21st Century classroom-Move classroom | 5 | Move classroom | La Puente HS | 21st Century classroom | Uline | Boxes & tapes | 2024-01-16 | 2024-06-01 | 2023/24 | 24-4973 |  | 1420.32 | 1420.32 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9401101 | 0% | Boxes & packing tapes for teachers' to pack their classrooms at La Puente HS. | La Puente HS-5-21st Century classroom
Workman HS-21st Century classroom-Move classroom | 5 | Move classroom | Workman HS | 21st Century classroom | Uline | Boxes & tapes | 2024-01-16 | 2024-06-01 | 2023/24 | 24-4973 |  | 1420.32 | 1420.32 |  |  |  | 0 |  |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9431101 | 0% | Boxes & packing tapes for teachers' to pack their classrooms at Workman HS. | Workman HS-5-21st Century classroom
District Office-Cost of Issuance-Issuance costs | 0 | Issuance costs | District Office | Cost of Issuance | Underwriter's fees | Underwriter's fees | 2017-07-12 | 2017-07-12 | 2019/20 |  | N/A - Cost of Issuance | 0 | 175000 |  |  |  | 175000 |  |  | 21.0 | 00036.0 | 00000 | 91000 | 5800 | 9900000 | 100% | Underwriter's fees, JVA21*384 | District Office-0-Cost of Issuance
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | Universal Asphalt | Contractor | 2019-07-23 | 2019-09-03 | 2019/20 | 2 -1131 | PO2W-200000000237 | 0 | 13776 | 40499 | 2019-09-03 | 000000020010771 | 13776 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 100% | Furnish & install asphalatic concrete over 4,800 SF @ $2.87/SF at Los Altos ES. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | Universal Asphalt | Contractor | 2019-07-23 | 2019-09-03 | 2019/20 | 2-2002 | PO2W-200000000632 | 0 | 4879 | 40500 | 2019-09-03 | 000000020010771 | 4879 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 100% | Additional work to furnish & install asphalatic concrete over 1,700 SF @ $2.87/SF at Los Altos ES. | Los Altos ES-2-Interim Housing
Los Altos ES-Interim Housing-Contractor | 2 | Contractor | Los Altos ES | Interim Housing | Universal Asphalt | Contractor | 2019-09-26 | 2019-10-25 | 2019/20 | 2-3684 | PO2W-200000001460 | 0 | 13902 | 40610 | 2019-10-25 | 000000020031054 | 13902 | 03-119857 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9191102 | 100% | Grind & remove existing AC as needed for paving, haul off debris, & furnish & install 3" AC cover over 4" base 2,100 SF at $6.62/SF - ramp to portables at Los Altos ES. | Los Altos ES-2-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Universal Asphalt | Contractor | 2020-03-03 | 2020-07-29 | 2019/20 |  | PO2W-200000004878 | 0 | 32487.91 | Pay app #1 | 2020-07-29 | 000000020116861 | 32487.91 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 32.73% | Remove & replace 3" AC over 4" base 27,280 SF at $3.50/SF, furnish and install 2x4 redwood header, 800 L.F. at $3.50 at Mesa Robles. The total project costs with the change order (PO2W-21*545) is $106,537.80 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Universal Asphalt | Contractor | 2020-03-03 | 2020-10-13 | 2020/21 |  | PO2W-200000004878 | 0 | 61448 | Pay app #2 | 2020-10-13 | 000000020134125 | 61448 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 61.9% | Remove & replace 3" AC over 4" base 27,280 SF at $3.50/SF, furnish and install 2x4 redwood header, 800 L.F. at $3.50 at Mesa Robles. The total project costs with the change order (PO2W-21*545) is $106,537.80 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Universal Asphalt | Contractor | 2020-03-03 | 2020-10-13 | 2020/21 | 2-8608 | PO2W-200000004878 | 0 | 5326.89 | Pay app #3 | 2020-10-13 | 000000020134125 | 5326.89 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6150 | 9221102 | 5.366% | Remove & replace 3" AC over 4" base 27,280 SF at $3.50/SF, furnish and install 2x4 redwood header, 800 L.F. at $3.50 at Mesa Robles. The total project costs with the change order (PO2W-21*545) is $106,537.80 | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Universal Asphalt | Contractor | 2020-09-03 | 2020-10-13 | 2020/21 | 21-1705 | PO2W-210000000545 | 0 | 7275 | Pay app #2 | 2020-10-13 | 000000020134125 | 7275 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 6260 | 9221102 | 100% | Change order for 3 additional move ins at no cost and 97 additional tons of asphalt concrete used @75.00/ton at Mesa Robles. Addendum to PO2W-20*4878. The total project costs with this change order is $106,537.80 | Mesa Robles-1-Interim Housing
Los Altos ES-21st Century classroom-Legal services | 2 | Legal services | Los Altos ES | 21st Century classroom | Walter Fajardo | Notary fees | 2022-07-11 | 2022-08-17 | 2022/23 | 23-826 | PO2W-230000000339 | 0 | 22.5 | Joel Duarte 07/18/22 | 2022-08-17 | 000000020586492 | 22.5 | 03-119947 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9191101 | 33.33% | To notarize Notice of Completion for Los Altos ES, 21st Century project | Los Altos ES-2-21st Century classroom
Nelson-21st Century classroom-Legal services | 1 | Legal services | Nelson | 21st Century classroom | Walter Fajardo | Notary fees | 2022-07-11 | 2022-08-17 | 2022/23 | 23-826 | PO2W-230000000339 | 0 | 22.5 | Joel Duarte 07/18/22 | 2022-08-17 | 000000020586492 | 22.5 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9231101 | 33.33% | To notarize Notice of Completion for Nelson, 21st Century project | Nelson-1-21st Century classroom
Workman ES-21st Century classroom-Legal services | 2 | Legal services | Workman ES | 21st Century classroom | Walter Fajardo | Notary fees | 2022-07-11 | 2022-08-17 | 2022/23 | 23-826 | PO2W-230000000339 | 0 | 22.5 | Joel Duarte 07/18/22 | 2022-08-17 | 000000020586492 | 22.5 | 03-119881 |  | 21.0 | 00036.0 | 91001 | 85000 | 5800 | 9381101 | 33.33% | To notarize Notice of Completion for Workman ES, 21st Century project | Workman ES-2-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Warehouse | Boxes | 2020-10-20 | 2020-10-28 | 2020/21 |  | XSRQ-210000001812 | 0 | 318.12 |  |  |  | 318.12 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(240) for teachers' to pack their classrooms at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Warehouse | Boxes & tapes | 2020-12-03 | 2020-12-08 | 2020/21 |  | XSRQ-210000002207 | 0 | 484.13 |  |  |  | 484.13 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(250) & packing tapes (50) for teachers' to pack their classrooms at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Warehouse | Boxes & tapes | 2020-12-08 | 2020-12-10 | 2020/21 |  | XSRQ-210000002247 | 0 | 484.13 |  |  |  | 484.13 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(250) & packing tapes (50) for teachers' to pack their classrooms at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Warehouse | Boxes & tapes | 2021-01-08 | 2021-01-12 | 2020/21 |  | XSRQ-210000002484 | 0 | 795.26 |  |  |  | 795.26 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(260) & packing tapes (150) for teachers' to pack their classrooms at Cedarlane. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-Move classroom | 1 | Move classroom | Cedarlane | 21st Century classroom | Warehouse | Boxes | 2021-01-14 | 2021-06-04 | 2020/21 |  | XSRQ-210000002565 | 0 | 466.62 |  |  |  | 466.62 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Boxes(360) for teachers' to pack their classrooms at Cedarlane. Ordered 540, returned 150: 540 - 180 = 360 boxes | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Warehouse | Soap dispensers | 2021-07-09 | 2021-07-12 | 2021/22 |  | XSRQ-220000000064 | 0 | 0 |  |  |  | 0 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Classroom soap dispensers (24) for Cedarlane. These items are free to sites. | Cedarlane-1-21st Century classroom
Cedarlane-21st Century classroom-FF & E | 1 | FF & E | Cedarlane | 21st Century classroom | Warehouse | Paper towel dispenser | 2021-07-13 | 2021-07-22 | 2021/22 |  | XSRQ-220000000112 | 0 | 918.52 |  |  |  | 918.52 | 03-120780 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9051101 | 100% | Classroom paper towel dispensers (24) for Cedarlane | Cedarlane-1-21st Century classroom
Grandview-21st Century classroom-Move classroom | 2 | Move classroom | Grandview | 21st Century classroom | Warehouse | Boxes & tapes | 2022-11-02 | 2022-11-04 | 2022/23 |  | XSRQ-230000002152 | 0 | 318.77 |  |  |  | 318.77 | 03-121294 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9121101 | 100% | Boxes(150) & packing tapes (20) for teachers' to pack their classrooms at Grandview | Grandview-2-21st Century classroom
Los Altos ES-21st Century classroom-FF & E | 2 | FF & E | Los Altos ES | 21st Century classroom | Warehouse | Paper towel dispenser | 2021-09-01 | 2021-09-03 | 2021/22 |  | XSRQ-220000000971 | 0 | 86.19 |  |  |  | 86.19 | 03-119947 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9191101 | 100% | Classroom paper towel dispensers (2) for Los Altos ES | Los Altos ES-2-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Warehouse | Boxes | 2020-10-20 | 2020-10-28 | 2020/21 |  | XSRQ-210000001813 | 0 | 265.1 |  |  |  | 265.1 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 100% | Boxes(200) for teachers' to pack their classrooms at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Warehouse | Boxes | 2020-10-20 | 2020-11-17 | 2020/21 |  | XSRQ-210000002024 | 0 | 180.27 |  |  |  | 180.27 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 100% | Boxes(136) for teachers' to pack their classrooms at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Warehouse | Boxes & tapes | 2020-12-08 | 2020-12-10 | 2020/21 |  | XSRQ-210000002249 | 0 | 759.34 |  |  |  | 759.34 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 100% | Boxes(400) & packing tapes (75) for teachers' to pack their classrooms at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Move classroom | 1 | Move classroom | Mesa Robles | 21st Century classroom | Warehouse | Boxes | 2021-02-04 | 2021-02-10 | 2020/21 |  | XSRQ-210000002810 | 0 | 648.09 |  |  |  | 648.09 | 03-120779 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9221101 | 100% | Boxes(500) for teachers' to pack their classrooms at Mesa Robles | Mesa Robles-1-21st Century classroom
Newton-21st Century classroom-Move classroom | 1 | Move classroom | Newton | 21st Century classroom | Warehouse | Boxes & tapes | 2022-11-02 | 2022-11-04 | 2022/23 |  | XSRQ-230000002153 | 0 | 318.77 |  |  |  | 318.77 | 03-121295 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9241101 | 100% | Boxes(150) & packing tapes (20) for teachers' to pack their classrooms at Newton | Newton-1-21st Century classroom
Sparks MS-21st Century classroom-Move classroom | 2 | Move classroom | Sparks MS | 21st Century classroom | Warehouse | Boxes & tapes | 2022-11-02 | 2022-11-04 | 2022/23 |  | XSRQ-230000002154 | 0 | 318.77 |  |  |  | 318.77 | 03-121296 |  | 21.0 | 00036.0 | 00002 | 81000 | 4300 | 9301101 | 100% | Boxes(150) & packing tapes (20) for teachers' to pack their classrooms at Sparks MS | Sparks MS-2-21st Century classroom
Newton-21st Century classroom-Contractor | 1 | Contractor | Newton | 21st Century classroom | Williams Tree Service | Tree Service | 2020-10-27 | 2020-11-04 | 2020/21 | 21-2727 | PO2W-210000000996 | 0 | 3400 | Newton | 2020-11-04 | 000000020139894 | 3400 | 03-121295 |  | 21.0 | 00036.0 | 91001 | 85000 | 5630 | 9241101 | 100% | Removed 3 palm trees and their stumps at Newton. | Newton-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Wolverine Fence | Contractor | 2020-07-06 | 2020-11-02 | 2020/21 | 21-404 | PO2W-210000000063 | 0 | 3500 | 3955 | 2020-11-02 | 000000020139125 | 3500 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 100% | Remove approx 80 LF of 6' high chain link fencing. Cut post off at grade. Return at later date and install inside sleeves to remove post and weld to existing. Reinstall fencing at a later date at Mesa Robles. | Mesa Robles-1-21st Century classroom
Mesa Robles-21st Century classroom-Contractor | 1 | Contractor | Mesa Robles | 21st Century classroom | Wolverine Fence | Contractor | 2020-10-29 | 2021-01-15 | 2020/21 | 21-2813 | PO2W-210000001036 | 0 | 1500 | 4055 | 2021-01-15 | 000000020157276 | 1500 | 03-120779 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221101 | 100% | Relocate 2 ea. 2 7/8" post to miss grounding box cover at electric enclosure at Mesa Robles | Mesa Robles-1-21st Century classroom
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Wolverine Fence | Contractor | 2020-02-13 | 2020-11-20 | 2020/21 | 2-7893 | PO2W-200000004114 | 0 | 17340 | 4012 | 2020-11-20 | 000000020144501 | 17340 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221102 | 100% | Furnish & install 6' high chain link fence and gate at electrical 10'2" x 14'7" electrical enclosure and dividing fence and gate. Furnish and install 4' x 6' emergency exit gate with hardware at Mesa Robles (for ADA handrail). | Mesa Robles-1-Interim Housing
Mesa Robles-Interim Housing-Contractor | 1 | Contractor | Mesa Robles | Interim Housing | Wolverine Fence | Contractor | 2021-01-21 | 2021-03-24 | 2020/21 | 21-3861 | PO2W-210000001628 | 0 | 8100 | 4135 | 2021-03-24 | 000000020174734 | 8100 | 03-120417 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9221102 | 100% | Furnish and install handrail per ADA requirement for building #5, 6, & C at Mesa Robles | Mesa Robles-1-Interim Housing
Nelson-21st Century classroom-Contractor | 1 | Contractor | Nelson | 21st Century classroom | Wolverine Fence | Contractor | 2020-01-15 | 2020-04-02 | 2019/20 | 2-6912 | PO2W-200000003505 | 0 | 4725 | 3822 | 2020-04-02 | 000000020086388 | 4725 | 03-119946 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9231101 | 100% | Furnish & install 42' LF of 8' FT high chain link fencing and 1 each 4' FT swing gate -sample for Nelson room #C1. | Nelson-1-21st Century classroom
Newton-Interim Housing-Contractor | 1 | Contractor | Newton | Interim Housing | Wolverine Fence | Contractor | 2022-07-01 | 2022-08-26 | 2022/23 | 23-288 | PO2W-230000000446 | 0 | 4500 | 4636 | 2022-08-26 | 000000020601036 | 4500 | 03-120447 |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9241102 | 100% | Furnish and install 1 each 6' high x 10' wide chain link swing gate at far rear of new portable bldgs. Attach 2 7/8" sch-40 hinge post to bldg and core drill and set latch post thru asphalt. Furnish and install 19 LF of 6' high chain link fencing at front corner of new portables at Newton | Newton-1-Interim Housing
Sunset-Drinking Fountain replacement-Contractor | 4 | Contractor | Sunset | Drinking Fountain replacement | Wolverine Fence | Contractor | 2020-08-11 | 2020-10-21 | 2020/21 | 21-1261 | PO2W-210000000383 | 0 | 4800 | 3988 | 2020-10-21 | 000000020136462 | 4800 |  |  | 21.0 | 00036.0 | 91001 | 85000 | 5600 | 9311104 | 100% | Install 3 sets of handrails at 3 drinking fountains, including core drilling at Sunset. | Sunset-4-Drinking Fountain replacement
[11 empty] | TOTAL: | 9428640.3 | 62120758.45 |  |  |  | 52692118.15
Fixed Assets:
| - | A plethora of Furniture, Fixtures, & Equipment (FF&E) from Culver Newlin, Lakeshore, David M. Bertino, & Uline.
| - | Carts: 2 from Uline for District-wide use.
| - | Charging carts for Laptops (Ergotron Zip40): 680 from Arey Jones (see below for break-down by site).
| - | Desktop Computers (ThinkCentre M70q): 58 from Arey Jones. Cedarlane: 2, Grandview: 19, Newton: 20, Sparks MS: 12, & District-wide: 5
| - | Desktop Computers (ThinkCentre M720q): 121 from Lenovo & Arey Jones. Lenovo (58) - Los Altos ES: 20, Nelson: 26, & Workman ES: 12. Arey Jones (63) - Cedarlane: 25 & Mesa: 38.
| - | Document Cameras (Elmo TT-12W): 172 from CDW-G, Camcor, & Arey Jones. CDW-G (1) - Nelson: 1. Camcor (171) - Cedarlane: 25, Grandview: 19, Los Altos ES: 20, Mesa: 38, Nelson: 25, Newton: 20, Sparks MS: 12, & Workman ES: 12. Arey Jones (5) - District-wide: 5
| - | Document Cameras (Elmo Stem-Cam Mo-2) bundles: 2 from Camcor for District-wide use.
| - | Drinking Fountains: 6 from Optima. Amar: 1, Los Altos HS: 1, Mesa: 1, Sunset: 1, Wedgeworth: 1, & Winglane: 1.
| - | Equipment to repair & replace security system: 5 from ICS. Cedarlane: 1, Los Altos ES: 1, Mesa Robles: 1, Nelson: 1, & Workman ES: 1.
| - | Hydraulic Stacker: 2 from Uline for District-wide use.
| - | Laptops (Lenovo 300e): 15,842 from Arey Jones (see below for break-down by site).
| - | Monitors (ViewSonic ViewBoard IFP7550): 191 from Arey Jones. Cedarlane: 27, Gradview: 19, Los Altos ES: 20, Mesa: 43, Nelson: 26, Newton: 20, Sparks MS: 12, Workman ES: 19 & District-wide: 5.
| - | Portable Buildings: 20 from Mobile Modular. Cedarlane: 4, Los Altos ES: 4, Mesa: 8, & Newton: 4.
| - | Power Switch (N2200-ON OS6): 15 from Dell. Cedarlane: 2, Los Altos ES: 2, Mesa: 7, Nelson: 2, & Workman ES: 2.
| - | Scissor lift table: 1 from Global Industrial for District-wide use.
| - | Tack Boards: 13 from Education Products & Chatfield. Education Products (8) - District: 8 & Chatfield (5) - Workman ES: 5.
| - | Voice Amplification Systems (Topcat with Flexmike): 124 from Lightspeed. Cedarlane: 25, Los Altos ES: 20, Mesa Robles: 42, Nelson: 25, & Workman ES: 12.
| - | Web Cameras (ViewSonic ViewCam VB-CAM-001): 53 from Arey Jones. Cedarlane: 2, Grandview: 19, Newton: 20, & Sparks MS: 12.
| - | White Boards: 8 from Education Products. Grandview: 1, Nelson: 6, & Valinda: 1.
| - | Wireless Network Equipment (HPE Aruba IAP-325 Wireless access point): 180 from CDW-G for District-wide use.
|  | Arey Jones - Charging carts (Ergotron Zip40): 680.00 units |  |  |  |  | Arey Jones - Laptops (Lenovo 300e): 15,842.00 units
|  | Project Site | Unit |  |  |  | Project Site |  | Unit
|  | Amar | 15 |  |  |  | Amar |  | 0
|  | Baldwin | 27 |  |  |  | Baldwin |  | 469
|  | Bixby | 14 |  |  |  | Bixby |  | 165
|  | California | 16 |  |  |  | California |  | 253
|  | Cedarlane | 22 |  |  |  | Cedarlane |  | 615
|  | Del Valle | 16 |  |  |  | Del Valle |  | 287
|  | Fairgrove | 36 |  |  |  | Fairgrove |  | 889
|  | Grandview | 18 |  |  |  | Grandview |  | 552
|  | Grazide | 23 |  |  |  | Grazide |  | 349
|  | Kwis | 15 |  |  |  | Kwis |  | 221
|  | Lassalette | 25 |  |  |  | Lassalette |  | 465
|  | Los Altos ES | 21 |  |  |  | Los Altos ES |  | 317
|  | Los Molinos | 22 |  |  |  | Los Molinos |  | 268
|  | Los Robles | 10 |  |  |  | Los Robles |  | 141
|  | Mesa Robles | 37 |  |  |  | Mesa Robles |  | 966
|  | Nelson | 18 |  |  |  | Nelson |  | 280
|  | Newton | 17 |  |  |  | Newton |  | 686
|  | Orange Grove | 12 |  |  |  | Orange Grove |  | 428
|  | Palm | 14 |  |  |  | Palm |  | 210
|  | Sierra Vista | 9 |  |  |  | Sierra Vista |  | 352
|  | Sparks ES | 18 |  |  |  | Sparks ES |  | 329
|  | Sparks MS | 14 |  |  |  | Sparks MS |  | 585
|  | Sunset | 9 |  |  |  | Sunset |  | 213
|  | Temple | 14 |  |  |  | Temple |  | 206
|  | Valinda | 27 |  |  |  | Valinda |  | 501
|  | Wedgeworth | 24 |  |  |  | Wedgeworth |  | 255
|  | Wing Lane | 15 |  |  |  | Wing Lane |  | 201
|  | Workman ES | 18 |  |  |  | Workman ES |  | 224
|  | La Puente HS | 31 |  |  |  | La Puente HS |  | 1027
|  | Los Altos HS | 44 |  |  |  | Los Altos HS |  | 1609
|  | Wilson HS | 41 |  |  |  | Wilson HS |  | 1372
|  | Workman HS | 32 |  |  |  | Workman HS |  | 1016
|  | Valley | 6 |  |  |  | Valley |  | 176
|  | TOTAL: | 680 |  |  |  | District Office |  | 146
[7 empty] | Palm Canyon |  | 23
[7 empty] | Stimson |  | 46
[7 empty] | TOTAL: |  | 15842
Note on C1: Nety Con: Per Dan Franco @ Cumming
Note on J3351: Nety Con: Fund 12 paid for 371 units @ Amar (PO2W-2*689) Amount paid: $167,909.78 Ok, per Annie Bui

## Detail_P
MEASURE BB
Vendor | Description (Services) | Site | Project | PO Number | Estimated start date | Estimated end date | Total Exp. & Committed | Completed Amount | Committed Amount
Amazon Capital Services | Wall plates | Nelson | 21st Century classroom | PO3W-210000000037 | 2020-07-08 | 2020-07-21 | 64.06 | 64.06 | 0
Amazon Capital Services Total | [6 empty] | 64.06 | 64.06 | 0
ARC Document Solutions | Scanning/printing | Cedarlane | 21st Century classroom | PO1-200000001133 | 2020-04-28 | 2020-10-13 | 167.96 | 167.96 | 0
[6 empty] | 2020-10-20 | 1517.4 | 48.2 | 1469.2
[6 empty] | 2021-06-30 | -1469.2 | 0 | -1469.2
|  | District Office | 21st Century classroom | 19-109342 | 2019-05-13 | 2019-06-03 | 2000 | 229.19 | 1770.81
[6 empty] | 2019-06-30 | -1770.81 | 0 | -1770.81
|  |  |  | PO1-230000000596 | 2023-02-24 | 2023-12-06 | 18.86 | 18.86 | 0
[6 empty] | 2023-12-18 | -18.86 | -18.86 | 0
[6 empty] | 2027-12-09 | 598.41 | 0 | 598.41
|  |  |  | PO1-230000000663 | 2023-05-23 | 2027-12-09 | 10000 | 0 | 10000
|  | Grandview | 21st Century classroom | PO1-210000000492 | 2020-10-05 | 2022-08-10 | 40.96 | 40.96 | 0
[6 empty] | 2022-08-18 | 97.62 | 97.62 | 0
[6 empty] | 2022-08-22 | 6.17 | 6.17 | 0
[6 empty] | 2022-08-31 | 21.57 | 21.57 | 0
[6 empty] | 2023-03-07 | 1179.62 | 1179.62 | 0
|  |  |  | PO1-230000000596 | 2023-02-24 | 2023-03-07 | 10.35 | 10.35 | 0
[6 empty] | 2023-06-06 | 764.42 | 764.42 | 0
[6 empty] | 2023-12-01 | 737.36 | 737.36 | 0
|  | La Puente HS | 21st Century classroom | PO1-230000000596 | 2023-02-24 | 2023-12-06 | 126.62 | 126.62 | 0
|  | Los Altos ES | 21st Century classroom | PO1-200000000625 | 2019-10-01 | 2020-04-22 | 728.6 | 728.6 | 0
|  | Los Altos HS | 21st Century classroom | PO1-230000000596 | 2023-02-24 | 2023-12-01 | 349.34 | 349.34 | 0
|  | Los Molinos | Fire Alarm replacement | PO1-210000000492 | 2020-10-05 | 2021-02-08 | 422.21 | 422.21 | 0
|  | Mesa Robles | 21st Century classroom | PO1-200000001133 | 2020-04-28 | 2020-10-13 | 167.95 | 167.95 | 0
[6 empty] | 2020-10-20 | 48.19 | 48.19 | 0
|  |  | Interim Housing | PO1-200000001133 | 2020-04-28 | 2020-06-17 | 1661.08 | 1661.08 | 0
|  | Nelson | 21st Century classroom | PO1-200000000625 | 2019-10-01 | 2020-04-30 | 728.6 | 728.6 | 0
|  | Newton | 21st Century classroom | PO1-210000000492 | 2020-10-05 | 2022-08-10 | 40.96 | 40.96 | 0
[6 empty] | 2022-08-18 | 97.62 | 97.62 | 0
[6 empty] | 2022-08-22 | 6.17 | 6.17 | 0
[6 empty] | 2022-08-31 | 21.58 | 21.58 | 0
[6 empty] | 2023-03-07 | 1179.63 | 1179.63 | 0
|  |  |  | PO1-230000000596 | 2023-02-24 | 2023-03-07 | 10.34 | 10.34 | 0
[6 empty] | 2023-06-06 | 764.42 | 764.42 | 0
[6 empty] | 2023-12-01 | 388.02 | 388.02 | 0
|  |  | Interim Housing | PO1-210000000492 | 2020-10-05 | 2021-09-08 | 186.94 | 186.94 | 0
[6 empty] | 2022-01-24 | 353 | 353 | 0
|  | Sparks MS | 21st Century classroom | PO1-210000000492 | 2020-10-05 | 2022-08-10 | 40.97 | 40.97 | 0
[6 empty] | 2022-08-18 | 97.62 | 97.62 | 0
[6 empty] | 2022-08-22 | 6.16 | 6.16 | 0
[6 empty] | 2022-08-31 | 21.57 | 21.57 | 0
[6 empty] | 2023-03-07 | 1179.63 | 1179.63 | 0
|  |  |  | PO1-230000000596 | 2023-02-24 | 2023-03-07 | 10.34 | 10.34 | 0
[6 empty] | 2023-06-06 | 764.41 | 764.41 | 0
[6 empty] | 2023-12-01 | 349.35 | 349.35 | 0
|  | Workman ES | 21st Century classroom | PO1-200000000625 | 2019-10-01 | 2020-04-22 | 78.14 | 78.14 | 0
[6 empty] | 2020-04-30 | 275.8 | 275.8 | 0
[6 empty] | 2020-05-06 | 188.86 | 188.86 | 0
|  |  |  | PO1-200000001133 | 2020-04-28 | 2020-05-06 | 185.8 | 185.8 | 0
[6 empty] | 2020-08-17 | 1251.62 | 1251.62 | 0
|  | Workman HS | 21st Century classroom | PO1-230000000596 | 2023-02-24 | 2023-12-06 | 126.62 | 126.62 | 0
ARC Document Solutions Total | [6 empty] | 25759.99 | 15161.58 | 10598.41
Arey Jones Educational Solutions | Charging carts | Amar | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-21 | 19593.92 | 19593.92 | 0
|  | Baldwin | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 18204.53 | 18204.53 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-11-07 | 16981.39 | 16981.39 | 0
|  | Bixby | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 6501.61 | 6501.61 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 11702.91 | 11702.91 | 0
|  | California | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-21 | 20900.18 | 20900.18 | 0
|  | Cedarlane | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1300.32 | 1300.32 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-15 | 27306.79 | 27306.79 | 0
|  | Del Valle | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 20900.18 | 20900.18 | 0
|  | Fairgrove | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1306.26 | 1306.26 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-11 | 43106.72 | 43106.72 | 0
[6 empty] | 2019-10-15 | 2612.43 | 2612.43 | 0
|  | Grandview | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-22 | 23405.82 | 23405.82 | 0
|  | Grazide | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 13003.23 | 13003.23 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 16904.22 | 16904.22 | 0
|  | Kwis | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 10402.58 | 10402.58 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 9102.26 | 9102.26 | 0
|  | La Puente HS | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1306.26 | 1306.26 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 39187.83 | 39187.83 | 0
|  | Lassalette | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 20900.19 | 20900.19 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-11-07 | 11756.35 | 11756.35 | 0
|  | Los Altos ES | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-22 | 27306.79 | 27306.79 | 0
|  | Los Altos HS | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1300.32 | 1300.32 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-11-07 | 55913.91 | 55913.91 | 0
|  | Los Molinos | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-22 | 28607.12 | 28607.12 | 0
|  | Los Robles | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-15 | 13003.22 | 13003.22 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-22 | 48111.97 | 48111.97 | 0
|  | Nelson | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-22 | 23512.7 | 23512.7 | 0
|  | Newton | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1300.32 | 1300.32 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-15 | 20805.18 | 20805.18 | 0
|  | Orange Grove | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1300.32 | 1300.32 | 0
[6 empty] | 2019-10-22 | 1300.32 | 1300.32 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 13003.23 | 13003.23 | 0
|  | Palm | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 9102.26 | 9102.26 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 9102.26 | 9102.26 | 0
|  | Sierra Vista | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 11756.35 | 11756.35 | 0
|  | Sparks ES | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-11 | 23512.7 | 23512.7 | 0
|  | Sparks MS | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-04 | 18287.65 | 18287.65 | 0
|  | Sunset | 21st Century classroom | PO2W-200000002766 | 2019-07-01 | 2019-12-06 | 1306.26 | 1306.26 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-22 | 10450.09 | 10450.09 | 0
|  | Temple | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-11 | 18287.65 | 18287.65 | 0
|  | Valinda | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1300.32 | 1300.32 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-11 | 33962.79 | 33962.79 | 0
|  | Valley | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-21 | 7801.94 | 7801.94 | 0
|  | Wedgeworth | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 31207.76 | 31207.76 | 0
|  | Wilson HS | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 53313.26 | 53313.26 | 0
|  | Wing Lane | 21st Century classroom | PO3W-200000000730 | 2019-07-01 | 2019-10-04 | 19593.91 | 19593.91 | 0
|  | Workman ES | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1306.26 | 1306.26 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-10-08 | 22206.44 | 22206.44 | 0
|  | Workman HS | 21st Century classroom | PO3W-200000000448 | 2019-07-01 | 2019-09-23 | 1300.32 | 1300.32 | 0
|  |  |  | PO3W-200000000730 | 2019-07-01 | 2019-11-07 | 40310.03 | 40310.03 | 0
| Desktop computer(s) | Cedarlane | 21st Century classroom | PO3W-210000001078 | 2020-12-03 | 2021-01-22 | 26352.28 | 26352.28 | 0
[6 empty] | 2021-03-04 | -2.74 | -2.74 | 0
|  |  |  | PO3W-220000000256 | 2021-08-18 | 2022-02-08 | 2148.06 | 2148.06 | 0
|  | District Office | 21st Century classroom | PO3W-240000000370 | 2023-08-15 | 2023-11-03 | 5965.07 | 5965.07 | 0
|  | Grandview | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 21054.09 | 21054.09 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000001078 | 2020-12-03 | 2021-01-22 | 40055.44 | 40055.44 | 0
[6 empty] | 2021-03-04 | -4.16 | -4.16 | 0
|  | Newton | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 22162.19 | 22162.19 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 13297.32 | 13297.32 | 0
| Document camera(s) | District Office | 21st Century classroom | PO3W-240000000370 | 2023-08-15 | 2023-11-03 | 3602.93 | 3602.93 | 0
| Laptops | Baldwin | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-08 | 30775.92 | 30775.92 | 0
[6 empty] | 2019-10-10 | 181485.61 | 181485.61 | 0
|  | Bixby | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 74384.41 | 74384.41 | 0
|  | California | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-08 | 8146.57 | 8146.57 | 0
[6 empty] | 2019-10-21 | 94590.68 | 94590.68 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-11-13 | 11767.26 | 11767.26 | 0
|  | Cedarlane | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 33811.1 | 33811.1 | 0
[6 empty] | 2019-10-21 | 9016.29 | 9016.29 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 234423.62 | 234423.62 | 0
|  | Del Valle | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 25797.45 | 25797.45 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-10 | 104095.01 | 104095.01 | 0
|  | District Office | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 19385.03 | 19385.03 | 0
|  |  |  | PO2W-200000004388 | 2020-02-07 | 2020-03-06 | 1349.45 | 1349.45 | 0
[6 empty] | 2020-04-23 | 1349.45 | 1349.45 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-11-21 | 43729.02 | 43729.02 | 0
|  | Fairgrove | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 35754.36 | 35754.36 | 0
[6 empty] | 2019-10-21 | 20366.42 | 20366.42 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 346229.06 | 346229.06 | 0
|  | Grandview | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 12172 | 12172 | 0
[6 empty] | 2019-10-21 | 9016.29 | 9016.29 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 227661.4 | 227661.4 | 0
|  | Grazide | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 157334.31 | 157334.31 | 0
|  | Kwis | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 99630.05 | 99630.05 | 0
|  | La Puente HS | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 464806.85 | 464806.85 | 0
|  | Lassalette | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 210452.96 | 210452.96 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 9917.92 | 9917.92 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 132990.32 | 132990.32 | 0
|  | Los Altos HS | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 725360.76 | 725360.76 | 0
|  | Los Molinos | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 10368.74 | 10368.74 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 110449.59 | 110449.59 | 0
|  | Los Robles | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 4958.96 | 4958.96 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 58605.9 | 58605.9 | 0
|  | Mesa Robles | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 20737.48 | 20737.48 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 414749.48 | 414749.48 | 0
|  | Nelson | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 9051.74 | 9051.74 | 0
[6 empty] | 2019-10-21 | 18103.47 | 18103.47 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 99569.15 | 99569.15 | 0
|  | Newton | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 27499.7 | 27499.7 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 281759.15 | 281759.15 | 0
|  | Orange Grove | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 174916.09 | 174916.09 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 18032.58 | 18032.58 | 0
|  | Palm | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 94671.08 | 94671.08 | 0
|  | Palm Canyon | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 1352.45 | 1352.45 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 9016.29 | 9016.29 | 0
|  | Sierra Vista | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 159310.62 | 159310.62 | 0
|  | Sparks ES | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-08 | 8599.15 | 8599.15 | 0
[6 empty] | 2019-10-21 | 9051.74 | 9051.74 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 131250.23 | 131250.23 | 0
|  | Sparks MS | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-08 | 9051.74 | 9051.74 | 0
[6 empty] | 2019-10-10 | 255711.66 | 255711.66 | 0
|  | Stimson | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 2704.88 | 2704.88 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 18032.58 | 18032.58 | 0
|  | Sunset | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 5883.63 | 5883.63 | 0
[6 empty] | 2019-11-12 | 9051.74 | 9051.74 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 81465.64 | 81465.64 | 0
|  | Temple | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-08 | 7241.39 | 7241.39 | 0
[6 empty] | 2019-10-21 | 9051.74 | 9051.74 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 76939.79 | 76939.79 | 0
|  | Valinda | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-08 | 32133.68 | 32133.68 | 0
[6 empty] | 2019-10-21 | 9051.74 | 9051.74 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 185560.67 | 185560.67 | 0
|  | Valley | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 7213.03 | 7213.03 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-22 | 72130.34 | 72130.34 | 0
|  | Wedgeworth | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 114957.74 | 114957.74 | 0
|  | Wilson HS | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 614009.56 | 614009.56 | 0
[6 empty] | 2019-10-21 | 4508.15 | 4508.15 | 0
|  | Wing Lane | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-08 | 16293.13 | 16293.13 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-10 | 74676.86 | 74676.86 | 0
|  | Workman ES | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 28965.57 | 28965.57 | 0
|  |  |  | PO3W-200000000332 | 2019-07-01 | 2019-10-10 | 72413.92 | 72413.92 | 0
|  | Workman HS | 21st Century classroom | PO2W-200000000689, 19-109955 | 2019-07-01 | 2019-10-10 | 458027.67 | 458027.67 | 0
| ViewSonic monitor(s) | Cedarlane | 21st Century classroom | PO3W-210000001075 | 2020-12-02 | 2021-03-04 | 13871.18 | 13871.18 | 0
[6 empty] | 2021-04-09 | 40746.58 | 40746.58 | 0
|  |  |  | PO3W-220000000256 | 2021-08-18 | 2022-02-08 | 4357.42 | 4357.42 | 0
|  | District Office | 21st Century classroom | PO3W-240000000370 | 2023-08-15 | 2023-11-03 | 13163.81 | 13163.81 | 0
|  | Grandview | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 40841.02 | 40841.02 | 0
|  | Los Altos ES | 21st Century classroom | PO3W-210000000003 | 2020-07-01 | 2020-10-01 | 43694.21 | 43694.21 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000001075 | 2020-12-02 | 2021-03-04 | 21084.19 | 21084.19 | 0
[6 empty] | 2021-04-09 | 61934.82 | 61934.82 | 0
|  |  |  | PO3W-210000003053 | 2021-06-14 | 2022-02-04 | 10923.55 | 10923.55 | 0
|  | Nelson | 21st Century classroom | PO3W-200000003014 | 2020-06-05 | 2020-07-01 | 2184.71 | 2184.71 | 0
|  |  |  | PO3W-210000000003 | 2020-07-01 | 2020-09-16 | 21946.59 | 21946.59 | 0
[6 empty] | 2020-10-01 | 32770.66 | 32770.66 | 0
|  | Newton | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 42990.55 | 42990.55 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 25794.32 | 25794.32 | 0
|  | Workman ES | 21st Century classroom | PO3W-210000000003 | 2020-07-01 | 2020-10-01 | 26216.53 | 26216.53 | 0
|  |  |  | PO3W-210000003054 | 2021-06-14 | 2022-02-11 | 15362.62 | 15362.62 | 0
| Web camera(s) | Cedarlane | 21st Century classroom | PO3W-220000000256 | 2021-08-18 | 2022-02-08 | 175.21 | 175.21 | 0
|  | Grandview | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 1004.27 | 1004.27 | 0
|  | Newton | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 1057.11 | 1057.11 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000001319 | 2022-11-18 | 2023-01-26 | 634.26 | 634.26 | 0
| Power supply | Grandview | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-06-26 | 332.88 | 332.88 | 0
|  | Newton | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-06-26 | 350.4 | 350.4 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-06-26 | 210.24 | 210.24 | 0
| Mounting bracket | Grandview | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-05-04 | 624.15 | 624.15 | 0
|  | Newton | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-05-04 | 657 | 657 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-05-04 | 394.2 | 394.2 | 0
| Keyboard & mouse | Grandview | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-05-04 | 811.4 | 811.4 | 0
|  | Newton | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-05-04 | 854.1 | 854.1 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000002778 | 2023-03-31 | 2023-05-04 | 512.46 | 512.46 | 0
Arey Jones Educational Solutions Total | [6 empty] | 8599020.56 | 8599020.56 | 0
Avia Communications, Inc. | Printing & posting of POS/Os | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-07-11 | 2017-07-11 | 1350.74 | 1350.74 | 0
Avia Communications, Inc. Total | [6 empty] | 1350.74 | 1350.74 | 0
AWP Marketing and Printing Services LLC | Decal | District Office | 21st Century classroom | PO2W-220000001278 | 2022-01-06 | 2022-01-24 | 455.52 | 455.52 | 0
|  |  |  | (blank) | 2024-01-18 | 2025-12-09 | 501.51 | 0 | 501.51
AWP Marketing and Printing Services LLC Total | [6 empty] | 957.03 | 455.52 | 501.51
Bay Alarm Company | Alarm for portables | Los Altos ES | Interim Housing | PO2W-220000001857 | 2022-03-23 | 2022-04-04 | 159 | 159 | 0
[6 empty] | 2023-07-13 | 318 | 318 | 0
[6 empty] | 2023-07-17 | -318 | -318 | 0
[6 empty] | 2023-07-18 | 2623.5 | 0 | 2623.5
[6 empty] | 2023-07-19 | -2623.5 | 0 | -2623.5
Bay Alarm Company Total | [6 empty] | 159 | 159 | 0
California Municipal Statistics, Inc. | Demographic data | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-07-11 | 2017-07-11 | 1700 | 1700 | 0
California Municipal Statistics, Inc. Total | [6 empty] | 1700 | 1700 | 0
Camcor Inc. | Document camera(s) | Cedarlane | 21st Century classroom | PO3W-210000001076 | 2020-12-02 | 2021-04-14 | 15519.98 | 15519.98 | 0
|  | Grandview | 21st Century classroom | PO3W-230000001318 | 2022-11-17 | 2023-01-09 | 12031.09 | 12031.09 | 0
|  | Los Altos ES | 21st Century classroom | PO3W-210000000006 | 2020-07-01 | 2020-07-16 | 11954.12 | 11954.12 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000001076 | 2020-12-02 | 2021-04-14 | 23590.37 | 23590.37 | 0
|  | Nelson | 21st Century classroom | PO3W-210000000006 | 2020-07-01 | 2020-07-16 | 14942.64 | 14942.64 | 0
|  | Newton | 21st Century classroom | PO3W-230000001318 | 2022-11-17 | 2023-01-09 | 12347.7 | 12347.7 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000001318 | 2022-11-17 | 2023-01-09 | 7281.97 | 7281.97 | 0
|  | Workman ES | 21st Century classroom | PO3W-210000000006 | 2020-07-01 | 2020-07-16 | 7172.46 | 7172.46 | 0
| Document camera(s) bundles | District Office | 21st Century classroom | PO3W-220000003018 | 2022-05-18 | 2022-06-03 | 1347.66 | 1347.66 | 0
Camcor Inc. Total | [6 empty] | 106187.99 | 106187.99 | 0
CDW-G Government Inc. | Document camera(s) | Nelson | 21st Century classroom | PO3W-210000000002 | 2020-07-01 | 2020-08-21 | 706.28 | 706.28 | 0
| Wall plates | Cedarlane | 21st Century classroom | PO3W-210000001145 | 2020-12-09 | 2021-03-05 | 766.5 | 766.5 | 0
|  | Los Altos ES | 21st Century classroom | PO3W-210000001145 | 2020-12-09 | 2021-03-05 | 643.86 | 643.86 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000001145 | 2020-12-09 | 2021-03-05 | 1226.4 | 1226.4 | 0
|  | Nelson | 21st Century classroom | PO3W-210000001145 | 2020-12-09 | 2021-03-05 | 613.2 | 613.2 | 0
|  | Workman ES | 21st Century classroom | PO3W-210000001145 | 2020-12-09 | 2021-03-05 | 582.54 | 582.54 | 0
| Wireless network equipment | District Office | 21st Century classroom | PO2W-200000000348 | 2019-07-01 | 2019-10-04 | 56459.52 | 56459.52 | 0
[6 empty] | 2019-10-08 | 312057.91 | 312057.91 | 0
CDW-G Government Inc. Total | [6 empty] | 373056.21 | 373056.21 | 0
Chalmers Construction Services, Inc. | Contractor | Grandview | 21st Century classroom | PO2W-230000001268 | 2022-09-23 | 2022-12-16 | 196317.5 | 196317.5 | 0
[6 empty] | 2023-01-23 | 160692.5 | 160692.5 | 0
[6 empty] | 2023-03-07 | 104737.5 | 104737.5 | 0
[6 empty] | 2023-04-10 | 124550.48 | 124550.48 | 0
[6 empty] | 2023-04-21 | 324235 | 324235 | 0
[6 empty] | 2023-05-01 | -124550.48 | -124550.48 | 0
[6 empty] | 2023-05-04 | 124550.48 | 124550.48 | 0
[6 empty] | 2023-05-18 | 218903.75 | 218903.75 | 0
[6 empty] | 2023-06-27 | 155990 | 155990 | 0
[6 empty] | 2023-08-04 | 142890.01 | 142890.01 | 0
[6 empty] | 2023-08-22 | 746961.26 | 746961.26 | 0
[6 empty] | 2023-11-06 | 21517.5 | 21517.5 | 0
[6 empty] | 2024-01-19 | 218690.54 | 218690.54 | 0
[6 empty] | 2027-12-09 | 324513.96 | 0 | 324513.96
|  | Mesa Robles | 21st Century classroom | PO2W-210000000935 | 2020-10-16 | 2020-11-30 | 194607.5 | 194607.5 | 0
[6 empty] | 2021-01-07 | 171275.5 | 171275.5 | 0
[6 empty] | 2021-02-11 | 547257 | 547257 | 0
[6 empty] | 2021-03-16 | 299915 | 299915 | 0
[6 empty] | 2021-04-06 | 476649.8 | 476649.8 | 0
[6 empty] | 2021-05-17 | 481460 | 481460 | 0
[6 empty] | 2021-06-17 | 492670 | 492670 | 0
[6 empty] | 2021-07-08 | 134615 | 134615 | 0
[6 empty] | 2021-09-09 | 143700.2 | 143700.2 | 0
[6 empty] | 2022-01-05 | 130557.95 | 130557.95 | 0
[6 empty] | 2022-08-05 | 24292.05 | 24292.05 | 0
|  |  |  | PO2W-220000001552, PO2W-210000000935 | 2021-12-16 | 2022-08-05 | 137429.42 | 137429.42 | 0
|  | Newton | 21st Century classroom | PO2W-230000001269 | 2022-09-23 | 2022-12-12 | 120966.35 | 120966.35 | 0
[6 empty] | 2023-01-23 | 32917.5 | 32917.5 | 0
[6 empty] | 2023-03-07 | 62937.5 | 62937.5 | 0
[6 empty] | 2023-04-10 | 152276.97 | 152276.97 | 0
[6 empty] | 2023-04-21 | 67640.01 | 67640.01 | 0
[6 empty] | 2023-05-01 | -152276.97 | -152276.97 | 0
[6 empty] | 2023-05-04 | 152276.97 | 152276.97 | 0
[6 empty] | 2023-05-18 | 218222.61 | 218222.61 | 0
[6 empty] | 2023-06-27 | 142063.96 | 142063.96 | 0
[6 empty] | 2023-08-04 | 397329.43 | 397329.43 | 0
[6 empty] | 2023-08-22 | 407181.88 | 407181.88 | 0
[6 empty] | 2023-11-06 | 23476.88 | 23476.88 | 0
[6 empty] | 2024-01-19 | 276738.47 | 276738.47 | 0
[6 empty] | 2027-12-09 | 213248.44 | 0 | 213248.44
|  |  | Interim Housing | PO2W-220000001166 | 2021-12-08 | 2022-03-11 | 117420 | 117420 | 0
[6 empty] | 2022-05-04 | 73435 | 73435 | 0
[6 empty] | 2022-05-06 | 86260 | 86260 | 0
[6 empty] | 2022-08-19 | 87591.8 | 87591.8 | 0
[6 empty] | 2022-12-07 | 11453.39 | 11453.39 | 0
[6 empty] | 2022-12-12 | 22339.81 | 19797.9 | 2541.91
[6 empty] | 2022-12-13 | -2541.91 | 0 | -2541.91
|  | Sparks MS | 21st Century classroom | PO2W-230000001271 | 2022-09-23 | 2022-12-16 | 169622.5 | 169622.5 | 0
[6 empty] | 2023-01-23 | 67070 | 67070 | 0
[6 empty] | 2023-03-07 | 51395 | 51395 | 0
[6 empty] | 2023-04-10 | 109369.54 | 109369.54 | 0
[6 empty] | 2023-04-21 | 325517.41 | 325517.41 | 0
[6 empty] | 2023-05-01 | -109369.54 | -109369.54 | 0
[6 empty] | 2023-05-04 | 109369.54 | 109369.54 | 0
[6 empty] | 2023-05-18 | 88373.66 | 88373.66 | 0
[6 empty] | 2023-06-27 | 153140 | 153140 | 0
[6 empty] | 2023-08-04 | 417040.26 | 417040.26 | 0
[6 empty] | 2023-08-22 | 151049.91 | 151049.91 | 0
[6 empty] | 2023-11-06 | 14962.5 | 14962.5 | 0
[6 empty] | 2024-01-19 | 36255.04 | 36255.04 | 0
[6 empty] | 2027-12-09 | 141204.18 | 0 | 141204.18
|  | Workman HS | 21st Century classroom | (blank) | 2024-01-09 | 2028-06-01 | 2080000 | 0 | 2080000
Chalmers Construction Services, Inc. Total | [6 empty] | 12290387.51 | 9531420.93 | 2758966.58
Chatfield-Clarke | Tack boards | Workman ES | 21st Century classroom | PO2W-210000000770 | 2020-09-23 | 2020-11-03 | 413.91 | 413.91 | 0
Chatfield-Clarke Total | [6 empty] | 413.91 | 413.91 | 0
Converse Consultants | Geotechnical | Cedarlane | Interim Housing | PO2W-210000001098 | 2020-11-06 | 2021-02-05 | 6702.5 | 6702.5 | 0
[6 empty] | 2021-04-19 | 1650 | 1650 | 0
[6 empty] | 2021-05-26 | 1732.5 | 1732.5 | 0
[6 empty] | 2021-09-15 | 232.5 | 232.5 | 0
[6 empty] | 2023-06-30 | 6602.5 | 0 | 6602.5
[6 empty] | 2023-07-11 | -6602.5 | 0 | -6602.5
|  | Grandview | 21st Century classroom | PO2W-230000001453 | 2022-11-02 | 2023-05-10 | 1760 | 1760 | 0
[6 empty] | 2025-12-09 | 320 | 0 | 320
|  | Los Altos ES | 21st Century classroom | PO2W-200000005542 | 2020-06-05 | 2020-08-17 | 779.5 | 779.5 | 0
[6 empty] | 2020-12-04 | 342.5 | 342.5 | 0
[6 empty] | 2021-02-05 | 1153.5 | 1153.5 | 0
[6 empty] | 2021-03-24 | 9223.5 | 9223.5 | 0
[6 empty] | 2021-04-19 | 880 | 880 | 0
[6 empty] | 2023-06-30 | 11301 | 0 | 11301
[6 empty] | 2023-07-11 | -11301 | 0 | -11301
|  |  | Interim Housing | PO2W-200000000203 | 2019-07-01 | 2019-12-11 | 5280.5 | 5280.5 | 0
[6 empty] | 2023-06-30 | 9249.5 | 0 | 9249.5
[6 empty] | 2023-07-11 | -9249.5 | 0 | -9249.5
|  | Mesa Robles | Interim Housing | PO2W-200000004115 | 2020-02-13 | 2020-06-22 | 7782.5 | 7782.5 | 0
[6 empty] | 2020-10-13 | 1050.5 | 1050.5 | 0
[6 empty] | 2021-04-19 | 1052.5 | 1052.5 | 0
[6 empty] | 2021-09-09 | 1445 | 1445 | 0
[6 empty] | 2023-06-30 | 2209.5 | 0 | 2209.5
[6 empty] | 2023-07-11 | -2209.5 | 0 | -2209.5
|  | Nelson | 21st Century classroom | PO2W-200000005543 | 2020-06-05 | 2021-02-05 | 1117.5 | 1117.5 | 0
[6 empty] | 2023-06-30 | 19732.5 | 0 | 19732.5
[6 empty] | 2023-07-11 | -19732.5 | 0 | -19732.5
|  | Newton | 21st Century classroom | PO2W-230000001453 | 2022-11-02 | 2023-04-13 | 540 | 540 | 0
[6 empty] | 2025-12-09 | 855 | 0 | 855
|  |  | Interim Housing | PO2W-230000000005 | 2022-07-01 | 2022-08-01 | 750 | 750 | 0
|  |  |  | PO2W-230000001454, PO2W-230000000005 | 2022-07-01 | 2023-06-30 | 435 | 0 | 435
[6 empty] | 2023-07-11 | -435 | 0 | -435
|  | Sparks MS | 21st Century classroom | PO2W-230000001453 | 2022-11-02 | 2023-04-13 | 2061.5 | 2061.5 | 0
[6 empty] | 2025-12-09 | 18.5 | 0 | 18.5
|  | Workman ES | 21st Century classroom | PO2W-200000005544 | 2020-06-05 | 2021-02-05 | 507.5 | 507.5 | 0
[6 empty] | 2023-06-30 | 16092.5 | 0 | 16092.5
[6 empty] | 2023-07-11 | -16092.5 | 0 | -16092.5
| Masonry inspection | Los Altos ES | 21st Century classroom | PO2W-210000001034 | 2020-10-28 | 2021-09-09 | 2537.5 | 2537.5 | 0
|  | Nelson | 21st Century classroom | PO2W-210000001034 | 2020-10-28 | 2021-10-01 | 5787.5 | 5787.5 | 0
Converse Consultants Total | [6 empty] | 55562.5 | 54369 | 1193.5
Culver Newlin, Inc. | Furniture | Cedarlane | 21st Century classroom | PO2W-210000001657 | 2021-01-28 | 2021-03-24 | 13783.38 | 13783.38 | 0
[6 empty] | 2021-08-16 | 62853 | 62853 | 0
|  |  |  | PO2W-210000001659 | 2021-01-28 | 2021-03-24 | 32607.76 | 32607.76 | 0
[6 empty] | 2021-04-19 | 5324.99 | 5324.99 | 0
|  |  |  | PO2W-210000002168 | 2021-04-29 | 2021-08-16 | 223009.81 | 223009.81 | 0
|  |  |  | PO2W-210000002280 | 2021-05-10 | 2021-08-16 | 54287.55 | 54287.55 | 0
[6 empty] | 2021-09-30 | 3728.48 | 3728.48 | 0
|  |  |  | PO2W-210000002281 | 2021-05-10 | 2021-08-16 | 38677.35 | 38677.35 | 0
|  |  |  | PO2W-220000001344 | 2022-01-14 | 2022-05-20 | 28827.85 | 28827.85 | 0
|  |  | Interim Housing | PO2W-200000004768 | 2020-03-17 | 2020-12-18 | 20580.53 | 20580.53 | 0
[6 empty] | 2021-05-07 | 11760.3 | 11760.3 | 0
[6 empty] | 2021-05-25 | 2940.07 | 2940.07 | 0
|  | District Office | 21st Century classroom | PO2W-200000004768 | 2020-03-17 | 2020-06-17 | 76394.76 | 76394.76 | 0
|  | Grandview | 21st Century classroom | PO3W-230000000771 | 2022-09-27 | 2023-05-19 | 151942.56 | 151942.56 | 0
[6 empty] | 2023-08-22 | 90681.47 | 90681.47 | 0
[6 empty] | 2024-01-04 | 105963.38 | 105963.38 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-200000004768 | 2020-03-17 | 2021-05-07 | 156387.52 | 156387.52 | 0
[6 empty] | 2021-05-25 | 192.72 | 192.72 | 0
[6 empty] | 2021-05-31 | 742.42 | 0 | 742.42
[6 empty] | 2021-06-01 | -742.42 | 0 | -742.42
|  |  |  | PO2W-210000001121 | 2020-11-06 | 2021-02-09 | 169275.1 | 169275.1 | 0
|  |  |  | PO2W-220000000413 | 2021-09-07 | 2021-11-16 | 983.31 | 983.31 | 0
|  |  |  | PO2W-220000001345 | 2021-09-07 | 2022-04-20 | 19218.56 | 19218.56 | 0
|  |  | Interim Housing | PO2W-200000004768 | 2020-03-17 | 2021-05-07 | 2450.06 | 2450.06 | 0
[6 empty] | 2021-05-25 | 8036.2 | 8036.2 | 0
|  | Los Molinos | 21st Century classroom | PO3W-200000001600 | 2019-10-22 | 2020-04-15 | 21169.42 | 21169.42 | 0
|  | Mesa Robles | 21st Century classroom | PO2W-200000004768 | 2020-03-17 | 2021-05-07 | 233.02 | 233.02 | 0
|  |  |  | PO2W-210000001658 | 2021-01-28 | 2021-03-23 | 25383.81 | 25383.81 | 0
[6 empty] | 2021-08-16 | 51252.57 | 51252.57 | 0
|  |  |  | PO2W-210000001660 | 2021-01-28 | 2021-03-24 | 97823.29 | 97823.29 | 0
[6 empty] | 2021-04-19 | 15974.96 | 15974.96 | 0
|  |  |  | PO2W-210000002169 | 2021-04-29 | 2021-08-16 | 148553.31 | 148553.31 | 0
[6 empty] | 2021-09-30 | 6156.09 | 6156.09 | 0
|  |  |  | PO2W-210000002282 | 2021-05-10 | 2021-08-16 | 77354.7 | 77354.7 | 0
|  |  |  | PO2W-210000002283 | 2021-05-10 | 2021-08-16 | 232064.09 | 232064.09 | 0
|  |  |  | PO2W-220000000464 | 2021-09-07 | 2022-01-24 | 40866.17 | 40866.17 | 0
|  |  |  | PO2W-220000001346 | 2022-01-14 | 2022-05-20 | 44442.93 | 44442.93 | 0
|  |  | Interim Housing | PO2W-200000004768 | 2020-03-17 | 2020-09-28 | 73150.29 | 73150.29 | 0
[6 empty] | 2021-05-07 | 12985.33 | 12985.33 | 0
[6 empty] | 2021-05-25 | 715.92 | 715.92 | 0
|  | Nelson | 21st Century classroom | PO2W-200000004768 | 2020-03-17 | 2020-08-24 | 109597.17 | 109597.17 | 0
[6 empty] | 2021-05-07 | 28994.79 | 28994.79 | 0
[6 empty] | 2021-05-25 | 192.72 | 192.72 | 0
[6 empty] | 2021-06-01 | 8499.94 | 8499.94 | 0
[6 empty] | 2021-06-02 | 3443.01 | 0 | 3443.01
[6 empty] | 2021-06-03 | -3443.01 | 0 | -3443.01
|  |  |  | PO2W-210000001122 | 2020-11-06 | 2021-02-09 | 131599.53 | 131599.53 | 0
|  |  |  | PO2W-220000001347 | 2022-01-14 | 2022-05-20 | 19306.32 | 19306.32 | 0
|  | Newton | 21st Century classroom | PO3W-230000000772 | 2022-09-27 | 2023-03-21 | 75971.28 | 75971.28 | 0
[6 empty] | 2023-08-04 | 56978.46 | 56978.46 | 0
[6 empty] | 2023-09-20 | 75971.27 | 75971.27 | 0
[6 empty] | 2023-10-02 | 36378.09 | 36378.09 | 0
[6 empty] | 2023-12-06 | 39593.19 | 39593.19 | 0
[6 empty] | 2023-12-19 | 66876.75 | 66876.75 | 0
[6 empty] | 2024-01-04 | 18992.82 | 18992.82 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000000773 | 2022-09-27 | 2023-05-18 | 170315.55 | 170315.55 | 0
[6 empty] | 2023-08-21 | 95101.27 | 95101.27 | 0
|  | Workman ES | 21st Century classroom | PO2W-200000004768 | 2020-03-17 | 2020-12-18 | 80713.17 | 80713.17 | 0
[6 empty] | 2021-05-07 | 20837.74 | 20837.74 | 0
[6 empty] | 2021-05-25 | 2266.65 | 2266.65 | 0
|  |  |  | PO2W-210000001123 | 2020-11-06 | 2021-04-19 | 113360.81 | 113360.81 | 0
|  |  |  | PO2W-210000001743 | 2021-02-05 | 2021-05-25 | 5321.7 | 5321.7 | 0
|  |  |  | PO2W-220000001348 | 2022-01-14 | 2022-03-23 | 16893.03 | 16893.03 | 0
Culver Newlin, Inc. Total | [6 empty] | 3301794.86 | 3301794.86 | 0
Cumming Construction Management, Inc. | Construction mgmt services | Baldwin | 21st Century classroom | PO1-220000000334 | 2021-07-01 | 2021-09-08 | 960 | 960 | 0
[6 empty] | 2021-09-29 | 1760 | 1760 | 0
[6 empty] | 2023-10-10 | 292142 | 0 | 292142
[6 empty] | 2023-10-11 | -292142 | 0 | -292142
|  |  |  | PO2W-220000000862, PO1-220000000334 | 2021-11-02 | 2021-11-08 | 5650 | 5650 | 0
|  | California | 21st Century classroom | PO1-220000000334 | 2021-07-01 | 2021-09-08 | 800 | 800 | 0
[6 empty] | 2021-09-29 | 7360 | 7360 | 0
[6 empty] | 2023-10-10 | 170210 | 0 | 170210
[6 empty] | 2023-10-11 | -170210 | 0 | -170210
|  |  |  | PO2W-220000000862, PO1-220000000334 | 2021-11-02 | 2021-11-08 | 9450 | 9450 | 0
|  | Cedarlane | 21st Century classroom | PO1-200000000640 | 2019-10-10 | 2020-01-09 | 9648.75 | 9648.75 | 0
[6 empty] | 2020-01-14 | 11572.5 | 11572.5 | 0
[6 empty] | 2020-04-01 | 18217.5 | 18217.5 | 0
[6 empty] | 2020-04-15 | 10562.5 | 10562.5 | 0
[6 empty] | 2020-05-28 | 10410 | 10410 | 0
[6 empty] | 2020-06-17 | 6977.5 | 6977.5 | 0
[6 empty] | 2020-07-27 | 14165 | 14165 | 0
[6 empty] | 2020-08-17 | 10209.09 | 10209.09 | 0
[6 empty] | 2020-10-13 | 9643.06 | 9643.06 | 0
[6 empty] | 2020-10-20 | 9136.35 | 9136.35 | 0
[6 empty] | 2020-12-18 | 18981.19 | 18981.19 | 0
[6 empty] | 2021-02-08 | 9411.62 | 9411.62 | 0
[6 empty] | 2021-04-05 | 6923.17 | 6923.17 | 0
[6 empty] | 2021-04-16 | 5862.68 | 5862.68 | 0
[6 empty] | 2021-05-25 | 9891.91 | 9891.91 | 0
[6 empty] | 2021-09-30 | 25509.18 | 25487.18 | 22
[6 empty] | 2022-04-20 | -22 | 0 | -22
|  | District Office | 21st Century classroom | PO1-200000000761 | 2019-10-10 | 2020-01-14 | 3840 | 3840 | 0
[6 empty] | 2020-04-01 | 27200 | 27200 | 0
[6 empty] | 2020-04-15 | 11535 | 11535 | 0
[6 empty] | 2020-05-28 | 12325 | 12325 | 0
[6 empty] | 2020-06-17 | 11885 | 11885 | 0
[6 empty] | 2020-07-27 | 22090 | 22090 | 0
[6 empty] | 2020-08-17 | 18080 | 18080 | 0
[6 empty] | 2020-10-13 | 19265 | 19265 | 0
[6 empty] | 2020-10-20 | 14080 | 14080 | 0
[6 empty] | 2020-12-17 | 46945 | 46945 | 0
[6 empty] | 2021-02-08 | 27150 | 27150 | 0
[6 empty] | 2021-04-05 | 34605 | 34605 | 0
[6 empty] | 2021-04-16 | 38455 | 38455 | 0
[6 empty] | 2021-05-07 | 46550 | 46550 | 0
[6 empty] | 2021-05-25 | 41875 | 41875 | 0
[6 empty] | 2021-06-22 | 37625 | 37625 | 0
[6 empty] | 2021-09-08 | 11520 | 11520 | 0
[6 empty] | 2021-09-09 | 24960 | 24960 | 0
[6 empty] | 2021-09-10 | 15 | 0 | 15
[6 empty] | 2022-04-27 | -15 | 0 | -15
|  |  |  | PO1-220000000675, PO1-200000000761 | 2022-02-09 | 2022-02-28 | 25600 | 25600 | 0
[6 empty] | 2022-03-15 | 25320 | 25320 | 0
[6 empty] | 2022-04-20 | 33410 | 33410 | 0
[6 empty] | 2022-05-10 | 33005 | 33005 | 0
[6 empty] | 2022-06-16 | 37325 | 37325 | 0
[6 empty] | 2022-07-15 | 38000 | 38000 | 0
[6 empty] | 2022-08-26 | 35270 | 35270 | 0
[6 empty] | 2022-10-04 | 32080 | 32080 | 0
[6 empty] | 2022-10-13 | 32320 | 32320 | 0
[6 empty] | 2022-11-21 | 7125 | 7125 | 0
[6 empty] | 2023-01-12 | 480 | 480 | 0
[6 empty] | 2023-04-24 | 65 | 0 | 65
[6 empty] | 2023-04-25 | -65 | 0 | -65
|  |  |  | PO2W-240000000890, PO2W-220000000862, PO1-220000000334 | 2023-10-11 | 2028-07-11 | 1790290 | 0 | 1790290
|  | Fairgrove | 21st Century classroom | PO1-220000000334 | 2021-07-01 | 2021-09-08 | 1440 | 1440 | 0
[6 empty] | 2021-09-29 | 5120 | 5120 | 0
[6 empty] | 2023-10-10 | 400194 | 0 | 400194
[6 empty] | 2023-10-11 | -400194 | 0 | -400194
|  |  |  | PO2W-220000000862, PO1-220000000334 | 2021-11-02 | 2021-11-08 | 6450 | 6450 | 0
|  | Grandview | 21st Century classroom | PO1-200000000640 | 2019-10-10 | 2020-01-09 | 7143.75 | 7143.75 | 0
[6 empty] | 2020-01-14 | 11325 | 11325 | 0
[6 empty] | 2020-04-01 | 16377.5 | 16377.5 | 0
[6 empty] | 2020-04-15 | 7442.5 | 7442.5 | 0
[6 empty] | 2020-05-28 | 9460 | 9460 | 0
[6 empty] | 2020-06-17 | 7020 | 7020 | 0
[6 empty] | 2020-07-27 | 3765 | 3765 | 0
[6 empty] | 2020-08-17 | 12733.4 | 12733.4 | 0
[6 empty] | 2020-10-13 | 12027.42 | 12027.42 | 0
[6 empty] | 2020-10-20 | 11395.42 | 11395.42 | 0
[6 empty] | 2020-12-18 | 23674.52 | 23674.52 | 0
[6 empty] | 2021-02-08 | 11738.76 | 11738.76 | 0
[6 empty] | 2021-04-05 | 8635.01 | 8635.01 | 0
[6 empty] | 2021-04-16 | 7312.3 | 7312.3 | 0
[6 empty] | 2021-05-25 | 12337.8 | 12337.8 | 0
[6 empty] | 2021-06-22 | 9920 | 9920 | 0
[6 empty] | 2021-09-08 | 4160 | 4160 | 0
[6 empty] | 2021-09-09 | 6240 | 6240 | 0
[6 empty] | 2022-03-15 | 4086.62 | 4086.62 | 0
[6 empty] | 2022-04-20 | 7395 | 7395 | 0
[6 empty] | 2022-04-21 | 15 | 0 | 15
[6 empty] | 2022-04-22 | -15 | 0 | -15
|  |  |  | PO1-220000000753, PO1-200000000640 | 2022-04-05 | 2022-04-21 | 1160 | 1160 | 0
[6 empty] | 2022-05-11 | 4930 | 4930 | 0
[6 empty] | 2022-05-20 | 44765 | 44765 | 0
[6 empty] | 2022-11-28 | 9920 | 9920 | 0
[6 empty] | 2023-01-17 | 12160 | 12160 | 0
[6 empty] | 2023-01-18 | 14160 | 14160 | 0
[6 empty] | 2023-03-07 | 24320 | 24320 | 0
[6 empty] | 2023-03-22 | 11960 | 11960 | 0
[6 empty] | 2023-05-10 | 28080 | 28080 | 0
[6 empty] | 2023-06-12 | 23680 | 23680 | 0
[6 empty] | 2023-06-28 | 26640 | 26640 | 0
[6 empty] | 2023-07-17 | 14720 | 14720 | 0
[6 empty] | 2023-07-18 | 31270 | 0 | 31270
[6 empty] | 2023-07-19 | -31270 | 0 | -31270
|  |  |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 2023-07-13 | 2023-09-21 | 14730 | 14730 | 0
[6 empty] | 2024-01-22 | 16500 | 16500 | 0
[6 empty] | 2025-07-11 | 40 | 0 | 40
|  | Grazide | 21st Century classroom | PO1-220000000334 | 2021-07-01 | 2021-09-08 | 800 | 800 | 0
[6 empty] | 2021-09-29 | 3960 | 3960 | 0
[6 empty] | 2023-10-10 | 196192 | 0 | 196192
[6 empty] | 2023-10-11 | -196192 | 0 | -196192
|  |  |  | PO2W-220000000862, PO1-220000000334 | 2021-11-02 | 2021-11-08 | 5650 | 5650 | 0
|  | La Puente HS | 21st Century classroom | PO2W-230000003838 | 2023-05-17 | 2023-07-13 | 21920 | 21920 | 0
[6 empty] | 2023-07-14 | 149480 | 0 | 149480
[6 empty] | 2023-08-03 | -149480 | 0 | -149480
|  |  |  | PO2W-240000000481, PO2W-230000003838 | 2023-08-04 | 2023-09-21 | 45330 | 45330 | 0
[6 empty] | 2023-11-17 | 12760 | 12760 | 0
[6 empty] | 2024-01-19 | 19840 | 19840 | 0
[6 empty] | 2027-12-09 | 71550 | 0 | 71550
|  | Los Altos ES | 21st Century classroom | PO1-200000000640 | 2019-10-10 | 2020-01-09 | 8571.25 | 8571.25 | 0
[6 empty] | 2020-01-14 | 12697.5 | 12697.5 | 0
[6 empty] | 2020-04-01 | 17397.5 | 17397.5 | 0
[6 empty] | 2020-04-15 | 12647.5 | 12647.5 | 0
[6 empty] | 2020-05-28 | 9337.5 | 9337.5 | 0
[6 empty] | 2020-06-17 | 9947.5 | 9947.5 | 0
[6 empty] | 2020-07-27 | 13287.5 | 13287.5 | 0
[6 empty] | 2020-08-17 | 5953.78 | 5953.78 | 0
[6 empty] | 2020-10-13 | 5623.68 | 5623.68 | 0
[6 empty] | 2020-10-20 | 5328.17 | 5328.17 | 0
[6 empty] | 2020-12-18 | 11069.53 | 11069.53 | 0
[6 empty] | 2021-02-08 | 5488.71 | 5488.71 | 0
[6 empty] | 2021-04-05 | 4037.49 | 4037.49 | 0
[6 empty] | 2021-04-16 | 3419.03 | 3419.03 | 0
[6 empty] | 2021-05-25 | 5768.8 | 5768.8 | 0
[6 empty] | 2021-09-30 | 11952.82 | 11952.82 | 0
[6 empty] | 2021-10-18 | 2897.99 | 2897.99 | 0
[6 empty] | 2022-04-19 | 25.75 | 0 | 25.75
[6 empty] | 2022-04-20 | -25.75 | 0 | -25.75
|  | Los Altos HS | 21st Century classroom | PO2W-230000003838 | 2023-05-17 | 2023-07-11 | 171400 | 0 | 171400
[6 empty] | 2023-08-03 | -171400 | 0 | -171400
|  |  |  | PO2W-240000000481, PO2W-230000003838 | 2023-08-04 | 2024-01-18 | 14210 | 14210 | 0
[6 empty] | 2024-01-19 | 2240 | 2240 | 0
[6 empty] | 2027-12-09 | 154950 | 0 | 154950
|  | Los Molinos | 21st Century classroom | PO1-220000000334 | 2021-07-01 | 2021-09-08 | 960 | 960 | 0
[6 empty] | 2021-09-29 | 4280 | 4280 | 0
[6 empty] | 2023-10-10 | 270840 | 0 | 270840
[6 empty] | 2023-10-11 | -270840 | 0 | -270840
|  |  |  | PO2W-220000000862, PO1-220000000334 | 2021-11-02 | 2021-11-08 | 5650 | 5650 | 0
|  | Mesa Robles | 21st Century classroom | PO1-200000000640 | 2019-10-10 | 2020-01-09 | 9691.25 | 9691.25 | 0
[6 empty] | 2020-01-14 | 11627.5 | 11627.5 | 0
[6 empty] | 2020-04-01 | 20417.5 | 20417.5 | 0
[6 empty] | 2020-04-15 | 8200 | 8200 | 0
[6 empty] | 2020-05-28 | 12690 | 12690 | 0
[6 empty] | 2020-06-17 | 13470 | 13470 | 0
[6 empty] | 2020-07-27 | 15197.5 | 15197.5 | 0
[6 empty] | 2020-08-17 | 16815.75 | 16815.75 | 0
[6 empty] | 2020-10-13 | 15883.43 | 15883.43 | 0
[6 empty] | 2020-10-20 | 15048.8 | 15048.8 | 0
[6 empty] | 2020-12-18 | 31264.6 | 31264.6 | 0
[6 empty] | 2021-02-08 | 15502.22 | 15502.22 | 0
[6 empty] | 2021-04-05 | 11403.41 | 11403.41 | 0
[6 empty] | 2021-04-16 | 9656.64 | 9656.64 | 0
[6 empty] | 2021-05-25 | 16293.31 | 16293.31 | 0
[6 empty] | 2021-06-22 | 3520 | 3520 | 0
[6 empty] | 2021-09-09 | 160 | 160 | 0
[6 empty] | 2021-10-18 | 3182.01 | 3182.01 | 0
[6 empty] | 2021-12-13 | 1280 | 1280 | 0
[6 empty] | 2022-01-24 | 13920 | 13920 | 0
[6 empty] | 2022-02-11 | 19869.83 | 19869.83 | 0
[6 empty] | 2022-04-19 | 85.25 | 0 | 85.25
[6 empty] | 2022-04-20 | -85.25 | 0 | -85.25
|  | Nelson | 21st Century classroom | PO1-200000000640 | 2019-10-10 | 2020-01-09 | 8556.25 | 8556.25 | 0
[6 empty] | 2020-01-14 | 12837.5 | 12837.5 | 0
[6 empty] | 2020-04-01 | 19960 | 19960 | 0
[6 empty] | 2020-04-15 | 13455 | 13455 | 0
[6 empty] | 2020-05-28 | 9450 | 9450 | 0
[6 empty] | 2020-06-17 | 10027.5 | 10027.5 | 0
[6 empty] | 2020-07-27 | 10887.5 | 10887.5 | 0
[6 empty] | 2020-08-17 | 6349.45 | 6349.45 | 0
[6 empty] | 2020-10-13 | 5997.42 | 5997.42 | 0
[6 empty] | 2020-10-20 | 5682.27 | 5682.27 | 0
[6 empty] | 2020-12-18 | 11805.19 | 11805.19 | 0
[6 empty] | 2021-02-08 | 5853.48 | 5853.48 | 0
[6 empty] | 2021-04-05 | 4305.81 | 4305.81 | 0
[6 empty] | 2021-04-16 | 3646.24 | 3646.24 | 0
[6 empty] | 2021-05-25 | 6152.18 | 6152.18 | 0
[6 empty] | 2022-02-11 | 2315.17 | 2315.17 | 0
[6 empty] | 2022-03-15 | 13530.29 | 13530.29 | 0
[6 empty] | 2022-04-19 | 19.75 | 0 | 19.75
[6 empty] | 2022-04-20 | -19.75 | 0 | -19.75
|  | Newton | 21st Century classroom | PO1-200000000640 | 2019-10-10 | 2020-01-09 | 7376.25 | 7376.25 | 0
[6 empty] | 2020-01-14 | 11395 | 11395 | 0
[6 empty] | 2020-04-01 | 17477.5 | 17477.5 | 0
[6 empty] | 2020-04-15 | 7480 | 7480 | 0
[6 empty] | 2020-05-28 | 9737.5 | 9737.5 | 0
[6 empty] | 2020-06-17 | 8587.5 | 8587.5 | 0
[6 empty] | 2020-07-27 | 6685 | 6685 | 0
[6 empty] | 2020-08-17 | 10803.44 | 10803.44 | 0
[6 empty] | 2020-10-13 | 10204.46 | 10204.46 | 0
[6 empty] | 2020-10-20 | 9668.25 | 9668.25 | 0
[6 empty] | 2020-12-18 | 20086.24 | 20086.24 | 0
[6 empty] | 2021-02-08 | 9959.55 | 9959.55 | 0
[6 empty] | 2021-04-05 | 7326.23 | 7326.23 | 0
[6 empty] | 2021-04-16 | 6204 | 6204 | 0
[6 empty] | 2021-05-25 | 10467.79 | 10467.79 | 0
[6 empty] | 2021-06-22 | 5920 | 5920 | 0
[6 empty] | 2021-09-08 | 21440 | 21440 | 0
[6 empty] | 2021-09-09 | 9760 | 9760 | 0
[6 empty] | 2021-09-10 | -10125.71 | 0 | -10125.71
[6 empty] | 2022-04-15 | 0 | -10142.46 | 10142.46
[6 empty] | 2022-04-20 | -16.75 | 0 | -16.75
|  |  |  | PO1-220000000753, PO1-200000000640 | 2022-04-05 | 2022-04-21 | 3335 | 3335 | 0
[6 empty] | 2022-05-11 | 4495 | 4495 | 0
[6 empty] | 2022-05-20 | 26330 | 26330 | 0
[6 empty] | 2022-06-17 | 24000 | 24000 | 0
[6 empty] | 2022-07-18 | 26400 | 26400 | 0
[6 empty] | 2022-08-18 | 20400 | 20400 | 0
[6 empty] | 2022-10-06 | 25200 | 25200 | 0
[6 empty] | 2022-11-28 | 29360 | 29360 | 0
[6 empty] | 2022-12-06 | 24000 | 24000 | 0
[6 empty] | 2023-01-17 | 24000 | 24000 | 0
[6 empty] | 2023-01-18 | 14000 | 14000 | 0
[6 empty] | 2023-03-07 | 3100 | 3100 | 0
[6 empty] | 2023-03-22 | 23120 | 23120 | 0
[6 empty] | 2025-07-11 | 25 | 0 | 25
|  | Orange Grove | 21st Century classroom | PO1-220000000334 | 2021-07-01 | 2021-09-08 | 800 | 800 | 0
[6 empty] | 2021-09-29 | 2960 | 2960 | 0
[6 empty] | 2023-10-10 | 197337 | 0 | 197337
[6 empty] | 2023-10-11 | -197337 | 0 | -197337
|  |  |  | PO2W-220000000862, PO1-220000000334 | 2021-11-02 | 2021-11-08 | 5505 | 5505 | 0
|  | Sparks MS | 21st Century classroom | PO1-200000000640 | 2019-10-10 | 2020-01-09 | 8306.25 | 8306.25 | 0
[6 empty] | 2020-01-14 | 10935 | 10935 | 0
[6 empty] | 2020-04-01 | 16222.5 | 16222.5 | 0
[6 empty] | 2020-04-15 | 7320 | 7320 | 0
[6 empty] | 2020-05-28 | 9337.5 | 9337.5 | 0
[6 empty] | 2020-06-17 | 6822.5 | 6822.5 | 0
[6 empty] | 2020-07-27 | 3765 | 3765 | 0
[6 empty] | 2020-08-17 | 8001.67 | 8001.67 | 0
[6 empty] | 2020-10-13 | 7558.04 | 7558.04 | 0
[6 empty] | 2020-10-20 | 7160.88 | 7160.88 | 0
[6 empty] | 2020-12-18 | 14877.08 | 14877.08 | 0
[6 empty] | 2021-02-08 | 7376.64 | 7376.64 | 0
[6 empty] | 2021-04-05 | 5426.24 | 5426.24 | 0
[6 empty] | 2021-04-16 | 4595.05 | 4595.05 | 0
[6 empty] | 2021-05-25 | 7753.08 | 7753.08 | 0
[6 empty] | 2021-06-22 | 5760 | 5760 | 0
[6 empty] | 2021-09-08 | 1600 | 1600 | 0
[6 empty] | 2021-09-09 | 8160 | 8160 | 0
[6 empty] | 2022-04-20 | 4470.07 | 4470.07 | 0
[6 empty] | 2022-04-21 | 3.5 | 0 | 3.5
[6 empty] | 2022-04-22 | -3.5 | 0 | -3.5
|  |  |  | PO1-220000000753, PO1-200000000640 | 2022-04-05 | 2022-04-21 | 2646.25 | 2646.25 | 0
[6 empty] | 2022-05-11 | 4640 | 4640 | 0
[6 empty] | 2022-05-20 | 47640 | 47640 | 0
[6 empty] | 2022-11-28 | 10080 | 10080 | 0
[6 empty] | 2023-01-17 | 13280 | 13280 | 0
[6 empty] | 2023-01-18 | 14320 | 14320 | 0
[6 empty] | 2023-03-07 | 23140 | 23140 | 0
[6 empty] | 2023-03-22 | 12040 | 12040 | 0
[6 empty] | 2023-05-10 | 27680 | 27680 | 0
[6 empty] | 2023-06-12 | 23360 | 23360 | 0
[6 empty] | 2023-06-28 | 26640 | 26640 | 0
[6 empty] | 2023-07-17 | 14240 | 14240 | 0
[6 empty] | 2023-07-18 | 28058.75 | 0 | 28058.75
[6 empty] | 2023-07-19 | -28058.75 | 0 | -28058.75
|  |  |  | PO2W-240000000484, PO1-220000000753, PO1-200000000640 | 2023-07-13 | 2023-09-21 | 15560 | 15560 | 0
[6 empty] | 2024-01-22 | 12450 | 12450 | 0
[6 empty] | 2025-07-11 | 48.75 | 0 | 48.75
|  | Stimson | 21st Century classroom | PO1-220000000334 | 2021-07-01 | 2021-09-08 | 480 | 480 | 0
[6 empty] | 2021-09-29 | 4800 | 4800 | 0
[6 empty] | 2023-10-10 | 64678 | 0 | 64678
[6 empty] | 2023-10-11 | -64678 | 0 | -64678
|  |  |  | PO2W-220000000862, PO1-220000000334 | 2021-11-02 | 2021-11-08 | 5170 | 5170 | 0
|  | Sunset | 21st Century classroom | PO1-220000000334 | 2021-07-01 | 2021-09-08 | 800 | 800 | 0
[6 empty] | 2021-09-29 | 1600 | 1600 | 0
[6 empty] | 2023-10-10 | 198697 | 0 | 198697
[6 empty] | 2023-10-11 | -198697 | 0 | -198697
|  |  |  | PO2W-220000000862, PO1-220000000334 | 2021-11-02 | 2021-11-08 | 5505 | 5505 | 0
|  | Wilson HS | 21st Century classroom | PO2W-230000003838 | 2023-05-17 | 2023-07-11 | 171400 | 0 | 171400
[6 empty] | 2023-08-03 | -171400 | 0 | -171400
|  |  |  | PO2W-240000000481, PO2W-230000003838 | 2023-08-04 | 2024-01-18 | 10005 | 10005 | 0
[6 empty] | 2024-01-19 | 4640 | 4640 | 0
[6 empty] | 2027-12-09 | 156755 | 0 | 156755
|  | Workman ES | 21st Century classroom | PO1-200000000640 | 2019-10-10 | 2020-01-09 | 9866.25 | 9866.25 | 0
[6 empty] | 2020-01-14 | 11340 | 11340 | 0
[6 empty] | 2020-04-01 | 17130 | 17130 | 0
[6 empty] | 2020-04-15 | 12972.5 | 12972.5 | 0
[6 empty] | 2020-05-28 | 9657.5 | 9657.5 | 0
[6 empty] | 2020-06-17 | 9947.5 | 9947.5 | 0
[6 empty] | 2020-07-27 | 12327.5 | 12327.5 | 0
[6 empty] | 2020-08-17 | 8313.42 | 8313.42 | 0
[6 empty] | 2020-10-13 | 7852.49 | 7852.49 | 0
[6 empty] | 2020-10-20 | 7439.86 | 7439.86 | 0
[6 empty] | 2020-12-18 | 15456.65 | 15456.65 | 0
[6 empty] | 2021-02-08 | 7664.02 | 7664.02 | 0
[6 empty] | 2021-04-05 | 5637.64 | 5637.64 | 0
[6 empty] | 2021-04-16 | 4774.06 | 4774.06 | 0
[6 empty] | 2021-05-25 | 8055.13 | 8055.13 | 0
[6 empty] | 2021-06-22 | 480 | 480 | 0
[6 empty] | 2022-03-15 | 5583.09 | 5583.09 | 0
[6 empty] | 2022-04-20 | 4483.68 | 4483.68 | 0
[6 empty] | 2022-04-21 | 10142.46 | 10142.46 | 0
|  | Workman HS | 21st Century classroom | PO2W-230000003838 | 2023-05-17 | 2023-07-11 | 171400 | 0 | 171400
[6 empty] | 2023-08-03 | -171400 | 0 | -171400
|  |  |  | PO2W-240000000481, PO2W-230000003838 | 2023-08-04 | 2023-09-21 | 27780 | 27780 | 0
[6 empty] | 2023-11-17 | 61520 | 61520 | 0
[6 empty] | 2024-01-18 | 3480 | 3480 | 0
[6 empty] | 2024-01-19 | 11600 | 11600 | 0
[6 empty] | 2027-12-09 | 67020 | 0 | 67020
Cumming Construction Management, Inc. Total | [6 empty] | 5494643.75 | 3253965 | 2240678.75
David M. Bertino Manufacturing, Inc. | Furniture | Cedarlane | 21st Century classroom | PO2W-220000000940 | 2021-11-09 | 2022-01-11 | 3858.78 | 3858.78 | 0
|  | Grandview | 21st Century classroom | PO3W-230000001317 | 2022-11-09 | 2023-08-10 | 7480 | 7480 | 0
|  | Newton | 21st Century classroom | PO3W-230000001317 | 2022-11-09 | 2023-08-10 | 7446 | 7446 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000001317 | 2022-11-09 | 2023-08-10 | 8800 | 8800 | 0
David M. Bertino Manufacturing, Inc. Total | [6 empty] | 27584.78 | 27584.78 | 0
Dell Marketing Lp | Networking power switches | Cedarlane | 21st Century classroom | PO3W-210000002719 | 2021-05-12 | 2021-08-27 | 9695.45 | 9695.45 | 0
|  | Los Altos ES | 21st Century classroom | PO3W-210000002719 | 2021-05-12 | 2021-08-27 | 9695.44 | 9695.44 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000002719 | 2021-05-12 | 2021-08-27 | 33934.03 | 33934.03 | 0
|  | Nelson | 21st Century classroom | PO3W-210000002719 | 2021-05-12 | 2021-08-27 | 9695.44 | 9695.44 | 0
|  | Workman ES | 21st Century classroom | PO3W-210000002719 | 2021-05-12 | 2021-08-27 | 9695.44 | 9695.44 | 0
Dell Marketing Lp Total | [6 empty] | 72715.8 | 72715.8 | 0
Department of General Services (DGS) | DSA fees | California | Fire Alarm replacement | PO2W-220000000367 | 2021-08-25 | 2021-09-09 | 1290 | 1290 | 0
|  | Cedarlane | Fire Alarm replacement | PO2W-210000001557 | 2021-01-06 | 2021-01-20 | 1290 | 1290 | 0
|  |  | Interim Housing | PO2W-230000000336 | 2022-08-08 | 2022-08-19 | 11662.54 | 11662.54 | 0
|  | Grandview | Fire Alarm replacement | PO2W-220000000119 | 2021-07-21 | 2021-08-04 | 1451.25 | 1451.25 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-220000001228 | 2021-12-15 | 2022-01-06 | 15210.87 | 15210.87 | 0
|  | Mesa Robles | Fire Alarm replacement | PO2W-220000000119 | 2021-07-21 | 2021-08-04 | 1720 | 1720 | 0
|  | Nelson | 21st Century classroom | PO2W-220000001343 | 2022-01-13 | 2022-01-28 | 14670.45 | 14670.45 | 0
|  | Newton | Fire Alarm replacement | PO2W-210000001789 | 2021-01-06 | 2021-03-20 | 645 | 645 | 0
|  |  | Interim Housing | PO2W-230000003701 | 2023-04-26 | 2023-07-13 | 7947.1 | 7947.1 | 0
|  | Sparks MS | Fire Alarm replacement | PO2W-210000001557 | 2021-01-06 | 2021-01-20 | 860 | 860 | 0
|  | Valley | Fire Alarm replacement | PO2W-220000000054 | 2021-07-13 | 2021-08-02 | 698.75 | 698.75 | 0
[6 empty] | 2021-08-08 | -698.75 | -698.75 | 0
[6 empty] | 2021-08-09 | 698.75 | 698.75 | 0
[6 empty] | 2022-02-22 | -698.75 | -698.75 | 0
[6 empty] | 2022-05-06 | 698.75 | 698.75 | 0
Department of General Services (DGS) Total | [6 empty] | 57445.96 | 57445.96 | 0
Division of the State Architect (DSA) | DSA fees | Baldwin | 21st Century classroom | PO2W-240000001909 | 2024-01-09 | 2024-01-22 | 37740 | 37740 | 0
|  |  | Drinking Fountain replacement | PO1-200000000954 | 2020-02-04 | 2020-02-13 | 1050 | 1050 | 0
|  |  | Fire Alarm replacement | PO2W-200000001057 | 2019-09-09 | 2019-09-13 | 1020 | 1020 | 0
|  | Bixby | Drinking Fountain replacement | PO2W-210000002164 | 2021-04-27 | 2021-05-05 | 1050 | 1050 | 0
|  |  | Fire Alarm replacement | PO1-200000000849 | 2020-01-15 | 2020-02-13 | 870 | 870 | 0
|  | California | 21st Century classroom | PO2W-240000001910 | 2024-01-09 | 2024-01-22 | 26400 | 26400 | 0
|  |  | Drinking Fountain replacement | PO1-200000000953 | 2020-02-04 | 2020-02-13 | 1050 | 1050 | 0
|  |  | Fire Alarm replacement | PO2W-200000001054 | 2019-09-09 | 2019-09-13 | 780 | 780 | 0
|  | Cedarlane | 21st Century classroom | PO2W-200000004897 | 2020-04-13 | 2020-04-24 | 22159 | 22159 | 0
|  |  |  | PO2W-230000000247 | 2022-08-02 | 2022-08-10 | 18962.47 | 18962.47 | 0
|  |  | Interim Housing | PO2W-200000003716 | 2020-01-28 | 2020-01-31 | 3052.5 | 3052.5 | 0
|  | Del Valle | Fire Alarm replacement | PO2W-210000001958 | 2021-03-17 | 2021-03-30 | 870 | 870 | 0
|  | Fairgrove | Fire Alarm replacement | PO2W-200000001056 | 2019-09-09 | 2019-09-13 | 1230 | 1230 | 0
|  | Grandview | 21st Century classroom | PO2W-210000001571 | 2021-01-12 | 2021-01-20 | 35235.88 | 35235.88 | 0
|  | Grazide | Fire Alarm replacement | PO1-200000000850 | 2020-01-15 | 2020-02-13 | 960 | 960 | 0
|  | Kwis | Fire Alarm replacement | PO2W-210000001958 | 2021-03-17 | 2021-03-30 | 891 | 891 | 0
|  | Lassalette | Fire Alarm replacement | PO1-200000000853 | 2020-01-15 | 2020-02-13 | 945 | 945 | 0
[6 empty] | 2020-04-30 | -945 | -945 | 0
|  | Los Altos ES | 21st Century classroom | 19-109963 | 2019-06-11 | 2019-06-19 | 14918.24 | 14918.24 | 0
|  |  | Drinking Fountain replacement | PO1-200000000955 | 2020-02-04 | 2020-02-13 | 1050 | 1050 | 0
|  |  | Interim Housing | 19-107318 | 2019-03-18 | 2019-03-21 | 3481.54 | 3481.54 | 0
|  |  |  | PO2W-200000004548 | 2020-03-06 | 2020-03-11 | 2687.5 | 2687.5 | 0
|  | Los Altos HS | Fire Alarm replacement | PO2W-200000001053 | 2019-09-09 | 2019-09-13 | 5500 | 5500 | 0
|  | Los Molinos | Drinking Fountain replacement | PO2W-210000002164 | 2021-03-17 | 2021-05-05 | 1050 | 1050 | 0
|  |  | Fire Alarm replacement | PO2W-200000001058 | 2019-09-09 | 2019-09-13 | 870 | 870 | 0
|  | Los Robles | Fire Alarm replacement | PO2W-210000001958 | 2021-03-17 | 2021-03-30 | 900 | 900 | 0
|  | Mesa Robles | 21st Century classroom | PO1-200000001113 | 2020-04-13 | 2020-04-24 | 28009 | 28009 | 0
|  |  |  | PO2W-230000001043 | 2022-09-22 | 2022-10-19 | 12075.87 | 12075.87 | 0
|  |  | Drinking Fountain replacement | PO1-200000000956 | 2020-02-04 | 2020-02-13 | 1050 | 1050 | 0
|  |  | Interim Housing | PO2W-200000001911 | 2019-10-22 | 2019-10-28 | 7425 | 7425 | 0
|  | Nelson | 21st Century classroom | 19-109964 | 2019-06-11 | 2019-06-19 | 15540.64 | 15540.64 | 0
|  |  | Drinking Fountain replacement | PO1-200000000957 | 2020-02-04 | 2020-02-13 | 1050 | 1050 | 0
|  | Newton | 21st Century classroom | PO2W-210000001572 | 2021-01-12 | 2021-01-20 | 28270.82 | 28270.82 | 0
|  |  | Interim Housing | PO1-200000000863 | 2020-01-15 | 2020-01-28 | 4175.44 | 4175.44 | 0
|  | Orange Grove | Fire Alarm replacement | PO2W-210000001958 | 2021-03-17 | 2021-03-30 | 1080 | 1080 | 0
|  | Palm | Drinking Fountain replacement | PO1-200000000958 | 2020-02-04 | 2020-02-13 | 1050 | 1050 | 0
|  |  | Fire Alarm replacement | PO2W-210000001958 | 2021-03-17 | 2021-03-30 | 870 | 870 | 0
|  | Sierra Vista | Fire Alarm replacement | PO2W-210000001958 | 2021-03-17 | 2021-03-30 | 1050 | 1050 | 0
|  | Sparks ES | Fire Alarm replacement | PO1-200000000848 | 2020-01-15 | 2020-02-13 | 930 | 930 | 0
|  | Sparks MS | 21st Century classroom | PO2W-210000001571 | 2021-01-12 | 2021-01-20 | 22264.25 | 22264.25 | 0
|  | Stimson | Fire Alarm replacement | PO1-200000000851 | 2020-01-15 | 2020-02-13 | 375 | 375 | 0
|  | Sunset | Fire Alarm replacement | PO2W-210000001958 | 2021-03-17 | 2021-03-30 | 564 | 564 | 0
|  | Valinda | Fire Alarm replacement | PO1-200000000852 | 2020-01-15 | 2020-02-13 | 1125 | 1125 | 0
|  | Valley | Fire Alarm replacement | PO2W-200000001055 | 2019-09-09 | 2019-09-13 | 630 | 630 | 0
|  | Wing Lane | Fire Alarm replacement | PO2W-210000001958 | 2021-03-17 | 2021-03-30 | 870 | 870 | 0
|  | Workman ES | 21st Century classroom | 19-108465 | 2019-04-16 | 2019-04-18 | 9500 | 9500 | 0
|  |  |  | PO2W-210000002165 | 2021-03-17 | 2021-05-05 | 800 | 800 | 0
|  |  |  | PO2W-220000001377 | 2022-01-19 | 2022-01-28 | 12085.87 | 12085.87 | 0
Division of the State Architect (DSA) Total | [6 empty] | 334569.02 | 334569.02 | 0
Education Products & Services | Contractor | Los Altos ES | Interim Housing | PO2W-200000002196 | 2019-10-14 | 2020-02-12 | 1894.88 | 1894.88 | 0
| Sink cabinet | Nelson | 21st Century classroom | PO2W-200000003740 | 2020-01-31 | 2020-04-23 | 3449.99 | 3449.99 | 0
| Sliding white boards | Nelson | 21st Century classroom | PO2W-200000003506 | 2020-01-15 | 2020-04-23 | 5465.85 | 5465.85 | 0
| Tack boards | District Office | 21st Century classroom | PO2W-200000004016 | 2020-02-04 | 2020-04-22 | 1886.36 | 1886.36 | 0
| White board(s) | Grandview | 21st Century classroom | PO2W-200000000102 | 2019-09-16 | 2019-09-25 | 1464.78 | 1464.78 | 0
|  | Nelson | 21st Century classroom | PO2W-200000003738 | 2020-01-31 | 2020-04-23 | 1253.77 | 1253.77 | 0
|  | Valinda | 21st Century classroom | PO3W-200000000563 | 2019-09-16 | 2019-10-01 | 1464.78 | 1464.78 | 0
Education Products & Services Total | [6 empty] | 16880.41 | 16880.41 | 0
Fagen Friedman & Fulfrost LLP | Attorney fees | District Office | 21st Century classroom | 18-104648 | 2017-07-11 | 2017-12-19 | 1064 | 1064 | 0
[6 empty] | 2017-12-20 | 48936 | 0 | 48936
[6 empty] | 2018-06-30 | -48936 | 0 | -48936
|  |  |  | 19-100300 | 2018-07-11 | 2019-04-09 | 2375 | 2375 | 0
[6 empty] | 2019-04-10 | 7625 | 0 | 7625
[6 empty] | 2019-06-30 | -7625 | 0 | -7625
|  |  |  | PO1-200000000812 | 2019-12-30 | 2020-01-03 | 7283.51 | 7283.51 | 0
[6 empty] | 2020-01-08 | 2112.68 | 2112.68 | 0
[6 empty] | 2020-01-13 | 10128 | 10128 | 0
[6 empty] | 2020-03-03 | 31.62 | 31.62 | 0
[6 empty] | 2020-04-29 | 444.19 | 444.19 | 0
|  |  |  | PO1-200000001126 | 2020-03-10 | 2020-04-29 | 6906.81 | 6906.81 | 0
[6 empty] | 2020-06-30 | 13093.19 | 13093.19 | 0
[6 empty] | 2020-07-01 | -13093.19 | -13093.19 | 0
[6 empty] | 2020-07-02 | 13093.19 | 0 | 13093.19
[6 empty] | 2021-06-30 | -13093.19 | 0 | -13093.19
|  |  |  | PO1-210000000260 | 2020-07-31 | 2021-12-14 | 1417.5 | 1417.5 | 0
[6 empty] | 2021-12-23 | 1799.5 | 1799.5 | 0
[6 empty] | 2022-01-24 | 5735 | 5735 | 0
[6 empty] | 2022-01-28 | 3513 | 3513 | 0
[6 empty] | 2022-03-02 | 2612.5 | 2612.5 | 0
[6 empty] | 2023-07-19 | 34922.5 | 0 | 34922.5
[6 empty] | 2023-07-20 | -34922.5 | 0 | -34922.5
|  |  |  | PO2W-200000000134 | 2019-07-11 | 2019-08-21 | 90 | 90 | 0
[6 empty] | 2019-08-28 | 3235 | 3235 | 0
[6 empty] | 2019-09-18 | 1387.5 | 1387.5 | 0
[6 empty] | 2020-01-03 | 5287.5 | 5287.5 | 0
Fagen Friedman & Fulfrost LLP Total | [6 empty] | 55423.31 | 55423.31 | 0
Fitch Ratings, Inc. | Rating Agency Fee | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-08-03 | 2017-08-03 | 45000 | 45000 | 0
Fitch Ratings, Inc. Total | [6 empty] | 45000 | 45000 | 0
Floor Tech America (FTA) | Contractor | California | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2020-12-08 | 12744.48 | 12744.48 | 0
|  | Del Valle | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2020-12-08 | 6372.24 | 6372.24 | 0
|  | District Office | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2020-05-07 | 259042.4 | 259042.4 | 0
|  | Los Altos HS | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2021-03-24 | 19116.72 | 19116.72 | 0
|  | Nelson | 21st Century classroom | PO2W-200000003507 | 2020-01-15 | 2020-04-23 | 11175 | 11175 | 0
|  | Orange Grove | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2022-05-11 | 19116.72 | 19116.72 | 0
|  | Palm | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2020-08-28 | 2006.79 | 2006.79 | 0
[6 empty] | 2020-12-08 | 4365.45 | 4365.45 | 0
|  | Sparks ES | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2020-12-08 | 19116.72 | 19116.72 | 0
|  | Valley | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2021-09-09 | 19116.72 | 19116.72 | 0
|  | Wedgeworth | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2021-04-06 | 12744.48 | 12744.48 | 0
|  | Wilson HS | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2020-12-08 | 12744.48 | 12744.48 | 0
[6 empty] | 2021-04-06 | 6372.24 | 6372.24 | 0
|  | Workman HS | 21st Century classroom | PO2W-200000004391 | 2020-02-26 | 2021-04-06 | 57350.16 | 57350.16 | 0
Floor Tech America (FTA) Total | [6 empty] | 461384.6 | 461384.6 | 0
GDL Best Contractors, Inc. | Contractor | Los Altos ES | 21st Century classroom | PO2W-210000000586 | 2020-09-11 | 2021-03-26 | 21696 | 21696 | 0
|  |  | Interim Housing | PO2W-200000000121 | 2019-07-01 | 2019-11-06 | 183825 | 183825 | 0
[6 empty] | 2020-06-16 | 36675 | 36675 | 0
|  | Mesa Robles | Interim Housing | PO2W-200000004670 | 2020-03-03 | 2020-07-28 | 382506.49 | 382506.49 | 0
[6 empty] | 2020-09-08 | 302947.4 | 302947.4 | 0
[6 empty] | 2021-05-21 | 51574.48 | 51574.48 | 0
[6 empty] | 2022-01-28 | 18937.04 | 18937.04 | 0
|  |  |  | PO2W-220000000897 | 2021-11-02 | 2022-02-01 | 17420.13 | 17420.13 | 0
|  | Nelson | 21st Century classroom | PO2W-200000004356 | 2020-02-03 | 2020-06-18 | 14900 | 14900 | 0
|  | Newton | Interim Housing | PO2W-230000000447 | 2022-07-01 | 2022-08-26 | 2645 | 2645 | 0
GDL Best Contractors, Inc. Total | [6 empty] | 1033126.54 | 1033126.54 | 0
Global Industrial | Scissor lift | District Office | 21st Century classroom | PO3W-210000002747 | 2021-05-18 | 2021-06-03 | 1665.5 | 1665.5 | 0
Global Industrial Total | [6 empty] | 1665.5 | 1665.5 | 0
Graybar Electric | Door hardware | Cedarlane | 21st Century classroom | PO3W-210000003051 | 2021-06-16 | 2021-08-30 | 376.36 | 376.36 | 0
[6 empty] | 2021-09-23 | 358.62 | 358.62 | 0
[6 empty] | 2022-03-15 | 101.99 | 101.99 | 0
|  | Los Altos ES | 21st Century classroom | PO3W-210000001162 | 2020-12-14 | 2021-02-08 | 246.82 | 246.82 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000003051 | 2021-06-16 | 2021-08-30 | 599.39 | 599.39 | 0
[6 empty] | 2021-09-23 | 571.14 | 571.14 | 0
[6 empty] | 2022-03-15 | 162.45 | 162.45 | 0
|  | Nelson | 21st Century classroom | PO3W-210000001162 | 2020-12-14 | 2021-02-08 | 246.82 | 246.82 | 0
|  | Workman ES | 21st Century classroom | PO3W-210000001162 | 2020-12-14 | 2021-02-08 | 246.8 | 246.8 | 0
Graybar Electric Total | [6 empty] | 2910.39 | 2910.39 | 0
Harley Ellis Devereaux (HED) | Architect | District Office | Design guidelines | PO2W-200000001205, 19-100491, 18-109571 | 2018-07-01 | 2018-09-17 | 16080 | 16080 | 0
[6 empty] | 2018-10-19 | 6720 | 6720 | 0
[6 empty] | 2021-06-02 | 1200 | 1200 | 0
|  |  |  | PO2W-200000001206, 19-103806 | 2018-07-01 | 2026-06-01 | 5500 | 0 | 5500
|  | Grandview | 21st Century classroom | PO2W-200000001207, 19-100507, 18-109551 | 2018-06-13 | 2018-07-24 | 2800 | 2800 | 0
[6 empty] | 2019-02-19 | 10110 | 10110 | 0
[6 empty] | 2019-09-16 | 15400 | 15400 | 0
[6 empty] | 2019-09-17 | 265.07 | 265.07 | 0
[6 empty] | 2020-02-13 | 19600 | 19600 | 0
[6 empty] | 2020-03-10 | -265.07 | -265.07 | 0
[6 empty] | 2020-06-04 | 23100 | 23100 | 0
[6 empty] | 2020-12-08 | 17221 | 17221 | 0
[6 empty] | 2021-05-07 | 23100 | 23100 | 0
[6 empty] | 2021-06-23 | 3500 | 3500 | 0
[6 empty] | 2021-12-20 | 1050 | 1050 | 0
[6 empty] | 2022-07-18 | 1750 | 1750 | 0
[6 empty] | 2022-08-18 | -350 | -350 | 0
[6 empty] | 2022-10-06 | 490 | 490 | 0
[6 empty] | 2022-10-28 | 210 | 210 | 0
[6 empty] | 2022-11-25 | 350 | 350 | 0
[6 empty] | 2023-01-10 | 2450 | 2450 | 0
[6 empty] | 2023-01-25 | 2450 | 2450 | 0
[6 empty] | 2023-03-07 | 2100 | 2100 | 0
[6 empty] | 2023-05-18 | 4900 | 4900 | 0
[6 empty] | 2023-07-14 | 2100 | 2100 | 0
[6 empty] | 2023-07-19 | 2450 | 2450 | 0
[6 empty] | 2023-08-28 | 2800 | 2800 | 0
[6 empty] | 2023-10-02 | 3500 | 3500 | 0
[6 empty] | 2023-12-05 | 2100 | 2100 | 0
[6 empty] | 2023-12-18 | 2800 | 2800 | 0
[6 empty] | 2026-06-01 | 33019 | 0 | 33019
|  |  |  | PO2W-210000000359 | 2020-08-07 | 2020-12-08 | 81300 | 81300 | 0
|  |  |  | PO2W-230000001310 | 2022-09-21 | 2022-11-03 | 30600 | 30600 | 0
[6 empty] | 2022-11-28 | 1700 | 1700 | 0
[6 empty] | 2023-01-10 | 1020 | 1020 | 0
[6 empty] | 2023-01-25 | 170 | 170 | 0
[6 empty] | 2023-05-23 | 510 | 510 | 0
|  | Newton | 21st Century classroom | PO2W-200000001210, 19-101980 | 2018-09-01 | 2018-10-19 | 2312.3 | 2312.3 | 0
[6 empty] | 2019-09-16 | 12717.65 | 12717.65 | 0
[6 empty] | 2020-02-13 | 16186.1 | 16186.1 | 0
[6 empty] | 2020-06-04 | 19076.48 | 19076.48 | 0
[6 empty] | 2020-09-10 | 11738 | 11738 | 0
[6 empty] | 2021-05-07 | 19076.47 | 19076.47 | 0
[6 empty] | 2021-06-23 | 2890.38 | 2890.38 | 0
[6 empty] | 2021-12-20 | 867.11 | 867.11 | 0
[6 empty] | 2022-07-18 | 1445.18 | 1445.18 | 0
[6 empty] | 2022-10-06 | 115.61 | 115.61 | 0
[6 empty] | 2022-10-28 | 173.42 | 173.42 | 0
[6 empty] | 2023-01-10 | 2312.3 | 2312.3 | 0
[6 empty] | 2023-01-25 | 2023.28 | 2023.28 | 0
[6 empty] | 2023-03-07 | 1734.21 | 1734.21 | 0
[6 empty] | 2023-05-18 | 4046.54 | 4046.54 | 0
[6 empty] | 2023-07-14 | 1734.22 | 1734.22 | 0
[6 empty] | 2023-07-19 | 2023.26 | 2023.26 | 0
[6 empty] | 2023-08-28 | 2312.3 | 2312.3 | 0
[6 empty] | 2023-10-02 | 2890.38 | 2890.38 | 0
[6 empty] | 2023-11-21 | 2312.3 | 2312.3 | 0
[6 empty] | 2023-12-05 | 1734.22 | 1734.22 | 0
[6 empty] | 2026-06-01 | 25893.29 | 0 | 25893.29
|  |  |  | PO2W-210000000360 | 2020-08-07 | 2020-09-10 | 85965 | 85965 | 0
|  |  |  | PO2W-230000001310 | 2022-09-21 | 2022-11-03 | 20700 | 20700 | 0
[6 empty] | 2022-11-28 | 1150 | 1150 | 0
[6 empty] | 2023-01-10 | 690 | 690 | 0
[6 empty] | 2023-01-25 | 115 | 115 | 0
[6 empty] | 2023-05-23 | 345 | 345 | 0
|  |  | Interim Housing | PO1-220000000605 | 2021-12-15 | 2026-12-09 | 1725 | 0 | 1725
|  |  |  | PO2W-200000001208, 19-101983 | 2018-09-01 | 2018-10-19 | 1006.76 | 1006.76 | 0
[6 empty] | 2019-02-28 | 11511.5 | 11511.5 | 0
[6 empty] | 2019-09-16 | 12584.52 | 12584.52 | 0
[6 empty] | 2019-09-17 | 24.36 | 24.36 | 0
[6 empty] | 2020-03-10 | -24.36 | -24.36 | 0
[6 empty] | 2020-04-02 | 16611.57 | 16611.57 | 0
[6 empty] | 2021-05-07 | 8488.5 | 8488.5 | 0
[6 empty] | 2021-06-02 | 1258.45 | 1258.45 | 0
[6 empty] | 2021-12-20 | 1258.45 | 1258.45 | 0
[6 empty] | 2022-03-11 | 7550.71 | 7550.71 | 0
[6 empty] | 2022-03-24 | 3146.13 | 3146.13 | 0
[6 empty] | 2022-05-04 | 880.92 | 880.92 | 0
[6 empty] | 2022-07-19 | 377.53 | 377.53 | 0
[6 empty] | 2022-10-06 | 377.54 | 377.54 | 0
[6 empty] | 2023-01-25 | 755.07 | 755.07 | 0
[6 empty] | 2023-05-18 | 4027.05 | 4027.05 | 0
[6 empty] | 2023-05-19 | 503.38 | 503.38 | 4.6612e-12
|  |  |  | PO2W-210000000374 | 2020-08-10 | 2021-05-07 | 4520 | 4520 | 0
|  |  |  | PO2W-210000001831 | 2021-02-24 | 2021-05-07 | 5000 | 5000 | 0
|  | Sparks MS | 21st Century classroom | PO2W-200000001211, 19-101981 | 2018-09-01 | 2018-10-19 | 1757.34 | 1757.34 | 0
[6 empty] | 2019-02-27 | 11610.5 | 11610.5 | 0
[6 empty] | 2020-02-13 | 21966.75 | 21966.75 | 0
[6 empty] | 2020-02-14 | 53.76 | 53.76 | 0
[6 empty] | 2020-03-10 | -53.76 | -53.76 | 0
[6 empty] | 2020-06-18 | 14498.06 | 14498.06 | 0
[6 empty] | 2020-12-08 | 8389.5 | 8389.5 | 0
[6 empty] | 2021-05-07 | 14498.05 | 14498.05 | 0
[6 empty] | 2021-06-23 | 2196.68 | 2196.68 | 0
[6 empty] | 2021-12-20 | 659 | 659 | 0
[6 empty] | 2022-07-18 | 1098.34 | 1098.34 | 0
[6 empty] | 2022-11-03 | 219.66 | 219.66 | 0
[6 empty] | 2023-01-10 | 1757.34 | 1757.34 | 0
[6 empty] | 2023-01-25 | 1537.68 | 1537.68 | 0
[6 empty] | 2023-03-07 | 1318 | 1318 | 0
[6 empty] | 2023-05-18 | 3075.35 | 3075.35 | 0
[6 empty] | 2023-07-14 | 1318 | 1318 | 0
[6 empty] | 2023-07-19 | 1537.67 | 1537.67 | 0
[6 empty] | 2023-08-28 | 1757.34 | 1757.34 | 0
[6 empty] | 2023-10-02 | 2196.68 | 2196.68 | 0
[6 empty] | 2023-11-21 | 1757.34 | 1757.34 | 0
[6 empty] | 2023-12-05 | 8567.03 | 8567.03 | 0
[6 empty] | 2026-06-01 | 6150.69 | 0 | 6150.69
|  |  |  | PO2W-210000000403 | 2020-08-07 | 2020-12-08 | 67606 | 67606 | 0
|  |  |  | PO2W-230000001310 | 2022-09-21 | 2022-11-03 | 20700 | 20700 | 0
[6 empty] | 2022-11-28 | 1150 | 1150 | 0
[6 empty] | 2023-01-10 | 690 | 690 | 0
[6 empty] | 2023-01-25 | 115 | 115 | 0
[6 empty] | 2023-05-23 | 345 | 345 | 0
Harley Ellis Devereaux (HED) Total | [6 empty] | 848436.08 | 776148.1 | 72287.98
Haul-Away Rubbish Service Co. | Rental/Moving of container(s) | Mesa Robles | 21st Century classroom | PO1-210000000609 | 2021-02-11 | 2021-02-22 | 125.17 | 125.17 | 0
[6 empty] | 2021-02-23 | 1116.9 | 0 | 1116.9
[6 empty] | 2021-06-30 | -1116.9 | 0 | -1116.9
Haul-Away Rubbish Service Co. Total | [6 empty] | 125.17 | 125.17 | 0
Hawkins Delafield & Wood LLP | Bond Counsel and Disclosure Counsel Fees | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-07-11 | 2017-07-11 | 115000 | 115000 | 0
Hawkins Delafield & Wood LLP Total | [6 empty] | 115000 | 115000 | 0
Home Depot | Hardware to install access point for classrooms | District Office | 21st Century classroom | PO1-200000001148 | 2020-05-18 | 2020-06-17 | 198.23 | 198.23 | 0
Home Depot Total | [6 empty] | 198.23 | 198.23 | 0
ICS Service Co. | Contractor | Cedarlane | 21st Century classroom | PO2W-220000000706 | 2021-10-06 | 2021-10-21 | 2332.6 | 2332.6 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-220000000706 | 2021-10-06 | 2021-10-21 | 130.8 | 130.8 | 0
|  | Mesa Robles | 21st Century classroom | PO2W-220000000706 | 2021-10-06 | 2021-10-21 | 479.6 | 479.6 | 0
|  | Nelson | 21st Century classroom | PO2W-220000000706 | 2021-10-06 | 2021-10-21 | 141.7 | 141.7 | 0
| Equipment to repair & replace security system | Cedarlane | 21st Century classroom | PO3W-210000002406 | 2021-04-20 | 2021-06-07 | 3219.62 | 3219.62 | 0
|  | Los Altos ES | 21st Century classroom | PO3W-210000002406 | 2021-04-20 | 2021-06-07 | 2530.58 | 2530.58 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000002442 | 2021-04-22 | 2021-06-07 | 3426.33 | 3426.33 | 0
|  | Nelson | 21st Century classroom | PO3W-210000002406 | 2021-04-20 | 2021-06-07 | 2599.48 | 2599.48 | 0
|  | Workman ES | 21st Century classroom | PO2W-210000001354 | 2020-11-30 | 2021-04-16 | 1111.09 | 1111.09 | 0
[6 empty] | 2022-06-03 | 957.98 | 957.98 | 0
ICS Service Co. Total | [6 empty] | 16929.78 | 16929.78 | 0
Integrated Demolition & Remediation, Inc. (IDR) | Asbestos abatement | Workman ES | 21st Century classroom | PO2W-210000000675 | 2020-09-18 | 2021-03-24 | 4250 | 4250 | 0
| Asbestos abatement & demolition | Los Altos ES | 21st Century classroom | PO2W-200000005820 | 2020-06-05 | 2020-08-18 | 18000 | 18000 | 0
|  |  |  | PO2W-210000000146 | 2020-07-06 | 2020-10-13 | 32000 | 32000 | 0
|  | Nelson | 21st Century classroom | PO2W-210000000145 | 2020-07-06 | 2020-10-13 | 27860 | 27860 | 0
|  | Workman ES | 21st Century classroom | PO2W-210000000144 | 2020-07-06 | 2020-08-18 | 32000 | 32000 | 0
| Contractor | Nelson | 21st Century classroom | PO2W-200000003741 | 2020-01-31 | 2020-04-02 | 12975 | 12975 | 0
| Demo ceiling tiles | Baldwin | 21st Century classroom | PO2W-210000001838 | 2021-02-25 | 2021-04-23 | 50000 | 50000 | 0
|  |  |  | PO2W-210000002615 | 2021-06-14 | 2021-09-09 | 6500 | 6500 | 0
|  | Bixby | 21st Century classroom | PO2W-210000002308 | 2021-05-11 | 2021-06-28 | 52500 | 52500 | 0
|  | California | 21st Century classroom | PO2W-210000000658 | 2020-09-10 | 2021-04-23 | 40000 | 40000 | 0
|  | Del Valle | 21st Century classroom | PO2W-210000000725 | 2020-09-10 | 2020-11-30 | 42500 | 42500 | 0
|  | Grazide | 21st Century classroom | PO2W-210000001556 | 2021-01-06 | 2021-03-24 | 37500 | 37500 | 0
|  | Kwis | 21st Century classroom | PO2W-210000002060 | 2021-04-06 | 2021-05-26 | 42500 | 42500 | 0
|  |  |  | PO2W-210000002615 | 2021-06-14 | 2021-09-09 | 6500 | 6500 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-210000000884 | 2020-10-09 | 2020-11-20 | 45000 | 45000 | 0
|  | Los Molinos | 21st Century classroom | PO2W-210000001556 | 2021-01-06 | 2021-03-24 | 37500 | 37500 | 0
|  | Los Robles | 21st Century classroom | PO2W-210000002060 | 2021-04-06 | 2021-05-26 | 40000 | 40000 | 0
|  | Nelson | 21st Century classroom | PO2W-210000000884 | 2020-10-09 | 2020-11-20 | 45000 | 45000 | 0
|  | Palm | 21st Century classroom | PO2W-210000001838 | 2021-02-25 | 2021-04-23 | 40000 | 40000 | 0
|  | Sparks ES | 21st Century classroom | PO2W-210000000726 | 2020-09-10 | 2020-10-13 | 40000 | 40000 | 0
|  |  |  | PO2W-210000002615 | 2021-06-14 | 2021-09-09 | 4000 | 4000 | 0
|  | Sunset | 21st Century classroom | PO2W-210000001556 | 2021-01-06 | 2021-03-24 | 22500 | 22500 | 0
|  |  |  | PO2W-220000000024 | 2021-07-16 | 2021-09-09 | 19000 | 19000 | 0
|  | Wing Lane | 21st Century classroom | PO2W-210000001838 | 2021-02-25 | 2021-04-23 | 40000 | 40000 | 0
|  | Workman ES | 21st Century classroom | PO2W-210000000884 | 2020-10-09 | 2020-11-20 | 27500 | 27500 | 0
Integrated Demolition & Remediation, Inc. (IDR) Total | [6 empty] | 765585 | 765585 | 0
Integrated Pest Control Management | Termite service | Los Altos ES | 21st Century classroom | PO2W-210000000362 | 2020-08-07 | 2020-08-24 | 785 | 785 | 0
Integrated Pest Control Management Total | [6 empty] | 785 | 785 | 0
LACOE | Remaining funds-dep. into District's debt service fund & close acct. | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-12-14 | 2017-12-14 | 11211.58 | 11211.58 | 0
LACOE Total | [6 empty] | 11211.58 | 11211.58 | 0
Lakeshore Learning Materials | Furniture | Amar | 21st Century classroom | PO3W-200000001592 | 2019-11-01 | 2020-02-03 | 70376.3 | 70376.3 | 0
|  |  |  | PO3W-200000001595 | 2019-11-01 | 2020-02-03 | 7509.33 | 7509.33 | 0
|  |  |  | PO3W-200000001597 | 2019-11-01 | 2020-01-31 | 14794.34 | 14794.34 | 0
|  | Baldwin | 21st Century classroom | PO3W-200000001593 | 2019-11-01 | 2019-12-19 | 23186.9 | 23186.9 | 0
|  |  |  | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Bixby | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | California | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Cedarlane | 21st Century classroom | PO2W-210000001495 | 2020-12-16 | 2021-04-16 | 39663.86 | 39663.86 | 0
|  |  |  | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Del Valle | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 41441.22 | 41441.22 | 0
|  | Fairgrove | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 41441.21 | 41441.21 | 0
|  | Grandview | 21st Century classroom | PO2W-240000000105 | 2023-07-03 | 2024-12-09 | 26820.97 | 26820.97 | 0
|  |  |  | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  |  |  | PO3W-230000000930 | 2022-09-29 | 2023-07-10 | 26977.62 | 26977.62 | 0
|  |  |  | PO3W-230000001205 | 2022-10-21 | 2023-05-01 | 8979.44 | 8979.44 | 0
[6 empty] | 2023-06-05 | 10101.87 | 10101.87 | 0
|  |  |  | PO3W-240000000842 | 2023-08-02 | 2023-10-30 | 842.5 | 842.5 | 0
|  | Kwis | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 38238.17 | 38238.17 | 0
|  | Lassalette | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-210000001120 | 2020-11-10 | 2021-02-17 | 59495.79 | 59495.79 | 0
|  | Mesa Robles | 21st Century classroom | PO2W-210000001496 | 2020-12-16 | 2021-04-05 | 79327.7 | 79327.7 | 0
|  | Nelson | 21st Century classroom | PO2W-200000004769 | 2020-03-17 | 2020-08-12 | 19922.5 | 19922.5 | 0
|  |  |  | PO2W-200000004771 | 2020-03-17 | 2021-03-23 | 19922.5 | 19922.5 | 0
|  |  |  | PO2W-200000004776 | 2020-03-17 | 2020-08-12 | 19922.5 | 19922.5 | 0
|  |  |  | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 41441.22 | 41441.22 | 0
|  | Newton | 21st Century classroom | PO3W-230000001205 | 2022-10-21 | 2023-05-01 | 4489.72 | 4489.72 | 0
[6 empty] | 2023-06-05 | 17958.88 | 17958.88 | 0
|  | Palm | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 19119.08 | 19119.08 | 0
|  | Sparks ES | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Sparks MS | 21st Century classroom | PO3W-230000001205 | 2022-10-21 | 2023-05-01 | 8979.44 | 8979.44 | 0
[6 empty] | 2023-06-05 | 5612.15 | 5612.15 | 0
|  | Sunset | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Temple | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Valinda | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Wing Lane | 21st Century classroom | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
|  | Workman ES | 21st Century classroom | PO2W-210000001119 | 2020-11-10 | 2021-03-24 | 104699.05 | 104699.05 | 0
[6 empty] | 2021-04-16 | -5086.56 | -5086.56 | 0
|  |  |  | PO3W-200000001596 | 2019-11-01 | 2020-02-03 | 20720.61 | 20720.61 | 0
Lakeshore Learning Materials Total | [6 empty] | 994825.02 | 994825.02 | 0
Lenovo Education | Desktop computer(s) | Los Altos ES | 21st Century classroom | PO3W-210000000004 | 2020-07-01 | 2020-07-27 | 1401.61 | 1401.61 | 0
[6 empty] | 2020-08-05 | 19688.1 | 19688.1 | 0
|  | Nelson | 21st Century classroom | PO3W-210000000004 | 2020-07-01 | 2020-07-27 | 1752 | 1752 | 0
[6 empty] | 2020-08-05 | 24610.13 | 24610.13 | 0
|  |  |  | PO3W-210000000005 | 2020-07-01 | 2020-08-20 | 1040.26 | 1040.26 | 0
|  | Workman ES | 21st Century classroom | PO3W-210000000004 | 2020-07-01 | 2020-07-27 | 840.96 | 840.96 | 0
[6 empty] | 2020-08-05 | 11812.86 | 11812.86 | 0
Lenovo Education Total | [6 empty] | 61145.92 | 61145.92 | 0
Lightspeed Technologies, Inc. | Voice amplification system | Cedarlane | 21st Century classroom | PO3W-210000001079 | 2020-12-03 | 2021-04-13 | 45825.82 | 45825.82 | 0
|  | Los Altos ES | 21st Century classroom | PO3W-210000000029 | 2020-07-07 | 2020-07-23 | 39485.7 | 39485.7 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000002832 | 2021-05-19 | 2021-09-02 | 76987.31 | 76987.31 | 0
|  | Nelson | 21st Century classroom | PO3W-210000000029 | 2020-07-07 | 2020-07-23 | 49357.13 | 49357.13 | 0
|  | Workman ES | 21st Century classroom | PO3W-210000000029 | 2020-07-07 | 2020-07-23 | 23691.42 | 23691.42 | 0
Lightspeed Technologies, Inc. Total | [6 empty] | 235347.38 | 235347.38 | 0
Martin Container, Inc. | Rental/Moving of container(s) | Cedarlane | 21st Century classroom | PO1-210000000608 | 2021-02-10 | 2021-02-22 | 3328.8 | 3328.8 | 0
[6 empty] | 2021-09-09 | 394.2 | 394.2 | 0
[6 empty] | 2021-09-10 | 1248.3 | 0 | 1248.3
[6 empty] | 2022-03-07 | -1248.3 | 0 | -1248.3
|  | District Office | 21st Century classroom | PO1-240000000624 | 2024-01-08 | 2028-12-09 | 7000 | 0 | 7000
|  | Grandview | 21st Century classroom | PO2W-230000001433 | 2022-10-27 | 2022-12-20 | 907.5 | 907.5 | 0
[6 empty] | 2023-01-18 | 247.5 | 247.5 | 0
[6 empty] | 2023-01-25 | 247.5 | 247.5 | 0
[6 empty] | 2023-03-23 | 247.5 | 247.5 | 0
[6 empty] | 2023-03-30 | 247.5 | 247.5 | 0
[6 empty] | 2023-05-18 | 247.5 | 247.5 | 0
[6 empty] | 2023-07-18 | 495 | 495 | 0
[6 empty] | 2023-08-28 | 247.5 | 247.5 | 0
[6 empty] | 2023-10-02 | 495 | 495 | 0
[6 empty] | 2023-12-06 | 247.5 | 247.5 | 0
|  |  |  | PO2W-240000001552 | 2023-10-06 | 2024-01-22 | 247.5 | 247.5 | 0
[6 empty] | 2024-06-01 | 2227.5 | 0 | 2227.5
|  | Los Altos ES | 21st Century classroom | PO1-210000000608 | 2021-02-10 | 2021-02-22 | 958.13 | 958.13 | 0
[6 empty] | 2021-03-24 | 958.11 | 958.11 | 0
[6 empty] | 2021-05-26 | 684.37 | 684.37 | 0
[6 empty] | 2021-06-23 | 958.13 | 958.13 | 0
[6 empty] | 2021-06-30 | 136.87 | 136.87 | 0
[6 empty] | 2021-09-09 | 958.13 | 958.13 | 0
[6 empty] | 2021-09-10 | 3695.64 | 0 | 3695.64
[6 empty] | 2022-03-07 | -3695.64 | 0 | -3695.64
|  |  |  | PO2W-200000005018 | 2020-05-06 | 2020-06-24 | 3328.8 | 3328.8 | 0
|  |  |  | PO2W-200000005483 | 2020-06-03 | 2020-08-18 | 1664.4 | 1664.4 | 0
|  |  |  | PO2W-210000000059 | 2020-07-06 | 2020-08-17 | 1664.4 | 1664.4 | 0
|  |  |  | PO2W-210000000340 | 2020-07-06 | 2020-10-13 | 1664.4 | 1664.4 | 0
|  | Mesa Robles | 21st Century classroom | PO1-210000000608 | 2021-02-10 | 2021-02-22 | 952.64 | 952.64 | 0
[6 empty] | 2021-03-24 | 667.94 | 667.94 | 0
[6 empty] | 2021-05-26 | 531.07 | 531.07 | 0
[6 empty] | 2021-06-23 | 1062.14 | 1062.14 | 0
[6 empty] | 2021-09-09 | 1850.54 | 1850.54 | 0
[6 empty] | 2021-09-10 | 2485.7 | 0 | 2485.7
[6 empty] | 2022-03-07 | -2485.7 | 0 | -2485.7
|  |  |  | PO2W-200000005019 | 2020-05-06 | 2020-06-24 | 1664.4 | 1664.4 | 0
|  |  |  | PO2W-210000000975 | 2020-10-22 | 2021-02-05 | 4993.2 | 4993.2 | 0
|  |  | Interim Housing | PO2W-200000005377 | 2020-05-27 | 2020-06-23 | 500 | 500 | 0
|  | Nelson | 21st Century classroom | PO1-210000000608 | 2021-02-10 | 2021-02-22 | 821.26 | 821.26 | 0
[6 empty] | 2021-03-24 | 684.37 | 684.37 | 0
[6 empty] | 2021-05-26 | 547.5 | 547.5 | 0
[6 empty] | 2021-06-23 | 684.39 | 684.39 | 0
[6 empty] | 2021-06-30 | 136.87 | 136.87 | 0
[6 empty] | 2021-09-09 | 684.39 | 684.39 | 0
[6 empty] | 2021-09-10 | 2737.47 | 0 | 2737.47
[6 empty] | 2022-03-07 | -2737.47 | 0 | -2737.47
|  |  |  | PO2W-200000005020 | 2020-05-06 | 2020-06-24 | 3328.8 | 3328.8 | 0
|  |  |  | PO2W-200000005484 | 2020-06-03 | 2020-08-18 | 1664.4 | 1664.4 | 0
|  |  |  | PO2W-210000000883 | 2020-10-09 | 2022-03-06 | 1664.4 | 0 | 1664.4
[6 empty] | 2022-03-07 | -1664.4 | 0 | -1664.4
|  | Newton | 21st Century classroom | PO2W-230000001433 | 2022-10-27 | 2023-01-17 | 1149.74 | 1149.74 | 0
[6 empty] | 2023-01-25 | 246.37 | 246.37 | 0
[6 empty] | 2023-03-23 | 246.37 | 246.37 | 0
[6 empty] | 2023-03-30 | 246.38 | 246.38 | 0
[6 empty] | 2023-05-23 | 246.38 | 246.38 | 0
[6 empty] | 2023-07-19 | 246.37 | 246.37 | 0
[6 empty] | 2023-07-21 | 492.74 | 492.74 | 0
[6 empty] | 2023-07-26 | -213.52 | -213.52 | 0
[6 empty] | 2023-07-27 | 213.52 | 213.52 | 0
[6 empty] | 2023-10-03 | 492.76 | 492.76 | 0
[6 empty] | 2024-01-08 | 246.38 | 246.38 | 0
[6 empty] | 2024-01-09 | 16.51 | 0 | 16.51
[6 empty] | 2024-01-16 | -16.51 | 0 | -16.51
|  |  |  | PO2W-240000001552 | 2023-10-06 | 2024-01-22 | 246.37 | 246.37 | 0
[6 empty] | 2024-06-01 | 2228.63 | 0 | 2228.63
|  | Sparks MS | 21st Century classroom | PO2W-230000001433 | 2022-10-27 | 2022-12-20 | 907.5 | 907.5 | 0
[6 empty] | 2023-01-17 | 247.5 | 247.5 | 0
[6 empty] | 2023-01-25 | 247.5 | 247.5 | 0
[6 empty] | 2023-03-07 | 247.5 | 247.5 | 0
[6 empty] | 2023-03-23 | 247.5 | 247.5 | 0
[6 empty] | 2023-05-18 | 247.5 | 247.5 | 0
[6 empty] | 2023-06-05 | 247.5 | 247.5 | 0
[6 empty] | 2023-07-18 | 247.5 | 247.5 | 0
[6 empty] | 2023-07-19 | 247.5 | 247.5 | 0
[6 empty] | 2023-07-26 | -206.25 | -206.25 | 0
[6 empty] | 2023-07-27 | 206.25 | 206.25 | 0
[6 empty] | 2023-10-02 | 495 | 495 | 0
[6 empty] | 2023-12-06 | 247.5 | 247.5 | 0
|  |  |  | PO2W-240000001552 | 2023-10-06 | 2024-06-01 | 2475 | 0 | 2475
|  | Workman ES | 21st Century classroom | PO1-210000000608 | 2021-02-10 | 2021-02-22 | 825.02 | 825.02 | 0
[6 empty] | 2021-03-24 | 687.52 | 687.52 | 0
[6 empty] | 2021-05-26 | 550.01 | 550.01 | 0
[6 empty] | 2021-06-23 | 825.02 | 825.02 | 0
[6 empty] | 2021-06-30 | 137.5 | 137.5 | 0
[6 empty] | 2021-09-09 | 687.52 | 687.52 | 0
[6 empty] | 2021-09-10 | 1488.66 | 0 | 1488.66
[6 empty] | 2022-03-07 | -1488.66 | 0 | -1488.66
|  |  |  | PO2W-200000005021 | 2020-05-06 | 2020-06-24 | 1373 | 1373 | 0
[6 empty] | 2020-07-01 | 1971 | 1971 | 0
|  |  |  | PO2W-200000005485 | 2020-06-03 | 2020-08-18 | 1672 | 1672 | 0
|  |  |  | PO2W-210000001957 | 2021-03-12 | 2021-03-30 | 137.5 | 137.5 | 0
[6 empty] | 2021-05-26 | 275 | 275 | 0
[6 empty] | 2021-09-09 | 275 | 275 | 0
[6 empty] | 2021-09-10 | 2359.5 | 0 | 2359.5
[6 empty] | 2022-03-07 | -2359.5 | 0 | -2359.5
Martin Container, Inc. Total | [6 empty] | 72187.23 | 58256.1 | 13931.13
Masek Consulting Services, Inc. | Asbestos & lead-based paint survey | Amar | 21st Century classroom | PO2W-200000005314 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | Baldwin | 21st Century classroom | PO2W-200000005315 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | Bixby | 21st Century classroom | PO2W-200000005316 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | California | 21st Century classroom | PO2W-200000005317 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | Cedarlane | 21st Century classroom | PO2W-200000005389 | 2020-05-29 | 2020-10-13 | 2800 | 2800 | 0
|  | Del Valle | 21st Century classroom | PO2W-200000005318 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | Dibble | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-20 | 2700 | 2700 | 0
|  | Fairgrove | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-13 | 2700 | 2700 | 0
|  | Grandview | 21st Century classroom | PO2W-200000005390 | 2020-05-29 | 2020-06-19 | 2900 | 2900 | 0
|  | Grazide | 21st Century classroom | PO2W-200000005319 | 2020-05-20 | 2020-08-17 | 2550 | 2550 | 0
|  | Kwis | 21st Century classroom | PO2W-200000005320 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | La Puente HS | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2021-03-23 | 6900 | 6900 | 0
|  | Lassalette | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-13 | 2800 | 2800 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-200000004874 | 2020-04-15 | 2020-06-03 | 2800 | 2800 | 0
|  | Los Altos HS | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2021-01-19 | 4350 | 4350 | 0
|  | Los Molinos | 21st Century classroom | PO2W-200000005321 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | Los Robles | 21st Century classroom | PO2W-200000005322 | 2020-05-20 | 2020-08-17 | 2800 | 2800 | 0
|  | Mesa Robles | 21st Century classroom | PO2W-200000005391 | 2020-05-29 | 2020-06-19 | 2950 | 2950 | 0
|  |  |  | PO2W-210000000986 | 2020-10-23 | 2021-02-04 | 1480 | 1480 | 0
|  | Nelson | 21st Century classroom | PO2W-200000004875 | 2020-04-15 | 2020-06-03 | 2530 | 2530 | 0
|  | Newton | 21st Century classroom | PO2W-200000005392 | 2020-05-29 | 2020-10-13 | 2950 | 2950 | 0
|  | Orange Grove | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-13 | 2800 | 2800 | 0
|  | Palm | 21st Century classroom | PO2W-200000005323 | 2020-05-20 | 2020-08-17 | 2500 | 2500 | 0
|  | Sierra Vista | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-13 | 3000 | 3000 | 0
|  | Sparks ES | 21st Century classroom | PO2W-200000005324 | 2020-05-20 | 2020-08-17 | 2670 | 2670 | 0
|  | Sparks MS | 21st Century classroom | PO2W-200000005393 | 2020-05-29 | 2020-06-19 | 2950 | 2950 | 0
|  | Sunset | 21st Century classroom | PO2W-200000005325 | 2020-05-20 | 2020-08-17 | 2700 | 2700 | 0
|  | Temple | 21st Century classroom | PO2W-200000005326 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | Valinda | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-13 | 3000 | 3000 | 0
|  | Valley | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-13 | 2700 | 2700 | 0
|  | Willow | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-20 | 2700 | 2700 | 0
|  | Wilson HS | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2020-10-20 | 3400 | 3400 | 0
|  | Wing Lane | 21st Century classroom | PO2W-200000005327 | 2020-05-20 | 2020-08-17 | 2600 | 2600 | 0
|  | Workman ES | 21st Century classroom | PO2W-200000004876 | 2020-04-15 | 2020-06-03 | 2500 | 2500 | 0
|  |  |  | PO2W-200000005541 | 2020-06-03 | 2020-06-26 | 1200 | 1200 | 0
|  | Workman HS | 21st Century classroom | PO1-210000000427 | 2020-08-26 | 2021-01-19 | 4150 | 4150 | 0
| Asbestos survey | Cedarlane | Fire Alarm replacement | PO2W-200000004872 | 2020-04-13 | 2020-04-29 | 800 | 800 | 0
|  | Grandview | Fire Alarm replacement | PO2W-200000004873 | 2020-04-13 | 2020-04-29 | 850 | 850 | 0
| Oversight asbestos abatement | Cedarlane | 21st Century classroom | PO2W-210000000995 | 2020-10-27 | 2021-02-04 | 6950 | 6950 | 0
[6 empty] | 2023-05-09 | 4850 | 0 | 4850
[6 empty] | 2023-05-10 | -4850 | 0 | -4850
|  |  |  | PO2W-210000001656 | 2021-01-27 | 2021-03-22 | 6950 | 6950 | 0
[6 empty] | 2023-05-09 | 500 | 0 | 500
[6 empty] | 2023-05-10 | -500 | 0 | -500
|  |  |  | PO2W-210000001982 | 2021-03-19 | 2021-04-16 | 4750 | 4750 | 0
[6 empty] | 2023-05-09 | 2200 | 0 | 2200
[6 empty] | 2023-05-10 | -2200 | 0 | -2200
|  |  |  | PO2W-210000002278 | 2021-05-06 | 2021-05-25 | 3050 | 3050 | 0
[6 empty] | 2021-09-08 | 2200 | 2200 | 0
[6 empty] | 2023-05-09 | 2300 | 0 | 2300
[6 empty] | 2023-05-10 | -2300 | 0 | -2300
|  |  |  | PO2W-210000002602 | 2021-06-07 | 2021-06-22 | 425 | 425 | 0
|  |  |  | PO2W-220000000246 | 2021-08-10 | 2021-09-30 | 2200 | 2200 | 0
[6 empty] | 2023-05-09 | 400 | 0 | 400
[6 empty] | 2023-05-10 | -400 | 0 | -400
|  | Grandview | 21st Century classroom | PO2W-230000001411 | 2022-10-19 | 2022-11-14 | 7100 | 7100 | 0
[6 empty] | 2023-07-14 | 2550 | 2550 | 0
[6 empty] | 2023-07-15 | 550 | 0 | 550
[6 empty] | 2023-07-16 | -550 | 0 | -550
|  |  |  | PO2W-230000004063 | 2023-05-18 | 2023-07-14 | 7100 | 7100 | 0
[6 empty] | 2023-07-15 | 550 | 0 | 550
[6 empty] | 2023-07-16 | -550 | 0 | -550
|  |  |  | PO2W-240000000516 | 2023-08-24 | 2023-10-24 | 3550 | 3550 | 0
|  |  |  | PO2W-240000000757 | 2023-07-26 | 2023-10-24 | 3550 | 3550 | 0
[6 empty] | 2026-12-09 | 1000 | 0 | 1000
|  | La Puente HS | 21st Century classroom | (blank) | 2024-01-12 | 2027-06-01 | 32500 | 0 | 32500
|  | Los Altos ES | 21st Century classroom | PO2W-210000000060 | 2020-07-06 | 2020-08-17 | 7775 | 7775 | 0
[6 empty] | 2023-05-09 | 6125 | 0 | 6125
[6 empty] | 2023-05-10 | -6125 | 0 | -6125
|  | Mesa Robles | 21st Century classroom | PO2W-210000000976 | 2020-10-22 | 2021-02-04 | 4400 | 4400 | 0
[6 empty] | 2023-05-09 | 1600 | 0 | 1600
[6 empty] | 2023-05-10 | -1600 | 0 | -1600
|  |  |  | PO2W-210000001656 | 2021-01-27 | 2021-03-22 | 4400 | 4400 | 0
[6 empty] | 2023-05-09 | 4900 | 0 | 4900
[6 empty] | 2023-05-10 | -4900 | 0 | -4900
|  |  |  | PO2W-210000001978 | 2021-03-18 | 2021-04-16 | 7910 | 7910 | 0
[6 empty] | 2023-05-09 | 1440 | 0 | 1440
[6 empty] | 2023-05-10 | -1440 | 0 | -1440
|  |  |  | PO2W-210000002602 | 2021-06-07 | 2021-06-22 | 850 | 850 | 0
|  | Nelson | 21st Century classroom | PO2W-210000000061 | 2020-07-06 | 2020-10-13 | 3975 | 3975 | 0
[6 empty] | 2023-05-09 | 4125 | 0 | 4125
[6 empty] | 2023-05-10 | -4125 | 0 | -4125
|  | Newton | 21st Century classroom | PO2W-230000001412 | 2022-10-19 | 2022-11-14 | 5550 | 5550 | 0
[6 empty] | 2023-05-09 | 1000 | 0 | 1000
[6 empty] | 2023-05-10 | -1000 | 0 | -1000
|  |  |  | PO2W-230000003345 | 2023-03-13 | 2023-05-16 | 2000 | 2000 | 0
[6 empty] | 2023-06-29 | 2000 | 2000 | 0
[6 empty] | 2027-06-01 | 1000 | 0 | 1000
|  |  |  | PO2W-230000004340 | 2023-06-15 | 2023-09-15 | 2550 | 2550 | 0
[6 empty] | 2024-06-01 | 2000 | 0 | 2000
|  |  |  | PO2W-240000000758 | 2023-07-26 | 2023-10-16 | 3000 | 3000 | 0
[6 empty] | 2026-12-09 | 8200 | 0 | 8200
|  | Sparks MS | 21st Century classroom | PO2W-230000001413 | 2022-10-19 | 2022-12-05 | 2000 | 2000 | 0
[6 empty] | 2023-07-20 | 2550 | 2550 | 0
[6 empty] | 2023-07-21 | 450 | 0 | 450
[6 empty] | 2023-07-22 | -450 | 0 | -450
|  |  |  | PO2W-230000004062 | 2023-04-21 | 2023-07-14 | 3000 | 3000 | 0
|  | Workman ES | 21st Century classroom | PO2W-210000000062 | 2020-07-06 | 2020-08-17 | 6775 | 6775 | 0
[6 empty] | 2023-05-09 | 4300 | 0 | 4300
[6 empty] | 2023-05-10 | -4300 | 0 | -4300
|  |  |  | PO2W-210000000585 | 2020-09-11 | 2020-11-19 | 825 | 825 | 0
[6 empty] | 2023-05-09 | 100 | 0 | 100
[6 empty] | 2023-05-10 | -100 | 0 | -100
|  | Workman HS | 21st Century classroom | (blank) | 2024-01-12 | 2027-06-01 | 3500 | 0 | 3500
| Pre-demo asbestos & lead-based paint | Mesa Robles | Interim Housing | PO2W-200000003739 | 2020-01-31 | 2020-06-03 | 1280 | 1280 | 0
Masek Consulting Services, Inc. Total | [6 empty] | 263945 | 215745 | 48200
Masters Contracting Corp. | Contractor | Cedarlane | 21st Century classroom | PO2W-210000000983 | 2020-10-23 | 2021-01-22 | 907368.75 | 907368.75 | 0
[6 empty] | 2021-03-17 | 137481.65 | 137481.65 | 0
[6 empty] | 2021-04-07 | 346238.1 | 346238.1 | 0
[6 empty] | 2021-05-21 | 325256.77 | 325256.77 | 0
[6 empty] | 2021-06-18 | 161808.95 | 161808.95 | 0
[6 empty] | 2021-07-12 | 470243.82 | 470243.82 | 0
[6 empty] | 2021-08-17 | 277494.35 | 277494.35 | 0
[6 empty] | 2021-11-23 | 143188.64 | 143188.64 | 0
[6 empty] | 2021-12-20 | 71418.97 | 71418.97 | 0
[6 empty] | 2022-07-05 | 99528.2 | 99528.2 | 0
[6 empty] | 2022-07-06 | 49971.8 | 49971.8 | 0
[6 empty] | 2022-08-18 | -49971.8 | -49971.8 | 0
[6 empty] | 2022-10-27 | 49971.8 | 49971.8 | 0
|  |  |  | PO2W-220000002554 | 2022-04-13 | 2022-07-06 | 50768.84 | 50768.84 | 0
[6 empty] | 2022-08-18 | -50768.84 | -50768.84 | 0
[6 empty] | 2022-10-28 | 84883.51 | 84883.51 | 0
[6 empty] | 2023-04-27 | 125925.8 | 125925.8 | 0
|  |  | Interim Housing | PO2W-210000000983 | 2020-10-23 | 2021-01-22 | 443898.33 | 443898.33 | 0
[6 empty] | 2021-03-23 | 13195.5 | 13195.5 | 0
[6 empty] | 2021-04-07 | 247627 | 247627 | 0
[6 empty] | 2021-05-21 | 64002.29 | 64002.29 | 0
[6 empty] | 2021-12-20 | 15026.88 | 15026.88 | 0
[6 empty] | 2022-05-23 | 41250 | 41250 | 0
|  |  |  | PO2W-220000002312 | 2022-03-25 | 2022-05-23 | 25953.39 | 25953.39 | 0
[6 empty] | 2022-10-27 | 44787.02 | 44787.02 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-200000005828 | 2020-06-04 | 2020-07-31 | 680168.65 | 680168.65 | 0
[6 empty] | 2020-08-18 | 63129.4 | 63129.4 | 0
[6 empty] | 2020-09-28 | 306478.32 | 306478.32 | 0
[6 empty] | 2020-11-09 | 589220.4 | 589220.4 | 0
[6 empty] | 2020-12-18 | 187365.65 | 187365.65 | 0
[6 empty] | 2021-01-15 | 79831.6 | 79831.6 | 0
[6 empty] | 2021-03-16 | 153632.87 | 153632.87 | 0
[6 empty] | 2021-05-21 | 46286.31 | 46286.31 | 0
[6 empty] | 2022-05-06 | 3836.8 | 3836.8 | 0
[6 empty] | 2022-09-15 | 111050 | 111050 | 0
|  |  |  | PO2W-220000002619 | 2022-06-14 | 2022-09-15 | 32583.58 | 32583.58 | 0
|  | Nelson | 21st Century classroom | PO2W-200000005829 | 2020-06-04 | 2020-07-31 | 496863.78 | 496863.78 | 0
[6 empty] | 2020-08-18 | 592077.52 | 592077.52 | 0
[6 empty] | 2020-09-28 | 301087.74 | 301087.74 | 0
[6 empty] | 2020-11-09 | 282947.52 | 282947.52 | 0
[6 empty] | 2021-01-15 | 177129.4 | 177129.4 | 0
[6 empty] | 2021-01-20 | 71383.63 | 71383.63 | 0
[6 empty] | 2021-03-16 | 107716.68 | 107716.68 | 0
[6 empty] | 2021-05-21 | 37289.79 | 37289.79 | 0
[6 empty] | 2022-05-23 | 123503.94 | 123503.94 | 0
|  |  |  | PO2W-220000002620 | 2022-06-14 | 2023-07-05 | 1400 | 0 | 1400
[6 empty] | 2023-07-06 | -1400 | 0 | -1400
Masters Contracting Corp. Total | [6 empty] | 8540133.3 | 8540133.3 | 0
Mijac Alarm | Alarm for portables | Los Altos ES | Interim Housing | PO1-200000000617 | 2019-10-01 | 2019-11-05 | 79.5 | 79.5 | 0
[6 empty] | 2020-01-14 | 79.5 | 79.5 | 0
[6 empty] | 2020-04-07 | 79.5 | 79.5 | 0
[6 empty] | 2020-08-17 | 79.5 | 79.5 | 0
[6 empty] | 2020-10-13 | 79.5 | 79.5 | 0
[6 empty] | 2021-01-15 | 79.5 | 79.5 | 0
[6 empty] | 2021-04-16 | 79.5 | 79.5 | 0
[6 empty] | 2021-11-30 | 159 | 159 | 0
[6 empty] | 2021-12-09 | 2782.5 | 0 | 2782.5
[6 empty] | 2022-03-23 | -2782.5 | 0 | -2782.5
Mijac Alarm Total | [6 empty] | 715.5 | 715.5 | 0
Mobile Modular Management Corp. | Portable classrooms | Cedarlane | Interim Housing | PO2W-200000003188, PO2W-200000001048, 19-107585 | 2019-03-20 | 2020-02-18 | 218488.74 | 218488.74 | 0
|  |  |  | PO2W-200000003189, PO2W-200000001048, 19-107585 | 2019-03-20 | 2021-02-05 | 21300 | 21300 | 0
|  | Los Altos ES | Interim Housing | PO2W-200000001050, 19-107587 | 2019-03-20 | 2020-01-16 | 236959.74 | 236959.74 | 0
|  | Mesa Robles | Interim Housing | PO2W-200000003190, PO2W-200000001052, 19-107584 | 2019-03-20 | 2020-02-18 | 436977.48 | 436977.48 | 0
|  |  |  | PO2W-200000003191, PO2W-200000001052, 19-107584 | 2019-03-20 | 2020-08-18 | 42600 | 42600 | 0
|  | Newton | Interim Housing | PO2W-200000003192, PO2W-200000001051, 19-107586 | 2019-03-20 | 2020-02-18 | 218488.74 | 218488.74 | 0
| Portable classrooms | Newton | Interim Housing | PO2W-200000003193, PO2W-200000001051, 19-107586 | 2019-03-20 | 2022-03-16 | 21300 | 21300 | 0
Mobile Modular Management Corp. Total | [6 empty] | 1196114.7 | 1196114.7 | 0
Montague DeRose and Associates, LLC | Municipal Advisory services | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-07-12 | 2017-07-12 | 42740 | 42740 | 0
Montague DeRose and Associates, LLC Total | [6 empty] | 42740 | 42740 | 0
Moody's Investors Service, Inc. | Rating Agency Fee | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-07-31 | 2017-07-31 | 37000 | 37000 | 0
Moody's Investors Service, Inc. Total | [6 empty] | 37000 | 37000 | 0
Office p.S. Architecture + Urbanism + Design | Architect | Mesa Robles | 21st Century classroom | 19-100488 | 2018-07-01 | 2019-02-26 | 7100 | 7100 | 0
[6 empty] | 2019-02-27 | 24900 | 0 | 24900
[6 empty] | 2019-06-05 | -24900 | 0 | -24900
|  |  |  | 19-100492, 18-109572 | 2018-06-13 | 2018-06-28 | 4007.97 | 4007.97 | 0
[6 empty] | 2018-07-17 | 4007.97 | 4007.97 | 0
[6 empty] | 2018-07-18 | 192382.83 | 0 | 192382.83
[6 empty] | 2019-06-05 | -192382.83 | 0 | -192382.83
|  |  |  | PO2W-200000001909 | 2018-07-01 | 2019-10-28 | 411.5 | 411.5 | 0
|  |  | Interim Housing | 19-100493, 18-109556 | 2018-06-13 | 2018-06-28 | 1286.49 | 1286.49 | 0
[6 empty] | 2018-07-17 | 1286.49 | 1286.49 | 0
[6 empty] | 2018-07-18 | 61751.42 | 0 | 61751.42
[6 empty] | 2019-06-05 | -61751.42 | 0 | -61751.42
|  |  |  | PO2W-200000001924 | 2018-07-01 | 2019-10-28 | 3894.95 | 3894.95 | 0
Office p.S. Architecture + Urbanism + Design Total | [6 empty] | 21995.37 | 21995.37 | 0
Optima | Contractor | Amar | Drinking Fountain replacement | PO2W-200000002201 | 2019-08-20 | 2020-02-20 | 8200 | 8200 | 0
|  | Los Altos HS | Drinking Fountain replacement | PO2W-200000002204 | 2019-08-20 | 2020-02-10 | 6600 | 6600 | 0
|  | Mesa Robles | Drinking Fountain replacement | PO2W-200000002203 | 2019-08-20 | 2020-02-10 | 11000 | 11000 | 0
|  | Sunset | Drinking Fountain replacement | PO1-200000000833 | 2019-12-18 | 2021-04-23 | 18000 | 18000 | 0
|  | Wedgeworth | Drinking Fountain replacement | PO1-200000000834 | 2019-12-18 | 2021-04-07 | 3502.75 | 3502.75 | 0
[6 empty] | 2023-03-02 | 2997.25 | 0 | 2997.25
[6 empty] | 2023-03-03 | -2997.25 | 0 | -2997.25
|  | Wing Lane | Drinking Fountain replacement | PO2W-200000002202 | 2019-08-20 | 2020-02-20 | 6800 | 6800 | 0
Optima Total | [6 empty] | 54102.75 | 54102.75 | 0
Orbach Huff Suarez + Henderson, LLP | Attorney fees | District Office | 21st Century classroom | PO1-200000001027 | 2020-02-26 | 2020-03-04 | 4647.5 | 4647.5 | 0
[6 empty] | 2020-04-07 | 2286.63 | 2286.63 | 0
[6 empty] | 2020-04-22 | 1799 | 1799 | 0
[6 empty] | 2020-06-30 | 1266.87 | 1266.87 | 0
[6 empty] | 2020-07-01 | -1266.87 | -1266.87 | 0
[6 empty] | 2020-07-02 | 1266.87 | 0 | 1266.87
[6 empty] | 2021-06-30 | -1266.87 | 0 | -1266.87
|  |  |  | PO1-230000000406 | 2022-07-01 | 2022-10-04 | 795 | 795 | 0
[6 empty] | 2022-11-28 | 6180.49 | 6180.49 | 0
[6 empty] | 2023-01-04 | 2652.5 | 2652.5 | 0
[6 empty] | 2023-01-23 | 4818.49 | 4818.49 | 0
[6 empty] | 2023-01-26 | 2462.79 | 2462.79 | 0
[6 empty] | 2023-03-17 | 8898.5 | 8898.5 | 0
[6 empty] | 2023-06-05 | 4865.41 | 4865.41 | 0
[6 empty] | 2023-06-22 | 6380 | 6380 | 0
[6 empty] | 2024-01-25 | 809.03 | 809.03 | 0
[6 empty] | 2026-12-09 | 212137.79 | 0 | 212137.79
|  |  |  | PO1-240000000018 | 2023-07-12 | 2024-06-30 | 50000 | 0 | 50000
|  |  |  | PO2W-200000004282 | 2020-01-29 | 2020-02-27 | 3492.5 | 3492.5 | 0
Orbach Huff Suarez + Henderson, LLP Total | [6 empty] | 312225.63 | 50087.84 | 262137.79
PBK Architects | Architect | Cedarlane | 21st Century classroom | PO2W-200000000856, 19-100508, 18-109907 | 2018-06-26 | 2018-10-12 | 2672 | 2672 | 0
[6 empty] | 2019-04-22 | 2672 | 2672 | 0
[6 empty] | 2019-10-10 | 21376 | 21376 | 0
[6 empty] | 2020-04-17 | 7481.6 | 7481.6 | 0
[6 empty] | 2020-06-22 | 45958.4 | 45958.4 | 0
[6 empty] | 2020-08-18 | 20770 | 20770 | 0
[6 empty] | 2020-10-13 | 2338 | 2338 | 0
[6 empty] | 2020-10-21 | 2672 | 2672 | 0
[6 empty] | 2021-02-05 | 3340 | 3340 | 0
[6 empty] | 2022-01-25 | 11356 | 11356 | 0
[6 empty] | 2022-01-26 | 5678 | 5678 | 0
[6 empty] | 2022-06-30 | 12358 | 12358 | 0
[6 empty] | 2022-08-18 | -12358 | -12358 | 0
[6 empty] | 2022-12-12 | 473.59 | 473.59 | 0
[6 empty] | 2026-06-01 | 26812.41 | 0 | 26812.41
|  |  | Interim Housing | PO2W-200000001212, 19-100509, 18-109906 | 2018-06-26 | 2018-10-12 | 1146.66 | 1146.66 | 0
[6 empty] | 2019-02-27 | 8313.29 | 8313.29 | 0
[6 empty] | 2019-05-23 | 15479.91 | 15479.91 | 0
[6 empty] | 2019-09-20 | 8500 | 8500 | 0
[6 empty] | 2019-10-01 | 9459.94 | 9459.94 | 0
[6 empty] | 2020-08-18 | 11679.99 | 11679.99 | 0
[6 empty] | 2021-02-05 | 286.66 | 286.66 | 0
[6 empty] | 2022-01-26 | 16633.25 | 16633.25 | 0
[6 empty] | 2022-06-30 | 2866.65 | 2866.65 | 0
[6 empty] | 2022-08-18 | -2866.65 | -2866.65 | 0
[6 empty] | 2022-12-12 | 100 | 100 | 0
[6 empty] | 2026-06-01 | 5733.3 | 0 | 5733.3
|  |  |  | PO2W-230000002021 | 2022-12-05 | 2023-01-17 | 1464.01 | 1464.01 | 0
|  | Fairgrove | 21st Century classroom | PO1-210000000684 | 2021-05-03 | 2022-06-30 | 19967.5 | 19967.5 | 0
[6 empty] | 2022-08-18 | -19967.5 | -19967.5 | 0
[6 empty] | 2028-06-01 | 407500 | 0 | 407500
|  |  | Interim Housing | PO1-210000000686 | 2021-05-03 | 2028-06-01 | 0 | 0 | 0
|  | Mesa Robles | 21st Century classroom | PO2W-200000000098 | 2019-07-01 | 2020-04-02 | 45600 | 45600 | 0
[6 empty] | 2020-04-17 | 12768 | 12768 | 0
[6 empty] | 2020-06-18 | 78432 | 78432 | 0
[6 empty] | 2020-08-18 | 2850 | 2850 | 0
[6 empty] | 2020-10-13 | 3990 | 3990 | 0
[6 empty] | 2021-02-05 | 4560 | 4560 | 0
[6 empty] | 2022-01-25 | 61560 | 61560 | 0
[6 empty] | 2022-07-05 | 30560 | 30560 | 0
[6 empty] | 2022-11-14 | 2280 | 2280 | 0
[6 empty] | 2022-12-14 | 780.44 | 780.44 | 0
[6 empty] | 2026-06-01 | 4619.56 | 0 | 4619.56
|  | Orange Grove | 21st Century classroom | PO1-210000000685 | 2021-05-03 | 2022-06-30 | 10878 | 10878 | 0
[6 empty] | 2022-08-18 | -10878 | -10878 | 0
[6 empty] | 2028-06-01 | 222000 | 0 | 222000
|  |  | Interim Housing | PO1-210000000687 | 2021-05-03 | 2028-06-01 | 0 | 0 | 0
PBK Architects Total | [6 empty] | 1109897.01 | 443231.74 | 666665.27
PI Manufacturing Corp. | Computer cables | Cedarlane | 21st Century classroom | PO3W-210000001096 | 2020-12-03 | 2021-02-10 | 1351.5 | 1351.5 | 0
|  | Los Altos ES | 21st Century classroom | PO2W-210000001349 | 2020-11-30 | 2021-02-10 | 1086.6 | 1086.6 | 0
|  | Mesa Robles | 21st Century classroom | PO3W-210000001095 | 2020-12-03 | 2021-02-17 | 1710.17 | 1710.17 | 0
[6 empty] | 2021-06-24 | 436.91 | 436.91 | 0
|  | Nelson | 21st Century classroom | PO2W-210000001350 | 2020-11-30 | 2021-02-10 | 1023.66 | 1023.66 | 0
|  | Workman ES | 21st Century classroom | PO2W-210000001351 | 2020-11-30 | 2021-02-10 | 1086.6 | 1086.6 | 0
PI Manufacturing Corp. Total | [6 empty] | 6695.44 | 6695.44 | 0
Rbc Capital Markets, LLC | Hotel reimb. during rating agency presentations in San Francisco | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-07-11 | 2017-07-11 | 647.68 | 647.68 | 0
| Reimb. Continuing Disclosure Report (DAC) | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-08-04 | 2017-08-04 | 550 | 550 | 0
Rbc Capital Markets, LLC Total | [6 empty] | 1197.68 | 1197.68 | 0
S&P Global Ratings | Rating Agency Fee | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-08-03 | 2017-08-03 | 35000 | 35000 | 0
S&P Global Ratings Total | [6 empty] | 35000 | 35000 | 0
San Gabriel Tribune | Newspaper Advertisement | La Puente HS | 21st Century classroom | (blank) | 2024-02-01 | 2024-06-30 | 417.06 | 0 | 417.06
|  | Workman HS | 21st Century classroom | (blank) | 2024-02-01 | 2024-06-30 | 417.06 | 0 | 417.06
San Gabriel Tribune Total | [6 empty] | 834.12 | 0 | 834.12
Schneider Electric Buildings Americas, Inc. | Contractor | Amar | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 17165.07 | 17165.07 | 0
[6 empty] | 2023-03-07 | 85825.38 | 85825.38 | 0
[6 empty] | 2023-12-18 | 68660.3 | 68660.3 | 0
[6 empty] | 2023-12-19 | 9034.25 | 9034.25 | 0
|  | Baldwin | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 29986.18 | 29986.18 | 0
[6 empty] | 2020-10-21 | 89958.54 | 89958.54 | 0
[6 empty] | 2021-06-17 | 179917.08 | 179917.08 | 0
[6 empty] | 2023-12-19 | 15782.2 | 15782.2 | 0
|  | Bixby | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 28196.47 | 28196.47 | 0
[6 empty] | 2021-09-09 | 253768.28 | 253768.28 | 0
[6 empty] | 2023-12-19 | 14840.25 | 14840.25 | 0
|  | California | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 22513.29 | 22513.29 | 0
[6 empty] | 2021-01-08 | 202619.61 | 202619.61 | 0
[6 empty] | 2023-12-19 | 11849.1 | 11849.1 | 0
|  | Del Valle | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 31652.38 | 31652.38 | 0
[6 empty] | 2020-10-21 | 94957.16 | 94957.16 | 0
[6 empty] | 2021-01-08 | 189914.31 | 189914.31 | 0
[6 empty] | 2023-12-19 | 16659.15 | 16659.15 | 0
|  | Grazide | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 26751.81 | 26751.81 | 0
[6 empty] | 2020-10-21 | 80255.43 | 80255.43 | 0
[6 empty] | 2021-04-27 | 160510.86 | 160510.86 | 0
[6 empty] | 2023-12-19 | 14079.9 | 14079.9 | 0
|  | Kwis | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 25747.66 | 25747.66 | 0
[6 empty] | 2021-06-17 | 231728.94 | 231728.94 | 0
[6 empty] | 2023-12-19 | 13551.4 | 13551.4 | 0
|  | Los Altos ES | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 22069.45 | 22069.45 | 0
[6 empty] | 2021-01-08 | 198625.05 | 198625.05 | 0
[6 empty] | 2023-12-19 | 11615.5 | 11615.5 | 0
|  | Los Molinos | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 34108.32 | 34108.32 | 0
[6 empty] | 2020-10-21 | 102324.98 | 102324.98 | 0
[6 empty] | 2021-04-27 | 204649.95 | 204649.95 | 0
[6 empty] | 2023-12-19 | 17951.75 | 17951.75 | 0
|  | Los Robles | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 20840.81 | 20840.81 | 0
[6 empty] | 2021-06-17 | 187567.34 | 187567.34 | 0
[6 empty] | 2023-12-19 | 10968.85 | 10968.85 | 0
|  | Nelson | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 29425.87 | 29425.87 | 0
[6 empty] | 2021-01-08 | 264832.83 | 264832.83 | 0
[6 empty] | 2023-12-19 | 15487.3 | 15487.3 | 0
|  | Palm | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 22069.45 | 22069.45 | 0
[6 empty] | 2020-10-21 | 66208.35 | 66208.35 | 0
[6 empty] | 2021-06-17 | 132416.7 | 132416.7 | 0
[6 empty] | 2023-12-19 | 11615.5 | 11615.5 | 0
|  | Sparks ES | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 24521.59 | 24521.59 | 0
[6 empty] | 2020-10-21 | 73564.77 | 73564.77 | 0
[6 empty] | 2021-01-08 | 147129.54 | 147129.54 | 0
[6 empty] | 2023-12-19 | 12906.1 | 12906.1 | 0
|  | Sunset | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 23073.6 | 23073.6 | 0
[6 empty] | 2020-10-21 | 69220.8 | 69220.8 | 0
[6 empty] | 2021-06-17 | 138441.6 | 138441.6 | 0
[6 empty] | 2023-12-19 | 12144 | 12144 | 0
|  | Temple | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 24518.64 | 24518.64 | 0
[6 empty] | 2021-04-27 | 220667.81 | 220667.81 | 0
[6 empty] | 2023-12-19 | 12904.55 | 12904.55 | 0
|  | Wing Lane | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 28760.11 | 28760.11 | 0
[6 empty] | 2021-04-27 | 258840.99 | 258840.99 | 0
[6 empty] | 2023-12-19 | 15136.9 | 15136.9 | 0
|  | Workman ES | Ceiling replacement | PO1-200000000729 | 2019-07-01 | 2019-12-17 | 23073.6 | 23073.6 | 0
[6 empty] | 2020-10-21 | 69220.8 | 69220.8 | 0
[6 empty] | 2021-01-08 | 138441.6 | 138441.6 | 0
[6 empty] | 2023-12-19 | 12144 | 12144 | 0
Schneider Electric Buildings Americas, Inc. Total | [6 empty] | 4573414 | 4573414 | 0
Southern California Edison Co (SCE) | Temporary power | Newton | Interim Housing | PO2W-220000001329 | 2022-01-10 | 2022-01-24 | 1072 | 1072 | 0
Southern California Edison Co (SCE) Total | [6 empty] | 1072 | 1072 | 0
Suburban Water Systems | Deposit for engineering costs to construct (1) 6" public fire hydrant | Mesa Robles | Interim Housing | 19-106996 | 2019-03-08 | 2019-03-12 | 2000 | 2000 | 0
| Deposit to construct (1) 6" public fire hydrant | Cedarlane | Interim Housing | PO2W-200000002737 | 2019-11-25 | 2019-12-10 | 3000 | 3000 | 0
| Fire flow testing | California | Interim Housing | PO2W-220000000489 | 2021-09-15 | 2021-09-27 | 212 | 212 | 0
[6 empty] | 2022-03-26 | -212 | -212 | 0
|  | Cedarlane | Interim Housing | 19-108466 | 2019-04-16 | 2019-04-17 | 212 | 212 | 0
|  | Mesa Robles | Interim Housing | 19-105188 | 2019-01-09 | 2019-01-11 | 636 | 636 | 0
|  | Newton | Interim Housing | PO2W-200000003382 | 2020-01-14 | 2020-01-23 | 212 | 212 | 0
| Remaining balance to construct (1) 6" public fire hydrant | Mesa Robles | Interim Housing | PO2W-200000003306 | 2020-01-08 | 2020-01-16 | 39498.69 | 39498.69 | 0
Suburban Water Systems Total | [6 empty] | 45558.69 | 45558.69 | 0
SVA Architects, Inc. | Architect | Workman ES | 21st Century classroom | PO2W-200000001213, 19-100506, 18-109555 | 2018-06-01 | 2018-06-28 | 2363.68 | 2363.68 | 0
[6 empty] | 2019-04-03 | 4581.84 | 4581.84 | 0
[6 empty] | 2019-09-05 | 54214.7 | 54214.7 | 0
[6 empty] | 2019-10-25 | 5850.11 | 5850.11 | 0
[6 empty] | 2020-05-26 | 9809.27 | 9809.27 | 0
[6 empty] | 2020-08-18 | 5909.2 | 5909.2 | 0
[6 empty] | 2021-02-05 | 19204.9 | 19204.9 | 0
[6 empty] | 2022-03-24 | 12704.78 | 12704.78 | 0
[6 empty] | 2022-05-04 | 3545.52 | 3545.52 | 0
|  |  |  | PO2W-200000001214, 19-101982 | 2018-06-01 | 2019-02-08 | 4900 | 4900 | 0
[6 empty] | 2020-06-03 | 404.95 | 404.95 | 0
[6 empty] | 2021-06-30 | 14695.05 | 0 | 14695.05
[6 empty] | 2022-04-28 | -14695.05 | 0 | -14695.05
| DSA fees | Workman ES | 21st Century classroom | PO2W-200000004424 | 2020-02-27 | 2020-04-02 | 2250 | 2250 | 0
SVA Architects, Inc. Total | [6 empty] | 125738.95 | 125738.95 | 0
tBP Architecture | Architect | Baldwin | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | Bixby | Fire Alarm replacement | PO1-200000000846 | 2020-01-14 | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | California | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2021-02-05 | 4850 | 4850 | 0
[6 empty] | 2021-03-24 | 2425 | 2425 | 0
[6 empty] | 2021-05-26 | 2425 | 2425 | 0
[6 empty] | 2021-09-09 | 1455 | 1455 | 0
[6 empty] | 2022-01-19 | 970 | 970 | 0
|  | Cedarlane | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2020-10-14 | 2375 | 2375 | 0
[6 empty] | 2021-02-05 | 1425 | 1425 | 0
[6 empty] | 2021-03-24 | 950 | 950 | 0
|  | Del Valle | Fire Alarm replacement | PO2W-210000000984 | 2020-10-20 | 2021-02-05 | 7275 | 7275 | 0
[6 empty] | 2021-02-09 | 7275 | 7275 | 0
[6 empty] | 2021-03-24 | 7275 | 7275 | 0
[6 empty] | 2021-05-26 | 12125 | 12125 | 0
[6 empty] | 2021-06-23 | 1455 | 1455 | 0
[6 empty] | 2021-09-09 | 970 | 970 | 0
[6 empty] | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | Fairgrove | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2021-03-24 | 4850 | 4850 | 0
[6 empty] | 2021-05-26 | 4850 | 4850 | 0
[6 empty] | 2021-09-09 | 1455 | 1455 | 0
[6 empty] | 2022-06-23 | 970 | 970 | 0
|  | Grandview | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2020-10-14 | 2375 | 2375 | 0
[6 empty] | 2021-01-07 | 2375 | 2375 | 0
[6 empty] | 2021-03-24 | 4750 | 4750 | 0
[6 empty] | 2021-09-09 | 1425 | 1425 | 0
[6 empty] | 2021-11-17 | 950 | 950 | 0
|  | Grazide | Fire Alarm replacement | PO1-200000000846 | 2020-01-14 | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | Kwis | Fire Alarm replacement | PO2W-210000000984 | 2020-10-20 | 2021-02-05 | 7275 | 7275 | 0
[6 empty] | 2021-02-09 | 7275 | 7275 | 0
[6 empty] | 2021-03-24 | 7275 | 7275 | 0
[6 empty] | 2021-05-26 | 12125 | 12125 | 0
[6 empty] | 2021-06-23 | 1455 | 1455 | 0
[6 empty] | 2021-09-09 | 970 | 970 | 0
[6 empty] | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | La Puente HS | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2023-03-02 | 14700 | 0 | 14700
[6 empty] | 2023-03-03 | -14700 | 0 | -14700
|  | Lassalette | Fire Alarm replacement | PO1-200000000846 | 2020-01-14 | 2023-03-02 | 12375 | 0 | 12375
[6 empty] | 2023-03-03 | -12375 | 0 | -12375
|  | Los Altos ES | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2021-03-24 | 7125 | 7125 | 0
[6 empty] | 2021-05-26 | 2375 | 2375 | 0
[6 empty] | 2021-09-09 | 1425 | 1425 | 0
[6 empty] | 2022-01-19 | 950 | 950 | 0
|  | Los Altos HS | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2023-03-02 | 13950 | 0 | 13950
[6 empty] | 2023-03-03 | -13950 | 0 | -13950
|  | Los Molinos | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2021-03-24 | 4850 | 4850 | 0
[6 empty] | 2021-05-26 | 4850 | 4850 | 0
[6 empty] | 2021-09-09 | 1455 | 1455 | 0
[6 empty] | 2022-06-23 | 970 | 970 | 0
|  | Los Robles | Fire Alarm replacement | PO2W-210000000984 | 2020-10-20 | 2021-02-05 | 7275 | 7275 | 0
[6 empty] | 2021-02-09 | 7275 | 7275 | 0
[6 empty] | 2021-03-24 | 7275 | 7275 | 0
[6 empty] | 2021-05-26 | 12125 | 12125 | 0
[6 empty] | 2021-06-23 | 1455 | 1455 | 0
[6 empty] | 2021-09-09 | 970 | 970 | 0
[6 empty] | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | Mesa Robles | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2021-01-07 | 2375 | 2375 | 0
[6 empty] | 2021-02-05 | 2375 | 2375 | 0
[6 empty] | 2021-03-24 | 4750 | 4750 | 0
[6 empty] | 2021-09-09 | 1425 | 1425 | 0
[6 empty] | 2021-12-10 | 950 | 950 | 0
|  |  | Interim Housing | PO2W-200000000855, 19-109962 | 2019-06-11 | 2019-08-22 | 26100 | 26100 | 0
[6 empty] | 2019-09-23 | 30450 | 30450 | 0
[6 empty] | 2020-01-15 | 8700 | 8700 | 0
[6 empty] | 2020-05-26 | 4350 | 4350 | 0
[6 empty] | 2020-06-19 | 4350 | 4350 | 0
[6 empty] | 2020-08-18 | 2610 | 2610 | 0
[6 empty] | 2020-10-14 | 6090 | 6090 | 0
[6 empty] | 2021-02-05 | 2610 | 2610 | 0
[6 empty] | 2021-10-01 | 1740 | 1740 | 0
|  | Nelson | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2021-03-24 | 7125 | 7125 | 0
[6 empty] | 2021-05-26 | 2375 | 2375 | 0
[6 empty] | 2021-09-09 | 1425 | 1425 | 0
[6 empty] | 2022-02-23 | 950 | 950 | 0
[6 empty] | 2022-04-04 | -950 | -950 | 0
[6 empty] | 2022-04-06 | 950 | 950 | 0
|  | Newton | Fire Alarm replacement | PO1-200000000899, 19-104053, JVER21-187 | 2018-07-01 | 2020-09-18 | 7125 | 7125 | 0
|  |  |  | PO2W-210000000680 | 2018-07-01 | 2021-02-05 | 1425 | 1425 | 0
[6 empty] | 2021-05-26 | 950 | 950 | 0
|  | Orange Grove | Fire Alarm replacement | PO2W-210000000984 | 2020-10-20 | 2021-02-05 | 7425 | 7425 | 0
[6 empty] | 2021-02-09 | 4920 | 4920 | 0
[6 empty] | 2021-02-22 | 30 | 30 | 0
[6 empty] | 2021-03-24 | 9900 | 9900 | 0
[6 empty] | 2021-05-26 | 12375 | 12375 | 0
[6 empty] | 2021-06-23 | 1485 | 1485 | 0
[6 empty] | 2021-09-09 | 990 | 990 | 0
[6 empty] | 2023-03-02 | 12375 | 0 | 12375
[6 empty] | 2023-03-03 | -12375 | 0 | -12375
|  | Palm | Fire Alarm replacement | PO2W-210000000984 | 2020-10-20 | 2021-02-05 | 7275 | 7275 | 0
[6 empty] | 2021-02-09 | 7275 | 7275 | 0
[6 empty] | 2021-03-24 | 7275 | 7275 | 0
[6 empty] | 2021-05-26 | 12125 | 12125 | 0
[6 empty] | 2021-06-23 | 1455 | 1455 | 0
[6 empty] | 2021-09-09 | 970 | 970 | 0
[6 empty] | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | Sierra Vista | Fire Alarm replacement | PO2W-210000000984 | 2020-10-20 | 2021-03-24 | 19800 | 19800 | 0
[6 empty] | 2021-05-26 | 14850 | 14850 | 0
[6 empty] | 2021-06-23 | 1485 | 1485 | 0
[6 empty] | 2021-09-09 | 990 | 990 | 0
[6 empty] | 2023-03-02 | 12375 | 0 | 12375
[6 empty] | 2023-03-03 | -12375 | 0 | -12375
|  | Sparks ES | Fire Alarm replacement | PO1-200000000846 | 2020-01-14 | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | Sparks MS | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2020-10-14 | 2475 | 2475 | 0
[6 empty] | 2021-02-05 | 1485 | 1485 | 0
[6 empty] | 2021-03-24 | 990 | 990 | 0
|  | Stimson | Fire Alarm replacement | PO1-200000000846 | 2020-01-14 | 2020-05-26 | 9875 | 9875 | 0
[6 empty] | 2020-06-19 | 9875 | 9875 | 0
[6 empty] | 2020-10-14 | 7900 | 7900 | 0
[6 empty] | 2021-05-26 | 1975 | 1975 | 0
[6 empty] | 2023-03-02 | 9875 | 0 | 9875
[6 empty] | 2023-03-03 | -9875 | 0 | -9875
|  | Sunset | Fire Alarm replacement | PO2W-210000000984 | 2020-10-20 | 2021-02-05 | 2425 | 2425 | 0
[6 empty] | 2021-02-09 | 9700 | 9700 | 0
[6 empty] | 2021-03-24 | 7275 | 7275 | 0
[6 empty] | 2021-05-26 | 14550 | 14550 | 0
[6 empty] | 2021-06-23 | 1455 | 1455 | 0
[6 empty] | 2021-09-09 | 970 | 970 | 0
[6 empty] | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | Valinda | Fire Alarm replacement | PO1-200000000846 | 2020-01-14 | 2023-03-02 | 12375 | 0 | 12375
[6 empty] | 2023-03-03 | -12375 | 0 | -12375
|  | Valley | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2020-10-14 | 2275 | 2275 | 0
[6 empty] | 2021-01-07 | 2275 | 2275 | 0
[6 empty] | 2021-02-05 | 2275 | 2275 | 0
[6 empty] | 2021-02-09 | 3640 | 3640 | 0
[6 empty] | 2021-10-28 | 910 | 910 | 0
|  | Wilson HS | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2021-01-07 | 2275 | 2275 | 0
[6 empty] | 2021-02-05 | 2275 | 2275 | 0
[6 empty] | 2021-03-24 | 2275 | 2275 | 0
[6 empty] | 2023-03-02 | 4550 | 0 | 4550
[6 empty] | 2023-03-03 | -4550 | 0 | -4550
|  | Wing Lane | Fire Alarm replacement | PO2W-210000000984 | 2020-10-20 | 2021-02-05 | 7275 | 7275 | 0
[6 empty] | 2021-02-09 | 7275 | 7275 | 0
[6 empty] | 2021-03-24 | 4850 | 4850 | 0
[6 empty] | 2021-05-26 | 14550 | 14550 | 0
[6 empty] | 2021-06-23 | 1455 | 1455 | 0
[6 empty] | 2021-09-09 | 970 | 970 | 0
[6 empty] | 2023-03-02 | 12125 | 0 | 12125
[6 empty] | 2023-03-03 | -12125 | 0 | -12125
|  | Workman ES | Fire Alarm replacement | PO2W-210000000680 | 2018-07-01 | 2021-01-07 | 2375 | 2375 | 0
[6 empty] | 2021-03-24 | 7125 | 7125 | 0
[6 empty] | 2021-09-09 | 1425 | 1425 | 0
[6 empty] | 2022-02-23 | 950 | 950 | 0
[6 empty] | 2022-04-04 | -950 | -950 | 0
[6 empty] | 2022-04-06 | 950 | 950 | 0
tBP Architecture Total | [6 empty] | 542275 | 542275 | 0
Teachers | Pack classrooms | Cedarlane | 21st Century classroom | Payroll register: C1E-C | 2020-10-16 | 2020-12-01 | 2142.81 | 2142.81 | 0
[6 empty] | 2022-01-19 | -2142.81 | -2142.81 | 0
|  |  |  | Payroll register: C1F-C | 2020-10-16 | 2021-01-04 | 803.69 | 803.69 | 0
[6 empty] | 2022-01-19 | -803.69 | -803.69 | 0
|  |  |  | Payroll register: C1H-C | 2020-10-16 | 2021-03-01 | 1836.21 | 1836.21 | 0
[6 empty] | 2022-01-19 | -1836.21 | -1836.21 | 0
|  |  |  | Payroll register: C1I-C | 2020-10-16 | 2021-04-01 | 306.06 | 306.06 | 0
[6 empty] | 2022-01-19 | -306.06 | -306.06 | 0
|  | Mesa Robles | 21st Century classroom | Payroll register: C1E-C | 2020-10-16 | 2020-12-01 | 3977.43 | 3977.43 | 0
[6 empty] | 2022-01-19 | -3977.43 | -3977.43 | 0
|  |  |  | Payroll register: C1H-C | 2020-10-16 | 2021-03-01 | 1396.86 | 1396.86 | 0
[6 empty] | 2022-01-19 | -1396.86 | -1396.86 | 0
|  |  |  | Payroll register: C1I-C | 2020-10-16 | 2021-04-01 | 612.03 | 612.03 | 0
[6 empty] | 2022-01-19 | -612.03 | -612.03 | 0
|  |  |  | Payroll register: C1J-C | 2020-10-16 | 2021-05-03 | 2219.5 | 2219.5 | 0
[6 empty] | 2022-01-19 | -2219.5 | -2219.5 | 0
|  |  |  | Payroll register: C1K-C | 2020-10-16 | 2021-06-01 | 306.08 | 306.08 | 0
[6 empty] | 2022-01-19 | -306.08 | -306.08 | 0
|  |  |  | Payroll register: V2B-C | 2020-10-16 | 2021-07-02 | 922.36 | 922.36 | 0
[6 empty] | 2022-01-19 | -922.36 | -922.36 | 0
Teachers Total | [6 empty] | 0 | 0 | 0
Team Inspections | General inspection | Amar | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2023-03-02 | 1200 | 0 | 1200
[6 empty] | 2023-03-03 | -1200 | 0 | -1200
|  | California | Fire Alarm replacement | PO2W-210000000977 | 2020-10-22 | 2021-02-05 | 3060 | 3060 | 0
[6 empty] | 2021-02-09 | 6120 | 6120 | 0
[6 empty] | 2021-09-15 | 2570 | 2570 | 0
[6 empty] | 2022-05-20 | 500 | 500 | 0
|  | Cedarlane | 21st Century classroom | PO2W-210000001035 | 2020-10-29 | 2021-03-24 | 8640 | 8640 | 0
[6 empty] | 2021-04-19 | 8352 | 8352 | 0
[6 empty] | 2021-04-20 | 6624 | 6624 | 0
[6 empty] | 2021-06-09 | 6336 | 6336 | 0
[6 empty] | 2021-06-23 | 2880 | 2880 | 0
[6 empty] | 2021-09-09 | 3168 | 3168 | 0
[6 empty] | 2021-09-22 | 11520 | 11520 | 0
[6 empty] | 2021-10-22 | 6480 | 6480 | 0
[6 empty] | 2021-12-01 | 5760 | 5760 | 0
[6 empty] | 2021-12-20 | 6048 | 6048 | 0
[6 empty] | 2022-01-12 | 3024 | 3024 | 0
[6 empty] | 2022-07-01 | 24768 | 0 | 24768
[6 empty] | 2023-06-30 | -24768 | 0 | -24768
|  |  | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2022-05-20 | 1200 | 1200 | 0
|  |  | Fire Alarm replacement | PO2W-200000004017 | 2020-02-07 | 2020-05-26 | 6185 | 6185 | 0
[6 empty] | 2020-10-14 | 2065 | 2065 | 0
|  |  | Interim Housing | PO2W-210000001035 | 2020-10-29 | 2021-03-24 | 5760 | 5760 | 0
[6 empty] | 2021-04-19 | 5904 | 5904 | 0
[6 empty] | 2021-04-20 | 3024 | 3024 | 0
|  | Fairgrove | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2023-03-02 | 1200 | 0 | 1200
[6 empty] | 2023-03-03 | -1200 | 0 | -1200
|  |  | Fire Alarm replacement | PO2W-210000001585 | 2021-01-14 | 2021-10-19 | 14350 | 14350 | 0
|  | Grandview | 21st Century classroom | PO2W-230000001740 | 2022-12-01 | 2023-01-11 | 4505 | 4505 | 0
[6 empty] | 2023-01-25 | 4080 | 4080 | 0
[6 empty] | 2023-03-07 | 3570 | 3570 | 0
[6 empty] | 2023-03-30 | 3230 | 3230 | 0
[6 empty] | 2023-05-18 | 7310 | 7310 | 0
[6 empty] | 2023-07-18 | 3740 | 3740 | 0
[6 empty] | 2023-07-19 | 3740 | 3740 | 0
[6 empty] | 2023-10-02 | 5100 | 5100 | 0
[6 empty] | 2023-12-08 | 12155 | 12155 | 0
[6 empty] | 2024-01-24 | 9265 | 9265 | 0
[6 empty] | 2027-06-01 | 595 | 0 | 595
|  |  | Fire Alarm replacement | PO2W-200000002809 | 2019-11-26 | 2020-05-26 | 2345 | 2345 | 0
[6 empty] | 2020-06-19 | 2345 | 2345 | 0
[6 empty] | 2020-10-14 | 2345 | 2345 | 0
[6 empty] | 2021-09-13 | 1840 | 1840 | 0
[6 empty] | 2022-05-20 | 500 | 500 | 0
|  | Kwis | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2023-03-02 | 1200 | 0 | 1200
[6 empty] | 2023-03-03 | -1200 | 0 | -1200
|  | La Puente HS | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2023-03-02 | 1200 | 0 | 1200
[6 empty] | 2023-03-03 | -1200 | 0 | -1200
|  | Lassalette | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2023-03-02 | 1200 | 0 | 1200
[6 empty] | 2023-03-03 | -1200 | 0 | -1200
|  | Los Altos ES | 21st Century classroom | PO2W-200000004960 | 2020-04-29 | 2020-06-19 | 4410 | 4410 | 0
[6 empty] | 2020-08-19 | 6440 | 6440 | 0
[6 empty] | 2020-10-14 | 5880 | 5880 | 0
[6 empty] | 2020-10-21 | 5880 | 5880 | 0
[6 empty] | 2021-02-05 | 3080 | 3080 | 0
[6 empty] | 2021-03-24 | 2030 | 2030 | 0
[6 empty] | 2021-04-19 | 7000 | 7000 | 0
|  |  | Fire Alarm replacement | PO2W-210000001492 | 2020-12-15 | 2021-02-09 | 3060 | 3060 | 0
[6 empty] | 2021-04-19 | 6120 | 6120 | 0
[6 empty] | 2021-09-09 | 500 | 500 | 0
[6 empty] | 2021-09-13 | 2570 | 2570 | 0
|  |  | Interim Housing | PO2W-200000000103 | 2019-07-01 | 2019-12-11 | 9900 | 9900 | 0
[6 empty] | 2020-01-15 | 3300 | 3300 | 0
|  | Los Molinos | Fire Alarm replacement | PO2W-210000001585 | 2021-01-14 | 2021-10-19 | 14350 | 14350 | 0
|  | Mesa Robles | 21st Century classroom | PO2W-210000001035 | 2020-10-29 | 2021-03-24 | 8640 | 8640 | 0
[6 empty] | 2021-04-19 | 11664 | 11664 | 0
[6 empty] | 2021-04-20 | 3600 | 3600 | 0
[6 empty] | 2021-05-26 | 6336 | 6336 | 0
[6 empty] | 2021-06-23 | 8640 | 8640 | 0
[6 empty] | 2021-09-09 | 18576 | 18576 | 0
[6 empty] | 2021-09-22 | 288 | 288 | 0
[6 empty] | 2022-07-01 | 35856 | 0 | 35856
[6 empty] | 2023-06-30 | -35856 | 0 | -35856
|  |  | Fire Alarm replacement | PO2W-200000005057 | 2020-05-13 | 2020-08-19 | 2065 | 2065 | 0
[6 empty] | 2020-10-14 | 2065 | 2065 | 0
[6 empty] | 2020-10-21 | 2065 | 2065 | 0
[6 empty] | 2021-09-13 | 2055 | 2055 | 0
|  |  | Interim Housing | PO2W-200000004113 | 2020-02-13 | 2020-06-19 | 19870 | 19870 | 0
[6 empty] | 2020-08-19 | 9935 | 9935 | 0
[6 empty] | 2020-10-14 | 5960 | 5960 | 0
[6 empty] | 2021-04-20 | 3975 | 3975 | 0
|  | Nelson | 21st Century classroom | PO2W-200000004961 | 2020-04-29 | 2020-06-19 | 4410 | 4410 | 0
[6 empty] | 2020-08-19 | 3360 | 3360 | 0
[6 empty] | 2020-10-14 | 2940 | 2940 | 0
[6 empty] | 2020-10-21 | 2940 | 2940 | 0
[6 empty] | 2021-02-05 | 6160 | 6160 | 0
[6 empty] | 2021-03-24 | 4270 | 4270 | 0
[6 empty] | 2021-04-19 | 5320 | 5320 | 0
[6 empty] | 2021-04-20 | 3220 | 3220 | 0
[6 empty] | 2022-07-11 | 2100 | 0 | 2100
[6 empty] | 2023-06-30 | -2100 | 0 | -2100
|  |  | Fire Alarm replacement | PO2W-210000001492 | 2020-12-15 | 2021-02-09 | 9180 | 9180 | 0
[6 empty] | 2021-09-09 | 500 | 500 | 0
[6 empty] | 2021-09-13 | 2570 | 2570 | 0
|  | Newton | 21st Century classroom | PO2W-230000001740 | 2022-12-01 | 2023-01-11 | 7140 | 7140 | 0
[6 empty] | 2023-01-25 | 7140 | 7140 | 0
[6 empty] | 2023-03-07 | 7140 | 7140 | 0
[6 empty] | 2023-03-30 | 6460 | 6460 | 0
[6 empty] | 2023-05-18 | 14620 | 14620 | 0
[6 empty] | 2023-07-18 | 7480 | 7480 | 0
[6 empty] | 2023-07-19 | 7480 | 7480 | 0
[6 empty] | 2023-10-02 | 6800 | 6800 | 0
[6 empty] | 2023-12-08 | 14620 | 14620 | 0
[6 empty] | 2024-01-24 | 17000 | 17000 | 0
[6 empty] | 2027-06-01 | 19890 | 0 | 19890
|  |  | Fire Alarm replacement | PO2W-200000002811 | 2019-11-26 | 2020-05-26 | 6090 | 6090 | 0
[6 empty] | 2020-06-19 | 2035 | 2035 | 0
|  |  | Interim Housing | PO2W-210000000015 | 2020-07-01 | 2022-05-20 | 12000 | 12000 | 0
[6 empty] | 2022-07-08 | 4000 | 4000 | 0
|  | Sparks ES | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2023-03-02 | 1200 | 0 | 1200
[6 empty] | 2023-03-03 | -1200 | 0 | -1200
|  | Sparks MS | 21st Century classroom | PO1-240000000569 | 2023-10-16 | 2024-01-24 | 5185 | 5185 | 0
[6 empty] | 2024-01-25 | 1530 | 1530 | 0
[6 empty] | 2027-12-09 | 3825 | 0 | 3825
|  |  |  | PO2W-230000001740 | 2022-12-01 | 2023-01-11 | 4335 | 4335 | 0
[6 empty] | 2023-01-25 | 3740 | 3740 | 0
[6 empty] | 2023-03-07 | 3570 | 3570 | 0
[6 empty] | 2023-03-30 | 3230 | 3230 | 0
[6 empty] | 2023-05-18 | 7310 | 7310 | 0
[6 empty] | 2023-07-18 | 3740 | 3740 | 0
[6 empty] | 2023-07-19 | 3740 | 3740 | 0
[6 empty] | 2023-10-02 | 1700 | 1700 | 0
[6 empty] | 2023-12-08 | 765 | 765 | 0
|  |  | Fire Alarm replacement | PO2W-200000002812 | 2019-11-26 | 2020-02-20 | 1720 | 1720 | 0
[6 empty] | 2020-04-17 | 3440 | 3440 | 0
[6 empty] | 2020-06-19 | 1715 | 1715 | 0
|  | Valley | Fire Alarm replacement | PO2W-210000000455 | 2020-08-19 | 2020-10-14 | 3675 | 3675 | 0
[6 empty] | 2021-02-09 | 3675 | 3675 | 0
|  | Wedgeworth | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2023-03-02 | 1200 | 0 | 1200
[6 empty] | 2023-03-03 | -1200 | 0 | -1200
|  | Wilson HS | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2023-03-02 | 1200 | 0 | 1200
[6 empty] | 2023-03-03 | -1200 | 0 | -1200
|  |  | Fire Alarm replacement | PO2W-200000005058 | 2020-05-13 | 2020-06-19 | 4125 | 4125 | 0
[6 empty] | 2020-08-19 | 8250 | 8250 | 0
[6 empty] | 2021-09-13 | 3625 | 3625 | 0
[6 empty] | 2022-05-20 | 500 | 500 | 0
|  | Workman ES | 21st Century classroom | PO2W-200000004962 | 2020-04-29 | 2020-06-19 | 2940 | 2940 | 0
[6 empty] | 2020-08-19 | 3080 | 3080 | 0
[6 empty] | 2020-10-14 | 3500 | 3500 | 0
[6 empty] | 2020-10-21 | 2940 | 2940 | 0
[6 empty] | 2021-02-05 | 3080 | 3080 | 0
[6 empty] | 2021-04-19 | 9940 | 9940 | 0
[6 empty] | 2022-07-11 | 9240 | 0 | 9240
[6 empty] | 2023-06-30 | -9240 | 0 | -9240
|  |  | Drinking Fountain replacement | PO2W-200000003303 | 2020-01-06 | 2021-03-24 | 1200 | 1200 | 0
|  |  | Fire Alarm replacement | PO2W-210000001574 | 2021-01-13 | 2021-02-09 | 6120 | 6120 | 0
[6 empty] | 2021-04-19 | 3060 | 3060 | 0
[6 empty] | 2021-09-13 | 2570 | 2570 | 0
[6 empty] | 2022-05-20 | 500 | 500 | 0
Team Inspections Total | [6 empty] | 663579 | 639269 | 24310
Telenet VOIP, Inc. | Contractor | California | Fire Alarm replacement | PO2W-200000004928 | 2020-04-13 | 2020-12-18 | 100034.1 | 100034.1 | 0
[6 empty] | 2021-02-02 | 95444.14 | 95444.14 | 0
[6 empty] | 2021-06-02 | 18626.19 | 18626.19 | 0
[6 empty] | 2022-05-20 | 12468.66 | 12468.66 | 0
|  | Cedarlane | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 1202.7 | 1202.7 | 0
[6 empty] | 2020-04-08 | 22141.65 | 22141.65 | 0
[6 empty] | 2020-05-29 | 38354.72 | 38354.72 | 0
[6 empty] | 2020-06-30 | 0 | 0 | 0
[6 empty] | 2020-07-30 | 38525.92 | 38525.92 | 0
[6 empty] | 2020-12-18 | 855 | 855 | 0
[6 empty] | 2022-06-02 | 5320 | 5320 | 0
|  | Fairgrove | Fire Alarm replacement | PO2W-200000004930 | 2020-04-13 | 2021-03-18 | 301327.64 | 301327.64 | 0
[6 empty] | 2021-05-21 | 52824.71 | 52824.71 | 0
[6 empty] | 2021-11-05 | 21534.68 | 21534.68 | 0
[6 empty] | 2022-05-20 | 3048.76 | 3048.76 | 0
|  | Grandview | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 1578.9 | 1578.9 | 0
[6 empty] | 2020-05-29 | 47652.48 | 47652.48 | 0
[6 empty] | 2020-07-30 | 48106.48 | 48106.48 | 0
[6 empty] | 2020-08-28 | 28361.78 | 28361.78 | 0
[6 empty] | 2021-05-21 | 9007.5 | 9007.5 | 0
[6 empty] | 2021-11-22 | 3650.96 | 3650.96 | 0
[6 empty] | 2022-05-23 | 950 | 950 | 0
[6 empty] | 2022-06-02 | 7332.01 | 7332.01 | 0
|  | La Puente HS | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 2717.95 | 2717.95 | 0
|  | Los Altos ES | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 943.35 | 943.35 | 0
[6 empty] | 2020-12-18 | 16828.3 | 16828.3 | 0
[6 empty] | 2021-05-21 | 58465.85 | 58465.85 | 0
[6 empty] | 2021-11-22 | 24679.6 | 24679.6 | 0
[6 empty] | 2022-05-23 | 950 | 950 | 0
[6 empty] | 2022-06-02 | 5361.43 | 5361.43 | 0
|  | Los Molinos | Fire Alarm replacement | PO2W-200000004929 | 2020-04-13 | 2021-03-18 | 102643.66 | 102643.66 | 0
[6 empty] | 2021-05-21 | 75557.98 | 75557.98 | 0
[6 empty] | 2022-05-20 | 10713.12 | 10713.12 | 0
|  | Mesa Robles | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 1402.2 | 1402.2 | 0
[6 empty] | 2020-07-30 | 5885.73 | 5885.73 | 0
[6 empty] | 2020-08-28 | 51687.41 | 51687.41 | 0
[6 empty] | 2020-10-13 | 36702.12 | 36702.12 | 0
[6 empty] | 2020-11-04 | 16603.41 | 16603.41 | 0
[6 empty] | 2020-12-18 | 1402.96 | 1402.96 | 0
[6 empty] | 2021-05-21 | 11102.84 | 11102.84 | 0
[6 empty] | 2021-11-22 | 14270.46 | 14270.46 | 0
[6 empty] | 2022-05-23 | 950 | 950 | 0
[6 empty] | 2022-06-02 | 6786.48 | 6786.48 | 0
|  |  | Interim Housing | PO2W-200000004671 | 2020-03-03 | 2020-07-30 | 61268.26 | 61268.26 | 0
[6 empty] | 2020-08-28 | 165673.54 | 165673.54 | 0
[6 empty] | 2020-11-09 | 12873.64 | 12873.64 | 0
[6 empty] | 2020-12-18 | 3965.31 | 3965.31 | 0
[6 empty] | 2021-03-12 | 7229.21 | 7229.21 | 0
[6 empty] | 2021-05-21 | 19093.1 | 19093.1 | 0
[6 empty] | 2022-11-28 | 475 | 475 | 0
[6 empty] | 2022-12-06 | 2457.25 | 2457.25 | 0
|  |  |  | PO2W-210000001738 | 2021-02-04 | 2022-12-06 | 4174.01 | 4174.01 | 0
|  |  |  | PO2W-210000001875 | 2021-03-08 | 2022-12-06 | 7609.69 | 7609.69 | 0
|  | Nelson | 21st Century classroom | PO2W-200000004053 | 2020-02-06 | 2020-03-19 | 13950.28 | 13950.28 | 0
[6 empty] | 2020-04-23 | 6200.12 | 6200.12 | 0
[6 empty] | 2020-05-29 | 10850.22 | 10850.22 | 0
[6 empty] | 2021-01-07 | 1631.61 | 1631.61 | 0
|  |  | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 1017.45 | 1017.45 | 0
[6 empty] | 2020-12-18 | 8907.87 | 8907.87 | 0
[6 empty] | 2021-05-21 | 72472.7 | 72472.7 | 0
[6 empty] | 2021-11-22 | 29445.32 | 29445.32 | 0
[6 empty] | 2022-05-23 | 1619.99 | 1619.99 | 0
[6 empty] | 2022-06-02 | 5971.75 | 5971.75 | 0
|  | Newton | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 3359.2 | 3359.2 | 0
[6 empty] | 2020-04-08 | 21443.4 | 21443.4 | 0
[6 empty] | 2020-04-24 | 17273.14 | 17273.14 | 0
[6 empty] | 2020-05-29 | 21295.68 | 21295.68 | 0
[6 empty] | 2020-07-30 | 13963.34 | 13963.34 | 0
[6 empty] | 2020-08-28 | 1211.25 | 1211.25 | 0
[6 empty] | 2022-06-02 | 4134 | 4134 | 0
|  | Sparks MS | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 35460.79 | 35460.79 | 0
[6 empty] | 2020-04-08 | 48832.8 | 48832.8 | 0
[6 empty] | 2020-04-24 | 47231.15 | 47231.15 | 0
[6 empty] | 2020-05-29 | 3640.69 | 3640.69 | 0
[6 empty] | 2020-07-30 | 9234.57 | 9234.57 | 0
[6 empty] | 2022-06-02 | 7600 | 7600 | 0
|  | Valley | Fire Alarm replacement | PO2W-200000004931 | 2020-04-13 | 2020-10-13 | 184497.98 | 184497.98 | 0
[6 empty] | 2020-11-04 | 14431.45 | 14431.45 | 0
[6 empty] | 2020-12-18 | 12210.58 | 12210.58 | 0
[6 empty] | 2021-05-07 | 6009.39 | 6009.39 | 0
|  |  |  | PO2W-210000002213 | 2021-05-03 | 2021-05-07 | 819.47 | 819.47 | 0
[6 empty] | 2021-05-12 | 1947.5 | 1947.5 | 0
[6 empty] | 2022-05-23 | 12074.55 | 12074.55 | 0
|  | Wilson HS | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 2997.25 | 2997.25 | 0
[6 empty] | 2020-05-29 | 1723.3 | 1723.3 | 0
[6 empty] | 2020-07-30 | 162318.85 | 162318.85 | 0
[6 empty] | 2020-08-28 | 25191.82 | 25191.82 | 0
[6 empty] | 2020-10-13 | 25638.05 | 25638.05 | 0
[6 empty] | 2020-11-04 | 12068.33 | 12068.33 | 0
[6 empty] | 2021-05-21 | 5085.54 | 5085.54 | 0
[6 empty] | 2021-11-22 | 25768.03 | 25768.03 | 0
[6 empty] | 2022-05-23 | 6612.8 | 6612.8 | 0
[6 empty] | 2022-06-02 | 14656.21 | 14656.21 | 0
|  | Workman ES | Fire Alarm replacement | PO1-200000000662 | 2019-09-26 | 2020-03-10 | 1131.45 | 1131.45 | 0
[6 empty] | 2021-05-21 | 84975.6 | 84975.6 | 0
[6 empty] | 2021-11-22 | 39885.71 | 39885.71 | 0
[6 empty] | 2022-05-23 | 950 | 950 | 0
[6 empty] | 2022-06-02 | 6824.25 | 6824.25 | 0
Telenet VOIP, Inc. Total | [6 empty] | 2623388.27 | 2623388.27 | 0
Temp Power Sytems | Rental of power pole | Newton | Interim Housing | PO2W-200000000234 | 2019-07-29 | 2021-02-05 | 8497 | 8497 | 0
[6 empty] | 2022-05-04 | 3325 | 3325 | 0
|  |  |  | PO2W-220000001932 | 2022-03-30 | 2022-05-04 | 1340 | 1340 | 0
[6 empty] | 2022-06-17 | 6325 | 6325 | 0
|  |  |  | PO2W-230000001681 | 2022-11-21 | 2022-12-20 | 150 | 150 | 0
[6 empty] | 2023-01-11 | 150 | 150 | 0
[6 empty] | 2023-01-12 | 150 | 150 | 0
[6 empty] | 2023-03-07 | 150 | 150 | 0
[6 empty] | 2023-05-18 | 450 | 450 | 0
[6 empty] | 2023-07-18 | 300 | 300 | 0
[6 empty] | 2023-08-28 | 150 | 150 | 0
[6 empty] | 2023-10-02 | 150 | 150 | 0
[6 empty] | 2024-01-16 | 1050 | 0 | 1050
[6 empty] | 2024-01-19 | 600 | 600 | 0
Temp Power Sytems Total | [6 empty] | 22787 | 21737 | 1050
The Nazerian Group | Contractor | La Puente HS | 21st Century classroom | (blank) | 2024-01-09 | 2028-06-01 | 2444123 | 0 | 2444123
|  | Workman ES | 21st Century classroom | PO2W-200000005821 | 2020-06-05 | 2020-10-13 | 445951.85 | 445951.85 | 0
[6 empty] | 2021-02-05 | 766840 | 766840 | 0
[6 empty] | 2021-04-06 | 95237.5 | 95237.5 | 0
[6 empty] | 2022-11-30 | 149296.56 | 149296.56 | 0
[6 empty] | 2022-12-12 | 36797.09 | 36797.09 | 0
|  |  |  | PO2W-220000002621 | 2022-03-07 | 2022-12-12 | 39293.51 | 39293.51 | 0
|  |  |  | PO2W-230000001683 | 2022-11-21 | 2022-12-12 | 610.76 | 610.76 | 0
The Nazerian Group Total | [6 empty] | 3978150.27 | 1534027.27 | 2444123
U.S. Bank National Association | Trust fees | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-07-12 | 2017-07-12 | 550 | 550 | 0
U.S. Bank National Association Total | [6 empty] | 550 | 550 | 0
Uline | Boxes & tapes | La Puente HS | 21st Century classroom | (blank) | 2024-01-16 | 2024-06-01 | 1420.32 | 0 | 1420.32
|  | Workman HS | 21st Century classroom | (blank) | 2024-01-16 | 2024-06-01 | 1420.32 | 0 | 1420.32
| Carts | District Office | 21st Century classroom | PO3W-210000001074 | 2020-12-01 | 2020-12-08 | 791.69 | 791.69 | 0
| Furniture | Grandview | 21st Century classroom | PO3W-200000000288 | 2019-07-01 | 2019-07-30 | 8041.68 | 8041.68 | 0
| Hydraulic stacker | District Office | 21st Century classroom | PO3W-210000002899 | 2021-05-27 | 2021-06-04 | 1834.13 | 1834.13 | 0
|  |  |  | PO3W-210000002998 | 2021-06-08 | 2021-06-15 | 1834.13 | 1834.13 | 0
Uline Total | [6 empty] | 15342.27 | 12501.63 | 2840.64
Underwriter's fees | Underwriter's fees | District Office | Cost of Issuance | N/A - Cost of Issuance | 2017-07-12 | 2017-07-12 | 175000 | 175000 | 0
Underwriter's fees Total | [6 empty] | 175000 | 175000 | 0
Universal Asphalt | Contractor | Los Altos ES | Interim Housing | PO2W-200000000237 | 2019-07-23 | 2019-09-03 | 13776 | 13776 | 0
|  |  |  | PO2W-200000000632 | 2019-07-23 | 2019-09-03 | 4879 | 4879 | 0
|  |  |  | PO2W-200000001460 | 2019-09-26 | 2019-10-25 | 13902 | 13902 | 0
|  | Mesa Robles | Interim Housing | PO2W-200000004878 | 2020-03-03 | 2020-07-29 | 32487.91 | 32487.91 | 0
[6 empty] | 2020-10-13 | 66774.89 | 66774.89 | 0
|  |  |  | PO2W-210000000545 | 2020-09-03 | 2020-10-13 | 7275 | 7275 | 0
Universal Asphalt Total | [6 empty] | 139094.8 | 139094.8 | 0
Walter Fajardo | Notary fees | Los Altos ES | 21st Century classroom | PO2W-230000000339 | 2022-07-11 | 2022-08-17 | 22.5 | 22.5 | 0
|  | Nelson | 21st Century classroom | PO2W-230000000339 | 2022-07-11 | 2022-08-17 | 22.5 | 22.5 | 0
|  | Workman ES | 21st Century classroom | PO2W-230000000339 | 2022-07-11 | 2022-08-17 | 22.5 | 22.5 | 0
Walter Fajardo Total | [6 empty] | 67.5 | 67.5 | 0
Warehouse | Boxes | Cedarlane | 21st Century classroom | XSRQ-210000001812 | 2020-10-20 | 2020-10-28 | 318.12 | 318.12 | 0
|  |  |  | XSRQ-210000002565 | 2021-01-14 | 2021-06-04 | 466.62 | 466.62 | 0
|  | Mesa Robles | 21st Century classroom | XSRQ-210000001813 | 2020-10-20 | 2020-10-28 | 265.1 | 265.1 | 0
|  |  |  | XSRQ-210000002024 | 2020-10-20 | 2020-11-17 | 180.27 | 180.27 | 0
|  |  |  | XSRQ-210000002810 | 2021-02-04 | 2021-02-10 | 648.09 | 648.09 | 0
| Boxes & tapes | Cedarlane | 21st Century classroom | XSRQ-210000002207 | 2020-12-03 | 2020-12-08 | 484.13 | 484.13 | 0
|  |  |  | XSRQ-210000002247 | 2020-12-08 | 2020-12-10 | 484.13 | 484.13 | 0
|  |  |  | XSRQ-210000002484 | 2021-01-08 | 2021-01-12 | 795.26 | 795.26 | 0
|  | Grandview | 21st Century classroom | XSRQ-230000002152 | 2022-11-02 | 2022-11-04 | 318.77 | 318.77 | 0
|  | Mesa Robles | 21st Century classroom | XSRQ-210000002249 | 2020-12-08 | 2020-12-10 | 759.34 | 759.34 | 0
|  | Newton | 21st Century classroom | XSRQ-230000002153 | 2022-11-02 | 2022-11-04 | 318.77 | 318.77 | 0
|  | Sparks MS | 21st Century classroom | XSRQ-230000002154 | 2022-11-02 | 2022-11-04 | 318.77 | 318.77 | 0
| Paper towel dispenser | Cedarlane | 21st Century classroom | XSRQ-220000000112 | 2021-07-13 | 2021-07-22 | 918.52 | 918.52 | 0
|  | Los Altos ES | 21st Century classroom | XSRQ-220000000971 | 2021-09-01 | 2021-09-03 | 86.19 | 86.19 | 0
| Soap dispensers | Cedarlane | 21st Century classroom | XSRQ-220000000064 | 2021-07-09 | 2021-07-12 | 0 | 0 | 0
Warehouse Total | [6 empty] | 6362.08 | 6362.08 | 0
Williams Tree Service | Tree Service | Newton | 21st Century classroom | PO2W-210000000996 | 2020-10-27 | 2020-11-04 | 3400 | 3400 | 0
Williams Tree Service Total | [6 empty] | 3400 | 3400 | 0
Wolverine Fence | Contractor | Mesa Robles | 21st Century classroom | PO2W-210000000063 | 2020-07-06 | 2020-11-02 | 3500 | 3500 | 0
|  |  |  | PO2W-210000001036 | 2020-10-29 | 2021-01-15 | 1500 | 1500 | 0
|  |  | Interim Housing | PO2W-200000004114 | 2020-02-13 | 2020-11-20 | 17340 | 17340 | 0
|  |  |  | PO2W-210000001628 | 2021-01-21 | 2021-03-24 | 8100 | 8100 | 0
|  | Nelson | 21st Century classroom | PO2W-200000003505 | 2020-01-15 | 2020-04-02 | 4725 | 4725 | 0
|  | Newton | Interim Housing | PO2W-230000000446 | 2022-07-01 | 2022-08-26 | 4500 | 4500 | 0
|  | Sunset | Drinking Fountain replacement | PO2W-210000000383 | 2020-08-11 | 2020-10-21 | 4800 | 4800 | 0
Wolverine Fence Total | [6 empty] | 44465 | 44465 | 0
Manoj Roychowdhury | Mileage | District Office | Cost of Issuance | PO2W-240000000437 | 2023-07-09 | 2023-09-19 | 23.32 | 23.32 | 0
Manoj Roychowdhury Total | [6 empty] | 23.32 | 23.32 | 0
Caston Inc. | Contractor | Grandview | 21st Century classroom | PO2W-240000001253 | 2023-09-12 | 2024-01-22 | 5000 | 5000 | 0
[6 empty] | 2024-12-09 | 13770.85 | 0 | 13770.85
Caston Inc. Total | [6 empty] | 18770.85 | 5000 | 13770.85
Dr. Alfonso Jimenez | Conference | District Office | Cost of Issuance | PO2W-240000000439 | 2023-08-02 | 2023-09-19 | 58.65 | 58.65 | 0
Dr. Alfonso Jimenez Total | [6 empty] | 58.65 | 58.65 | 0
Herc Rentals Inc. | Rental/Moving of container(s) | Grandview | 21st Century classroom | PO2W-240000001651 | 2023-10-26 | 2023-12-18 | 1498.44 | 1498.44 | 0
[6 empty] | 2023-12-19 | 166.24 | 166.24 | 0
[6 empty] | 2025-12-09 | 2986.32 | 0 | 2986.32
Herc Rentals Inc. Total | [6 empty] | 4651 | 1664.68 | 2986.32
Network Integration Company Partners, Inc. (NIC Partners) | Loudspeakers & horns | District Office | 21st Century classroom | PO2W-240000000158 | 2023-07-20 | 2023-10-13 | 261019.31 | 261019.31 | 0
Network Integration Company Partners, Inc. (NIC Partners) Total | [6 empty] | 261019.31 | 261019.31 | 0
Studio Plus Architecture Corp. (TDM Architects, Inc.) | Architect | Baldwin | 21st Century classroom | PO2W-210000002222 | 2021-05-03 | 2021-09-09 | 29733.8 | 29733.8 | 0
[6 empty] | 2021-10-19 | 33815.5 | 33815.5 | 0
[6 empty] | 2024-01-24 | 94483.85 | 94483.85 | 0
[6 empty] | 2024-01-25 | 39140 | 39140 | 0
[6 empty] | 2027-07-11 | 238521.85 | 0 | 238521.85
|  |  | Interim Housing | PO2W-210000002227 | 2021-05-03 | 2023-11-30 | 79400 | 0 | 79400
[6 empty] | 2023-12-09 | -79400 | 0 | -79400
|  | California | 21st Century classroom | PO2W-210000002223 | 2021-05-03 | 2021-09-09 | 24160.2 | 24160.2 | 0
[6 empty] | 2021-10-01 | 18877.95 | 18877.95 | 0
[6 empty] | 2021-10-19 | 19695.11 | 19695.11 | 0
[6 empty] | 2024-01-24 | 63120.59 | 63120.59 | 0
[6 empty] | 2024-01-29 | 39140 | 39140 | 0
[6 empty] | 2027-07-11 | 173121.15 | 0 | 173121.15
|  |  | Interim Housing | PO2W-210000002228 | 2021-05-03 | 2021-09-09 | 3096 | 3096 | 0
[6 empty] | 2021-10-19 | 1550.25 | 1550.25 | 0
[6 empty] | 2023-12-08 | 92753.75 | 0 | 92753.75
[6 empty] | 2023-12-09 | -92753.75 | 0 | -92753.75
|  | Grazide | 21st Century classroom | PO2W-210000002224 | 2021-05-03 | 2021-09-09 | 24121.52 | 24121.52 | 0
[6 empty] | 2021-10-19 | 8978.93 | 8978.93 | 0
[6 empty] | 2024-01-24 | 53450 | 53450 | 0
[6 empty] | 2024-01-29 | 32460 | 32460 | 0
[6 empty] | 2027-07-11 | 211457.55 | 0 | 211457.55
|  |  | Interim Housing | PO2W-210000002229 | 2021-05-03 | 2023-11-30 | 79400 | 0 | 79400
[6 empty] | 2023-12-09 | -79400 | 0 | -79400
|  | Los Altos ES | 21st Century classroom | PO2W-200000000858, 19-100485 | 2018-07-17 | 2018-10-11 | 3514.68 | 3514.68 | 0
[6 empty] | 2019-01-28 | 3712 | 3712 | 0
[6 empty] | 2019-09-05 | 20209.46 | 20209.46 | 0
[6 empty] | 2019-09-13 | 28996.18 | 28996.18 | 0
[6 empty] | 2020-06-04 | 8786.73 | 8786.73 | 0
[6 empty] | 2021-02-05 | 18708.97 | 18708.97 | 0
[6 empty] | 2021-04-19 | 4393.35 | 4393.35 | 0
[6 empty] | 2021-12-20 | 19545.81 | 4393.35 | 15152.46
[6 empty] | 2022-02-07 | -15152.46 | 0 | -15152.46
|  |  |  | PO2W-200000005064 | 2020-05-11 | 2020-10-21 | 12980 | 12980 | 0
|  |  | Interim Housing | PO2W-200000000857, 19-100486 | 2018-07-17 | 2018-11-20 | 1515.6 | 1515.6 | 0
[6 empty] | 2019-02-06 | 3410.12 | 3410.12 | 0
[6 empty] | 2019-03-28 | 4774.16 | 4774.16 | 0
[6 empty] | 2019-09-05 | 14928.74 | 14928.74 | 0
[6 empty] | 2019-11-15 | 2816 | 2816 | 0
[6 empty] | 2019-12-11 | 9472.55 | 9472.55 | 0
[6 empty] | 2020-06-04 | 3789.01 | 3789.01 | 0
[6 empty] | 2023-12-09 | 0 | 0 | 0
|  | Los Molinos | 21st Century classroom | PO2W-210000002225 | 2021-05-03 | 2021-09-09 | 25060.16 | 25060.16 | 0
[6 empty] | 2021-10-19 | 8326.87 | 8326.87 | 0
[6 empty] | 2024-01-24 | 58450 | 58450 | 0
[6 empty] | 2024-01-29 | 32460 | 32460 | 0
[6 empty] | 2027-07-11 | 234636.97 | 0 | 234636.97
|  |  | Interim Housing | PO2W-210000002230 | 2021-05-03 | 2023-11-30 | 79400 | 0 | 79400
[6 empty] | 2023-12-09 | -79400 | 0 | -79400
|  | Nelson | 21st Century classroom | PO2W-200000000859, 19-100470 | 2018-07-17 | 2018-10-11 | 3699.66 | 3699.66 | 0
[6 empty] | 2019-01-28 | 4962 | 4962 | 0
[6 empty] | 2019-09-05 | 21272.98 | 21272.98 | 0
[6 empty] | 2019-09-11 | 30522.1 | 30522.1 | 0
[6 empty] | 2020-06-04 | 9249.12 | 9249.12 | 0
[6 empty] | 2020-10-21 | 19633.76 | 19633.76 | 0
[6 empty] | 2021-04-19 | 4624.55 | 4624.55 | 0
[6 empty] | 2021-12-20 | 4624.55 | 4624.55 | 0
[6 empty] | 2021-12-21 | 13902.48 | 0 | 13902.48
[6 empty] | 2022-02-07 | -13902.48 | 0 | -13902.48
|  |  |  | PO2W-200000005063 | 2020-05-11 | 2020-10-21 | 11306 | 11306 | 0
|  | Sunset | 21st Century classroom | PO2W-210000002226 | 2021-05-03 | 2021-09-09 | 23712 | 23712 | 0
[6 empty] | 2021-10-19 | 5833.89 | 5833.89 | 0
[6 empty] | 2023-12-08 | 157014.11 | 0 | 157014.11
[6 empty] | 2023-12-09 | -157014.11 | 0 | -157014.11
|  |  | Interim Housing | PO2W-210000002231 | 2021-05-03 | 2023-12-08 | 97400 | 0 | 97400
[6 empty] | 2023-12-09 | -97400 | 0 | -97400
|  | Workman ES | 21st Century classroom | PO2W-210000002075 | 2021-04-08 | 2021-08-31 | 8116.8 | 8116.8 | 0
[6 empty] | 2023-12-08 | 5411.2 | 0 | 5411.2
[6 empty] | 2023-12-09 | -5411.2 | 0 | -5411.2
Studio Plus Architecture Corp. (TDM Architects, Inc.) Total | [6 empty] | 1761816.56 | 904079.04 | 857737.52
San Gabriel Valley Tribune | Newspaper Advertisement | Cedarlane | 21st Century classroom | PO2W-210000000882 | 2020-10-05 | 2020-10-19 | 301.67 | 301.67 | 0
|  |  | Interim Housing | PO2W-210000000882 | 2020-10-05 | 2020-10-19 | 301.66 | 301.66 | 0
|  | District Office | 21st Century classroom | PO2W-210000000381 | 2020-08-11 | 2020-10-22 | 632 | 632 | 0
|  |  |  | PO2W-220000001958 | 2022-03-15 | 2022-04-25 | 611.25 | 611.25 | 0
|  | Grandview | 21st Century classroom | PO1-230000000194 | 2022-07-19 | 2022-08-17 | 324.48 | 324.48 | 0
|  | Los Altos HS | 21st Century classroom | (blank) | 2023-12-15 | 2024-06-30 | 292.31 | 0 | 292.31
|  | Mesa Robles | 21st Century classroom | PO2W-210000000882 | 2020-10-05 | 2020-10-19 | 301.67 | 301.67 | 0
|  | Newton | 21st Century classroom | PO1-230000000194 | 2022-07-19 | 2022-08-17 | 324.48 | 324.48 | 0
|  |  | Interim Housing | PO2W-220000000052 | 2021-07-09 | 2021-07-30 | 1088 | 1088 | 0
|  | Sparks MS | 21st Century classroom | PO1-230000000194 | 2022-07-19 | 2022-08-17 | 324.48 | 324.48 | 0
|  | Stimson | 21st Century classroom | (blank) | 2023-12-15 | 2024-06-30 | 292.31 | 0 | 292.31
|  | Wilson HS | 21st Century classroom | (blank) | 2023-12-15 | 2024-06-30 | 292.31 | 0 | 292.31
San Gabriel Valley Tribune Total | [6 empty] | 5086.62 | 4209.69 | 876.93
ATC LLC | Moving of container(s) | District Office | 21st Century classroom | (blank) | 2024-01-17 | 2028-12-09 | 4950 | 0 | 4950
ATC LLC Total | [6 empty] | 4950 | 0 | 4950
Grand Total: | [6 empty] | 62120758.45 | 52692118.15 | 9428640.3

## % Completion_Summary
Combined Headers 2 | Phase | Site | Project | Total Exp. & Committed | Completed Amount | % Completion
Amar-0-21st Century classroom | 0 | Amar | 21st Century classroom | 114873.89 | 114873.89 | 100%
Amar-0-Ceiling replacement | 0 | Amar | Ceiling replacement | 180685 | 180685 | 100%
Amar-0-Drinking Fountain replacement | 0 | Amar | Drinking Fountain replacement | 8200 | 8200 | 100%
Amar-0-Fire Alarm replacement | 0 | Amar | Fire Alarm replacement | 0 | 0 | #DIV/0!
Amar-0-Interim Housing | 0 | Amar | Interim Housing | 0 | 0 | #DIV/0!
Baldwin-3-21st Century classroom | 3 | Baldwin | 21st Century classroom | 832259.96 | 593738.11 | 71.34%
Baldwin-3-Ceiling replacement | 3 | Baldwin | Ceiling replacement | 315644 | 315644 | 100%
Baldwin-3-Drinking Fountain replacement | 3 | Baldwin | Drinking Fountain replacement | 1050 | 1050 | 100%
Baldwin-3-Fire Alarm replacement | 3 | Baldwin | Fire Alarm replacement | 1020 | 1020 | 100%
Baldwin-3-Interim Housing | 3 | Baldwin | Interim Housing | 0 | 0 | #DIV/0!
Bixby-6-21st Century classroom | 6 | Bixby | 21st Century classroom | 168409.54 | 168409.54 | 100%
Bixby-6-Ceiling replacement | 6 | Bixby | Ceiling replacement | 296805 | 296805 | 100%
Bixby-6-Drinking Fountain replacement | 6 | Bixby | Drinking Fountain replacement | 1050 | 1050 | 100%
Bixby-6-Fire Alarm replacement | 6 | Bixby | Fire Alarm replacement | 870 | 870 | 100%
Bixby-6-Interim Housing | 6 | Bixby | Interim Housing | 0 | 0 | #DIV/0!
California-3-21st Century classroom | 3 | California | 21st Century classroom | 593594.78 | 420473.63 | 70.84%
California-3-Ceiling replacement | 3 | California | Ceiling replacement | 236982 | 236982 | 100%
California-3-Drinking Fountain replacement | 3 | California | Drinking Fountain replacement | 1050 | 1050 | 100%
California-3-Fire Alarm replacement | 3 | California | Fire Alarm replacement | 253018.09 | 253018.09 | 100%
California-3-Interim Housing | 3 | California | Interim Housing | 4646.25 | 4646.25 | 100%
Cedarlane-1-21st Century classroom | 1 | Cedarlane | 21st Century classroom | 4688893.36 | 4662080.95 | 99.43%
Cedarlane-1-Ceiling replacement | 1 | Cedarlane | Ceiling replacement | 0 | 0 | #DIV/0!
Cedarlane-1-Drinking Fountain replacement | 1 | Cedarlane | Drinking Fountain replacement | 1200 | 1200 | 100%
Cedarlane-1-Fire Alarm replacement | 1 | Cedarlane | Fire Alarm replacement | 121489.99 | 121489.99 | 100%
Cedarlane-1-Interim Housing | 1 | Cedarlane | Interim Housing | 1292841.26 | 1287107.96 | 99.56%
Del Valle-7-21st Century classroom | 7 | Del Valle | 21st Century classroom | 243706.1 | 243706.1 | 100%
Del Valle-7-Ceiling replacement | 7 | Del Valle | Ceiling replacement | 333183 | 333183 | 100%
Del Valle-7-Drinking Fountain replacement | 7 | Del Valle | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Del Valle-7-Fire Alarm replacement | 7 | Del Valle | Fire Alarm replacement | 37245 | 37245 | 100%
Del Valle-7-Interim Housing | 7 | Del Valle | Interim Housing | 0 | 0 | #DIV/0!
Dibble-0-21st Century classroom | 0 | Dibble | 21st Century classroom | 2700 | 2700 | 100%
Dibble-0-Ceiling replacement | 0 | Dibble | Ceiling replacement | 0 | 0 | #DIV/0!
Dibble-0-Drinking Fountain replacement | 0 | Dibble | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Dibble-0-Fire Alarm replacement | 0 | Dibble | Fire Alarm replacement | 0 | 0 | #DIV/0!
Dibble-0-Interim Housing | 0 | Dibble | Interim Housing | 0 | 0 | #DIV/0!
District Office-0-21st Century classroom | 0 | District Office | 21st Century classroom | 3995913.18 | 1920435.47 | 48.06%
District Office-0-Ceiling replacement | 0 | District Office | Ceiling replacement | 0 | 0 | #DIV/0!
District Office-0-Cost of Issuance | 0 | District Office | Cost of Issuance | 465831.97 | 465831.97 | 100%
District Office-0-Design guidelines | 0 | District Office | Design guidelines | 29500 | 24000 | 81.36%
District Office-0-Fire Alarm replacement | 0 | District Office | Fire Alarm replacement | 0 | 0 | #DIV/0!
District Office-0-Interim Housing | 0 | District Office | Interim Housing | 0 | 0 | #DIV/0!
Fairgrove-4-21st Century classroom | 4 | Fairgrove | 21st Century classroom | 914026.46 | 506526.46 | 55.42%
Fairgrove-4-Ceiling replacement | 4 | Fairgrove | Ceiling replacement | 0 | 0 | #DIV/0!
Fairgrove-4-Drinking Fountain replacement | 4 | Fairgrove | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Fairgrove-4-Fire Alarm replacement | 4 | Fairgrove | Fire Alarm replacement | 406440.79 | 406440.79 | 100%
Fairgrove-4-Interim Housing | 4 | Fairgrove | Interim Housing | 0 | 0 | #DIV/0!
Grandview-2-21st Century classroom | 2 | Grandview | 21st Century classroom | 4440610.34 | 4062137.71 | 91.48%
Grandview-2-Ceiling replacement | 2 | Grandview | Ceiling replacement | 0 | 0 | #DIV/0!
Grandview-2-Drinking Fountain replacement | 2 | Grandview | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Grandview-2-Fire Alarm replacement | 2 | Grandview | Fire Alarm replacement | 170191.36 | 170191.36 | 100%
Grandview-2-Interim Housing | 2 | Grandview | Interim Housing | 0 | 0 | #DIV/0!
Grazide-3-21st Century classroom | 3 | Grazide | 21st Century classroom | 568169.76 | 356712.21 | 62.78%
Grazide-3-Ceiling replacement | 3 | Grazide | Ceiling replacement | 281598 | 281598 | 100%
Grazide-3-Drinking Fountain replacement | 3 | Grazide | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Grazide-3-Fire Alarm replacement | 3 | Grazide | Fire Alarm replacement | 960 | 960 | 100%
Grazide-3-Interim Housing | 3 | Grazide | Interim Housing | 0 | 0 | #DIV/0!
Kwis-7-21st Century classroom | 7 | Kwis | 21st Century classroom | 208973.06 | 208973.06 | 100%
Kwis-7-Ceiling replacement | 7 | Kwis | Ceiling replacement | 271028 | 271028 | 100%
Kwis-7-Drinking Fountain replacement | 7 | Kwis | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Kwis-7-Fire Alarm replacement | 7 | Kwis | Fire Alarm replacement | 37266 | 37266 | 100%
Kwis-7-Interim Housing | 7 | Kwis | Interim Housing | 0 | 0 | #DIV/0!
La Puente HS-5-21st Century classroom | 5 | La Puente HS | 21st Century classroom | 3162187.94 | 612177.56 | 19.36%
La Puente HS-5-Ceiling replacement | 5 | La Puente HS | Ceiling replacement | 0 | 0 | #DIV/0!
La Puente HS-5-Drinking Fountain replacement | 5 | La Puente HS | Drinking Fountain replacement | 0 | 0 | #DIV/0!
La Puente HS-5-Fire Alarm replacement | 5 | La Puente HS | Fire Alarm replacement | 2717.95 | 2717.95 | 100%
La Puente HS-5-Interim Housing | 5 | La Puente HS | Interim Housing | 0 | 0 | #DIV/0!
Lassalette-6-21st Century classroom | 6 | Lassalette | 21st Century classroom | 266630.11 | 266630.11 | 100%
Lassalette-6-Ceiling replacement | 6 | Lassalette | Ceiling replacement | 0 | 0 | #DIV/0!
Lassalette-6-Drinking Fountain replacement | 6 | Lassalette | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Lassalette-6-Fire Alarm replacement | 6 | Lassalette | Fire Alarm replacement | 0 | 0 | #DIV/0!
Lassalette-6-Interim Housing | 6 | Lassalette | Interim Housing | 0 | 0 | #DIV/0!
Los Altos ES-2-21st Century classroom | 2 | Los Altos ES | 21st Century classroom | 3432665.06 | 3432665.06 | 100%
Los Altos ES-2-Ceiling replacement | 2 | Los Altos ES | Ceiling replacement | 232310 | 232310 | 100%
Los Altos ES-2-Drinking Fountain replacement | 2 | Los Altos ES | Drinking Fountain replacement | 1050 | 1050 | 100%
Los Altos ES-2-Fire Alarm replacement | 2 | Los Altos ES | Fire Alarm replacement | 131353.53 | 131353.53 | 100%
Los Altos ES-2-Interim Housing | 2 | Los Altos ES | Interim Housing | 568628.1 | 568628.1 | 100%
Los Altos HS-5-21st Century classroom | 5 | Los Altos HS | 21st Century classroom | 978083.36 | 822841.05 | 84.13%
Los Altos HS-5-Ceiling replacement | 5 | Los Altos HS | Ceiling replacement | 0 | 0 | #DIV/0!
Los Altos HS-5-Drinking Fountain replacement | 5 | Los Altos HS | Drinking Fountain replacement | 6600 | 6600 | 100%
Los Altos HS-5-Fire Alarm replacement | 5 | Los Altos HS | Fire Alarm replacement | 5500 | 5500 | 100%
Los Altos HS-5-Interim Housing | 5 | Los Altos HS | Interim Housing | 0 | 0 | #DIV/0!
Los Molinos-4-21st Century classroom | 4 | Los Molinos | 21st Century classroom | 580518.87 | 345881.9 | 59.58%
Los Molinos-4-Ceiling replacement | 4 | Los Molinos | Ceiling replacement | 359035 | 359035 | 100%
Los Molinos-4-Drinking Fountain replacement | 4 | Los Molinos | Drinking Fountain replacement | 1050 | 1050 | 100%
Los Molinos-4-Fire Alarm replacement | 4 | Los Molinos | Fire Alarm replacement | 216681.97 | 216681.97 | 100%
Los Molinos-4-Interim Housing | 4 | Los Molinos | Interim Housing | 0 | 0 | #DIV/0!
Los Robles-9-21st Century classroom | 9 | Los Robles | 21st Century classroom | 119368.08 | 119368.08 | 100%
Los Robles-9-Ceiling replacement | 9 | Los Robles | Ceiling replacement | 219377 | 219377 | 100%
Los Robles-9-Drinking Fountain replacement | 9 | Los Robles | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Los Robles-9-Fire Alarm replacement | 9 | Los Robles | Fire Alarm replacement | 37275 | 37275 | 100%
Los Robles-9-Interim Housing | 9 | Los Robles | Interim Housing | 0 | 0 | #DIV/0!
Mesa Robles-1-21st Century classroom | 1 | Mesa Robles | 21st Century classroom | 5482236.7 | 5477617.14 | 99.92%
Mesa Robles-1-Ceiling replacement | 1 | Mesa Robles | Ceiling replacement | 0 | 0 | #DIV/0!
Mesa Robles-1-Drinking Fountain replacement | 1 | Mesa Robles | Drinking Fountain replacement | 12050 | 12050 | 100%
Mesa Robles-1-Fire Alarm replacement | 1 | Mesa Robles | Fire Alarm replacement | 168638.61 | 168638.61 | 100%
Mesa Robles-1-Interim Housing | 1 | Mesa Robles | Interim Housing | 1954150.57 | 1954150.57 | 100%
Nelson-1-21st Century classroom | 1 | Nelson | 21st Century classroom | 3409017.99 | 3409017.99 | 100%
Nelson-1-Ceiling replacement | 1 | Nelson | Ceiling replacement | 309746 | 309746 | 100%
Nelson-1-Drinking Fountain replacement | 1 | Nelson | Drinking Fountain replacement | 1050 | 1050 | 100%
Nelson-1-Fire Alarm replacement | 1 | Nelson | Fire Alarm replacement | 143560.08 | 143560.08 | 100%
Nelson-1-Interim Housing | 1 | Nelson | Interim Housing | 0 | 0 | #DIV/0!
Newton-1-21st Century classroom | 1 | Newton | 21st Century classroom | 3787547.41 | 3514207.05 | 92.78%
Newton-1-Ceiling replacement | 1 | Newton | Ceiling replacement | 0 | 0 | #DIV/0!
Newton-1-Drinking Fountain replacement | 1 | Newton | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Newton-1-Fire Alarm replacement | 1 | Newton | Fire Alarm replacement | 100950.01 | 100950.01 | 100%
Newton-1-Interim Housing | 1 | Newton | Interim Housing | 779046.39 | 776271.39 | 99.64%
Orange Grove-3-21st Century classroom | 3 | Orange Grove | 21st Century classroom | 461734.26 | 239734.26 | 51.92%
Orange Grove-3-Ceiling replacement | 3 | Orange Grove | Ceiling replacement | 0 | 0 | #DIV/0!
Orange Grove-3-Drinking Fountain replacement | 3 | Orange Grove | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Orange Grove-3-Fire Alarm replacement | 3 | Orange Grove | Fire Alarm replacement | 38205 | 38205 | 100%
Orange Grove-3-Interim Housing | 3 | Orange Grove | Interim Housing | 0 | 0 | #DIV/0!
Palm Canyon-0-21st Century classroom | 0 | Palm Canyon | 21st Century classroom | 10368.74 | 10368.74 | 100%
Palm Canyon-0-Ceiling replacement | 0 | Palm Canyon | Ceiling replacement | 0 | 0 | #DIV/0!
Palm Canyon-0-Drinking Fountain replacement | 0 | Palm Canyon | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Palm Canyon-0-Fire Alarm replacement | 0 | Palm Canyon | Fire Alarm replacement | 0 | 0 | #DIV/0!
Palm Canyon-0-Interim Housing | 0 | Palm Canyon | Interim Housing | 0 | 0 | #DIV/0!
Palm-6-21st Century classroom | 6 | Palm | 21st Century classroom | 180866.92 | 180866.92 | 100%
Palm-6-Ceiling replacement | 6 | Palm | Ceiling replacement | 232310 | 232310 | 100%
Palm-6-Drinking Fountain replacement | 6 | Palm | Drinking Fountain replacement | 1050 | 1050 | 100%
Palm-6-Fire Alarm replacement | 6 | Palm | Fire Alarm replacement | 37245 | 37245 | 100%
Palm-6-Interim Housing | 6 | Palm | Interim Housing | 0 | 0 | #DIV/0!
Sierra Vista-8-21st Century classroom | 8 | Sierra Vista | 21st Century classroom | 174066.97 | 174066.97 | 100%
Sierra Vista-8-Ceiling replacement | 8 | Sierra Vista | Ceiling replacement | 0 | 0 | #DIV/0!
Sierra Vista-8-Drinking Fountain replacement | 8 | Sierra Vista | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Sierra Vista-8-Fire Alarm replacement | 8 | Sierra Vista | Fire Alarm replacement | 38175 | 38175 | 100%
Sierra Vista-8-Interim Housing | 8 | Sierra Vista | Interim Housing | 0 | 0 | #DIV/0!
Sparks ES-7-21st Century classroom | 7 | Sparks ES | 21st Century classroom | 258921.15 | 258921.15 | 100%
Sparks ES-7-Ceiling replacement | 7 | Sparks ES | Ceiling replacement | 258122 | 258122 | 100%
Sparks ES-7-Drinking Fountain replacement | 7 | Sparks ES | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Sparks ES-7-Fire Alarm replacement | 7 | Sparks ES | Fire Alarm replacement | 930 | 930 | 100%
Sparks ES-7-Interim Housing | 7 | Sparks ES | Interim Housing | 0 | 0 | #DIV/0!
Sparks MS-2-21st Century classroom | 2 | Sparks MS | 21st Century classroom | 3023402.28 | 2869680.16 | 94.92%
Sparks MS-2-Ceiling replacement | 2 | Sparks MS | Ceiling replacement | 0 | 0 | #DIV/0!
Sparks MS-2-Drinking Fountain replacement | 2 | Sparks MS | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Sparks MS-2-Fire Alarm replacement | 2 | Sparks MS | Fire Alarm replacement | 164685 | 164685 | 100%
Sparks MS-2-Interim Housing | 2 | Sparks MS | Interim Housing | 0 | 0 | #DIV/0!
Stimson-4-21st Century classroom | 4 | Stimson | 21st Century classroom | 31479.77 | 31187.46 | 99.07%
Stimson-4-Ceiling replacement | 4 | Stimson | Ceiling replacement | 0 | 0 | #DIV/0!
Stimson-4-Drinking Fountain replacement | 4 | Stimson | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Stimson-4-Fire Alarm replacement | 4 | Stimson | Fire Alarm replacement | 30000 | 30000 | 100%
Stimson-4-Interim Housing | 4 | Stimson | Interim Housing | 0 | 0 | #DIV/0!
Sunset-4-21st Century classroom | 4 | Sunset | 21st Century classroom | 210528.86 | 210528.86 | 100%
Sunset-4-Ceiling replacement | 4 | Sunset | Ceiling replacement | 242880 | 242880 | 100%
Sunset-4-Drinking Fountain replacement | 4 | Sunset | Drinking Fountain replacement | 22800 | 22800 | 100%
Sunset-4-Fire Alarm replacement | 4 | Sunset | Fire Alarm replacement | 36939 | 36939 | 100%
Sunset-4-Interim Housing | 4 | Sunset | Interim Housing | 0 | 0 | #DIV/0!
Temple-8-21st Century classroom | 8 | Temple | 21st Century classroom | 134841.18 | 134841.18 | 100%
Temple-8-Ceiling replacement | 8 | Temple | Ceiling replacement | 258091 | 258091 | 100%
Temple-8-Drinking Fountain replacement | 8 | Temple | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Temple-8-Fire Alarm replacement | 8 | Temple | Fire Alarm replacement | 0 | 0 | #DIV/0!
Temple-8-Interim Housing | 8 | Temple | Interim Housing | 0 | 0 | #DIV/0!
Valinda-6-21st Century classroom | 6 | Valinda | 21st Century classroom | 287194.59 | 287194.59 | 100%
Valinda-6-Ceiling replacement | 6 | Valinda | Ceiling replacement | 0 | 0 | #DIV/0!
Valinda-6-Drinking Fountain replacement | 6 | Valinda | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Valinda-6-Fire Alarm replacement | 6 | Valinda | Fire Alarm replacement | 1125 | 1125 | 100%
Valinda-6-Interim Housing | 6 | Valinda | Interim Housing | 0 | 0 | #DIV/0!
Valley-8-21st Century classroom | 8 | Valley | 21st Century classroom | 108962.03 | 108962.03 | 100%
Valley-8-Ceiling replacement | 8 | Valley | Ceiling replacement | 0 | 0 | #DIV/0!
Valley-8-Drinking Fountain replacement | 8 | Valley | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Valley-8-Fire Alarm replacement | 8 | Valley | Fire Alarm replacement | 252044.67 | 252044.67 | 100%
Valley-8-Interim Housing | 8 | Valley | Interim Housing | 0 | 0 | #DIV/0!
Wedgeworth-0-21st Century classroom | 0 | Wedgeworth | 21st Century classroom | 158909.98 | 158909.98 | 100%
Wedgeworth-0-Ceiling replacement | 0 | Wedgeworth | Ceiling replacement | 0 | 0 | #DIV/0!
Wedgeworth-0-Drinking Fountain replacement | 0 | Wedgeworth | Drinking Fountain replacement | 3502.75 | 3502.75 | 100%
Wedgeworth-0-Fire Alarm replacement | 0 | Wedgeworth | Fire Alarm replacement | 0 | 0 | #DIV/0!
Wedgeworth-0-Interim Housing | 0 | Wedgeworth | Interim Housing | 0 | 0 | #DIV/0!
Willow-0-21st Century classroom | 0 | Willow | 21st Century classroom | 2700 | 2700 | 100%
Willow-0-Ceiling replacement | 0 | Willow | Ceiling replacement | 0 | 0 | #DIV/0!
Willow-0-Drinking Fountain replacement | 0 | Willow | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Willow-0-Fire Alarm replacement | 0 | Willow | Fire Alarm replacement | 0 | 0 | #DIV/0!
Willow-0-Interim Housing | 0 | Willow | Interim Housing | 0 | 0 | #DIV/0!
Wilson HS-5-21st Century classroom | 5 | Wilson HS | 21st Century classroom | 866040 | 708992.69 | 81.87%
Wilson HS-5-Ceiling replacement | 5 | Wilson HS | Ceiling replacement | 0 | 0 | #DIV/0!
Wilson HS-5-Drinking Fountain replacement | 5 | Wilson HS | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Wilson HS-5-Fire Alarm replacement | 5 | Wilson HS | Fire Alarm replacement | 305385.18 | 305385.18 | 100%
Wilson HS-5-Interim Housing | 5 | Wilson HS | Interim Housing | 0 | 0 | #DIV/0!
Wing Lane-9-21st Century classroom | 9 | Wing Lane | 21st Century classroom | 173884.51 | 173884.51 | 100%
Wing Lane-9-Ceiling replacement | 9 | Wing Lane | Ceiling replacement | 302738 | 302738 | 100%
Wing Lane-9-Drinking Fountain replacement | 9 | Wing Lane | Drinking Fountain replacement | 6800 | 6800 | 100%
Wing Lane-9-Fire Alarm replacement | 9 | Wing Lane | Fire Alarm replacement | 37245 | 37245 | 100%
Wing Lane-9-Interim Housing | 9 | Wing Lane | Interim Housing | 0 | 0 | #DIV/0!
Workman ES-2-21st Century classroom | 2 | Workman ES | 21st Century classroom | 2555658.55 | 2555658.55 | 100%
Workman ES-2-Ceiling replacement | 2 | Workman ES | Ceiling replacement | 242880 | 242880 | 100%
Workman ES-2-Drinking Fountain replacement | 2 | Workman ES | Drinking Fountain replacement | 1200 | 1200 | 100%
Workman ES-2-Fire Alarm replacement | 2 | Workman ES | Fire Alarm replacement | 157892.01 | 157892.01 | 100%
Workman ES-2-Interim Housing | 2 | Workman ES | Interim Housing | 0 | 0 | #DIV/0!
Workman HS-5-21st Century classroom | 5 | Workman HS | 21st Century classroom | 2818002.18 | 665644.8 | 23.62%
Workman HS-5-Ceiling replacement | 5 | Workman HS | Ceiling replacement | 0 | 0 | #DIV/0!
Workman HS-5-Drinking Fountain replacement | 5 | Workman HS | Drinking Fountain replacement | 0 | 0 | #DIV/0!
Workman HS-5-Fire Alarm replacement | 5 | Workman HS | Fire Alarm replacement | 0 | 0 | #DIV/0!
Workman HS-5-Interim Housing | 5 | Workman HS | Interim Housing | 0 | 0 | #DIV/0!
|  |  | Total: | 62120758.45 | 52692118.15
|  |  |  | 999999999.99 | 999999999.99

## Measure BB_Comparison Data
Combined Headers | Phase | Site | Project | Category | Preliminary Budget | Proposed Budget | Total Exp. & Committed | Committed Amount | Completed Amount | % Completion
Amar-21st Century classroom-Advertisement | 0 | Amar | 21st Century classroom | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Asbestos oversight/survey/abatement | 0 | Amar | 21st Century classroom | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-CM/PM Management | 0 | Amar | 21st Century classroom | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Construction Contingency | 0 | Amar | 21st Century classroom | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Contractor | 0 | Amar | 21st Century classroom | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Design | 0 | Amar | 21st Century classroom | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-DSA Fees | 0 | Amar | 21st Century classroom | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-DSA Inspection | 0 | Amar | 21st Century classroom | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-DSA Special Inspection | 0 | Amar | 21st Century classroom | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Environ Consultant | 0 | Amar | 21st Century classroom | Environ Consultant | 0 | 0 | 2600 | 0 | 2600 | 100%
Amar-21st Century classroom-FF & E | 0 | Amar | 21st Century classroom | FF & E | N/A | No Proposal Provided | 92679.97 | 0 | 92679.97 | 100%
Amar-21st Century classroom-Legal Services | 0 | Amar | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Move classroom | 0 | Amar | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Move Management | 0 | Amar | 21st Century classroom | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Reprographics | 0 | Amar | 21st Century classroom | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-21st Century classroom-Technology | 0 | Amar | 21st Century classroom | Technology | N/A | N/A | 19593.92 | 0 | 19593.92 | 100%
Amar-Ceiling replacement-CM/PM Management | 0 | Amar | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Ceiling replacement-Contractor | 0 | Amar | Ceiling replacement | Contractor | 180685 | 180685 | 180685 | 0 | 180685 | 100%
Amar-Drinking Fountain replacement-Advertisement | 0 | Amar | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking Fountain replacement-Contractor | 0 | Amar | Drinking Fountain replacement | Contractor | 8200 | 8200 | 8200 | 0 | 8200 | 100%
Amar-Drinking Fountain replacement-Design | 0 | Amar | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking Fountain replacement-DSA Fees | 0 | Amar | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking Fountain replacement-DSA Inspection | 0 | Amar | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking Fountain replacement-DSA Special Inspection | 0 | Amar | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking Fountain replacement-Environ Consultant | 0 | Amar | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Drinking Fountain replacement-Reprographics | 0 | Amar | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm replacement-Advertisement | 0 | Amar | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm replacement-Contractor | 0 | Amar | Fire Alarm replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm replacement-Design | 0 | Amar | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm replacement-DSA Fees | 0 | Amar | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm replacement-DSA Inspection | 0 | Amar | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm replacement-Environ Consultant | 0 | Amar | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Fire Alarm replacement-Reprographics | 0 | Amar | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Advertisement | 0 | Amar | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Alarm | 0 | Amar | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-CM/PM Management | 0 | Amar | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Construction Contingency | 0 | Amar | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Contractor | 0 | Amar | Interim Housing | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Design | 0 | Amar | Interim Housing | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-DSA Fees | 0 | Amar | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-DSA Inspection | 0 | Amar | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-DSA Special Inspection | 0 | Amar | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Environ Consultant | 0 | Amar | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-FF & E | 0 | Amar | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Legal Services | 0 | Amar | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Modular Buildings | 0 | Amar | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Move Management | 0 | Amar | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Reprographics | 0 | Amar | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Amar-Interim Housing-Technology | 0 | Amar | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-Advertisement | 3 | Baldwin | 21st Century classroom | Advertisement | 2001.44 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-Asbestos oversight/survey/abatement | 3 | Baldwin | 21st Century classroom | Asbestos oversight/survey/abatement | 105000 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-CM/PM Management | 3 | Baldwin | 21st Century classroom | CM/PM Management | 319939.4 | N/A | 8370 | 0 | 8370 | 100%
Baldwin-21st Century classroom-Construction Contingency | 3 | Baldwin | 21st Century classroom | Construction Contingency | 311903.6 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-Contractor | 3 | Baldwin | 21st Century classroom | Contractor | 3327075.7 | N/A | 56500 | 0 | 56500 | 100%
Baldwin-21st Century classroom-Design | 3 | Baldwin | 21st Century classroom | Design | 382092.83 | 325287 | 435695 | 238521.85 | 197173.15 | 45.25%
Baldwin-21st Century classroom-DSA Fees | 3 | Baldwin | 21st Century classroom | DSA Fees | 63682.14 | N/A | 37740 | 0 | 37740 | 100%
Baldwin-21st Century classroom-DSA Inspection | 3 | Baldwin | 21st Century classroom | DSA Inspection | 54584.69 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-DSA Special Inspection | 3 | Baldwin | 21st Century classroom | DSA Special Inspection | 45487.24 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-Environ Consultant | 3 | Baldwin | 21st Century classroom | Environ Consultant | 16011.51 | N/A | 2600 | 0 | 2600 | 100%
Baldwin-21st Century classroom-FF & E | 3 | Baldwin | 21st Century classroom | FF & E | 580000 | No Proposal Provided | 43907.51 | 0 | 43907.51 | 100%
Baldwin-21st Century classroom-Legal Services | 3 | Baldwin | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-Move classroom | 3 | Baldwin | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-Move Management | 3 | Baldwin | 21st Century classroom | Move Management | 14555.92 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-Reprographics | 3 | Baldwin | 21st Century classroom | Reprographics | 2001.44 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-21st Century classroom-Technology | 3 | Baldwin | 21st Century classroom | Technology | 580000 | No Proposal Provided | 247447.45 | 0 | 247447.45 | 100%
Baldwin-Ceiling replacement-CM/PM Management | 3 | Baldwin | Ceiling replacement | CM/PM Management | N/A | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Ceiling replacement-Contractor | 3 | Baldwin | Ceiling replacement | Contractor | 315644 | 315644 | 315644 | 0 | 315644 | 100%
Baldwin-Drinking Fountain replacement-Advertisement | 3 | Baldwin | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking Fountain replacement-Contractor | 3 | Baldwin | Drinking Fountain replacement | Contractor | 22500 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking Fountain replacement-Design | 3 | Baldwin | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking Fountain replacement-DSA Fees | 3 | Baldwin | Drinking Fountain replacement | DSA Fees | 0 | No Proposal Provided | 1050 | 0 | 1050 | 100%
Baldwin-Drinking Fountain replacement-DSA Inspection | 3 | Baldwin | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking Fountain replacement-DSA Special Inspection | 3 | Baldwin | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking Fountain replacement-Environ Consultant | 3 | Baldwin | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Drinking Fountain replacement-Reprographics | 3 | Baldwin | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm replacement-Advertisement | 3 | Baldwin | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm replacement-Contractor | 3 | Baldwin | Fire Alarm replacement | Contractor | 435000 | 338939 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm replacement-Design | 3 | Baldwin | Fire Alarm replacement | Design | 0 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm replacement-DSA Fees | 3 | Baldwin | Fire Alarm replacement | DSA Fees | 0 | No Proposal Provided | 1020 | 0 | 1020 | 100%
Baldwin-Fire Alarm replacement-DSA Inspection | 3 | Baldwin | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm replacement-Environ Consultant | 3 | Baldwin | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Fire Alarm replacement-Reprographics | 3 | Baldwin | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Advertisement | 3 | Baldwin | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Alarm | 3 | Baldwin | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-CM/PM Management | 3 | Baldwin | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Construction Contingency | 3 | Baldwin | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Contractor | 3 | Baldwin | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Design | 3 | Baldwin | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-DSA Fees | 3 | Baldwin | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-DSA Inspection | 3 | Baldwin | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-DSA Special Inspection | 3 | Baldwin | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Environ Consultant | 3 | Baldwin | Interim Housing | Environ Consultant | N/A | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-FF & E | 3 | Baldwin | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Legal Services | 3 | Baldwin | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Modular Buildings | 3 | Baldwin | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Move Management | 3 | Baldwin | Interim Housing | Move Management | N/A | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Reprographics | 3 | Baldwin | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Baldwin-Interim Housing-Technology | 3 | Baldwin | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Advertisement | 6 | Bixby | 21st Century classroom | Advertisement | 1477.85 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Asbestos oversight/survey/abatement | 6 | Bixby | 21st Century classroom | Asbestos oversight/survey/abatement | 73500 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-CM/PM Management | 6 | Bixby | 21st Century classroom | CM/PM Management | 235166.16 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Construction Contingency | 6 | Bixby | 21st Century classroom | Construction Contingency | 230307.4 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Contractor | 6 | Bixby | 21st Century classroom | Contractor | 2456689.04 | N/A | 52500 | 0 | 52500 | 100%
Bixby-21st Century classroom-Design | 6 | Bixby | 21st Century classroom | Design | 282134.63 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-DSA Fees | 6 | Bixby | 21st Century classroom | DSA Fees | 47022.44 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-DSA Inspection | 6 | Bixby | 21st Century classroom | DSA Inspection | 40304.95 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-DSA Special Inspection | 6 | Bixby | 21st Century classroom | DSA Special Inspection | 20152.47 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Environ Consultant | 6 | Bixby | 21st Century classroom | Environ Consultant | 11822.78 | No Proposal Provided | 2600 | 0 | 2600 | 100%
Bixby-21st Century classroom-FF & E | 6 | Bixby | 21st Century classroom | FF & E | 420000 | No Proposal Provided | 20720.61 | 0 | 20720.61 | 100%
Bixby-21st Century classroom-Legal Services | 6 | Bixby | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Move classroom | 6 | Bixby | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Move Management | 6 | Bixby | 21st Century classroom | Move Management | 10747.99 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Reprographics | 6 | Bixby | 21st Century classroom | Reprographics | 1477.85 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-21st Century classroom-Technology | 6 | Bixby | 21st Century classroom | Technology | 420000 | No Proposal Provided | 92588.93 | 0 | 92588.93 | 100%
Bixby-Ceiling replacement-CM/PM Management | 6 | Bixby | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Ceiling replacement-Contractor | 6 | Bixby | Ceiling replacement | Contractor | 296805 | 296805 | 296805 | 0 | 296805 | 100%
Bixby-Drinking Fountain replacement-Advertisement | 6 | Bixby | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking Fountain replacement-Contractor | 6 | Bixby | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking Fountain replacement-Design | 6 | Bixby | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking Fountain replacement-DSA Fees | 6 | Bixby | Drinking Fountain replacement | DSA Fees | 0 | 0 | 1050 | 0 | 1050 | 100%
Bixby-Drinking Fountain replacement-DSA Inspection | 6 | Bixby | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking Fountain replacement-DSA Special Inspection | 6 | Bixby | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking Fountain replacement-Environ Consultant | 6 | Bixby | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Drinking Fountain replacement-Reprographics | 6 | Bixby | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm replacement-Advertisement | 6 | Bixby | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm replacement-Contractor | 6 | Bixby | Fire Alarm replacement | Contractor | 315000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm replacement-Design | 6 | Bixby | Fire Alarm replacement | Design | 12125 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm replacement-DSA Fees | 6 | Bixby | Fire Alarm replacement | DSA Fees | 0 | 0 | 870 | 0 | 870 | 100%
Bixby-Fire Alarm replacement-DSA Inspection | 6 | Bixby | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm replacement-Environ Consultant | 6 | Bixby | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Fire Alarm replacement-Reprographics | 6 | Bixby | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Advertisement | 6 | Bixby | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Alarm | 6 | Bixby | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-CM/PM Management | 6 | Bixby | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Construction Contingency | 6 | Bixby | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Contractor | 6 | Bixby | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Design | 6 | Bixby | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-DSA Fees | 6 | Bixby | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-DSA Inspection | 6 | Bixby | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-DSA Special Inspection | 6 | Bixby | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Environ Consultant | 6 | Bixby | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-FF & E | 6 | Bixby | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Legal Services | 6 | Bixby | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Modular Buildings | 6 | Bixby | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Move Management | 6 | Bixby | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Reprographics | 6 | Bixby | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Bixby-Interim Housing-Technology | 6 | Bixby | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-Advertisement | 3 | California | 21st Century classroom | Advertisement | 2752.27 | 0 | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-Asbestos oversight/survey/abatement | 3 | California | 21st Century classroom | Asbestos oversight/survey/abatement | 52500 | N/A | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-CM/PM Management | 3 | California | 21st Century classroom | CM/PM Management | 173510.81 | N/A | 17610 | 0 | 17610 | 100%
California-21st Century classroom-Construction Contingency | 3 | California | 21st Century classroom | Construction Contingency | 200164.87 | N/A | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-Contractor | 3 | California | 21st Century classroom | Contractor | 2168827.2 | No Proposal Provided | 52744.48 | 0 | 52744.48 | 100%
California-21st Century classroom-Design | 3 | California | 21st Century classroom | Design | 210173.13 | 270392 | 338115 | 173121.15 | 164993.85 | 48.8%
California-21st Century classroom-DSA Fees | 3 | California | 21st Century classroom | DSA Fees | 40032.98 | N/A | 26400 | 0 | 26400 | 100%
California-21st Century classroom-DSA Inspection | 3 | California | 21st Century classroom | DSA Inspection | 35028.85 | N/A | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-DSA Special Inspection | 3 | California | 21st Century classroom | DSA Special Inspection | 15012.37 | N/A | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-Environ Consultant | 3 | California | 21st Century classroom | Environ Consultant | 28125 | No Proposal Provided | 2600 | 0 | 2600 | 100%
California-21st Century classroom-FF & E | 3 | California | 21st Century classroom | FF & E | 300000 | No Proposal Provided | 20720.61 | 0 | 20720.61 | 100%
California-21st Century classroom-Legal Services | 3 | California | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-Move classroom | 3 | California | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-Move Management | 3 | California | 21st Century classroom | Move Management | 8006.6 | N/A | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-Reprographics | 3 | California | 21st Century classroom | Reprographics | 2752.27 | N/A | 0 | 0 | 0 | #DIV/0!
California-21st Century classroom-Technology | 3 | California | 21st Century classroom | Technology | 300000 | No Proposal Provided | 135404.69 | 0 | 135404.69 | 100%
California-Ceiling replacement-CM/PM Management | 3 | California | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Ceiling replacement-Contractor | 3 | California | Ceiling replacement | Contractor | 236982 | 236982 | 236982 | 0 | 236982 | 100%
California-Drinking Fountain replacement-Advertisement | 3 | California | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking Fountain replacement-Contractor | 3 | California | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
California-Drinking Fountain replacement-Design | 3 | California | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking Fountain replacement-DSA Fees | 3 | California | Drinking Fountain replacement | DSA Fees | 1050 | No Proposal Provided | 1050 | 0 | 1050 | 100%
California-Drinking Fountain replacement-DSA Inspection | 3 | California | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking Fountain replacement-DSA Special Inspection | 3 | California | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking Fountain replacement-Environ Consultant | 3 | California | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Drinking Fountain replacement-Reprographics | 3 | California | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Fire Alarm replacement-Advertisement | 3 | California | Fire Alarm replacement | Advertisement | 400 | 0 | 0 | 0 | 0 | #DIV/0!
California-Fire Alarm replacement-Contractor | 3 | California | Fire Alarm replacement | Contractor | 225000 | 226573.08 | 226573.09 | 0 | 226573.09 | 100%
California-Fire Alarm replacement-Design | 3 | California | Fire Alarm replacement | Design | 12125 | No Proposal Provided | 12125 | 0 | 12125 | 100%
California-Fire Alarm replacement-DSA Fees | 3 | California | Fire Alarm replacement | DSA Fees | 780 | No Proposal Provided | 2070 | 0 | 2070 | 100%
California-Fire Alarm replacement-DSA Inspection | 3 | California | Fire Alarm replacement | DSA Inspection | 12250 | No Proposal Provided | 12250 | 0 | 12250 | 100%
California-Fire Alarm replacement-Environ Consultant | 3 | California | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Fire Alarm replacement-Reprographics | 3 | California | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Advertisement | 3 | California | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Alarm | 3 | California | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-CM/PM Management | 3 | California | Interim Housing | CM/PM Management | 51590 | N/A | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Construction Contingency | 3 | California | Interim Housing | Construction Contingency | 77000 | N/A | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Contractor | 3 | California | Interim Housing | Contractor | 770000 | N/A | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Design | 3 | California | Interim Housing | Design | 80000 | N/A | 4646.25 | 0 | 4646.25 | 100%
California-Interim Housing-DSA Fees | 3 | California | Interim Housing | DSA Fees | 16100 | N/A | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-DSA Inspection | 3 | California | Interim Housing | DSA Inspection | 13800 | N/A | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-DSA Special Inspection | 3 | California | Interim Housing | DSA Special Inspection | 13800 | N/A | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Environ Consultant | 3 | California | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-FF & E | 3 | California | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Legal Services | 3 | California | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Modular Buildings | 3 | California | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Move Management | 3 | California | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Reprographics | 3 | California | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
California-Interim Housing-Technology | 3 | California | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-21st Century classroom-Advertisement | 1 | Cedarlane | 21st Century classroom | Advertisement | 1728.75 | No Proposal Provided | 301.67 | 0 | 301.67 | 100%
Cedarlane-21st Century classroom-Asbestos oversight/survey/abatement | 1 | Cedarlane | 21st Century classroom | Asbestos oversight/survey/abatement | 100000 | Incl in GC | 0 | 0 | 0 | #DIV/0!
Cedarlane-21st Century classroom-CM/PM Management | 1 | Cedarlane | 21st Century classroom | CM/PM Management | 276221.51 | 187122 | 187100 | 0 | 187100 | 100%
Cedarlane-21st Century classroom-Construction Contingency | 1 | Cedarlane | 21st Century classroom | Construction Contingency | 269407.5 | 299000 | 0 | 0 | 0 | #DIV/0!
Cedarlane-21st Century classroom-Contractor | 1 | Cedarlane | 21st Century classroom | Contractor | 2873769.8 | 2990000 | 3203141.91 | 0 | 3203141.91 | 100%
Cedarlane-21st Century classroom-Design | 1 | Cedarlane | 21st Century classroom | Design | 330033.62 | 153600 | 153600 | 26812.41 | 126787.59 | 82.54%
Cedarlane-21st Century classroom-DSA Fees | 1 | Cedarlane | 21st Century classroom | DSA Fees | 55005.6 | No Proposal Provided | 41121.47 | 0 | 41121.47 | 100%
Cedarlane-21st Century classroom-DSA Inspection | 1 | Cedarlane | 21st Century classroom | DSA Inspection | 47147.66 | 93600 | 68832 | 0 | 68832 | 100%
Cedarlane-21st Century classroom-DSA Special Inspection | 1 | Cedarlane | 21st Century classroom | DSA Special Inspection | 23573 | N/A | 0 | 0 | 0 | #DIV/0!
Cedarlane-21st Century classroom-Environ Consultant | 1 | Cedarlane | 21st Century classroom | Environ Consultant | 13829.98 | 0 | 29325 | 0 | 29325 | 100%
Cedarlane-21st Century classroom-FF & E | 1 | Cedarlane | 21st Century classroom | FF & E | 500000 | 453688.26 | 529098.91 | 0 | 529098.91 | 100%
Cedarlane-21st Century classroom-Legal Services | 1 | Cedarlane | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-21st Century classroom-Move classroom | 1 | Cedarlane | 21st Century classroom | Move classroom | 0 | 0 | 2548.26 | 0 | 2548.26 | 100%
Cedarlane-21st Century classroom-Move Management | 1 | Cedarlane | 21st Century classroom | Move Management | 12572.71 | 0 | 3723 | 0 | 3723 | 100%
Cedarlane-21st Century classroom-Reprographics | 1 | Cedarlane | 21st Century classroom | Reprographics | 1728.75 | 0 | 216.16 | 0 | 216.16 | 100%
Cedarlane-21st Century classroom-Technology | 1 | Cedarlane | 21st Century classroom | Technology | 500000 | 54618.01 | 469884.98 | 0 | 469884.98 | 100%
Cedarlane-Ceiling replacement-CM/PM Management | 1 | Cedarlane | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Ceiling replacement-Contractor | 1 | Cedarlane | Ceiling replacement | Contractor | N/A | N/A | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking Fountain replacement-Advertisement | 1 | Cedarlane | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking Fountain replacement-Contractor | 1 | Cedarlane | Drinking Fountain replacement | Contractor | 18000 | N/A | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking Fountain replacement-Design | 1 | Cedarlane | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking Fountain replacement-DSA Fees | 1 | Cedarlane | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking Fountain replacement-DSA Inspection | 1 | Cedarlane | Drinking Fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 1200 | 0 | 1200 | 100%
Cedarlane-Drinking Fountain replacement-DSA Special Inspection | 1 | Cedarlane | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking Fountain replacement-Environ Consultant | 1 | Cedarlane | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Drinking Fountain replacement-Reprographics | 1 | Cedarlane | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Fire Alarm replacement-Advertisement | 1 | Cedarlane | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Fire Alarm replacement-Contractor | 1 | Cedarlane | Fire Alarm replacement | Contractor | 116400 | 116400 | 106399.99 | 0 | 106399.99 | 100%
Cedarlane-Fire Alarm replacement-Design | 1 | Cedarlane | Fire Alarm replacement | Design | 47500 | 47500 | 4750 | 0 | 4750 | 100%
Cedarlane-Fire Alarm replacement-DSA Fees | 1 | Cedarlane | Fire Alarm replacement | DSA Fees | 1290 | No Proposal Provided | 1290 | 0 | 1290 | 100%
Cedarlane-Fire Alarm replacement-DSA Inspection | 1 | Cedarlane | Fire Alarm replacement | DSA Inspection | 8250 | No Proposal Provided | 8250 | 0 | 8250 | 100%
Cedarlane-Fire Alarm replacement-Environ Consultant | 1 | Cedarlane | Fire Alarm replacement | Environ Consultant | 0 | 0 | 800 | 0 | 800 | 100%
Cedarlane-Fire Alarm replacement-Reprographics | 1 | Cedarlane | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Advertisement | 1 | Cedarlane | Interim Housing | Advertisement | 850 | 0 | 301.66 | 0 | 301.66 | 100%
Cedarlane-Interim Housing-Alarm | 1 | Cedarlane | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-CM/PM Management | 1 | Cedarlane | Interim Housing | CM/PM Management | Incl in 21st | Incl in 21st | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Construction Contingency | 1 | Cedarlane | Interim Housing | Construction Contingency | 82500 | 82500 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Contractor | 1 | Cedarlane | Interim Housing | Contractor | 825000 | 825000 | 898952.41 | 0 | 898952.41 | 100%
Cedarlane-Interim Housing-Design | 1 | Cedarlane | Interim Housing | Design | 100000 | 117105 | 78797.01 | 5733.3 | 73063.71 | 92.72%
Cedarlane-Interim Housing-DSA Fees | 1 | Cedarlane | Interim Housing | DSA Fees | 17000 | No Proposal Provided | 14715.04 | 0 | 14715.04 | 100%
Cedarlane-Interim Housing-DSA Inspection | 1 | Cedarlane | Interim Housing | DSA Inspection | 14875 | 14688 | 14688 | 0 | 14688 | 100%
Cedarlane-Interim Housing-DSA Special Inspection | 1 | Cedarlane | Interim Housing | DSA Special Inspection | 10625 | 16920 | 10317.5 | 0 | 10317.5 | 100%
Cedarlane-Interim Housing-Environ Consultant | 1 | Cedarlane | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-FF & E | 1 | Cedarlane | Interim Housing | FF & E | 0 | 0 | 35280.9 | 0 | 35280.9 | 100%
Cedarlane-Interim Housing-Legal Services | 1 | Cedarlane | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Modular Buildings | 1 | Cedarlane | Interim Housing | Modular Buildings | 239788.74 | 239788.74 | 239788.74 | 0 | 239788.74 | 100%
Cedarlane-Interim Housing-Move Management | 1 | Cedarlane | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Reprographics | 1 | Cedarlane | Interim Housing | Reprographics | 850 | 0 | 0 | 0 | 0 | #DIV/0!
Cedarlane-Interim Housing-Technology | 1 | Cedarlane | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Advertisement | 7 | Del Valle | 21st Century classroom | Advertisement | 1217.69 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Asbestos oversight/survey/abatement | 7 | Del Valle | 21st Century classroom | Asbestos oversight/survey/abatement | 48872.24 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-CM/PM Management | 7 | Del Valle | 21st Century classroom | CM/PM Management | 192978.68 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Construction Contingency | 7 | Del Valle | 21st Century classroom | Construction Contingency | 189763.3 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Contractor | 7 | Del Valle | 21st Century classroom | Contractor | 2024205.12 | 0 | 48872.24 | 0 | 48872.24 | 100%
Del Valle-21st Century classroom-Design | 7 | Del Valle | 21st Century classroom | Design | 232466.68 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-DSA Fees | 7 | Del Valle | 21st Century classroom | DSA Fees | 38744.45 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-DSA Inspection | 7 | Del Valle | 21st Century classroom | DSA Inspection | 33209.53 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-DSA Special Inspection | 7 | Del Valle | 21st Century classroom | DSA Special Inspection | 16604.76 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Environ Consultant | 7 | Del Valle | 21st Century classroom | Environ Consultant | 12176.83 | N/A | 2600 | 0 | 2600 | 100%
Del Valle-21st Century classroom-FF & E | 7 | Del Valle | 21st Century classroom | FF & E | 340000 | No Request for Proposal | 41441.22 | 0 | 41441.22 | 100%
Del Valle-21st Century classroom-Legal Services | 7 | Del Valle | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Move classroom | 7 | Del Valle | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Move Management | 7 | Del Valle | 21st Century classroom | Move Management | 8855.87 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Reprographics | 7 | Del Valle | 21st Century classroom | Reprographics | 1217.69 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-21st Century classroom-Technology | 7 | Del Valle | 21st Century classroom | Technology | 340000 | 0 | 150792.64 | 0 | 150792.64 | 100%
Del Valle-Ceiling replacement-CM/PM Management | 7 | Del Valle | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Ceiling replacement-Contractor | 7 | Del Valle | Ceiling replacement | Contractor | 333183 | 333183 | 333183 | 0 | 333183 | 100%
Del Valle-Drinking Fountain replacement-Advertisement | 7 | Del Valle | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking Fountain replacement-Contractor | 7 | Del Valle | Drinking Fountain replacement | Contractor | 15000 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking Fountain replacement-Design | 7 | Del Valle | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking Fountain replacement-DSA Fees | 7 | Del Valle | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking Fountain replacement-DSA Inspection | 7 | Del Valle | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking Fountain replacement-DSA Special Inspection | 7 | Del Valle | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking Fountain replacement-Environ Consultant | 7 | Del Valle | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Drinking Fountain replacement-Reprographics | 7 | Del Valle | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm replacement-Advertisement | 7 | Del Valle | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm replacement-Contractor | 7 | Del Valle | Fire Alarm replacement | Contractor | 255000 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm replacement-Design | 7 | Del Valle | Fire Alarm replacement | Design | 48500 | 48500 | 36375 | 0 | 36375 | 100%
Del Valle-Fire Alarm replacement-DSA Fees | 7 | Del Valle | Fire Alarm replacement | DSA Fees | 0 | 0 | 870 | 0 | 870 | 100%
Del Valle-Fire Alarm replacement-DSA Inspection | 7 | Del Valle | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm replacement-Environ Consultant | 7 | Del Valle | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Fire Alarm replacement-Reprographics | 7 | Del Valle | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Advertisement | 7 | Del Valle | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Alarm | 7 | Del Valle | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-CM/PM Management | 7 | Del Valle | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Construction Contingency | 7 | Del Valle | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Contractor | 7 | Del Valle | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Design | 7 | Del Valle | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-DSA Fees | 7 | Del Valle | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-DSA Inspection | 7 | Del Valle | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-DSA Special Inspection | 7 | Del Valle | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Environ Consultant | 7 | Del Valle | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-FF & E | 7 | Del Valle | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Legal Services | 7 | Del Valle | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Modular Buildings | 7 | Del Valle | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Move Management | 7 | Del Valle | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Reprographics | 7 | Del Valle | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Del Valle-Interim Housing-Technology | 7 | Del Valle | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Advertisement | 0 | Dibble | 21st Century classroom | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Asbestos oversight/survey/abatement | 0 | Dibble | 21st Century classroom | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-CM/PM Management | 0 | Dibble | 21st Century classroom | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Construction Contingency | 0 | Dibble | 21st Century classroom | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Contractor | 0 | Dibble | 21st Century classroom | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Design | 0 | Dibble | 21st Century classroom | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-DSA Fees | 0 | Dibble | 21st Century classroom | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-DSA Inspection | 0 | Dibble | 21st Century classroom | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-DSA Special Inspection | 0 | Dibble | 21st Century classroom | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Environ Consultant | 0 | Dibble | 21st Century classroom | Environ Consultant | 2700 | No Proposal Provided | 2700 | 0 | 2700 | 100%
Dibble-21st Century classroom-FF & E | 0 | Dibble | 21st Century classroom | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Legal Services | 0 | Dibble | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Move classroom | 0 | Dibble | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Move Management | 0 | Dibble | 21st Century classroom | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Reprographics | 0 | Dibble | 21st Century classroom | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-21st Century classroom-Technology | 0 | Dibble | 21st Century classroom | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Ceiling replacement-CM/PM Management | 0 | Dibble | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Ceiling replacement-Contractor | 0 | Dibble | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking Fountain replacement-Advertisement | 0 | Dibble | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking Fountain replacement-Contractor | 0 | Dibble | Drinking Fountain replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking Fountain replacement-Design | 0 | Dibble | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking Fountain replacement-DSA Fees | 0 | Dibble | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking Fountain replacement-DSA Inspection | 0 | Dibble | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking Fountain replacement-DSA Special Inspection | 0 | Dibble | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking Fountain replacement-Environ Consultant | 0 | Dibble | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Drinking Fountain replacement-Reprographics | 0 | Dibble | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm replacement-Advertisement | 0 | Dibble | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm replacement-Contractor | 0 | Dibble | Fire Alarm replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm replacement-Design | 0 | Dibble | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm replacement-DSA Fees | 0 | Dibble | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm replacement-DSA Inspection | 0 | Dibble | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm replacement-Environ Consultant | 0 | Dibble | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Fire Alarm replacement-Reprographics | 0 | Dibble | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Advertisement | 0 | Dibble | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Alarm | 0 | Dibble | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-CM/PM Management | 0 | Dibble | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Construction Contingency | 0 | Dibble | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Contractor | 0 | Dibble | Interim Housing | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Design | 0 | Dibble | Interim Housing | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-DSA Fees | 0 | Dibble | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-DSA Inspection | 0 | Dibble | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-DSA Special Inspection | 0 | Dibble | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Environ Consultant | 0 | Dibble | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-FF & E | 0 | Dibble | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Legal Services | 0 | Dibble | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Modular Buildings | 0 | Dibble | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Move Management | 0 | Dibble | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Reprographics | 0 | Dibble | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Dibble-Interim Housing-Technology | 0 | Dibble | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-Advertisement | 0 | District Office | 21st Century classroom | Advertisement | 0 | 0 | 1243.25 | 0 | 1243.25 | 100%
District Office-21st Century classroom-Asbestos oversight/survey/abatement | 0 | District Office | 21st Century classroom | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-CM/PM Management | 0 | District Office | 21st Century classroom | CM/PM Management | 450000 | 450000 | 2540210 | 1790290 | 749920 | 29.52%
District Office-21st Century classroom-Construction Contingency | 0 | District Office | 21st Century classroom | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-Contractor | 0 | District Office | 21st Century classroom | Contractor | 392859.44 | No Proposal Provided | 259042.4 | 0 | 259042.4 | 100%
District Office-21st Century classroom-Design | 0 | District Office | 21st Century classroom | Design | 2022.86 | 2022.86 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-DSA Fees | 0 | District Office | 21st Century classroom | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-DSA Inspection | 0 | District Office | 21st Century classroom | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-DSA Special Inspection | 0 | District Office | 21st Century classroom | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-Environ Consultant | 0 | District Office | 21st Century classroom | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-FF & E | 0 | District Office | 21st Century classroom | FF & E | 2678.05 | No Proposal Provided | 85363.6 | 501.51 | 84862.09 | 99.41%
District Office-21st Century classroom-Legal Services | 0 | District Office | 21st Century classroom | Legal Services | 774388.14 | No Proposal Provided | 367648.94 | 262137.79 | 105511.15 | 28.7%
District Office-21st Century classroom-Move classroom | 0 | District Office | 21st Century classroom | Move classroom | 146130.33 | N/A | 0 | 0 | 0 | #DIV/0!
District Office-21st Century classroom-Move Management | 0 | District Office | 21st Century classroom | Move Management | 0 | 0 | 11950 | 11950 | 0 | 0%
District Office-21st Century classroom-Reprographics | 0 | District Office | 21st Century classroom | Reprographics | 7950.01 | No Proposal Provided | 10827.6 | 10598.41 | 229.19 | 2.117%
District Office-21st Century classroom-Technology | 0 | District Office | 21st Century classroom | Technology | 434528.6 | No Proposal Provided | 719627.39 | 0 | 719627.39 | 100%
District Office-Ceiling replacement-CM/PM Management | 0 | District Office | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Ceiling replacement-Contractor | 0 | District Office | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Cost of Issuance-Issuance costs | 0 | District Office | Cost of Issuance | Issuance costs | 1572741.59 | No Proposal Provided | 465831.97 | 0 | 465831.97 | 100%
District Office-Design guidelines-Design | 0 | District Office | Design guidelines | Design | 29500 | 29500 | 29500 | 5500 | 24000 | 81.36%
District Office-Fire Alarm replacement-Advertisement | 0 | District Office | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm replacement-Contractor | 0 | District Office | Fire Alarm replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm replacement-Design | 0 | District Office | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm replacement-DSA Fees | 0 | District Office | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm replacement-DSA Inspection | 0 | District Office | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm replacement-Environ Consultant | 0 | District Office | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Fire Alarm replacement-Reprographics | 0 | District Office | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Advertisement | 0 | District Office | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Alarm | 0 | District Office | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-CM/PM Management | 0 | District Office | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Construction Contingency | 0 | District Office | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Contractor | 0 | District Office | Interim Housing | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Design | 0 | District Office | Interim Housing | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-DSA Fees | 0 | District Office | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-DSA Inspection | 0 | District Office | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-DSA Special Inspection | 0 | District Office | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Environ Consultant | 0 | District Office | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-FF & E | 0 | District Office | Interim Housing | FF & E | 621114.33 | 621114.33 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Legal Services | 0 | District Office | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Modular Buildings | 0 | District Office | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Move Management | 0 | District Office | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Reprographics | 0 | District Office | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
District Office-Interim Housing-Technology | 0 | District Office | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Advertisement | 4 | Fairgrove | 21st Century classroom | Advertisement | 2585.85 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Asbestos oversight/survey/abatement | 4 | Fairgrove | 21st Century classroom | Asbestos oversight/survey/abatement | 129500 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-CM/PM Management | 4 | Fairgrove | 21st Century classroom | CM/PM Management | 412143.23 | N/A | 13010 | 0 | 13010 | 100%
Fairgrove-21st Century classroom-Construction Contingency | 4 | Fairgrove | 21st Century classroom | Construction Contingency | 402977.3 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Contractor | 4 | Fairgrove | 21st Century classroom | Contractor | 4298558.86 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Design | 4 | Fairgrove | 21st Century classroom | Design | 493661.3 | N/A | 407500 | 407500 | 0 | 0%
Fairgrove-21st Century classroom-DSA Fees | 4 | Fairgrove | 21st Century classroom | DSA Fees | 82276.88 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-DSA Inspection | 4 | Fairgrove | 21st Century classroom | DSA Inspection | 70523.04 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-DSA Special Inspection | 4 | Fairgrove | 21st Century classroom | DSA Special Inspection | 35261.52 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Environ Consultant | 4 | Fairgrove | 21st Century classroom | Environ Consultant | 20686.76 | N/A | 2700 | 0 | 2700 | 100%
Fairgrove-21st Century classroom-FF & E | 4 | Fairgrove | 21st Century classroom | FF & E | 740000 | 0 | 41441.21 | 0 | 41441.21 | 100%
Fairgrove-21st Century classroom-Legal Services | 4 | Fairgrove | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Move classroom | 4 | Fairgrove | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Move Management | 4 | Fairgrove | 21st Century classroom | Move Management | 18806.14 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Reprographics | 4 | Fairgrove | 21st Century classroom | Reprographics | 2585.85 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-21st Century classroom-Technology | 4 | Fairgrove | 21st Century classroom | Technology | 740000 | 0 | 449375.25 | 0 | 449375.25 | 100%
Fairgrove-Ceiling replacement-CM/PM Management | 4 | Fairgrove | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Ceiling replacement-Contractor | 4 | Fairgrove | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking Fountain replacement-Advertisement | 4 | Fairgrove | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking Fountain replacement-Contractor | 4 | Fairgrove | Drinking Fountain replacement | Contractor | 30000 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking Fountain replacement-Design | 4 | Fairgrove | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking Fountain replacement-DSA Fees | 4 | Fairgrove | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking Fountain replacement-DSA Inspection | 4 | Fairgrove | Drinking Fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking Fountain replacement-DSA Special Inspection | 4 | Fairgrove | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking Fountain replacement-Environ Consultant | 4 | Fairgrove | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Drinking Fountain replacement-Reprographics | 4 | Fairgrove | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Fire Alarm replacement-Advertisement | 4 | Fairgrove | Fire Alarm replacement | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Fire Alarm replacement-Contractor | 4 | Fairgrove | Fire Alarm replacement | Contractor | 555000 | 378735.79 | 378735.79 | 0 | 378735.79 | 100%
Fairgrove-Fire Alarm replacement-Design | 4 | Fairgrove | Fire Alarm replacement | Design | 12125 | No Proposal Provided | 12125 | 0 | 12125 | 100%
Fairgrove-Fire Alarm replacement-DSA Fees | 4 | Fairgrove | Fire Alarm replacement | DSA Fees | 1230 | No Proposal Provided | 1230 | 0 | 1230 | 100%
Fairgrove-Fire Alarm replacement-DSA Inspection | 4 | Fairgrove | Fire Alarm replacement | DSA Inspection | 14350 | No Proposal Provided | 14350 | 0 | 14350 | 100%
Fairgrove-Fire Alarm replacement-Environ Consultant | 4 | Fairgrove | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Fire Alarm replacement-Reprographics | 4 | Fairgrove | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Advertisement | 4 | Fairgrove | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Alarm | 4 | Fairgrove | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-CM/PM Management | 4 | Fairgrove | Interim Housing | CM/PM Management | 37150 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Construction Contingency | 4 | Fairgrove | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Contractor | 4 | Fairgrove | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Design | 4 | Fairgrove | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-DSA Fees | 4 | Fairgrove | Interim Housing | DSA Fees | 12250 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-DSA Inspection | 4 | Fairgrove | Interim Housing | DSA Inspection | 10500 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-DSA Special Inspection | 4 | Fairgrove | Interim Housing | DSA Special Inspection | 10500 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Environ Consultant | 4 | Fairgrove | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-FF & E | 4 | Fairgrove | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Legal Services | 4 | Fairgrove | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Modular Buildings | 4 | Fairgrove | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Move Management | 4 | Fairgrove | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Reprographics | 4 | Fairgrove | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Fairgrove-Interim Housing-Technology | 4 | Fairgrove | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-21st Century classroom-Advertisement | 2 | Grandview | 21st Century classroom | Advertisement | 2087.79 | N/A | 324.48 | 0 | 324.48 | 100%
Grandview-21st Century classroom-Asbestos oversight/survey/abatement | 2 | Grandview | 21st Century classroom | Asbestos oversight/survey/abatement | 105000 | N/A | 0 | 0 | 0 | #DIV/0!
Grandview-21st Century classroom-CM/PM Management | 2 | Grandview | 21st Century classroom | CM/PM Management | 333089.53 | 194205 | 441955 | 40 | 441915 | 99.99%
Grandview-21st Century classroom-Construction Contingency | 2 | Grandview | 21st Century classroom | Construction Contingency | 325360 | N/A | 0 | 0 | 0 | #DIV/0!
Grandview-21st Century classroom-Contractor | 2 | Grandview | 21st Century classroom | Contractor | 3470615.12 | N/A | 2758770.85 | 338284.81 | 2420486.04 | 87.74%
Grandview-21st Century classroom-Design | 2 | Grandview | 21st Century classroom | Design | 398577.39 | 248631 | 294300 | 33019 | 261281 | 88.78%
Grandview-21st Century classroom-DSA Fees | 2 | Grandview | 21st Century classroom | DSA Fees | 66429.56 | 35235.88 | 35235.88 | 0 | 35235.88 | 100%
Grandview-21st Century classroom-DSA Inspection | 2 | Grandview | 21st Century classroom | DSA Inspection | 56939.63 | N/A | 57290 | 595 | 56695 | 98.96%
Grandview-21st Century classroom-DSA Special Inspection | 2 | Grandview | 21st Century classroom | DSA Special Inspection | 28469.81 | N/A | 2080 | 320 | 1760 | 84.62%
Grandview-21st Century classroom-Environ Consultant | 2 | Grandview | 21st Century classroom | Environ Consultant | 16702.29 | No Proposal Provided | 27750 | 1000 | 26750 | 96.4%
Grandview-21st Century classroom-FF & E | 2 | Grandview | 21st Century classroom | FF & E | 600000 | No Proposal Provided | 460016.88 | 0 | 460016.88 | 100%
Grandview-21st Century classroom-Legal Services | 2 | Grandview | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-21st Century classroom-Move classroom | 2 | Grandview | 21st Century classroom | Move classroom | 0 | 0 | 318.77 | 0 | 318.77 | 100%
Grandview-21st Century classroom-Move Management | 2 | Grandview | 21st Century classroom | Move Management | 15183.9 | N/A | 10756 | 5213.82 | 5542.18 | 51.53%
Grandview-21st Century classroom-Reprographics | 2 | Grandview | 21st Century classroom | Reprographics | 2087.79 | N/A | 2858.07 | 0 | 2858.07 | 100%
Grandview-21st Century classroom-Technology | 2 | Grandview | 21st Century classroom | Technology | 600000 | No Proposal Provided | 348954.41 | 0 | 348954.41 | 100%
Grandview-Ceiling replacement-CM/PM Management | 2 | Grandview | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Ceiling replacement-Contractor | 2 | Grandview | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking Fountain replacement-Advertisement | 2 | Grandview | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking Fountain replacement-Contractor | 2 | Grandview | Drinking Fountain replacement | Contractor | 30000 | N/A | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking Fountain replacement-Design | 2 | Grandview | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking Fountain replacement-DSA Fees | 2 | Grandview | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking Fountain replacement-DSA Inspection | 2 | Grandview | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking Fountain replacement-DSA Special Inspection | 2 | Grandview | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking Fountain replacement-Environ Consultant | 2 | Grandview | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Drinking Fountain replacement-Reprographics | 2 | Grandview | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Fire Alarm replacement-Advertisement | 2 | Grandview | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Fire Alarm replacement-Contractor | 2 | Grandview | Fire Alarm replacement | Contractor | 450000 | 152797 | 146640.11 | 0 | 146640.11 | 100%
Grandview-Fire Alarm replacement-Design | 2 | Grandview | Fire Alarm replacement | Design | 11875 | No Proposal Provided | 11875 | 0 | 11875 | 100%
Grandview-Fire Alarm replacement-DSA Fees | 2 | Grandview | Fire Alarm replacement | DSA Fees | 1230 | No Proposal Provided | 1451.25 | 0 | 1451.25 | 100%
Grandview-Fire Alarm replacement-DSA Inspection | 2 | Grandview | Fire Alarm replacement | DSA Inspection | 0 | 0 | 9375 | 0 | 9375 | 100%
Grandview-Fire Alarm replacement-Environ Consultant | 2 | Grandview | Fire Alarm replacement | Environ Consultant | 0 | 0 | 850 | 0 | 850 | 100%
Grandview-Fire Alarm replacement-Reprographics | 2 | Grandview | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Advertisement | 2 | Grandview | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Alarm | 2 | Grandview | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-CM/PM Management | 2 | Grandview | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Construction Contingency | 2 | Grandview | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Contractor | 2 | Grandview | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Design | 2 | Grandview | Interim Housing | Design | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-DSA Fees | 2 | Grandview | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-DSA Inspection | 2 | Grandview | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-DSA Special Inspection | 2 | Grandview | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Environ Consultant | 2 | Grandview | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-FF & E | 2 | Grandview | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Legal Services | 2 | Grandview | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Modular Buildings | 2 | Grandview | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Move Management | 2 | Grandview | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Reprographics | 2 | Grandview | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grandview-Interim Housing-Technology | 2 | Grandview | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Advertisement | 3 | Grazide | 21st Century classroom | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Asbestos oversight/survey/abatement | 3 | Grazide | 21st Century classroom | Asbestos oversight/survey/abatement | 70000 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-CM/PM Management | 3 | Grazide | 21st Century classroom | CM/PM Management | 0 | 0 | 10410 | 0 | 10410 | 100%
Grazide-21st Century classroom-Construction Contingency | 3 | Grazide | 21st Century classroom | Construction Contingency | 218338 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Contractor | 3 | Grazide | 21st Century classroom | Contractor | 2329011.45 | No Proposal Provided | 37500 | 0 | 37500 | 100%
Grazide-21st Century classroom-Design | 3 | Grazide | 21st Century classroom | Design | 267471.69 | 285705 | 330468 | 211457.55 | 119010.45 | 36.01%
Grazide-21st Century classroom-DSA Fees | 3 | Grazide | 21st Century classroom | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-DSA Inspection | 3 | Grazide | 21st Century classroom | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-DSA Special Inspection | 3 | Grazide | 21st Century classroom | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Environ Consultant | 3 | Grazide | 21st Century classroom | Environ Consultant | 0 | 0 | 2550 | 0 | 2550 | 100%
Grazide-21st Century classroom-FF & E | 3 | Grazide | 21st Century classroom | FF & E | 400000 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Legal Services | 3 | Grazide | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Move classroom | 3 | Grazide | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Move Management | 3 | Grazide | 21st Century classroom | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Reprographics | 3 | Grazide | 21st Century classroom | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-21st Century classroom-Technology | 3 | Grazide | 21st Century classroom | Technology | 400000 | 0 | 187241.76 | 0 | 187241.76 | 100%
Grazide-Ceiling replacement-CM/PM Management | 3 | Grazide | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Ceiling replacement-Contractor | 3 | Grazide | Ceiling replacement | Contractor | 0 | 0 | 281598 | 0 | 281598 | 100%
Grazide-Drinking Fountain replacement-Advertisement | 3 | Grazide | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking Fountain replacement-Contractor | 3 | Grazide | Drinking Fountain replacement | Contractor | 15000 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking Fountain replacement-Design | 3 | Grazide | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking Fountain replacement-DSA Fees | 3 | Grazide | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking Fountain replacement-DSA Inspection | 3 | Grazide | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking Fountain replacement-DSA Special Inspection | 3 | Grazide | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking Fountain replacement-Environ Consultant | 3 | Grazide | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Drinking Fountain replacement-Reprographics | 3 | Grazide | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm replacement-Advertisement | 3 | Grazide | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm replacement-Contractor | 3 | Grazide | Fire Alarm replacement | Contractor | 300000 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm replacement-Design | 3 | Grazide | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm replacement-DSA Fees | 3 | Grazide | Fire Alarm replacement | DSA Fees | 0 | 0 | 960 | 0 | 960 | 100%
Grazide-Fire Alarm replacement-DSA Inspection | 3 | Grazide | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm replacement-Environ Consultant | 3 | Grazide | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Fire Alarm replacement-Reprographics | 3 | Grazide | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Advertisement | 3 | Grazide | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Alarm | 3 | Grazide | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-CM/PM Management | 3 | Grazide | Interim Housing | CM/PM Management | 33600 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Construction Contingency | 3 | Grazide | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Contractor | 3 | Grazide | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Design | 3 | Grazide | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-DSA Fees | 3 | Grazide | Interim Housing | DSA Fees | 15750 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-DSA Inspection | 3 | Grazide | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-DSA Special Inspection | 3 | Grazide | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Environ Consultant | 3 | Grazide | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-FF & E | 3 | Grazide | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Legal Services | 3 | Grazide | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Modular Buildings | 3 | Grazide | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Move Management | 3 | Grazide | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Reprographics | 3 | Grazide | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Grazide-Interim Housing-Technology | 3 | Grazide | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Advertisement | 7 | Kwis | 21st Century classroom | Advertisement | 1344.05 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Asbestos oversight/survey/abatement | 7 | Kwis | 21st Century classroom | Asbestos oversight/survey/abatement | 66500 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-CM/PM Management | 7 | Kwis | 21st Century classroom | CM/PM Management | 213618.67 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Construction Contingency | 7 | Kwis | 21st Century classroom | Construction Contingency | 209456.6 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Contractor | 7 | Kwis | 21st Century classroom | Contractor | 2234273.55 | N/A | 49000 | 0 | 49000 | 100%
Kwis-21st Century classroom-Design | 7 | Kwis | 21st Century classroom | Design | 256591.67 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-DSA Fees | 7 | Kwis | 21st Century classroom | DSA Fees | 42765.28 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-DSA Inspection | 7 | Kwis | 21st Century classroom | DSA Inspection | 36655.95 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-DSA Special Inspection | 7 | Kwis | 21st Century classroom | DSA Special Inspection | 18327.98 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Environ Consultant | 7 | Kwis | 21st Century classroom | Environ Consultant | 10752.41 | No Proposal Provided | 2600 | 0 | 2600 | 100%
Kwis-21st Century classroom-FF & E | 7 | Kwis | 21st Century classroom | FF & E | 380000 | No Proposal Provided | 38238.17 | 0 | 38238.17 | 100%
Kwis-21st Century classroom-Legal Services | 7 | Kwis | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Move classroom | 7 | Kwis | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Move Management | 7 | Kwis | 21st Century classroom | Move Management | 9774.92 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Reprographics | 7 | Kwis | 21st Century classroom | Reprographics | 1344.05 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-21st Century classroom-Technology | 7 | Kwis | 21st Century classroom | Technology | 380000 | No Proposal Provided | 119134.89 | 0 | 119134.89 | 100%
Kwis-Ceiling replacement-CM/PM Management | 7 | Kwis | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Ceiling replacement-Contractor | 7 | Kwis | Ceiling replacement | Contractor | 271028 | 271208 | 271028 | 0 | 271028 | 100%
Kwis-Drinking Fountain replacement-Advertisement | 7 | Kwis | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking Fountain replacement-Contractor | 7 | Kwis | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking Fountain replacement-Design | 7 | Kwis | Drinking Fountain replacement | Design | 0 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking Fountain replacement-DSA Fees | 7 | Kwis | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking Fountain replacement-DSA Inspection | 7 | Kwis | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking Fountain replacement-DSA Special Inspection | 7 | Kwis | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking Fountain replacement-Environ Consultant | 7 | Kwis | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Drinking Fountain replacement-Reprographics | 7 | Kwis | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm replacement-Advertisement | 7 | Kwis | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm replacement-Contractor | 7 | Kwis | Fire Alarm replacement | Contractor | 285000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm replacement-Design | 7 | Kwis | Fire Alarm replacement | Design | 48500 | No Proposal Provided | 36375 | 0 | 36375 | 100%
Kwis-Fire Alarm replacement-DSA Fees | 7 | Kwis | Fire Alarm replacement | DSA Fees | 0 | 0 | 891 | 0 | 891 | 100%
Kwis-Fire Alarm replacement-DSA Inspection | 7 | Kwis | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm replacement-Environ Consultant | 7 | Kwis | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Fire Alarm replacement-Reprographics | 7 | Kwis | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Advertisement | 7 | Kwis | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Alarm | 7 | Kwis | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-CM/PM Management | 7 | Kwis | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Construction Contingency | 7 | Kwis | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Contractor | 7 | Kwis | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Design | 7 | Kwis | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-DSA Fees | 7 | Kwis | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-DSA Inspection | 7 | Kwis | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-DSA Special Inspection | 7 | Kwis | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Environ Consultant | 7 | Kwis | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-FF & E | 7 | Kwis | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Legal Services | 7 | Kwis | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Modular Buildings | 7 | Kwis | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Move Management | 7 | Kwis | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Reprographics | 7 | Kwis | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Kwis-Interim Housing-Technology | 7 | Kwis | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-Advertisement | 5 | La Puente HS | 21st Century classroom | Advertisement | 5093.8 | N/A | 417.06 | 417.06 | 0 | 0%
La Puente HS-21st Century classroom-Asbestos oversight/survey/abatement | 5 | La Puente HS | 21st Century classroom | Asbestos oversight/survey/abatement | 224000 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-CM/PM Management | 5 | La Puente HS | 21st Century classroom | CM/PM Management | 788769.21 | N/A | 171400 | 71550 | 99850 | 58.26%
La Puente HS-21st Century classroom-Construction Contingency | 5 | La Puente HS | 21st Century classroom | Construction Contingency | 793815.6 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-Contractor | 5 | La Puente HS | 21st Century classroom | Contractor | 8467631.01 | N/A | 2444123 | 2444123 | 0 | 0%
La Puente HS-21st Century classroom-Design | 5 | La Puente HS | 21st Century classroom | Design | 972451.89 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-DSA Fees | 5 | La Puente HS | 21st Century classroom | DSA Fees | 162075.32 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-DSA Inspection | 5 | La Puente HS | 21st Century classroom | DSA Inspection | 138921.7 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-DSA Special Inspection | 5 | La Puente HS | 21st Century classroom | DSA Special Inspection | 69460.85 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-Environ Consultant | 5 | La Puente HS | 21st Century classroom | Environ Consultant | 40750.37 | No Proposal Provided | 39400 | 32500 | 6900 | 17.51%
La Puente HS-21st Century classroom-FF & E | 5 | La Puente HS | 21st Century classroom | FF & E | 1280000 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-Legal Services | 5 | La Puente HS | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-Move classroom | 5 | La Puente HS | 21st Century classroom | Move classroom | 0 | 0 | 1420.32 | 1420.32 | 0 | 0%
La Puente HS-21st Century classroom-Move Management | 5 | La Puente HS | 21st Century classroom | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-21st Century classroom-Reprographics | 5 | La Puente HS | 21st Century classroom | Reprographics | 5093.8 | N/A | 126.62 | 0 | 126.62 | 100%
La Puente HS-21st Century classroom-Technology | 5 | La Puente HS | 21st Century classroom | Technology | 1280000 | N/A | 505300.94 | 0 | 505300.94 | 100%
La Puente HS-Ceiling replacement-CM/PM Management | 5 | La Puente HS | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Ceiling replacement-Contractor | 5 | La Puente HS | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking Fountain replacement-Advertisement | 5 | La Puente HS | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking Fountain replacement-Contractor | 5 | La Puente HS | Drinking Fountain replacement | Contractor | 60000 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking Fountain replacement-Design | 5 | La Puente HS | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking Fountain replacement-DSA Fees | 5 | La Puente HS | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking Fountain replacement-DSA Inspection | 5 | La Puente HS | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking Fountain replacement-DSA Special Inspection | 5 | La Puente HS | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking Fountain replacement-Environ Consultant | 5 | La Puente HS | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Drinking Fountain replacement-Reprographics | 5 | La Puente HS | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm replacement-Advertisement | 5 | La Puente HS | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm replacement-Contractor | 5 | La Puente HS | Fire Alarm replacement | Contractor | 1152000 | No Proposal Provided | 2717.95 | 0 | 2717.95 | 100%
La Puente HS-Fire Alarm replacement-Design | 5 | La Puente HS | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm replacement-DSA Fees | 5 | La Puente HS | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm replacement-DSA Inspection | 5 | La Puente HS | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm replacement-Environ Consultant | 5 | La Puente HS | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Fire Alarm replacement-Reprographics | 5 | La Puente HS | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Advertisement | 5 | La Puente HS | Interim Housing | Advertisement | 412.5 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Alarm | 5 | La Puente HS | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-CM/PM Management | 5 | La Puente HS | Interim Housing | CM/PM Management | 54275 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Construction Contingency | 5 | La Puente HS | Interim Housing | Construction Contingency | 82500 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Contractor | 5 | La Puente HS | Interim Housing | Contractor | 825000 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Design | 5 | La Puente HS | Interim Housing | Design | 82500 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-DSA Fees | 5 | La Puente HS | Interim Housing | DSA Fees | 14437.5 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-DSA Inspection | 5 | La Puente HS | Interim Housing | DSA Inspection | 15750 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-DSA Special Inspection | 5 | La Puente HS | Interim Housing | DSA Special Inspection | 15750 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Environ Consultant | 5 | La Puente HS | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-FF & E | 5 | La Puente HS | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Legal Services | 5 | La Puente HS | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Modular Buildings | 5 | La Puente HS | Interim Housing | Modular Buildings | 225000 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Move Management | 5 | La Puente HS | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Reprographics | 5 | La Puente HS | Interim Housing | Reprographics | 412.5 | N/A | 0 | 0 | 0 | #DIV/0!
La Puente HS-Interim Housing-Technology | 5 | La Puente HS | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Advertisement | 6 | Lassalette | 21st Century classroom | Advertisement | 2881.28 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Asbestos oversight/survey/abatement | 6 | Lassalette | 21st Century classroom | Asbestos oversight/survey/abatement | 94500 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-CM/PM Management | 6 | Lassalette | 21st Century classroom | CM/PM Management | 304893.42 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Construction Contingency | 6 | Lassalette | 21st Century classroom | Construction Contingency | 299345.3 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Contractor | 6 | Lassalette | 21st Century classroom | Contractor | 3193116.32 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Design | 6 | Lassalette | 21st Century classroom | Design | 366708.47 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-DSA Fees | 6 | Lassalette | 21st Century classroom | DSA Fees | 61118.08 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-DSA Inspection | 6 | Lassalette | 21st Century classroom | DSA Inspection | 52386.92 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-DSA Special Inspection | 6 | Lassalette | 21st Century classroom | DSA Special Inspection | 26193.46 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Environ Consultant | 6 | Lassalette | 21st Century classroom | Environ Consultant | 15366.83 | N/A | 2800 | 0 | 2800 | 100%
Lassalette-21st Century classroom-FF & E | 6 | Lassalette | 21st Century classroom | FF & E | 540000 | No Proposal Provided | 20720.61 | 0 | 20720.61 | 100%
Lassalette-21st Century classroom-Legal Services | 6 | Lassalette | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Move classroom | 6 | Lassalette | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Move Management | 6 | Lassalette | 21st Century classroom | Move Management | 13969.85 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Reprographics | 6 | Lassalette | 21st Century classroom | Reprographics | 2881.28 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-21st Century classroom-Technology | 6 | Lassalette | 21st Century classroom | Technology | 540000 | No Proposal Provided | 243109.5 | 0 | 243109.5 | 100%
Lassalette-Ceiling replacement-CM/PM Management | 6 | Lassalette | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Ceiling replacement-Contractor | 6 | Lassalette | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking Fountain replacement-Advertisement | 6 | Lassalette | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking Fountain replacement-Contractor | 6 | Lassalette | Drinking Fountain replacement | Contractor | 30000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking Fountain replacement-Design | 6 | Lassalette | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking Fountain replacement-DSA Fees | 6 | Lassalette | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking Fountain replacement-DSA Inspection | 6 | Lassalette | Drinking Fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking Fountain replacement-DSA Special Inspection | 6 | Lassalette | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking Fountain replacement-Environ Consultant | 6 | Lassalette | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Drinking Fountain replacement-Reprographics | 6 | Lassalette | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm replacement-Advertisement | 6 | Lassalette | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm replacement-Contractor | 6 | Lassalette | Fire Alarm replacement | Contractor | 405000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm replacement-Design | 6 | Lassalette | Fire Alarm replacement | Design | 12375 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm replacement-DSA Fees | 6 | Lassalette | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm replacement-DSA Inspection | 6 | Lassalette | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm replacement-Environ Consultant | 6 | Lassalette | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Fire Alarm replacement-Reprographics | 6 | Lassalette | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Advertisement | 6 | Lassalette | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Alarm | 6 | Lassalette | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-CM/PM Management | 6 | Lassalette | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Construction Contingency | 6 | Lassalette | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Contractor | 6 | Lassalette | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Design | 6 | Lassalette | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-DSA Fees | 6 | Lassalette | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-DSA Inspection | 6 | Lassalette | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-DSA Special Inspection | 6 | Lassalette | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Environ Consultant | 6 | Lassalette | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-FF & E | 6 | Lassalette | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Legal Services | 6 | Lassalette | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Modular Buildings | 6 | Lassalette | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Move Management | 6 | Lassalette | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Reprographics | 6 | Lassalette | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Lassalette-Interim Housing-Technology | 6 | Lassalette | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century classroom-Advertisement | 2 | Los Altos ES | 21st Century classroom | Advertisement | 1328.33 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century classroom-Asbestos oversight/survey/abatement | 2 | Los Altos ES | 21st Century classroom | Asbestos oversight/survey/abatement | 66500 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century classroom-CM/PM Management | 2 | Los Altos ES | 21st Century classroom | CM/PM Management | 211697.5 | 145452 | 145426.25 | 0 | 145426.25 | 100%
Los Altos ES-21st Century classroom-Construction Contingency | 2 | Los Altos ES | 21st Century classroom | Construction Contingency | 207006.2 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century classroom-Contractor | 2 | Los Altos ES | 21st Century classroom | Contractor | 2208135.14 | 2288481 | 2371195.38 | 0 | 2371195.38 | 100%
Los Altos ES-21st Century classroom-Design | 2 | Los Altos ES | 21st Century classroom | Design | 0 | 0 | 105694.72 | 0 | 105694.72 | 100%
Los Altos ES-21st Century classroom-DSA Fees | 2 | Los Altos ES | 21st Century classroom | DSA Fees | 42264.97 | No Proposal Provided | 30129.11 | 0 | 30129.11 | 100%
Los Altos ES-21st Century classroom-DSA Inspection | 2 | Los Altos ES | 21st Century classroom | DSA Inspection | 36227.12 | No Proposal Provided | 34720 | 0 | 34720 | 100%
Los Altos ES-21st Century classroom-DSA Special Inspection | 2 | Los Altos ES | 21st Century classroom | DSA Special Inspection | 18113.56 | No Proposal Provided | 14916.5 | 0 | 14916.5 | 100%
Los Altos ES-21st Century classroom-Environ Consultant | 2 | Los Altos ES | 21st Century classroom | Environ Consultant | 10626.62 | 13900 | 10575 | 0 | 10575 | 100%
Los Altos ES-21st Century classroom-FF & E | 2 | Los Altos ES | 21st Century classroom | FF & E | 380000 | 249195.59 | 405886.01 | 0 | 405886.01 | 100%
Los Altos ES-21st Century classroom-Legal Services | 2 | Los Altos ES | 21st Century classroom | Legal Services | 0 | 0 | 22.5 | 0 | 22.5 | 100%
Los Altos ES-21st Century classroom-Move classroom | 2 | Los Altos ES | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-21st Century classroom-Move Management | 2 | Los Altos ES | 21st Century classroom | Move Management | 9660.57 | 0 | 12975.74 | 0 | 12975.74 | 100%
Los Altos ES-21st Century classroom-Reprographics | 2 | Los Altos ES | 21st Century classroom | Reprographics | 1328.33 | 0 | 728.6 | 0 | 728.6 | 100%
Los Altos ES-21st Century classroom-Technology | 2 | Los Altos ES | 21st Century classroom | Technology | 380000 | 43694.21 | 300395.25 | 0 | 300395.25 | 100%
Los Altos ES-Ceiling replacement-CM/PM Management | 2 | Los Altos ES | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Ceiling replacement-Contractor | 2 | Los Altos ES | Ceiling replacement | Contractor | 232310 | 232310 | 232310 | 0 | 232310 | 100%
Los Altos ES-Drinking Fountain replacement-Advertisement | 2 | Los Altos ES | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking Fountain replacement-Contractor | 2 | Los Altos ES | Drinking Fountain replacement | Contractor | 15000 | Incl in GC | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking Fountain replacement-Design | 2 | Los Altos ES | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking Fountain replacement-DSA Fees | 2 | Los Altos ES | Drinking Fountain replacement | DSA Fees | 1050 | No Proposal Provided | 1050 | 0 | 1050 | 100%
Los Altos ES-Drinking Fountain replacement-DSA Inspection | 2 | Los Altos ES | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking Fountain replacement-DSA Special Inspection | 2 | Los Altos ES | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking Fountain replacement-Environ Consultant | 2 | Los Altos ES | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Drinking Fountain replacement-Reprographics | 2 | Los Altos ES | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Fire Alarm replacement-Advertisement | 2 | Los Altos ES | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Fire Alarm replacement-Contractor | 2 | Los Altos ES | Fire Alarm replacement | Contractor | 285000 | 91250 | 107228.53 | 0 | 107228.53 | 100%
Los Altos ES-Fire Alarm replacement-Design | 2 | Los Altos ES | Fire Alarm replacement | Design | 0 | 0 | 11875 | 0 | 11875 | 100%
Los Altos ES-Fire Alarm replacement-DSA Fees | 2 | Los Altos ES | Fire Alarm replacement | DSA Fees | 945 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Fire Alarm replacement-DSA Inspection | 2 | Los Altos ES | Fire Alarm replacement | DSA Inspection | 12250 | No Proposal Provided | 12250 | 0 | 12250 | 100%
Los Altos ES-Fire Alarm replacement-Environ Consultant | 2 | Los Altos ES | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Fire Alarm replacement-Reprographics | 2 | Los Altos ES | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Advertisement | 2 | Los Altos ES | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Alarm | 2 | Los Altos ES | Interim Housing | Alarm | 3498 | No Proposal Provided | 874.5 | 0 | 874.5 | 100%
Los Altos ES-Interim Housing-CM/PM Management | 2 | Los Altos ES | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Construction Contingency | 2 | Los Altos ES | Interim Housing | Construction Contingency | 59526 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Contractor | 2 | Los Altos ES | Interim Housing | Contractor | 254951.88 | 254951.88 | 254951.88 | 0 | 254951.88 | 100%
Los Altos ES-Interim Housing-Design | 2 | Los Altos ES | Interim Housing | Design | 57890.18 | 57890.18 | 40706.18 | 0 | 40706.18 | 100%
Los Altos ES-Interim Housing-DSA Fees | 2 | Los Altos ES | Interim Housing | DSA Fees | 6169.04 | No Proposal Provided | 6169.04 | 0 | 6169.04 | 100%
Los Altos ES-Interim Housing-DSA Inspection | 2 | Los Altos ES | Interim Housing | DSA Inspection | 19369.04 | No Proposal Provided | 13200 | 0 | 13200 | 100%
Los Altos ES-Interim Housing-DSA Special Inspection | 2 | Los Altos ES | Interim Housing | DSA Special Inspection | 14530 | No Proposal Provided | 5280.5 | 0 | 5280.5 | 100%
Los Altos ES-Interim Housing-Environ Consultant | 2 | Los Altos ES | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-FF & E | 2 | Los Altos ES | Interim Housing | FF & E | 1894.88 | 0 | 10486.26 | 0 | 10486.26 | 100%
Los Altos ES-Interim Housing-Legal Services | 2 | Los Altos ES | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Modular Buildings | 2 | Los Altos ES | Interim Housing | Modular Buildings | 236959.74 | 236959.74 | 236959.74 | 0 | 236959.74 | 100%
Los Altos ES-Interim Housing-Move Management | 2 | Los Altos ES | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Reprographics | 2 | Los Altos ES | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos ES-Interim Housing-Technology | 2 | Los Altos ES | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-Advertisement | 5 | Los Altos HS | 21st Century classroom | Advertisement | 5394.01 | N/A | 292.31 | 292.31 | 0 | 0%
Los Altos HS-21st Century classroom-Asbestos oversight/survey/abatement | 5 | Los Altos HS | 21st Century classroom | Asbestos oversight/survey/abatement | 224000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-CM/PM Management | 5 | Los Altos HS | 21st Century classroom | CM/PM Management | 835850.17 | N/A | 171400 | 154950 | 16450 | 9.597%
Los Altos HS-21st Century classroom-Construction Contingency | 5 | Los Altos HS | 21st Century classroom | Construction Contingency | 840601.2 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-Contractor | 5 | Los Altos HS | 21st Century classroom | Contractor | 8966693 | N/A | 19116.72 | 0 | 19116.72 | 100%
Los Altos HS-21st Century classroom-Design | 5 | Los Altos HS | 21st Century classroom | Design | 1029765.89 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-DSA Fees | 5 | Los Altos HS | 21st Century classroom | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-DSA Inspection | 5 | Los Altos HS | 21st Century classroom | DSA Inspection | 147109.41 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-DSA Special Inspection | 5 | Los Altos HS | 21st Century classroom | DSA Special Inspection | 73554.71 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-Environ Consultant | 5 | Los Altos HS | 21st Century classroom | Environ Consultant | 43152.09 | No Proposal Provided | 4350 | 0 | 4350 | 100%
Los Altos HS-21st Century classroom-FF & E | 5 | Los Altos HS | 21st Century classroom | FF & E | 1360000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-Legal Services | 5 | Los Altos HS | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-Move classroom | 5 | Los Altos HS | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-Move Management | 5 | Los Altos HS | 21st Century classroom | Move Management | 39229.18 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-21st Century classroom-Reprographics | 5 | Los Altos HS | 21st Century classroom | Reprographics | 5394.01 | N/A | 349.34 | 0 | 349.34 | 100%
Los Altos HS-21st Century classroom-Technology | 5 | Los Altos HS | 21st Century classroom | Technology | 1360000 | N/A | 782574.99 | 0 | 782574.99 | 100%
Los Altos HS-Ceiling replacement-CM/PM Management | 5 | Los Altos HS | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Ceiling replacement-Contractor | 5 | Los Altos HS | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking Fountain replacement-Advertisement | 5 | Los Altos HS | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking Fountain replacement-Contractor | 5 | Los Altos HS | Drinking Fountain replacement | Contractor | 60000 | 0 | 6600 | 0 | 6600 | 100%
Los Altos HS-Drinking Fountain replacement-Design | 5 | Los Altos HS | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking Fountain replacement-DSA Fees | 5 | Los Altos HS | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking Fountain replacement-DSA Inspection | 5 | Los Altos HS | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking Fountain replacement-DSA Special Inspection | 5 | Los Altos HS | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking Fountain replacement-Environ Consultant | 5 | Los Altos HS | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Drinking Fountain replacement-Reprographics | 5 | Los Altos HS | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm replacement-Advertisement | 5 | Los Altos HS | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm replacement-Contractor | 5 | Los Altos HS | Fire Alarm replacement | Contractor | 1224000 | 1144366.69 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm replacement-Design | 5 | Los Altos HS | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm replacement-DSA Fees | 5 | Los Altos HS | Fire Alarm replacement | DSA Fees | 0 | 0 | 5500 | 0 | 5500 | 100%
Los Altos HS-Fire Alarm replacement-DSA Inspection | 5 | Los Altos HS | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm replacement-Environ Consultant | 5 | Los Altos HS | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Fire Alarm replacement-Reprographics | 5 | Los Altos HS | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Advertisement | 5 | Los Altos HS | Interim Housing | Advertisement | 412.5 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Alarm | 5 | Los Altos HS | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-CM/PM Management | 5 | Los Altos HS | Interim Housing | CM/PM Management | 55275 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Construction Contingency | 5 | Los Altos HS | Interim Housing | Construction Contingency | 82500 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Contractor | 5 | Los Altos HS | Interim Housing | Contractor | 825000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Design | 5 | Los Altos HS | Interim Housing | Design | 82500 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-DSA Fees | 5 | Los Altos HS | Interim Housing | DSA Fees | 14437 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-DSA Inspection | 5 | Los Altos HS | Interim Housing | DSA Inspection | 15750 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-DSA Special Inspection | 5 | Los Altos HS | Interim Housing | DSA Special Inspection | 15750 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Environ Consultant | 5 | Los Altos HS | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-FF & E | 5 | Los Altos HS | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Legal Services | 5 | Los Altos HS | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Modular Buildings | 5 | Los Altos HS | Interim Housing | Modular Buildings | 225000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Move Management | 5 | Los Altos HS | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Reprographics | 5 | Los Altos HS | Interim Housing | Reprographics | 412.5 | N/A | 0 | 0 | 0 | #DIV/0!
Los Altos HS-Interim Housing-Technology | 5 | Los Altos HS | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-Advertisement | 4 | Los Molinos | 21st Century classroom | Advertisement | 1282.02 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-Asbestos oversight/survey/abatement | 4 | Los Molinos | 21st Century classroom | Asbestos oversight/survey/abatement | 80500 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-CM/PM Management | 4 | Los Molinos | 21st Century classroom | CM/PM Management | 260826.25 | N/A | 10890 | 0 | 10890 | 100%
Los Molinos-21st Century classroom-Construction Contingency | 4 | Los Molinos | 21st Century classroom | Construction Contingency | 256403.7 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-Contractor | 4 | Los Molinos | 21st Century classroom | Contractor | 2735058.27 | No Proposal Provided | 37500 | 0 | 37500 | 100%
Los Molinos-21st Century classroom-Design | 4 | Los Molinos | 21st Century classroom | Design | 314103.51 | 281510 | 358934 | 234636.97 | 124297.03 | 34.63%
Los Molinos-21st Century classroom-DSA Fees | 4 | Los Molinos | 21st Century classroom | DSA Fees | 52350.58 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-DSA Inspection | 4 | Los Molinos | 21st Century classroom | DSA Inspection | 44871.93 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-DSA Special Inspection | 4 | Los Molinos | 21st Century classroom | DSA Special Inspection | 22435.96 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-Environ Consultant | 4 | Los Molinos | 21st Century classroom | Environ Consultant | 13162.43 | No Proposal Provided | 2600 | 0 | 2600 | 100%
Los Molinos-21st Century classroom-FF & E | 4 | Los Molinos | 21st Century classroom | FF & E | 460000 | 0 | 21169.42 | 0 | 21169.42 | 100%
Los Molinos-21st Century classroom-Legal Services | 4 | Los Molinos | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-Move classroom | 4 | Los Molinos | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-Move Management | 4 | Los Molinos | 21st Century classroom | Move Management | 11965.85 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-Reprographics | 4 | Los Molinos | 21st Century classroom | Reprographics | 1282.02 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-21st Century classroom-Technology | 4 | Los Molinos | 21st Century classroom | Technology | 460000 | N/A | 149425.45 | 0 | 149425.45 | 100%
Los Molinos-Ceiling replacement-CM/PM Management | 4 | Los Molinos | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Ceiling replacement-Contractor | 4 | Los Molinos | Ceiling replacement | Contractor | 359035 | 359035 | 359035 | 0 | 359035 | 100%
Los Molinos-Drinking Fountain replacement-Advertisement | 4 | Los Molinos | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking Fountain replacement-Contractor | 4 | Los Molinos | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking Fountain replacement-Design | 4 | Los Molinos | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking Fountain replacement-DSA Fees | 4 | Los Molinos | Drinking Fountain replacement | DSA Fees | 0 | 0 | 1050 | 0 | 1050 | 100%
Los Molinos-Drinking Fountain replacement-DSA Inspection | 4 | Los Molinos | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking Fountain replacement-DSA Special Inspection | 4 | Los Molinos | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking Fountain replacement-Environ Consultant | 4 | Los Molinos | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Drinking Fountain replacement-Reprographics | 4 | Los Molinos | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Fire Alarm replacement-Advertisement | 4 | Los Molinos | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Fire Alarm replacement-Contractor | 4 | Los Molinos | Fire Alarm replacement | Contractor | 345000 | 188914.76 | 188914.76 | 0 | 188914.76 | 100%
Los Molinos-Fire Alarm replacement-Design | 4 | Los Molinos | Fire Alarm replacement | Design | 12125 | No Proposal Provided | 12125 | 0 | 12125 | 100%
Los Molinos-Fire Alarm replacement-DSA Fees | 4 | Los Molinos | Fire Alarm replacement | DSA Fees | 870 | No Proposal Provided | 870 | 0 | 870 | 100%
Los Molinos-Fire Alarm replacement-DSA Inspection | 4 | Los Molinos | Fire Alarm replacement | DSA Inspection | 0 | No Proposal Provided | 14350 | 0 | 14350 | 100%
Los Molinos-Fire Alarm replacement-Environ Consultant | 4 | Los Molinos | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Fire Alarm replacement-Reprographics | 4 | Los Molinos | Fire Alarm replacement | Reprographics | 0 | No Proposal Provided | 422.21 | 0 | 422.21 | 100%
Los Molinos-Interim Housing-Advertisement | 4 | Los Molinos | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Alarm | 4 | Los Molinos | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-CM/PM Management | 4 | Los Molinos | Interim Housing | CM/PM Management | 37350 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Construction Contingency | 4 | Los Molinos | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Contractor | 4 | Los Molinos | Interim Housing | Contractor | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Design | 4 | Los Molinos | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-DSA Fees | 4 | Los Molinos | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-DSA Inspection | 4 | Los Molinos | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-DSA Special Inspection | 4 | Los Molinos | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Environ Consultant | 4 | Los Molinos | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-FF & E | 4 | Los Molinos | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Legal Services | 4 | Los Molinos | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Modular Buildings | 4 | Los Molinos | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Move Management | 4 | Los Molinos | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Reprographics | 4 | Los Molinos | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Los Molinos-Interim Housing-Technology | 4 | Los Molinos | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Advertisement | 9 | Los Robles | 21st Century classroom | Advertisement | 1222.31 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Asbestos oversight/survey/abatement | 9 | Los Robles | 21st Century classroom | Asbestos oversight/survey/abatement | 59500 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-CM/PM Management | 9 | Los Robles | 21st Century classroom | CM/PM Management | 193544.35 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Construction Contingency | 9 | Los Robles | 21st Century classroom | Construction Contingency | 190484 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Contractor | 9 | Los Robles | 21st Century classroom | Contractor | 2031901.36 | N/A | 40000 | 0 | 40000 | 100%
Los Robles-21st Century classroom-Design | 9 | Los Robles | 21st Century classroom | Design | 233350.55 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-DSA Fees | 9 | Los Robles | 21st Century classroom | DSA Fees | 38891.76 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-DSA Inspection | 9 | Los Robles | 21st Century classroom | DSA Inspection | 33335.79 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-DSA Special Inspection | 9 | Los Robles | 21st Century classroom | DSA Special Inspection | 16667.9 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Environ Consultant | 9 | Los Robles | 21st Century classroom | Environ Consultant | 9778.5 | No Proposal Provided | 2800 | 0 | 2800 | 100%
Los Robles-21st Century classroom-FF & E | 9 | Los Robles | 21st Century classroom | FF & E | 340000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Legal Services | 9 | Los Robles | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Move classroom | 9 | Los Robles | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Move Management | 9 | Los Robles | 21st Century classroom | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Reprographics | 9 | Los Robles | 21st Century classroom | Reprographics | 1222.31 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-21st Century classroom-Technology | 9 | Los Robles | 21st Century classroom | Technology | 340000 | N/A | 76568.08 | 0 | 76568.08 | 100%
Los Robles-Ceiling replacement-CM/PM Management | 9 | Los Robles | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Ceiling replacement-Contractor | 9 | Los Robles | Ceiling replacement | Contractor | 219377 | 219377 | 219377 | 0 | 219377 | 100%
Los Robles-Drinking Fountain replacement-Advertisement | 9 | Los Robles | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking Fountain replacement-Contractor | 9 | Los Robles | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking Fountain replacement-Design | 9 | Los Robles | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking Fountain replacement-DSA Fees | 9 | Los Robles | Drinking Fountain replacement | DSA Fees | 1050 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking Fountain replacement-DSA Inspection | 9 | Los Robles | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking Fountain replacement-DSA Special Inspection | 9 | Los Robles | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking Fountain replacement-Environ Consultant | 9 | Los Robles | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Drinking Fountain replacement-Reprographics | 9 | Los Robles | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm replacement-Advertisement | 9 | Los Robles | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm replacement-Contractor | 9 | Los Robles | Fire Alarm replacement | Contractor | 255000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm replacement-Design | 9 | Los Robles | Fire Alarm replacement | Design | 48500 | No Proposal Provided | 36375 | 0 | 36375 | 100%
Los Robles-Fire Alarm replacement-DSA Fees | 9 | Los Robles | Fire Alarm replacement | DSA Fees | 0 | 0 | 900 | 0 | 900 | 100%
Los Robles-Fire Alarm replacement-DSA Inspection | 9 | Los Robles | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm replacement-Environ Consultant | 9 | Los Robles | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Fire Alarm replacement-Reprographics | 9 | Los Robles | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Advertisement | 9 | Los Robles | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Alarm | 9 | Los Robles | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-CM/PM Management | 9 | Los Robles | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Construction Contingency | 9 | Los Robles | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Contractor | 9 | Los Robles | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Design | 9 | Los Robles | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-DSA Fees | 9 | Los Robles | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-DSA Inspection | 9 | Los Robles | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-DSA Special Inspection | 9 | Los Robles | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Environ Consultant | 9 | Los Robles | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-FF & E | 9 | Los Robles | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Legal Services | 9 | Los Robles | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Modular Buildings | 9 | Los Robles | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Move Management | 9 | Los Robles | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Reprographics | 9 | Los Robles | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Los Robles-Interim Housing-Technology | 9 | Los Robles | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century classroom-Advertisement | 1 | Mesa Robles | 21st Century classroom | Advertisement | 2276.66 | 0 | 301.67 | 0 | 301.67 | 100%
Mesa Robles-21st Century classroom-Asbestos oversight/survey/abatement | 1 | Mesa Robles | 21st Century classroom | Asbestos oversight/survey/abatement | 108000 | 12480 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century classroom-CM/PM Management | 1 | Mesa Robles | 21st Century classroom | CM/PM Management | 371765.88 | 265179 | 265093.75 | 0 | 265093.75 | 100%
Mesa Robles-21st Century classroom-Construction Contingency | 1 | Mesa Robles | 21st Century classroom | Construction Contingency | 354793.28 | 309700 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century classroom-Contractor | 1 | Mesa Robles | 21st Century classroom | Contractor | 3784579.12 | 3097000 | 3239909.02 | 0 | 3239909.02 | 100%
Mesa Robles-21st Century classroom-Design | 1 | Mesa Robles | 21st Century classroom | Design | 434634.19 | 269527.44 | 263527.44 | 4619.56 | 258907.88 | 98.25%
Mesa Robles-21st Century classroom-DSA Fees | 1 | Mesa Robles | 21st Century classroom | DSA Fees | 72439.03 | 0 | 40084.87 | 0 | 40084.87 | 100%
Mesa Robles-21st Century classroom-DSA Inspection | 1 | Mesa Robles | 21st Century classroom | DSA Inspection | 62090.6 | 93600 | 57744 | 0 | 57744 | 100%
Mesa Robles-21st Century classroom-DSA Special Inspection | 1 | Mesa Robles | 21st Century classroom | DSA Special Inspection | 31045 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century classroom-Environ Consultant | 1 | Mesa Robles | 21st Century classroom | Environ Consultant | 0 | 0 | 21990 | 0 | 21990 | 100%
Mesa Robles-21st Century classroom-FF & E | 1 | Mesa Robles | 21st Century classroom | FF & E | 720000 | 656535.85 | 820765.62 | 0 | 820765.62 | 100%
Mesa Robles-21st Century classroom-Legal Services | 1 | Mesa Robles | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-21st Century classroom-Move classroom | 1 | Mesa Robles | 21st Century classroom | Move classroom | 0 | 0 | 1852.8 | 0 | 1852.8 | 100%
Mesa Robles-21st Century classroom-Move Management | 1 | Mesa Robles | 21st Century classroom | Move Management | 16557.49 | 0 | 11847.1 | 0 | 11847.1 | 100%
Mesa Robles-21st Century classroom-Reprographics | 1 | Mesa Robles | 21st Century classroom | Reprographics | 2276.66 | 0 | 216.14 | 0 | 216.14 | 100%
Mesa Robles-21st Century classroom-Technology | 1 | Mesa Robles | 21st Century classroom | Technology | 720000 | 83019.38 | 758904.29 | 0 | 758904.29 | 100%
Mesa Robles-Ceiling replacement-CM/PM Management | 1 | Mesa Robles | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Ceiling replacement-Contractor | 1 | Mesa Robles | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking Fountain replacement-Advertisement | 1 | Mesa Robles | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking Fountain replacement-Contractor | 1 | Mesa Robles | Drinking Fountain replacement | Contractor | 24000 | 16000 | 11000 | 0 | 11000 | 100%
Mesa Robles-Drinking Fountain replacement-Design | 1 | Mesa Robles | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking Fountain replacement-DSA Fees | 1 | Mesa Robles | Drinking Fountain replacement | DSA Fees | 0 | 0 | 1050 | 0 | 1050 | 100%
Mesa Robles-Drinking Fountain replacement-DSA Inspection | 1 | Mesa Robles | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking Fountain replacement-DSA Special Inspection | 1 | Mesa Robles | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking Fountain replacement-Environ Consultant | 1 | Mesa Robles | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Drinking Fountain replacement-Reprographics | 1 | Mesa Robles | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Fire Alarm replacement-Advertisement | 1 | Mesa Robles | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Fire Alarm replacement-Contractor | 1 | Mesa Robles | Fire Alarm replacement | Contractor | 540000 | 408743.31 | 146793.61 | 0 | 146793.61 | 100%
Mesa Robles-Fire Alarm replacement-Design | 1 | Mesa Robles | Fire Alarm replacement | Design | 0 | 55800 | 11875 | 0 | 11875 | 100%
Mesa Robles-Fire Alarm replacement-DSA Fees | 1 | Mesa Robles | Fire Alarm replacement | DSA Fees | 0 | 0 | 1720 | 0 | 1720 | 100%
Mesa Robles-Fire Alarm replacement-DSA Inspection | 1 | Mesa Robles | Fire Alarm replacement | DSA Inspection | 8250 | No Proposal Provided | 8250 | 0 | 8250 | 100%
Mesa Robles-Fire Alarm replacement-Environ Consultant | 1 | Mesa Robles | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Fire Alarm replacement-Reprographics | 1 | Mesa Robles | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Advertisement | 1 | Mesa Robles | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Alarm | 1 | Mesa Robles | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-CM/PM Management | 1 | Mesa Robles | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Construction Contingency | 1 | Mesa Robles | Interim Housing | Construction Contingency | 87894 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Contractor | 1 | Mesa Robles | Interim Housing | Contractor | 879842.2 | 879842.2 | 1232317.04 | 0 | 1232317.04 | 100%
Mesa Robles-Interim Housing-Design | 1 | Mesa Robles | Interim Housing | Design | 93467.93 | 93467.93 | 93467.93 | 0 | 93467.93 | 100%
Mesa Robles-Interim Housing-DSA Fees | 1 | Mesa Robles | Interim Housing | DSA Fees | 7425 | 7425 | 7425 | 0 | 7425 | 100%
Mesa Robles-Interim Housing-DSA Inspection | 1 | Mesa Robles | Interim Housing | DSA Inspection | 39740 | 39740 | 39740 | 0 | 39740 | 100%
Mesa Robles-Interim Housing-DSA Special Inspection | 1 | Mesa Robles | Interim Housing | DSA Special Inspection | 13540 | 13540 | 11330.5 | 0 | 11330.5 | 100%
Mesa Robles-Interim Housing-Environ Consultant | 1 | Mesa Robles | Interim Housing | Environ Consultant | 1280 | No Proposal Provided | 1280 | 0 | 1280 | 100%
Mesa Robles-Interim Housing-FF & E | 1 | Mesa Robles | Interim Housing | FF & E | 0 | 0 | 86851.54 | 0 | 86851.54 | 100%
Mesa Robles-Interim Housing-Legal Services | 1 | Mesa Robles | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Mesa Robles-Interim Housing-Modular Buildings | 1 | Mesa Robles | Interim Housing | Modular Buildings | 479577.48 | 0 | 479577.48 | 0 | 479577.48 | 100%
Mesa Robles-Interim Housing-Move Management | 1 | Mesa Robles | Interim Housing | Move Management | 0 | 0 | 500 | 0 | 500 | 100%
Mesa Robles-Interim Housing-Reprographics | 1 | Mesa Robles | Interim Housing | Reprographics | 1661.08 | 1661.08 | 1661.08 | 0 | 1661.08 | 100%
Mesa Robles-Interim Housing-Technology | 1 | Mesa Robles | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century classroom-Advertisement | 1 | Nelson | 21st Century classroom | Advertisement | 1306.06 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century classroom-Asbestos oversight/survey/abatement | 1 | Nelson | 21st Century classroom | Asbestos oversight/survey/abatement | 85835 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century classroom-CM/PM Management | 1 | Nelson | 21st Century classroom | CM/PM Management | 208976.71 | 150831 | 150811.25 | 0 | 150811.25 | 100%
Nelson-21st Century classroom-Construction Contingency | 1 | Nelson | 21st Century classroom | Construction Contingency | 203535.9 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century classroom-Contractor | 1 | Nelson | 21st Century classroom | Contractor | 2234549.68 | 2253432.23 | 2339408.93 | 0 | 2339408.93 | 100%
Nelson-21st Century classroom-Design | 1 | Nelson | 21st Century classroom | Design | 249338.6 | 127727.2 | 109894.72 | 0 | 109894.72 | 100%
Nelson-21st Century classroom-DSA Fees | 1 | Nelson | 21st Century classroom | DSA Fees | 41556.43 | No Proposal Provided | 30211.09 | 0 | 30211.09 | 100%
Nelson-21st Century classroom-DSA Inspection | 1 | Nelson | 21st Century classroom | DSA Inspection | 35619.8 | 34720 | 32620 | 0 | 32620 | 100%
Nelson-21st Century classroom-DSA Special Inspection | 1 | Nelson | 21st Century classroom | DSA Special Inspection | 17809.9 | 26880 | 6905 | 0 | 6905 | 100%
Nelson-21st Century classroom-Environ Consultant | 1 | Nelson | 21st Century classroom | Environ Consultant | 10448.47 | 0 | 6505 | 0 | 6505 | 100%
Nelson-21st Century classroom-FF & E | 1 | Nelson | 21st Century classroom | FF & E | 380000 | 131001.36 | 409815.62 | 0 | 409815.62 | 100%
Nelson-21st Century classroom-Legal Services | 1 | Nelson | 21st Century classroom | Legal Services | 0 | 0 | 22.5 | 0 | 22.5 | 100%
Nelson-21st Century classroom-Move classroom | 1 | Nelson | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-21st Century classroom-Move Management | 1 | Nelson | 21st Century classroom | Move Management | 9498.61 | 0 | 8551.98 | 0 | 8551.98 | 100%
Nelson-21st Century classroom-Reprographics | 1 | Nelson | 21st Century classroom | Reprographics | 1306.06 | No Proposal Provided | 728.6 | 0 | 728.6 | 100%
Nelson-21st Century classroom-Technology | 1 | Nelson | 21st Century classroom | Technology | 380000 | 54617.76 | 313543.3 | 0 | 313543.3 | 100%
Nelson-Ceiling replacement-CM/PM Management | 1 | Nelson | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Ceiling replacement-Contractor | 1 | Nelson | Ceiling replacement | Contractor | 309746 | 309746 | 309746 | 0 | 309746 | 100%
Nelson-Drinking Fountain replacement-Advertisement | 1 | Nelson | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking Fountain replacement-Contractor | 1 | Nelson | Drinking Fountain replacement | Contractor | 30000 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking Fountain replacement-Design | 1 | Nelson | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking Fountain replacement-DSA Fees | 1 | Nelson | Drinking Fountain replacement | DSA Fees | 0 | 0 | 1050 | 0 | 1050 | 100%
Nelson-Drinking Fountain replacement-DSA Inspection | 1 | Nelson | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking Fountain replacement-DSA Special Inspection | 1 | Nelson | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking Fountain replacement-Environ Consultant | 1 | Nelson | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Drinking Fountain replacement-Reprographics | 1 | Nelson | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Fire Alarm replacement-Advertisement | 1 | Nelson | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Fire Alarm replacement-Contractor | 1 | Nelson | Fire Alarm replacement | Contractor | 285000 | 98440 | 119435.08 | 0 | 119435.08 | 100%
Nelson-Fire Alarm replacement-Design | 1 | Nelson | Fire Alarm replacement | Design | 11875 | No Proposal Provided | 11875 | 0 | 11875 | 100%
Nelson-Fire Alarm replacement-DSA Fees | 1 | Nelson | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Fire Alarm replacement-DSA Inspection | 1 | Nelson | Fire Alarm replacement | DSA Inspection | 0 | 0 | 12250 | 0 | 12250 | 100%
Nelson-Fire Alarm replacement-Environ Consultant | 1 | Nelson | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Fire Alarm replacement-Reprographics | 1 | Nelson | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Advertisement | 1 | Nelson | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Alarm | 1 | Nelson | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-CM/PM Management | 1 | Nelson | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Construction Contingency | 1 | Nelson | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Contractor | 1 | Nelson | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Design | 1 | Nelson | Interim Housing | Design | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-DSA Fees | 1 | Nelson | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-DSA Inspection | 1 | Nelson | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-DSA Special Inspection | 1 | Nelson | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Environ Consultant | 1 | Nelson | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-FF & E | 1 | Nelson | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Legal Services | 1 | Nelson | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Modular Buildings | 1 | Nelson | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Move Management | 1 | Nelson | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Reprographics | 1 | Nelson | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Nelson-Interim Housing-Technology | 1 | Nelson | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century classroom-Advertisement | 1 | Newton | 21st Century classroom | Advertisement | 1380.36 | 0 | 324.48 | 0 | 324.48 | 100%
Newton-21st Century classroom-Asbestos oversight/survey/abatement | 1 | Newton | 21st Century classroom | Asbestos oversight/survey/abatement | 66500 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century classroom-CM/PM Management | 1 | Newton | 21st Century classroom | CM/PM Management | 220654.2 | 180453 | 428201.25 | 25 | 428176.25 | 99.99%
Newton-21st Century classroom-Construction Contingency | 1 | Newton | 21st Century classroom | Construction Contingency | 215114 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century classroom-Contractor | 1 | Newton | 21st Century classroom | Contractor | 2294621.04 | No Proposal Provided | 2118400 | 213248.44 | 1905151.56 | 89.93%
Newton-21st Century classroom-Design | 1 | Newton | 21st Century classroom | Design | 263522.18 | 232763 | 244580 | 25893.29 | 218686.71 | 89.41%
Newton-21st Century classroom-DSA Fees | 1 | Newton | 21st Century classroom | DSA Fees | 43920.36 | 28270.82 | 28270.82 | 0 | 28270.82 | 100%
Newton-21st Century classroom-DSA Inspection | 1 | Newton | 21st Century classroom | DSA Inspection | 37646.03 | N/A | 115770 | 19890 | 95880 | 82.82%
Newton-21st Century classroom-DSA Special Inspection | 1 | Newton | 21st Century classroom | DSA Special Inspection | 18823.01 | N/A | 1395 | 855 | 540 | 38.71%
Newton-21st Century classroom-Environ Consultant | 1 | Newton | 21st Century classroom | Environ Consultant | 0 | 0 | 29250 | 11200 | 18050 | 61.71%
Newton-21st Century classroom-FF & E | 1 | Newton | 21st Century classroom | FF & E | 400000 | 0 | 400656.46 | 0 | 400656.46 | 100%
Newton-21st Century classroom-Legal Services | 1 | Newton | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-21st Century classroom-Move classroom | 1 | Newton | 21st Century classroom | Move classroom | 0 | 0 | 318.77 | 0 | 318.77 | 100%
Newton-21st Century classroom-Move Management | 1 | Newton | 21st Century classroom | Move Management | 10038.94 | 0 | 6088.49 | 2228.63 | 3859.86 | 63.4%
Newton-21st Century classroom-Reprographics | 1 | Newton | 21st Century classroom | Reprographics | 1380.36 | 0 | 2508.74 | 0 | 2508.74 | 100%
Newton-21st Century classroom-Technology | 1 | Newton | 21st Century classroom | Technology | 400000 | 0 | 411783.4 | 0 | 411783.4 | 100%
Newton-Ceiling replacement-CM/PM Management | 1 | Newton | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Ceiling replacement-Contractor | 1 | Newton | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking Fountain replacement-Advertisement | 1 | Newton | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking Fountain replacement-Contractor | 1 | Newton | Drinking Fountain replacement | Contractor | 30000 | N/A | 0 | 0 | 0 | #DIV/0!
Newton-Drinking Fountain replacement-Design | 1 | Newton | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking Fountain replacement-DSA Fees | 1 | Newton | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking Fountain replacement-DSA Inspection | 1 | Newton | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking Fountain replacement-DSA Special Inspection | 1 | Newton | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking Fountain replacement-Environ Consultant | 1 | Newton | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Drinking Fountain replacement-Reprographics | 1 | Newton | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Fire Alarm replacement-Advertisement | 1 | Newton | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Fire Alarm replacement-Contractor | 1 | Newton | Fire Alarm replacement | Contractor | 285000 | 102680 | 82680.01 | 0 | 82680.01 | 100%
Newton-Fire Alarm replacement-Design | 1 | Newton | Fire Alarm replacement | Design | 47500 | No Proposal Provided | 9500 | 0 | 9500 | 100%
Newton-Fire Alarm replacement-DSA Fees | 1 | Newton | Fire Alarm replacement | DSA Fees | 0 | 0 | 645 | 0 | 645 | 100%
Newton-Fire Alarm replacement-DSA Inspection | 1 | Newton | Fire Alarm replacement | DSA Inspection | 8125 | No Proposal Provided | 8125 | 0 | 8125 | 100%
Newton-Fire Alarm replacement-Environ Consultant | 1 | Newton | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Fire Alarm replacement-Reprographics | 1 | Newton | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Advertisement | 1 | Newton | Interim Housing | Advertisement | 0 | 0 | 1088 | 0 | 1088 | 100%
Newton-Interim Housing-Alarm | 1 | Newton | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-CM/PM Management | 1 | Newton | Interim Housing | CM/PM Management | Incl in 21st | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Construction Contingency | 1 | Newton | Interim Housing | Construction Contingency | 31300 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Contractor | 1 | Newton | Interim Housing | Contractor | 313100.97 | 0 | 426102.09 | 1050 | 425052.09 | 99.75%
Newton-Interim Housing-Design | 1 | Newton | Interim Housing | Design | 75338.08 | 75338.08 | 81583.08 | 1725 | 79858.08 | 97.89%
Newton-Interim Housing-DSA Fees | 1 | Newton | Interim Housing | DSA Fees | 32799.17 | No Proposal Provided | 12122.54 | 0 | 12122.54 | 100%
Newton-Interim Housing-DSA Inspection | 1 | Newton | Interim Housing | DSA Inspection | 16000 | 0 | 16000 | 0 | 16000 | 100%
Newton-Interim Housing-DSA Special Inspection | 1 | Newton | Interim Housing | DSA Special Inspection | 12000 | 0 | 750 | 0 | 750 | 100%
Newton-Interim Housing-Environ Consultant | 1 | Newton | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-FF & E | 1 | Newton | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Legal Services | 1 | Newton | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Modular Buildings | 1 | Newton | Interim Housing | Modular Buildings | 239959.74 | 239959.74 | 239788.74 | 0 | 239788.74 | 100%
Newton-Interim Housing-Move Management | 1 | Newton | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Reprographics | 1 | Newton | Interim Housing | Reprographics | 0 | 0 | 539.94 | 0 | 539.94 | 100%
Newton-Interim Housing-Technology | 1 | Newton | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Newton-Interim Housing-Utilities | 1 | Newton | Interim Housing | Utilities | 0 | 0 | 1072 | 0 | 1072 | 100%
Orange Grove-21st Century classroom-Advertisement | 3 | Orange Grove | 21st Century classroom | Advertisement | 1231.11 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-Asbestos oversight/survey/abatement | 3 | Orange Grove | 21st Century classroom | Asbestos oversight/survey/abatement | 49000 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-CM/PM Management | 3 | Orange Grove | 21st Century classroom | CM/PM Management | 194619.4 | N/A | 9265 | 0 | 9265 | 100%
Orange Grove-21st Century classroom-Construction Contingency | 3 | Orange Grove | 21st Century classroom | Construction Contingency | 191856 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-Contractor | 3 | Orange Grove | 21st Century classroom | Contractor | 2046527.95 | N/A | 19116.72 | 0 | 19116.72 | 100%
Orange Grove-21st Century classroom-Design | 3 | Orange Grove | 21st Century classroom | Design | 223838.4 | N/A | 222000 | 222000 | 0 | 0%
Orange Grove-21st Century classroom-DSA Fees | 3 | Orange Grove | 21st Century classroom | DSA Fees | 39171.72 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-DSA Inspection | 3 | Orange Grove | 21st Century classroom | DSA Inspection | 33575.76 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-DSA Special Inspection | 3 | Orange Grove | 21st Century classroom | DSA Special Inspection | 16787.88 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-Environ Consultant | 3 | Orange Grove | 21st Century classroom | Environ Consultant | 12311.11 | No Proposal Provided | 2800 | 0 | 2800 | 100%
Orange Grove-21st Century classroom-FF & E | 3 | Orange Grove | 21st Century classroom | FF & E | 340000 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-Legal Services | 3 | Orange Grove | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-Move classroom | 3 | Orange Grove | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-Move Management | 3 | Orange Grove | 21st Century classroom | Move Management | 8953.54 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-Reprographics | 3 | Orange Grove | 21st Century classroom | Reprographics | 1231.11 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-21st Century classroom-Technology | 3 | Orange Grove | 21st Century classroom | Technology | 340000 | 0 | 208552.54 | 0 | 208552.54 | 100%
Orange Grove-Ceiling replacement-CM/PM Management | 3 | Orange Grove | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Ceiling replacement-Contractor | 3 | Orange Grove | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking Fountain replacement-Advertisement | 3 | Orange Grove | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking Fountain replacement-Contractor | 3 | Orange Grove | Drinking Fountain replacement | Contractor | 22500 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking Fountain replacement-Design | 3 | Orange Grove | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking Fountain replacement-DSA Fees | 3 | Orange Grove | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking Fountain replacement-DSA Inspection | 3 | Orange Grove | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking Fountain replacement-DSA Special Inspection | 3 | Orange Grove | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking Fountain replacement-Environ Consultant | 3 | Orange Grove | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Drinking Fountain replacement-Reprographics | 3 | Orange Grove | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm replacement-Advertisement | 3 | Orange Grove | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm replacement-Contractor | 3 | Orange Grove | Fire Alarm replacement | Contractor | 255000 | N/A | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm replacement-Design | 3 | Orange Grove | Fire Alarm replacement | Design | 49500 | No Proposal Provided | 37125 | 0 | 37125 | 100%
Orange Grove-Fire Alarm replacement-DSA Fees | 3 | Orange Grove | Fire Alarm replacement | DSA Fees | 0 | 0 | 1080 | 0 | 1080 | 100%
Orange Grove-Fire Alarm replacement-DSA Inspection | 3 | Orange Grove | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm replacement-Environ Consultant | 3 | Orange Grove | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Fire Alarm replacement-Reprographics | 3 | Orange Grove | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Advertisement | 3 | Orange Grove | Interim Housing | Advertisement | 400 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Alarm | 3 | Orange Grove | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-CM/PM Management | 3 | Orange Grove | Interim Housing | CM/PM Management | 42410 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Construction Contingency | 3 | Orange Grove | Interim Housing | Construction Contingency | 65000 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Contractor | 3 | Orange Grove | Interim Housing | Contractor | 650000 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Design | 3 | Orange Grove | Interim Housing | Design | 80000 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-DSA Fees | 3 | Orange Grove | Interim Housing | DSA Fees | 14000 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-DSA Inspection | 3 | Orange Grove | Interim Housing | DSA Inspection | 12000 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-DSA Special Inspection | 3 | Orange Grove | Interim Housing | DSA Special Inspection | 12000 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Environ Consultant | 3 | Orange Grove | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-FF & E | 3 | Orange Grove | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Legal Services | 3 | Orange Grove | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Modular Buildings | 3 | Orange Grove | Interim Housing | Modular Buildings | 150000 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Move Management | 3 | Orange Grove | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Reprographics | 3 | Orange Grove | Interim Housing | Reprographics | 400 | 0 | 0 | 0 | 0 | #DIV/0!
Orange Grove-Interim Housing-Technology | 3 | Orange Grove | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Advertisement | 0 | Palm Canyon | 21st Century classroom | Advertisement | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Asbestos oversight/survey/abatement | 0 | Palm Canyon | 21st Century classroom | Asbestos oversight/survey/abatement | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-CM/PM Management | 0 | Palm Canyon | 21st Century classroom | CM/PM Management | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Construction Contingency | 0 | Palm Canyon | 21st Century classroom | Construction Contingency | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Contractor | 0 | Palm Canyon | 21st Century classroom | Contractor | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Design | 0 | Palm Canyon | 21st Century classroom | Design | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-DSA Fees | 0 | Palm Canyon | 21st Century classroom | DSA Fees | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-DSA Inspection | 0 | Palm Canyon | 21st Century classroom | DSA Inspection | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-DSA Special Inspection | 0 | Palm Canyon | 21st Century classroom | DSA Special Inspection | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Environ Consultant | 0 | Palm Canyon | 21st Century classroom | Environ Consultant | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-FF & E | 0 | Palm Canyon | 21st Century classroom | FF & E | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Legal Services | 0 | Palm Canyon | 21st Century classroom | Legal Services | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Move classroom | 0 | Palm Canyon | 21st Century classroom | Move classroom | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Move Management | 0 | Palm Canyon | 21st Century classroom | Move Management | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Reprographics | 0 | Palm Canyon | 21st Century classroom | Reprographics | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-21st Century classroom-Technology | 0 | Palm Canyon | 21st Century classroom | Technology | 10368.74 | No Proposal Provided | 10368.74 | 0 | 10368.74 | 100%
Palm Canyon-Ceiling replacement-CM/PM Management | 0 | Palm Canyon | Ceiling replacement | CM/PM Management | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Ceiling replacement-Contractor | 0 | Palm Canyon | Ceiling replacement | Contractor | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking Fountain replacement-Advertisement | 0 | Palm Canyon | Drinking Fountain replacement | Advertisement | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking Fountain replacement-Contractor | 0 | Palm Canyon | Drinking Fountain replacement | Contractor | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking Fountain replacement-Design | 0 | Palm Canyon | Drinking Fountain replacement | Design | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking Fountain replacement-DSA Fees | 0 | Palm Canyon | Drinking Fountain replacement | DSA Fees | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking Fountain replacement-DSA Inspection | 0 | Palm Canyon | Drinking Fountain replacement | DSA Inspection | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking Fountain replacement-DSA Special Inspection | 0 | Palm Canyon | Drinking Fountain replacement | DSA Special Inspection | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking Fountain replacement-Environ Consultant | 0 | Palm Canyon | Drinking Fountain replacement | Environ Consultant | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Drinking Fountain replacement-Reprographics | 0 | Palm Canyon | Drinking Fountain replacement | Reprographics | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm replacement-Advertisement | 0 | Palm Canyon | Fire Alarm replacement | Advertisement | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm replacement-Contractor | 0 | Palm Canyon | Fire Alarm replacement | Contractor | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm replacement-Design | 0 | Palm Canyon | Fire Alarm replacement | Design | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm replacement-DSA Fees | 0 | Palm Canyon | Fire Alarm replacement | DSA Fees | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm replacement-DSA Inspection | 0 | Palm Canyon | Fire Alarm replacement | DSA Inspection | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm replacement-Environ Consultant | 0 | Palm Canyon | Fire Alarm replacement | Environ Consultant | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Fire Alarm replacement-Reprographics | 0 | Palm Canyon | Fire Alarm replacement | Reprographics | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Advertisement | 0 | Palm Canyon | Interim Housing | Advertisement | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Alarm | 0 | Palm Canyon | Interim Housing | Alarm | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-CM/PM Management | 0 | Palm Canyon | Interim Housing | CM/PM Management | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Construction Contingency | 0 | Palm Canyon | Interim Housing | Construction Contingency | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Contractor | 0 | Palm Canyon | Interim Housing | Contractor | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Design | 0 | Palm Canyon | Interim Housing | Design | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-DSA Fees | 0 | Palm Canyon | Interim Housing | DSA Fees | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-DSA Inspection | 0 | Palm Canyon | Interim Housing | DSA Inspection | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-DSA Special Inspection | 0 | Palm Canyon | Interim Housing | DSA Special Inspection | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Environ Consultant | 0 | Palm Canyon | Interim Housing | Environ Consultant | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-FF & E | 0 | Palm Canyon | Interim Housing | FF & E | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Legal Services | 0 | Palm Canyon | Interim Housing | Legal Services | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Modular Buildings | 0 | Palm Canyon | Interim Housing | Modular Buildings | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Move Management | 0 | Palm Canyon | Interim Housing | Move Management | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Reprographics | 0 | Palm Canyon | Interim Housing | Reprographics | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm Canyon-Interim Housing-Technology | 0 | Palm Canyon | Interim Housing | Technology | No Scope Established | 0 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Advertisement | 6 | Palm | 21st Century classroom | Advertisement | 1393.47 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Asbestos oversight/survey/abatement | 6 | Palm | 21st Century classroom | Asbestos oversight/survey/abatement | 70000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-CM/PM Management | 6 | Palm | 21st Century classroom | CM/PM Management | 222256.74 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Construction Contingency | 6 | Palm | 21st Century classroom | Construction Contingency | 217158 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Contractor | 6 | Palm | 21st Century classroom | Contractor | 2316424.39 | No Proposal Provided | 46372.24 | 0 | 46372.24 | 100%
Palm-21st Century classroom-Design | 6 | Palm | 21st Century classroom | Design | 266026.15 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-DSA Fees | 6 | Palm | 21st Century classroom | DSA Fees | 44337.69 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-DSA Inspection | 6 | Palm | 21st Century classroom | DSA Inspection | 38003.74 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-DSA Special Inspection | 6 | Palm | 21st Century classroom | DSA Special Inspection | 19001.87 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Environ Consultant | 6 | Palm | 21st Century classroom | Environ Consultant | 11147.76 | No Proposal Provided | 2500 | 0 | 2500 | 100%
Palm-21st Century classroom-FF & E | 6 | Palm | 21st Century classroom | FF & E | 400000 | No Proposal Provided | 19119.08 | 0 | 19119.08 | 100%
Palm-21st Century classroom-Legal Services | 6 | Palm | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Move classroom | 6 | Palm | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Move Management | 6 | Palm | 21st Century classroom | Move Management | 10134.33 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Reprographics | 6 | Palm | 21st Century classroom | Reprographics | 1393.47 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-21st Century classroom-Technology | 6 | Palm | 21st Century classroom | Technology | 400000 | No Proposal Provided | 112875.6 | 0 | 112875.6 | 100%
Palm-Ceiling replacement-CM/PM Management | 6 | Palm | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Ceiling replacement-Contractor | 6 | Palm | Ceiling replacement | Contractor | 232310 | 232310 | 232310 | 0 | 232310 | 100%
Palm-Drinking Fountain replacement-Advertisement | 6 | Palm | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking Fountain replacement-Contractor | 6 | Palm | Drinking Fountain replacement | Contractor | 30000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Drinking Fountain replacement-Design | 6 | Palm | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking Fountain replacement-DSA Fees | 6 | Palm | Drinking Fountain replacement | DSA Fees | 1050 | No Proposal Provided | 1050 | 0 | 1050 | 100%
Palm-Drinking Fountain replacement-DSA Inspection | 6 | Palm | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking Fountain replacement-DSA Special Inspection | 6 | Palm | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking Fountain replacement-Environ Consultant | 6 | Palm | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Drinking Fountain replacement-Reprographics | 6 | Palm | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm replacement-Advertisement | 6 | Palm | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm replacement-Contractor | 6 | Palm | Fire Alarm replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm replacement-Design | 6 | Palm | Fire Alarm replacement | Design | 48500 | No Proposal Provided | 36375 | 0 | 36375 | 100%
Palm-Fire Alarm replacement-DSA Fees | 6 | Palm | Fire Alarm replacement | DSA Fees | 0 | 0 | 870 | 0 | 870 | 100%
Palm-Fire Alarm replacement-DSA Inspection | 6 | Palm | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm replacement-Environ Consultant | 6 | Palm | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Fire Alarm replacement-Reprographics | 6 | Palm | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Advertisement | 6 | Palm | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Alarm | 6 | Palm | Interim Housing | Alarm | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-CM/PM Management | 6 | Palm | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Construction Contingency | 6 | Palm | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Contractor | 6 | Palm | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Design | 6 | Palm | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-DSA Fees | 6 | Palm | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-DSA Inspection | 6 | Palm | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-DSA Special Inspection | 6 | Palm | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Environ Consultant | 6 | Palm | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-FF & E | 6 | Palm | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Legal Services | 6 | Palm | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Modular Buildings | 6 | Palm | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Move Management | 6 | Palm | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Reprographics | 6 | Palm | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Palm-Interim Housing-Technology | 6 | Palm | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Advertisement | 8 | Sierra Vista | 21st Century classroom | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Asbestos oversight/survey/abatement | 8 | Sierra Vista | 21st Century classroom | Asbestos oversight/survey/abatement | 59500 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-CM/PM Management | 8 | Sierra Vista | 21st Century classroom | CM/PM Management | 196289.63 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Construction Contingency | 8 | Sierra Vista | 21st Century classroom | Construction Contingency | 190476.3 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Contractor | 8 | Sierra Vista | 21st Century classroom | Contractor | 2031810.69 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Design | 8 | Sierra Vista | 21st Century classroom | Design | 233340.13 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-DSA Fees | 8 | Sierra Vista | 21st Century classroom | DSA Fees | 38890.02 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-DSA Inspection | 8 | Sierra Vista | 21st Century classroom | DSA Inspection | 33334.3 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-DSA Special Inspection | 8 | Sierra Vista | 21st Century classroom | DSA Special Inspection | 16667.15 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Environ Consultant | 8 | Sierra Vista | 21st Century classroom | Environ Consultant | 9778.06 | No Proposal Provided | 3000 | 0 | 3000 | 100%
Sierra Vista-21st Century classroom-FF & E | 8 | Sierra Vista | 21st Century classroom | FF & E | 340000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Legal Services | 8 | Sierra Vista | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Move classroom | 8 | Sierra Vista | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Move Management | 8 | Sierra Vista | 21st Century classroom | Move Management | 8889.15 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Reprographics | 8 | Sierra Vista | 21st Century classroom | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-21st Century classroom-Technology | 8 | Sierra Vista | 21st Century classroom | Technology | 340000 | No Proposal Provided | 171066.97 | 0 | 171066.97 | 100%
Sierra Vista-Ceiling replacement-CM/PM Management | 8 | Sierra Vista | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Ceiling replacement-Contractor | 8 | Sierra Vista | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking Fountain replacement-Advertisement | 8 | Sierra Vista | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking Fountain replacement-Contractor | 8 | Sierra Vista | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking Fountain replacement-Design | 8 | Sierra Vista | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking Fountain replacement-DSA Fees | 8 | Sierra Vista | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking Fountain replacement-DSA Inspection | 8 | Sierra Vista | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking Fountain replacement-DSA Special Inspection | 8 | Sierra Vista | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking Fountain replacement-Environ Consultant | 8 | Sierra Vista | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Drinking Fountain replacement-Reprographics | 8 | Sierra Vista | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm replacement-Advertisement | 8 | Sierra Vista | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm replacement-Contractor | 8 | Sierra Vista | Fire Alarm replacement | Contractor | 255000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm replacement-Design | 8 | Sierra Vista | Fire Alarm replacement | Design | 49500 | No Proposal Provided | 37125 | 0 | 37125 | 100%
Sierra Vista-Fire Alarm replacement-DSA Fees | 8 | Sierra Vista | Fire Alarm replacement | DSA Fees | 0 | 0 | 1050 | 0 | 1050 | 100%
Sierra Vista-Fire Alarm replacement-DSA Inspection | 8 | Sierra Vista | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm replacement-Environ Consultant | 8 | Sierra Vista | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Fire Alarm replacement-Reprographics | 8 | Sierra Vista | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Advertisement | 8 | Sierra Vista | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Alarm | 8 | Sierra Vista | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-CM/PM Management | 8 | Sierra Vista | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Construction Contingency | 8 | Sierra Vista | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Contractor | 8 | Sierra Vista | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Design | 8 | Sierra Vista | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-DSA Fees | 8 | Sierra Vista | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-DSA Inspection | 8 | Sierra Vista | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-DSA Special Inspection | 8 | Sierra Vista | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Environ Consultant | 8 | Sierra Vista | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-FF & E | 8 | Sierra Vista | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Legal Services | 8 | Sierra Vista | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Modular Buildings | 8 | Sierra Vista | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Move Management | 8 | Sierra Vista | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Reprographics | 8 | Sierra Vista | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Sierra Vista-Interim Housing-Technology | 8 | Sierra Vista | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Advertisement | 7 | Sparks ES | 21st Century classroom | Advertisement | 1408.87 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Asbestos oversight/survey/abatement | 7 | Sparks ES | 21st Century classroom | Asbestos oversight/survey/abatement | 70000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-CM/PM Management | 7 | Sparks ES | 21st Century classroom | CM/PM Management | 224138.39 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Construction Contingency | 7 | Sparks ES | 21st Century classroom | Construction Contingency | 219558 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Contractor | 7 | Sparks ES | 21st Century classroom | Contractor | 2342025.19 | No Proposal Provided | 63116.72 | 0 | 63116.72 | 100%
Sparks ES-21st Century classroom-Design | 7 | Sparks ES | 21st Century classroom | Design | 268966.23 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-DSA Fees | 7 | Sparks ES | 21st Century classroom | DSA Fees | 44827.71 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-DSA Inspection | 7 | Sparks ES | 21st Century classroom | DSA Inspection | 38423.75 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-DSA Special Inspection | 7 | Sparks ES | 21st Century classroom | DSA Special Inspection | 19211.87 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Environ Consultant | 7 | Sparks ES | 21st Century classroom | Environ Consultant | 11270.97 | No Proposal Provided | 2670 | 0 | 2670 | 100%
Sparks ES-21st Century classroom-FF & E | 7 | Sparks ES | 21st Century classroom | FF & E | 400000 | No Proposal Provided | 20720.61 | 0 | 20720.61 | 100%
Sparks ES-21st Century classroom-Legal Services | 7 | Sparks ES | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Move classroom | 7 | Sparks ES | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Move Management | 7 | Sparks ES | 21st Century classroom | Move Management | 10246.33 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Reprographics | 7 | Sparks ES | 21st Century classroom | Reprographics | 1408.87 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-21st Century classroom-Technology | 7 | Sparks ES | 21st Century classroom | Technology | 400000 | No Proposal Provided | 172413.82 | 0 | 172413.82 | 100%
Sparks ES-Ceiling replacement-CM/PM Management | 7 | Sparks ES | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Ceiling replacement-Contractor | 7 | Sparks ES | Ceiling replacement | Contractor | 258122 | 258122 | 258122 | 0 | 258122 | 100%
Sparks ES-Drinking Fountain replacement-Advertisement | 7 | Sparks ES | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking Fountain replacement-Contractor | 7 | Sparks ES | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking Fountain replacement-Design | 7 | Sparks ES | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking Fountain replacement-DSA Fees | 7 | Sparks ES | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking Fountain replacement-DSA Inspection | 7 | Sparks ES | Drinking Fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking Fountain replacement-DSA Special Inspection | 7 | Sparks ES | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking Fountain replacement-Environ Consultant | 7 | Sparks ES | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Drinking Fountain replacement-Reprographics | 7 | Sparks ES | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm replacement-Advertisement | 7 | Sparks ES | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm replacement-Contractor | 7 | Sparks ES | Fire Alarm replacement | Contractor | 300000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm replacement-Design | 7 | Sparks ES | Fire Alarm replacement | Design | 12125 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm replacement-DSA Fees | 7 | Sparks ES | Fire Alarm replacement | DSA Fees | 0 | 0 | 930 | 0 | 930 | 100%
Sparks ES-Fire Alarm replacement-DSA Inspection | 7 | Sparks ES | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm replacement-Environ Consultant | 7 | Sparks ES | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Fire Alarm replacement-Reprographics | 7 | Sparks ES | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Advertisement | 7 | Sparks ES | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Alarm | 7 | Sparks ES | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-CM/PM Management | 7 | Sparks ES | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Construction Contingency | 7 | Sparks ES | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Contractor | 7 | Sparks ES | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Design | 7 | Sparks ES | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-DSA Fees | 7 | Sparks ES | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-DSA Inspection | 7 | Sparks ES | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-DSA Special Inspection | 7 | Sparks ES | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Environ Consultant | 7 | Sparks ES | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-FF & E | 7 | Sparks ES | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Legal Services | 7 | Sparks ES | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Modular Buildings | 7 | Sparks ES | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Move Management | 7 | Sparks ES | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Reprographics | 7 | Sparks ES | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks ES-Interim Housing-Technology | 7 | Sparks ES | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-21st Century classroom-Advertisement | 2 | Sparks MS | 21st Century classroom | Advertisement | 1181.31 | N/A | 324.48 | 0 | 324.48 | 100%
Sparks MS-21st Century classroom-Asbestos oversight/survey/abatement | 2 | Sparks MS | 21st Century classroom | Asbestos oversight/survey/abatement | 56000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks MS-21st Century classroom-CM/PM Management | 2 | Sparks MS | 21st Century classroom | CM/PM Management | 204134.44 | 0 | 393212.5 | 48.75 | 393163.75 | 99.99%
Sparks MS-21st Century classroom-Construction Contingency | 2 | Sparks MS | 21st Century classroom | Construction Contingency | 184094.8 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks MS-21st Century classroom-Contractor | 2 | Sparks MS | 21st Century classroom | Contractor | 1963739.23 | N/A | 1725000 | 141204.18 | 1583795.82 | 91.81%
Sparks MS-21st Century classroom-Design | 2 | Sparks MS | 21st Century classroom | Design | 225522.57 | 150523 | 198473 | 6150.69 | 192322.31 | 96.9%
Sparks MS-21st Century classroom-DSA Fees | 2 | Sparks MS | 21st Century classroom | DSA Fees | 0 | 0 | 22264.25 | 0 | 22264.25 | 100%
Sparks MS-21st Century classroom-DSA Inspection | 2 | Sparks MS | 21st Century classroom | DSA Inspection | 32217.51 | N/A | 42670 | 3825 | 38845 | 91.04%
Sparks MS-21st Century classroom-DSA Special Inspection | 2 | Sparks MS | 21st Century classroom | DSA Special Inspection | 16108.76 | N/A | 2080 | 18.5 | 2061.5 | 99.11%
Sparks MS-21st Century classroom-Environ Consultant | 2 | Sparks MS | 21st Century classroom | Environ Consultant | 9450.47 | No Proposal Provided | 10500 | 0 | 10500 | 100%
Sparks MS-21st Century classroom-FF & E | 2 | Sparks MS | 21st Century classroom | FF & E | 460000 | 0 | 288808.41 | 0 | 288808.41 | 100%
Sparks MS-21st Century classroom-Legal Services | 2 | Sparks MS | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-21st Century classroom-Move classroom | 2 | Sparks MS | 21st Century classroom | Move classroom | 0 | 0 | 318.77 | 0 | 318.77 | 100%
Sparks MS-21st Century classroom-Move Management | 2 | Sparks MS | 21st Century classroom | Move Management | 8591.34 | N/A | 6105 | 2475 | 3630 | 59.46%
Sparks MS-21st Century classroom-Reprographics | 2 | Sparks MS | 21st Century classroom | Reprographics | 1181.31 | N/A | 2470.05 | 0 | 2470.05 | 100%
Sparks MS-21st Century classroom-Technology | 2 | Sparks MS | 21st Century classroom | Technology | 460000 | No Proposal Provided | 331175.82 | 0 | 331175.82 | 100%
Sparks MS-Ceiling replacement-CM/PM Management | 2 | Sparks MS | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Ceiling replacement-Contractor | 2 | Sparks MS | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking Fountain replacement-Advertisement | 2 | Sparks MS | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking Fountain replacement-Contractor | 2 | Sparks MS | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking Fountain replacement-Design | 2 | Sparks MS | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking Fountain replacement-DSA Fees | 2 | Sparks MS | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking Fountain replacement-DSA Inspection | 2 | Sparks MS | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking Fountain replacement-DSA Special Inspection | 2 | Sparks MS | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking Fountain replacement-Environ Consultant | 2 | Sparks MS | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Drinking Fountain replacement-Reprographics | 2 | Sparks MS | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Fire Alarm replacement-Advertisement | 2 | Sparks MS | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Fire Alarm replacement-Contractor | 2 | Sparks MS | Fire Alarm replacement | Contractor | 240000 | 162000 | 152000 | 0 | 152000 | 100%
Sparks MS-Fire Alarm replacement-Design | 2 | Sparks MS | Fire Alarm replacement | Design | 4950 | No Proposal Provided | 4950 | 0 | 4950 | 100%
Sparks MS-Fire Alarm replacement-DSA Fees | 2 | Sparks MS | Fire Alarm replacement | DSA Fees | 0 | 0 | 860 | 0 | 860 | 100%
Sparks MS-Fire Alarm replacement-DSA Inspection | 2 | Sparks MS | Fire Alarm replacement | DSA Inspection | 6875 | No Proposal Provided | 6875 | 0 | 6875 | 100%
Sparks MS-Fire Alarm replacement-Environ Consultant | 2 | Sparks MS | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Fire Alarm replacement-Reprographics | 2 | Sparks MS | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Advertisement | 2 | Sparks MS | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Alarm | 2 | Sparks MS | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-CM/PM Management | 2 | Sparks MS | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Construction Contingency | 2 | Sparks MS | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Contractor | 2 | Sparks MS | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Design | 2 | Sparks MS | Interim Housing | Design | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-DSA Fees | 2 | Sparks MS | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-DSA Inspection | 2 | Sparks MS | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-DSA Special Inspection | 2 | Sparks MS | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Environ Consultant | 2 | Sparks MS | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-FF & E | 2 | Sparks MS | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Legal Services | 2 | Sparks MS | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Modular Buildings | 2 | Sparks MS | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Move Management | 2 | Sparks MS | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Reprographics | 2 | Sparks MS | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sparks MS-Interim Housing-Technology | 2 | Sparks MS | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Advertisement | 4 | Stimson | 21st Century classroom | Advertisement | 0 | 0 | 292.31 | 292.31 | 0 | 0%
Stimson-21st Century classroom-Asbestos oversight/survey/abatement | 4 | Stimson | 21st Century classroom | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-CM/PM Management | 4 | Stimson | 21st Century classroom | CM/PM Management | 72491 | N/A | 10450 | 0 | 10450 | 100%
Stimson-21st Century classroom-Construction Contingency | 4 | Stimson | 21st Century classroom | Construction Contingency | 79796.4 | N/A | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Contractor | 4 | Stimson | 21st Century classroom | Contractor | 851188.2 | N/A | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Design | 4 | Stimson | 21st Century classroom | Design | 41893.11 | N/A | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-DSA Fees | 4 | Stimson | 21st Century classroom | DSA Fees | 16292.23 | N/A | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-DSA Inspection | 4 | Stimson | 21st Century classroom | DSA Inspection | 13964.77 | N/A | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-DSA Special Inspection | 4 | Stimson | 21st Century classroom | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Environ Consultant | 4 | Stimson | 21st Century classroom | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-FF & E | 4 | Stimson | 21st Century classroom | FF & E | 240000 | N/A | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Legal Services | 4 | Stimson | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Move classroom | 4 | Stimson | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Move Management | 4 | Stimson | 21st Century classroom | Move Management | 3723.94 | N/A | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Reprographics | 4 | Stimson | 21st Century classroom | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-21st Century classroom-Technology | 4 | Stimson | 21st Century classroom | Technology | 240000 | No Proposal Provided | 20737.46 | 0 | 20737.46 | 100%
Stimson-Ceiling replacement-CM/PM Management | 4 | Stimson | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Ceiling replacement-Contractor | 4 | Stimson | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking Fountain replacement-Advertisement | 4 | Stimson | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking Fountain replacement-Contractor | 4 | Stimson | Drinking Fountain replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking Fountain replacement-Design | 4 | Stimson | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking Fountain replacement-DSA Fees | 4 | Stimson | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking Fountain replacement-DSA Inspection | 4 | Stimson | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking Fountain replacement-DSA Special Inspection | 4 | Stimson | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking Fountain replacement-Environ Consultant | 4 | Stimson | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Drinking Fountain replacement-Reprographics | 4 | Stimson | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm replacement-Advertisement | 4 | Stimson | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm replacement-Contractor | 4 | Stimson | Fire Alarm replacement | Contractor | 180000 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm replacement-Design | 4 | Stimson | Fire Alarm replacement | Design | 39500 | No Proposal Provided | 29625 | 0 | 29625 | 100%
Stimson-Fire Alarm replacement-DSA Fees | 4 | Stimson | Fire Alarm replacement | DSA Fees | 375 | No Proposal Provided | 375 | 0 | 375 | 100%
Stimson-Fire Alarm replacement-DSA Inspection | 4 | Stimson | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm replacement-Environ Consultant | 4 | Stimson | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Fire Alarm replacement-Reprographics | 4 | Stimson | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Advertisement | 4 | Stimson | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Alarm | 4 | Stimson | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-CM/PM Management | 4 | Stimson | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Construction Contingency | 4 | Stimson | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Contractor | 4 | Stimson | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Design | 4 | Stimson | Interim Housing | Design | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-DSA Fees | 4 | Stimson | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-DSA Inspection | 4 | Stimson | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-DSA Special Inspection | 4 | Stimson | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Environ Consultant | 4 | Stimson | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-FF & E | 4 | Stimson | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Legal Services | 4 | Stimson | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Modular Buildings | 4 | Stimson | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Move Management | 4 | Stimson | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Reprographics | 4 | Stimson | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Stimson-Interim Housing-Technology | 4 | Stimson | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-Advertisement | 4 | Sunset | 21st Century classroom | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-Asbestos oversight/survey/abatement | 4 | Sunset | 21st Century classroom | Asbestos oversight/survey/abatement | 42000 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-CM/PM Management | 4 | Sunset | 21st Century classroom | CM/PM Management | 139528.37 | N/A | 7905 | 0 | 7905 | 100%
Sunset-21st Century classroom-Construction Contingency | 4 | Sunset | 21st Century classroom | Construction Contingency | 138170 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-Contractor | 4 | Sunset | 21st Century classroom | Contractor | 1473859.39 | No Proposal Provided | 41500 | 0 | 41500 | 100%
Sunset-21st Century classroom-Design | 4 | Sunset | 21st Century classroom | Design | 169263.09 | 225488 | 29545.89 | 0 | 29545.89 | 100%
Sunset-21st Century classroom-DSA Fees | 4 | Sunset | 21st Century classroom | DSA Fees | 28210.51 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-DSA Inspection | 4 | Sunset | 21st Century classroom | DSA Inspection | 24180.44 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-DSA Special Inspection | 4 | Sunset | 21st Century classroom | DSA Special Inspection | 12090.22 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-Environ Consultant | 4 | Sunset | 21st Century classroom | Environ Consultant | 7092.93 | No Proposal Provided | 2700 | 0 | 2700 | 100%
Sunset-21st Century classroom-FF & E | 4 | Sunset | 21st Century classroom | FF & E | 240000 | No Proposal Provided | 20720.61 | 0 | 20720.61 | 100%
Sunset-21st Century classroom-Legal Services | 4 | Sunset | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-Move classroom | 4 | Sunset | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-Move Management | 4 | Sunset | 21st Century classroom | Move Management | 6448.12 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-Reprographics | 4 | Sunset | 21st Century classroom | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-21st Century classroom-Technology | 4 | Sunset | 21st Century classroom | Technology | 240000 | No Proposal Provided | 108157.36 | 0 | 108157.36 | 100%
Sunset-Ceiling replacement-CM/PM Management | 4 | Sunset | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Ceiling replacement-Contractor | 4 | Sunset | Ceiling replacement | Contractor | 242880 | 242880 | 242880 | 0 | 242880 | 100%
Sunset-Drinking Fountain replacement-Advertisement | 4 | Sunset | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking Fountain replacement-Contractor | 4 | Sunset | Drinking Fountain replacement | Contractor | 15000 | No Proposal Provided | 22800 | 0 | 22800 | 100%
Sunset-Drinking Fountain replacement-Design | 4 | Sunset | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking Fountain replacement-DSA Fees | 4 | Sunset | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking Fountain replacement-DSA Inspection | 4 | Sunset | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking Fountain replacement-DSA Special Inspection | 4 | Sunset | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking Fountain replacement-Environ Consultant | 4 | Sunset | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Drinking Fountain replacement-Reprographics | 4 | Sunset | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm replacement-Advertisement | 4 | Sunset | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm replacement-Contractor | 4 | Sunset | Fire Alarm replacement | Contractor | 180000 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm replacement-Design | 4 | Sunset | Fire Alarm replacement | Design | 48500 | No Proposal Provided | 36375 | 0 | 36375 | 100%
Sunset-Fire Alarm replacement-DSA Fees | 4 | Sunset | Fire Alarm replacement | DSA Fees | 0 | 0 | 564 | 0 | 564 | 100%
Sunset-Fire Alarm replacement-DSA Inspection | 4 | Sunset | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm replacement-Environ Consultant | 4 | Sunset | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Fire Alarm replacement-Reprographics | 4 | Sunset | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Advertisement | 4 | Sunset | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Alarm | 4 | Sunset | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-CM/PM Management | 4 | Sunset | Interim Housing | CM/PM Management | 51650 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Construction Contingency | 4 | Sunset | Interim Housing | Construction Contingency | 77000 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Contractor | 4 | Sunset | Interim Housing | Contractor | 770000 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Design | 4 | Sunset | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-DSA Fees | 4 | Sunset | Interim Housing | DSA Fees | 16100 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-DSA Inspection | 4 | Sunset | Interim Housing | DSA Inspection | 13800 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-DSA Special Inspection | 4 | Sunset | Interim Housing | DSA Special Inspection | 13800 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Environ Consultant | 4 | Sunset | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-FF & E | 4 | Sunset | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Legal Services | 4 | Sunset | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Modular Buildings | 4 | Sunset | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Move Management | 4 | Sunset | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Reprographics | 4 | Sunset | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Sunset-Interim Housing-Technology | 4 | Sunset | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Advertisement | 8 | Temple | 21st Century classroom | Advertisement | 1347.71 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Asbestos oversight/survey/abatement | 8 | Temple | 21st Century classroom | Asbestos oversight/survey/abatement | 66500 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-CM/PM Management | 8 | Temple | 21st Century classroom | CM/PM Management | 214065.56 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Construction Contingency | 8 | Temple | 21st Century classroom | Construction Contingency | 210026.6 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Contractor | 8 | Temple | 21st Century classroom | Contractor | 2240353.74 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Design | 8 | Temple | 21st Century classroom | Design | 257289.94 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-DSA Fees | 8 | Temple | 21st Century classroom | DSA Fees | 42881.66 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-DSA Inspection | 8 | Temple | 21st Century classroom | DSA Inspection | 36755.71 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-DSA Special Inspection | 8 | Temple | 21st Century classroom | DSA Special Inspection | 18377.85 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Environ Consultant | 8 | Temple | 21st Century classroom | Environ Consultant | 13477.09 | No Proposal Provided | 2600 | 0 | 2600 | 100%
Temple-21st Century classroom-FF & E | 8 | Temple | 21st Century classroom | FF & E | 380000 | No Proposal Provided | 20720.61 | 0 | 20720.61 | 100%
Temple-21st Century classroom-Legal Services | 8 | Temple | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Move classroom | 8 | Temple | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Move Management | 8 | Temple | 21st Century classroom | Move Management | 9801.52 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Reprographics | 8 | Temple | 21st Century classroom | Reprographics | 1347.71 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-21st Century classroom-Technology | 8 | Temple | 21st Century classroom | Technology | 380000 | No Proposal Provided | 111520.57 | 0 | 111520.57 | 100%
Temple-Ceiling replacement-CM/PM Management | 8 | Temple | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Ceiling replacement-Contractor | 8 | Temple | Ceiling replacement | Contractor | 0 | 0 | 258091 | 0 | 258091 | 100%
Temple-Drinking Fountain replacement-Advertisement | 8 | Temple | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking Fountain replacement-Contractor | 8 | Temple | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-Drinking Fountain replacement-Design | 8 | Temple | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking Fountain replacement-DSA Fees | 8 | Temple | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking Fountain replacement-DSA Inspection | 8 | Temple | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking Fountain replacement-DSA Special Inspection | 8 | Temple | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking Fountain replacement-Environ Consultant | 8 | Temple | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Drinking Fountain replacement-Reprographics | 8 | Temple | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm replacement-Advertisement | 8 | Temple | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm replacement-Contractor | 8 | Temple | Fire Alarm replacement | Contractor | 285000 | N/A | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm replacement-Design | 8 | Temple | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm replacement-DSA Fees | 8 | Temple | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm replacement-DSA Inspection | 8 | Temple | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm replacement-Environ Consultant | 8 | Temple | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Fire Alarm replacement-Reprographics | 8 | Temple | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Advertisement | 8 | Temple | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Alarm | 8 | Temple | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-CM/PM Management | 8 | Temple | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Construction Contingency | 8 | Temple | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Contractor | 8 | Temple | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Design | 8 | Temple | Interim Housing | Design | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-DSA Fees | 8 | Temple | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-DSA Inspection | 8 | Temple | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-DSA Special Inspection | 8 | Temple | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Environ Consultant | 8 | Temple | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-FF & E | 8 | Temple | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Legal Services | 8 | Temple | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Modular Buildings | 8 | Temple | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Move Management | 8 | Temple | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Reprographics | 8 | Temple | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Temple-Interim Housing-Technology | 8 | Temple | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Advertisement | 6 | Valinda | 21st Century classroom | Advertisement | 2198.02 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Asbestos oversight/survey/abatement | 6 | Valinda | 21st Century classroom | Asbestos oversight/survey/abatement | 108500 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-CM/PM Management | 6 | Valinda | 21st Century classroom | CM/PM Management | 349157.78 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Construction Contingency | 6 | Valinda | 21st Century classroom | Construction Contingency | 342538.4 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Contractor | 6 | Valinda | 21st Century classroom | Contractor | 3653857.11 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Design | 6 | Valinda | 21st Century classroom | Design | 419621.53 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-DSA Fees | 6 | Valinda | 21st Century classroom | DSA Fees | 69936.92 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-DSA Inspection | 6 | Valinda | 21st Century classroom | DSA Inspection | 59945.93 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-DSA Special Inspection | 6 | Valinda | 21st Century classroom | DSA Special Inspection | 29972.97 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Environ Consultant | 6 | Valinda | 21st Century classroom | Environ Consultant | 17584.14 | No Proposal Provided | 3000 | 0 | 3000 | 100%
Valinda-21st Century classroom-FF & E | 6 | Valinda | 21st Century classroom | FF & E | 620000 | No Proposal Provided | 22185.39 | 0 | 22185.39 | 100%
Valinda-21st Century classroom-Legal Services | 6 | Valinda | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Move classroom | 6 | Valinda | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Move Management | 6 | Valinda | 21st Century classroom | Move Management | 15985.58 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Reprographics | 6 | Valinda | 21st Century classroom | Reprographics | 2198.02 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-21st Century classroom-Technology | 6 | Valinda | 21st Century classroom | Technology | 620000 | No Proposal Provided | 262009.2 | 0 | 262009.2 | 100%
Valinda-Ceiling replacement-CM/PM Management | 6 | Valinda | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Ceiling replacement-Contractor | 6 | Valinda | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking Fountain replacement-Advertisement | 6 | Valinda | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking Fountain replacement-Contractor | 6 | Valinda | Drinking Fountain replacement | Contractor | 30000 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking Fountain replacement-Design | 6 | Valinda | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking Fountain replacement-DSA Fees | 6 | Valinda | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking Fountain replacement-DSA Inspection | 6 | Valinda | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking Fountain replacement-DSA Special Inspection | 6 | Valinda | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking Fountain replacement-Environ Consultant | 6 | Valinda | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Drinking Fountain replacement-Reprographics | 6 | Valinda | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm replacement-Advertisement | 6 | Valinda | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm replacement-Contractor | 6 | Valinda | Fire Alarm replacement | Contractor | 465000 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm replacement-Design | 6 | Valinda | Fire Alarm replacement | Design | 12375 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm replacement-DSA Fees | 6 | Valinda | Fire Alarm replacement | DSA Fees | 0 | 0 | 1125 | 0 | 1125 | 100%
Valinda-Fire Alarm replacement-DSA Inspection | 6 | Valinda | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm replacement-Environ Consultant | 6 | Valinda | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Fire Alarm replacement-Reprographics | 6 | Valinda | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Advertisement | 6 | Valinda | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Alarm | 6 | Valinda | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-CM/PM Management | 6 | Valinda | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Construction Contingency | 6 | Valinda | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Contractor | 6 | Valinda | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Design | 6 | Valinda | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-DSA Fees | 6 | Valinda | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-DSA Inspection | 6 | Valinda | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-DSA Special Inspection | 6 | Valinda | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Environ Consultant | 6 | Valinda | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-FF & E | 6 | Valinda | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Legal Services | 6 | Valinda | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Modular Buildings | 6 | Valinda | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Move Management | 6 | Valinda | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Reprographics | 6 | Valinda | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Valinda-Interim Housing-Technology | 6 | Valinda | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Advertisement | 8 | Valley | 21st Century classroom | Advertisement | 894.83 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Asbestos oversight/survey/abatement | 8 | Valley | 21st Century classroom | Asbestos oversight/survey/abatement | 42000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-CM/PM Management | 8 | Valley | 21st Century classroom | CM/PM Management | 140531.3 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Construction Contingency | 8 | Valley | 21st Century classroom | Construction Contingency | 139449.2 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Contractor | 8 | Valley | 21st Century classroom | Contractor | 1487504.62 | N/A | 19116.72 | 0 | 19116.72 | 100%
Valley-21st Century classroom-Design | 8 | Valley | 21st Century classroom | Design | 170830.15 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-DSA Fees | 8 | Valley | 21st Century classroom | DSA Fees | 28471.69 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-DSA Inspection | 8 | Valley | 21st Century classroom | DSA Inspection | 24404.31 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-DSA Special Inspection | 8 | Valley | 21st Century classroom | DSA Special Inspection | 12202.15 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Environ Consultant | 8 | Valley | 21st Century classroom | Environ Consultant | 8948.25 | No Proposal Provided | 2700 | 0 | 2700 | 100%
Valley-21st Century classroom-FF & E | 8 | Valley | 21st Century classroom | FF & E | 240000 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Legal Services | 8 | Valley | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Move classroom | 8 | Valley | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Move Management | 8 | Valley | 21st Century classroom | Move Management | 6507.82 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Reprographics | 8 | Valley | 21st Century classroom | Reprographics | 894.83 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-21st Century classroom-Technology | 8 | Valley | 21st Century classroom | Technology | 240000 | 0 | 87145.31 | 0 | 87145.31 | 100%
Valley-Ceiling replacement-CM/PM Management | 8 | Valley | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Ceiling replacement-Contractor | 8 | Valley | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking Fountain replacement-Advertisement | 8 | Valley | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking Fountain replacement-Contractor | 8 | Valley | Drinking Fountain replacement | Contractor | 15000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Drinking Fountain replacement-Design | 8 | Valley | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking Fountain replacement-DSA Fees | 8 | Valley | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking Fountain replacement-DSA Inspection | 8 | Valley | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking Fountain replacement-DSA Special Inspection | 8 | Valley | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking Fountain replacement-Environ Consultant | 8 | Valley | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Drinking Fountain replacement-Reprographics | 8 | Valley | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Fire Alarm replacement-Advertisement | 8 | Valley | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Fire Alarm replacement-Contractor | 8 | Valley | Fire Alarm replacement | Contractor | 216000 | 217149.4 | 231990.92 | 0 | 231990.92 | 100%
Valley-Fire Alarm replacement-Design | 8 | Valley | Fire Alarm replacement | Design | 11375 | No Proposal Provided | 11375 | 0 | 11375 | 100%
Valley-Fire Alarm replacement-DSA Fees | 8 | Valley | Fire Alarm replacement | DSA Fees | 630 | No Proposal Provided | 1328.75 | 0 | 1328.75 | 100%
Valley-Fire Alarm replacement-DSA Inspection | 8 | Valley | Fire Alarm replacement | DSA Inspection | 7350 | No Proposal Provided | 7350 | 0 | 7350 | 100%
Valley-Fire Alarm replacement-Environ Consultant | 8 | Valley | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Fire Alarm replacement-Reprographics | 8 | Valley | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Advertisement | 8 | Valley | Interim Housing | Advertisement | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Alarm | 8 | Valley | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-CM/PM Management | 8 | Valley | Interim Housing | CM/PM Management | 43850 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Construction Contingency | 8 | Valley | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Contractor | 8 | Valley | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Design | 8 | Valley | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-DSA Fees | 8 | Valley | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-DSA Inspection | 8 | Valley | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-DSA Special Inspection | 8 | Valley | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Environ Consultant | 8 | Valley | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-FF & E | 8 | Valley | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Legal Services | 8 | Valley | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Modular Buildings | 8 | Valley | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Move Management | 8 | Valley | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Reprographics | 8 | Valley | Interim Housing | Reprographics | 400 | N/A | 0 | 0 | 0 | #DIV/0!
Valley-Interim Housing-Technology | 8 | Valley | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Advertisement | 0 | Wedgeworth | 21st Century classroom | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Asbestos oversight/survey/abatement | 0 | Wedgeworth | 21st Century classroom | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-CM/PM Management | 0 | Wedgeworth | 21st Century classroom | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Construction Contingency | 0 | Wedgeworth | 21st Century classroom | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Contractor | 0 | Wedgeworth | 21st Century classroom | Contractor | 0 | 0 | 12744.48 | 0 | 12744.48 | 100%
Wedgeworth-21st Century classroom-Design | 0 | Wedgeworth | 21st Century classroom | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-DSA Fees | 0 | Wedgeworth | 21st Century classroom | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-DSA Inspection | 0 | Wedgeworth | 21st Century classroom | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-DSA Special Inspection | 0 | Wedgeworth | 21st Century classroom | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Environ Consultant | 0 | Wedgeworth | 21st Century classroom | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-FF & E | 0 | Wedgeworth | 21st Century classroom | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Legal Services | 0 | Wedgeworth | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Move classroom | 0 | Wedgeworth | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Move Management | 0 | Wedgeworth | 21st Century classroom | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Reprographics | 0 | Wedgeworth | 21st Century classroom | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-21st Century classroom-Technology | 0 | Wedgeworth | 21st Century classroom | Technology | 0 | 0 | 146165.5 | 0 | 146165.5 | 100%
Wedgeworth-Ceiling replacement-CM/PM Management | 0 | Wedgeworth | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Ceiling replacement-Contractor | 0 | Wedgeworth | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking Fountain replacement-Advertisement | 0 | Wedgeworth | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking Fountain replacement-Contractor | 0 | Wedgeworth | Drinking Fountain replacement | Contractor | 0 | 0 | 3502.75 | 0 | 3502.75 | 100%
Wedgeworth-Drinking Fountain replacement-Design | 0 | Wedgeworth | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking Fountain replacement-DSA Fees | 0 | Wedgeworth | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking Fountain replacement-DSA Inspection | 0 | Wedgeworth | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking Fountain replacement-DSA Special Inspection | 0 | Wedgeworth | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking Fountain replacement-Environ Consultant | 0 | Wedgeworth | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Drinking Fountain replacement-Reprographics | 0 | Wedgeworth | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm replacement-Advertisement | 0 | Wedgeworth | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm replacement-Contractor | 0 | Wedgeworth | Fire Alarm replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm replacement-Design | 0 | Wedgeworth | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm replacement-DSA Fees | 0 | Wedgeworth | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm replacement-DSA Inspection | 0 | Wedgeworth | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm replacement-Environ Consultant | 0 | Wedgeworth | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Fire Alarm replacement-Reprographics | 0 | Wedgeworth | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Advertisement | 0 | Wedgeworth | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Alarm | 0 | Wedgeworth | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-CM/PM Management | 0 | Wedgeworth | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Construction Contingency | 0 | Wedgeworth | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Contractor | 0 | Wedgeworth | Interim Housing | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Design | 0 | Wedgeworth | Interim Housing | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-DSA Fees | 0 | Wedgeworth | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-DSA Inspection | 0 | Wedgeworth | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-DSA Special Inspection | 0 | Wedgeworth | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Environ Consultant | 0 | Wedgeworth | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-FF & E | 0 | Wedgeworth | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Legal Services | 0 | Wedgeworth | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Modular Buildings | 0 | Wedgeworth | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Move Management | 0 | Wedgeworth | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Reprographics | 0 | Wedgeworth | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wedgeworth-Interim Housing-Technology | 0 | Wedgeworth | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Advertisement | 0 | Willow | 21st Century classroom | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Asbestos oversight/survey/abatement | 0 | Willow | 21st Century classroom | Asbestos oversight/survey/abatement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-CM/PM Management | 0 | Willow | 21st Century classroom | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Construction Contingency | 0 | Willow | 21st Century classroom | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Contractor | 0 | Willow | 21st Century classroom | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Design | 0 | Willow | 21st Century classroom | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-DSA Fees | 0 | Willow | 21st Century classroom | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-DSA Inspection | 0 | Willow | 21st Century classroom | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-DSA Special Inspection | 0 | Willow | 21st Century classroom | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Environ Consultant | 0 | Willow | 21st Century classroom | Environ Consultant | 0 | 0 | 2700 | 0 | 2700 | 100%
Willow-21st Century classroom-FF & E | 0 | Willow | 21st Century classroom | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Legal Services | 0 | Willow | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Move classroom | 0 | Willow | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Move Management | 0 | Willow | 21st Century classroom | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Reprographics | 0 | Willow | 21st Century classroom | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-21st Century classroom-Technology | 0 | Willow | 21st Century classroom | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Ceiling replacement-CM/PM Management | 0 | Willow | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Ceiling replacement-Contractor | 0 | Willow | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking Fountain replacement-Advertisement | 0 | Willow | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking Fountain replacement-Contractor | 0 | Willow | Drinking Fountain replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking Fountain replacement-Design | 0 | Willow | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking Fountain replacement-DSA Fees | 0 | Willow | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking Fountain replacement-DSA Inspection | 0 | Willow | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking Fountain replacement-DSA Special Inspection | 0 | Willow | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking Fountain replacement-Environ Consultant | 0 | Willow | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Drinking Fountain replacement-Reprographics | 0 | Willow | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm replacement-Advertisement | 0 | Willow | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm replacement-Contractor | 0 | Willow | Fire Alarm replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm replacement-Design | 0 | Willow | Fire Alarm replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm replacement-DSA Fees | 0 | Willow | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm replacement-DSA Inspection | 0 | Willow | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm replacement-Environ Consultant | 0 | Willow | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Fire Alarm replacement-Reprographics | 0 | Willow | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Advertisement | 0 | Willow | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Alarm | 0 | Willow | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-CM/PM Management | 0 | Willow | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Construction Contingency | 0 | Willow | Interim Housing | Construction Contingency | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Contractor | 0 | Willow | Interim Housing | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Design | 0 | Willow | Interim Housing | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-DSA Fees | 0 | Willow | Interim Housing | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-DSA Inspection | 0 | Willow | Interim Housing | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-DSA Special Inspection | 0 | Willow | Interim Housing | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Environ Consultant | 0 | Willow | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-FF & E | 0 | Willow | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Legal Services | 0 | Willow | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Modular Buildings | 0 | Willow | Interim Housing | Modular Buildings | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Move Management | 0 | Willow | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Reprographics | 0 | Willow | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Willow-Interim Housing-Technology | 0 | Willow | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-Advertisement | 5 | Wilson HS | 21st Century classroom | Advertisement | 5225.48 | N/A | 292.31 | 292.31 | 0 | 0%
Wilson HS-21st Century classroom-Asbestos oversight/survey/abatement | 5 | Wilson HS | 21st Century classroom | Asbestos oversight/survey/abatement | 231000 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-CM/PM Management | 5 | Wilson HS | 21st Century classroom | CM/PM Management | 810058.76 | N/A | 171400 | 156755 | 14645 | 8.544%
Wilson HS-21st Century classroom-Construction Contingency | 5 | Wilson HS | 21st Century classroom | Construction Contingency | 814337.4 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-Contractor | 5 | Wilson HS | 21st Century classroom | Contractor | 8686537.05 | No Proposal Provided | 19116.72 | 0 | 19116.72 | 100%
Wilson HS-21st Century classroom-Design | 5 | Wilson HS | 21st Century classroom | Design | 997591.82 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-DSA Fees | 5 | Wilson HS | 21st Century classroom | DSA Fees | 166265.3 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-DSA Inspection | 5 | Wilson HS | 21st Century classroom | DSA Inspection | 142513.12 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-DSA Special Inspection | 5 | Wilson HS | 21st Century classroom | DSA Special Inspection | 71256.56 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-Environ Consultant | 5 | Wilson HS | 21st Century classroom | Environ Consultant | 52254.81 | N/A | 3400 | 0 | 3400 | 100%
Wilson HS-21st Century classroom-FF & E | 5 | Wilson HS | 21st Century classroom | FF & E | 1320000 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-Legal Services | 5 | Wilson HS | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-Move classroom | 5 | Wilson HS | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-Move Management | 5 | Wilson HS | 21st Century classroom | Move Management | 38003.5 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-Reprographics | 5 | Wilson HS | 21st Century classroom | Reprographics | 5225.48 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-21st Century classroom-Technology | 5 | Wilson HS | 21st Century classroom | Technology | 1320000 | N/A | 671830.97 | 0 | 671830.97 | 100%
Wilson HS-Ceiling replacement-CM/PM Management | 5 | Wilson HS | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Ceiling replacement-Contractor | 5 | Wilson HS | Ceiling replacement | Contractor | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking Fountain replacement-Advertisement | 5 | Wilson HS | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking Fountain replacement-Contractor | 5 | Wilson HS | Drinking Fountain replacement | Contractor | 60000 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking Fountain replacement-Design | 5 | Wilson HS | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking Fountain replacement-DSA Fees | 5 | Wilson HS | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking Fountain replacement-DSA Inspection | 5 | Wilson HS | Drinking Fountain replacement | DSA Inspection | 1200 | No Proposal Provided | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking Fountain replacement-DSA Special Inspection | 5 | Wilson HS | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking Fountain replacement-Environ Consultant | 5 | Wilson HS | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Drinking Fountain replacement-Reprographics | 5 | Wilson HS | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Fire Alarm replacement-Advertisement | 5 | Wilson HS | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Fire Alarm replacement-Contractor | 5 | Wilson HS | Fire Alarm replacement | Contractor | 1188000 | 291000 | 282060.18 | 0 | 282060.18 | 100%
Wilson HS-Fire Alarm replacement-Design | 5 | Wilson HS | Fire Alarm replacement | Design | 0 | 0 | 6825 | 0 | 6825 | 100%
Wilson HS-Fire Alarm replacement-DSA Fees | 5 | Wilson HS | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Fire Alarm replacement-DSA Inspection | 5 | Wilson HS | Fire Alarm replacement | DSA Inspection | 16500 | No Proposal Provided | 16500 | 0 | 16500 | 100%
Wilson HS-Fire Alarm replacement-Environ Consultant | 5 | Wilson HS | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Fire Alarm replacement-Reprographics | 5 | Wilson HS | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Advertisement | 5 | Wilson HS | Interim Housing | Advertisement | 1000 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Alarm | 5 | Wilson HS | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-CM/PM Management | 5 | Wilson HS | Interim Housing | CM/PM Management | 55275 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Construction Contingency | 5 | Wilson HS | Interim Housing | Construction Contingency | 82500 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Contractor | 5 | Wilson HS | Interim Housing | Contractor | 825000 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Design | 5 | Wilson HS | Interim Housing | Design | 82500 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-DSA Fees | 5 | Wilson HS | Interim Housing | DSA Fees | 14437.5 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-DSA Inspection | 5 | Wilson HS | Interim Housing | DSA Inspection | 15750 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-DSA Special Inspection | 5 | Wilson HS | Interim Housing | DSA Special Inspection | 15750 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Environ Consultant | 5 | Wilson HS | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-FF & E | 5 | Wilson HS | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Legal Services | 5 | Wilson HS | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Modular Buildings | 5 | Wilson HS | Interim Housing | Modular Buildings | 225000 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Move Management | 5 | Wilson HS | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Reprographics | 5 | Wilson HS | Interim Housing | Reprographics | 1000 | N/A | 0 | 0 | 0 | #DIV/0!
Wilson HS-Interim Housing-Technology | 5 | Wilson HS | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Advertisement | 9 | Wing Lane | 21st Century classroom | Advertisement | 1482.47 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Asbestos oversight/survey/abatement | 9 | Wing Lane | 21st Century classroom | Asbestos oversight/survey/abatement | 73500 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-CM/PM Management | 9 | Wing Lane | 21st Century classroom | CM/PM Management | 235730.26 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Construction Contingency | 9 | Wing Lane | 21st Century classroom | Construction Contingency | 231026.9 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Contractor | 9 | Wing Lane | 21st Century classroom | Contractor | 2464363.94 | N/A | 40000 | 0 | 40000 | 100%
Wing Lane-21st Century classroom-Design | 9 | Wing Lane | 21st Century classroom | Design | 283016.04 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-DSA Fees | 9 | Wing Lane | 21st Century classroom | DSA Fees | 47169.34 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-DSA Inspection | 9 | Wing Lane | 21st Century classroom | DSA Inspection | 40430.86 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-DSA Special Inspection | 9 | Wing Lane | 21st Century classroom | DSA Special Inspection | 20215.43 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Environ Consultant | 9 | Wing Lane | 21st Century classroom | Environ Consultant | 11859.72 | N/A | 2600 | 0 | 2600 | 100%
Wing Lane-21st Century classroom-FF & E | 9 | Wing Lane | 21st Century classroom | FF & E | 420000 | No Proposal Provided | 20720.61 | 0 | 20720.61 | 100%
Wing Lane-21st Century classroom-Legal Services | 9 | Wing Lane | 21st Century classroom | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Move classroom | 9 | Wing Lane | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Move Management | 9 | Wing Lane | 21st Century classroom | Move Management | 10781.56 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Reprographics | 9 | Wing Lane | 21st Century classroom | Reprographics | 1482.47 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-21st Century classroom-Technology | 9 | Wing Lane | 21st Century classroom | Technology | 420000 | No Proposal Provided | 110563.9 | 0 | 110563.9 | 100%
Wing Lane-Ceiling replacement-CM/PM Management | 9 | Wing Lane | Ceiling replacement | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Ceiling replacement-Contractor | 9 | Wing Lane | Ceiling replacement | Contractor | 302738 | 302738 | 302738 | 0 | 302738 | 100%
Wing Lane-Drinking Fountain replacement-Advertisement | 9 | Wing Lane | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking Fountain replacement-Contractor | 9 | Wing Lane | Drinking Fountain replacement | Contractor | 15000 | 0 | 6800 | 0 | 6800 | 100%
Wing Lane-Drinking Fountain replacement-Design | 9 | Wing Lane | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking Fountain replacement-DSA Fees | 9 | Wing Lane | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking Fountain replacement-DSA Inspection | 9 | Wing Lane | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking Fountain replacement-DSA Special Inspection | 9 | Wing Lane | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking Fountain replacement-Environ Consultant | 9 | Wing Lane | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Drinking Fountain replacement-Reprographics | 9 | Wing Lane | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm replacement-Advertisement | 9 | Wing Lane | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm replacement-Contractor | 9 | Wing Lane | Fire Alarm replacement | Contractor | 315000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm replacement-Design | 9 | Wing Lane | Fire Alarm replacement | Design | 48500 | No Proposal Provided | 36375 | 0 | 36375 | 100%
Wing Lane-Fire Alarm replacement-DSA Fees | 9 | Wing Lane | Fire Alarm replacement | DSA Fees | 0 | 0 | 870 | 0 | 870 | 100%
Wing Lane-Fire Alarm replacement-DSA Inspection | 9 | Wing Lane | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm replacement-Environ Consultant | 9 | Wing Lane | Fire Alarm replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Fire Alarm replacement-Reprographics | 9 | Wing Lane | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Advertisement | 9 | Wing Lane | Interim Housing | Advertisement | 1000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Alarm | 9 | Wing Lane | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-CM/PM Management | 9 | Wing Lane | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Construction Contingency | 9 | Wing Lane | Interim Housing | Construction Contingency | 55000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Contractor | 9 | Wing Lane | Interim Housing | Contractor | 550000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Design | 9 | Wing Lane | Interim Housing | Design | 80000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-DSA Fees | 9 | Wing Lane | Interim Housing | DSA Fees | 14000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-DSA Inspection | 9 | Wing Lane | Interim Housing | DSA Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-DSA Special Inspection | 9 | Wing Lane | Interim Housing | DSA Special Inspection | 12000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Environ Consultant | 9 | Wing Lane | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-FF & E | 9 | Wing Lane | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Legal Services | 9 | Wing Lane | Interim Housing | Legal Services | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Modular Buildings | 9 | Wing Lane | Interim Housing | Modular Buildings | 150000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Move Management | 9 | Wing Lane | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Reprographics | 9 | Wing Lane | Interim Housing | Reprographics | 1000 | N/A | 0 | 0 | 0 | #DIV/0!
Wing Lane-Interim Housing-Technology | 9 | Wing Lane | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century classroom-Advertisement | 2 | Workman ES | 21st Century classroom | Advertisement | 1328.8 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century classroom-Asbestos oversight/survey/abatement | 2 | Workman ES | 21st Century classroom | Asbestos oversight/survey/abatement | 66500 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century classroom-CM/PM Management | 2 | Workman ES | 21st Century classroom | CM/PM Management | 211755.44 | 169207 | 169123.75 | 0 | 169123.75 | 100%
Workman ES-21st Century classroom-Construction Contingency | 2 | Workman ES | 21st Century classroom | Construction Contingency | 207080.1 | 152162.3 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century classroom-Contractor | 2 | Workman ES | 21st Century classroom | Contractor | 2208923.43 | 1521623 | 1597777.27 | 0 | 1597777.27 | 100%
Workman ES-21st Century classroom-Design | 2 | Workman ES | 21st Century classroom | Design | 253680.37 | 138184 | 131605.75 | 0 | 131605.75 | 100%
Workman ES-21st Century classroom-DSA Fees | 2 | Workman ES | 21st Century classroom | DSA Fees | 42280.06 | 11750 | 24635.87 | 0 | 24635.87 | 100%
Workman ES-21st Century classroom-DSA Inspection | 2 | Workman ES | 21st Century classroom | DSA Inspection | 36240.05 | 0 | 25480 | 0 | 25480 | 100%
Workman ES-21st Century classroom-DSA Special Inspection | 2 | Workman ES | 21st Century classroom | DSA Special Inspection | 18120.03 | 0 | 507.5 | 0 | 507.5 | 100%
Workman ES-21st Century classroom-Environ Consultant | 2 | Workman ES | 21st Century classroom | Environ Consultant | 10630.42 | 0 | 11300 | 0 | 11300 | 100%
Workman ES-21st Century classroom-FF & E | 2 | Workman ES | 21st Century classroom | FF & E | 380000 | 209239.26 | 360386.91 | 0 | 360386.91 | 100%
Workman ES-21st Century classroom-Legal Services | 2 | Workman ES | 21st Century classroom | Legal Services | 5315.21 | 0 | 22.5 | 0 | 22.5 | 100%
Workman ES-21st Century classroom-Move classroom | 2 | Workman ES | 21st Century classroom | Move classroom | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-21st Century classroom-Move Management | 2 | Workman ES | 21st Century classroom | Move Management | 9664.01 | No Proposal Provided | 9416.09 | 0 | 9416.09 | 100%
Workman ES-21st Century classroom-Reprographics | 2 | Workman ES | 21st Century classroom | Reprographics | 1328.8 | 0 | 1980.22 | 0 | 1980.22 | 100%
Workman ES-21st Century classroom-Technology | 2 | Workman ES | 21st Century classroom | Technology | 380000 | 26216.56 | 223422.69 | 0 | 223422.69 | 100%
Workman ES-Ceiling replacement-CM/PM Management | 2 | Workman ES | Ceiling replacement | CM/PM Management | 206440.23 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Ceiling replacement-Contractor | 2 | Workman ES | Ceiling replacement | Contractor | 2428800 | 242880 | 242880 | 0 | 242880 | 100%
Workman ES-Drinking Fountain replacement-Advertisement | 2 | Workman ES | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking Fountain replacement-Contractor | 2 | Workman ES | Drinking Fountain replacement | Contractor | 12600 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking Fountain replacement-Design | 2 | Workman ES | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking Fountain replacement-DSA Fees | 2 | Workman ES | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking Fountain replacement-DSA Inspection | 2 | Workman ES | Drinking Fountain replacement | DSA Inspection | 1200 | 0 | 1200 | 0 | 1200 | 100%
Workman ES-Drinking Fountain replacement-DSA Special Inspection | 2 | Workman ES | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking Fountain replacement-Environ Consultant | 2 | Workman ES | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Drinking Fountain replacement-Reprographics | 2 | Workman ES | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Fire Alarm replacement-Advertisement | 2 | Workman ES | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Fire Alarm replacement-Contractor | 2 | Workman ES | Fire Alarm replacement | Contractor | 109500 | 109500 | 133767.01 | 0 | 133767.01 | 100%
Workman ES-Fire Alarm replacement-Design | 2 | Workman ES | Fire Alarm replacement | Design | 11875 | No Proposal Provided | 11875 | 0 | 11875 | 100%
Workman ES-Fire Alarm replacement-DSA Fees | 2 | Workman ES | Fire Alarm replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Fire Alarm replacement-DSA Inspection | 2 | Workman ES | Fire Alarm replacement | DSA Inspection | 12250 | 12250 | 12250 | 0 | 12250 | 100%
Workman ES-Fire Alarm replacement-Environ Consultant | 2 | Workman ES | Fire Alarm replacement | Environ Consultant | N/A | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Fire Alarm replacement-Reprographics | 2 | Workman ES | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Advertisement | 2 | Workman ES | Interim Housing | Advertisement | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Alarm | 2 | Workman ES | Interim Housing | Alarm | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-CM/PM Management | 2 | Workman ES | Interim Housing | CM/PM Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Construction Contingency | 2 | Workman ES | Interim Housing | Construction Contingency | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Contractor | 2 | Workman ES | Interim Housing | Contractor | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Design | 2 | Workman ES | Interim Housing | Design | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-DSA Fees | 2 | Workman ES | Interim Housing | DSA Fees | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-DSA Inspection | 2 | Workman ES | Interim Housing | DSA Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-DSA Special Inspection | 2 | Workman ES | Interim Housing | DSA Special Inspection | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Environ Consultant | 2 | Workman ES | Interim Housing | Environ Consultant | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-FF & E | 2 | Workman ES | Interim Housing | FF & E | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Legal Services | 2 | Workman ES | Interim Housing | Legal Services | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Modular Buildings | 2 | Workman ES | Interim Housing | Modular Buildings | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Move Management | 2 | Workman ES | Interim Housing | Move Management | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Reprographics | 2 | Workman ES | Interim Housing | Reprographics | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman ES-Interim Housing-Technology | 2 | Workman ES | Interim Housing | Technology | No IH Required | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-Advertisement | 5 | Workman HS | 21st Century classroom | Advertisement | 9515.36 | 0 | 417.06 | 417.06 | 0 | 0%
Workman HS-21st Century classroom-Asbestos oversight/survey/abatement | 5 | Workman HS | 21st Century classroom | Asbestos oversight/survey/abatement | 206500 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-CM/PM Management | 5 | Workman HS | 21st Century classroom | CM/PM Management | 715671.39 | 0 | 171400 | 67020 | 104380 | 60.9%
Workman HS-21st Century classroom-Construction Contingency | 5 | Workman HS | 21st Century classroom | Construction Contingency | 741435.6 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-Contractor | 5 | Workman HS | 21st Century classroom | Contractor | 7414356 | 0 | 2137350.16 | 2080000 | 57350.16 | 2.683%
Workman HS-21st Century classroom-Design | 5 | Workman HS | 21st Century classroom | Design | 908284.56 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-DSA Fees | 5 | Workman HS | 21st Century classroom | DSA Fees | 151380.76 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-DSA Inspection | 5 | Workman HS | 21st Century classroom | DSA Inspection | 129754.94 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-DSA Special Inspection | 5 | Workman HS | 21st Century classroom | DSA Special Inspection | 64877.47 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-Environ Consultant | 5 | Workman HS | 21st Century classroom | Environ Consultant | 38061.45 | 0 | 7650 | 3500 | 4150 | 54.25%
Workman HS-21st Century classroom-FF & E | 5 | Workman HS | 21st Century classroom | FF & E | 1180000 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-Legal Services | 5 | Workman HS | 21st Century classroom | Legal Services | 19030.72 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-Move classroom | 5 | Workman HS | 21st Century classroom | Move classroom | 0 | 0 | 1420.32 | 1420.32 | 0 | 0%
Workman HS-21st Century classroom-Move Management | 5 | Workman HS | 21st Century classroom | Move Management | 34601.32 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-21st Century classroom-Reprographics | 5 | Workman HS | 21st Century classroom | Reprographics | 9515.36 | 0 | 126.62 | 0 | 126.62 | 100%
Workman HS-21st Century classroom-Technology | 5 | Workman HS | 21st Century classroom | Technology | 1180000 | 0 | 499638.02 | 0 | 499638.02 | 100%
Workman HS-Ceiling replacement-CM/PM Management | 5 | Workman HS | Ceiling replacement | CM/PM Management | no scope | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Ceiling replacement-Contractor | 5 | Workman HS | Ceiling replacement | Contractor | no scope | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking Fountain replacement-Advertisement | 5 | Workman HS | Drinking Fountain replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking Fountain replacement-Contractor | 5 | Workman HS | Drinking Fountain replacement | Contractor | 48000 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking Fountain replacement-Design | 5 | Workman HS | Drinking Fountain replacement | Design | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking Fountain replacement-DSA Fees | 5 | Workman HS | Drinking Fountain replacement | DSA Fees | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking Fountain replacement-DSA Inspection | 5 | Workman HS | Drinking Fountain replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking Fountain replacement-DSA Special Inspection | 5 | Workman HS | Drinking Fountain replacement | DSA Special Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking Fountain replacement-Environ Consultant | 5 | Workman HS | Drinking Fountain replacement | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Drinking Fountain replacement-Reprographics | 5 | Workman HS | Drinking Fountain replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm replacement-Advertisement | 5 | Workman HS | Fire Alarm replacement | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm replacement-Contractor | 5 | Workman HS | Fire Alarm replacement | Contractor | 1062000 | 300000 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm replacement-Design | 5 | Workman HS | Fire Alarm replacement | Design | 68600 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm replacement-DSA Fees | 5 | Workman HS | Fire Alarm replacement | DSA Fees | 18585 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm replacement-DSA Inspection | 5 | Workman HS | Fire Alarm replacement | DSA Inspection | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm replacement-Environ Consultant | 5 | Workman HS | Fire Alarm replacement | Environ Consultant | 0 | N/A | 0 | 0 | 0 | #DIV/0!
Workman HS-Fire Alarm replacement-Reprographics | 5 | Workman HS | Fire Alarm replacement | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Advertisement | 5 | Workman HS | Interim Housing | Advertisement | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Alarm | 5 | Workman HS | Interim Housing | Alarm | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-CM/PM Management | 5 | Workman HS | Interim Housing | CM/PM Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Construction Contingency | 5 | Workman HS | Interim Housing | Construction Contingency | 82500 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Contractor | 5 | Workman HS | Interim Housing | Contractor | 825000 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Design | 5 | Workman HS | Interim Housing | Design | 82500 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-DSA Fees | 5 | Workman HS | Interim Housing | DSA Fees | 14437.5 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-DSA Inspection | 5 | Workman HS | Interim Housing | DSA Inspection | 15750 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-DSA Special Inspection | 5 | Workman HS | Interim Housing | DSA Special Inspection | 15750 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Environ Consultant | 5 | Workman HS | Interim Housing | Environ Consultant | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-FF & E | 5 | Workman HS | Interim Housing | FF & E | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Legal Services | 5 | Workman HS | Interim Housing | Legal Services | 1650 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Modular Buildings | 5 | Workman HS | Interim Housing | Modular Buildings | 225000 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Move Management | 5 | Workman HS | Interim Housing | Move Management | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Reprographics | 5 | Workman HS | Interim Housing | Reprographics | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Workman HS-Interim Housing-Technology | 5 | Workman HS | Interim Housing | Technology | 0 | 0 | 0 | 0 | 0 | #DIV/0!
|  |  |  | Total: | 146521367.76 | 28812221.72 | 62120758.45 | 9428640.3 | 52692118.15
Note on E1: Nety Con: Per Dan Franco @ Cumming
Note on F1: Nety Con: Data from Dan Franco & Jessica Morley @ Cumming updated as of: 10/08/21
Note on G1: Nety Con: Data from Dan Franco & Jessica Morley @ Cumming updated as of: 10/08/21

## Comparison_P & Chart
MEASURE BB
Project | Preliminary Budget | Proposed Budget | Total Exp. & Committed | Completed Amount | Category | Preliminary Budget | Proposed Budget | Total Exp. & Committed | Completed Amount |  | Category | Total Exp. & Committed | Completed Amount
21st Century classroom | 177333135.47 | 19677470.97 | 49447947.92 | 40033315.92 | Advertisement | 74642.95 | 0 | 5920.74 | 4209.69 |  | Utilities | 1072 | 1072
Ceiling replacement | 6426085.23 | 4033905 | 4573414 | 4573414 | Alarm | 3898 | 0 | 874.5 | 874.5 |  | Technology | 9729295.98 | 9729295.98
Cost of Issuance | 1572741.59 | 0 | 465831.97 | 465831.97 | Asbestos oversight/survey/abatement | 2901207.24 | 12480 | 0 | 0 |  | Reprographics | 25759.99 | 15161.58
Design guidelines | 29500 | 29500 | 29500 | 24000 | CM/PM Management | 10909889.37 | 1742449 | 5494643.75 | 3253965 |  | Move Management | 81913.4 | 60045.95
Drinking Fountain replacement | 782200 | 24200 | 69702.75 | 69702.75 | Construction Contingency | 11261001.45 | 843362.3 | 0 | 0 |  | Move classroom | 8198.01 | 5357.37
Fire Alarm replacement | 13626510 | 4491539.03 | 2935049.24 | 2935049.24 | Contractor | 137944881.2 | 22495924.34 | 34599513.16 | 29381602.73 |  | Modular Buildings | 1196114.7 | 1196114.7
Interim Housing | 26246941.98 | 3817891.9 | 4599312.57 | 4590804.27 | Design | 14294886.36 | 3236461.69 | 4407908.97 | 2811218.2 |  | Legal Services | 367716.44 | 105578.65
Total: | 226017114.27 | 32074506.9 | 62120758.45 | 52692118.15 | DSA Fees | 2118169.18 | 82681.7 | 394264.98 | 394264.98 |  | Issuance costs | 465831.97 | 465831.97
[5 empty] | DSA Inspection | 2131082.83 | 288598 | 663579 | 639269 |  | FF & E | 4358643.36 | 4358141.85
| 999999999 |  |  |  | DSA Special Inspection | 1163678.71 | 57340 | 55562.5 | 54369 |  | Environ Consultant | 263945 | 215745
[5 empty] | Environ Consultant | 491240.05 | 13900 | 263945 | 215745 |  | DSA Special Inspection | 55562.5 | 54369
[5 empty] | FF & E | 17705687.26 | 2320774.65 | 4358643.36 | 4358141.85 |  | DSA Inspection | 663579 | 639269
[5 empty] | Issuance costs | 1572741.59 | 0 | 465831.97 | 465831.97 |  | DSA Fees | 394264.98 | 394264.98
[5 empty] | Legal Services | 800384.07 | 0 | 367716.44 | 105578.65 |  | Design | 4407908.97 | 2811218.2
[5 empty] | Modular Buildings | 4496285.7 | 716708.22 | 1196114.7 | 1196114.7 |  | Contractor | 34599513.16 | 29381602.73
[5 empty] | Move classroom | 146130.33 | 0 | 8198.01 | 5357.37 |  | Construction Contingency | 0 | 0
[5 empty] | Move Management | 391756.6 | 0 | 81913.4 | 60045.95 |  | CM/PM Management | 5494643.75 | 3253965
[5 empty] | Reprographics | 84654.04 | 1661.08 | 25759.99 | 15161.58 |  | Asbestos oversight/survey/abatement | 0 | 0
[5 empty] | Technology | 17524897.34 | 262165.92 | 9729295.98 | 9729295.98 |  | Alarm | 874.5 | 874.5
[5 empty] | Utilities | 0 | 0 | 1072 | 1072 |  | Advertisement | 5920.74 | 4209.69
[5 empty] | Total: | 226017114.27 | 32074506.9 | 62120758.45 | 52692118.15 | FF & E: Furniture, Fixtures, & Equipment | Total: | 62120758.45 | 52692118.15
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.