## Sheet1
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Week 1 | Email Staff Notification from SMART; Pre-Implementation Survey Available Online |  |  | Confirm all equipment is delivered: sign holders, landfill buckets
Week 2 |  | Parent Notification Sent Home; Include article in parent newsletter |  |  | Pre-Implementation Surveys Completed
Week 3 | Place SMART Container in visible area; "Are you ready to compost?" and "Compost is coming!" signs; Distribute teacher educational resources | Begin Student Monitoring for Signage Project | Students tip their own trays if they are not already |  | Complete Student monitoring
Week 4 | Begin Signage Project; Post Waste Items lists in Cafeteria; Begin Trash Log | Trash Log; Incorporate Recycling container into waste station | Trash Log | Begin practicing with Landfill Buckets; Complete Student Signs, Place in cafeteria (not to be used yet); Trash Log | Practice with buckets; Trash Log
Week 5 | Practice with buckets; Trash Log | Practice with buckets; Trash Log | STUDENT WASTE DIVERSION! Students begin separating.; Trash Log | Trash Log | Trash Log | Post Implementation Survey to be given between 3 and 5 weeks after student diversion begins in cafeteria.
| Trash Log | Trash Log | Trash Log | Trash Log | Trash Log