## 18-19
Strategic Plan Monitoring Tool (Year 1)
Crabapple Crossing Elementary School 2018-2019
Student Achievement |  | Outcome | Baseline (Yr. 1) | Evidence of Progress | Date | Results
Initiatves | Balanced Literacy Framework Implement literacy instruction that includes a progression of teacher modeling, guided practice, and student independent learning | 3rd Grade English Language Arts 85% of 3rd grade students will score at proficient and distinguished levels in ELA | 76% | Students are showing growth in F & P levels + Carryover of strategies and skills from professional development into classrooms | Spring 2019 GMAS | 82%
|  | Student Growth 85% of 5th grade students will demonstrate typical to high growth in ELA | 56% | Analyzing past years Milestones data to determine areas of strength and weakness. An increase in targeted instruction has been observed. | Spring 2019 GMAS | 55%
People & Culture |  | Outcome | Baseline (Yr. 1) | Evidence of Progress | Date | Results
Initiaties | Stakeholder Connections Increase engagement with families via technology and face to face interactions | School and District Culture Increase the percentage of families and students who would recommend Crabapple Crossing Elementary School as a place to attend school to a family member or friend | No baseline data | Approx. 1000 people attended International Night + Increased attendance as a result of school tours + 224 families attended spring Student Showcase- discussed improvements to event for next year | May 2019 SP 2022 Survey | 77.1%
| Professional Learning Communities Establish educational teams that meet regularly, share expertise, and work collaboratively to improve teaching skills and the academic performance of students | Staff Engagement Increase the percentage of employees who would recommend Crabapple Crossing Elementary School as a place to work to a family member or friend | No baseline data | Partnership with PTO provides monthly staff appreciation + High voluntary attendance of staff members at International Night | May 2019 SP 2022 Survey | 65.6%
Community Collaboration |  | Outcome | Baseline (Yr. 1) | Evidence of Progress | Date | Results
Initiatives | Community Champions Cultivate and sustain community champions to support student achievement | Partnerships Increase the number of impactful partnerships that align to school goals | 25 | SGC Committee to explored book partnerships in community + New Book Parents chosen to be trained: Michele Melton and Lisa Webb + Ticket Out The Door for Math/ELA Night
| Parent University Offer programs that include free courses, family events, and activities to equip families with new or additional skills, knowledge, resources and confidence | Family Engagement Increase the percentage of families who feel empowered to support their students’ educational journeys | No baseline data | 10/29/19 Parent University on Risk of E-Cigarettes for Teens + 11/1/19 Parent University on Launchpad & Digital Citizenship + 11/28/19 Parent University on Supporting Mental Wellness + 1/25/19 International Night celebrated student diversity and led to increased feelings of inclusivity + 3/1/19 Summit Counseling Onsite Parent Workshop on Emotional Health + 3/6/19 GA Milestones Parent Session + 3/15/19 Spring Showcase + 4/11/19 Parent University on Cyber Security | May 2019 SP 2022 Survey
Fiscal Responsibility |  | Public Engagement |  | Additional Council Professional Development
Budget Approval Date | 2019-02-26 |  | Bulletin Board at the front of the school with SGC information | List all the additional trainings/professional development where at least one (1) member from your Council attended. | 7/21/18 - 1 member attended summer SGC conference
How were resources allocated to support your strategic plan? | Flex Funds allocated for literacy resources, on-site staff development in reading and writing, off-site teacher PD and technology paraprofessional. | List all the opporunities provided to the public to engage with the Council | ***SGC Meeting with Public Comment- 3/26/19*** |  | 9/24/18 - 2 members attended Cross Council meeting
|  |  | ***SGC Meeting with Public Comment- 4/30/19*** |  | 12/11/18- 6 attended Outreach & Communications Committee Training
1/23/19 - 1 member attended Budget Training
2/11/19 -3 members attended Budget Committee Training
2/25/19 - 4 members attended NW Learning Community Spring Cross Council Meeting
|  | Reduce the number of audit findings for Student Activity funds and ensure effective management of funds between school and School Governance Council |  |  | 4/17/19 - 5 members attended the Superintendent Finalist Meet and Greet at Roswell High School
Note on D15: Benschine, Frederick: Was determined in Spring 2018
Note on G15: Benschine, Frederick: What are we considering an impactful partnership and when are we measuring this?
Note on G16: Benschine, Frederick: Results should be released to principals in November

## 19-20
Strategic Plan Monitoring Tool (Year 2)
Crabapple Crossing Elementary School 2019-2020
Student Achievement |  | Outcome | Baseline (Yr. 2) | Evidence of Progress | Date | Results
Initiatves | Balanced Literacy Framework Implement literacy instruction that includes a progression of teacher modeling, guided practice, and student independent learning | 3rd Grade English Language Arts 85% of 3rd grade students will score at proficient and distinguished levels in ELA | 82% | Mid Year BAS Results show that 110/121 students met the mid year expectations - 90.9% Mid Year I-Ready diagnostic results show that 105/122 students met the mid year expectations - 86% | Spring 2020 GMAS | N/A - No Milestones Assessment
|  | Student Growth 85% of 5th grade students will demonstrate typical to high growth in ELA | 55% | In a comparison of BOY - MOY iReady Diagnostic Results, 74.2% of 5th graders made typical growth in ELA | Spring 2020 GMAS | N/A - No Milestones ASsessment
People & Culture |  | Outcome | Baseline (Yr. 2) | Evidence of Progress | Date | Results
Initiaties | Stakeholder Connections Increase engagement with families via technology and face to face interactions | School and District Culture Increase the percentage of families and students who would recommend Crabapple Crossing Elementary School as a place to attend school to a family member or friend | 77.1% | An estimate of 1000 people attended International Night + Padlet for families to shout out teachers/staff + PTO Sponsored Basket Raffle and Dance | May 2020 SP 2022 Survey | TBD
| Professional Learning Communities Establish educational teams that meet regularly, share expertise, and work collaboratively to improve teaching skills and the academic performance of students | Staff Engagement Increase the percentage of employees who would recommend Crabapple Crossing Elementary School as a place to work to a family member or friend | 65.6% | Partnership with PTO provides monthly staff appreciation + Staff t-shirts for Valentines Day + Padlet on the teleschool website for staff members to shout out each other + high number of staff attendance at PTO events like International Night & Basket Raffle | May 2020 SP 2022 Survey | TBD
Community Collaboration |  | Outcome | Baseline (Yr. 2) | Evidence of Progress | Date | Results
Initiatives | Community Champions Cultivate and sustain community champions to support student achievement | Partnerships Increase the number of impactful partnerships that align to school goals | 23 | Partnership with Milton Library + Staff Members Attended BOY Picnic at Crabapple First Baptist + We need to get information from PTO for the # of partnerships from last year - Dr. C and J. Jackson met with Crabapple First Baptist to begin establishing a community partnership - how can we follow up on this? | 2020-05-12 | 19
| Parent University Offer programs that include free courses, family events, and activities to equip families with new or additional skills, knowledge, resources and confidence | Family Engagement Increase the percentage of families who feel empowered to support their students’ educational journeys |  | 10/6/2019 Ms. Jackson presented a Workshop on Digital Citizenship + 10/6/2019 Mrs. Jones presented a workshop on Reading Levels + 11/06/2019 Summit Counseling Workshop on Mindfulness + 01/24/2020 International Night celebrated student diversity and led to increased feelings of inclusivity | May 2020 SP 2022 Survey | TBD
Fiscal Responsibility |  | Public Engagement |  | Additional Council Professional Development
Budget Approval Date | February 24th, 2020 |  |  | 2 SGC Members attended the Cross Council Meeting on February 4th, 2020. 1 Member attended the training for Vice Chair's in August, 2019. One Member attended the SGC Conference on September 21st, 2019.
How were resources allocated to support your strategic plan? | CCES used charter dollars to fund a custodian position. The remainder of the charter dollars will be rolled over to the 2020-21 school year. | Opportunities for public comment were offered at the following meetings: October 29, 2019, December 9, 2019, January 14th, 2020 and February 24th, 2020.
Reduce the number of audit findings for Student Activity funds and ensure effective management of funds between school and School Governance Council

## 20-21
Strategic Plan Monitoring Tool (Year 3)
School Name
Student Achievement | Outcome | Baseline (Yr. 3) | Evidence of Progress | Date | Results
Initiatves
People & Culture | Outcome | Baseline (Yr. 3) | Evidence of Progress | Date | Results
Initiaties
Community Collaboration | Outcome | Baseline (Yr. 3) | Evidence of Progress | Date | Results
Initiatives
Fiscal Responsibility | Public Engagement |  | Additional Council Professional Development
Budget Approval Date | List all the opporunities provided to the public to engage with the Council |  | List all the additional trainings/professional development where at least one (1) member from your Council attended.
How were resources allocated to support your strategic plan?

## 21-22
Strategic Plan Monitoring Tool (Year 4)
School Name
Student Achievement | Outcome | Baseline (Yr. 4) | Evidence of Progress | Date | Results
Initiatves
People & Culture | Outcome | Baseline (Yr. 4) | Evidence of Progress | Date | Results
Initiaties
Community Collaboration | Outcome | Baseline (Yr. 4) | Evidence of Progress | Date | Results
Initiatives
Fiscal Responsibility | Public Engagement |  | Additional Council Professional Development
Budget Approval Date | List all the opporunities provided to the public to engage with the Council |  | List all the additional trainings/professional development where at least one (1) member from your Council attended.
How were resources allocated to support your strategic plan?