## Goal1_Obj1
Goal Area 1: | Student Achievement
Annual Goal 1: | By June 2021, Liberty Middle School will improve to the following levels on STAAR Reading at least 70% at Approaches, 45% at Meets, 25% at Masters.
Objective:1 | By June 2021, all students will improve Reading performance in grades 6th, 7th, and 8th by implementing an effective systemic literacy plan across the content areas.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Campus CLCs will serve as a vehicle to implement a systemic literacy plan. | Classroom Teachers AVID Teacher CLL/Department Chairs Librarian Administrators | Library and Collection STAR Reading Program/Data MyON/Accelerated Reader Data: STAAR 2019 and TELPAS 2020 Benchmark Data - 2020 AVID Strategies Literacy Committee Planning/Meeting Times PearDeck,Google Classroom /Meets | August 2020 through June 2021 | Literacy Committee Documentation (Agendas/Attendance/Minutes) Literacy Plan CLC Agendas/Attendance Documentation Individualized Student Plans Walkthrough Documentation | Gains: Local Assessments Gains: STAAR Assessment Gains: AR Tests Gains: Class Performance Gains: STAR Reading Level | *Formative: Checks for Understanding Assignment Grades *Summative: Weekly Assessments CBAs Benchmarks STAAR AR Tests Lexiles | Title I - 4: High-Quality and Ongoing Professional Development a. Required: select professional development to meet the needs of teachers b. Best Practice: utilize profesional learning communities to meet the needs and schedules of teachers. c. Best Practice: Rearrange the school day to provide a block of time for collaborative planning. Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
Assemble a literacy committee for program implementation and development.
Analyze the results of the 2020 Reading STAR diagnostic assessment, STAAR 2019, TELPAS 2020, and 2020 benchmark data to personalize the instructional needs of all students.
Develop a plan to implement and monitor literacy (reading and writing) practices across all contents.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Targeted interventions will be implemented and monitored based on identified areas of concern synchronously and asynchronously virtually and or face to face. | Classroom Teachers AVID Teacher CLL/Department Chairs Administrators Tutors | Planning Time Summit K12 Read 180/Systems 44 Istation Google Classroom/Meet AVID Strategies Time/Schedule for Tutorials (before, during, or after school; Saturdays) Technology: computers, document readers, slates, etc. PearDeck | October 2020 through June 2021 | Intervention Lists (appr/meets/masters) Attendance Lists for Tutorials Home Contact Logs Completion of Assignments/Lessons Reports (READ 180, Systems 44, Summit K12, Istation) Walkthrough Documentation | Gains: Local Assessments Gains: STAAR Assessment Gains: Class Performance | *Formative: Checks for Understanding Assignment Grades *Summative: Weekly Assessments CBAs Benchmarks STAAR Lexiles | Title I - 9: Effectively and Timely Assistance to Students Experiencing Difficulty a. Required: Analyze individual student data to identify needs and provide additional learning opportunities for all students who need it. b. and c. Best Practices: Provide individualized and small group learning sessions; incorporate computer-assisted instruction Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
Conduct campus review sessions through CLCs to identify and immediately address areas of concern.
Use a blended learning approach for targeted interventions (Istation, Systems 44, READ 180, Summit K12).
Use small group instruction to provide additional support to students in need (by classroom teachers, SE teachers, retired ELA/R teachers, university students).
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Close reading activities will be implemented across all contents virtually using PearDeck online platfom and or face to face. | Classroom Teachers AVID Teacher CLL/Department Chairs Administrators Tutors | PLORE Class Posters Newsela Subscription Newsela Passages by Content Questions (STAAR Format) Writing Prompts for Passages AVID Strategies PearDeck Google Classroom /Meet | October 2020 through June 2021 | Lesson Plans Newsela Binders by Content Student Work/Annotations Walkthrough Documentation | Gains: Local Assessments Gains: STAAR Assessment Gains: Class Performance | *Formative: Checks for Understanding Assignment Grades Newsela Activity Grades *Summative: Weekly Assessments CBAs Benchmarks STAAR | Title I - 2: Reform Strategies a. Required: Review program documentation to ensure that all instructional programs/instructional strategies are supported by scientifically-based research. c. Best Practice: Identify scientifically-based research programs that increase the amount and quality of learning time. Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Acrion Steps
Align close reading passages from Newsela to content area timelines.
Monitor the implementation of close reading.
Implement PLORE reading strategies across the disciplines.

## Goal1_Obj2
Goal Area 1: | Student Achievement
Annual Goal 2: | By June 2021, all Liberty Middle School students will improve in WRITING to the following levels: at least 70% at the Approaches level; 45% at the Meets level; and 15% at the Masters level.
Objective: 1 | By June 2021, all students will improve in WRITING at every performance level by implementing differentiated data-driven instruction to meet the needs of all students.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
A plan will be developed to implement and monitor best practices in writing. | Literacy Committee Members ELA/R Teachers AVID Teacher Language Support Teachers CLL/Department Chairs Content Administrator | DMAC Access/Reports TELPAS Data - 2020 STAAR Data - 2019 Mini-Assessment Data Benchmark Data Google Classroom /Meet | October 2020 through June 2021 | Literacy Plan CLC Agendas/Attendance Review Session Agendas/Findings Classroom Observations Walkthrough Documentation Use of AVID Strategies | Gains: Local Assessments Gains: STAAR Assessment Gains: Class Performance | *Formative: Checks for Understanding Assignment Grades Grades *Summative: Weekly Assessments CBAs Benchmarks STAAR | Title I - 8: Teacher Decision-Making Regarding Assessments a. Required: Include teachers in the decisions and planning regarding use of assessments. c. Best practice: Provide professional development on using data to make instructional decisions, improve curriculum, and design assignments.
Action Steps
A literacy committee will be assembled to for program implementation and development.
Teachers will analyze data from TELPAS 2020, STAAR 2019 to identify areas of concern; teachers will use mini-assessment and benchmark data (2020) to drive instructional practice in writing.
The campus will conduct a review session bi-weekly and at the end of the Six Weeks to identify areas of concern in: written composition; revising; editing.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Writing exercises/activities will be implemented across the contents. | Classroom Teachers AVID Teacher CLL/Department Chairs Administrators | Lesson Plans Writing Prompts by Content AVID Strategies Designated Planning Time | August 2020 through June 2021 | Lesson Plans/Annotations Student Work Use of AVID Strategies Walkthrough Documentation | Gains: Local Assessments Gains: STAAR Assessment Gains: Class Performance | *Formative: Checks for Understanding Assignment Grades Newsela Activity Grades *Summative: Weekly Assessments CBAs Benchmarks STAAR | Title I - 2: Reform Strategies a. Required: Review program documentation to ensure that all instructional programs/instructional strategies are supported by scientifically-based research. c. Best Practice: Identify scientifically-based research programs that increase the amount and quality of learning time. Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
Write-to-Learn exercises/activities will be incorporated into lessons across the contents.
Teachers will produce evidence of writing in their respective classes.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Targeted interventions will be implemented and monitored based on identified areas of concern synchronously and asynchronously virtually and or face to face. | ELA/R Teachers AVID Teacher CLL/Department Chairs Language Support Teachers Tutors Content Administrator | Planning Time Summit K12/Istation Read 180/Systems 44 AVID Strategies Google Classroom/Meet/TEAMS Time/Schedule for Tutorials (before, during, or after school; Saturdays) Technology: computers, document readers, slates, etc. | October 2020 through June 2021 | Intervention Lists (appr/meets/masters) Attendance Lists for Tutorials Home Contact Logs Completion of Assignments/Lessons Reports (READ 180, Systems 44, Summit K12, Istation) Use of AVID Strategies Walkthrough Documentation | Gains: Local Assessments Gains: STAAR Assessment Gains: Class Performance | *Formative: Checks for Understanding Assignment Grades *Summative: Weekly Assessments CBAs Benchmarks STAAR | Title I - 9: Effectively and Timely Assistance to Students Experiencing Difficulty a. Required: Analyze individual student data to identify needs and provide additional learning opportunities for all students who need it. b. and c. Best Practices: Provide individualized and small group learning sessions; incorporate computer-assisted instruction Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
Teachers will analyze classroom and assessment data to identify areas of concern.
Teachers will provide small group instruction to students within and beyond the class period synchronously and asynchronously virtually and or face to face.
Tutors (retired ELA/R teachers and university students) will provide additional support to students within and beyond the class period.

## Goal1_Obj3
Goal Area 1: | Student Achievement
Annual Goal 3: | By June 2021, Liberty Middle School students will improve to the following levels on the STAAR in MATHEMATICS: at least 80% at the Approaches level; 45% at the Meets level; and 25% at the Masters level.
Objective:1 | Students will improve student achievement to the given levels in mathematics through data-driven practices: planning, instruction, and interventions.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Lesson planning and delivery of instruction will be thorough and thoughtful. | Grade Level Math Teachers Grade Level SE Teachers CLL/Department Chair Content Administrator | TEKS Resources Lead4Ward Resources District Curriculum IB Unit Planners Designated Planning Time Google Classroom/Meet | August 2020 through June 2021 | Lesson Plans with Annotations Participation/Observation of Planning Time TCLC Agendas Walkthrough Documentation | Gains: Local Assessments Gains: STAAR Assessment | *Formative: Checks for Understanding *Summative: Weekly Assessments CBAs Benchmarks STAAR/EOC | Title I - 4: High-Quality and Ongoing Professional Development a. Required: select professional development to meet the needs of teachers b. Best Practice: utilize profesional learning communities to meet the needs and schedules of teachers. c. Best Practice: Rearrange the school day to provide a block of time for collaborative planning. Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Teachers will use the planning time allotted to collaborate and determine best practices to use in lesson delivery virtually and or face to face.
Teachers will consult resources that match the rigor of the state assessment to the rigor used in lesson assignments, activities, and projects.
Teacher will select assignments, activities, projects for implementation that reflect the given rigor match.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Consistent monitoring of performance and progress will be observed by teachers and students. | Grade Level Math Teachers Grade Level Sp. Ed. Teachers Students Deparment Chair/Leadership Content Administrator | LMS Monitoring Tool Student Portfolios/Graphs DMAC Access/Reports STAAR Data Local Assessment Data Time for St. Conferences Google Classroom/ Meet | October 2020 through June 2021 | Completed and Current Monitoring Forms Completed and Current Student Graphs Teacher/Student Conferences Walkthrough Documentation | Gains: Local Assessments Gains: STAAR Assessment Student Ownership/Goals | *Formative: Checks for Understanding Student Goal Setting *Summative: Weekly Assessments CBAs Benchmarks STAAR/EOC | Title I - 8: Teacher Decision-Making Regarding Assessments a. Required: Include teachers in the decisions and planning regarding use of assessments. Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
A consistent monitoring tool will be used and kept current by teachers and students to document performance and progress.
Data analysis will be conducted at given intervals, including , but not limited to CBA and Benchmarks, to identify areas of concern and to develop targeted interventions accordingly.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Targeted interventions will be implemented and monitored based on identified areas of concern synchronoysly and asynchronously virtually and or face to face. | Grade Level Math Teachers Grade Level Sp. Ed. Teachers Students Department Chair/Leadership Administration Tutors | Planning Time Google Classroom/Meet Google Slides/Forms Imagine Math Time/Schedule for Tutorials (before, during, or after school; Saturdays)Technology: computers, document readers, slates, etc. | October 2020 through June 2021 | Intervention Lists (appr/meets/masters) Attendance Lists for Tutorials Home Contact Logs Completion of Assignments/Lessons Imagine Math Reports Walkthrough Documentation | Gains: Local Assessments Gains: STAAR Assessment Gains: Class Performance | *Formative: Checks for Understanding Assignment Grades *Summative: Weekly Assessments CBAs Benchmarks STAAR/EOC | Title I - 9: Effectively and Timely Assistance to Students Experiencing Difficulty a. Required: Analyze individual student data to identify needs and provide additional learning opportunities for all students who need it. b. and c. Best Practices: Provide individualized and small group learning sessions; incorporate computer-assisted instruction Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Acrion Steps
Teachers will provide virtual opprtunities for intervention, including, but not limited to Google Classroom/Slides/Meet and Imagine Math.
Teachers and tutors (retired teachers and/or university students) will provide small group instruction to students within and beyond the class period, virtually and or face to face.

## Goal2_Obj1
Goal Area 2: | Closing the Gap
Annual Goal 1: | By June 2021,75% of our identified student groups in the Academic Achievement component in the Closing the Gaps, will meet the STAAR performance targets in Reading and Math.
Objective 1: | All identified student groups in the Academic Achievement component will be monitored to ensure that at least 80% of the indicators are met in Reading and Math by June 2021.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Collect and assess (all subgroup) student data to monitor the progress of weekly assessments by using "meets" level stanadard in reading and math. (Reg Ed, RTI,504,SPED,GT Migrants, EL's, EP) | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44/Read180 District Curriculum | August 2020 - August 2021 | Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Sample | -Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS | Weekly Assessments BM1 & 2 STAAR TELPAS Reading Lexile measures | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Meet with Grade Level once a week to discuss progress monitoring.
2. Use ongoing district created formative assessments to track data.
3.Use data to drive instructional decsions and provide interventions related to students needs. Provide opportunities for small group instruction.
4. Provide diffirintiated instruction, accommodations, and intervention plans based on students IEPs.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Implement action plans to ensure (all subgroup) students meet Reading and Math Meets Standards on district local assessments | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44 District Curriculum | August 2020 - August 2021 | Classroom Tracking Chart Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Sample Lesson Plans | Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS -Domain I & II | Weekly Assessments BM1 & 2 STAAR TELPAS | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Create an intervention plan that targets specific groups for skill and performance level targets.
2. Track student progress,by identifying current levels in STAAR assessments and set goals to show progress/growth.
3. Teachers hold conferences with student to identify, set goals and track progress virtually and or face to face.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Monitor and evaluate the implementaiton of action plans to ensure that (all subgroups)students are progressing to meets standards in both reading and math. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44 District Curriculum | August 2020 - August 2021 | Classroom Tracking Chart Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Sample Lesson Plans | -Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS | Progress Monitoring Tool, Action Plan, Weekly Assessments BM1 & 2 STAAR TELPAS | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Acrion Steps
1. Meet with CLF's and leadership team to evaluate the use of resources for specific target groups.
2. Review lesson plans,discuss instructions and stratagies to target specific students needs.
3. Provide teachers with quality intentional planning during their confrence periods and TCLC's.

## Goal2_Obj2
Goal Area 2: | Closing the Gap
Annual Goal 1: | By June 2021,75% of our identified student groups in the Academic Achievement component in the Closing the Gaps, will meet the STAAR performance targets in Reading and Math.
Objective 2: | All student groups will increase in the Growth component by at least 10 percentage points in Reading and Math performance level. In Reading from 31% to 41% and from 42% to 52% in Math.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Identify all students in STAAR 2019 assessment who can potentially meet expected growth. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44 District Curriculum | August 2020 - August 2021 | STAAR Data 2019 Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Samples | -Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS -Domain I & II | Weekly Assessments Benchmarks 1 & 2 STAAR | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Schedule opportunities for blended learning ( IStation, Imagine Math, AR, Systems 44, Read 180)
2. Students will monitor/track their progress towards Meets or exceedes expected expected growth.
3. Campus will employ Intentionall flexible scheduling.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Create and develop a plan to ensure all teachers are delivering high-quality, best practice close reading activities during their instructional time. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44 District Curriculum | August 2020 - August 2021 | STAAR Data 2019 Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Samples | -Student Growth -Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS -Domain I & II | Weekly Assessments Benchmarks 1 & 2 STAAR | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Scheduled advance courses to provide more rigorous curriculum and instruction.
2. Provide "close reading" professional development to engage the rigor of instruction at the meets and masters levevl.
3. Implement and monitor instruction through walkthroughs and effective feedback.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Provide STAAR intervention block to teachers for Monitoring and evaluating student progress as well as reflecting on insturctional time to ensure high quality best practices are being delivered to the assigned "meets" and "masters" level groups of students. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44 District Curriculum Lesson Plans Scheduling | August 2020 - August 2021 | STAAR Data 2019 Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Samples | -Student Growth -Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS -Domain I & II | Weekly Assessments Benchmarks 1 & 2 STAAR | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Acrion Steps
1. Implement STAAR alligned resrouces for whole group instrcutions for targeted intervention groups and tutoring.
2. Develop an action plan and the identification of who, when and what skill is being targeted.
3. Implement Close reading, informal/ formal assessments, STAAR released question stems, and open ended questions to track student progress.

## Goal2_Obj2 B
Goal Area 2: | Closing the Gap
Annual Goal 2: | By June 2021, 75% of our identified student groups in the Academic Growth status component in the Closing the Gaps domain will meet the expected growth targets in reading and math.
Objective 1: | All student groups will meet or exceed growth expectations by at least 5% increase of academic growth in the area of Reading and Math by June 2021: from 61% to at least 66% in Reading and from 60% to at least 65% in Math.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Target English learners student groups to demonstrate at least 5% increase in academic growth in the areas of Reading and Math. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | ELPS Stratagies Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44 District Curriculum | August 2020 - August 2021 | STAAR Data 2019 Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Sample | -Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS -Domain I & II | Weekly Assessments Benchmarks 1 & 2 STAAR | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. ELs will be monitored bi-weekly through the progress monitoring tool.
2. Teachers will be provided with quality training on how ELP Stratagies are embedded in weekly lesson plans to enhance the overall instructional program for ELs
3. Teachers will be trained and guided on the implementation of EL supplemental aids on provisions of routinely testing accommodations to personalize the need of every EL student in their classroom.
4. Teachers will use BIC/CALP vocabulary stratagies across all contents.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Target and monitor our SPED student groups to demonstrate a 5% increase of academic growth in the area of Reading and Math. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44 District Curriculum | August 2020 - August 2021 | STAAR Data 2019 Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Sample | -Student Growth -Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS -Domain I & II | Weekly Assessments Benchmarks 1 & 2 STAAR | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Use progress monitoring tool and track student growth.
2.Provide System 44 reding intervention for struggling readers.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Target and monitor our ECD student groups which will demonstrate a 10% increase in academic growth in the areas of Reading and Math. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Counselor | Progress Monitoirng Tool STAAR Release Data IStation Reading Imagine Math Systems 44 District Curriculum Lesson Plans Scheduling | August 2020 - August 2021 | Lesson Plans Progress Monitoring Data Weekly Assessments McREL Walkthroughs Student Work Sample District Curriculim | -Student Growth -Closing the achivement Gaps -Increase in academic Performance in Benchmarks and STAAR, TELPAS -Domain I & II | Weekly Assessments Benchmarks 1 & 2 STAAR | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Acrion Steps
1. Use progress monitoring tool and track student growth.
2. Tailor interventions to each student's needs.
3. Communicate and reach out to parents for support and provide student with needed resources to suceed.

## Goal 2 Obj 3
Goal Area 2: | Closing the Gap
Annual Goal 3: | By June 2021, 55% of English Learners will advance by at least one proficiency level of the composite rating from June 2019 to June 2021 in the TELPAS state assessment.
Objective 1: | In grades 6th-8th grade student will increase at least one proficiency level or maintain Adv High in the areas of Listening by at least 75%, in Speaking by at least 40% and in Reading by at least 60%.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Develop, implement, and monitor a plan so all identified EL students can practice TELPAS Listening activities in their classroom | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Spanish Teachers | Summit K-12 TELPAS Data IStation Reading Imagine Math Test Practice Items District Curriculum Scheduled Lab Time | August 2020 - August 2021 | TELPAS Data 2019 Weekly Assessment McREL Walkthroughs Student Work Sample/ Sets | Closing the achivement Gaps Summit K-12 TELPAS Pracitce Sets Domian III Walkthorughs Classroom Student engagment/participation | Practice Sets Data Summit K-12 Reports Classroom Listening Activites CIF Protocols | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Provide professional development for all teachers on effective TELPAS listening activities that can be implemented across all subjects
2. Provide students with lab time to practice Listening activities using Summit K-12 program twice a week during spanish classess.
3. Incorportate CIF protocols, such as cold calling, to give students the opportunity to discuss in class.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Develop, implement, and monitor a plan so all identified EL students can practice TELPAS Speaking activities throughout their classroom. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Spanish Teachers | Summit K-12 TELPAS Data IStation Reading Imagine Math Test Practice Items District Curriculum Scheduled Lab Time | August 2020 - August 2021 | TELPAS Data 2019 Weekly Assessment McREL Walkthroughs Student Work Sample/ Sets | Closing the achivement Gaps Summit K-12 TELPAS Pracitce Sets Domian III Walkthorughs Classroom Student engagment/participation | Practice Sets Data K-12 Summit Reports Classroom Speaking Activites CIF Protocols | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Provide professional development for all teachers on effective TELPAS Speaking activities that can be implemented across al subjects
2. Provide students with lab time to practice Speaking activities using Summit K-12 program twice a week during spanish classess.
3. Incorportate CIF protocols, such as Think, Pair, Share to give students opportunities to speak in class discussions.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Develop, implement, and monitor a plan so all identified EL students can practice TELPAS Reading activities throughout their classroom. | Principal Dean of Instruction Asst. Principals CLL Department GL Chairs Teachers Spanish Teachers | Summit K-12 TELPAS Data IStation Reading Imagine Math Test Practice Items District Curriculum Scheduled Lab Time | August 2020 - August 2021 | TELPAS Data 2019 Weekly Assessment McREL Walkthroughs Student Work Sample/ Sets | Closing the achivement Gaps Summit K-12 TELPAS Pracitce Sets Domian III Walkthorughs Classroom Student engagment/participation | Practice Sets Data K-12 Summit Reports Classroom Reading Activites Close Reading Stratagy CIF Protocols | *Comprehensive Needs Assessment (A,B,C) *Reform stratagies (A,B,C) *Teacher Decison-Making Regarding Assessments (A,B,C) *Effective and Timely Assistance to Students Experiencing Difficulty (A,B,C) *Coordination and Intergration of Federal, State, and Local Services, Programs, and Funds (A) Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Acrion Steps
1. Close reading strategies routinely used across the contents.
2. Provide student tutors for individualized reading interventions.
3. Train teachers on TELPAS Reading rubric
4. Provide students with lab time to practice Reading activities using Summit K-12 program twice a week during spanish classess.

## Goal3_Obj1
Goal Area 3: | Improve Safety, Public Support, Culture and Climate
Annual Goal 1: | To meet our annual goal of 97.5% attendance rate by June 2021
Objective 1: | To monitor daily student attendance to ensure students are in school actively learning daily
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Increase student attendance. | Grade level Administrator School Community Liaison Teachers Attendance Clerk Counselors Nurse Security Guard | Attendance Rosters Grade level incentive (snacks/prizes). Trophies Banners Attendance and Tardy Logs Sign in and Sign out Forms District Portal for Attendance Recovery | August 2020 - August 2021 | Attendance Reports PowerPoints Shared by District Student Profiles Completed Logs Teacher Logs Attendance Recovery Program (ARP) | Increase of student attendance Culture and Climate Survey Increase in Student Achievement | Weekly district attendance District six weeks attendance Attendance Recovery Participation (ARP) Certificates Sign-in/out sheets Yearly Attendance Rate of 97.5% | Reform Strategies 2A 2C Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 A 10 C Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
Make daily parent contact for students who are absent.
Disseminate policy awareness presentation/ information handouts to parents.
Require and enforce student sign-in at: front office, ccounselors, nurse
Require students to turn in written excuses for being absent to the attendance office/School Attendance Specialist.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Enforce district/state attendance policies. | Grade level Administrator School Community Liaison Teachers Attendance Clerk Counselors Nurse Security Guard | Non-Attendance Referral forms Warning letters. Telephone contact. Meeting date Hearing dates. Warning dates. Attendance and Tardy Logs Sign in and Sign out Forms District Portal for Attendance Recovery | August 2020 - August 2021 | Attendance Reports at the Campus Weekly District Attendance PowerPoints Shared by District Student Profiles Completed Logs Teacher Logs Attendance Recovery Attendance | Increase of student attendance Culture and Climate Survey Increase in Student Achievement | Non-attendance referral forms Attendance logs Warning letter copies Parent conference dates on file Hearing dates on file Attendance Action Plan | Reform Strategies 2A 2C Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 A 10 C
Action Steps
Provide attendance clerk with rosters of planned activities.
Encourage teachers to submit non-attendance referral forms after three unexcused absences
Issue warning letters to parent/guardian. Give verbal reprimands.
Make contact with students and parents after three unexcused absences.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Enforce an Attendance Action Plan | Grade level Administrator School Community Liaison Teachers Attendance Clerk Counselors Nurse Security Guard | District/TEA attendance rate. Attendance and Tardy Logs Sign in and Sign out Forms District Portal for Attendance Recovery | August 2020 - August 2021 | Attendance Reports at the Campus Attendance Rate comparison with State PowerPoints Shared by District Student Profiles Attendance Recovery Application | Committee Input Culture and Climate Survey Increase in Student Achievement/Attendance | Campus Meeting Sign In Measured Goals | Reform Strategies 2A 2C Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 A 10 C
Acrion Steps
Create an Attendance Action Plan with: attendance procedures for parents, helpful tips for parents, automated phone system calls to parents to inform them about Attendance Recovery Program (ARP)

## Goal3_Obj2 (A) (2)
Goal Area 3: | Improve Safety, Public Support, Culture and Climate
Annual Goal 2: | By June 2021, student and staff perception for their physical and psychological saferty will improve by 10%
Objective 1: | By June 2021, student social and emotional learning knowledge and skills will increase by 10%
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
All students will be provided guidance lessons that build on the social emotional development of the student. | Principal Assistant Principals Counselors Teachers Security Guards School Liason | District Curriculum for Advisory Counseling and Guidance Curriculum Feedback Surveys District Training Materials Professional Development District LPC | August 2020 - June 2021 | Walk Through Reports Lesson Plans Student SEL (Social Emotional Learning) profile Student Guidance Lessons Ongoing assistance of emotional needs | Culture and Climate Survey Increase in student attendance Inrease in student achievement | Benchmarks STAAR/EOC Campus Climate Survey Walk Through | Reform Strategies 2A 2C Effective and Timely Assistance to Students Experiencing Difficulty 9A Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 A Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
Schedule presentation of lessons in the classroom by counselors.
Contact appropriate personnel and schedule presentations.
Distribute pertinent infromation related to Social Emotional Learning for students and parents.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
All students and staff will be provided with infromationa on various topics such as cyberbullying, bullying, social media, and emotional abuse. | Principal Assistant Principals Counselors Safety Committee Security Guards School Liason | District Wraparound Services District LPC Safe2SpeakUp Application PowerPoint Presentation Student Survey Training Material | August 2020 - June 2021 | Agendas Counselor Sign In Sheet PEIMS Discipline Data Student Survey Data | Decrease in behavior intervention forms Sudent perception of school safety improved Increase in student attendance and academics | Survey Safety Audits Six Week Behavior Reports | Reform Strategies 2A 2C Effective and Timely Assistance to Students Experiencing Difficulty 9A Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 A
Action Steps
Provide teachers and students training on de-escalation, bullying, cyberbullying, Safe2SpeakUp, and restorative practices
Conduct and collect student surveys to evaluate the student's perception on physical and psychological school safety
Implement the five social emotional learning competencies into lessons: self-awareness, self-management, social awareness, relationship skills, and responsible decision making.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Increase student career awareness and promote college readiness/connection | Counselors Principal High School Principal Guidance and Counseling Department | PowerPoint Presentation School Pamphlets University Visual Packets (Website) High School pathway brochures/pamphlets avid | August 2020 - June 2021 | University Visits High School Visits Student Career inventory Career Pathway Survey University Shirts Campus Website pictures of visits Agendas | Increase interest in college Increase in academic achievement Completion of careeer pathways | Participation Sheets Student Survey High School Graduation Data | Reform Strategies 2A 2C Effective and Timely Assistance to Students Experiencing Difficulty 9A Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 C
Action Steps
Contact appropriate personnel to schedule presentaions and/or visitations to high schools/university -(Virtual or in person)
Schedule Career Pathway surveys and provide parents information of selections/interest
Invite community speakers to provide career awareness to students such as bankers, managers, police officers, etc.
Promote college ready initiatives throughout all contents and grade levels. (Friday Spirit Day)

## Goal3_Obj2 (B)
Goal Area 3: | Improve Safety, Public Support, Culture and Climate
Annual Goal 2: | By June 2021, student and staff perception for their physical and psychological saferty will improve by 10%
Objective 2: | By June 2021, 100% of the district will implement safety and violence prevention protocols that will increase school safety
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Provide staff development for staff and students on safety procedures | Principal Assistant Principals Counselors Teachers Security Guards School Liason | Training Equipment Security Cameras Security and Safety Audits Feedback Surveys District Training Materials Professional Development Crisis Managemen Plan | August 2020 - June 2021 | Agendas Sign In Sheets Security Safety Audits School Lockdown Documentation Fire Drills Report District Crisis Audits | Incrase in student safety perception Results of audits Increase in sfaff survey results | Safety Audits Drill Reports Survey on Students Staff Survey | Reform Strategies 2A 2C Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 C
Action Steps
Schedule presentation for staff, practice drills with students, and become familiar with the crisis mangament plan.
Contact appropirate personnel and schedule presentations.
Distribute pertinent information related to school safety.
Conduct daily security/safety audits
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Promote school safety and train all staff in restorative practices. | Principal Assistant Principals Teachers Support Staff Counselors Safety Committee Security Guards School Liason Parental Involvement | Student Code of Conduct District Behavior Application Cameras Safety Audits Professional Development Community Speakers | August 2020 - June 2021 | Agendas Sign In Sheets Security Safety Audits District Six Week Reports Counselor classroom presentations on drug prevention Red Ribbon Week | Reduce disciplinary assignments Reduce hearing for placement Drug Prevention Material | District Six Week Reports Documented Referrals Behavior Management plan in place Sign In Sheets Student Survey | Reform Strategies 2A 2C
Action Steps
Invite community speakers and provide information on drug awareness.
Follow policies outlined by the distrcit and in the student code of conduct manual.
Hold team conferences with students and parents, as needed.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Ensure that all COVID 19 protocols and systems are established and followed to provide a safe and healthy environment for all stakeholders for the entire 2020-2021 school year. | Principal Nurse District RisK Management District Dierector for Health Services Assistant Principal Security Guards Custodial Staff Cafeteria Personnel Transportation Department | Center for Disease and Control Guidelines and Website District COVID 19 Resources Personal Protective Equipment Technology Visuals Cameras | August 2020 - June 2021 | Visuals on campus indicating safety standards and practices Classroom Structures Agendas Sign In Sheets PowerPoint TEA Guidelines COVID 19 Team (Campus) | Mandating face coverings and social distancing Accessability to hand sanitizer and other personal protective equipment | Distirct Audits COVID 19 Team Audits | Reform Strategies 2A 2C High Quality and ONgoing Professional Development 4A Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 C Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
Train staff, parents, and students on protocols and procedures at different phases of COVID 19 school openings
Conduct dailiy screening on all personnel and students on campus
Create a COVID 19 team that will ensure that all procedures, guidelines and safety standards are being followed

## Goal 3 Obj 3
Goal Area 3: | Improve Safety, Public Support, Culture and Climate
Annual Goal 3: | By June 2021, 100% of our staff, students, and parents will engage and interact with the child's school
Objective 1: | Encourage and collaborate with all stakeholders to increase parental involvement and interactions with school community.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Host campus information and training sessions on varying topics using different days and times | Parental Director Parental Educator Principal Assistant Principals Counselors School Liason Nurse Teachers | Research Based Best Practices District and Campus Policy Handbook Student Code of Conduct Handbook ESL/GED Brochures School Messenger Reading Materials District Public Relations Department | August 2020 - June 2021 | Agendas Meetings Invites Campus Website Sign In Sheets PowerPoints Photos Facebook | Parent Survey Results Increase Parental Involvement Increase Student Attendance Increase Student Achievement | Participation Counts Event Performances Benchmark STAAR Attendance Comparison in District | Strategies to Increase Parental Invovlvement 6A, 6B, 6C Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 C Title I,II,II State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
Provide campus sessions on multiple topics (Titile I, Campus Policy and Student Handbook, Home-School Compacts, Attendance, and State Assessments) and Have district public relations (KTRI) provide essential information.
Send letters home, provide updated information on the campus website and Facebook aksing parents to participate.
Provide certificates and acknowldgements to parental volunteers on campus (Marquee and Bulletin Boards),
Continually recruit parents to join parental program and equip parental involvement center with needed appliances and materials.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Invite parents and community members to pariticpate in school activities and events. | Parental Director Parental Educator Principal Assistant Principals Counselors School Liason Nurse Teachers | Research Based Best Practices District and Campus Policy Handbook Student Code of Conduct Handbook UIL School Messenger Reading Materials District Public Relations Department | August 2020 - June 2021 | Parental Participation at events Invites Campus Website Sign In Sheets PowerPoints Photos Facebook | Parent Survey Results Increase Parental Involvement Increase Student Attendance Increase Student Achievement Decrease in Disciplinary Actions | Participation Counts Event Performances Benchmark STAAR Attendance District Behavior Reports Attendance Reports in District | Strategies to Increase Parental Invovlvement 6A, 6B, 6C Coordination and Integration of Federal, State, and Local Services, Programs and Funds 10 C
Action Steps
Develop a monthly calendar with reminders, activities, and celebrations to have buy in from all stake holders
Sponsors will coordinate with administration and librarian to promote and effectively schedule all events taking place. Recognize parental support at the events.
Utlize all means of communications to promote and inform communitiy of events (marquee, Liberty website and Facebook page, District Public Relations)
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Action Steps

## Goal4_Obj1
Goal Area 4: | Increase staff quality, recruitment and retention
Annual Goal 1: | All teachers will be provided with resources and will be trained to deliver engaging and high-quality lessons to increase staff quality.
Objective 1: | Professional development will be offered to target research-based strategies for teachers to integrate in their classrooms.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Integrate and provide effective professional development to implement research based strategies to enhance student learning. | Principal Assistant Principals CLL Dept. Heads Teachers | TCLC's Weekly Content Planning Grade Level Meetings | August 2020-2021 | Staff integrates research based strategies that are shared with them during TCLC's Teachers analyze student work. | Integration within lesson plans Observed in classroom walkthroughs Increase in student academic achievement through weekly progress monitoring tool. | Weekly Walkthroughs Observations | Title I-4 High Quality and Ongoing Profesisonal Development a. required- select professional development to meet th eneeds of all principals,teachers, paraprofessionals parents, and other as appropriate State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Will utilize campus and grade level data to identify area of needs and provide/address effective professional development opportunities.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Intentional professonal development will be afforded based on data collected in the evaluation system to show growth. | Principal Assistant Principals CLL Department Heads Teachers | TCLC's Weekly Content Grade Level Meetings McRel | August 2020-2021 | Walk-through data reviewAgendas Data Reports | Professional growth and high quality teaching Implementation of best practices Improved student performance. | Weekly walkthroughs Observations Data Student progress | Title I-4 High Quality and Ongoing Profesisonal Development a. required- select professional development to meet th eneeds of all principals,teachers, paraprofessionals parents, and other as appropriate State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. All new teachers will be provided with a teacher mentor.
2. Collaborative instructional practices will be reviewed among staff. (e.g., instructional rounds, walkthroughs, observations, feedback)
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Acrion Steps

## Goal4_Obj2
Goal Area 4: | Increase staff quality, recruitment and retention
Annual Goal 2: | By June 2021, all teachers will show growth in McREL’s Performance Evaluation Report by one level to improve student achievement.
Objective 1 | Based on 2019-2020 McREL’s Performance Evaluation Reports, by the end of the 2020-2021 school year, two of the developing rating teachers will improve to effective, and 20% of the 50 teachers at effective rating will increase to highly effective by providing Intentional professional development to all staff
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Provide instructional coaching support for developing and proficient staff. | Principal Assistant Principals CLL Department Heads | -Teachers complete their McREL Self-Assessments and submit their PD goals by September 30th -Analyze data to create, assess, and monitor Student Learning Objectives -Provide effective feedback based on walkthroughs and observations to identify teachers’ areas of needs -Use walkthroughs and observations evaluations to provide effective coaching and professional development for all teachers. | August 2020 to June 2021 | Mentor/Coaching logs Sign-in sheets CLC's Walkthroughs Analyzing student work | -Increase in teacher satisfaction and moral improvement in student performance; better adjustments for new and all teacher personnel -McREL Teacher Evaluation Proficiency level increase -Increase in scores, academic achievement and closing the gaps. | Weekly Walkthroughs Observations McREL Student Academic Performance Rigor/Relevance Rubric | Title I-4 High Quality and Ongoing Profesisonal Development a. required- select professional development to meet th eneeds of all principals,teachers, paraprofessionals parents, and other as appropriate State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Teachers participate in weekly TCLCs and job-embedded professional development on best practices.
2. Provide teacher with feedback through classroom walkthoughs.
3. Conduct at least 1 learning walk per teacher each semester.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Implement and monitor staff PD goals for growth throughout the 2021 school year. | Principal Assistant Principal CLL Department Heads Teachers | Mcrel Guide Book/Rubric Evaluation Tool District Instructional Focus Walkthrough Form TEEMS | August 2020 to June 2021 | Mentor/Coaching logs Sign-in sheets CLC's Walkthroughs Analyzing evidence in transformation from TCLC's student work. | Teacher growth in EOY McREL ratings Student achievment Application | BOY, MOY, and EOY Conferences Walkthroughs and Effective Feedback | Title I-4 High Quality and Ongoing Profesisonal Development a. required- select professional development to meet th eneeds of all principals,teachers, paraprofessionals parents, and other as appropriate State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Teachers complete their McREL Self-Assessments and submit their PD goals by September 30th.
2. Provide effective teacher feedback based on classroom walkthoughs and observations to identify teachers' areas of need.
3. Analyze data to create, assess, and monitor Student Learning Objectives.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
New teacher professional development and coaching support for those who need to improve delivery of classroom instruction. | Principal Assistant Principals CLL Department Heads | Coaching Cycle McREL Rubic Walkthroughs and Effective Feeback TCLC | August 2020 to June 2021 | Mentor/coaching logs Sign-in sheets CLCs Walkthroughs Analyzing student work | Teacher growth in EOY McREL ratings Student achievment Application | BOY, MOY, and EOY Conferences Walkthroughs and Effective Feedback | Title I-4 High Quality and Ongoing Profesisonal Development a. required- select professional development to meet th eneeds of all principals,teachers, paraprofessionals parents, and other as appropriate State Compensatory Fund State Bilingual Funds Local Funds
Acrion Steps
1. Teachers participate in weekly TCLCs and job-embedded professional development on best practices.
2. Provide effective teacher feedback based on classroom walkthoughs and observations to identify teachers' areas of needs.
3. Conduct at least 1 Learning walk per teacher each semester.

## Goal 4 Obj 3 (A)
Goal Area 4: | Increase staff quality, recruitment and retention
Annual Goal 3: | By June 2021, all teachers will be highly qualified to teach their current assignment.
Objective 1 | 1a: All secondary ESL ELA teachers will be certified by May 2021
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Teachers will participate in district training. | Principal Dean of Instruction Content Administrator Teachers | Calendar of District Trainings Bilingual Department | August 2020 to June 2021 | Sign-in logs Registration documents on file ERO Printout Sheets | Professional growth High level teaching | Highly qualified teachers resulting in a stronger learning enviornment Student achievement | Title I-4 High Quality and Ongoing Profesisonal Development a. required- select professional development to meet th eneeds of all principals,teachers, paraprofessionals parents, and other as appropriate State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Provide a calendar of meaningful district professional development.
2. Teachers will participate in trainings offered by the district.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Action Steps
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Acrion Steps

## Goal 4 Obj 3 (B)
Goal Area 4: | Increase staff quality, recruitment and retention
Annual Goal 3: | By June 2021, all teachers will be highly qualified to teach their current assignment.
Obective 2 | Campus recruitment and retention of highly qualified and certified teadchers in all assignments by June 2021.
Strategy 1 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Promote strategies for attracting/retaining highly qualified staff. | -Principal -Dean of Instruction -Content Administrator | -Survey forms -Surveys -Staff Development Plan | August 2020 to June 2021 | -Highly qualified teachers resulting in a stronger learning enviornment and student achievement. | -Professional growth -High level teaching | Survey results -Staff Development Plan -Teacher Evaluations of presentations -Effective trainings in higher STAAR scores | Title I-4 High Quality and Ongoing Profesisonal Development a. required- select professional development to meet th eneeds of all principals,teachers, paraprofessionals parents, and other as appropriate State Compensatory Fund State Bilingual Funds Local Funds
Action Steps
1. Distribute staff development needs surveys.
2. Review survey findings and target exact areas of staff development needs.
3. Progress staff development plan SBDM Committee.
4. Coordinate quality on-going professional development.
Strategy 2 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Seek reasearch-based professional development opportunities for all staff members. | -Principal -Dean of Instruction -Content Administrator -CLL -Department Heads | Professional Development -Research Based Strategies | August 2020 to June 2021 | Sign-in logs -Registration documents on file -ERO Printout Sheets | -Professional growth and high level teaching | Registration documents on file -ERO Print-outs -Master Schedule -Highly qualified Staff resulting in a stronger learning environment -Walkthroughs | Title I-4 High Quality and Ongoing Profesisonal Development c.Best Practices rearrange the school day to provide a block of tiem for collaboration planning.
Action Steps
1. Register for training in their content areas.
2. Allow common planning periods for teachers to share strategies learned.
3. Conduct vibrant TCLCs for all teachers.
Strategy 3 | Persons Responsible/Title | Resources | Timeline | Evidence of Implementation | Evidence of Impact | Formative/ Summative Assessment | Title-I School- wide Component
Provide new teacher professional development and coaching support for those who need to pass certification exams | Principal, Assistant Principal, CLL, Grade level chairs, ACP | McREL Rubric, Provide effective feedback based on walkthroughs and observations to identify teachers’ areas of needs. Use walkthroughs and observations evaluations to provide effective coaching and professional development for all teachers. | August 2020 to June 2021 | Mentor/Coaching logs, Sign-in sheets, CLCs,walkthroughs, Analyzing student work | Increase in Teacher Performance and McREL Teacher Evaluation Proficiency level, Increase in Student Achievement and Closing the Gaps. | Weekly walkthroughs, Observations, McREL Student Academic Performance Rigor/Relevance Rubric | Title I-4 High Quality and Ongoing Profesisonal Development a. required- select professional development to meet th eneeds of all principals,teachers, paraprofessionals parents, and other as appropriate State Compensatory Fund State Bilingual Funds Local Funds
Acrion Steps
1. Schedule McREL trainings for all new teachers.
2.Provide coaching support for all new teachers
3. Provide meaningful opportunities for professional develpment to all new teachers