## Sheet1
| 2020-07-01 | [5 empty] | Tentative
Horace Mann School, 225 Nevada Street, 2020 Phase 1 Improvements Project Schedule
|  | week of: | 2019-06-29 | 2019-07-06 | 2019-07-13 | 2019-07-20 | 2019-07-27 | 2019-08-03 | 2019-08-10 | 2019-08-17 | 2019-08-24 | 2020-08-31 | 2020-09-03
Task
Cafeteria Acoustical Ceiling Panels
| Delivery / Off Gas | (7/6-7/24) | bar: 2019-07-06 to 2019-07-20
| Installation of ceiling racks/panels ,final clean | (7/6-8/24/2020 | bar: 2019-07-06 to 2019-08-24
Remove Walls between Rooms 115,116,117 / 212,213,214 / 101,102 and build new classroom walls
| Demolition of walls | (7/6-24) | bar: 2019-07-06 to 2019-07-20
| Construction of new walls, finmal clean | (7/27-8/31/20) | bar: 2019-07-27 to 2020-08-31
Second Floor Corridor Sinks
| Demolition of wall, plumbing, coring for new plumbing | (7/6-10) | bar: 2019-07-06
| Installation of new plumbing (new water lines and drain lines, prep for sink and water bubbler installation | 2017-07-13 | bar: 2019-07-13
| Install new countertops, sinks and bubblers, install finish panels and shelving, final clean | (7/6-8/24/20) | bar: 2019-07-20