## Sheet1
| PROJECT | ORIGINAL BUDGET | CURRENT BUDGET | OVER | STATUS | NOTES
(UNDER)
GROWTH
601 | Elementary # 6 - Van Raub | 30199255 | 27576576 | -2622679 | C |  |  | 601
601 | Elementary # 7 - Herff | 31900981 | 31490675 | -410306 | UC |  |  | 601
601 | Middle School # 3 - Voss | 57702289 | 59758812 | 2056523 | UC |  | 118826063 | 601
602 | CHS & BHS Additions | 9865680 | 9587039 | -278641 | C | 1 |  | 602
602 | BMS South Choir Fine Arts remodel | 1244667 | 786027 | -458640 | UC |  |  | 602
602 | BMS North Band & Fine Arts Remodel | 1336327 | 844327 | -492000 | UC |  | 20179128 | 602
606 | BHS Tennis w/ CHS & BMSS Tennis | 1265116 | 1200327 | -64789 | C |  | 1200327 | 606
602 | CHS CTE/Ag Expansion | 0 |  | 0 | C | 1 |  | 602
602 | BHS Locker | 0 |  | 0 | C | 1 |  | 602
612 | CHS & BHS Softball | 307801 | 312446 | 4645 | C |  | 312446 | 612
613 | CHS Football Turf | 1565092 | 1394048 | -171044 | C |  | 2001235 | 613
602 | Repurpose Old Fabra (Admin Center) | 9197192 | 8961735 | -235457 | C |  |  | 602
603 | Land | 7000000 | 8325000 | 1325000 | C | 2 | 8325000 | 603
610 | Portables Classrooms | 300000 | 238000 | -62000 |  |  | 238000 | 610
616 | White Fleet (non bus) | 180000 | 179000 | -1000 |  |  |  | 616
616 | Buses | 1600000 | 1597000 | -3000 |  | 4 | 1776000 | 616
SAFETY & SECURITY
611 | Alarms - Security | 684225 | 631436 | -52789 | C | 3 |  | 611
611 | Campus Access | 0 |  | 0 | C | 3 | 631436 | 611
609 | Elementary Playgrounds Upgrades | 1512922 | 2091255 | 578333 | C |  | 2091255 | 609
613 | BHS Parking/Drainage | 453650 | 607187 | 153537 | C |  |  | 613
615 | Civil/Site work- drainage, etc. | 2099803 | 2201169 | 101366 | C |  | 2201169 | 615
616 | Communications Equip | 0 |  | 0 | C | 4 |  | 616
DISTRICT-WIDE IMPROVEMENTS
617 | Wireless, network, Data Center | 9138903 | 9088903 | -50000 | UC | 5 | 9088903 | 617
617 | Tech equipment refresh | 0 |  | 0 |  | 5 |  | 617
604 | Roofing repair/replace | 1957923 | 1925139 | -32784 | C |  | 1925139 | 604
607 | HVAC upgrades | 2957174 | 4685473 | 1728299 | UC |  | 4685473 | 607
614 | Lighting upgrades | 500000 | 301006 | -198994 | UC |  | 301006 | 614
605 | Energy Mgmt. Systems | 931000 | 924483 | -6517 | C |  | 924483 | 605
608 | Kitchen Walk-ins and Equipment | 1100000 | 844771 | -255229 | C |  | 844771 | 608
619 | Camera Initiative | 0 | 168133 | 168133 | D |  | 168133
618 | BOND MANAGEMENT | 0 | 1223033 | 1223033 |  | 6 | 1223033 | 618
0 | OTHER FEES & BOND EXPENSES | 0 | 357924 | 357924 | C |  | 57000
|  | 175000000 | 177300924 | 2300924 |  | 7 | 177000000
Note 1: BHS & CHS additions, CTE/Ag Expansion, BHS Locker combined into one project.
Note 2: Land - Funding for Voss & future school site, Utilities for site (water, sewer, fire & road).
Note 3: Security & Campus Access combined into one project.
Note 4: Communications (radios) of $400,000 included with Buses.
Note 5: Wireless ($4,000,000) and Tech equipment ($5,138,903) combined into one for accounting.
Note 6: Bond Management. Approximately 0.7% allocated from each project. $1,200,000 estimate.
Note 7: Interest earned to date.
Values as of 1/10/2019
UC-under construction; C-complete; B-bidding; D-in design.