## Slide 1: Measure BB Bond
21st Century Classroom Improvements
SEPTEMBER 26, 2024

## Slide 2: HLPUSD MEASURE BB - SUMMARY SCHOOLS IN PROGRESS
STIMSON
IN PROGRESS-
CONSTRUCTION
La Puente HS
Los Altos HS
Wilson HS
BIDDING CURRENTLY
California ES
Baldwin ES
Los Molinos ES
Grazide ES
AT DSA FOR REVIEW
Kwis ES
Lassalette ES
Fairgrove K-8
Sierra Vista MS
IN DESIGN
Orange Grove MS
Palm ES
Valinda ES
Sparks E
Wing Lane ES
Valley Alternative
COMPLETED
Nelson ES
Los Altos ES
Workman ES
Mesa Robles K-8
Cedarlane K-8
Sparks MS
Newton MS
Grandview K-8
Stimson EC
Workman HS

## Slide 3: PHASE B PROGRESS
Anticipated Construction Start Fall of 2024
1. Baldwin ES Construction Documents First Bid advertisement 8/14/2024 Open Sept 24, 2024
2. California ES Construction Documents First Bid advertisement 8/14/2024 Open Sept 24, 2024
3. Los Molinos ES Construction Documents First Bid advertisement 8/14/2024 Open Sept 24, 2024
Interim Housing Los Robles (Tentative)
4. Grazide ES Construction Documents First Bid advertisement 8/14/2024 Open Sept 24, 2024
Interim Housing Bixby (Tentative)
Anticipated Construction Start Fall of 2024
5. Kwis ES Construction Documents At DSA for Plan Review Submitted 8/9/2024
6. Lassalette ES Construction Documents At DSA for Plan Review Submitted 8/9/2024 Anticipated Construction Start New Year of 2025
7. Palm ES Construction Documents 50% Const. Docs. District Review 8/16/2024
Interim Housing Los Robles (Tentative)
8. Valinda ES Construction Documents 50% Const. Docs. District Review 8/16/2024
9. Fairgrove K-8 Construction Documents At DSA for Plan Review Submitted 8/12/2024
Interim Housing Del Valle (Tentative)
Anticipated Construction Start Spring of 2025
10. Orange Grove MS Construction Documents Schematic Design
Anticipated Construction Start Summer of 2025
11. Sierra Vista Construction Documents At DSA for Plan Review Submitted 9/17/2024
12. Sparks ES Construction Documents Design Development District Reviewed 8/2/2024
Interim Housing Sunset (Tentative)
Anticipated Construction Start Summer -Fall of 2025
13. Wing Lane ES Construction Documents Design Development District Reviewed 9/18/2024
14. Valley Alternative Construction Documents Design Development District Reviewed 9/19/2024
Anticipated Construction Start Fall of 2025

## Slide 4: DSA PLAN APPROVAL GRAZIDE ELEMENTARY
“Drawings and specifications for the subject project have been examined and stamped by the Division of the State Architect (DSA) 8/29/2024.”

## Slide 5: HIGH SCHOOL REFRESH PROJECTS

## Slide 6: HIGH SCHOOL REFRESH GROUP 1
WORKMAN HIGH SCHOOL
43 CLASSROOMS
LA PUENTE HIGH SCHOOL
55 CLASSROOMS
SCHOOL | START DATE | ANTICIPATED COMPLETION DATE
WORKMAN HS | 1/16/2024 | 9/13/2024 Completed
LA PUENTE HS | 1/16/2024 | 11/1/2024

## Slide 7: REFRESH GROUP 1
Workman HS Phase 4: Classroom C-2
Risers Removed
Before
After

## Slide 8: REFRESH GROUP 1
La Puente HS Phase 4:
Classroom A-12 Before and Progress
Bee
Before
After

## Slide 9: HIGH SCHOOL REFRESH GROUP 2
LOS ALTOS HIGH SCHOOL
69 CLASSROOMS
WILSON HIGH SCHOOL
59 CLASSROOMS
STIMSON LEARNING CENTER
10 CLASSROOMS
SCHOOL | START DATE | ANTICIPATED COMPLETION DATE
WILSON HS | 3/4/2024 | 2/21/2025
LOS ALTOS HS | 3/4/2024 | 4/18/2025
STIMSON EC | 7/1/2024 | 7/31/24 COMPLETED

## Slide 10: REFRESH GROUP 2
Wilson HS Phase 2
Classroom D-2 Before
and After
Before
After

## Slide 11: REFRESH GROUP 2
Los Altos HS Phase 4 Completed Classrooms

## Slide 12
QUESTIONS