| School Name: Frederic T. Greenhalge Elementary School Principal: Jennifer Scarpati School-Site Council Members: Jennifer Scarpati, Principal; Susan Cappellini, Grade 3 Teacher; Elizabeth Kulesza, Grade 4 Teacher; Taylor Mendonca, Grade 1 Teacher; Erin Hart, Pre-K Teacher; Danielle Baribeault, Kindergarten Teacher; Cheryl Squeglia, Music Teacher; Sharon Kearney, Special Education Teacher; Taryn Terwilliger, ELL Teacher; Abby Phillips, Parent; Christine McCann, Parent; Jenelle Lamarche, Parent; Denise Moses, Parent, Nyel Espinola, Parent; Laura Morse, Parent; Officer Mindy Dower, LPD; William Ma,, CTI |  |  |  |
| --- | --- | --- | --- |
| School Mission |  |  |  |
| Educators will support students to master rigorous standards across academic domains within a safe and caring learning environment. |  |  |  |
| School Vision |  |  |  |
| All students will graduate the Greenhalge fully prepared for their middle school experience. |  |  |  |
| Core Values/Commitments |  |  |  |
| - High quality tier one instruction in all academic domains is our priority. - Some students will require differentiated learning supports. These must be provided in a thoughtful, targeted way. - Students must feel safe and cared for in school in order to learn. - Families are a critical component of the educational process. - Extended learning opportunities help to enrich students’ overall educational experience. |  |  |  |
| School Strategic Objectives and Initiatives |  |  |  |
| Leadership, Shared Responsibility, and Professional Collaboration Collective, distributed leadership structures and practices are apparent throughout the school building in the form of an active, well-represented instructional leadership team and grade-level and vertical teams. Administrators and teachers are jointly committed to and have assumed shared ownership and collective responsibility for improving student achievement. | Intentional Practices for Improving Instruction – Engaged Learning School leadership has identified a clear instructional focus and shared expectations for instructional best practices that address clearly identified, student-specific instructional needs. Administrative observations lead to constructive, teacher-specific feedback, supports, and professional development. Provide an engaging, rigorous, and relevant program to meet the academic, social, and emotional needs of each student. | Student-Specific Supports and Instruction to All Students Administrators and teachers use a variety of ongoing assessments (formative, benchmark, and summative) to frequently and continually assess instructional effectiveness and to identify students' individual academic needs (e.g., content or standard-specific academic needs) in order to provide student-specific interventions, enrichment, and supports. | School Climate and Culture Provide human and financial resources to support high quality, engaged learning. Student Safety Ensure two-way, respectful communication, with families, and the LPS community. |
| - Maintain representative leadership structures through ILT, PBIS,Family engagement, and site council committees, as well as PTO. - Continue to hold weekly CPT meetings - Plan at least two opportunities per year for vertical collaboration - Increase the use of data within CPTs, including presentation of student reading benchmarks every 6 weeks. | - PD to focus on improved tier one instruction and incorporation of UDL strategies. UDL course (UDL 101) will be offered. - Increase frequency of administrator feedback to teachers regarding use of discourse strategies, hands-on learning, and rigor of discussion and learning tasks. - At the K-2 level, implement Heggerty phonemic awareness program. Support Teachers’ College Phonics program through purchase of decodable texts - Increase volume and quality of classroom libraries - Offer book study on “Number Sense Routines” to support work in fluency and numbers & operations K-4 - Provide professional development time for curriculum alignment of social studies and science with reading, writing, and Content Literacy in grades 3 & 4. - Refine implementation of Open Circle, a tier one SEL curriculum for K-4, and Second Steps for Pre-K, including supplemental resources. | - School goals and professional development have focused on providing more targeted small group instruction based on data. This work will continue by aligning strategic intervention schedule and research-based interventions with student needs. - Staff need continued training on how to use results of BAS testing to plan guided reading groups. - Strategically utilize i-Ready personalized learning modules for math intervention. - Plan and systematize tier two SEL interventions and social skills groups, using the DESSA assessment. - Collaborate with BRYT for proper implementation of Reset Room model for students exhibiting Tier 2 and Tier 3 behaviors | - Increase parental participation in PTO through use of language affinity groups, and other recruitment methods - Diversify communications, including twitter, facebook, and improving the school website. - Offer at least two events for families that showcase students’ work and learning. - Pending grant status, continue to offer FISS program for families - Implement strategies for improving student attendance including attendance incentives, effective use of SBATMs, and home visits. |
| School Data Profile |  |  |  |
| Data 2019-2021 - click for full data presentation - Showing growth on i-Ready even in remote setting - Reading went from 28% Tier 1 to 34% Tier 1 - Math went from 17% Tier 1 to 21% Tier 1 - In February 2020, BAS Reading proficiency were as follows (Gr. 1-4) - 58, 48, 56, 51% - In Fall 2020, scores were 18, 2, 22, 23%, we are waiting on the February scores - Attendance - significant reduction in % of students chronically absent - 27% (2018) - 22% (2019), this has increased during remote learning to 34% - Conduct - conduct referrals increased last year- over 500 major referrals in 2019-2020 SY. |  |  |  |
| Reflection on Current Practices |  |  |  |
| - What are your current efforts in targeting school improvement? How can you leverage these efforts when determining school priorities? Offering UDL course for staff Focus on phonics & phonemic awareness work K-2 Focus on guided reading 3-4 Continue implementation, monitor, and refine SEL initiatives from 20-21 All special educators Orton-Gillingham trained These will build the foundational work for the next steps listed above. - What progress is your school making towards academic goals? What is data saying the priorities should be? Where there is not desired progress, what is holding up momentum that should be addressed? School-wide progress has been demonstrated through i-Ready testing and benchmark assessments. A continued focus on phonics and comprehension is warranted, as well as continued focus on numbers & operations and problem solving. We continue to struggle with progress with some of our students that are significantly below level in reading. We will focus on phonics & phonemic awareness in K-2 and guided reading in 3 & 4. - Where are students making the greatest academic gains and why? The least academic gains and why? Prior to the shutdown, students in K and 1 were demonstrating significant growth in reading scores. Students in grades 3 & 4 have larger gaps in their reading scores, due to less than expected progress for students who are below level in reading. |  |  |  |

| Monitoring Progress - Process Benchmarks What will be done, when, and by whom |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Leadership, Shared Responsibility, and Professional Collaboration | Person Responsible | Aug 2021 | Dec 2021 | June 2022 | Status |
| Ensure representation on school committees and create schedule for 21-22 school year; create master calendar for weekly CPT meetings | Principal | X |  |  |  |
| Recruit new members for PTO and hold at least two family events | Principal, Parent Liaison, Family engagement committee, PTO | X |  | X |  |
| Plan time for vertical team meetings | Principal, AP & Coaches |  | X | X |  |
| Generate and review reading data in 6 week intervals | Literacy Coach, teachers | x | X | X |  |
| Intentional Practices for Improving Instruction – Engaged Learning | Person Responsible | Aug 2021 | Dec 2021 | June 2022 | Status |
| Offer UDL 101 course for staff | AP, teachers | x | x |  |  |
| Provide feedback to teachers on use of strategies that increase rigor and engagement in 6-8 week intervals | Principals & Coaches & ILT | x | x | x |  |
| Offer a book study on “Number Sense Routines” for teachers | Principals & Coaches & ILT | x | x |  |  |
| Offer PD time for curriculum development to integrate social studies and science with language arts and content literacy | Principal, Grade 3 & 4 teachers | x | x |  |  |
| Implement Heggerty phonemic awareness program K-2 | Literacy Specialist, K-2 teachers | x | x | x |  |
| Purchase decodable readers and classroom libraries | Principal & Literacy specialist | X |  |  |  |
| Monitor implementation of and enrichment of Open Circle Curriculum | Principal, social workers | x | x |  |  |
| Student-Specific Supports and Instruction to All Students | Person Responsible | Aug 2021 | Dec 2021 | June 2022 | Status |
| Provide more in-depth training on using the benchmark assessment/Reading A-Z Assessment results to tailor lesson plans for guided reading groups through formal lesson study/PD/Coaching. | Literacy specialist | x | x |  |  |
| Design a strategic intervention schedule that targets research-based interventions to students’ needs | Principal, literacy specialist | X |  |  |  |
| Match students struggling in math with i-Ready instructional modules, as appropriate | Principal & AP | x | x |  |  |
| Continue implementation of Tier 2 SEL interventions based on universal screeners | Principal, Social Workers |  | x |  |  |
| Participate in BRYT trainings and implement intake process for Reset Room | Principal, Social Workers | x | x |  |  |
| School Climate and Culture | Person Responsible | Aug 2021 | Dec 2021 | June 2022 | Status |
| Recruit new members for PTO through recruitment at Open House and language affinity groups | Principal, Parent liaison | x |  |  |  |
| Diversify communications to include paper/online newsletters (S’more), Class Dojo messages, facebook, twitter, and up to date website. | Principal, AP | x |  |  |  |
| Offer at least two parent showcases of student work in order to increase parental engagement in the curriculum, leverage language affinity groups as part of this process | Principal, ILT, parent liaison |  | x | x |  |
| Hold orientations and meetings for our PK & K families to increase engagement as well as parent education meetings | SW & parent liaison | X | X |  |  |
| Attendance team will meet at least biweekly to review student attendance and implement improvement strategies including SBATMs, home visits, and attendance incentives | Principal, Social workers, Parent Liaison | x | X | X |  |

| Measuring Impact Changes in practice, attitude, or behavior when the initiative is having its desired impact. Desired Targets. |  |  |  |
| --- | --- | --- | --- |
| Leadership, Shared Responsibility, and Professional Collaboration | Person Responsible | Date | Status |
| CPT notes will reflect regular use of data to drive instruction | Principals, Coaches | December 2021 |  |
| Survey results indicating staff approval of opportunities for input, collaboration, and shared leadership | Principal | September 2021 & May 2022 |  |
| Family attendance at student showcases | Parent liaison | June 2022 |  |
| Intentional Practices for Improving Instruction – Engaged Learning | Person Responsible | Date | Status |
| Students will demonstrate expected growth in Reading, as measured by the F&P Benchmark assessment | Principal & AP & ILT | May 2022 |  |
| Increased feedback to teachers and teaching teams on their use of student engagement strategies - feedback will be provided at least every 6 weeks. | Principal & AP | December 2021 |  |
| Teacher enrollment in UDL 101 course and Number Sense book study | Principal & AP | December 2021 |  |
| A tier one SEL curriculum will be provided to all students according to curriculum guidelines | Principal & Social Workers | September 2021 |  |
| Student-Specific Supports and Instruction to All Students | Person Responsible | Date | Status |
| Increased growth in reading levels, as measured by the BAS/Reading A-Z | Literacy Specialist | May 2022 |  |
| Increased growth in math levels, as measured by the i-Ready math assessment | Principal, AP & teachers | May 2022 |  |
| Tier two SEL interventions will be provided for all students identified through the universal screening process (DESSA) | Principal, Social Workers | December 2021 |  |
| Reduced conduct referrals | Principal, AP, Social workers & teachers | May 2022 |  |
| School Climate and Culture | Person Responsible | Date | Status |
| Increase PTO participation so that average meeting attendance is at least 10 members | Principal, Parent liaison | December 2021 |  |
| The school will disseminate at least 3 communications per week, utilizing a range of media, including paper, S’more, DOJO, Facebook, Twitter, website updates, Blackboard Connect | Principal, AP, parent liaison | September 2021 |  |
| At least two curriculum showcase events will be hosted for parents. Attendance sheets will be collected. | Principal, ILT, Coaches, Parent liaison | May 2022 |  |
| Reduction in percentage of students deemed chronically absent | Principal & AP & Social Workers | May 2022 |  |