## Slide 1: HACIENDA LA PUENTE UNIFIED SCHOOL DISTRICT
Regular Board Meeting October 24, 2024
Business Services
School Site Improvement Projects
Notes: Good evening Ma’dam President, Ms. Christine Salazar, Distinguish Board Members; Superintendent, Dr. Jimenez, Executive Cabinet, Colleagues, and community members.
A special greetings to our Principals, Administrators, staff member who are joining us via the virtual platform.

## Slide 2
Site | Item Description | Funding Source | Completed Date
Fairgrove Academy | Playground & Shade Structure | Child Development | 09/2024
Lassalette Elementary School | Inclusive Playground | Facilities | 09/2024
Nelson Elementary School | Playground, Shade Structure, & Accessibility Path of Travel | Child Development | 09/2024
Sierra Vista Middle School | HVAC Repair MPR Room | Facilities | 09/2024
Dibble Adult Education | Phase II of Re-Roofing | Adult Ed | 10/2024
Districtwide | Trip Hazard Repair/ Ramp Repair | Facilities | 10/2024
Lassalette Elementary | Playground Restriping | Facilities | 10/2024
Los Altos High School, Buildings 60s, 70s | Gym & Locker Room HVAC (65 tons of temporary HVAC units have been installed) | Facilities | 10/2024
Wing Lane Elementary School | HVAC Repair | Facilities | 10/2024
PROJECT COMPLETE LIST
Changes And Progress Since Last Report - Blue
2024/2025

## Slide 3: Projects Completed as of October 24, 2024 Fairgrove Academy – Playground & Shade Structure
AFTER
BEORE

## Slide 4: Projects Completed as of October 24, 2024 Lassalette Elementary School – Playground Restriping
AFTER
BEORE
BEFORE
AFTER

## Slide 5: Projects Completed as of October 24, 2024 Lassalette Elementary School – Inclusive Playground
AFTER

## Slide 6: Projects Completed as of October 24, 2024 Nelson Elementary School – Playground & Shade Structure

## Slide 7: Projects Completed as of October 24, 2024 Districtwide – Trip Hazard Repair (Sierra Vista Middle School)
AFTER
BEORE

## Slide 8: Projects Completed as of October 24, 2024 Districtwide – Ramp Repair
AFTER
BEORE

## Slide 9: Projects Completed as of October 24, 2024 Wing Lane Elementary School, Building 60 – HVAC Repair
AFTER
BEORE

## Slide 10: Projects In Progress 2024-2025

## Slide 11: Projects in Progress as of October 24, 2024
Site | Item Description | Architect Plans | DSA Approval | Procurement | Construct | Funding Source | Target Completion Date
District Office | Data Center Move | Complete | N/A | Complete | Pending | ESSR/General | TBD
Districtwide | HVAC System Replacement | Pending | TBD | TBD | TBD | Facilities | TBD
Grazide Elementary School | Portable 7 | N/A | N/A | Pending | Pending | Facilities | TBD
Kwis Elementary School | Baseball Fields | Complete | Approved | In Progress | TBD | Grant | TBD
La Puente High School | Custom Shade Structure | Complete | Approved | Pending | Pending | Facilities | TBD
Los Altos High School | Stadium Press Box & Bleachers | Complete | Pending | Pending | Pending | Facilities | TBD
Stimson Learning Center | Phase II of re-roofing | Complete | Complete | Complete | In Progress | Facilities | 12/2024
Wedgeworth Elementary School | K-5 Permanent School | Complete | Approved | Complete | In Progress | COPS | 06/2025
Wilson High School | Media Center | Pending | TBD | TBD | TBD | Grant | 06/2025
Wilson High School | Stadium Press Box & Bleachers | Complete | Pending | Pending | Pending | Facilities | TBD
Workman High School | Phase II Stadium and Baseball Field | Complete | Approved | Approved | In Progress | Facilities | TBD
Workman High School | Shade Structure, Wall, & Track Lighting | Complete | Pending | Pending | Pending | Facilities | TBD
Facilities
Notes: Los Altos High School, expected to begin in July

## Slide 12: Projects in Progress as of October 24, 2024
Site | Item Description | Architect Plans | DSA Approval | Procurement | Construct | Funding Source | Target Completion Date
Amar Center | Entry Security Project | Complete | Approved | Pending | Pending | Child Development | TBD
Amar Center | Phase II of Re-Roofing | N/A | N/A | Pending | Pending | Child Development | TBD
Workman Elementary School Head Start | Playground & Accessibility Path of Travel | Pending | TBD | TBD | TBD | Child Development | TBD
Changes And Progress Since Last Report - Blue
Child Development

## Slide 13: Projects in Progress as of October 24, 2024
Site | Item Description | Architect Plans | DSA Approval | Procurement | Construct | Funding Source | Target Completion Date
Center for the Performing Arts | Center for the Performing Arts | In Redesign | Complete | Pending | TBD | Adult Ed | TBD
Dibble Adult Ed | Admin Upgrade | In Progress | NA | TBD | TBD | Adult Ed | TBD
Willow Adult Ed | Marquee | Complete | NA | Pending | TBD | Adult Ed | TBD
Changes And Progress Since Last Report - Blue
Adult Ed

## Slide 14: Projects in Progress as of October 24, 2024
Site | Item Description | Architect Plans | DSA Approval | Procurement | Construct | Funding Source | Target Completion Date
Baldwin Academy | Kitchen Renovation - Three Compartment Sink Installation | Complete | NA | Pending | TBD | Food Services | TBD
District Office | Warehouse Freezer | Complete | NA | Pending | TBD | Food Services | TBD
Mesa Robles Middle School | Kitchen Renovation | Complete | Approved | Pending | TBD | Food Services | TBD
Wilson High School | Kitchen Modernization | Pending | Pending | Pending | TBD | Food Services | TBD
Changes And Progress Since Last Report - Blue
Nutrition Services
Notes: Kwis Baseball – Will be Re-Bid, uncertified entry was added to scope of work into the project.
Cedarlane Portable – In design phase with PBK architecture. Soils samples being conducted.
Willow Adult School = Two Story Building continues to be under construction. It coming along very well.

## Slide 15
Next Report – December 17, 2024