## Slide 1
Community Service Graduation Requirement Update
Board of Education Meeting
February 11, 2015
Herman Mendez, Superintendent
Deborah Stark, Ed.D., Assistant Superintendent, Educational Services
Manuel San Miguel, Ed.D., Director, Educational Services
Great Things Are Happening In Paramount Schools - Where We Inspire Great Learning Through Great Teaching
Great Things Are Happening In Paramount Schools - We Inspire Great Learning Through Great Teaching

## Slide 2: Purpose of Presentation
Provide the Board an update on the progress of the Community Service Graduation Requirement.
Outline next steps.

## Slide 3: Community Service Action Plan
The Board was provided an Action Plan on January 23, 2015 that outlined specific actions that would be taken to ensure all seniors fulfill their Community Service Graduation Requirement.

## Slide 4
Action | Person Responsible | Date
Assign Community Service staff member for PHS. Develop targets for completion of community service hours, calendar of events. | Manuel San Miguel, Greg Buckner | January 13
Identify seniors in need of Community Service hours. | Manuel San Miguel Rachel Dominguez | January 16
Create calendar of Community Service events. | Manuel San Miguel Rachel Dominguez | January 16
Meet with seniors to discuss Community Service events, sign up, and log hours. | Manuel San Miguel Rachel Dominguez | January 22
Create action plan to address areas of need. | Manuel San Miguel Rachel Dominguez | January 22
Explore additional Community Service opportunities. | Manuel San Miguel Rachel Dominguez | February
Communicate with parents of seniors who need to complete hours (letters, phone calls). | Manuel San Miguel Rachel Dominguez | January 30
Plan school sponsored Saturday beach clean-up days every Saturday in February, March and April. | Manuel San Miguel Rachel Dominguez | February – April
Update completed community Service hour. Provide written update to Board of Education. | Manuel San Miguel Rachel Dominguez | February 27 March 27 April 24
Meet with Community Service Staff, Advisors from PHS, PHS-West and Director of Student Service to update progress. | Manuel San Miguel Rachel Dominguez | Monthly, January through May
Provide updates to school administrators. | Manuel San Miguel Rachel Dominguez | Monthly, January through May

## Slide 5: Update on Student Progress
Students |  |  |  | 
Hours | November 2014 | December 2014 | February 2015 | Percentage of Students
30 or More | 418 | 468 | 551 | 50%
20 to 29 | 113 | 124 | 118 | 10%
1 to 19 | 351 | 325 | 286 | 26%
No Hours | 232 | 205 | 153 | 14%
40%

## Slide 6: Next Steps
Continue to:
  Seek out new Community Service opportunities.
  Meet with students and provide activities for students to complete hours.
  Track student progress.
  Communicate with parents on progress.
  Update Board of Education on progress and policy.

## Slide 7: Questions?