# School Comprehensive Education Plan

# 2025-26

| District | School Name | Grades Served |
| --- | --- | --- |
| Kingston CSD | Chambers | K-4 |

Collaboratively Developed By:

The Chambers SCEP Development Team Kate Berardi Melissa Potter Jessica Benjamin Laura Feeney Heidi Malenski Sarah Gruber Andrea Stenta Maria Rojas Jackie Nelson Cori Zupko-Williams Amy Fetahi Heather Watzka Amanda Green Megan Fuoco Jocelyn Kraft Alicia Chisaguano Noemy Aguirre Raul Jimenez Enma Villacis Sonia Lliviasaca Yenny Munoz Munoz Ninette Warner And in partnership with the staff, students, and families of Chambers School

# Guidance for Teams

## Navigating the Plan

You can expand or collapse any section of the plan by clicking the triangle next to the blue headings. Additionally, you can move through sections using the Navigation Pane in Microsoft Word.

## Before Writing the Plan

Before working on this document, school teams should have:

- Completed the Five-Part Needs Assessment, which consists of:

  - Activity 1: Analyze: Data Variation Identification

  - Activity 2: Analyze: Data Variation Share and Explore

  - Activity 3: Analyze: Survey Data

  - Activity 4: Listen: Student Interviews

  - Activity 5: Envision: Reflect and Synthesize

- Met with their NYSED/District/BOCES liaison:

- Following Activity 1: Analyze Data Variation Identification

- Following Activity 5: Envision: Reflect, Synthesize, and Plan after identifying the Key Strategies and before writing the implementation plan.

- Met with their district to share ensure alignment and coherence between the school’s improvement vision and the district’s vision.

## Key Strategies

Schools must identify the evidence-based, high-impact levers, known as “Key Strategies,” they believe will improve current outcomes.  Each Key Strategy should represent a change in the upcoming year compared to previous years.  The Key Strategy should fall into one of the following categories:

- Something new to the school; or

- An existing strategy being expanded to reach a wider audience; or

- An existing strategy being refined or adjusted from previous years.

To ensure effective implementation, school teams must be strategic in selecting the number of approaches they plan to use to improve outcomes, avoiding the temptation to implement too many initiatives.  To assist this process, NYSED has provided the following guidance:

- At least 1 Instructional Key Strategy must be identified.

- Non-Instructional Key Strategies are optional.

- Total number of Key Strategies (Instructional and Non-Instructional combined) must be between 2 and 5.

- Non-Instructional Key Strategies should not outnumber Instructional Key Strategies.

These Key Strategies should be aligned with the data reviewed and student interviews from the needs assessment. Teams must also explain the rationale for each Key Strategy selected on the provided template.

Schools may find Hattie’s High Impact Teaching Strategies and the resources gathered at Visible Learning, especially the Teaching Strategies, to be helpful resources when considering Key Strategies.  The Diagnostic Tool for School and District Effectiveness (DTSDE) Framework and Phases of Implementation may also be useful when considering different options to pursue.

## Key Strategy Implementation

For each Key Strategy, the school team needs to outline its implementation plan for the upcoming year.

- For new strategies, the plan should detail how the strategy will be introduced and rolled out.

- For expanded strategies, the plan should explain how the expansion will occur.

- For refined strategies, the plan should highlight how this year’s approach differs from previous years.

Each plan should include a sequence of activities that build upon one another. In the column to the right of each activity, include the target date for implementation.  This will help the team track progress during the 2025-26 school year.

## Key Strategy Progress Monitoring

After identifying their Key Strategies, school teams should set success criteria and benchmarks to evaluate progress throughout the year.

Each Key Strategy must include at least one Early Progress Milestone to provide early feedback on the strategy’s success. The data, which could be implementation data and/or outcome data, should directly align with the Key Strategy.

Each Key Strategy must include at least one outcome-based Mid-Year Benchmark and End-of-The-Year target that is directly related to the strategy.

## Performance Targets

In addition to setting Mid-Year Benchmarks and End-of-Year targets for each Key Strategy, the plan must also establish overall Performance Targets that reflect the anticipated improvement from the combined impact of all strategies. While the Key Strategy Progress Monitoring will track data specific to each individual strategy, the Performance Targets serve as broader indicators of overall school improvement.

## Ongoing Monitoring

The plan template allows school teams to revisit and update their plan throughout the year. A designated section tracks progress for each Key Strategy and for the Performance Targets, allowing teams to record outcome data or evidence alongside original targets. This section should remain blank when first writing the plan and will be updated throughout the year as the team assesses the success of the plan.

## SCEP Rubric

NYSED has created the SCEP Rubric to help teams identify areas for improvement in their plan.  The rubric can be a valuable reference tool while writing the plan.  After completing the initial draft, schools should self-assess using the rubric before finalizing their plan.

## Resources for Team

- Assembling Your Improvement Planning Team

- NYSED Improvement Planning website: http://www.nysed.gov/accountability/improvement-planning

# Evidence-Based Intervention

All key strategies pursued by schools should be rooted in evidence.  All schools in the CSI, ATSI, and TSI support models must implement at least one evidence-based intervention that meets the criteria of a Tier 1, Tier 2, or Tier 3 evidence-based intervention under ESSA. More information can be found at: http://www.nysed.gov/accountability/evidence-based-interventions.

School teams should indicate all of the evidence-based interventions that meet the federal definition that will be pursued next year by placing an “X” in the corresponding box below.  Schools that adopt the State-Supported Evidence-Based Intervention under the parameters outlined at: https://www.nysed.gov/accountability/state-supported-evidence-based-strategies will fulfil the evidence-based intervention requirement.

| State-Supported Evidence-Based Interventions | Mark “X” if the school will implement this in 25-26 |
| --- | --- |
| Align High School and College Courses to Increase Post-Secondary Transition Outcomes |  |
| Community Schools |  |
| Elementary School Looping |  |
| Establish an Early Warning Intervention and Monitoring System |  |
| Evidence-Based Instructional Methods |  |
| Expanding access to high-quality Out-of-School-Time programs |  |
| High-Quality Instructional Materials | x |
| High-Quality Tutoring |  |
| Incoming Student Induction Programs and Summer Bridge Programs |  |
| Instructional Coaching |  |
| Middle School Flexible Scheduling |  |
| Multi-Tiered System of Supports – Integrated (MTSS-I) |  |
| Ongoing Job-Embedded Professional Development |  |
| Principal Leadership Development |  |
| Professional Learning Communities |  |
| Restorative Practices |  |

Other (required if no State-Supported Evidence-Based Intervention is identified above): Identify and describe a School-Identified Intervention that meets the criteria of a Tier 1, Tier 2, or Tier 3 Evidence-Based Intervention. Please also indicate the Clearinghouse, Evidence Review, or research that indicates the intervention qualifies as a Tier 1, Tier 2, or Tier 3 Evidence-Based Intervention.

# Learning as a Team

## Directions

Teams should complete the reflective prompt below.

### Student Interviews

Describe how the Student Interview process informed the team’s plan

Across all grade levels, Chambers students expressed enthusiasm for learning new content and exploring unfamiliar topics. CKLA supports this by intentionally building background knowledge and exposing students to diverse subjects. Students shared that they enjoy the topics and like learning about things that they have never learned about before. They expressed that they like when things are “hard” and they look forward to the challenges. Students interviewed who were not part of the pilot groups did not share that things we challenging this year and seemed to have less enthusiasm for learning than those in the pilot groups. Students also expressed wanting to do more “regular math”. After further questioning, this was determined to be more fact practice, as many of them stated that they didn’t feel they had a grasp on math facts and automaticity. Generally, all students stated that they enjoyed our whole school activities the most, particularly field day and Morning Meeting and stated that they felt that those things were the source of our strong school community.

Schools in the ATSI and TSI model only

### Subgroup Spotlight

Describe how the team has determined that the strategies within this plan are likely to result in improved subgroup performance for the subgroup(s) for which the school has been identified.

# Instructional Key Strategies for Improvement

## Key Strategies

(What are we doing? Why are we doing this?)

In column 1, input at least one, but no more than five strategies that reflect something new the school is introducing or something currently in existence that the school is expanding or refining for the upcoming school year.  In column 2, specify whether the strategy is something new, something being expanded, or something being refined.  In column 3, identify the data that indicates these strategies will be beneficial for the school.  For any Key Strategy that is not new, provide a 1-2 sentence summary of how the key strategy will be expanded or refined next year.

| KEY STRATEGY (What are we doing?) | HOW TO DOES THIS COMPARE TO EXISTING EFFORTS? | WHY: What did we learn from our needs assessment that suggests this is the right Key Strategy and will have a positive impact on students? Use evidence. Consider both data trends observed and student interview responses. Additionally, for any Key Strategy that does not represent something new, provide 1-2 sentences describing how the school will expand or refine the Key Strategy next year. |
| --- | --- | --- |
| Chambers School staff will facilitate a comprehensive implementation of CKLA, a Tier 1 Reading program, during the 2025-2026 school year. | NEW EXPAND REFINE | This initiative will involve collaboration among all educators supporting student learning to ensure instruction is aligned, student needs are met at every level, and learning is maximized. The intended outcome is a measurable increase in the number of students reading and performing at grade level. When we looked at iReady data from the CKLA pilot classes, it was clearly evident, that within one year, most participating students outperformed their peers on the assessments. This was a clear indication that a consistently implemented Tier 1 curriculum would aide in increasing student performance. |
| Chambers School will develop a comprehensive plan that will aim to increase math fact fluency and create more automaticity and recall ability in students. | NEW EXPAND REFINE | The District Resource Allocation Review revealed a disparity between the demographics of students enrolled in middle school advanced math and the overall student population. The team recognized the need to cultivate a strong, early interest in math to increase long-term participation and access to advanced coursework. Concurrently, the students interviewed at Chambers spoke of not feeling adequately prepared with basic math facts, leading to less math readiness for higher level math. iReady data is showing that our students have made growth this year, but this strategy aims to provide students with research-based learning opportunities that will increase their comfort level with higher level math. |

## Implementation

How will we do this?

| KEY STRATEGY 1 | Chambers School staff will facilitate a comprehensive implementation of CKLA, a Tier 1 Reading program, during the 2025-2026 school year. |
| --- | --- |

| BEFORE THE 1st DAY OF SCHOOL IMPLEMENTATION What is our plan for preparing our school for success with this Key Strategy before the school year starts? What steps are involved? | When will this be in place? |
| --- | --- |
| CRE/WELLNESS: Teachers will assess/organize their own classroom for Culturally Responsive materials related to CKLA units. | 9/25 |
| CE: Coordinate and brainstorm guest speakers that align with CKLA units. | 9/25 |
| Secure staff volunteers for events | 9/25 |
| Begin to coordinate guest readers for the beginning of the school year (will continue to schedule as the year progresses) | 9/25 |
| CKLA: Teachers will familiarize themselves with materials. | 9/25 |
| School Leader will ensure all non-classroom teachers and teaching assistants have access to CKLA curriculum. | 9/25 |
| School Leader will create a schedule to maximize time. | 9/25 |
| WALT Whiteboards purchased and installed outside classrooms to share CKLA learning goals each day. | 9/25 |
| Classroom and special area teachers will meet during the first week to discuss integration of topics. This will continue on the last Friday of each month. | 9/25 |
| FIRST HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the first half of the year? What steps are involved? | When will this be in place? |
| CRE/WELLNESS: Teachers will collaborate with the Librarian and/or the Director of DEI to have culturally Responsive books related to CKLA units. | 9/25 |
| CE: Identify and secure guest speakers for morning meeting and schedule to align with CKLA units. | 10/25 |
| Plan and schedule parent readers to volunteer to read CKLA aligned stories to each class (goal of one reader per unit in each class). | 9/25 |
| CKLA: School Leader will create a schoolwide timeline for connecting historical topics studied in CKLA. This will be contributed to by all classrooms and will grown throughout the year. | 9/25 |
| Teachers/co-teachers/special area teachers will share best practices during monthly/bimonthly common planning times (2nd and 3rd Friday’s of each month) | 9/25 |
| SECOND HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the second half of the year? What steps are involved? | When will this be in place? |
| CRE/WELLNESS: Teachers will identify CKLA topics that need more Culturally Responsive materials and will provide a list of materials needed to the School Leader | 1/26 |
| CE: Community Engagement Team will begin planning for a January Make and Take Night. The theme for the event will align with CKLA and math key strategies. | 1/26 |
| CKLA: Students will begin weekly presentations of CKLA learning/knowledge in schoolwide morning meetings – one grade per week on a rotating basis. | 1/26 |
| Marching Through Time will become our theme for Read Across America Month. The plan for the month will incorporate CKLA learning. (CKLA committee will meet with school leader to plan) | 3/26 |

### Progress Monitoring

How will we measure progress and impact for this Key Strategy?

|  | What data will we be reviewing? | What do we hope to see when we review that data? | What we ended up seeing. What are our next steps? complete when reviewing data |
| --- | --- | --- | --- |
| Early Progress Milestones (implementation/outcome data) | Knowledge end-of-domain assessments (Grades K–2) End-of-unit assessments (Grades 3–5) | 100% completion of these assessments by all students |  |
| Mid-Year Benchmark(s) (outcome data) | Knowledge end-of-domain assessments (Grades K–2) End-of-unit assessments (Grades 3–5) | 100% completion of these assessments by all students + 50% of our students scoring proficiently on the assessments |  |
| End-of-the Year Targets (outcome data) | Knowledge end-of-domain assessments (Grades K–2) End-of-unit assessments (Grades 3–5) | 100% completion of these assessments by all students + 70% of our students scoring proficiently on the assessments |  |

| KEY STRATEGY 2 | Chambers School will develop a comprehensive plan that will aim to increase math fact fluency and create more automaticity and recall ability in students. |
| --- | --- |

| BEFORE THE 1st DAY OF SCHOOL IMPLEMENTATION What is our plan for preparing our school for success with this Key Strategy before the school year starts? What steps are involved? | When will this be in place? |
| --- | --- |
| CRE/WELLNESS: Teachers will create a math fact fluency tool kit (Chambers Challenge Kit) for home use to eliminate barriers and engage families. These toolkits will be highlighted at Back to School Night. | 9/25 |
| CE: School Leader will work with the CE Team to create YouTube learning videos that can be accessed from home and used as a companion to the Chambers Challenge Kit. | 8/25 |
| FIRST HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the first half of the year? What steps are involved? | When will this be in place? |
| CRE/WELLNESS: Teachers will volunteer to create videos about different math games and strategies for students to watch/play at home. | 10/25 |
| CE: The Community Engagement Team will plana fall community engagement night that will focus on Math Games and family math engagement. | 9/25 - 10/25 |  |
| The School Leader will highlight math fact cards on the Morning Announcements each morning (visible on the screen from 8:45-8:55) and teachers will ensure students have access to this. | 9/25 – 6/26 |
| The School Leader will incorporate one math fact game into each Friday Morning Meeting of the school year. | 9/25-6/26 |
| SECOND HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the second half of the year? What steps are involved? | When will this be in place? |
| CRE/WELLNESS: The CRE/Wellness Team will collaborate with the CE Team to organize a Math Night. | 9/25-10/25 |
| The Math March, a spin on the Snowflake Stroll, will be developed in the Spring of 2026. Students will engage in a day of hands on, math activities, rotating between each classroom | 3/26 |
| CE: The CE Team will develop and execute Make and Take Night. The focus for 2026 will be Math Strategies and Fluency | 1/26/26 |  |

### Progress Monitoring

How will we measure progress and impact for this Key Strategy?

|  | What data will we be reviewing? | What do we hope to see when we review that data? | What we ended up seeing. What are our next steps? complete when reviewing data |
| --- | --- | --- | --- |
| Early Progress Milestones (implementation/outcome data) | iReady diagnostic data | Individual student growth on iReady between 2024-25 and 2025-26 |  |
| Mid-Year Benchmark(s) (outcome data) | iReady Winter diagnostic | 50% or more of students making growth on iReady |  |
| End-of-the Year Targets (outcome data) | iReady Spring diagnostic | 75% or more of students making growth on iReady |  |

# Non-Instructional Key Strategies for Improvement

## Key Strategies

(What are we doing? Why are we doing this?)

| KEY STRATEGY | HOW TO DOES THIS COMPARE TO EXISTING EFFORTS? | WHY: What did we learn from our needs assessment that suggests this is the right Key Strategy and will have a positive impact on students? Use evidence. Consider both data trends observed and student interview responses. Additionally, for any Key Strategy that does not represent something new, provide 1-2 sentences describing how the school will expand or refine the Key Strategy next year. |
| --- | --- | --- |
| Chambers School staff will facilitate the implementation of the Beeutiful Trail, a nature trail developed on the school property. | NEW EXPAND REFINE | Our student interviews indicated that students are looking for more: - Opportunities for real-world learning application - Opportunities for leadership - Opportunities to come together as a community The trail will incorporate themes of physical, social, and mental wellness and will provide for student leadership opportunities, hands on, real-world learning, and a greater appreciation of the cultures within our community. The result of this implementation will be reflected in survey data from staff, students, and families, as well as parent engagement at school events. |

## Implementation

(How will we do this?)

| KEY STRATEGY 1 | Chambers School staff will facilitate the implementation of the Beeutiful Trail, a nature trail developed on the school property. |
| --- | --- |

| BEFORE THE 1st DAY OF SCHOOL IMPLEMENTATION What is our plan for preparing our school for success with this Key Strategy before the school year starts? What steps are involved? | When will this be in place? |
| --- | --- |
| CRE/WELLNESS: The ribbon cutting will be 6/11/25. The teachers will be taught how to use the Beeutiful Trail on 6/12/25 New staff members will also be given an overview of the trail during SCD on 9/2 | 6/11/25 |
| CE: Promote ENL Potluck at June Trail ribbon cutting. | 6/25 |
| Promote the trail by handing out flyers during community events. | 6/25-9/25 |
| Help to organize details regarding the opening of the trail as needed | 6/25 |
| CKLA: Teachers will familiarize themselves with the trail and any instructional overlaps. | 8/25 |
| School Leader: Create the Digital Trail Guide to help engage the community in the Beeutiful Trail, thus increasing family and community engagement during afterschool hours | 6/25 |
| FIRST HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the first half of the year? What steps are involved? | When will this be in place? |
| The School Leader will highlight the trail on the morning announcements to encourage both staff and student use - station highlights - selfie collections - short videos about new additions to the trail | 9/25 |
| CRE/WELLNESS: The CRE/Wellness Team will manage the implementation of the trail and will facilitate the coordination of the stations as they begin to change with the 2025-26 school year. They will create a working document in which teachers can upload new station ideas and meet with trail managers to help execute them. |  |
| CE: The Community Engagement Team will plan for and execute the inclusion of the Beeutiful Trail in Back to School Night. | 9/25 |
| The Community Engagement Team will plan for incorporating the Trail into all events that they facilitate for the 2025-26 school year. | 9/25 |
| CKLA: Classroom Teachers will begin to plan for new trail station additions (to be completed by January 2026) that will include CKLA topics and the integration of those into the Beeutiful Trail stops. The trail will stops will remain fluid and will change as learning evolves throughout the year. | 9/25 |
| Each class will visit the trail at least once per month. | 9/25 |
| SECOND HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the second half of the year? What steps are involved? | When will this be in place? |
| CRE/WELLNESS: The CRE/Wellness Team will continue to manage the implementation of the trail and will facilitate the coordination of the stations as they begin to change with the 2025-26 school year. They will create a working document in which teachers can upload new station ideas and meet with trail managers to help execute them. All classes will have updated their trail stop by 2/26 | 2/26 |
| CE: The Community Engagement Team will continue incorporate the Trail into all events that they facilitate for the 2025-26 school year. | 1/26 |
| All sub-teams (CE, CKLA, CRE/Wellness) will work together to plan for a year end Beeutiful Trail Celebration. The goal of each station will be to have some element of CKLA learning incorporated into each trail station. The final trail changes will be completed by 4/26 and the event will be planned for 6/26 | 4/26 |

### Progress Monitoring

How will we measure progress and impact for this Key Strategy?

|  | What data will we be reviewing? | What do we hope to see when we review that data? | What we ended up seeing. What are our next steps? complete when reviewing data |
| --- | --- | --- | --- |
| Early Progress Milestones (implementation/outcome data) | Visits to the Beeutiful Trail Digital Guide | An increase in the number of visits as the trail is promoted to stakeholders |  |
| Mid-Year Benchmark(s) (outcome data) | Mid year survey | Increased opportunities for stakeholder groups |  |
| End-of-the Year Targets (outcome data) | End of year survey | Satisfaction of stakeholder groups (100% agreement for all questions regarding the Beeutiful Trail) |  |

## Non-Academic Performance Targets

### Mid-Year Benchmarks and End-Of-The-Year Targets

We believe successful implementation of these Non-Instructional strategies will allow us to reach the following mid-year benchmarks and end-of-the-year goals.

|  | What student data will we be reviewing? | What Key Strategies are intended to directly impact this student data? | What do we hope to see when we review that student data? | What we ended up seeing: (complete when reviewing mid-year data) |
| --- | --- | --- | --- | --- |
| Mid-Year Benchmark(s) | Mid year survey | Chambers School staff will facilitate the implementation of the Beeutiful Trail, a nature trail developed on the school property. | 75% of students are in agreement that the Beeutiful Trail provides opportunities for hands-on, interactive learning. |  |
| End-of-the Year Targets | End of year survey | Chambers School staff will facilitate the implementation of the Beeutiful Trail, a nature trail developed on the school property. | 100% of students are in agreement that the Beeutiful Trail provides opportunities for hands-on, interactive learning. |  |

### Spring Survey Targets

We believe these Spring survey responses will give us helpful feedback about our progress with our Non-Instructional Key Strategy/Key Strategies:

|  | Survey Question(s) or Statement(s | Corresponding Key Strategies | 2024-25 data if available (e.g., % agree or strongly agree) | Desired response (e.g., % agree or strongly agree) | What we ended up seeing: (complete once Spring survey results are available) |
| --- | --- | --- | --- | --- | --- |
| Student Survey | The Beeutiful Trail has helped me to learn new things that I didn’t know before. | Chambers School staff will facilitate the implementation of the Beeutiful Trail, a nature trail developed on the school property. | n/a | 100% |  |
| Staff Survey | The Beeutiful Trail has increased the learning opportunities for my students. | Chambers School staff will facilitate the implementation of the Beeutiful Trail, a nature trail developed on the school property. | n/a | 100% |  |
| Family Survey | The Beeutiful Trail has provided me with a way to connect with my child’s learning. | Chambers School staff will facilitate the implementation of the Beeutiful Trail, a nature trail developed on the school property. | n/a | 100% |  |

# Our Team’s Process

## Background

NYSED requires that the SCEP is developed in consultation with parents and school staff, and in accordance with §100.11 of Commissioner’s Regulations. All schools are expected to follow the guidelines outlined in the document "Assembling Your Improvement Planning Team" This section outlines how we worked together to develop our plan.

## Our Team’s Steps

Our plan is the result of collaborating to complete several distinct steps:

  - Activity 1: Analyze: Data Variation Identification

  - Activity 2: Analyze: Data Variation Share and Explore

  - Activity 3: Analyze: Survey Data

  - Activity 4: Listen: Student Interviews

  - Activity 5: Envision: Reflect and Synthesize

  - Writing the Plan

## Team Collaboration

In the first two columns, identify the members of the SCEP team and their role (e.g., teacher, assistant principal, parent).  In the rest of columns, indicate that team member’s participation in each of the activities by identifying the date that person participated in that activity OR leaving the space blank if the person did not participate in that activity.

| Name | Role | Orientation to School Teams (required for new TSI) | Analyze: Data Variation Identification | Analyze: Data Variation Share and Explore | Analyze: Survey Data | Listen: Student Interviews | Envision: Reflect and Synthesize | Plan Writing and Revision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 4/3/25 | 4/4/25 | 5/2/25 | 5/6/25;5/8/25 | 5/9/25 | 5/9/25, 5/16/25, 6/2 |
| Kate Berardi | Principal |  | x | x | x | x | x | x |
| Melissa Potter | School Psych. |  | x | x | x | x | x | x |
| Jessica Benjamin | Grade 1 teacher |  | x | x | x |  | x | x |
| Laura Feeney | Grade K teacher |  | x | x | x |  | x | x |
| Heidi Malenski | Social Worker |  | x | x | x |  | x | x |
| Sarah Gruber | Grade 2 teacher |  | x | x | x |  | x | x |
| Andrea Stenta | Grade 3 teacher |  | x | x | x |  | x | x |
| Maria Rojas | Bilingual Family Worker |  | x | x | x | x | x | x |
| Jackie Nelson | Grade 2 teacher |  | x | x | x |  | x | x |
| Cori Zupko-Williams | RtI teacher |  | x | x | x |  | x | x |
| Amy Fetahi | SPED teacher |  | x |  |  |  | x | x |
| Heather Watzka | Kindergarten Teacher |  | x | x | x |  | x | x |
| Amanda Green | Library Media Specialist |  | x | x | x |  | x | x |
| Megan Fuoco | SPED teacher |  | x | x | x |  | x | x |
| Jocelyn Kraft | TA |  | x | x | x | x | x | x |
| Alicia Chisaguano | Parent |  |  | x | x |  |  |  |
| Noemy Aguirre | Parent |  |  | x | x |  |  |  |
| Enma Villacis | Parent |  |  | x | x |  |  |  |
| Sonia Lliviasaca | Parent |  |  |  |  |  |  |  |
| Yenny Munoz Munoz | Parent |  |  |  |  |  |  |  |
| Ninette Warner | Community Member |  |  | x | x |  | x |  |

# Next Steps

## Sharing the Plan

### Schools in the CSI Model

As you develop your plan, please feel free to share the plan with your NYSED liaison for input when it would be helpful. When the SCEP team is satisfied with the plan, use the SCEP Rubric to consider where there may be opportunities to strengthen the plan.  After the team has analyzed the completed plan using the SCEP Rubric and made any necessary revisions, the principal should email the NYSED liaison and:

- Confirm that the team has reviewed the plan using the SCEP rubric, ensured the plan met minimum expectations, and made any necessary changes;

- Identify the areas of the plan where the team feels most confident;

- If applicable, specify any areas of the plan where the team feels less confident. The principal may also request a follow-up meeting to further explore these areas prior to meeting with the NYSED liaison.

- Indicate to your liaison that the school is ready to share its full plan for verification that it meets NYSED’s minimum expectations. Plans should be shared by July 1, 2025.

- Once the plan is finalized, representatives from the school and district should meet to complete the SIG Expenditure Plan.

- Ensure that the district (Superintendent or designee) and local Board of Education have approved the plan and the plan is posted on the district website.

### Schools in the ATSI model and TSI Model

  - When the SCEP team is satisfied with the plan, use the SCEP Rubric to consider where there may be opportunities to strengthen the plan.  After the team has analyzed the completed plan using the SCEP rubric and made any necessary revisions, please share the plan with your District, who will verify that the plan meets NYSED’s minimum expectations.  Once your plan is finalized, representatives from the school and district should meet to complete the SIG Expenditure Plan.  Plans will need to be approved by the District before the first day of the 2025-26 school year.

  - The final plan will need to be approved by the local Board of Education and posted on the district website.

## Implementing the Plan (All Schools)

  - Ensure the plan is implemented no later than the first day of school.

  - Monitor implementation closely and adjust as needed.

  - Plan to have the SCEP team reconvene during the year to discuss implementation and review progress in relation to the Early Progress Milestones and Mid-Year benchmarks identified.

  - Ensure that there is professional development provided to support the strategic efforts described within this plan.

# School Comprehensive Education Plan

# School Improvement Grant Expenditure Plan

# 2025-26

| District | School Name | Grades Served |
| --- | --- | --- |
| Kingston | Chambers | K-4 |

# School-Level SIG Expenditure Plan

## Instructions

After the School Comprehensive Education Plan (SCEP) has been finalized, representatives from the school should work with representatives of the district to determine how best to leverage Title I, 1003 School Improvement Grant (SIG) funding to implement the Key Strategies outlined.

This template will need to be attached to the SCEP and submitted as one document in the Business Portal as part of the SIG application process.

There are four different types of expenses that can be included:

- Instructional Key Strategies identified through the SCEP

- Non-Instructional Key Strategies identified through the SCEP

- Plan Monitoring

- Plan Development expenses for 2026-27

### Evidence-Based Intervention Category

All expenses must adhere to the Every Student Succeeds Act definition of an evidence-based intervention.  To assist with this, the Department has identified 16 State-Supported Evidence-Based Interventions, that if implemented in accordance to the parameters provided, fulfill this criteria.

- Align High School and College Courses to Increase Post-Secondary Transition Outcomes

- Community Schools

- Elementary School Looping

- Establish an Early Warning Intervention and Monitoring System

- Evidence-Based Instructional Methods

- Expanding access to high-quality Out-of-School-Time programs

- High-Quality Instructional Materials

- High-Quality Tutoring

- Incoming Student Induction Programs and Summer Bridge Programs

- Instructional Coaching

- Middle School Flexible Scheduling

- Multi-Tiered System of Supports – Integrated (MTSS-I)

- Ongoing Job-Embedded Professional Development

- Principal Leadership Development

- Professional Learning Communities

- Restorative Practices

In the Column labeled “Evidence-Based Intervention Category” enter the category for that specific expense.  If the expense does not fit within the State-Supported Evidence-Based Interventions (e.g. survey and feedback tools, HS internship coordinator) enter “Other.”

### Plan Monitoring and Development

The team that drafted the plan should anticipate reconvening at least twice during the 2025-26 school year to discuss implementation and review Early Progress Milestone and Mid-Year Benchmark data.

The school should also anticipate having a team come together in Spring 2026 to conduct a five-part needs assessment in conjunction with the development of its 2026-27 school plan.

### Budget Code

In the “Budget Code” category, enter the FS-10 budget code.  The following are Budget Codes used for this grant.  Any Code 80 (Employee Benefits) and Code 90 (Indirect Cost) expenses do not need to be referenced here but will need to be included on the FS-10.

Code 15: Professional Salaries

Code 16: Support Staff Salaries

Code 20: Equipment

Code 40:  Purchased Services

Code 45: Supplies and Materials

Code 46: Travel

Code 49: BOCES Services

### Expenses That Go Across Key Strategies

A school may have a single expense that covers multiple key strategies.  For those situations, the expense can be referenced in multiple categories, but the amount of the expense should only be inserted into the “Full Cost” column the first time the expense appears.

## Instructional Key Strategy Implementation

| INSTRUCTIONAL KEY STRATEGY 1 |  |
| --- | --- |

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |

| TOTAL AMOUNT FOR THIS INSTRUCTIONAL KEY STRATEGY |  |
| --- | --- |

| INSTRUCTIONAL KEY STRATEGY 2 |  |
| --- | --- |

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |

| TOTAL AMOUNT FOR THIS INSTRUCTIONAL KEY STRATEGY |  |
| --- | --- |

| INSTRUCTIONAL KEY STRATEGY 3 |  |
| --- | --- |

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |

| TOTAL AMOUNT FOR THIS INSTRUCTIONAL KEY STRATEGY |  |
| --- | --- |

| INSTRUCTIONAL KEY STRATEGY 4 |  |
| --- | --- |

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |

| TOTAL AMOUNT FOR THIS INSTRUCTIONAL KEY STRATEGY |  |
| --- | --- |

| INSTRUCTIONAL KEY STRATEGY 5 |  |
| --- | --- |

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |

| TOTAL AMOUNT FOR THIS INSTRUCTIONAL KEY STRATEGY |  |
| --- | --- |

## Non-Instructional Key Strategy Implementation

| NON-INSTRUCTIONAL KEY STRATEGY 1 |  |
| --- | --- |

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |

| TOTAL AMOUNT FOR THIS NON- INSTRUCTIONAL KEY STRATEGY |  |
| --- | --- |

| NON-INSTRUCTIONAL KEY STRATEGY 2 |  |
| --- | --- |

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |

| TOTAL AMOUNT FOR THIS NON- INSTRUCTIONAL KEY STRATEGY |  |
| --- | --- |

## Plan Monitoring Expenses

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |
|  | Plan Monitoring |  |  |
|  | Plan Monitoring |  |  |
|  | Plan Monitoring |  |  |
|  | Plan Monitoring |  |  |
|  | Plan Monitoring |  |  |

| TOTAL AMOUNT FOR PLAN MONITORING |  |
| --- | --- |

## 2026-27 Plan Development Expenses

| Expense | Evidence-Based Intervention Category | Budget Code | Full Cost |
| --- | --- | --- | --- |
|  | Plan Development |  |  |
|  | Plan Development |  |  |
|  | Plan Development |  |  |
|  | Plan Development |  |  |
|  | Plan Development |  |  |

| TOTAL AMOUNT FOR 2026-27 PLAN DEVELOPMENT |  |
| --- | --- |