# School Comprehensive Education Plan

# 2025-26

| District | School Name | Grades Served |
| --- | --- | --- |
| Kingston City School District | JFK Elementary | K - 4 |

Collaboratively Developed By:

The JFK SCEP Development Team: Alexandria Bailey, Teacher Amy Brekke, ENL Teacher Ashlei Bauer, Special Education Teacher Ashley Anzalone, Teacher Beth Dominowski, Library Typist & JFK Parent Brittany Myers, Special Education Teacher Christy Bennett, Teacher Emily Zifchak, Instructional Coach Heidi McGarry, Teacher Jennifer Torok, Special Education Teacher, RST Facilitator Jessica Feshold, Teacher Jessica Kelly, Parent Jessica Miller, Teacher Kim Williams, Office Manager Melissa Jamieson, Principal Robyn Tiano, Parent Rodney Brown, TA Rose Maire Reid, Reading Teacher Trudian Hay, Social Worker Katie Gibbons, Community Partner (Wild Earth) Emily Daniels, Parent Robert Weickel, Community Partner (Wild Earth) And in partnership with the staff, students, and families of John F. Kennedy Elementary.

# Guidance for Teams

## Navigating the Plan

You can expand or collapse any section of the plan by clicking the triangle next to the blue headings. Additionally, you can move through sections using the Navigation Pane in Microsoft Word.

## Before Writing the Plan

Before working on this document, school teams should have:

- Completed the Five-Part Needs Assessment, which consists of:

  - Activity 1: Analyze: Data Variation Identification

  - Activity 2: Analyze: Data Variation Share and Explore

  - Activity 3: Analyze: Survey Data

  - Activity 4: Listen: Student Interviews

  - Activity 5: Envision: Reflect and Synthesize

- Met with their NYSED/District/BOCES liaison:

- Following Activity 1: Analyze Data Variation Identification

- Following Activity 5: Envision: Reflect, Synthesize, and Plan after identifying the Key Strategies and before writing the implementation plan.

- Met with their district to share ensure alignment and coherence between the school’s improvement vision and the district’s vision.

## Key Strategies

Schools must identify the evidence-based, high-impact levers, known as “Key Strategies,” they believe will improve current outcomes.  Each Key Strategy should represent a change in the upcoming year compared to previous years.  The Key Strategy should fall into one of the following categories:

- Something new to the school; or

- An existing strategy being expanded to reach a wider audience; or

- An existing strategy being refined or adjusted from previous years.

To ensure effective implementation, school teams must be strategic in selecting the number of approaches they plan to use to improve outcomes, avoiding the temptation to implement too many initiatives.  To assist this process, NYSED has provided the following guidance:

- At least 1 Instructional Key Strategy must be identified.

- Non-Instructional Key Strategies are optional.

- Total number of Key Strategies (Instructional and Non-Instructional combined) must be between 2 and 5.

- Non-Instructional Key Strategies should not outnumber Instructional Key Strategies.

These Key Strategies should be aligned with the data reviewed and student interviews from the needs assessment. Teams must also explain the rationale for each Key Strategy selected on the provided template.

Schools may find Hattie’s High Impact Teaching Strategies and the resources gathered at Visible Learning, especially the Teaching Strategies, to be helpful resources when considering Key Strategies.  The Diagnostic Tool for School and District Effectiveness (DTSDE) Framework and Phases of Implementation may also be useful when considering different options to pursue.

## Key Strategy Implementation

For each Key Strategy, the school team needs to outline its implementation plan for the upcoming year.

- For new strategies, the plan should detail how the strategy will be introduced and rolled out.

- For expanded strategies, the plan should explain how the expansion will occur.

- For refined strategies, the plan should highlight how this year’s approach differs from previous years.

Each plan should include a sequence of activities that build upon one another. In the column to the right of each activity, include the target date for implementation.  This will help the team track progress during the 2025-26 school year.

## Key Strategy Progress Monitoring

After identifying their Key Strategies, school teams should set success criteria and benchmarks to evaluate progress throughout the year.

Each Key Strategy must include at least one Early Progress Milestone to provide early feedback on the strategy’s success. The data, which could be implementation data and/or outcome data, should directly align with the Key Strategy.

Each Key Strategy must include at least one outcome-based Mid-Year Benchmark and End-of-The-Year target that is directly related to the strategy.

## Performance Targets

In addition to setting Mid-Year Benchmarks and End-of-Year targets for each Key Strategy, the plan must also establish overall Performance Targets that reflect the anticipated improvement from the combined impact of all strategies. While the Key Strategy Progress Monitoring will track data specific to each individual strategy, the Performance Targets serve as broader indicators of overall school improvement.

## Ongoing Monitoring

The plan template allows school teams to revisit and update their plan throughout the year. A designated section tracks progress for each Key Strategy and for the Performance Targets, allowing teams to record outcome data or evidence alongside original targets. This section should remain blank when first writing the plan and will be updated throughout the year as the team assesses the success of the plan.

## SCEP Rubric

NYSED has created the SCEP Rubric to help teams identify areas for improvement in their plan.  The rubric can be a valuable reference tool while writing the plan.  After completing the initial draft, schools should self-assess using the rubric before finalizing their plan.

## Resources for Team

- Assembling Your Improvement Planning Team

- NYSED Improvement Planning website: http://www.nysed.gov/accountability/improvement-planning

# Evidence-Based Intervention

All key strategies pursued by schools should be rooted in evidence.  All schools in the CSI, ATSI, and TSI support models must implement at least one evidence-based intervention that meets the criteria of a Tier 1, Tier 2, or Tier 3 evidence-based intervention under ESSA. More information can be found at: http://www.nysed.gov/accountability/evidence-based-interventions.

School teams should indicate all of the evidence-based interventions that meet the federal definition that will be pursued next year by placing an “X” in the corresponding box below.  Schools that adopt the State-Supported Evidence-Based Intervention under the parameters outlined at: https://www.nysed.gov/accountability/state-supported-evidence-based-strategies will fulfil the evidence-based intervention requirement.

| State-Supported Evidence-Based Interventions | Mark “X” if the school will implement this in 25-26 |
| --- | --- |
| Align High School and College Courses to Increase Post-Secondary Transition Outcomes |  |
| Community Schools |  |
| Elementary School Looping |  |
| Establish an Early Warning Intervention and Monitoring System |  |
| Evidence-Based Instructional Methods |  |
| Expanding access to high-quality Out-of-School-Time programs |  |
| High-Quality Instructional Materials |  |
| High-Quality Tutoring |  |
| Incoming Student Induction Programs and Summer Bridge Programs |  |
| Instructional Coaching | X |
| Middle School Flexible Scheduling |  |
| Multi-Tiered System of Supports – Integrated (MTSS-I) |  |
| Ongoing Job-Embedded Professional Development |  |
| Principal Leadership Development |  |
| Professional Learning Communities |  |
| Restorative Practices |  |

Other (required if no State-Supported Evidence-Based Intervention is identified above): Identify and describe a School-Identified Intervention that meets the criteria of a Tier 1, Tier 2, or Tier 3 Evidence-Based Intervention. Please also indicate the Clearinghouse, Evidence Review, or research that indicates the intervention qualifies as a Tier 1, Tier 2, or Tier 3 Evidence-Based Intervention.

# Learning as a Team

## Directions

Teams should complete the reflective prompt below.

### Student Interviews

Describe how the Student Interview process informed the team’s plan.

In each grade, the students interviewed discussed that they like learning more things that they don’t know. CKLA is specifically designed to build background knowledge and expose students to new opportunities. When asked about CKLA, students expressed that they love, “reading the books; learning new things; learning about the solar system; end of unit tests to see what they learned.” Additionally, students identified ways that they know they are learning (metacognition), such as recognizing when they have an incorrect answer and knowing how to correct it. When asked what JFK should continue next year, 100% of students named experiential learning opportunities including, but not limited to: Field Trips, Wild Earth, Field Day, Talent Show, Plays, learning new things. The strategies we have selected provide students with consistent and ongoing exposure to opportunities that help them think about their learning as well as engage them in activities they consider “fun,” which they identified makes them want to come to school.

Schools in the ATSI and TSI model only

### Subgroup Spotlight

Describe how the team has determined that the strategies within this plan are likely to result in improved subgroup performance for the subgroup(s) for which the school has been identified.

# Instructional Key Strategies for Improvement

## Key Strategies

(What are we doing? Why are we doing this?)

In column 1, input at least one, but no more than five strategies that reflect something new the school is introducing or something currently in existence that the school is expanding or refining for the upcoming school year.  In column 2, specify whether the strategy is something new, something being expanded, or something being refined.  In column 3, identify the data that indicates these strategies will be beneficial for the school.  For any Key Strategy that is not new, provide a 1-2 sentence summary of how the key strategy will be expanded or refined next year.

| KEY STRATEGY (What are we doing?) | HOW TO DOES THIS COMPARE TO EXISTING EFFORTS? | WHY: What did we learn from our needs assessment that suggests this is the right Key Strategy and will have a positive impact on students? Use evidence. Consider both data trends observed and student interview responses. Additionally, for any Key Strategy that does not represent something new, provide 1-2 sentences describing how the school will expand or refine the Key Strategy next year. |
| --- | --- | --- |
| Implement a Tier 1 Reading Curriculum in all classrooms. | ☐ NEW ☐ EXPAND ☐ REFINE | The data in the CKLA Pilot classes demonstrated that in 1 year, most students in pilot classes outperformed the other students on the i-Ready assessments. The data also showed that without a Tier 1 common curriculum, student proficiency was not improving. Additionally, the data showed that from 2021-2023 in Math we had a 10% increase in students scoring a level 3 after a Tier 1 Curriculum was implemented, while there was a 7% drop in student proficiency in ELA between 2021-2023. |
| Immerse students in mathematical thinking. | ☐ NEW ☐ EXPAND ☐ REFINE | The data shows that between 22-23 and 23-24 school years, level 3 proficiency declined slightly and level 1 increased. In an effort to retain the growth that students had after adopting a Tier 1 Math curriculum, we want to provide students the research opportunity to learn in a way that meets their developmental needs. The District Resource Allocation Review indicated that the demographic of students enrolled in middle school advanced math classes did not correlate with the demographics of all students in the district. The team agreed that it is imperative to build a love of math in younger learners in order to increase the likelihood that they will continue into advanced math and STEAM classes as they progress through their educational careers. |
| Increase student keyboarding capacity by incorporating schoolwide, consistent use of EduTyping. | ☐ NEW ☐ EXPAND ☐ REFINE | Students regularly use computer programs during instruction and for assessments. When students are proficient in keyboarding, they can focus on the content rather than the mechanics of typing—improving overall performance. We've seen a drop in state test proficiency rates since transitioning to computer-based testing, suggesting that keyboarding fluency is a necessary foundation for demonstrating academic knowledge effectively. |
| Align experiential learning to support all SCEP strategies and academic goals. | ☐ NEW ☐ EXPAND ☐ REFINE | Student data and survey data indicate that everyone values experiential learning because it helps students retain information. Student comprehension is an area of focus, and the experiences help build their background knowledge. Finally, providing experiences to students improves attendance. |

## Implementation

How will we do this?

| KEY STRATEGY 1 | Implement a Tier 1 Reading Curriculum in all classrooms. |
| --- | --- |

| BEFORE THE 1st DAY OF SCHOOL IMPLEMENTATION What is our plan for preparing our school for success with this Key Strategy before the school year starts? What steps are involved? | When will this be in place? |
| --- | --- |
| JULY CKLA WORK: Use the Summer SIG to have a day of planning with all teachers led by our instructional coach and teachers who piloted CKLA in the 2025-2026 school year. The time will minimally include: - Reviewing all the materials - Planning for the first 21 days of instruction - including pacing and timing - Sharing lessons learned from the pilot teachers | July 2025 |
| Provide all stakeholders access to the Amplify resources, specifically the Scope and Sequence and vocabulary, so that it can be supported across the school in both AIS and ENL classes. | 8/28/25 |
| Ongoing PD training calendar | 8/28/25 |
| Book Fairy picture books - Plan the monthly books and order the first quarter. | 8/28/25 |
| FIRST HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the first half of the year? What steps are involved? | When will this be in place? |
| Teach the Program with Fidelity: - Avoid picking and choosing parts of the curriculum. Follow the lessons as designed to ensure students receive the full benefit of the program. - The Instructional Coach and Principal will do informal observations to observe implementation across classrooms. - Peer observations in the rooms of teachers who piloted CKLA during the 2024-2025 school year. - Model lessons provided by the instructional coach as needed. | 9/3/25 - last day of school |
| Utilize formative assessments in data driven instruction meetings across grade levels. - Administer unit assessments according to the CKLA pacing guide. - Use the results to monitor student understanding and growth. - Review CKLA assessment data to determine students' current performance levels. - Use this data to reassess Tier 2 and Tier 3 placements as needed. - Adjust Instruction as Needed: Use data and collaboration outcomes to differentiate instruction and provide targeted support for students who need it. | Minimum - 1x per quarter Ideally - 1x per month |
| Collaborate with Support Staff - Meet with interventionists, special educators, and related service providers to discuss tier changes and specific student needs. - Coordinate instruction and interventions based on shared data and observations. - Using data from grade level data meetings, ensure all support staff are involved in planning next steps / referring to MTSS Team. | First meeting to occur no later than end of Quarter 1 / early November |
| SECOND HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the second half of the year? What steps are involved? | When will this be in place? |
| Review What’s Left to Cover - consult scope and sequence to ensure pacing is on track - Identify which units or domains remain in your grade-level scope and sequence. - Use your grade’s curriculum map to plan out the remainder of the year. | Prior to beginning of Q3 / mid-January |
| Utilize formative assessments in data driven instruction meetings across grade levels. - Administer unit assessments according to the CKLA pacing guide. - Use the results to monitor student understanding and growth. - Review CKLA assessment data to determine students' current performance levels. - Use this data to reassess Tier 2 and Tier 3 placements as needed. - Adjust Instruction as Needed: Use data and collaboration outcomes to differentiate instruction and provide targeted support for students who need it. | Minimum - 1x per quarter Ideally - 1x per month |

### Progress Monitoring

How will we measure progress and impact for this Key Strategy?

|  | What data will we be reviewing? | What do we hope to see when we review that data? | What we ended up seeing. What are our next steps? complete when reviewing data |
| --- | --- | --- | --- |
| Early Progress Milestones (implementation/outcome data) | Admin & Coach Observation Walk-Through Forms with a specific focus on vocabulary | Instructional quality and 80% of classrooms implementing CKLA with fidelity |  |
| Mid-Year Benchmark(s) (outcome data) | Admin & Coach Observation Walk-Through Forms with a specific focus on vocabulary | Instructional quality and 90% of classrooms implementing CKLA with fidelity |  |
| End-of-the Year Targets (outcome data) | Admin & Coach Observation Walk-Through Forms with a specific focus on vocabulary | Instructional quality and 100% of classrooms implementing CKLA with fidelity |  |

| KEY STRATEGY 2 | In conjunction with the Tier 1 Math Curriculum, immerse students in mathematical thinking, analysis, vocabulary, problem-solving, and games to reinforce fluency and build confidence in their mathematical ability. |
| --- | --- |

| BEFORE THE 1st DAY OF SCHOOL IMPLEMENTATION What is our plan for preparing our school for success with this Key Strategy before the school year starts? What steps are involved? | When will this be in place? |
| --- | --- |
| Summer Curriculum Writing / Planning: - All teachers will provide 60 minutes of math instruction per day, up from the previously mandated 40 minutes per day. Teachers will work with our Instructional Coach to determine: - How to introduce or revisit routines that immerse students in mathematical thinking, analysis, vocabulary, problem-solving, and games to reinforce fluency and build confidence. - Ensure each classroom is equipped with the supplies/manipulatives needed for implementation. - Instructional Coach will work with teachers to align curriculum maps with intentional opportunities for rich math discussions, vocabulary focus, and fluency games. - Principal and Instructional Coach will create a shared bank of math games and sentence stems for math discourse. | Summer 2025 |
| Professional Development - Teachers will receive information and training from both Instructional Coach and district administration on: - Structure of the 60 minute math block - NYSED Math Briefs | 8/28/25 and 9/2/25 |
| FIRST HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the first half of the year? What steps are involved? | When will this be in place? |
| Student Readiness & Mindset Planning - Prepare plans for teaching math norms and growth mindset at the start of the year (e.g., "Everyone is a math person"), include common language in the morning announcements. - Plan classroom routines that build perseverance and confidence early on. - Distribute I’m Trying to Love Math as one of the book fairy books early in the school year. | 9/2/25 and throughout first quarter |
| Curriculum Mapping & Resources - Work with Instructional Coach to identify and prepare anchor charts, math manipulatives, and visual supports that promote vocabulary and thinking strategies. - Dedicate time at staff meetings to discuss progress in the classes: what’s going well, what could be better? | 9/2/25 and throughout first quarter |
| Observations - Instructional Coach and Principal will do informal observations to observe implementation across classrooms and identify trends to discuss during staff meetings and team collaboration time. | Ongoing beginning in late September |
| SECOND HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the second half of the year? What steps are involved? | When will this be in place? |
| Sharing Teacher Best Practices - Create a video library of effective models of math instruction to use for professional development. - Provide opportunity for peer observations. | January - May 2026 |
| Progress Monitoring & Instructional Check-Ins - Use assessment data (unit tests, math fluency checks, classwork) to identify gaps and adjust instruction. - Conduct classroom walkthroughs focused on math discourse, vocabulary usage, and problem-solving strategies in action. - Have grade-level teams reflect on: Are students talking about math more? Is vocabulary becoming part of student explanations? | January - May 2026 |
| Collaborative Learning & Sharing: Host a mid-year PLC or math-focused staff meeting to: - Share successful strategies for integrating games and problem-solving. - Review and refine pacing guides if needed. - Highlight student work that shows growth in analysis and confidence. | January 2026 |
| Student Engagement Boost - Introduce or renew interest in math challenges, fluency games, or classroom math competitions. - Spotlight students who show growth in thinking, risk-taking, or use of math language. | January 2026 |

### Progress Monitoring

How will we measure progress and impact for this Key Strategy?

|  | What data will we be reviewing? | What do we hope to see when we review that data? | What we ended up seeing. What are our next steps? complete when reviewing data |
| --- | --- | --- | --- |
| Early Progress Milestones (implementation/outcome data) | Admin & Coach Observation Walk-Through Forms with a specific focus on use of math vocabulary | 80% of classrooms showing evidence of quality activities that immerse students in mathematical thinking, analysis, vocabulary, problem-solving, and games to reinforce fluency and build confidence in their mathematical ability. |  |
| Mid-Year Benchmark(s) (outcome data) | Admin & Coach Observation Walk-Through Forms with a specific focus on math vocabulary | 90% of classrooms showing evidence of quality activities that immerse students in mathematical thinking, analysis, vocabulary, problem-solving, and games to reinforce fluency and build confidence in their mathematical ability. |  |
| End-of-the Year Targets (outcome data) | Admin & Coach Observation Walk-Through Forms with a specific focus on math vocabulary | 100% of classrooms showing evidence of quality activities that immerse students in mathematical thinking, analysis, vocabulary, problem-solving, and games to reinforce fluency and build confidence in their mathematical ability. |  |

| KEY STRATEGY 3 | Increase student keyboarding capacity by incorporating schoolwide, consistent use of EduTyping. |
| --- | --- |

| BEFORE THE 1st DAY OF SCHOOL IMPLEMENTATION What is our plan for preparing our school for success with this Key Strategy before the school year starts? What steps are involved? | When will this be in place? |
| --- | --- |
| Schedule Integration - Team will agree on how to build EduTyping into the master schedule—daily or multiple times per week based on grade level. - Team will decide whether integration is through tech class, homeroom, center time, or core subject block. - Have current teacher users model how to effectively use Go Guardian to ensure that computer time is productive. | 9/2/25 |
| Set Clear Expectations - Define grade-level keyboarding goals (e.g., words per minute, posture, accuracy). - Establish daily/weekly practice expectations and create a system for tracking progress. | 9/2/25 |
| Use Current Staff to Train Teachers and Staff - Provide brief training on EduTyping access, monitoring, and reports. - Share rationale behind the initiative: stronger typing = stronger test-taking and content engagement. | 9/2/25 |
| FIRST HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the first half of the year? What steps are involved? | When will this be in place? |
| Track & Celebrate Student Progress - Use EduTyping reports to check typing speed, accuracy, and usage consistency by class and grade. - Identify students not meeting benchmarks and provide extra practice or support. - Highlight students or classes with most improvement or consistency. - Include keyboarding celebrations or challenges (e.g., “WPM Wednesday,” typing contests). | By end of September 2025 |
| Align with Content Area Needs - Encourage content teachers (ELA, SS, Science) to assign typed responses to reinforce practice in authentic ways. - Have students reflect on how typing has helped them with writing assignments or online tests. | Beginning in October 2025 |
| Review and Troubleshoot - Collect teacher feedback on scheduling, engagement, and barriers to daily integration. - Adjust schedules or support if usage is inconsistent. | December 2025 |
| SECOND HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the second half of the year? What steps are involved? | When will this be in place? |
| Evaluate Impact and Connect to State Test Outcomes - Compare beginning and end-of-year keyboarding data (speed/accuracy) to identify student and grade-level growth. - Analyze correlation between improved typing fluency and student performance on CBT-style writing tasks or interim assessments. - Review this year’s CBT results in light of the EduTyping rollout. Did typing fluency help improve performance or reduce tech-related barriers? - Use data to strengthen the case for sustained or expanded implementation. | April - June 2026 |
| Plan for Next Year - Adjust keyboarding goals and scheduling based on outcomes. - Develop a streamlined plan for onboarding new teachers or students. - Prepare a showcase of success stories and challenges for leadership or staff debriefs. | May - June 2026 |

### Progress Monitoring

How will we measure progress and impact for this Key Strategy?

|  | What data will we be reviewing? | What do we hope to see when we review that data? | What we ended up seeing. What are our next steps? complete when reviewing data |
| --- | --- | --- | --- |
| Early Progress Milestones (implementation/outcome data) | Clever Dashboard Student Trackers | Consistent use of Edutyping per the agreed upon schedule / minutes. That students set goals and tracked their own progress toward them. |  |
| Mid-Year Benchmark(s) (outcome data) | Clever Dashboard Student Trackers | Consistent use of Edutyping per the agreed upon schedule / minutes. 60% of students reaching the goals they have set for themselves. |  |
| End-of-the Year Targets (outcome data) | Teacher Anecdotal Data | Teachers indicated how difficult it was for students to have stamina during testing. We hope to hear that after having consistent typing classes, this barrier has been eliminated. 80% of students reaching the goals they have set for themselves. |  |

| KEY STRATEGY 4 | Increase opportunities for experiential learning. |
| --- | --- |

| BEFORE THE 1st DAY OF SCHOOL IMPLEMENTATION What is our plan for preparing our school for success with this Key Strategy before the school year starts? What steps are involved? | When will this be in place? |
| --- | --- |
| WildEarth - Finalize commitments with Wild Earth and provide Wild Earth team our finalized SCEP. | 8/28/25 |
| Acorn School - Finalize commitments with Acorn School and provide Acorn team our finalized SCEP. | 8/28/25 |
| Land to Learn - Finalize commitments with Land to Learn and provide Land to Learn team our finalized SCEP. | 8/28/25 |
| TOPS – Finalize TOPS plan for the 2025-2026 school year with district administration and provide TOPS director our finalized SCEP. | 8/28/25 |
| Create a schedule to ensure equity and alignment amongst grade level experiences. | 8/28/25 |
| FIRST HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the first half of the year? What steps are involved? | When will this be in place? |
| Use the TOPS program to support student progress toward SCEP goals, for example - having lego robotics to increase math experiences. BLT will meet with the TOPS team to determine Scope and Sequence for the first semester. | 10/2025 |
| Check in with all partner programs (WildEarth, Acorn School, Land to Learn) to share how their work aligns with our school goals and troubleshoot any challenges that have arisen. | 10/2025 |
| Track Quarter 1 attendance and behavior data on days we have community partner programming and/or TOPS after school programming. |  |
| Meet quarterly with Building Leadership Team to look at and examine data. | Quarterly |
| SECOND HALF OF THE YEAR IMPLEMENTATION What is our plan implementing this Key Strategy in the second half of the year? What steps are involved? | When will this be in place? |
| Use the TOPS program to support student progress toward SCEP goals, for example - having lego robotics to increase math experiences. BLT will meet with the TOPS team to determine Scope and Sequence for the second semester. | January 2026 |
| Meet quarterly with Building Leadership Team to look at and examine data. | Quarterly |
| Check in with all partner programs (WildEarth, Acorn School, Land to Learn) to reflect on lessons learned, big wins, and consider alignment with SCEP goals for upcoming school year. | May or June 2026 |

### Progress Monitoring

How will we measure progress and impact for this Key Strategy?

|  | What data will we be reviewing? | What do we hope to see when we review that data? | What we ended up seeing. What are our next steps? complete when reviewing data |
| --- | --- | --- | --- |
| Early Progress Milestones (implementation/outcome data) | Attendance Sign In Sheets Schedule | Verify that all programs are up and running. |  |
| Mid-Year Benchmark(s) (outcome data) | 100 Day Survey Data | 60% of stakeholders are satisfied with the quality and quantity of experiences to which students have been exposed to and recognize the alignment with our academic goals. |  |
| End-of-the Year Targets (outcome data) | EOY Survey Data | 80% of stakeholders are satisfied with the quality and quantity of experiences to which students have been exposed to and recognize the alignment with our academic goals. |  |

## Academic Performance Targets

### Mid-Year Benchmarks and End-Of-The-Year Targets

We believe successful implementation of these instructional strategies will allow us to reach the following mid-year benchmarks and end-of-the-year goals.

|  | What student data will we be reviewing? | What Key Strategies are intended to directly impact this student data? | What do we hope to see when we review that student data? | What we ended up seeing: (complete when reviewing mid-year data) |
| --- | --- | --- | --- | --- |
| Mid-Year Benchmark(s) | Winter i-Ready diagnostic: | All | Number of students on or above grade level will increase by 18% Number of students below grade level will decrease by 8% |  |
| End-of-the Year Targets | Spring i-Ready diagnostic: | All | Number of students on or above grade level will increase by 18% Number of students below grade level will decrease by 10% |  |

### Spring Survey Targets

We believe these spring survey responses will give us helpful feedback about our progress with our Instructional Key Strategy/Strategies:

|  | Survey Question(s) or Statement(s | Corresponding Key Strategies | 2024-25 data if available (e.g., % agree or strongly agree) | Desired response (e.g., % agree or strongly agree) | What we ended up seeing: (complete once Spring survey results are available) |
| --- | --- | --- | --- | --- | --- |
| Student Survey | I know how to track my own iReady data I know what is expected of me to meet my iReady goals. | 1-2 1-2 | 14% of students were unsure and 11% of students said no 20% of students were unsure and 7% of students said no | 0% of students unsure and 0% of students saying no 0% of students unsure and 0% of students saying no |  |
| Staff Survey | I have regular opportunities for professional development. I have regular opportunities to collaborate with my colleagues and feel supported by them. | 1-3 1-4 | 6% or staff were unsure and 6% of staff disagreed 10% of staff were unsure and 6% of staff disagreed. | 0% of staff unsure 0% of staff disagreeing 0% of staff unsure 0% of staff disagreeing |  |
| Family Survey | My child uses academic vocabulary at home. My child has access to experiences at school (trips, after school programs, community partners, etc.) that enrich and build on what they are learning in class. | 1-2 4 | N/A | 75% of parents agreeing or strongly agreeing 75% of parents agreeing or strongly agreeing |  |

# Civic Empowerment Project (schools in CSI only)

## Background

As part of the New York State Every Student Succeeds Act Plan (ESSA)and Commissioner’s Regulation 100.21, all schools identified for Comprehensive Support and Improvement (CSI) Support Model are required to annually implement a Participatory Budgeting Process or provide opportunities for parent and student engagement in a manner prescribed by the Commissioner.

## Options for Schools

The Department has outlined six ways in which schools may address the requirement for schools in the CSI Support Model to implement Participatory Budgeting or an Approved Alternative:

- Participatory Budgeting

- Monthly School Focus Groups

- Climate Survey Inquiry Team

- Schoolwide Voting

- Students Reimagining School

- Design Your Own

These options were identified because they build on essential components of Participatory Budgeting: expanding stakeholder voice, providing opportunities to practice democracy, and promoting civic engagement.

The available options are described in more detail in the guidebooks available on the NYSED Civic Empowerment Projects website.  Schools should consider how to incorporate their selection into their proposed Key Strategies.

### Directions (Schools in CSI only)

Place an "X" in the box next to the Civic Empowerment Project the SCEP Development Team has selected for the 2025-26 school year.

☐ Participatory Budgeting

X Monthly School Focus Groups

☐ Climate Survey Inquiry Team

☐ Schoolwide Voting

☐ Students Reimagining School

☐ Design Your Own (proposals should be sent to FieldSupport@nysed.gov)

# Our Team’s Process

## Background

NYSED requires that the SCEP is developed in consultation with parents and school staff, and in accordance with §100.11 of Commissioner’s Regulations. All schools are expected to follow the guidelines outlined in the document "Assembling Your Improvement Planning Team" This section outlines how we worked together to develop our plan.

## Our Team’s Steps

Our plan is the result of collaborating to complete several distinct steps:

  - Activity 1: Analyze: Data Variation Identification

  - Activity 2: Analyze: Data Variation Share and Explore

  - Activity 3: Analyze: Survey Data

  - Activity 4: Listen: Student Interviews

  - Activity 5: Envision: Reflect and Synthesize

  - Writing the Plan

## Team Collaboration

In the first two columns, identify the members of the SCEP team and their role (e.g., teacher, assistant principal, parent).  In the rest of columns, indicate that team member’s participation in each of the activities by identifying the date that person participated in that activity OR leaving the space blank if the person did not participate in that activity.

| Name | Role | Orientation to School Teams (required for new TSI) N/A at JFK | Analyze Data Variation Identification | Analyze Data Variation Share and Explore | AnalyzeSurvey Data | Listen Student Interviews | Envision Reflect and Synthesize | Plan Writing and Revision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Example: Mary James | ELL Teacher | 3/4 | 3/12 | 3/19 |  | 4/10, 4/11 | 4/17 | 5/2 5/9 5/16 |
| All KTF Staff |  |  |  |  | 5/8 |  | 5/9 | 5/20 & 6/12 |
| All KTF & ESP Staff |  |  |  |  |  |  | 5/9 |  |
| Alexandria Bailey | Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Amy Brekke | ENL Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Ashlei Bauer | Special Education Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Ashley Anzalone | Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Beth Dominowski | Library Typist/ JFK Parent |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Brittany Myers | Special Education Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Christy Bennett | Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Heidi McGarry | Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Jennifer Torok | Special Education Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Jessica Feshold | Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Jessica Kelly | Parent |  |  |  | 5/8 |  |  | 5/20 & 6/12 |
| Jessica Miller | Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Kim Williams | Office Manager |  |  |  |  |  | 5/9 |  |
| Melissa Jamieson | Principal |  | Week of 3/24 | 4/8 | 5/8 | 5/8 | 5/9 | 5/20, 6/12, 6/25, 6/26, 6/27 |
| Rodney Brown | TA |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Rose Maire Reid | Reading Teacher |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Trudian Hay | Social Worker |  |  | 4/8 | 5/8 |  | 5/9 | 5/20 & 6/12 |
| Katie Gibbons | Community Partner (Wild Earth) |  |  |  |  |  | 5/9 |  |
| Robert Weikel | Community Partner (Wild Earth) |  |  |  |  |  | 5/9 |  |
| Emily Daniels | Parent |  |  | 4/8 | 5/8 |  | 5/9 |  |

Next Steps

## Sharing the Plan

### Schools in the CSI Model

As you develop your plan, please feel free to share the plan with your NYSED liaison for input when it would be helpful. When the SCEP team is satisfied with the plan, use the SCEP Rubric to consider where there may be opportunities to strengthen the plan.  After the team has analyzed the completed plan using the SCEP Rubric and made any necessary revisions, the principal should email the NYSED liaison and:

- Confirm that the team has reviewed the plan using the SCEP rubric, ensured the plan met minimum expectations, and made any necessary changes;

- Identify the areas of the plan where the team feels most confident;

- If applicable, specify any areas of the plan where the team feels less confident. The principal may also request a follow-up meeting to further explore these areas prior to meeting with the NYSED liaison.

- Indicate to your liaison that the school is ready to share its full plan for verification that it meets NYSED’s minimum expectations. Plans should be shared by July 1, 2025.

- Once the plan is finalized, representatives from the school and district should meet to complete the SIG Expenditure Plan.

- Ensure that the district (Superintendent or designee) and local Board of Education have approved the plan and the plan is posted on the district website.

### Schools in the ATSI model and TSI Model

  - When the SCEP team is satisfied with the plan, use the SCEP Rubric to consider where there may be opportunities to strengthen the plan.  After the team has analyzed the completed plan using the SCEP rubric and made any necessary revisions, please share the plan with your District, who will verify that the plan meets NYSED’s minimum expectations.  Once your plan is finalized, representatives from the school and district should meet to complete the SIG Expenditure Plan.  Plans will need to be approved by the District before the first day of the 2025-26 school year.

  - The final plan will need to be approved by the local Board of Education and posted on the district website.

## Implementing the Plan (All Schools)

  - Ensure the plan is implemented no later than the first day of school.

  - Monitor implementation closely and adjust as needed.

  - Plan to have the SCEP team reconvene during the year to discuss implementation and review progress in relation to the Early Progress Milestones and Mid-Year benchmarks identified.

  - Ensure that there is professional development provided to support the strategic efforts described within this plan.