# District Comprehensive Improvement Plan (DCIP) 2025-2026

District-Level Systems for Supporting Schools Identified for Additional Support

| District | Superintendent |
| --- | --- |
| Kingston City School District | Dr. Paul J. Padalino |

## School Key Strategies

What Instructional and Non-Instructional Key Strategies have the schools in the CSI, ATSI, and TSI support models identified on their SCEPs?

| Instructional Key Strategies | Schools |
| --- | --- |
| To Improve Tier 1 Instruction in Reading and Math | Bailey Middle, Miller Middle, JFK Elementary, Edson Elementary, George Washington Elementary |
| Implementation of Mult-Tiered Systems of Supports - Integrated | Bailey Middle, Miller Middle, JFK Elementary, Edson Elementary, George Washington Elementary |
| Socio-Emotional Learning | JFK, Miller, George Washington |
| Mentorship and Student Goal Setting | Bailey, Miller |
| Non-Instructional Key Strategies | Schools |
| Family Engagement | Bailey, Miller, JFK, Edson, George Washington |

## District Support

What actions will the district lead to support improving teaching practices related to these key strategies?

| Action | Person Responsible | When |
| --- | --- | --- |
| Professional Development | Teaching and Learning Committee |  |
| Consistent Data Review Meetings | Teaching and Learning Committee |  |
| Family Engagement Workshop Sessions | Teaching and Learning Committee |  |

## Measuring Success

What will the district look for as evidence of the success of the actions listed above? Use the following sentence frame: “If we achieve [Quantitative Data Target] [time reference of when you would want to see that], then we will know we are making progress through these actions.” Examples: - If we achieve 85% of teachers using accountable talk stems within two weeks of the September PD, then we will know we are making progress through these actions.” - If we achieve more than 85% of students with 1 or 0 absences a month, then we know we are making progress through these actions.” - If we achieve 90% of students achieving more than 80% of the possible points from short constructed response questions on our mid-year assessment, then we will know we are making progress through these actions.” If 85% of staff respond favorably to the survey question ‘Teachers at this school have the opportunity to provide feedback and influence decisions’ on the end-of-the-year survey, then we know we are making progress through these actions.”

| Quantitative Data Target | Time Reference of When You Would Want to See That |
| --- | --- |
| By October 1st, 85% of classroom teachers will be implementing the district-adopted math and reading curricula with instructional fidelity, as measured by walkthroughs, lesson plans, and/or fidelity checklists. Achieving this benchmark will indicate that instruction is aligned to grade-level standards and consistent across classrooms, ensuring equitable and high-quality learning experiences for all students. | By September 1st a consistent instructional walk-through tool will be developed and implemented across classrooms to identify instructional practices and areas where teachers may benefit from targeted professional development. By January 31st Using the data collected from the walk-through tool, specific trends and areas of instructional need will be identified. These findings will guide the development of focused support strategies for educators. By March 1st a comprehensive Professional Development Plan will be finalized and launched. This plan will directly address the areas of need identified through the walk-through process and provide teachers with support and training to enhance Tier 1 instructional delivery in both math and reading. |
| By October 1st, all RTI providers will be trained in using a consistent progress monitoring process and tools to accurately identify students in need of academic support. A consistent approach to progress monitoring will ensure that student data is reliable, actionable, and aligned across classrooms and grade levels, enabling targeted interventions and informed instructional decisions. | October 1st all RTI providers will be trained in using consistent progress monitoring. May 1st all RTI providers will utilize consistent progress monitoring tools to evaluate areas for academic support. |
| SEL |  |
| By September 1st 85% of the topics for the Parent Academy will be identified using feedback from the District Leadership Team and Parent-Teacher Organizations (PTOs). Dates for the sessions will be strategically scheduled in conjunction with other school-based events to encourage increased parent participation and engagement. | By September 1st At least 85% of Parent Academy topics will be identified using input from the District Leadership Team and Parent-Teacher Organizations (PTOs). In addition, Parent Academy dates will be coordinated with existing school events to help maximize attendance and community involvement. By December 1st Feedback collected from PTOs will be used to finalize the remaining 15% of Parent Academy topics, ensuring that all content is relevant, responsive to family needs, and aligned with district priorities. |

## Coherence

The Key Strategies are intended to be drivers that will improve current results in schools that are in the CSI, ATSI, and TSI support models, rather than everything a school is doing to support instruction. In consideration of this, what is the district’s plan to ensure coherence in the upcoming year so that its support of the Key Strategies above is aligned to its own districtwide vision for instruction?

KCSD admin team will regularly communicate with stakeholders about our shared and unified vision for instructional improvement that focuses on successful student outcomes. We will develop and implement standardized walkthrough tools and protocols for walkthroughs that focus on specific instructional strategies such as Tier 1 instruction and MTSS implementation. We will establish structured feedback processes and data review that foster actionable insights for educators, guiding professional development, growth and instructional improvement. The KCSD admin team will implement a system for monitoring progress aligned with our collective vision, using data points such as student performance, teacher feedback, and family engagement metrics to adjust strategies as needed. The KCSd administrative team will continuously monitor intents versus outcomes to identify and recommend shifts, practices and/or expenditures.

## Equitable Distribution of Resources

What is the district’s plan to review resource allocation in the upcoming year to ensure equitable distribution based on the needs of its schools?

The KCSD admin team will focus on progress monitoring intent compared with outcomes when implementing the key strategies. Continuous feedback loops will include surveys, data analysis, and feedback sessions with stakeholders to assess progress. The team will collaboratively analyze performance data to understand how resources are supporting a return on investments and to pinpoint areas that may require additional support. By engaging with parents, community members, and other stakeholders to gather input on progress, we will ensure the inclusion of perspectives of stakeholders who are directly impacted. The district will also continue to work collaboratively with building leaders on equitable resource management and effective practices for utilizing allocated resources. This will enhance our collective capacity to address the needs of students with optimal proficiency.

What is the district’s plan in the upcoming year to ensure that students in schools identified for CSI/ATSI/TSI have at least as much access to strong teachers as their peers in schools identified for LSI?

The District will continue to actively recruit highly qualified teachers in areas of need. The District will provide ongoing professional development tailored to the unique challenges faced by schools requiring additional support in order to focus high yield instructional strategies. The District will foster a system for continuous monitoring of teacher school performance and collaboration by providing dedicated time for teachers to collaborate, share best practices, peer to peer observations, and effective teaching strategies.

# Stakeholder Participation

## Background

The DCIP must be developed in consultation with parents, school staff, and others in accordance with §100.11 of Commissioner’s Regulations.

## Team Members

Use the space below to identify the members of the DCIP team, their role (e.g. principal, teacher, parent), and, when applicable, the school the individual represents.

| Name | Role | School (if applicable) |
| --- | --- | --- |
| Dr. Paul J. Padalino | Superintendent | KCSD |
| Reinhardt, Kirk | Deputy Superintendent | KCSD |
| Oliveto, Alissa | Assistant Superintendent for CIA & D | KCSD |
| Felicello, Stacia | Assistant Superintendent for Elementary & PPS | KCSD |
| Williams, Lynnette | Assistant Superintendent for Secondary & PPS | KCSD |
| Long, Joyce | Director of Special Services | KCSD |
| Carbon, Sharifa | Assistant Superintendent for Business | KCSD |
| Bonville, Mary Beth | Assistant Superintendent for HR & Communications | KCSD |
| Anderson, Marie | BOE President | KCSD |
| Beesmer, Jennifer | Teacher | Robert Graves |
| Berrios, Laurie | Parent | KHS |
| Brown, Erica | Parent | KHS |
| Clemente, Jodi | Teaching Assistant | Chambers |
| Cordel, Malia | Parent from Title I school | Miller |
| Creft, Stevie | Director for MST | KCSD |
| Cutrone, Alexandra | Specialized Instructional support Personnel | Edson |
| Dallies, Susan | Parent | KHS |
| Daniels, Jason | Parent from Title I school | JFK |
| Fischer, Yanna | Parent from Title I school | GW |
| Fitzpatrick, Anthony | BOE Trustee | KCSD |
| Gribbin, Jennifer | Director of ENL & World Language | KCSD |
| Heddleson, Heather | Parent from Title I school | Crosby |
| Heredia, Shellian | Other School Leaders | JWB |
| Hilgart, Erin | Parent from Title I school | GW |
| Jacobowitz, Robin | Professor SUNY New Paltz | Community Member/Higher Ed |
| Jiorg, Benny | Student | KHS |
| Kearns, Stephanie | Parent from Title I school/ BOE Trustee (7/9/25) | Crosby/Miller |
| Lebowitz, Rebecca | Parent | KHS |
| LoBianco, Wanda | Principal | GW |
| Lowell, Kathleen | Principal | Edson |
| Mann, Jacqueline | Instructional Coach | Miller |
| Medenbach, Jenna | Parent |  |
| Nelson, Erin | Principal | Myer |
| Schwimmer, Edith | Social Worker | KHS |
| Shannon, Monae | Teacher | Miller |
| Sheber, Andrew | Principal | Miller |
| Spicer, Steven | BOE Trustee | KCSD |
| Stein, Chris | Parent Title I School | Crosby |
| VanKleeck, Bonnie | Special Education Teacher/ KTF President | Chambers/ KCSD |
| Holbrook, Sarah | Director of Humanities | KCSD |
| Warner, Ninette | Cornell Cooperative Extension | Community Partner |
| Whalen, Daniel | Boy’s & Girl’s Club | Community Partner |
| Woodworth, Rose | Parent from Title I School |  |
| Diedhou, Kristen | Instructional Coach | JWB |

## Meeting Dates

Use the table below to identify the dates and locations of DCIP planning meetings.

| Meeting Date | Location |
| --- | --- |
| June 26, 2025 | KHS Library |
| November 20, 2025 | KHS Library |
| February 24, 2026 | KHS Library |
| June 30, 2026 | KHS Library |

## Districts with Schools Identified for TSI/ATSI Support Only

Identify how the perspectives of stakeholders associated with the identified subgroup(s) have been incorporated.

| Stakeholder group | How the perspectives of this group have been incorporated into the DCIP? |
| --- | --- |
| Teachers responsible for teaching each identified subgroup |  |
| Parents with children from each identified subgroup |  |
| Secondary Schools: Students from each identified subgroup |  |

# Submission Assurances

## Directions

Place an "X" in the box next to each item prior to submission.

- The District Comprehensive Improvement Plan (DCIP) has been developed in consultation with parents, school staff, and others in accordance with the requirements of Shared-Decision Making (CR 100.11) to provide a meaningful opportunity for stakeholders to participate in the development of the plan and comment on the plan before it is approved.

- The DCIP will be implemented no later than the beginning of the first day of regular student attendance.

- Professional development will be provided to teachers and school leaders that will fully support the strategic efforts described within this plan.

- The DCIP will be posted on the district’s website and easily accessible when navigating the website.

- A comprehensive systems approach will be established to recruit, develop, retain, and equitably distribute effective teachers and school leaders as part of the implementation of the Annual Professional Performance Review (APPR) system required by Education Law §3012(c) and §3012(d).

- Meaningful time for collaboration will be used to review and analyze data in order to inform and improve district policies, procedures, and instructional practices.

## Submission Instructions

All Districts: Submit this document to DCIP@nysed.gov by July 1, 2025.

The final plan must be approved by the Superintendent and the Board of Education (in New York City, the Chancellor or the Chancellor’s designee).