# Virginia’s Comprehensive School Support Plan

Virginia’s comprehensive school support plan (CSSP) integrates findings from Virginia’s needs assessment to help guide schools as they prioritize work, predict and neutralize barriers, and catalyze transformative practices that will improve student outcomes.  There are four sections to the comprehensive school support plan, aligned to the Virginia Support Framework:

- Academic Supports

- Staffing Supports

- Professional Learning Supports

- School Climate Supports

High-quality plans support school leaders as they work to allocate human and fiscal resources, establish short-and long-term goals, monitor processes, and scale successes. Specifically, a high-quality plan is:

- Grounded in the continuous improvement process and high expectations for all students;

- Developed and revised through engagement with stakeholders-- including families; and,

- Based on evidence-and research-based strategies aligned to the needs and context of the school.

Effective plans are based on the most important changes needed in the school and demonstrate alignment to federal, state, division, and school priorities by relating goals, measures, strategies, and resources to division plans, federal and state laws and guidance, including Virginia’s Support Framework.

How to use the Virginia Comprehensive School Support Plan:

- Review the Virginia Support Framework domains and the results of the Virginia Support Framework Needs Assessment.

- Become familiar with the explanation and example of the Comprehensive School Support Plan template which includes a description and example for each item.

- Complete the profile information, providing information on designations, School Quality Indicators, Levels, and/or federal identification. An overview of the internal and external stakeholder, including families, that have been engaged in the school improvement process should also be documented.

- Use the results from the needs assessment to develop the plan for each domain and indicator, including barriers from a root-cause analysis establishing SMART goals, the alignment to evidence and research-based strategies, the development and implementation of the plan, and the artifacts to be regularly collected and analyzed for progress monitoring.

| Domain of Support | Description |
| --- | --- |
| Academic | Providing high-quality instructional materials, routines, and prioritized placement are critical to the successful operation of the school division, and focuses on alignment, engagement, rigor, and organizing staff based on need. |
| Staffing | Recruiting, allocating, and retaining teachers and principals to address schools and areas with the greatest needs, to include building capacity from those within and the retention of high-quality staff are integral to school division success. |
| Professional Learning | Managing a school building effectively by providing logistical support to maximize learning through clear calendars and master schedules; and targeting professional learning centered on the instructional cycle with a focus on student outcomes. |
| School Climate | Engaging with families and providing instructional materials, learning opportunities, and supports to improve attendance creates a welcoming culture. Connecting each student with an adult creates a safe and orderly environment. |

| Profile Information |  |
| --- | --- |
| Division: Roanoke City Public Schools | School: Preston Park Elementary School |
| Principal: Eric Fisher | Designations (if applicable): |
| Stakeholder/Family Engagement |  |
| Describe how the school will routinely involve internal and external stakeholders in the school improvement process to include conducting the needs assessment; selecting evidence-and research-based strategies; and developing, implementing, monitoring, and evaluating the plan. |  |
| The school will involve internal and external stakeholders in the school improvement process by identifying and establishing priorities based on our needs assessment data. We will communicate our vision and goals of our CSSP to our stakeholders, soliciting their feedback and input. Upon completion of meetings and discussions, we conduct activities for all school personnel, students, and families to share our CSSP and provide updates throughout the process. On selecting our evidence and research-based strategies, our Leadership Team will identify the behaviors outlined in our CSSP and create a measurable goal for the behavior. To successfully involve all participants throughout this process, we will disseminate information about our improvement events via our school website, parent communication platforms, newsletters, PTA meetings, and staff meetings. We will discuss, monitor, and evaluate our plan by collecting data from assessments, surveys, observations, and lesson plans while analyzing our data utilizing using a rubric to assist with determining provisions needed. We will share data with all stakeholders via newsletters, staff meetings, and PTA meetings. |  |

| Domain I: Academic Supports |  |  | Content Area: English |  |
| --- | --- | --- | --- | --- |
| Barrier(s): - Time for and quality of professional development - Master schedule (intervention opportunities) - 50% of student population are English learners |  |  |  |  |
| SMART Goal Statement: By June 2025, we will increase the number of K-2 students who meet the spring VALLS benchmark by 10% points and subgroups of students in grades 3-5 will increase proficiency by at least 3% to meet academic achievement on reading SOL assessments. |  |  |  |  |
| (Evidence-based) Strategy Name: WWC IES Practice Guide: Improving Adolescent Literacy – Effective Classroom and Intervention Practices (4th/5th grade focus): Recommendation 1 – Provide Explicit Vocabulary Instruction (Level of Evidence- Strong) Teachers should provide students with explicit vocabulary instruction both as part of reading and language arts classes and as part of content area classes such as science and social studies. By giving students explicit instruction in vocabulary, teachers help them learn the meaning of new words and strengthen their independent skills of constructing the meaning of text. Tier of Evidence: Strong |  | Description: Integrate vocabulary instruction in the content areas and during the language arts block by identifying the vocabulary students need in order to access/understand grade level complex text and build knowledge. Develop an effective routine for targeted and explicit vocabulary instruction. Use repeated exposure to new words in multiple oral and written contexts and allow multiple opportunities for students to practice using the vocabulary. Give students many opportunities to use new vocabulary in a variety of contexts through activities such as discussion, writing, and extended reading. Provide students with strategies to make them independent vocabulary learners such as using word components (affixes) to derive the meaning of unfamiliar words as well as the use of glossaries available included in the texts that students are reading. Provide Spanish cognates as it applies to working with Spanish speaking English learners. |  |  |
| (Evidence-based) Strategy Name: LETRS VOL. 2 Objective 5.1 Use a variety of techniques to explore word relationships (K-5th grade) (Level of Evidence- Strong…research shows that words are more likely to be learned in relation to other words LETRS Unit 5 p. 43) After students are introduced to new vocabulary, they must be provided with meaningful opportunities to use the new words and apply meaning to the words in context through reading and writing. |  | Description: After words are introduced, they should be revisited frequently with elaboration/extension activities that include speaking, reading and writing (LETRS VOL. 2, p. 44). Dimensions of word knowledge and shades of meaning should be practiced with a variety of supports including graphic organizers, word classification activities, identification of synonyms and antonyms and sematic feature analysis activities. |  |  |
| Student Measure #1: VALLs, Benchmarks, Heggerty, UFLI (formative/summative assessment) |  | Student Measure #2: Pre and post assessments |  |  |
| Staff Measure #1: Walk-throughs and lesson plan feedback |  | Staff Measure #2: Student performance reports from HQIM (High Quality Instructional Materials) |  |  |
| Action Plan |  |  |  |  |
| Action Steps (Describe the step and include who will implement and how often it will be implemented) | Start of Action Step | End of Action Step | Position Responsible for Monitoring | Budget (local, state, federal funds) |
| Develop and monitor lesson plans and collaborative learning team structures to ensure instruction is aligned with Virginia's SOLs and Curriculum Framework | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Develop and monitor data meetings to review reading data to inform instruction in group students based on their academic needs | October 2024 | June 2025 | Administration, Instructional Coach, Reading Specialists, Grade Level Chairs | n/a |
| Provides feedback to teachers through the observation and walkthrough process to ensure that instruction aligns with Virginia SOLs and Curriculum Framework | October 2024 | June 2025 | Administration, Instructional Coach | n/a |
| Teachers will participate in ongoing professional development to ensure alignment and consistency | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Utilize grade level meetings to build capacity on lesson planning and alignment to the Virginia standards and curriculum framework and both content and cognition | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Local Educational Agency (LEA) Support: Describe how the LEA will support in implementing, monitoring, and evaluating this strategy. |  |  |  |  |
| District supervisors will provide support and guidance, as requested |  |  |  |  |
| Evidence: Based on the action steps, define what measurable evidence would indicate progress towards the long-term goal. Analysis: Address impact and next steps. |  |  |  |  |
| Evidence of Progress (update monthly) |  | Analysis of Progress (update monthly) |  |  |

| Domain I: Academic Supports |  |  | Content Area: Mathematics |  |
| --- | --- | --- | --- | --- |
| Barrier(s): - Time for and quality of professional development - Master schedule (intervention opportunities) - 50% of student population are English learners |  |  |  |  |
| SMART Goal Statement: By June 2025, students in grades K-2 will demonstrate growth on math assessments while student subgroups in grades 3-5 will demonstrate 3% increase in pass rates on the math SOL test. |  |  |  |  |
| (Evidence-based) Strategy Name: https://ies.ed.gov/ncee/wwc/PracticeGuide/26 Tier of Evidence: Strong |  | Description: This practice guide provides evidence-based practices that can help teachers tailor their instructional approaches and/or their mathematics intervention programs to meet the needs of their students. |  |  |
| Student Measure #1: MAP assessment results |  | Student Measure #2: Pre and post assessments |  |  |
| Staff Measure #1: Walk-throughs and lesson plan feedback |  | Staff Measure #2: Student performance reports from HQIM (High Quality Instructional Materials) |  |  |
| Action Plan |  |  |  |  |
| Action Steps (Describe the step and include who will implement and how often it will be implemented) | Start of Action Step | End of Action Step | Position Responsible for Monitoring | Budget (local, state, federal funds) |
| Develop and monitor lesson plans and collaborative learning team structures to ensure instruction is aligned with Virginia's SOLs and Curriculum Framework | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Develop and monitor data meetings to review math data to inform instruction in group students based on their academic needs | October 2024 | June 2025 | Administration, Instructional Coach, Reading Specialists, Grade Level Chairs | n/a |
| Provides feedback to teachers through the observation and walkthrough process to ensure that instruction aligns with Virginia SOLs and Curriculum Framework | October 2024 | June 2025 | Administration, Instructional Coach | n/a |
| Teachers will participate in ongoing professional development to ensure alignment and consistency | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Utilize grade level meetings to build capacity on lesson planning and alignment to the Virginia standards and curriculum framework and both content and cognition | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Local Educational Agency (LEA) Support: Describe how the LEA will support in implementing, monitoring, and evaluating this strategy. |  |  |  |  |
| District supervisors will provide support and guidance, as requested |  |  |  |  |
| Evidence: Based on the action steps, define what measurable evidence would indicate progress towards the long-term goal. Analysis: Address impact and next steps. |  |  |  |  |
| Evidence of Progress (update monthly) |  | Analysis of Progress (update monthly) |  |  |

| Domain I: Academic Supports |  |  | Content Area: Science |  |
| --- | --- | --- | --- | --- |
| Barrier(s): - Time for and quality of professional development - Master schedule (intervention opportunities) - 50% of student population are English learners |  |  |  |  |
| SMART Goal Statement: By June 2025, teachers in grades K-4 will share an increased exposure to science instruction while student subgroups in grade 5 will demonstrate 3% increase in pass rates on the science SOL test. |  |  |  |  |
| (Evidence-based) Strategy Name: (Evidence-based) Strategy Name: WWC IES Practice Guide: Improving Adolescent Literacy – Effective Classroom and Intervention Practices (4th/5th grade focus): Recommendation 1 – Provide Explicit Vocabulary Instruction (Level of Evidence- Strong) Teachers should provide students with explicit vocabulary instruction both as part of reading and language arts classes and as part of content area classes such as science and social studies. By giving students explicit instruction in vocabulary, teachers help them learn the meaning of new words and strengthen their independent skills of constructing the meaning of text. Tier of Evidence: Strong |  | Description: Integrate vocabulary instruction in the content areas and during the language arts block by identifying the vocabulary students need in order to access/understand grade level complex text and build knowledge. Develop an effective routine for targeted and explicit vocabulary instruction. Use repeated exposure to new words in multiple oral and written contexts and allow multiple opportunities for students to practice using the vocabulary. Give students many opportunities to use new vocabulary in a variety of contexts through activities such as discussion, writing, and extended reading. Provide students with strategies to make them independent vocabulary learners such as using word components (affixes) to derive the meaning of unfamiliar words as well as the use of glossaries available included in the texts that students are reading. Provide Spanish cognates as it applies to working with Spanish speaking English learners. |  |  |
| (Evidence-based) Strategy Name: LETRS VOL. 2 Objective 5.1 Use a variety of techniques to explore word relationships (K-5th grade) (Level of Evidence- Strong…research shows that words are more likely to be learned in relation to other words LETRS Unit 5 p. 43) After students are introduced to new vocabulary, they must be provided with meaningful opportunities to use the new words and apply meaning to the words in context through reading and writing. |  | Description: After words are introduced, they should be revisited frequently with elaboration/extension activities that include speaking, reading and writing (LETRS VOL. 2, p. 44). Dimensions of word knowledge and shades of meaning should be practiced with a variety of supports including graphic organizers, word classification activities, identification of synonyms and antonyms and sematic feature analysis activities. |  |  |
| Student Measure #1: Benchmark assessment results |  | Student Measure #2: Pre and post assessments |  |  |
| Staff Measure #1: Walk-throughs and lesson plan feedback |  | Staff Measure #2: Student performance reports from HQIM (High Quality Instructional Materials) |  |  |
| Action Plan |  |  |  |  |
| Action Steps (Describe the step and include who will implement and how often it will be implemented) | Start of Action Step | End of Action Step | Position Responsible for Monitoring | Budget (local, state, federal funds) |
| Develop and monitor lesson plans and collaborative learning team structures to ensure instruction is aligned with Virginia's SOLs and Curriculum Framework | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Develop and monitor data meetings to review science data to inform instruction in group students based on their academic needs | October 2024 | June 2025 | Administration, Instructional Coach, Reading Specialists, Grade Level Chairs | n/a |
| Provides feedback to teachers through the observation and walkthrough process to ensure that instruction aligns with Virginia SOLs and Curriculum Framework | October 2024 | June 2025 | Administration, Instructional Coach | n/a |
| Teachers will participate in ongoing professional development to ensure alignment and consistency | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Utilize grade level meetings to build capacity on lesson planning and alignment to the Virginia standards and curriculum framework and both content and cognition | October 2024 | June 2025 | Administration, Instructional Coach, Grade Level Chairs | n/a |
| Local Educational Agency (LEA) Support: Describe how the LEA will support in implementing, monitoring, and evaluating this strategy. |  |  |  |  |
| District supervisors will provide support and guidance, as requested |  |  |  |  |
| Evidence: Based on the action steps, define what measurable evidence would indicate progress towards the long-term goal. Analysis: Address impact and next steps. |  |  |  |  |
| Evidence of Progress (update monthly) |  | Analysis of Progress (update monthly) |  |  |

Domain of Support

| Domain II: Staffing Supports |  |  |  |  |
| --- | --- | --- | --- | --- |
| Barrier(s): The needs of our high number of EL students are not being fully met, as more staff is needed. Until that happens in 25-26, enhanced collaboration is needed between classroom teachers and EL staff. |  |  |  |  |
| SMART Goal Statement: By June 2025 (for the upcoming 25-26 school year), our school will increase the number of staff members dedicated to working with our EL students. In the meantime, Preston Park will increase support opportunities for teachers. |  |  |  |  |
| (Evidence-based) Strategy Name: Promote teacher engagement and create supportive school culture that supports teacher well-being Tier of Evidence: 1 |  | Description: We will engage teachers by increasing communication, establish goals that address the needs of the school and ensuring our initiatives align with our goals. |  |  |
| Student Measure #1: Increase in student engagement and achievement |  | Student Measure #2: Increase in student attendance due to improved engagement with teaching staff. |  |  |
| Staff Measure #1: More EL staff slated for 25-26 |  | Staff Measure #2: More collaboration opportunities between general education staff and EL staff |  |  |
| Action Plan |  |  |  |  |
| Action Steps (Describe the step and include who will implement and how often it will be implemented) | Start of Action Step | End of Action Step | Position Responsible for Monitoring | Budget (local, state, federal funds) |
| Encourage a culture of collaboration where teachers share resources and strategies. | August 2024 | May 2025 | Administration Team, Instructional Coach | N/A |
| Establish open lines of communication between teachers and administration to discuss concerns and suggestions. | August 2024 | May 2025 | Leadership Team | N/A |
| Promote a leadership style that is supportive, transparent, and responsive to teacher needs. | August 2024 | May 2025 | Administration Team, Instructional Coach | N/A |
| Offer professional development opportunities to enhance collaboration between classroom teachers and EL staff | October 2024 | June 2025 | Administration Team, Instructional Coach, EL Coordinator |  |
| Local Educational Agency (LEA) Support: Describe how the LEA will support in implementing, monitoring, and evaluating this strategy. |  |  |  |  |
| District office staff will provide support and guidance, as requested |  |  |  |  |
| Evidence: Based on the action steps, define what measurable evidence would indicate progress towards the long-term goal. Analysis: Address impact and next steps. |  |  |  |  |
| Evidence of Progress (update monthly) |  | Analysis of Progress (update monthly) |  |  |

Domain of Support

| Domain III: Professional Learning Supports |  |  |  |  |
| --- | --- | --- | --- | --- |
| Barrier(s): Time constraints, resistance to change, lack of personnel resources |  |  |  |  |
| SMART Goal Statement: By June 2025, all classrooms will have designated times and personnel to provide small group/individualized intervention support. |  |  |  |  |
| (Evidence-based) Strategy Name: Tier of Evidence: Choose an item. |  | Description: |  |  |
| Student Measure #1: Participation in intervention groups |  | Student Measure #2: Improved academic performance |  |  |
| Staff Measure #1: Adjustments to master schedule to allow for intervention times |  | Staff Measure #2: Acquisition of personnel to accommodate intervention support in every classroom |  |  |
| Action Plan |  |  |  |  |
| Action Steps (Describe the step and include who will implement and how often it will be implemented) | Start of Action Step | End of Action Step | Position Responsible for Monitoring | Budget (local, state, federal funds) |
| Adjustments will be made to the master schedule to allow for every class to have a designated intervention time | October 2024 | June 2025 | Administration | n/a |
| Personnel will be recruited and hired to provide support for intervention groups in every classroom | October 2024 | June 2025 | Administration | All In funding |

| Local Educational Agency (LEA) Support: Describe how the LEA will support in implementing, monitoring, and evaluating this strategy. |  |
| --- | --- |
| Central office staff will provide support and guidance, as requested |  |
| Evidence: Based on the action steps, define what measurable evidence would indicate progress towards the long-term goal. Analysis: Address impact and next steps. |  |
| Evidence of Progress (update monthly) | Analysis of Progress (update monthly) |

| Domain IV: School Climate Supports |  |  |  |  |
| --- | --- | --- | --- | --- |
| Barrier(s): transportation, language, stakeholder buy-in |  |  |  |  |
| SMART Goal Statement: By June 2025, Preston Park’s chronic absenteeism rate will decrease by 5% (19.58 to 14.58). |  |  |  |  |
| (Evidence-based) Strategy Name: Attendance Works Chronic Attendance Nudge Letters Tier of Evidence: Strong |  | Description: Caregivers will receive a personalized letter detailing the amount of days and which days their student was absent. The information will be displayed on a calendar to drive home how absences can directly affect student academic growth and understanding. Attendance Works recommends a tiered approach that starts with foundational supports for the whole school. These foundational supports are followed by prevention-oriented supports for attendance (Tier1), more personalized outreach or early intervention (Tier 2), and intensive intervention (Tier 3). |  |  |
| Student Measure #1: Decrease in days absent |  | Student Measure #2: Increase in academic growth |  |  |
| Staff Measure #1: Weekly attendance meeting logs |  | Staff Measure #2: Communication logs |  |  |
| Action Plan |  |  |  |  |
| Action Steps (Describe the step and include who will implement and how often it will be implemented) | Start of Action Step | End of Action Step | Position Responsible for Monitoring | Budget (local, state, federal funds) |
| Weekly attendance data review. | October 2024 | June 2025 | Administration, office staff, intervention specialists | n/a |
| The use of Attendance Nudge Letters for students with chronic attendance behaviors. | October 2024 | June 2025 | Administration, intervention specialists, teachers | School funds for postage |
| Meetings held with parents of students who demonstrate excessive absences | October 2024 | June 2025 | Administration, intervention specialists | n/a |

| Local Educational Agency (LEA) Support: Describe how the LEA will support in implementing, monitoring, and evaluating this strategy. |  |
| --- | --- |
| Central office staff will provide support and guidance, as requested |  |
| Evidence: Based on the action steps, define what measurable evidence would indicate progress towards the long-term goal. Analysis: Address impact and next steps. |  |
| Evidence of Progress (update monthly) | Analysis of Progress (update monthly) |

In accordance with the Standards of Quality (SOQ) and Standards of Accreditation (SOA), all schools are to prepare a comprehensive, unified, long-range plan in conjunction with the division long-range comprehensive plan, and make it available to the public (SOQ, § 22.1-253.13:6.; SOA 8VAC20-131-390; 8VAC20-131-400). Under the Every Student Succeeds Act (ESSA), schools identified for comprehensive, targeted, and additional targeted support and improvement are required to develop plans based on a set criteria with state educational agency (SEA), local educational agency (LEA), and school approval (ESSA §1111(d)(1)(B); §1111(d)(2)(B)-(C))