| Timberlane Action Plan Response to Instruction Subcommittee |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Goal 1. The District Framework for RTI for Literacy, Math and Behavior is written, articulated and implemented district-wide as measured by staff professional development and student progress monitoring data, resulting in increased student achievement. |  |  |  |  |  |
|  | Activity/ Strategy | Intended Outcomes | Measurement of Success | Goal Alignment | Progress Notes |
| 1.1 | Finish writing RTI frameworks with NH Responds (Howard Muscott) | To generate a document that all staff can access | District receives final copy of plan from Howard M. | Strategic Plan Goal 2 | Complete by Sept 2013 Not received as of 12/16/13 |
| 1.2 | District-wide roll- out of overview of RTI framework (presented by RTI SAU team) | All staff hear same message; all staff receive a copy of the document at October 7th faculty meeting. | Copy of framework given to every staff member; is used in mentoring training for new staff. Staff can articulate framework Presentation is posted on Sharepoint | Strategic Plan Goal 2 | Complete by October 7, 2013* *All except HS- completed Ele paras- done Nov 6th Need to roll out to all HS staff and MS para staff |
| 1.3 | Each school completes needs assessment for RTI implementation Needs assessment is approved by SLT for distribution (1/2014) | Determine focus of their RTI work ( Literacy, Math or Behavior) | Needs assessment is developed on Survey Monkey; staff complete survey- Completed Written product | Strategic Plan Goal 2 | Completed by January 31,2014 |
| 1.4 | Each School develops an action plan to implement RTI focus area | Each school will build capacity for implementation of RTI | Written product | Strategic Plan Goal 2 | Completed by Spring 2014 |

| Timberlane Action Plan Response to Instruction Subcommittee |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Goal 2. Tier 2 instruction is articulated and implemented in each school and measured by student progress monitoring data, supported by staff development resulting in increased student achievement. |  |  |  |  |  |
| 2.1 | Each school will define the scientifically based intervention programs/strategies to be used at Tier 2 | Consistency and efficacy of Tier 2 interventions Use Scientific research based instruction and strategies for maximum result | Written product and classroom observations | Strategic Plan Goal 2 | Completed by June 2014 |
| 2.2 | Each school will know what progress monitoring tools to be used for Tier 2 (as determined by the District Data Team). | To be able to measure effectiveness of intervention Use Scientific research based assessment tool(s) for most accurate data | Written product and observation of PLC discussions | Strategic Plan Goal 2 | Completed by June 2014 |
| 2.3 | Each school will determine staff professional development needs based on the interventions and monitoring tool used | To ensure that all staff have the necessary training to implement Tier 2 strategies with fidelity, and to collect and interpret progress monitoring data accurately | Record of staff training; classroom observation | Strategic Plan Goal 2 | Completed by September 2014 |
| 2.4 | Each school will define the scientific research based enrichment/extension strategies to be used at Tier 2 | To extend the learning and challenge students who have mastered the core | Written product and classroom observations Increase number of students scoring a 4 on the NECAP | Strategic Plan Goal 2 | Completed by September 2014 |