| Revision History |  |
| --- | --- |
| Revision Date | Section/Nature of Revision |
| 3/1/17 | Document issued |
| 5/19/26 | 1.3 A: removed 1-15 |

PART 1 – GENERAL

1.1     SCOPE

- This section encompasses the summarization of procedures for closing out the construction contract and the project's transition into the owner's control and requirements prerequisite to reduction of retainage and final payment.

1.2     PUNCH LIST AND FINAL INSPECTION

A.	When the Construction Manager (CM) or Contractor determines that the project is at a point of substantial completion, they shall prepare a punch list of the items to be completed or corrected.  The Owner shall be notified in writing, through the Project Architect, that the project will be ready for Substantial Completion Inspection, a definite date and hour shall be stated in such notice.  Such notification shall be given at least 30 days prior to the date stated for the inspection.

B.	It shall be noted here and emphasized that preparation of the initial punch list is the responsibility of the CM/Contractor and not the Project Architect.  At the substantial completion inspection(s), the Project Architect shall use the skilled and experienced in-house engineers who prepared the corresponding portions of the contract documents, to assist in the preparation of the Project Architect's punch list.  The Owner shall be invited to participate in the punch list inspection(s).  It may be anticipated that the Owner will include the following people in the walkthrough punch list inspection:  the Director, Manager Design, Manager Construction and Project Coordinator assigned to the project and inspectors of the Facilities Design and Construction Department; Maintenance Department inspectors; school principal or designee and Head Plant Operator; the General Manager for the facility and all other pertinent representatives of Pinellas County Schools (PCS).  The CM/Contractor shall participate in the Project Architect/Engineer's (PAE) punch list inspection(s).

C.	The punch list shall be generated in such a fashion that all items (trade comments) shall be per building, per room in one area of the punch list.

Example: B4, Rm 6

Architect comments

Electrical comments

Mechanical comments

Plumbing comments

PCS comments

B4, Rm 7

Architect comments

Electrical comments

Mechanical comments

Plumbing comments

PCS comments

D.	Any person participating in the punch list inspection may request items be added to the punch list.  However, it shall be the responsibility of the PAE and his sole prerogative to determine whether an item is to be placed on the punch list." Only items of work judged to be required by the CM/Contract documents may be placed on the punch list.  The punch list inspection is not to be used as opportunity to express opinion of how things should have been otherwise.  Such comments will be considered ill-mannered and out of order.

E.	The punch list for a portion of the project shall be called a partial punch list.  A punch list for the full project shall be identified as the full punch list.  The punch list once made shall be considered the official one and final punch list for a portion of the Project or the full Project, as applicable.  Neither additions nor deductions shall be made to the punch list once determined by the PAE.  The following people are required to personally sign the punch list(s):

- The PAE's designee.

- PCS’ Coordinator.

- The CM/Contractor's designee.

- The school's principal of the facility, or director of the facility, or their designee.

F.	Should the CM/Contractor disagree that an item or items should be on the punch list, they shall designate such item(s) by an asterisk and at the bottom or end of the punch list and shall write the notation I do not agree that items marked by an asterisk should be included on the punch list, the CM/Contractor shall sign such notation.  Such notation shall be sufficient notice to have the design professional determine whether the item is a contract deficiency.  If the asterisk item is not a contract deficiency it shall be marked Not in Contract (NIC) and signed off by the design professional.  The CM/Contractor shall proceed immediately to complete or correct all undisputed items on the punch list.

G.	Should the school's principal, plant director or other designee, or the Facilities Design and Construction Department Coordinator or other designee believe items of work should be included on the punch list but were determined by the PAE as not proper to include as work required under the contract, such representatives of the Owner shall, nevertheless, sign the punch list thus identifying it as the official punch list but shall by asterisk and notation qualify his/her signature stating additional items should, in their opinion have been included on the punch list.  Such a point of dispute shall immediately be brought to the personal attention of the Facilities Design and Construction Department Coordinator with a copy of such additional items.  The PAE shall likewise be notified.  In such an event the punch list may be reopened.

H.	Items of work found, after the punch list has been signed, which are incomplete or require correction, shall be considered a responsibility of the CM/Contractor under his guarantees and warranties or as discovered latent defects.  Such shall not be a reason for nonpayment to the CM/Contractor.

I.	Copies of the signed punch list shall be immediately delivered by the PAE to each person signing the punch list.  The original signed copy of the punch list shall be delivered to the Facilities Design and Construction Coordinator.  The original copy shall be considered to be the punch list.  The punch list(s) may be partial for a portion of the project or full for the entire project; there shall be only one punch list for each portion of a project.

J.	The punch list(s) shall be the document used to determine the completeness of the work for purposes of reduction of retainage and final payment to the CM/Contractor after the date of Substantial Completion.  Upon completion and/or corrections to all items on the punch list(s), (30 days for project value less than $10 million and 60 days for project value more than $10 million). The PAE or Owner may not refuse to certify payment due to the CM/Contractor on the basis of the work being incomplete.

K.	When the CM/Contractor notifies the PAE that he has completed the work on the punch list, the PAE shall schedule an inspection meeting with the CM/Contractor, the PAE, the Facilities Design and Construction Department Coordinator and the school's principal or center, or plant director (or their designee).  Each item on the punch list, which is found to be completed or corrected, shall be marked accordingly.  Any item not completed or corrected shall remain on the punch list.

L.	The original punch list inspection for each portion of the project and one follow-up punch list inspection shall be considered normal services of the PAE.  All additional punch list follow-up inspections shall be considered extended services of the PA/E and the Owner will back charge the CM/Contractor for such excessive inspections.

1.3	CLOSEOUT DOCUMENTS

A.	At the time of the Substantial Completion inspection for the entire project, or within fifteen days thereafter, the CM/Contractor shall submit to the Project Architect two (2) thumb drives of the following:

- The Facilities Design and Construction Department Project Closeout Checklist (Appendix 01 70 00.01) shall organize the closeout package.  All items listed on the Facilities Design and Construction Department Project Closeout Checklist that pertains to this project shall be provided.

1.4     INSTRUCTION OF PERSONNEL

- The CM/Contractor shall schedule, through the Facilities Design and Construction Department Coordinator, instructional and demonstration meetings at the site of work.  Skilled and experienced representatives of the subcontractor and of the equipment manufacturers shall lead these meetings.

B.	Comply with the specific requirements set forth in the several technical trade sections bound into these specifications.

C.	General:

- The CM/Contractor shall provide free instruction on the proper use and operation of installed equipment to the designated representatives of the Owner.

- Instruction of the Owner's maintenance supervisor in the proper methods of cleaning and maintaining all the finished surfaces and the proper methods of replacement of the consumable items such as filters, light bulbs, washers, etc., shall be part of this work.

- The CM/Contractor shall submit to the Facilities Design and Construction Department documentation for each instructional period required, i.e. Agenda and Sign-In Sheet and video of training.

1.5     TESTING AND MAINTENANCE

- The CM/Contractor guarantees and warrants the work that all materials used and workmanship performed in connection with this contract shall be free from defects for a period of one year from date of execution of the final Certificate of Substantial Completion.

- The CM/Contractor shall start up, test, adjust, balance and otherwise place in a satisfactory working condition all items of mechanical and electrical systems and shall fully instruct representatives of the Owner in the care and operation of such systems.  Comply with all requirements of the Test and Balance Section of these specifications.

- During a valid warranty period, if the CM/Contractor is unable or unwilling to respond immediately to make emergency repairs under conditions which PCS may determine to be an emergency situation, the Owner reserves the right and the CM/Contractor recognizes such right, to make such emergency repairs and then to bill the CM/Contractor for a fair and reasonable amount in reimbursement for such repairs.  Under no circumstances shall such action void the warranty or guarantee as required by the General Conditions or amplified by the Supplementary General Conditions.

PART 2 – PRODUCTS

(Not Used)

PART 3 – EXECUTION

(Not Used)

***END OF SECTION***