### Division and School Information

#### Table 2: Division and School Information

| Information Needed | Enter Information Below |
| --- | --- |
| School Year | 2025-2026 |
| Division Name | Roanoke City Public Schools |
| Division Superintendent | Verletta White |
| School Name | Fallon Park Elementary |
| Grades Served | PK-5 |
| Principal Name | Natosha Weddle |
| Principal Email | nweddle@rcps.info |
| Division Multi-year School Support Plan Lead Name and Title | Kevin G. Bowman, Supervisor of School Improvement |
| Division Multi-year School Support Plan Lead Email | kevinbowman@rcps.info |

### Stakeholder Engagement

Developing the plan with stakeholders is required and includes teachers, school leaders, community partners, parents, students, and representatives from business, higher education, or the military. Actively involving stakeholders supports purposeful planning, builds shared ownership, and helps translate the plan from intent to action, leading to improved student outcomes.

#### Table 3: Stakeholder engagement

Identify the stakeholder group represented, name, email department/office/organization, and title for each stakeholder. Add or remove rows as necessary.

| Stakeholder Representation | Name | Email | Organization, Department, or Office | Title |
| --- | --- | --- | --- | --- |
| School | Natasha Weddle | Nweddle@rcps.info | Fallon Park Elementary | Principal |
| School | Salvatore DAngelo | Sdangelo@rcps.info | Fallon Park Elementary | Assistant Principal |
| School | Rhonda Rhodes | Rrhodes@rcps.info | Fallon Park Elementary | Assistant Principal |
| School | Nate Wills | Nwills@rcps.info | Fallon Park Elementary | Dean of Students |
| School | Rosemary Rincon | Rrincon@rcps.info | Fallon Park Elementary | Targeted School Improvement Mentor |
| School | Liza Burks | Eburks@rcps.info | Fallon Park Elementary | Instructional Coach |
| School |  |  |  |  |
| School |  |  |  |  |
| School |  |  |  |  |
| Division |  |  |  |  |
| Division |  |  |  |  |
| Division |  |  |  |  |

Multi-year School Support Plan

| Multi-year School Support Plan Reading |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Fewer than 10% of K–2 students will be identified as high risk on VALLSS; at least 80% of students in grades 3–5 will score proficient or above on the VA Reading SOL; at least 80% of grades 2–5 students will meet or exceed growth on MAP Reading; and school‑level achievement gaps will be reduced by at least 50% on the Reading SOL. Sustained gains will be maintained and incrementally increased in years two and three |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Reading Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | Reduce the percentage of K–2 students identified as high risk on VALLSS to <10%. Increase grades 3–5 Reading SOL proficiency to ≥80%. Ensure ≥80% of grades 2–5 students meet or exceed MAP Reading growth expectations. Reduce Reading SOL achievement gaps for all student reporting groups by ≥50% from baseline. |  | Maintain or exceed 80% Reading SOL proficiency and MAP growth ≥80%, with documented progress toward 85% on both measures. Keep K–2 VALLSS high‑risk ≤8% and sustain reductions in subgroup gaps beyond Year 1 levels. |  |  | Achieve ≥85% Reading SOL proficiency and MAP growth ≥85%. Reduce K–2 VALLSS high‑risk to ≤6% and sustain cumulative subgroup gap reductions. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Foundational Skills, K–3: Teach students to decode words, analyze word parts, and recognize/write words through explicit, systematic instruction (WWC foundational skills) Grades 4–5: Build decoding and fluency while routinely implementing comprehension‑building practices: build world/word knowledge, teach students to ask/answer text‑dependent questions, use a gist routine, and monitor comprehension. Rationale: Reading performance requires consistent Tier 1 alignment and daily use of research‑based routines. Strengthening decoding and fluency (K–5) and embedding comprehension practices (3–5), combined with progress monitoring and flexible grouping, directly addresses identified needs and supports equitable access to grade‑level texts. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Increased decoding, multisyllabic word reading, and fluency. Improved comprehension with grade‑level texts and stronger stamina. Higher MAP and SOL outcomes with reduced subgroup gaps. Coherent alignment among written, taught, and assessed curriculum, with routine progress monitoring |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Natosha Weddle) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Administration; Targeted School Improvement Mentor; Instructional Coach; Reading Specialists/Coaches; Classroom, SPED, and EL Teachers |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Standards‑Aligned Planning and Delivery | Administration; TSI Mentor; Instructional Coach | August 2025 – May 2026 |  | lesson‑plan reviews; division walkthrough tool; observation feedback |  | Plans and instruction consistently align to SOLs and curriculum framework; explicit foundational and comprehension routines evident in observations | None |  | N/A |
| Data‑Driven Grouping and Intervention | Reading Specialists/Coaches | August 2025 – May 2026 |  | VALLSS, MAP, Lexia, and program reports; pre/post assessments; PLC regrouping logs |  | Movement of students out of high‑risk bands; ≥80% MAP Reading growth; increases on benchmarks/SOLs | None |  | N/A |
| Monthly Literacy PLCs and Feedback Cycles | Administration; TSI Mentor; Instructional Coach | August 2025 – May 2026 |  | PLC agendas/notes; coaching cycles; look‑for trend analyses |  | Instructional adjustments implemented; improved formative/summative results; narrowed subgroup gaps | None |  | N/A |
| Ongoing Professional Learning | Division PD Office; Instructional Coach; TSI Mentor | August 2025 – May 2026 |  | PD rosters; implementation look‑fors; teacher artifacts |  | Increased fidelity to evidence‑based routines K–5; consistent use of HQIM | None |  | SIG |

| Multi-year School Support Plan Math |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | By June 2026, at least 80% of grades 3–5 students will score proficient or above on the VA Math SOL; at least 80% of grades 2–5 students will meet or exceed MAP Math growth; and school‑level achievement gaps will be reduced by ≥50% on the Math SOL. These gains will be maintained and incrementally increased in years two and three. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Math Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | Achieve ≥80% Math SOL proficiency in grades 3–5. Ensure ≥80% of grades 2–5 students meet or exceed MAP Math growth expectations. Reduce Math SOL achievement gaps by ≥50% from baseline. |  | Maintain or exceed 80% SOL proficiency and MAP growth ≥80%, with documented progress toward 85% on both measures. Demonstrate improved performance on representation‑dependent items and multi‑step word problems. |  |  | Achieve ≥85% SOL proficiency and MAP growth ≥85%. Sustain cumulative subgroup gap reductions with consistent CRA and problem‑solving routines across |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Mathematical language instruction to build precise communication. Representations (CRA) and number lines to model and connect concepts and procedures. Rationale: Students struggle to apply concepts in multi‑step contexts; structured, sequenced instruction with accurate visual models, explicit math language, and routine problem‑solving instruction, monitored through regular checks, addresses these gaps and improves access to grade‑level content. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Increased use and accuracy of visual models (number lines, place‑value tools, arrays/bar models) to solve problems. Higher mastery on unit assessments/benchmarks and improved MAP growth. Stronger alignment among written, taught, and tested curriculum; coherent intervention systems. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Natosha Weddle) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Administration; Targeted School Improvement Mentor; Instructional Coach; Division Math Coach; Classroom and SPED Teachers |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| PLCs for Data Review, Placement, and Intervention | Administration; TSI Mentor; Instructional Coach; Division Math Coach | August 2025 – May 2026 |  | PLC agendas/notes; regrouping logs; benchmark/MAP analyses |  | Timely regrouping; improved mastery and MAP growth; documented intervention effectiveness | None |  | N/A |
| Written–Taught–Tested Alignment Training | Administration; TSI Mentor; Instructional Coach; Division Math Coach | August 2025 – May 2026 |  | Lesson‑plan reviews; observation look‑fors on content and cognitive alignment |  | Increased alignment fidelity; higher rigor in observed lessons | None |  | N/A |
| Instructional Walkthroughs and Feedback | Administration; TSI Mentor; Instructional Coach | August 2025 – May 2026 |  | Division walkthrough tool; feedback cycles with follow‑up |  | Consistent implementation of CRA, number lines, and word‑problem routines | None |  | SIG |
| Systematic Small‑Group Instruction and Number‑Sense Routines | Classroom Teachers | August 2025 – May 2026 |  | VKRP/MAP skill checks; Zearn/Hand2Mind usage and performance; pre/post assessments |  | Gains on unit assessments and MAP; acceleration of students below benchmark | Assessment tools |  | N/A |
| Monitor Intervention Effectiveness | Classroom Teachers; Administration; TSI Mentor; Instructional Coach | August 2025 – May 2026 |  | Intervention trackers; bi‑weekly progress monitoring; PLC reviews |  | Students meet benchmark targets; effective interventions scaled; ineffective ones revised or discontinued | None |  | SIG |

Assurances

## Assurance of Review and Approval

School Year: 2025-2026

Division Name: Roanoke City Public Schools

Division-Level Team Lead Name: Archie Freeman III

Division-Level Team Lead Email: Archie Freeman III

School Name: Fallon Park Elementary School

Principal Name: Natosha Waddle

Principal Email: nweddle@rcps.info

School Performance Category: Choose an item.Off Track

School Federal Designation: Choose an item. Targeted Support and Improvement

For Comprehensive Support and Improvement Schools, the Multi-year School Support Plan must be written by the school division for the school and include four evidence-based Interventions. The proposed plan must be approved by the principal and division, reviewed by the local school board, and submitted to the Virginia Department of Education (the Department) by the Division Superintendent for final approval. The Virginia Department of Education will review the plan and may request revisions before approving the plan. The Department-approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(C)(1)) (ESEA Section 1111(d)(1)(B)(v)).

For Targeted Support and Improvement and Additional Targeted Support and Improvement schools, the Multi-year School Support Plan must be written by the school and include two evidence-based Interventions. The proposed plan must be approved by school division and the local school board. The approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(B)) (ESEA Section 1111(d)(2)(B)(iii)).

By signing below, I certify that I have thoroughly reviewed the Multi-year School Support Plan for the federally identified school named in this document. I affirm that the plan:

- Aligns with federal and state requirements for school improvement;

- Addresses the needs identified through a school needs assessment;

- Includes the minimum number of required evidence-based interventions;

- Reflects stakeholder input and collaboration; and

- Establishes clear goals, timelines, and progress monitoring processes.

I approve the contents of this plan and commit to supporting its implementation with fidelity to ensure improved outcomes for all students.

| Principal Name |  | Principal Signature |  | Date Approved |
| --- | --- | --- | --- | --- |
| Division-Level Lead Name |  | Division-Level Lead Signature |  | Date Approved |
| Division Superintendent Name |  | Division Superintendent Signature |  | Date Approved |
|  |  |  |  | Date Reviewed/Approved per School Board Minutes |