### Division and School Information

#### Table 2: Division and School Information

| Information Needed | Enter Information Below |
| --- | --- |
| School Year | 2025-2026 |
| Division Name | Roanoke City Public Schools |
| Division Superintendent | Verletta White |
| School Name | Round Hill Elementary |
| Grades Served | PK-5 |
| Principal Name | Steven Sizemore |
| Principal Email | Stevensizemore@rcps.info |
| Division Multi-year School Support Plan Lead Name and Title | Kevin G. Bowman, Supervisor of School Improvement |
| Division Multi-year School Support Plan Lead Email | kevinbowman@rcps.info |

### Stakeholder Engagement

Developing the plan with stakeholders is required and includes teachers, school leaders, community partners, parents, students, and representatives from business, higher education, or the military. Actively involving stakeholders supports purposeful planning, builds shared ownership, and helps translate the plan from intent to action, leading to improved student outcomes.

#### Table 3: Stakeholder engagement

Identify the stakeholder group represented, name, email department/office/organization, and title for each stakeholder. Add or remove rows as necessary.

| Stakeholder Representation | Name | Email | Organization, Department, or Office | Title |
| --- | --- | --- | --- | --- |
| School | Steve Sizemore | stevensizemore@rcps.info | Principal | Principal |
| School | James Hyatt | jhyatt@rcps.info | AP | AP |
| School | Jake Fumic | jfumic@rcps.info | AP | AP |
| School | Mary Ellen Berry | mberry@rcps.info | TSIM | TSIM |
| School | Nichole Fisher | nfisher@rcps.info | Instructional Coach | Instructional Coach |
| School | Eric Roberts | eroberts@rcps.info | Math Specialist | Math Specialist |
| School | LeighAnn Thurman | Lthurman@rcps.info | EL | EL Team Lead |
| School | Anita Ungs | Aungs@rcps.info | Reading Specialist | Reading Specialist |
| Division | Dr. Wendy Durham | wdurham@rcps.info | Academics | Executive Director |
| Division | Kevin Bowman | kevinbowan@rcps.info | School Improvement | Supervisor of School Improvement |
| Division | Amy Duffy | Aduffy@rcps.info | Math | Math Coach |
| Division | Kaleigh Critzer | Kcritzer@rcps.info | Reading | Reading Coach |

Multi-year School Support Plan

| Multi-year School Support Plan Reading |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | By June 2026, at least 75% of K–2 students will be low risk on VALLSS, and at least 75% of students in grades 3–5 will be proficient on the Reading SOL; these gains will be maintained and incrementally increased through 2027–2028 via aligned instruction, targeted intervention, and ongoing professional learning. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Reading Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | K–2: ≥75% of students identified low risk on VALLSS. Grades 3–5: ≥75% proficient on the Reading SOL. Implement monthly professional learning and systematic progress monitoring to drive regrouping and instructional adjustments in all grades. |  | Maintain or improve Year 1 outcomes (targeting continued increases in K–2 low‑risk and 3–5 proficiency rates) through strengthened fidelity to EBIs, feedback cycles, and PLC‑driven planning |  |  | Sustain or further improve outcomes beyond Year 2 levels with consistent implementation of routines, aligned lesson design, and data‑informed intervention. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | K–3: Teach students to decode words, analyze word parts, and write/recognize words through explicit, systematic routines. Grades 4–5: Routinely use comprehension‑building practices: (A) build world/word knowledge, (B) teach students to ask/answer text‑dependent questions, (C) teach a gist routine, and (D) teach students to monitor comprehension. Rationale: The school has identified variability in training, resources, pacing, and student vocabulary as barriers. Systematic foundational skills (K–3) and daily comprehension routines (4–5), implemented with aligned planning, observation feedback, and PLC data reviews, directly address the documented needs. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Stronger decoding, multisyllabic word reading, and high‑frequency word recognition in K–3. Improved vocabulary, gist generation, and comprehension monitoring in grades 4–5. Increased VALLSS and SOL performance with consistent use of progress‑monitoring data to drive instruction |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Steve Sizemore) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Instructional Leadership Team (ILT) members; Instructional Coaches; Reading Specialist; Grade‑level Teams; District Specialists/Coordinators; CSSP Members; Lead Teachers/Mentors |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Develop and Monitor Aligned Lesson Plan Template and CLT Structures | Principal; ILT Members; District Specialists/Coordinators | August 2025 – May 2026 |  | Lesson plan reviews; RCPS 5 Components/LETRS design checks |  | Plans/observations reflect SOL/alignment and explicit routines | None |  | N/A |
| Data Meetings to Drive Grouping and Instruction | Principal; Instructional Coaches; Reading Specialist; ILT; CSSP Members; District Specialists/Coordinators | August 2025 – May 2026 |  | VALLSS, MAP, SOL, and IL EL “Playground” data reviews; regrouping logs |  | Increased movement to low‑risk (K–2) and SOL proficiency (3–5) | None |  | N/A |
| Observation/Feedback Cycles Using Grows/Glows | Principal; ILT Members; Lead Teachers/Mentors (non‑evaluative) | October 2025 – June 2026 |  | Walkthroughs/observations; feedback logs; follow‑up coaching |  | Improved fidelity to EBIs; upward trends in walkthrough data | None |  | N/A |
| Targeted Professional Learning (SOR, LETRS 1 & 2; IL EL Literacy PLC) | Principal; ILT Members; District Specialists/Coordinators; Instructional Coaches; Reading Specialists; Teachers | October 2025 – June 2026 |  | PD attendance; implementation look‑fors; coaching notes |  | Classroom evidence of SOR‑aligned practices and comprehension routines | None |  | SIG |
| Weekly Planning/PLCs and Monthly Literacy PLCs | Principal; ILT Members; Instructional Coaches; Grade‑level Teams; Reading Specialists | October 2025 – June 2026 |  | PLC agendas/minutes; unit plans; student work protocols |  | Documented instructional adjustments; improved interim outcomes | None |  | N/A |

| Multi-year School Support Plan Math |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | By June 2026, at least 75% of K–1 students will be on grade level (local benchmarks/VKRP), 75% of Grade 2 students will be proficient (MAP), and 75% of Grades 3–5 students will be proficient on the Mathematics SOL; these gains will be maintained and incrementally increased through 2027–2028. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Math Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | K–1: ≥75% on grade level via local benchmarks/VKRP. Grade 2: ≥75% proficient on MAP. Grades 3–5: ≥75% proficient on Mathematics SOL. Implement monthly math PLCs and progress‑monitoring cycles to adjust Tier 1 and small‑group instruction. |  | Maintain or improve Year 1 outcomes with increased fidelity to CRA, number‑sense routines, and intervention tracking (Zearn, Exemplars, VKRP/MAP). |  |  | Sustain or further improve outcomes beyond Year 2 with consistent written–taught–tested alignment and representation‑based problem solving across all grades. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Systematic instruction (intervention/Tier 1) to build conceptual understanding through sequenced, supported lessons and timely feedback. Representations (CRA): provide and connect concrete/semi‑concrete to abstract representations; revisit models to deepen understanding. Rationale: Students struggle to apply concepts in multi‑step contexts; structured, sequenced instruction with accurate visual models, explicit math language, and routine problem‑solving instruction, monitored through regular checks, addresses these gaps and improves access to grade‑level content. Systematic instruction combined with accurate, routine use of visual representations addresses these needs and supports mastery of grade‑level mathematics. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Increased student use and accuracy of models (base‑ten, number lines, arrays, fraction tiles, etc.) to solve problems. Improved unit/benchmark performance and MAP growth across grades. Stronger alignment across written, taught, and tested curriculum; coherent intervention systems and documentation. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Steve Sizemore) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | ILT Members; Instructional Coaches; District Specialists/Coordinators; Grade‑level Teams; CSSP Members; Lead Teachers/Mentors |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Develop and Monitor Lesson Plan Template and Collaborative Structures | Principal; ILT Members; District Specialists/Coordinators | August 2025 – June 2026 |  | Lesson plan reviews; written–taught–tested checks |  | Evidence of SOL/cognitive alignment and planned CRA use | None |  | N/A |
| Data Meetings for Grouping/Intervention (VKRP, MAP, SOL, Exemplars) | Principal; Instructional Coaches; ILT; CSSP Members; District | October 2025 – June 2026 |  | Bi‑weekly/Monthly progress reviews; regrouping logs |  | Increased unit mastery/MAP growth; targeted intervention impact | None |  | N/A |
| Observation/Feedback Cycles Using Grows/Glows | Principal; ILT Members; Lead Teachers/Mentors (non‑evaluative) | October 2025 – June 2026 |  | Walkthroughs/observations; feedback cycles |  | Increased fidelity to CRA routines and math language | None |  | SIG |
| Targeted Professional Learning (Math Small Group, Zearn, Exemplars, HCPS/RCPS Framework) | Principal; ILT Members; Instructional Coaches; Grade‑level Teams | October 2025 – June 2026 |  | PLC agendas/minutes; task analyses; model selection/accuracy checks |  | Documented adjustments to Tier 1/small groups; improved interim results | None |  | N/A |

Assurances

## Assurance of Review and Approval

School Year: 2025-2026

Division Name: Roanoke City Public Schools

Division-Level Team Lead Name: Archie Freeman III

Division-Level Team Lead Email: afreeman@rcps.info

School Name: Round Hill Elementary School

Principal Name: Steven Sizemore

Principal Email: stevensizemore@rcps.info

School Performance Category: Choose an item.Off Track

School Federal Designation: Choose an item.Targeted Support and Improvement

For Comprehensive Support and Improvement Schools, the Multi-year School Support Plan must be written by the school division for the school and include four evidence-based Interventions. The proposed plan must be approved by the principal and division, reviewed by the local school board, and submitted to the Virginia Department of Education (the Department) by the Division Superintendent for final approval. The Virginia Department of Education will review the plan and may request revisions before approving the plan. The Department-approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(C)(1)) (ESEA Section 1111(d)(1)(B)(v)).

For Targeted Support and Improvement and Additional Targeted Support and Improvement schools, the Multi-year School Support Plan must be written by the school and include two evidence-based Interventions. The proposed plan must be approved by school division and the local school board. The approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(B)) (ESEA Section 1111(d)(2)(B)(iii)).

By signing below, I certify that I have thoroughly reviewed the Multi-year School Support Plan for the federally identified school named in this document. I affirm that the plan:

- Aligns with federal and state requirements for school improvement;

- Addresses the needs identified through a school needs assessment;

- Includes the minimum number of required evidence-based interventions;

- Reflects stakeholder input and collaboration; and

- Establishes clear goals, timelines, and progress monitoring processes.

I approve the contents of this plan and commit to supporting its implementation with fidelity to ensure improved outcomes for all students.

| Principal Name |  | Principal Signature |  | Date Approved |
| --- | --- | --- | --- | --- |
| Division-Level Lead Name |  | Division-Level Lead Signature |  | Date Approved |
| Division Superintendent Name |  | Division Superintendent Signature |  | Date Approved |
|  |  |  |  | Date Reviewed/Approved per School Board Minutes |