### Division and School Information

#### Table 2: Division and School Information

| Information Needed | Enter Information Below |
| --- | --- |
| School Year | 2025-2026 |
| Division Name | Roanoke City Public Schools |
| Division Superintendent | Verletta White |
| School Name | Morningside Elementary |
| Grades Served | PK-5 |
| Principal Name | Stephanie Davis |
| Principal Email | stephaniedavis@rcps.info |
| Division Multi-year School Support Plan Lead Name and Title | Kevin G. Bowman, Supervisor of School Improvement |
| Division Multi-year School Support Plan Lead Email | kevinbowman@rcps.info |

### Stakeholder Engagement

Developing the plan with stakeholders is required and includes teachers, school leaders, community partners, parents, students, and representatives from business, higher education, or the military. Actively involving stakeholders supports purposeful planning, builds shared ownership, and helps translate the plan from intent to action, leading to improved student outcomes.

#### Table 3: Stakeholder engagement

Identify the stakeholder group represented, name, email department/office/organization, and title for each stakeholder. Add or remove rows as necessary.

| Stakeholder Representation | Name | Email | Organization, Department, or Office | Title |
| --- | --- | --- | --- | --- |
| School Leader | Stephanie Davis | stephaniedavis@rcps.info | Morningside Elementary | Principal |
| School Leader | Eric Weber | Eweber@rcps.info | Morningside Elementary | Assistant Principal |
| Instructional Leader | Sierra Morris | Smmorris@rcps.info | Morningside Elementary | Instructional Coach |
| Instructional Leader | Danielle Coxon | Dcoxon@rcps.info | Morningside Elementary | Reading Specialist |
| Teacher | Beth Gordon | Bgordon@rcps.info | Morningside Elementary | 3rd Grade Teacher |
| Teacher | Miranda Lewis | mirandalewis@rcps.info | Morningside Elementary | EL Teacher |

Multi-year School Support Plan

| Multi-year School Support Plan Reading |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Increase overall reading performance for grades 3–5 through explicit, systematic literacy instruction using high-quality instructional materials and coherent intervention systems, resulting in sustained growth and proficiency gains across student groups and reductions in Below Basic performance. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Reading Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | Increase the percentage of students in grades 3–5 meeting projected growth on MAP Reading by at least 5%. Improve Reading Benchmark averages across grades 3–5 to 60% or higher. Ensure 100% of teachers implement division-approved literacy materials and evidence-based routines, as evidenced by walkthroughs, observations, and lesson plan reviews. Decrease K–3 early-literacy risk through systematic phonics and fluency routines during intervention blocks. |  | Increase the percentage of students in grades 3–5 meeting projected growth on MAP Reading by an additional 5%. Improve Reading Benchmark averages across grades 3–5 to 65% or higher. Reduce Below Basic performance in reading through stronger Tier 1 alignment and targeted small-group intervention. |  |  | Achieve an overall 15% increase in MAP Reading projected growth (grades 3–5) from baseline. Raise Reading Benchmark averages to 70% or higher. Demonstrate consistent schoolwide fidelity to explicit early-literacy instruction (K–3) and comprehension-building routines (3–5). |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Foundational skills (K–3): Explicit, systematic instruction in phonemic awareness, phonics/decoding, and word recognition. Intermediate grades (3–5): Comprehension-building practices that include world and word knowledge, structured questioning, gist statements, and self-monitoring of comprehension. Rationale: Student data indicate gaps in phonics, vocabulary, background knowledge, fluency, and comprehension. A unified approach that couples explicit foundational skills (K–3) with daily comprehension routines (3–5), aligned to Tier 1 and intervention, directly addresses these needs and supports growth for students with disabilities and other struggling learners. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Improved K–3 decoding, word recognition, and fluency. Increased comprehension, vocabulary, and stamina in grades 3–5. Stronger alignment between Tier 1, intervention, and assessment data. Increased MAP Reading growth and improved Reading Benchmark performance. Reduced gaps for students with disabilities. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Stephanie Davis) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal, Instructional Coach, Reading Specialist, Classroom Teachers, Special Education Teachers, EL Teacher(s) |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Align Tier 1 Lesson Planning and Instruction | Instructional Coach | August 2025 – June 2026 |  | Monthly PLC agendas/notes, lesson plan reviews, walkthrough/observation feedback |  | Lesson plans demonstrate SOL/Curriculum Framework alignment; observations show explicit instruction and engagement | None |  | N/A |
| Strengthen Intervention Planning and Delivery | Literacy Coaches | August 2025 – June 2026 |  | Bi-weekly progress monitoring using Lexia, MAP, and unit assessments |  | Decrease in K–3 high-risk early literacy; increased MAP Reading growth; improved Benchmark results | Existing personnel/materials |  | N/A |
| Facilitate Data-Driven PLCs | Principal and Instructional Coach | August 2025 – June 2026 |  | PLC agendas/notes; quarterly data reviews; regrouping logs |  | Documented instructional adjustments and student regrouping; rising interim results | Minimal (printing, coverage as needed) |  | Local |
| Provide Feedback Cycles for Explicit Literacy Practices | Administration | September 2025 – May 2026 |  | Observation schedules, coaching notes, follow-up look-fors |  | ncreased fidelity to foundational skills routines (K–3) and comprehension practices (3–5) | None |  | N/A |

| Multi-year School Support Plan Math |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Increase overall math performance for grades 3–5 by implementing explicit, systematic instruction that incorporates visual representations and targeted small-group intervention, resulting in sustained gains in growth and proficiency across all student groups, with focused improvement for students with disabilities. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Math Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | Increase overall math achievement in grades 3–5 by at least 20%, increase Students with Disabilities by 15%. Implement systematic small-group intervention for students below benchmark, with bi-weekly progress monitoring and documented regrouping. Ensure 100% of teachers implement division-approved math materials and planned use of visual representations, as evidenced by walkthroughs and lesson plan reviews. |  | Increase overall math achievement in grades 3–5 by an additional 5–7% and continue targeted gains for Students with Disabilities. Improve grade-level benchmark averages to at least 65% across grades 3–5. Demonstrate consistent use of representation-based problem solving in Tier 1 and intervention in 100% of observed classrooms. |  |  | Achieve a cumulative three-year increase in overall math achievement of at least 30% from baseline for grades 3–5, with cumulative gains of at least 20% for Students with Disabilities. Increase Math Benchmark averages to 70% or higher across grades 3–5. Demonstrate sustained schoolwide fidelity to systematic math instruction, including visual representations and explicit problem-solving routines. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Provide systematic instruction during intervention to build conceptual understanding and fluency, explicitly teaching mathematical language and problem-solving steps. Use a well-chosen set of visual representations (e.g., number lines, models, arrays, bar diagrams) to support learning of concepts and procedures and to strengthen multi-step problem solving. Rationale: Student data indicate persistent difficulty with multi-step problem solving and with using and interpreting visual models. Systematic instruction paired with explicit, accurate use of representations addresses these gaps, improves access to grade-level content, and supports growth for students with disabilities and other struggling learners. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Improved student selection, interpretation, and creation of visual representations to solve problems. Increased accuracy and explanation of reasoning in multi-step problem solving. Stronger alignment among written, taught, and tested curriculum and coherent Tier 1 and intervention practices. Increased benchmark performance and measurable gains on interim and growth measures. Reduced achievement gaps for students with disabilities. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Stephanie Davis) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal, Instructional Coach, Division Math Specialist, Classroom Teachers, Special Education Teachers, EL Teacher(s), Math Resource Teacher |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Conduct Walkthroughs and Provide Targeted Feedback | Principal, Assistant Principal, Instructional Coach, Division Math Specialist | August 2025 – June 2026 |  | Bi-monthly walkthroughs with a math fidelity look-for tool; feedback cycles with follow-up observations |  | Walkthrough data show increased accuracy and frequency of modeling, guided practice, independent application, and representation use | None |  | N/A |
| Implement Systematic Small-Group Instruction for Students Below Benchmark | Principal, Assistant Principal, Instructional Coach, Division Math Specialist, Classroom | August 2025 – June 2026 |  | Bi-weekly skill checks; quarterly benchmark reviews; student intervention trackers |  | Increased MAP growth percentiles and unit mastery for students receiving intervention; documented regrouping and acceleration | None |  | Local |
| Implement and Monitor Interventions with Dedicated Staff Collaboration | Principal, Assistant Principal, Instructional Coach, Math Resource Teacher, Division Math Specialist, Classroom Teachers, Special Education Teachers | August 2025 – June 2026 |  | Monthly review of intervention plans and progress logs in PLCs |  | Intervention logs show clear targets, strategies, and progress; increasing rates of students exiting intervention | None |  | SIG |
| Use the Reversed Release Model to Build Mathematical Thinking | Principal, Assistant Principal, Instructional Coach, Division Math Specialist, Classroom Teachers, Special Education Teachers | August 2025 – June 2026 |  | Walkthrough look-fors on modeling - guided - independent phases; student work samples audited monthly |  | Increased student independence and accuracy on multi-step problems; improved discourse and explanation of reasoning | Assessment tools |  | N/A |
| Provide Targeted Professional Development | Principal, Assistant Principal, Instructional Coach, Division Specialists, New Teacher Mentors | August 2025 – June 2026 |  | PD attendance logs; coaching cycles; look-fors aligned to PD topics |  | Observations reflect strategies from PD; improved task implementation quality; increased student talk and reasoning | Professional development |  | SIG |
| Ensure Consistent Use of Visual Representations in Tier 1 and Intervention | Principal, Assistant Principal, Instructional Coach, Division Math Specialist, Math Resource Teacher, Classroom Teachers | August 2025 – June 2026 |  | Lesson plan reviews; look-fors on representation choice and accuracy; student artifacts |  | Increased correct use of representations by students during instruction and assessment; improved performance on representation-dependent items | None |  | N/A |
| Data-Driven PLCs for Placement, Grouping, and Adjustment | Principal, Assistant Principal, Instructional Coach, Division Math Specialist, Grade-Level Leads | August 2025 – June 2026 |  | Monthly PLC agendas/notes; student grouping rosters; quarterly data reviews with the division |  | Timely regrouping; increasing benchmark averages; steady MAP growth across student groups | None |  | N/A |

Assurances

## Assurance of Review and Approval

School Year: 2025-2026

Division Name: Roanoke City Public Schools

Division-Level Team Lead Name: Archie Freeman III

Division-Level Team Lead Email: afreeman@rcps.info

School Name: Morningside Elementary

Principal Name: Stephanie Davis

Principal Email: stephaniedavis@rcps.info

School Performance Category: Choose an item. Off Track

School Federal Designation: Choose an item. Targeted Support and Improvement

For Comprehensive Support and Improvement Schools, the Multi-year School Support Plan must be written by the school division for the school and include four evidence-based Interventions. The proposed plan must be approved by the principal and division, reviewed by the local school board, and submitted to the Virginia Department of Education (the Department) by the Division Superintendent for final approval. The Virginia Department of Education will review the plan and may request revisions before approving the plan. The Department-approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(C)(1)) (ESEA Section 1111(d)(1)(B)(v)).

For Targeted Support and Improvement and Additional Targeted Support and Improvement schools, the Multi-year School Support Plan must be written by the school and include two evidence-based Interventions. The proposed plan must be approved by school division and the local school board. The approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(B)) (ESEA Section 1111(d)(2)(B)(iii)).

By signing below, I certify that I have thoroughly reviewed the Multi-year School Support Plan for the federally identified school named in this document. I affirm that the plan:

- Aligns with federal and state requirements for school improvement;

- Addresses the needs identified through a school needs assessment;

- Includes the minimum number of required evidence-based interventions;

- Reflects stakeholder input and collaboration; and

- Establishes clear goals, timelines, and progress monitoring processes.

I approve the contents of this plan and commit to supporting its implementation with fidelity to ensure improved outcomes for all students.

| Principal Name |  | Principal Signature |  | Date Approved |
| --- | --- | --- | --- | --- |
| Division-Level Lead Name |  | Division-Level Lead Signature |  | Date Approved |
| Division Superintendent Name |  | Division Superintendent Signature |  | Date Approved |
|  |  |  |  | Date Reviewed/Approved per School Board Minutes |