### Division and School Information

#### Table 2: Division and School Information

| Information Needed | Enter Information Below |
| --- | --- |
| School Year | 2025-2026 |
| Division Name | Roanoke City Public Schools |
| Division Superintendent | Verletta White |
| School Name | Monterey Elementary |
| Grades Served | PK-5 |
| Principal Name | Lezlie Yaeger |
| Principal Email | lyaeger@rcps.info |
| Division Multi-year School Support Plan Lead Name and Title | Kevin G. Bowman, Supervisor of School Improvement |
| Division Multi-year School Support Plan Lead Email | kevinbowman@rcps.info |

### Stakeholder Engagement

Developing the plan with stakeholders is required and includes teachers, school leaders, community partners, parents, students, and representatives from business, higher education, or the military. Actively involving stakeholders supports purposeful planning, builds shared ownership, and helps translate the plan from intent to action, leading to improved student outcomes.

#### Table 3: Stakeholder engagement

Identify the stakeholder group represented, name, email department/office/organization, and title for each stakeholder. Add or remove rows as necessary.

| Stakeholder Representation | Name | Email | Organization, Department, or Office | Title |
| --- | --- | --- | --- | --- |
| School Leader | Lezlie Yaeger | lyaeger@rcps.info | Monterey Elementary | Principal |
| Instructional Leader | Amanda Fulton | afulton@rcps.info | Monterey Elementary | Instructional Coach |
| Instructional Leader | Kelly Surprenant | Ksurprenant@rcps.info | Monterey Elementary | Literacy Coach |
| Instructional Leader | Abigail Snay | asnay@rcps.info | Monterey Elementary | Literacy Coach |
| Instructional Leader | Amy Ralph | aralph@rcps.info | Monterey Elementary | Literacy Coach |
| Classroom Teacher | Jennifer Ayles | JAyles@rcps.info | Monterey Elementary | 3rd Grade Teacher |

Multi-year School Support Plan

| Multi-year School Support Plan Reading |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Over the next three years, Monterey Elementary will increase the percentage of students making adequate reading growth from 67% to 80% and decrease the percentage of students performing in the Below Basic range on the Reading SOL by improving Tier 1 instruction, strengthening intervention alignment, and implementing evidence‑based literacy practices schoolwide. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Reading Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | Increase adequate reading growth from 67% to at least 72%. Reduce the percentage of students in the Below Basic category in reading. Decrease the percentage of K–3 students identified as “high risk” on VALLSS. Increase MAP Reading growth for grades 3–5. Ensure 100% of teachers implement division-approved literacy materials with fidelity. |  | Increase adequate reading growth to at least 76%. Reduce Below Basic reading performance by an additional margin. Increase the percentage of students meeting MAP Reading projected growth by an additional 5%. Improve Reading Benchmark averages to 65% or higher.. |  |  | Increase adequate reading growth to 80%, meeting the 3-year target. Reduce Below Basic reading performance by 50% from baseline. Increase Reading Benchmark averages for grades 3–5 to 70% or higher. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | K–3: Teach students to decode words, analyze word parts, and develop phonemic awareness through explicit, systematic instruction. Grades 4–5: Provide comprehension‑building practices including vocabulary development, questioning routines, summarizing, and monitoring comprehension. Rationale: Data show persistent weaknesses in foundational reading skills, comprehension, and alignment between Tier 1 and intervention instruction. These strategies emphasize explicit, systematic practices aligned to the needs of students with disabilities and other struggling learners. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Improved phonics, decoding, and foundational literacy skills in early grades. Increased comprehension and reading stamina in grades 3–5. Reduction in the number of K–3 students identified as “high risk.” Increased MAP Reading growth for grades 3–5. Improved alignment between Tier 1 instruction, intervention, and assessment data. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Lezlie Yaeger) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal, Instructional Coach, Literacy Coaches, Special Education Teachers, Classroom Teachers, EL Teachers, Reading Specialist |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Ensure Tier 1 Lesson Plan Alignment and Instructional Consistency | Instructional Coach | September 2025 – May 2026 |  | Monthly PLC agendas, walkthrough notes, division learning walks |  | Lesson plans demonstrate alignment to SOLs; observations show explicit instruction, engagement, and use of evidence-based practices | None |  | N/A |
| Strengthen Intervention Planning and Delivery | Literacy Coaches | September 2025 – May 2026 |  | Bi-weekly progress monitoring using VALLSS, MAP, and classroom data |  | Decreased early literacy “high‑risk” students; increased MAP Reading growth; improved SPSF Reading Growth outcomes | Reading Specialist salary, instructional materials |  | Title I |
| Facilitate Monthly Data Meetings to Adjust Instruction | Principal and Instructional Coach | September 2025 – May 2026 |  | PLC agendas and notes; benchmark data reviews |  | Documented regrouping of students; targeted instructional adjustments | Minimal (printing, coverage as needed) |  | Local |
| Implement Feedback Cycles for Explicit Literacy Instruction | Administration | September 2025 – May 2026 |  | Observation schedules; feedback logs |  | Increased fidelity to evidence-based practices; improved walkthrough ratings | None |  | N/A |

| Multi-year School Support Plan Math |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3-Year Goal Statement Include the goal statement completed as part of the needs assessment process. |  |  | Over the next three years, Monterey Elementary will increase the percentage of students in grades 3–5 who demonstrate adequate math growth on the School Performance and Support Framework from 65% to 80% and increase the percentage of students scoring Proficient or Advanced on the Math SOL from 62% to 75%. |  |  |  |  |  |  |
| School Performance and Support Framework Alignment Select indicator that the goal addresses. |  |  | Math Growth |  |  |  |  |  |  |
| Measurable Objectives Define objectives that support accomplishing the goal. |  |  | Measurable Objective Year 1 |  | Measurable Objective Year 2 |  |  | Measurable Objective Year 3 |  |
|  |  |  | Increase the percentage of students meeting adequate math growth from 65% to at least 70%. Increase the percentage of students scoring Proficient/Advanced on the Math SOL from 62% to at least 65%. Ensure 100% of K–5 teachers implement division-approved math materials and follow explicit, systematic instructional routines as evidenced by walkthroughs and lesson plan reviews. |  | Increase adequate math growth to at least 75%. Increase Proficient/Advanced Math SOL performance to at least 70%. Reduce gaps in Math SPSF Growth for students with disabilities through consistent differentiation and intervention aligned to student data. |  |  | Increase adequate math growth to 80%, meeting the 3-year goal. Increase Proficient/Advanced performance to 75%, meeting the 3-year mastery goal. Demonstrate consistent implementation of systematic math instruction, targeted small‑group intervention, and use of visual representations across all K–5 classrooms. |  |
| Evidence-Based Strategy Describe the evidence-based strategy and the rationale for selection. Identify evidence tier. |  |  | Provide intentional and systematic instruction to build conceptual understanding of mathematical ideas and skills, including the use of small‑group instruction and sequenced skill development. Implement visual representations (such as number lines, models, diagrams, arrays, and other concrete‑to‑representational‑to‑abstract strategies) to support problem solving and comprehension of mathematical concepts. Data show that students struggle with foundational number sense, computation, and problem solving, particularly when visual models are required. Systematic instruction and explicit use of representations directly address these gaps and support stronger math reasoning for all learners, including students with disabilities. |  |  |  |  |  |  |
| Intended Outcomes Describe how student outcomes will improve as a result implementing the evidence-based strategy. |  |  | Improved student ability to use visual models to support problem solving. Increased accuracy and understanding of multi-step mathematical problems. Improved alignment across written, taught, and tested curriculum. Increased MAP Growth scores and SOL proficiency. Reduced performance gaps for students with disabilities. |  |  |  |  |  |  |
| Lead person (Who is responsible for ensuring the work gets done?) |  |  | Principal (Lezlie Yaeger) |  |  |  |  |  |  |
| Team Members (Who are responsible for doing the work?) |  |  | Assistant Principal, Instructional Coach, Division Math Specialist, Math Teachers, Special Education Teachers, Tutors |  |  |  |  |  |  |
| Action Step (What will be accomplished?) List the specific, sequenced steps required to complete the activity. | Process Owner (Who is responsible for ensuring the action step is complete?) Identify a single, accountability lead. | Time Frame (How long will it take?) Identify the start and end dates for each action step, including any key milestones. |  | Progress Checks (How will the team monitor progress?) Define key dates to review process, make adjustments, and confirm the work remains on track. |  | Measures of Success (How will the team know if the action step is complete?) Define clear, observable indicators of completion. | Cost Elements (What resources are needed to complete the action step?) |  | Funding Source (Where will the money come from?) |
| Strengthen Tier 1 Lesson Planning and Alignment | Instructional Coach | September 2025 – May 2026 |  | Monthly PLC notes; division learning walk feedback; lesson plan reviews |  | Lesson plans show alignment and sequencing; walkthroughs reflect explicit modeling and use of visual representations | None |  | N/A |
| Implement Systematic Small‑Group Math Instruction | Grade-Level Leads | September 2025 – May 2026 |  | Bi-weekly skill checks; quarterly benchmark reviews |  | Increased MAP growth percentiles; improved benchmark and unit assessment performance | None |  | Local |
| Strengthen Supports for Students with Disabilities in Math | Special Education Lead | September 2025 – April 2026 |  | Monthly lesson plan and co-teaching schedule review |  | Lesson plans show aligned scaffolds, use of representations, and IEP-driven supports | Professional development |  | SIG |
| Implement Ongoing Progress Monitoring and Instructional Adjustment | Administrators | September 2025 – May 2026 |  | MAP growth reports; benchmark data; weekly formative checks |  | Growth and improvement toward annual MAP growth and SOL proficiency targets | Assessment tools ( |  | N/A |

Assurances

## Assurance of Review and Approval

School Year: 2025-2026

Division Name: Roanoke City Public Schools

Division-Level Team Lead Name: Archie Freeman III

Division-Level Team Lead Email: afreeman@rcps.info

School Name: Monterey Elementary

Principal Name: Lezlie Yaeger

Principal Email: lyaeger@rcps.info

School Performance Category: Choose an item.Off Track

School Federal Designation: Choose an item.Targeted Support and Improvement

For Comprehensive Support and Improvement Schools, the Multi-year School Support Plan must be written by the school division for the school and include four evidence-based Interventions. The proposed plan must be approved by the principal and division, reviewed by the local school board, and submitted to the Virginia Department of Education (the Department) by the Division Superintendent for final approval. The Virginia Department of Education will review the plan and may request revisions before approving the plan. The Department-approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(C)(1)) (ESEA Section 1111(d)(1)(B)(v)).

For Targeted Support and Improvement and Additional Targeted Support and Improvement schools, the Multi-year School Support Plan must be written by the school and include two evidence-based Interventions. The proposed plan must be approved by school division and the local school board. The approved plan must be published on the division website and the school website. The Multi-year School Support Plan will be incorporated as a component of the school's comprehensive, unified, long-range plan. (8VAC20-132-280(B)) (ESEA Section 1111(d)(2)(B)(iii)).

By signing below, I certify that I have thoroughly reviewed the Multi-year School Support Plan for the federally identified school named in this document. I affirm that the plan:

- Aligns with federal and state requirements for school improvement;

- Addresses the needs identified through a school needs assessment;

- Includes the minimum number of required evidence-based interventions;

- Reflects stakeholder input and collaboration; and

- Establishes clear goals, timelines, and progress monitoring processes.

I approve the contents of this plan and commit to supporting its implementation with fidelity to ensure improved outcomes for all students.

| Principal Name |  | Principal Signature |  | Date Approved |
| --- | --- | --- | --- | --- |
| Division-Level Lead Name |  | Division-Level Lead Signature |  | Date Approved |
| Division Superintendent Name |  | Division Superintendent Signature |  | Date Approved |
|  |  |  |  | Date Reviewed/Approved per School Board Minutes |